## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Approved Design Report |  | Approved Design Report | f9b0314d-fdc5-41e5-b6b7-8d9a75197b47
| checkpoint | Approved Design Report
| checklist | Approved JMF |  | Approved JMF | 023c1fe1-faec-4f3f-bcc8-cb8bff955a47
| checkpoint | Approved JMF
| checklist | ITP - AC Resurfacing | itp | ITP - AC Resurfacing | 5f9d2097-5af6-4481-8af9-571ddda356fb
| section | 1.0 Pre-Work
| checkpoint | Approved JMF for Strengthening Repairs Mix (if required)
23d213c0-aedf-544f-ba36-8b76a8de3de5 | note | H
d3b52225-64ce-5bcd-afba-a052bf19f818 | note | Reference or Specification - Design Report
48efa284-8c40-5042-979f-e0900b8e80f3 | note | Method/Test Required - Confirm approved JMF dates in Design Report
fa0c5a55-6e5e-5e39-ad8b-edd22b6d12a4 | note | How Often? Each site
afef1409-31b8-50af-9a2e-831ab7bf131f | note | Records Required - Copy of Approved Design Report
a5488746-dafc-5f90-9964-83ef8216ae44 | note | Responsibility - Project Manager(AC)
| checkpoint | Approved JMF for Pre-Level Mix (if required)
edbe4eef-7983-5008-9928-86e95c4154f3 | note | H
16fafdea-3ae4-530d-b5dd-2d0e0cc7df51 | note | Reference or Specification - Design Report
ec18babf-2a89-5605-a001-f9c541f0fc4d | note | Method/Test Required - Confirm approved JMF dates in Design Report
135b3aea-55e6-5a29-b778-ddde58a3cd45 | note | How Often? Each site
40433539-5150-53ac-b95f-712ec950f683 | note | Records Required - Copy of Approved Design Report
9f299068-33cb-5227-8eaa-059b07727397 | note | Responsibility - Project Manager(AC)
| checkpoint | Approved JMF for Wearing Course Mix
fdcc2b4a-b953-5d2f-94f3-b80d3f518194 | note | H
6bcddac3-e9ab-5ade-bd3e-db8b84108a3d | note | Reference or Specification - Design Report
6fab8bc6-adef-5994-958a-cd0e93163d57 | note | Method/Test Required - Confirm approved JMF dates in Design Report
3867d601-9447-56db-a213-c2a9667cb4bb | note | How Often? Each site
48fbf5ff-278c-59f9-87ce-b0869a113757 | note | Records Required - Copy of Approved Design Report
153fa346-ad79-5502-97eb-a499df59581d | note | Responsibility - Project Manager(AC)
| checkpoint | Approved Design Report
a0c0fff8-ef6d-5af4-8684-cf510d75a2bc | note | H
a2dc34c3-9378-5f70-8164-1a5047fd0ead | note | Reference or Specification - Design Report
bc17a6b2-3a0b-5c43-9a40-1a3f759b05b2 | note | Method/Test Required - Confirm document on-site
c034bb6f-6eb1-5bc6-90bd-e6d88347c298 | note | How Often? Each site
992aa2ac-b825-5871-af5d-69db4a7f1c8b | note | Records Required - Copy of Approved Design Report
1efcc3c9-5653-5cd0-a33c-5d6b0d322d77 | note | Responsibility - Renewals Manager
| checkpoint | Treatment of affected Service Covers (to be raised or protected)
73207b1b-3b19-56d9-ac86-c3b6a057fac9 | note | H
a07e0a6c-ba79-55c9-9307-2b1913550a7c | note | Reference or Specification - Job sheet
57fe00a9-148d-580c-84b0-c88055b5eecf | note | Method/Test Required - Confirm plan in place
d65c05bf-d77c-5623-a3cc-a5a8fd97a52a | note | How Often? Each site
7945b1ca-d0c3-5073-b7ac-5bfe8a5af1de | note | Records Required - Job Sheet record
0962de76-c0b3-560f-af61-4c1ce4c91d76 | note | Responsibility - Project Manager(AC)
| checkpoint | Stakeholder Management Requirements met
6869005d-7655-5636-b133-aca3df03ef37 | note | H
e6a04e76-6ac5-58d5-8c51-5fa8710fff24 | note | Reference or Specification - CSCMP
67231635-28e1-598a-aecc-2460e1a734cf | note | Method/Test Required - Confirm requirements followed
8cb0bbd4-c8a6-538b-a9cf-158f14efdd4a | note | How Often? Each site
077a6b1e-2c5e-59c1-af62-09abaa7c6e95 | note | Records Required - Copy of stakeholder notification / Photographs of VMS Boards
fa47cef2-8fd2-5a00-b5ad-7550be0a58bc | note | Responsibility - Renewals Manager
| checkpoint | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work
ec802785-dcab-5808-be8b-aa5ae49200a2 | note | H
b03691a7-2fb3-511f-b93a-bc2a2f530973 | note | Reference or Specification - QMP
822ad070-c145-53ab-8514-bc49ac92fd34 | note | Method/Test Required - Brief all team members on day’s work plan
f0b75cda-643e-5a1c-b6d6-317172f3c06d | note | How Often? Each site
ec9ca2d7-ae09-55a7-950e-839d2e413243 | note | Records Required - Daily diary
829f3aa4-ecee-5869-900d-e57376337191 | note | Responsibility - Project Manager(AC)
| checkpoint | Confirm if any environmental protection is required
73be47c3-5430-5770-8fc0-514315daf00a | note | H
b3011aa0-7ee6-53c5-aff0-fc27dc80e0ac | note | Reference or Specification - ESMP
acb3257b-afc2-5861-8186-fff42fffcce1 | note | Method/Test Required - Record decision
914f701c-fad9-5e87-946f-92cc91422dab | note | How Often? Each site
6e78781e-94b8-5d03-9cd6-93cb63f4030e | note | Records Required - Job Sheet record
c267607a-893c-5017-a4b3-90533d865c1e | note | Responsibility - Project Manager AC/Site Supervisor
| section | 2.0 Site set up
| checkpoint | Ambient Conditions; Pavement Surface Temp ≥ 5ºC (Intermediate or structural layers) and ≥ 10ºC (wearing course) and forecast to rise
e82cc7d1-ac11-571d-b29a-cb57fa676def | note | H
11457fef-b088-5f40-adbc-a8eb1914a109 | note | Reference or Specification - NZTA M10: 2020 9.5.2
74db3ca5-34aa-56ef-8ebb-1df540b6021b | note | Method/Test Required - Temperature Gun Check, Acceptable / Unacceptable
abd2d648-1c09-5494-9d7f-beb4b49c4ffa | note | How Often? Each site
5af51569-dfff-55b6-8a3d-4edb10d46cd7 | note | Records Required - Job Sheet record
d71f2efc-777b-56c9-afa6-b6ab11f007ce | note | Responsibility - Site Supervisor
| checkpoint | Job start, identify risks and controls, communicated to team
b3d54b88-fed7-541e-ad96-765d99e677e8 | note | H
046d7ecc-96ee-5ed1-bf47-668d805e1a85 | note | Reference or Specification - HSMP
7f726c41-6612-5dc4-872e-03ab4d5acc60 | note | Method/Test Required - Record all risks and controls on Hazard ID following Team discussion
ed20bc00-6ab8-56af-9efa-3ebdc1d497f1 | note | How Often? Each site
f62626fa-c1b7-5def-9e0c-fc15e3e1f87a | note | Records Required - Hazard ID form
a034f4aa-b652-5f2f-bae2-a911ea3b6db1 | note | Responsibility - Site Supervisor
| checkpoint | Establish traffic management to plan
3968e39f-6d24-59cd-994b-b8ba117d09fc | note | H
19120aaf-f1d0-50bb-89c7-173bd41dab78 | note | Reference or Specification - TMP
2923b2c6-746c-5862-bd17-c6a5a175d991 | note | Method/Test Required - Site audit post set up
519e9ba9-9da0-55c7-be9a-58618644c08b | note | How Often? Each site
44109c33-b5fc-5ea5-90fb-34f4d336ad5c | note | Records Required - TTM diary
ee9cdbaa-7381-5f8b-8624-d1fee69492e3 | note | Responsibility - STMS
| checkpoint | Confirm site extents by checking what’s marked on the road matches the job sheet / Design Report
deca7328-c7c6-5306-84ee-3f2967bfbcba | note | H
b88f6885-9acd-568e-a723-86ffb918bbf6 | note | Reference or Specification - Design Report
f254b0e3-3b09-50da-bbf9-9256b5532dcb | note | Method/Test Required - Record as-built site dimensions
214ee2ea-0989-5352-981d-a0e70f3db61d | note | How Often? Each site
96c3cf53-1327-587c-a8da-5a5b826c71c0 | note | Records Required - Job Sheet record
6c38d12a-26e4-5e2c-b102-a16fddbc73bd | note | Responsibility - Site Supervisor
| checkpoint | Identification of Services; Service Plans on-site; Shallow Services marked
242b7b88-757a-5d0a-a307-a83dcbabd613 | note | H
e1cde310-7f6c-5586-80a9-b6d457f14fa1 | note | Reference or Specification - SOP
2c5ef002-e4aa-5e55-91e8-d77220cbf5e8 | note | Method/Test Required - Confirm document on-site / Visual check
94765fbe-8fd6-594a-a5bc-a93a98be01fa | note | How Often? Each site
7fe62f99-95d7-5913-97ab-1c05c4238225 | note | Records Required - Job Sheet record
f6292cd6-153a-5a02-9e60-8ab67c35b0fa | note | Responsibility - Site Supervisor
| checkpoint | Service Covers treated as planned
a1137188-62bb-5216-8065-45f2ebfe59e0 | note | H
b8438c78-df77-5014-868a-e563d8cb4ee9 | note | Reference or Specification - Job sheet
d99deed5-abbe-5acd-9a34-6a43a4a7a0d5 | note | Method/Test Required - Visual check
4d097c0e-ad56-5398-ac3b-af06a5cd9ef7 | note | How Often? Each site
0874d8de-e99d-5a2a-903b-715ee668c099 | note | Records Required - Job Sheet record
75647c37-14e6-52f9-8c1b-af68e3ce6e6a | note | Responsibility - Site Supervisor
| checkpoint | Record & photograph environmental protection measures installed
5e0f4a5e-2a37-5798-a988-c40d32baaf12 | note | I
e9058490-3ca8-52ab-a1ea-1b93a65d022c | note | Reference or Specification - ESMP
b982ec97-a9c0-5f7d-bcf7-490985c18e9b | note | Method/Test Required - Record temporary measures
6af90ec5-ea72-55c5-a33b-71c87f978081 | note | How Often? Each site
880aa4a7-7544-5d4c-bf49-c0c285002593 | note | Records Required - Job Sheet record & photograph
a172c759-9068-5105-8e26-cd2bba3140fa | note | Responsibility - Site Supervisor / Site QA
| section | 3.0 Milling (If Required)
| checkpoint | Milling undertaken to correct depth; ±5mm nominal thickness
34f3bf61-5d05-5b53-b925-fbc114607800 | note | I
65ac39d8-8edc-595e-bf6d-6d4aa0b68dfc | note | Reference or Specification - Design Report
e0416f74-cdca-5118-b752-0cf38da21f65 | note | Method/Test Required - Dip checks
5e2886a2-8732-52c4-90fb-6df49fba66f2 | note | How Often? Per site
4341e670-e610-5228-bed3-4694f470e7e2 | note | Records Required - Job Sheet record
caf0ea12-b566-5d0a-9b0d-6a20b9d33e45 | note | Responsibility - Site Supervisor / Site QA
| checkpoint | Exposed Basecourse waterproofed / levelled
4a0c370e-41b5-54ce-9fc5-caf7de5adbd1 | note | I
ed82ae74-37be-524b-8e69-8d0a2963937f | note | Reference or Specification - QMP
61dd4efb-e1b3-5765-b5f2-36f3cab698fa | note | Method/Test Required - Acceptable / Unacceptable
d1015ab2-1ff4-5be7-b458-11cfc9854bfc | note | How Often? Per site
ea44e5a2-c446-5b20-94a5-39cc69cb9378 | note | Records Required - Job Sheet record
f76643f9-0277-5fd0-8598-a3295a15d8b2 | note | Responsibility - Site Supervisor
| section | 4.0 Membrane (If Required)
| checkpoint | Application as per Design Requirements (Chip size / binder application rate)
d5de9175-d333-589d-a328-7d8ca28c0627 | note | I
237dd39d-5b8e-54b6-b939-11f268f9dcd2 | note | Reference or Specification - Design Report
ad5bc624-26dc-56c0-b7a6-4d96104dd6c8 | note | Method/Test Required - Spray Sheet/s
54cb3e44-a40f-5f63-8f31-e57267b44138 | note | How Often? Per site
81341f86-2ed2-58da-9ee8-d866ac1ba667 | note | Records Required - Job Sheet record
72318606-0112-5bad-ba3c-0cf4c722fad2 | note | Responsibility - Site Supervisor / Site QA
| section | 5.0 Strengthening Repairs (If Required)
| checkpoint | Delivery temperature; ±30 degrees from recommended mixing temperature
6ef2dbb4-b893-57f2-926c-7c7035adb18b | note | T
67f04e8a-41dd-5bfd-8522-de6b88c834ea | note | Reference or Specification - NZTA M10: 2020 Notes
81cba69e-eb7e-5de0-8925-e81b9ccce3e2 | note | Method/Test Required - Temperature Gun Check, Acceptable / Unacceptable
3c38be0a-9c72-5fdd-aa8d-25faca16ee0d | note | How Often? Per load
6b4ab569-7b15-5cbe-a033-f82af7df4725 | note | Records Required - Job Sheet record
36e87dad-0bad-5eb5-9bb3-d0664ddd725a | note | Responsibility - Site Supervisor
| checkpoint | Structural Asphalt Layer Thickness; Each Layer >55mm
178f9413-cada-5379-a4ca-8ae4cc1000dc | note | T
9eaf6d64-11bb-501a-b314-a8b51eb11d14 | note | Reference or Specification - NZTA M10 2020 10.1 & Table 3.1
8ab85e2e-74a4-5006-9ef9-971cb19e3c20 | note | Method/Test Required - Dip checks during paving process / Cores
86149b3e-9bfd-5d4c-93b6-904765288268 | note | How Often? One test per patch & / or One test per 300m2
4b6239d5-6cfd-5042-974d-1aa6d9b33955 | note | Records Required - Job Sheet record & photograph
b1f1d4c2-f170-59aa-879b-a4dcd3905880 | note | Responsibility - Site Supervisor / Site QA
| checkpoint | ±10mm nominal thickness
e415a6bc-4346-5b12-a0b4-1187aea2c62c | note | T
1c01ea54-4e80-51bb-a1c2-21ee2f4fa1aa | note | Reference or Specification - NZTA M10: 2020 10.1 & Table 3.1
36733ad7-76c5-5deb-896a-c291fae526ad | note | Method/Test Required - Dip checks during paving process / Cores
ffe14860-cfeb-58da-ade2-5ba5ddf6f923 | note | How Often? One test per patch & / or One test per 300m2
9cdc753c-d22b-5511-b585-2b6b956a38b8 | note | Records Required - Job Sheet record & photograph
33c7f5f1-f07e-514c-8e29-135cd41d4018 | note | Responsibility - Site Supervisor / Site QA
| checkpoint | Compaction and Air Voids
dec7b691-b7d2-5826-bca1-a5607968ce74 | note | T
84509e23-8587-5475-8a49-c29fc6a1f918 | note | Reference or Specification - Paving SOP
0d6283ab-6085-5c8b-bbf5-2a5491d03117 | note | Method/Test Required - NDM for Quality Control Only
e9818284-c233-5e7a-a40e-058c79334ca2 | note | How Often? One test per patch & / or One test per 50m2
9891538b-edc5-5dda-bb94-f07c0ab8cbd4 | note | Records Required - Job Sheet record & photograph
74b6356e-ff4b-5c93-8961-1aec1cc55327 | note | Responsibility - Site Supervisor / Site QA
| section | 6.0 Pre-Levelling (If Required)
| checkpoint | Delivery Temperature; +10 / -30 degrees from recommended mixing temperature
86330494-2f60-5c12-9e56-a8277603b209 | note | T
60c4dfc2-ef53-5aec-9e1e-3d04ab4665a6 | note | Reference or Specification - NZTA M10: 2020 Notes
48203a3d-3676-5145-8ec4-0d8e45388fd6 | note | Method/Test Required - Temperature Gun Check, Acceptable / Unacceptable
b6b56d11-e245-5290-a819-52811ea5e736 | note | How Often? Per load
edef504d-8b1e-5ff7-821b-7fa8681801cd | note | Records Required - Job Sheet record
0aedc5e1-9e25-56eb-8da9-88a029fe7a90 | note | Responsibility - Site Supervisor
| checkpoint | -5mm / +5mm below bottom of the nominal thickness of wearing course specified in Design Report
0fea8169-0a2a-5ade-9281-399ea8ff8604 | note | T
f54596b9-e8d9-5bac-bf6e-50a06d3ebea1 | note | Reference or Specification - Design Report
0d7e7fac-b7c2-5b17-a0a8-e372256dc137 | note | Method/Test Required - Dip checks during paving process / Cores
073f1242-27f9-5932-920c-40849063111d | note | How Often? Every 15m
345a0e06-18ea-595b-8578-3ad2040a6e5b | note | Records Required - Stringline Sheet record & photograph
7c4cb311-94ef-52bf-b8d9-6fd283cff5ec | note | Responsibility - Site Supervisor / Site QA
| section | 7.0 Wearing Course
| checkpoint | Delivery temperature; ±30 degrees from recommended mixing temperature
2095c805-27e3-5f6a-af49-2891a53d6315 | note | T
c2d70dce-27ac-565a-bb53-608c296da554 | note | Reference or Specification - NZTA M10: 2020 Notes
5a40564d-6b2a-5fd3-9c17-9ba24482367e | note | Method/Test Required - Temperature Gun Check, Acceptable / Unacceptable
b278280e-8ed7-55b6-b482-1aa69f5ed3b5 | note | How Often? Per load
a5df0598-fef5-500f-b7c0-fd64f6e402a2 | note | Records Required - Job Sheet record
78898378-1fee-5ec5-9882-b06dda1de68d | note | Responsibility - Site Supervisor
| checkpoint | -5mm / +10mm nominal thickness specified in Design Report; If applicable all mix is not more than 5mm above lip of channel unless specified otherwise in the Design Report
7a25ce2c-a587-5c63-a8fd-be806de1c311 | note | T
4e2f6560-5632-5ae5-a8f0-d8064ec72108 | note | Reference or Specification - NZTA M10:2020 10.1 & NZTA M10:2020 Notes Table 3.3 & 3.4 or NZTA M27:2020 10.2 & NZTA M27:2020 Notes Table 3.1
00379173-d8ef-5bcd-8a1e-1208bfe69e26 | note | Method/Test Required - Dip checks during paving process / Stringline Sheet
ec43900a-05ce-5bef-96bd-9a5d9ce72fdd | note | How Often? Every 15m
24ddab7b-ee2a-5494-8dbf-1dd857fc0928 | note | Records Required - Stringline Sheet record & photograph
ac66b598-651d-500b-bc53-f5c21d3eeab5 | note | Responsibility - Site Supervisor / Site QA
| checkpoint | Compaction and Air Voids; Mat density air voids (+3 and -2) and joint density air voids (+5 and -2) as noted on JMF with the offset (1)
db988252-c8fe-5765-9a39-05dc9a7fb71e | note | T
c1dedb22-de03-5b4a-9430-a7aa181c65ec | note | Reference or Specification - NZTA M10: 2020 Table 9.2 + ASTM D3203 or NZTA M27: 2020 Table 9.2
432b69c7-d6a3-5ee2-9e2d-58817abbc0f3 | note | Method/Test Required - 150mm Diameter Cores where:
b3bf7447-60e6-522b-85cb-4eedaa063355 | note | 1. >30tonnes
eff0a7a2-ffbc-57ba-9fcf-9f858d01dfc0 | note | 2. >=35mm lift thickness
d9137498-3944-5e1e-8524-960afbd2e933 | note | 100mm Diameter Cores where:
56a0f457-d96f-5c75-9620-87aca07f289b | note | 1. >30tonnes
f3c286ef-6eea-564f-a90f-fd3f9ab9686d | note | 2. >=35mm and <40mm lift thickness
ce0651d1-2c9f-5b4c-876c-ae633b70f678 | note | NDM (only where accepted by the Engineer in writing along with the testing plan.)
7c486017-0a65-5e3a-92c0-8f62b8724aeb | note | How Often? Mat Cores: Cores to be randomly located using ASTM D5361 in each sublot. 1 core per 300m2 sublot and a min 8 cores each lot
954da4f5-ba01-57b1-a5b0-698b868bcbda | note | ○ Joint Cores: Cores to be randomly located using ASTM D5361 in every 100m of joint.
70a78294-dfbb-57ea-a6f2-bfee5735ec7b | note | ○ NDM (only where accepted by then Engineer as per agreed testing plan.)
41df0421-674d-59d0-83e0-60ef617261d3 | note | Records Required - IANZ Accredited Laboratory
b0c7ffb7-8018-5b5c-8edb-6418161d29af | note | Responsibility - Site Supervisor / Site QA
| checkpoint | Compaction and Air Voids; Mat density air voids (+3 and -2) and joint density air voids (+5 and -2) as noted on JMF with the offset (2)
e0636edd-dfef-5bc7-aabe-250f1271d414 | note | T
1a2e7dce-fec3-5506-87d3-a7a8d3278ba5 | note | Reference or Specification - NZTA M10: 2020 Table 9.2 + ASTM D3203 or NZTA M27: 2020 Table 9.2
8c9f7462-0e76-5af9-a054-1d210bfd4569 | note | Method/Test Required - NDM for Quality Control Only
2eddfec4-90b1-55b4-86bc-365afb61c1ff | note | How Often? Every 20m alternating wheel tracks
46c7f539-c507-5efa-af23-0f2ae9e529a0 | note | Records Required - Job Sheet record
bf202c70-927b-5553-870e-9e34ae4151d7 | note | Responsibility - Site Supervisor / Site QA
| checkpoint | Post construction surface condition
2f8709fd-8cf2-50bf-9d57-7fa4c732dbc5 | note | I
2b10a672-f0a5-571f-8c34-ac5521f63f2c | note | Reference or Specification - Design
02f90c21-a8a5-55d2-a6e6-737a83fd65cd | note | Method/Test Required - Acceptable / Unacceptable
4af93a31-d226-5fe6-8f3b-a1eca4ba1168 | note | How Often? Per site
8b732e90-18f5-50da-91c8-7cfbb032b8b6 | note | Records Required - Job Sheet record
05299416-c26f-51fe-af79-be17331d1031 | note | Responsibility - Site Supervisor
| checkpoint | Supervisor/QA to provide an update regarding site completion per shift
5e44e1a5-2b25-5ff9-9f5c-9c702f478b11 | note | H
53234cf9-593f-59fa-b582-83fe18f13e9e | note | Reference or Specification - Design
63384f2b-4931-5502-90fd-e4e7e701392f | note | Method/Test Required - Acceptable / Unacceptable
d5ba6734-2baa-5fd7-9ca9-35796d1065bd | note | How Often? Per site
154c3143-c859-560d-a0b7-249f1bbc6d15 | note | Records Required - Email
6e726133-a72a-5509-96f8-b56d9e79bec2 | note | Responsibility - Site Supervisor/Site QA
| section | 8.0 Post-Construction
| checkpoint | Linemarking and RRPM Reinstated; Matches previous linemarking - within 48 hours of sealing
61e7fe2b-a931-5af3-b547-efedbef6b6a8 | note | H
d4a410fa-3974-53fa-96c2-27929d39d06d | note | Reference or Specification - MOTSAM
4aec795f-bc7d-50e8-999d-4f98cdac32bb | note | Method/Test Required - Visual check
5580f2ca-b5df-58f4-96b0-489be6fc072c | note | How Often? Per site
89790b72-ca20-5a92-a084-a5ec828d5c8d | note | Records Required - Job Sheet record & photograph
6ba8a1f5-42d9-5f70-bbd4-1a48d30a615d | note | Responsibility - Project Manager(AC)
| checkpoint | As-Built records – structural patches
fa099bed-c4c6-5e5d-878e-87554ce6bb2f | note | H
ae8f824a-503e-5b90-ab35-7d976ed69b5f | note | Reference or Specification - Design
6a8bbf0e-49f3-5145-b208-47bcc633e744 | note | Method/Test Required - Record as-built patch dimensions & RPs
0ac8ad1e-234a-5a51-89a4-9d50f83f9d9e | note | How Often? Per site
c10c070e-8167-5d8a-bf0f-e3f0b4f18e45 | note | Records Required - Job Sheet record & photograph
647b2d4d-c74f-5d82-8956-be245c0b6617 | note | Responsibility - Project Manager AC / Site QA
| checkpoint | Collect RAMM data
8939a23c-77e7-5289-a437-ce5b8e35dcec | note | H
17e7b602-9dcc-5309-91a2-4476d8da5100 | note | Reference or Specification - Comply with Waka Kotahi format
52eb71d3-da5b-5eef-a815-bf84535e1b8f | note | Method/Test Required - Correct data supplied
2cf02976-208d-571b-abce-46aef7bae2b6 | note | How Often? Per site
4f808b65-fe3c-5db4-8690-4c3a124bdfec | note | Records Required - Job Sheet record + As-Builts + photographs
98eb70d6-e534-5e1c-a0f1-6fa6c62328bc | note | Responsibility - Project Manager AC / Site QA
| section | 9.0 Out Of Season Paving
| checkpoint | Out of Season Paving
490798f0-1680-5933-b00e-2c3486dc8334 | note | H
377c6c62-8821-55e1-8631-481f978dc63a | note | Reference or Specification - Winter Surfacing Site Note
eaa95ec5-edb1-5d8c-8182-af3b8a324ac1 | note | Method/Test Required - Waka Kotahi Approval
bb8cb134-dc36-5ed1-a43f-cd7e670c4b5d | note | How Often? Per Applicable Site
ff2cb49c-f2c4-5c96-b9a4-0f4039668b9d | note | Records Required - Copy of Waka Kotahi Approval on-site
eb35e0e5-4e50-50b4-8c4c-d5f959d3efee | note | Responsibility - Project Manager AC / Site Supervisor
| checkpoint | Dispatching Temperature compliance
cbc6b157-7cdf-5c1c-b22b-da679c4ca12b | note | T
dc5c7f9a-abcd-524d-91dd-41c1c32b28ff | note | Reference or Specification - NZTA M10: 2020 Notes - Table 3.3
4834ae38-3a11-5755-8b00-7b34de12c7a4 | note | Method/Test Required - As per Table N4.1: NZTA M/10: 2014
2e0781cc-348b-51ba-bacc-832f7daf5b25 | note | How Often? Per Load
71e8d7c9-ed8f-5651-9b60-e6f9183368c8 | note | Records Required - Job Sheet record
2bfdf228-972f-555b-a881-23edced05b39 | note | Responsibility - Asphalt Plant Manager
| checkpoint | Arrival and Compaction Temperature: 110-170°C
d740a54f-8889-5167-bd8c-24a0eba189ff | note | To be recorded when mix is tipped into the paver.
be357e24-3442-5092-8b32-c22f8a070f43 | note | Manager to be notified if temperature falls below:
b2c52b00-c801-5b4c-bddd-15790ef16486 | note | ○ SMA9.5 134°C
23603f7a-57ac-58af-a417-2ee3104a856b | note | ○ SMA12.5 134°C
6a499980-38cb-5317-b9db-c13a6b2912ec | note | ○ SMA11 134°C
5396f01f-c24e-515f-b5f8-211b87b09763 | note | ○ AC20 145°C
3beebffe-448d-543e-87fa-ce0453b75fde | note | ○ AC14 142°C
8de52b37-170c-5a13-a8e5-fa05e6139108 | note | ○ If temperature falls below 110°C mix will not be used
195b0977-0383-5230-aedf-a8de6c663ccd | note | T
2eefd953-afbb-58ac-99fc-05f646138751 | note | Reference or Specification - NZTA M10: 2020 Notes - Table 3.3
e1bf0639-96ff-5ec0-86fc-ec8639fe38eb | note | Method/Test Required - Temperature Gun, Acceptable / Unacceptable
596d93b7-dfab-532b-bed6-07b10e3e457b | note | How Often? Per Load
bbb28095-715e-5a6e-ba5b-8efd4ea5d9f5 | note | Records Required - Job Sheet record
162a5c33-6d8a-5a41-a7fa-a483a678f508 | note | Responsibility - Site Supervisor / Site QA
| checklist | ITP - CS Resurfacing Physical Works | itp | ITP - CS Resurfacing Physical Works | d35dea3a-2c90-4e99-bfaa-db0fd82433d8
| section | 1.0 Pre-Works (Off Site)
| checkpoint | Stakeholder Management Requirements met
39a5a48f-4950-5af2-8b2a-837f5ee31fea | note | H
f485e1e9-f138-534c-809c-c41bb531a547 | note | Reference or Specification - CSCMP
737092be-2ec6-5973-a75c-67b36bf833ba | note | Method/Test Required - Confirm requirements followed
e8c46ce9-19f3-59e8-9a57-0742ad1a91d4 | note | How Often? Each site
d8b1c167-7827-5fde-bc5d-579a64aa7f93 | note | Records Required - Copy of stakeholder notification / Photographs of VMS Boards
fe93bc8e-353d-5819-ad7a-507338023530 | note | Responsibility - Project Manager / Renewals Manager
| checkpoint | Confirm if any environmental protection is required
9de85a5e-aace-55c1-9221-006995fac5ac | note | I
f0a0c3ff-d849-59b6-ad03-b1a157b0da7f | note | Reference or Specification - ESMP
51215c7d-090b-5b52-b7aa-c5f496505295 | note | Method/Test Required - Record decision
32f01e2d-143d-5af2-976a-ebf5bf633d83 | note | How Often? Each site
fd5e573f-e17a-5e0c-a8b9-505981272250 | note | Records Required - Pre-seal Inspection Form
5e445104-c683-5a45-b034-908e5dfe11da | note | Responsibility - Project Manager
| checkpoint | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work
f9e3fc36-678d-5c76-8b6c-2ad24539b175 | note | H
48f44b3d-94db-5da4-a71d-142534acb8df | note | Reference or Specification - QMP
424031c3-59ac-5982-824c-a221e18a5064 | note | Method/Test Required - QMP
aadfb09c-7042-564a-8e63-05279ee15cda | note | How Often? Each site
9a4759e8-2d68-5b7a-b243-201ef8fb539a | note | Records Required - Pre-seal Inspection Form
5ec72d4e-88af-5416-b947-3c24b8b636a9 | note | Responsibility - Project Manager
| section | 2.0 Pre-Construction (On Site)
| checkpoint | Job start, identify risks and controls, communicated to team
bafae4f1-23dd-5de2-8a5e-d5ff8f4f759b | note | H
a1c9e907-eafa-54a1-a40c-209c7af43634 | note | Reference or Specification - HSMP
34018b9a-2fc3-557e-a237-e1c9e48ee9b0 | note | Method/Test Required - Record all risks and controls on Hazard ID following Team discussion
73fec59b-e46d-532c-b4c5-0f23499ed39d | note | How Often? Each site
38ffa15e-040d-5da4-ae37-42cd602a298a | note | Records Required - Hazard ID form
376b7ebe-dc0e-5687-89b9-2b214e7f8c82 | note | Responsibility - Site Foreperson
| checkpoint | Establish traffic management to plan
e13e0ce2-28af-52a8-b5ae-137afd283289 | note | H
b65b06ad-7fb4-5c75-982c-9cf70c71ae2a | note | Reference or Specification - TMP
0bacbb7b-f30b-539f-afd4-182fd44c5930 | note | Method/Test Required - Site audit post set up
e3120d7b-7bd8-518d-a2d5-64ac99833573 | note | How Often? Each site
a5ee2c43-63ca-51bb-b7e2-25443f65e0ba | note | Records Required - TTM Diary
058b4297-5be4-5609-81b4-cdd3b00d2669 | note | Responsibility - STMS
| checkpoint | Confirm site is on approved programme
1b4931c5-c371-5c26-be0d-370f385f3a3c | note | H
6993b2fe-5c25-5957-8493-d6109f986448 | note | Reference or Specification - Approved Programme
7730bd64-7efc-53aa-8d32-a12ce019680e | note | Method/Test Required - Record as-built site dimensions
7beffe3c-2ea5-5b39-8c3e-d856b992f82d | note | How Often? Each Site
15f9f321-17a0-5ab9-9c5b-f7bd4707042b | note | Records Required - Pre-seal Inspection Form
f7b14c6b-dfa0-5b47-bb94-6619f1c4e615 | note | Responsibility - Site Foreperson
| checkpoint | Confirm site extents (i.e. Check what is marked on the road matches the job sheet / programme details
6ebc9878-b660-5aeb-a494-5ae63c6a62be | note | H
21fbdb91-426b-52cb-a85c-f6664bd8af3e | note | Reference or Specification - Approved Programme
76973980-e8fd-51e3-9a6b-35c167c2ee14 | note | Method/Test Required - Record as-built site dimensions
9565010d-9f08-548c-8a19-4a46c2d44786 | note | How Often? Each Site
915888d9-6e0f-559a-85e1-bbf5b3b05b41 | note | Records Required - Pre-seal Inspection Form
f400e981-72b5-52fe-a9f7-7090f32092a8 | note | Responsibility - Site Foreperson / Site QA
| checkpoint | Stockpiled sealing chip is clean and suitable for sealing
77ecced1-1f5d-51c3-8fc6-6541b6754f25 | note | H
f043472b-51aa-5088-a996-5a22d4ce0496 | note | Reference or Specification - QMP
6186464e-ca49-52ed-9acc-b53be3d4fd82 | note | Method/Test Required - Acceptable/Unacceptable
4c0e759e-21d4-54d0-8894-1b66244ad655 | note | How Often? Each Stockpile
c3777dab-2610-5bc3-b902-67181fe468f7 | note | Records Required - Pre-seal Inspection Form & Photograph
7c105a91-a7a4-5fc4-8f3d-eb64e6d04016 | note | Responsibility - Site Foreperson / Site QA
| checkpoint | Stockpiled sealing chip is the same grade(s) as specified in the chipseal design
acf042f0-978c-5685-88ca-b745952081b8 | note | H
b06f84e3-05d7-5138-8443-385e23d7af94 | note | Reference or Specification - QMP
14d3eac0-9f84-5658-b8f9-495d9959d592 | note | Method/Test Required - Acceptable/Unacceptable
92f3b93f-3d34-5bb6-9e21-f8d090173289 | note | How Often? Each Stockpile
1aad9f09-ac0d-5114-bf80-9388eb617c6b | note | Records Required - Pre-seal Inspection Form
cbb7c0aa-cc7a-5ec5-a0c9-f04180ef8576 | note | Responsibility - Site Foreperson / Site QA
| checkpoint | Record & photograph environmental protection measures installed
556274a6-6fba-5c9a-8471-af07b85fb81a | note | I
de2e79d0-894a-5f30-be60-1c9d8395b605 | note | Reference or Specification - ESMP
da149a96-ab68-56e7-b6c4-efc554aeb19e | note | Method/Test Required - Record temporary measures
26b452df-17bc-5827-95d1-6d163c87ae84 | note | How Often? Each site
822426a7-6203-5c6c-9659-70c80866429f | note | Records Required - Pre-seal Inspection Form & Photograph
2f3cf983-14bb-5ebb-b3cb-9a52f10985f8 | note | Responsibility - Site Foreperson / Site QA
| checkpoint | Binder application rate
827b0b38-7a75-5ed2-a488-0900a333891a | note | T
e5be3c21-4e83-527e-989c-8473d06a1452 | note | Reference or Specification - Seal Design / Spraying Insructions
f340b776-ecfc-5ffb-995e-a505c5a406a2 | note | Method/Test Required - Confirm seal design requirements from programme
5f2ed7dc-ed5a-56d0-92cc-3438281920dd | note | How Often? Per site
785d83af-f9b4-5f7b-8ad0-c79368bfb460 | note | Records Required - Spray Sheet
20efbcfd-6825-5a7c-b07f-8f9582a164bf | note | Responsibility - Site Foreperson / Site QA
| checkpoint | Pre-Sealing surface condition
029a6b72-98a7-55ee-87dc-9fc820b469e6 | note | I
0b8de01c-3abe-5bf8-bc32-a38fac6b01a9 | note | Reference or Specification - QMP
4ecc33b3-56ef-55a7-a310-805570ad1883 | note | Method/Test Required - Acceptable/Unacceptable
ac4df6b5-06a9-5467-bb56-71fe31cadf1d | note | How Often? Per Site
f81ed6c4-4c2e-5648-9460-cf893c71afc0 | note | Records Required - Pre-seal Inspection Form & Photograph
7e64f451-2375-56e5-8d6f-3840782b8179 | note | Responsibility - Site Foreperson / Site QA
| section | 3.0 Construction
| checkpoint | Start spraying Temp >10°C
14bc19c5-620c-5f78-8ea9-115364e8ca33 | note | T
53ad3ed5-e22a-58ff-9bff-f997efde4a71 | note | Reference or Specification - NZTA P/17
946d8bae-0e04-53a6-ae1d-57b3a9b69221 | note | Method/Test Required - Start >10°C
b4e5376b-3a6c-5e52-99b9-2685ed887811 | note | How Often? Per site
1aa1db7c-45a3-55ad-a09f-ae48b71cebe3 | note | Records Required - Spray Sheet
62888f16-a6de-5bf2-9b22-8b99549a5f3a | note | Responsibility - Site Foreperson / Site QA
| checkpoint | Binder application variation
6b822dc6-d600-5a0a-b7e3-446069449551 | note | T
ce3230fd-89ff-5324-b32b-79e5f2b6f672 | note | Reference or Specification - NZTA P/17
8cad59c8-9264-5c7c-875c-0db1f8b5b677 | note | Method/Test Required - +/- 4% (spray rate), +/- 50l (tank dip)
9e0f98af-35f6-509b-af47-581779c07636 | note | How Often? Per site
fd29a09c-82fb-57f1-8b43-e9d20cefc1f3 | note | Records Required - Spray Sheet
e69da77c-50db-5e4d-9a8d-0f64c0f37433 | note | Responsibility - Site Foreperson / Site QA
| checkpoint | Sealing chip application
4edabbb8-9977-50b2-96ca-9e5f28e0f926 | note | I
4316b877-d380-52b5-bafc-3cffb554adb4 | note | Reference or Specification - NZTA P/17
01485931-6b6c-5357-b0ff-78fddb7b2ceb | note | Method/Test Required - Full and even coverage of sprayed area
83863cda-0885-5972-a0ba-c01c59b436ee | note | How Often? Per site
7b92ba1d-933c-5838-86c0-e763bb96f574 | note | Records Required - Post-seal Inspection Form
1b9f482b-2708-52e7-bfb1-61106fa76057 | note | Responsibility - Site Foreperson / Site QA
| checkpoint | PTR Rolling pattern
73f22319-c9ad-5892-88e9-70062d998198 | note | I
89a57ad3-e1b9-5fd4-b60e-d7e0fbe3e33e | note | Reference or Specification - NZTA P/17
52145537-4f08-5505-ab00-8ddf7a7ff9ea | note | Method/Test Required - Initial rolling completed along with traffic-rolling under controlled TTM
0f02c7e2-d699-5e94-9125-9d04968a2a7c | note | How Often? Per Site
65e9dd05-e3fc-5eaa-bf29-c75e950cf60d | note | Records Required - Post-seal Inspection Form
15972532-2bed-57d4-81ca-1dc8436feaca | note | Responsibility - Site Foreperson
| checkpoint | Trafficating
27aaabc9-4157-58b8-81db-decd661f818a | note | I
bb242253-f146-5530-b5e2-9d52de1232d7 | note | Reference or Specification - Chapter 11 - Chipsealing in NZ
2eaeb738-531c-5c30-a23a-5f21f5a81f98 | note | Method/Test Required - Initial rolling completed along with traffic-rolling under controlled TTM
f49cadff-83de-529e-aff9-0e163176b99f | note | How Often? Per Site
b4354016-fb14-519d-b74d-5156f2f6ead2 | note | Records Required - Post-seal Inspection Form
83a7a683-cbb2-5da8-939f-2e7a27efbfb3 | note | Responsibility - Site Foreperson / STMS
| checkpoint | Tagging for line marking
7b94f579-7aaa-576e-b383-9b07c13cb644 | note | I
0404b2d1-7e21-5d70-a2af-bb42675bde41 | note | Reference or Specification - Chapter 11 - Chipsealing in NZ
f71e8731-bff5-5f46-8ea6-32ee6eeee084 | note | Method/Test Required - Pre-seal Visual check
2fbe157d-bc73-5c10-aaf5-5d1bad5520e5 | note | How Often? Per site
8fed2750-9f05-59a0-9f52-09638aa8594c | note | Records Required - Post-seal Inspection Form
3a58ec5e-989a-5f85-9f27-e33f32cdf112 | note | Responsibility - Site Foreperson
| checkpoint | Post-Sealing Surfacing Condition
d118cb21-6a60-51d7-b49c-1703ac39a0a7 | note | I
55beafee-b24b-51ef-8df9-ca8af9691a0f | note | Reference or Specification - QMP
adc9efac-6cac-5b27-b28f-d0954577506f | note | Method/Test Required - Visual check
40b131bb-85eb-58a4-82e8-72404cbc3902 | note | How Often? Per site
eff53bc9-06aa-50cf-8f32-e5fe35835933 | note | Records Required - Post-seal Inspection Form & Photograph
e21ebfd3-c9c7-5463-8945-31a5518ff8a6 | note | Responsibility - Site Foreperson
| section | 4.0 Post-Construction
| checkpoint | Linemarking and RRPM Reinstated; Matches previous linemarking - within 48 hours of sealing
95aaf1ac-4637-5bcd-b801-f83134bef37d | note | H
5393d6fa-99b2-5b18-844b-e2fd516db3ff | note | Reference or Specification - MOTSAM
9b777be4-b260-59cc-896a-ace5ff9a1863 | note | Method/Test Required - Visual check
e48282f5-83ad-52ff-8c1f-4f43d9369714 | note | How Often? Per site
1ee3a515-a3f1-52e2-b3bb-75bd3bb62b2c | note | Records Required - Photograph
f9ce98fa-c560-54a9-b51d-fe7d194efb23 | note | Responsibility - Project Manager
| checkpoint | Spray Sheet/s Checked & Supplied for Claiming
684108b8-8dc7-5601-a5b9-30ec944e6300 | note | H
01b45000-de7f-54d2-84c9-9e6a193de7f5 | note | Reference or Specification - QMP
322ea423-20a5-59dd-be42-cbc0f09baf38 | note | Method/Test Required - Spray sheet data verified against design/programme
469cb76a-dca4-5baf-a687-b49f496c5e95 | note | How Often? Per site
41a19284-df3a-5a54-8394-3a8b03f2c3ba | note | Records Required - Spray Sheet/s
8cd4dc75-872f-53d0-b168-84166ce360fe | note | Responsibility - Project Manager
| checkpoint | Collect & Upload RAMM data
1f10c491-371e-59ee-afce-8e8de1d47893 | note | H
08a31b37-816e-50cc-b83e-fdab808916f7 | note | Reference or Specification - Comply with Waka Kotahi format
75f11b7c-9ac6-5a99-880f-c472a7b0bdc8 | note | Method/Test Required - Correct data supplied
764d0058-9176-5a31-b7d9-064b6060276e | note | How Often? Per site
8d8b91cc-0174-5831-b387-8a4edffc247f | note | Records Required - Spary Sheet/s & Photographs
cf6b5b2a-99d4-5dd3-af69-2d611cc9ebbb | note | Responsibility - Renewals Manager
| section | 5.0 Out Of Season Sealing
| checkpoint | Out of Season Sealing
0f1e4578-e4d4-52de-a2b0-7d8fea21ea70 | note | H
34c0eef9-4abc-5244-99cd-502691e407ab | note | Reference or Specification - Winter Surfacing Site Note
3b797c96-2a6a-5ea7-ae01-9033a989ea0d | note | Method/Test Required - Waka Kotahi Approval
8c957d17-96a2-552a-9639-2c62a35c4c48 | note | How Often? Per Applicable Site
1f2a4b98-f8ce-5750-bcb9-7885c1fe5711 | note | Records Required - Copy of Waka Kotahi Approval on-site
83fe05d5-0146-50bc-801c-394e6af33684 | note | Responsibility - Project Manager / Renewals Manager
| checklist | ITP - Granular Rehab |  | ITP - Granular Rehab | c15272b8-6989-46f0-b7c3-7f4fc6dcbdaf
| section | 1.0 AP 40 M4 – Raw Aggregate Testing
| checkpoint | Sand equivalent, or
4d2cf821-6520-517d-89e2-f157321da96e | note | T
40e57aaa-d5d9-5315-897a-14636bbc276c | note | Reference or Specification: Design
f9e7a357-cd45-5c73-ac52-251436925c1d | note | Method/Test required: ≥35 Unit of measure?
db1f0675-d026-5ed4-98b7-643dffe70408 | note | How Often? 1 sample per 500m3
5e2b0a56-1333-5089-9d5a-e6dcdac1df8a | note | Records Required: Test Report
7151d52a-76d7-5d08-9811-7a7b07fd45ee | note | Responsibility: Project Manager
| checkpoint | Clay Index (passing 0.075 mm), or
adc13250-18dd-5721-b72a-7774db43d903 | note | T
d70f3f03-e8d4-530f-b074-b01ecefaff13 | note | Reference or Specification: Design
22eade97-91c1-57fc-a849-ca23b243417e | note | Method/Test required: <=3 Unit of measure?
ecbbd81f-a8f4-537d-ac1d-6fd46b75c8b5 | note | How Often? 1 sample per 500m3
e62f4a84-0e2e-59db-b079-85393c299beb | note | Records Required: Test Report
e5a3d3e1-49e4-5bae-8ba1-64810a107d1e | note | Responsibility: Project Manager
| checkpoint | Plasticity Index
6466c61d-56b8-56eb-8ad4-3aed70989037 | note | T
1dcf757e-8a2c-57e8-acc1-f5271302fd94 | note | Reference or Specification: Design
cddd3fdf-0ce8-5530-bd55-75b7cf384967 | note | Method/Test required: <=3 Unit of measure?
9033373f-a8a8-5aef-9d75-54519f75b383 | note | How Often? 1 sample per 500m3
af29a198-296c-559c-9363-8023aef1e7fe | note | Records Required: Test Report
48b18bfd-1c2f-5dee-b9e3-9b44269e6a9e | note | Responsibility: Project Manager
| section | 2.0 Site set up
| checkpoint | Particle size distribution
f8660252-3d97-50e1-9b24-e4bee69c630b | note | T
a92b4e01-de56-58e7-8468-17e86b81f1e7 | note | Reference or Specification: Design
6ee26eda-ad2c-5938-b0b9-a46df3641603 | note | Method/Test required:
4d6cc165-6e00-5a49-88ef-ca9f61066dbb | note | • 100% passing 63mm
f96f54c6-e9c2-5dd7-a82a-50f8ec198d76 | note | • 40% ≥ 65%passing 19mm
e364518e-2cee-5f83-989e-1768970372ca | note | • ≤ 10% passing 0.425mm425µm
55bbfdb8-4249-56ff-83ab-f9a935b86299 | note | How Often? 1 sample per 250m3
eb926334-f237-53f2-9f2c-6c7e3c8dea65 | note | Records Required: Test Report
8e7e8f87-a9ac-5d91-a70e-4492baefeac7 | note | Responsibility: Project Manager
| checkpoint | Solid Density
0f673e4e-1ef0-5c31-a4ad-e69efcf9260d | note | T
bfac5a10-9847-519d-9db6-6d0ac78bf455 | note | Reference or Specification: NZTA B/2 7.5
4d13ad2d-f21d-5720-a7cf-d0b356458ea3 | note | Method/Test required:
836e9828-fbc1-583f-a8b4-2d4ebb108583 | note | • Unit of measure?
387bcbfd-864b-56e8-bfcd-175c9561d9b2 | note | • Tolerance?
cbe032be-b7aa-56cc-a842-a20bbf0ff17a | note | How Often? 1 test
8addba43-addf-58a2-a024-70cff39f2116 | note | Records Required: Test Report
2c35083f-121b-5324-ac11-d2586adfa957 | note | Responsibility: Project Manager
| checkpoint | Determination of MDD & OWC
c382fc98-a0ab-5dd0-8c77-cf29859a8d6f | note | T
dc640a7b-e1fd-59ab-8ac9-e414d5066e97 | note | Reference or Specification: NZTA B/2 7.5
63be52d9-6fc1-57cd-a779-e852616774d3 | note | Method/Test required:
70296419-1b13-5031-b7d1-70b63def0d2e | note | • Unit of measure?
f6b13779-58ac-54e6-9338-6fed223a2a51 | note | • Tolerance?
b05a6c03-f72b-5a6d-85d7-9b10a4d15a89 | note | How Often? 1 test
4d7f1c4c-73d9-5856-b1bd-fcfbe760d0bc | note | Records Required: Test Report
5973aa65-b64a-57ca-b404-ec4b02517ebf | note | Responsibility: Project Manager
| section | 2.0 Site set up
| checkpoint | Stakeholder notifications undertaken
d9bb7c78-03d0-55c2-a148-29ef131f9971 | note | H
4e1108c7-d070-5281-aae0-a4edba97d28f | note | Reference or Specification: CSCMP
1134cb07-3254-5cca-b4fc-71e3361a6b15 | note | Method/Test required: Stakeholder notification emails and letter drops
7dae037c-0971-54bf-bb92-8e40ca6b504b | note | How Often? Each site
db85e112-63cb-5d1f-9e9b-4dcee681e086 | note | Records Required: Evidence of notifications
e3285768-0dbf-5523-83be-4b8ae7f06811 | note | Responsibility: Network Manager
| checkpoint | Mark-out of services and Permits in place
a2a5a143-068e-5f6c-92b3-0ad9fff01d88 | note | H
cf2baabb-d5c5-5856-8775-6586e90948a4 | note | Reference or Specification: HSMP
2534efed-950d-526f-bec9-70faaf2b77b4 | note | Method/Test required: Physical mark-out of all services and signed permits
4b21e569-ceb8-5e6e-b5ee-9d7917fe5d1f | note | How Often? Each site
ded77b56-cc00-5ca3-994a-56cd4885004e | note | Records Required: Signed permit
3e328bd6-6d95-53a1-a748-53e41b51a13d | note | Responsibility: Project Manager
| checkpoint | Job start, identify risks and mitigations, communicate to team
9d41bbee-bae7-506c-912c-8f23441d7caf | note | H
d2b5883a-7e96-576d-bd7a-e54b0259806d | note | Reference or Specification: HSMP
af869c72-4c95-5d1a-baef-8f49b59aab16 | note | Method/Test required: Record all hazards on JSEA and brief team
0b5f397d-033a-5e10-8d7f-419ebf2eb0b8 | note | How Often? Each morning
c0bd7f07-f60c-53be-b7b7-3b393598aba3 | note | Records Required: Job start form
22598b30-f560-504e-90c7-b6b50a57a113 | note | Responsibility: Supervisor
| checkpoint | Set up traffic management to plan
c9b1a23f-3309-562f-89d8-48cf666e0d6c | note | T
1d35345c-d03e-5217-b8d0-ccc0d12ff55c | note | Reference or Specification: TMP
5d4b4c16-57cc-5710-9e5e-9e3fa8812125 | note | Method/Test required: Perform Site audit post-set up
488be8df-3d9f-5f9e-96cc-2b83aa333e98 | note | How Often? Each site
2566039b-c037-592b-80d3-1f85cbf63801 | note | Records Required: Daily Diary
f765b09d-b5d3-54c1-ac53-585df13d4594 | note | Responsibility: STMS
| checkpoint | Assess environmental requirements of site and install sediment and erosion control measures if required
e12d909d-29d6-5d37-a6be-f61843cc8547 | note | I
d3e3992f-aedc-5207-85f1-702836ccc3b1 | note | Reference or Specification: ESMP
0de59572-3914-5a6d-838a-ca46591ec597 | note | Method/Test required: Identify areas at risk and install control measures
465caefb-1ec9-52b3-a0de-ff04acb14990 | note | How Often? Each site
36555d0c-03dc-59ae-b411-c913c6150166 | note | Records Required: Daily diary
5718283e-b05f-5c89-9e3a-b66e2580274f | note | Responsibility: Supervisor
| section | 3.0 Basecourse Inlay
| checkpoint | Cement Spread Rate
bf16d9bc-8f5b-57da-b829-708a2352dc6d | note | H
9b811293-1d83-5b75-bede-ae4a2d58125c | note | Reference or Specification: NZTA B/5
6a68f046-b2ef-5585-8b1c-4f6a51fa212c | note | Method/Test required:
68ba3c08-d4f6-5b77-905f-032501337e49 | note | • ±0.5kg/m2
b096e5a4-7f4c-51fc-813a-f7e648555d54 | note | • Weigh mat: Every 400m²
fdfdce63-d212-5d51-b3f0-992c4c5cbe96 | note | • Average usage test: Within ±2.5% of the specified rate
0f31b1cb-f744-53f0-8f46-4f19a5ed7793 | note | How Often? Upon emptying the spreader and bulk tanker
33d8dd3a-78d5-56d6-a05d-c4a1a40553ee | note | Records Required: Cement Sheet
83d56b0c-36af-5060-92f3-87ff7d6fb1b4 | note | Responsibility: Stabilizing Supervisor
| checkpoint | Hoe and stabilise to design depth
eb0660a5-38db-5cfe-ba49-72c8d345588a | note | I
31721692-6633-5822-9ed3-3a44e076a990 | note | Reference or Specification: NZTA B/5
7a02c458-b75f-5079-b05e-556484f8aa3d | note | Method/Test required: -0mm / +20mm
bfb09783-69da-5fc6-9acd-1e8dd0f9c9ec | note | How Often? Per run
b3adb155-f7f8-5955-9f19-51f210abe61c | note | Records Required: Cement Sheet
e9e6ea49-5b10-5319-8aa3-337a1137c7a8 | note | Responsibility: Stabilizing Supervisor
| checkpoint | Overlap longitudinal joints
afd0e67c-9fb1-584c-9a3b-8cad3b1d8be2 | note | I
65d97dcf-ddca-52e9-8820-460a1ca5a591 | note | Reference or Specification: NZTA B/5
bed21a60-bda6-5bfc-948c-f42b870e3634 | note | Method/Test required: Record hoe-depth setting
f6e7f3ef-fd88-5667-b22b-294a4bb6c22e | note | How Often? Per run
f450dba8-c609-5982-8777-d61a1dcc4823 | note | Records Required: Stringline Sheet
6c731e93-ccb3-5e25-93f0-df4bc702727d | note | Responsibility: Stabilizing Supervisor
| checkpoint | Plateau density test
78480592-72c1-519f-b144-de3712c26bff | note | T
dbff464a-b31c-5bfd-8102-cce2e86103cc | note | Reference or Specification: NZTA B/5
9f233171-54fd-558c-8c71-ac6cc9404c91 | note | Method/Test required: 200mm overlap
d7c82225-022c-5a9f-a546-f40df3535128 | note | How Often? 20m centres each side
10f235f4-9621-5b60-819b-866d3af32c40 | note | Records Required: Plateau Density Sheet
8b1b533a-93f3-5dbc-a8fc-cdda2ca57ae3 | note | Responsibility: Quality Engineer
| checkpoint | Confirm layer thickness
1a8f87b1-8dd7-5a8e-bcca-a076b199753c | note | T
9eca8c52-f26f-5eef-8e29-aa76d2e2db6b | note | Reference or Specification: NZTA B/5
263e5fc8-9055-563b-9aa3-9cba9778a158 | note | Method/Test required: Nuclear Densometer
28e3d9ae-7477-568e-aae6-2dcee381ad7f | note | How Often? 20m alternating wheel tracks
78e33726-b2ca-5422-a15f-bc3e87c28e88 | note | Records Required: Plateau Density Sheet
c1345231-9ddf-58cf-b40d-0df8a9dfdbd4 | note | Responsibility: Quality Engineer
| checkpoint | Compaction as per sample test results
5c316744-7f26-531d-bbd4-816aa938e518 | note | H
cc0a7653-a96b-52e5-ba7b-b9d32bed51f7 | note | Reference or Specification: NZTA B/5
043b2a5c-6517-5107-a919-6dbab6a49805 | note | Method/Test required:
3398d414-5c9b-5b2d-a13d-06b18b49b1e9 | note | • Mean ≥95%
11c94841-0e96-58ad-86c3-647234e6ebac | note | • Minimum ≥92%
9e9de884-4bb4-50db-9308-b700cb7573ba | note | How Often? Every 20m alternating wheel tracks
49173af8-d500-5efd-853c-5838382bb2db | note | Records Required: NDM Sheet
b76b3b52-3c94-5b50-b87d-5f99d4ef7544 | note | Responsibility: IANZ Accredited Lab
| checkpoint | Impact hammer test
680c8d34-ca05-5022-9099-1deea95b1211 | note | H
7c2d6a11-6368-568f-9c64-a86fcfcef3af | note | Reference or Specification: Spec?
196015ac-bcc8-5589-b25f-f6d47a2c27ea | note | Method/Test required: ≥70 CIV
40a20b84-51a2-5c7b-b77c-32c0fc09d24d | note | How Often? Every 20m alternating wheel tracks
259f8966-6dcc-5799-904d-55528f390b10 | note | Records Required: Clegg Sheet
131017c0-2a28-5a3a-944e-ecc195e8ff27 | note | Responsibility: IANZ Accredited Lab
| checkpoint | Confirm surface levels
bed4c548-1e0f-5d80-b4a4-e46ba226daa0 | note | T
89a89dbf-2076-55f1-bf9e-8e7f08750010 | note | Reference or Specification: NZTA B/2 5.1
387adf1a-4e89-59af-bdc1-603c6dcdd208 | note | Method/Test required: -5mm / +15mm
d21068b1-c78b-5d09-be60-d12348df6283 | note | How Often? Every 20m, full width
e917014d-1d21-5834-ba0a-a1d505541fb2 | note | Records Required: Stringline Sheet/As-Builts
d859786b-8c83-5799-a4e4-c73dbef89aad | note | Responsibility: Project Manager
| checkpoint | Surface Finish
4629df34-1ea7-5406-ae47-b05f7165c7d3 | note | T
05a81796-ccc5-5df8-8833-061ecbc7e71a | note | Reference or Specification: NZTA B/2 5.1
e660842d-8201-57e1-a32a-e6f1894ef1a8 | note | Method/Test required: -5mm / +15mm
2bac587f-98cc-5960-a955-5fd1015003ab | note | How Often? Every 20m, full width
0ba47bc4-4de1-57f6-b1bc-f3b81a335bde | note | Records Required: Stringline Sheet/As-Builts
64b26e2c-fe93-5c96-a381-5d55f160299e | note | Responsibility: Project Manager
| checkpoint | Confirm surface levels
b69a9972-69aa-594c-bb92-e7708a82eead | note | H
febc5fe1-0d34-5940-abfa-c62c02de88b3 | note | Reference or Specification: NZTA B/2
db87e87a-d635-5a46-a552-7eb83d5a8467 | note | Method/Test required: On-Site Inspection
a3c7ce0f-48bc-5dc3-b238-67c235ff8a56 | note | How Often? Per site
0ee85361-2f51-57bf-8045-fbc9760dfada | note | Records Required: Inspection between BECA/Higgins Staff
7cb796ce-4d02-56cb-b417-1a2fb0dd1e62 | note | Responsibility: Renewals Manager
| checkpoint | Surface Finish
a1ae4017-b135-52ac-a91c-3933ee03734f | note | H
402c44bf-64a4-53d0-8543-fba480afad1f | note | Reference or Specification: NZTA B/2
f1dd320a-4d6b-55d5-8bf6-749813915f1a | note | Method/Test required: On-Site Inspection
16d6bcbd-0df5-5e5e-98b4-7409eadbee39 | note | How Often? Per site
bc4b9e9a-8006-5c3d-b88a-121c5e804f34 | note | Records Required: Inspection between BECA/Higgins Staff
cc447cc4-61b6-5e60-b14e-4a379d4d6f63 | note | Responsibility: Renewals Manager
| section | 5.0 Aggregate Testing – Sealing Chip
| checkpoint | Crushing Strength
7070f8d8-a0f5-57d0-8a3e-5824f4770671 | note | T
748c5d9f-f7e4-5b72-b2b0-10f1bf06b808 | note | Reference or Specification: NZTA M/6 3.2
4f866c38-8db4-5df1-ba87-5cc19f88e7ae | note | Method/Test required: <10% fines passing 2.36mm under 230 KN load
7a8ded36-3778-5d35-a4b1-4d0a8d4de65e | note | How Often? 1 Test
beaa1565-22e3-59db-934d-ef72a58285eb | note | Records Required: Test Report
aea084fe-1f33-5d72-bb02-19fa6baf9280 | note | Responsibility: IANZ accredited laboratory
| checkpoint | Weathering Quality
9d9317af-5f3f-5f2a-86dd-d8733b7d5219 | note | T
92499d89-57aa-5d15-9016-c90bb4dec94c | note | Reference or Specification: NZTA M/6 3.3
169e6599-35e7-56b0-b968-833a3e3a0816 | note | Method/Test required: AA or BA
f06690c6-2e3d-5d33-a4b8-2b642be48f06 | note | How Often? 1 Test
8bcdb6e6-65df-51df-9c0a-d8d5530e08f8 | note | Records Required: Test Report
5bcb59ab-0e00-5aaf-a842-8c074e45c8b2 | note | Responsibility: IANZ accredited laboratory
| checkpoint | Polished Stone Value
8cafa7a5-85a4-581e-9155-f3e60813c009 | note | T
5d170ef9-dd35-5933-964c-80054b3a1a85 | note | Reference or Specification: NZTA M/6 3.5
b7abbb26-4083-55e7-9430-cd44d52bf847 | note | Method/Test required: PSV Required = 52 min
31066e80-2007-547c-b67b-2455d6f67c0b | note | How Often? 1 Test
530a2762-d03a-5b27-8e8c-50150d26190f | note | Records Required: Test Report
3a130578-c3f7-56ee-8d29-1d674d8c35e5 | note | Responsibility: Accredited PSV Testing Agency
| checkpoint | Cleanliness
b69296ea-2e07-54e3-906e-b65dcb100599 | note | T
da6bb7ab-a42b-5ff2-8ce5-f41cc58e6dac | note | Reference or Specification: NZTA M/6 4.1.1
2078bb69-dc2e-58be-8806-0a567c980fdf | note | Method/Test required:
7ee7e749-29d0-5a20-8082-e1ab6ebf717d | note | • Grade 5 – 89 min
41d6dfcc-6d05-5f27-acab-0acc92ae4466 | note | • Grade 3 – 87 min
bccbe0e5-c8ac-538e-8ad4-820da49a133a | note | • Grade 4 – 85 min
c2e3b567-f226-5344-b641-f4562ae52d52 | note | How Often? 1 Test
97c54b40-18ae-5800-9726-317115cfc3fb | note | Records Required: Test Report
d6829b8d-c448-5f80-80b4-8fd8f9fb9740 | note | Responsibility: IANZ accredited laboratory
| checkpoint | Grading
24348b10-a28d-5fda-a031-35ba86c8b985 | note | T
5b4bbfbf-fbe5-5e4b-a51b-43b8d678742a | note | Reference or Specification: NZTA M/6 4.2.1
e7189720-f022-5f4e-8648-64929346c7fd | note | Method/Test required: See NZTA M/6 4.2.1
81e48e2c-7154-57ab-a70d-b8276f385a10 | note | How Often? 1 Test
d1621ec8-6c97-559e-ae14-a008c221731f | note | Records Required: Test Report
590f871c-2c58-58fe-9683-f86407494c71 | note | Responsibility: IANZ accredited laboratory
| section | 6.0 Chipseal Control
| checkpoint | Confirm viscosity of bitumen
47df2033-a360-5a15-a90b-14d0719ab875 | note | T
f72afa0a-fdcb-5617-b964-921d3842fc53 | note | Reference or Specification: NZTA M/1 Table 1
229ad8c9-c54f-5dee-9404-94727f5f71a9 | note | Method/Test required: Viscosity PaS at 60°C
7804ba2f-5859-5490-a11a-dcbb68482113 | note | How Often? 1 Test
2f6b3c3f-44d2-54d3-a610-a5d50c4e96e7 | note | Records Required: Construction
2a19f162-53e7-5b73-a29a-1b72d29ad08c | note | Responsibility: IANZ accredited laboratory
| checkpoint | Confirm penetration grade of bitumen
071b38a2-a96e-58ad-a8e6-f6e92971601a | note | T
f4d2f8b2-c4d9-5c92-bd0a-eb15475b7d16 | note | Reference or Specification: NZTA M/1 Table 1
b681b191-804b-5c34-9439-7adc8f00ada6 | note | Method/Test required: Penetration at 25°C,100g, five seconds
db474ba6-fcfc-50fe-88ce-be548abd47fe | note | How Often? 1 Test
7cd55794-3c2c-526f-9d40-1e32164b7dc8 | note | Records Required: Construction
fb0af783-dbf3-597f-b979-31de0f316905 | note | Responsibility: IANZ accredited laboratory
| checkpoint | Spray bitumen, then place chip *and roll – refer design for chipseal Grade
8c4a121a-20a4-57bd-a485-95f37755e8fe | note | I
8ba0e5f0-dba0-51d2-8bfc-09adc8a251f6 | note | Reference or Specification: NZTA M/1 Table 1
2b810410-e512-515b-bead-1f850ecaeeec | note | Method/Test required: Visual Check
5992d0df-2b6f-5201-aa93-038ed961e812 | note | How Often? On-Site
3cb908ce-2534-5dd5-af3b-57edc92c8eda | note | Records Required: Visual check
850e82eb-f2a2-5b7a-a1ce-a26b1b031053 | note | Responsibility: Supervisor
| checkpoint | Check for excessive "windows"
dfae82b9-d6b5-5cfc-8d7b-a6ed7d0fc1cf | note | I
ebd0d65d-26cf-5c58-8390-4576578d894d | note | Reference or Specification: NZTA M/1 Table 1
e677fc85-7f52-512b-9475-83554ab826a9 | note | Method/Test required: Visual Check
72df6607-5ed0-51a8-809e-1c2c433a12b8 | note | How Often? On-Site
e163318d-22d2-5e3f-a9c5-77e7c63c5847 | note | Records Required: Visual check
3f7f11b5-30a6-5156-9018-70d6b95450f2 | note | Responsibility: Supervisor
| section | 7.0 Site Close-out
| checkpoint | Field Quality Review
718daf32-2204-52ff-8302-66bf1ad11cc2 | note | I
412e1f62-b1e1-5145-bb6d-eb69b1fec135 | note | Reference or Specification: QMP
3a9f264c-f827-5b2b-97d1-83fec248b45d | note | Method/Test required: Verification of Work Standards
49bc71f8-dcbd-51ed-ab1d-3ae48473bf28 | note | How Often? 10% of sites
b1b63f13-93cc-5e55-8cf9-d4dc92daa9bc | note | Records Required: Record in Audit Field of RAMM Contractor
6ac1a871-4cf8-5d76-b90d-47bae6768724 | note | Responsibility: Supervisor
| checkpoint | Collect RAMM Data
71452bf1-2a5c-5d04-b3a4-9d329f380161 | note | I
224c0ca6-bd40-5ea2-9848-c353d53ff609 | note | Reference or Specification: SHDOM / Data Quality Plan
9f4e3e89-8120-50b8-880e-654b5502ec5e | note | Method/Test required: L1 Accredited Personnel
97cffd38-f35d-5ffe-b215-0924c10da84c | note | How Often? All Jobs
04a70fab-66fc-5dfc-b73f-c911e03dfa4e | note | Records Required: SHDOM Specs
348b77a1-a5cb-5456-9c96-078167acce17 | note | Responsibility: Foreman / Supervisor
| checkpoint | Verify RAMM Data
f72b2ee7-0942-5733-bb74-840fc7cb6e65 | note | I
dc3d4038-ad5c-5c88-a782-ab15a86f58af | note | Reference or Specification: SHDOM / Data Quality Plan
bbde9e30-d538-5cd3-b512-25e45455734f | note | Method/Test required: Level 2 Accredited Personnel
bb35265a-c611-524f-8bca-f26db01bf8d8 | note | How Often? All Jobs
97fcedb0-1431-578b-8457-4110ea6f8365 | note | Records Required: SHDOM Specs
22783c80-eb3c-5bc7-a4ab-619bda58830f | note | Responsibility: Renewals Manager
| checklist | ITP - Resurfacing |  | ITP - Resurfacing | 5c426b84-eb5f-4995-a622-d9ebaf03f148
| section | 1.0 Pre-Work
| checkpoint | Approved JMF for Strengthening Repairs Mix (if required)
614627f2-b74d-572a-93c2-1206b9d70a36 | note | H
a4599147-a955-5e59-afb7-8a072cabeb4e | note | Reference or Specification - Design Report
f25a13da-a035-5d65-87fb-406cfbae7e6d | note | Method/Test Required - Confirm approved JMF dates in Design Report
b36050ca-3467-5d12-ab7d-3a08e898d891 | note | How Often? Each site
73b3c01e-ddde-5626-b1ac-c8d5b1ebd76a | note | Records Required - Copy of Approved Design Report
c376fcaf-eb4c-5879-92b3-364fa475b5e2 | note | Responsibility - Project Manager
| checkpoint | Approved JMF for Pre-Level Mix (if required)
d813c995-78b9-5365-9e89-8f7a71674d45 | note | H
b0633d86-1045-567d-bae6-da3566d8afeb | note | Reference or Specification - Design Report
670c37fa-920d-5fd5-aed0-6e13c22d1d24 | note | Method/Test Required - Confirm approved JMF dates in Design Report
04d5ee12-4df0-527e-93c3-81c1063bbc17 | note | How Often? Each site
a67a0c72-bbcb-5327-9e26-73eb23ff9bb7 | note | Records Required - Copy of Approved Design Report
c9cc4d17-5dea-51ef-bec0-c7e5e69d51c3 | note | Responsibility - Project Manager
| checkpoint | Approved JMF for Wearing Course Mix
23f34bbb-d9a1-5f1e-b6e5-754fffbf8417 | note | H
176691ad-808e-595f-a8ce-f78a009425ec | note | Reference or Specification - Design Report
a812eef0-95d1-5f5d-9e8a-de1731637260 | note | Method/Test Required - Confirm approved JMF dates in Design Report
0f3c22bf-8763-54b1-89b3-55bf457a7613 | note | How Often? Each site
50161ef5-97a8-587c-8999-54ed96ed13dc | note | Records Required - Copy of Approved Design Report
d8dce541-23bb-5520-921d-571da2d5456b | note | Responsibility - Project Manager
| checkpoint | Approved Design Report
638614c2-e5e1-5620-8064-19752bbc689c | note | H
487064df-d9a1-5d3b-9c89-e9c279384360 | note | Reference or Specification - Design Report
21fbd821-af9c-58fe-b7b2-7678d6adeff5 | note | Method/Test Required - Confirm document on-site
a9683f08-17db-58d1-9003-d7f9a894bbfd | note | How Often? Each site
e41c3d6e-014f-5dc8-8fc3-959fb316e386 | note | Records Required - Copy of Approved Design Report
338722f8-ad38-5c3c-a45e-fb634921d99e | note | Responsibility - Project Manager
| checkpoint | Treatment of affected Service Covers (to be raised or protected)
b626627d-f299-5a46-a85a-4e8672fa2137 | note | H
00a3c5a6-b7da-5e74-9740-398d86296fac | note | Reference or Specification - Job sheet
b5d2e7bc-9980-5180-a769-3c81b2752ce4 | note | Method/Test Required - Confirm plan in place
7e953416-76c4-598b-a310-917a254412c5 | note | How Often? Each site
60079e14-430e-5914-82ec-e83b42a7d074 | note | Records Required - Job Sheet record
227a205e-7f87-552d-98f8-dec815c5b7e4 | note | Responsibility - Project Manager
| checkpoint | Stakeholder Management Requirements met
2d349e5e-e7e4-5bea-938a-a3e1c06ea3b4 | note | H
57014eea-2650-5122-a56a-a246f267e1b0 | note | Reference or Specification - CSCMP
d43ad804-14e0-5be8-a08c-6a47fbb0f124 | note | Method/Test Required - Confirm requirements followed
ac8e2abe-702f-5768-bdc1-276a2d263151 | note | How Often? Each site
9d4b6897-cfd7-5e6c-af50-ec2809570fe0 | note | Records Required - Copy of stakeholder notification / Photographs of VMS Boards
25028f5e-0e68-5100-a8a9-a8c3df0fd833 | note | Responsibility - Project Manager
| checkpoint | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work
408e6f58-2477-5ffd-b344-ce665f954cd5 | note | H
8612560e-25a2-585d-9ba2-8cd258ae28e6 | note | Reference or Specification - QMP
e1209e46-8acc-5e69-8cd5-be5c1481535b | note | Method/Test Required - Brief all team members on day’s work plan
a1e6276a-6c57-54a3-8b52-200203208e8b | note | How Often? Each site
295d5654-1d54-5c96-9075-c70d2c8e9e71 | note | Records Required - Daily diary
02e7d41e-68d9-5f50-9c4a-4cdaaf5f23a1 | note | Responsibility - Project Manager
| checkpoint | Confirm if any environmental protection is required
943e1b8f-1fab-57ec-8e14-62a5cafc962b | note | H
887612ab-7ea4-50a5-93f5-4b74f875f9f3 | note | Reference or Specification - ESMP
191c1918-08bf-5423-bb34-f27a92eb8787 | note | Method/Test Required - Record decision
2f3ac495-f88c-5f09-908f-7cc5723eeb64 | note | How Often? Each site
014fd651-995c-5a87-a03c-c534463fb482 | note | Records Required - Job Sheet record
bbf6b828-0f7f-5282-9297-ded97af60776 | note | Responsibility - Project Manager
| section | 2.0 Site set up
| checkpoint | Ambient Conditions - Pavement Surface Temp ≥ 5ºC (Intermediate or structural layers) and ≥ 10ºC (wearing course) and forecast to rise
bea5a76f-e571-5b48-8afe-64e1233565b4 | note | H
078e3f1f-429b-5f77-9791-4f39d50400c4 | note | Reference or Specification - NZTA M10: 2020 9.5.2
fb0c6aa1-4429-542e-8a56-7aeccb9aab5a | note | Method/Test Required - Temperature Gun Check
d6619223-8d12-5d1e-95d1-9adf03ec1117 | note | How Often? Each site
2b7b46b8-7ea2-5f00-b057-ccc59cb68aa8 | note | Records Required - Job Sheet record
3571fcc7-4440-5ef9-a337-a29ccc846412 | note | Responsibility - Site Supervisor
| checkpoint | Job start, identify risks and controls, communicated to team
f8e86750-39df-527c-83cb-e0b2513eddf7 | note | H
ffd7d8c6-18fd-543f-944c-6f1eaade95c7 | note | Reference or Specification - HSMP
cad2d865-8ba6-5f27-bc7a-6da709a04be0 | note | Method/Test Required - Record all risks and controls on Hazard ID following Team discussion
359f8519-f970-54e2-ab58-2a470d78cb58 | note | How Often? Each site
ede2b1ef-0f23-56c6-a7e9-9f7239597eb2 | note | Records Required - Hazard ID form
44be61e7-6356-5654-ba3d-f4f2e57207e9 | note | Responsibility - Site Supervisor
| checkpoint | Establish traffic management to plan
bf779cbf-9fe6-59a8-a815-4de28db97bbf | note | H
84d0fae2-17f0-5c1a-8612-1209f0ae2d2b | note | Reference or Specification - TMP
40c8e5c3-5e8a-5cb2-8ba3-85909f681777 | note | Method/Test Required - Site audit post set up
9dfcbd02-e48b-50f9-b525-8f80e1846e19 | note | How Often? Each site
54922c69-ddeb-54d7-9088-e9dc4f9894ab | note | Records Required - TTM diary
7c4ecd00-9090-53e7-bdec-d1cc3fda8456 | note | Responsibility - STMS
| checkpoint | Confirm site extents by checking what’s marked on the road matches the job sheet / Design Report
2f0cd4b4-2f61-5498-9bb5-d269a2dda676 | note | H
603c8afb-1a2e-56ca-bcb7-1b2a864429cb | note | Reference or Specification - Design Report
07c4dd0b-2113-53e6-b2ee-28f1f2cc6161 | note | Method/Test Required - Record as-built site dimensions
355ffec6-e4b7-527a-87e7-70f161f02f74 | note | How Often? Each site
6387ef6d-e132-5540-8a3e-a3db8ebc14ea | note | Records Required - Job Sheet record
cdb28a15-4b23-5218-bded-2797f173666c | note | Responsibility - Site Supervisor
| checkpoint | Identification of Services; Service Plans on Site; Shallow Services Marked
7a3ff944-de0d-5e9d-8c8d-b0fd0ec46291 | note | H
d8fd0243-e8e7-5172-b709-668789f58d38 | note | Reference or Specification - SOP
ab35c67b-2c2a-53ef-955b-a570fabcc3f2 | note | Method/Test Required - Confirm document on-site / Visual check
83f633a6-3a40-5073-b21f-2f796effbf6a | note | How Often? Each site
bc8bf08a-b50f-5ede-ac73-8b64d931507f | note | Records Required - Job Sheet record
be544faf-513a-513e-a016-e8790600e63e | note | Responsibility - Site Supervisor
| checkpoint | Record & photograph environmental protection measures installed
814ac63c-b716-552b-85bc-54ba6e60274b | note | I
b25fdae7-2fa1-5bde-aec7-f72786775548 | note | Reference or Specification - ESMP
7e0ec370-bc41-5eb4-8fb7-87046bbbc531 | note | Method/Test Required - Record temporary measures
5f658e7c-84f2-5b88-8020-f07c9bd55f97 | note | How Often? Each site
2a8d9a7d-3847-50aa-b052-20c2ab7caf11 | note | Records Required - Job Sheet record & photograph
1ad6eabd-76ef-5f7e-9cc7-7f4855d376d1 | note | Responsibility - Site Supervisor / Site QA
| section | 3.0 Milling (If Required)
| checkpoint | Milling undertaken to correct depth - +/- 5mm nominal thickness
8a8e9c8a-3759-5e84-be41-117191ba5ce0 | note | I
be2b601a-be94-516f-974c-6dfdad45ee46 | note | Reference or Specification - Design Report
25e2ce9f-922e-554e-920d-27c9f29fe3fb | note | Method/Test Required - Dip checks
7588ed96-5774-51c6-a3ae-9218a07a4bad | note | How Often? Per site
777f14c7-7213-51db-b298-8c679b85ca5d | note | Records Required - Job Sheet record
e112f572-b4a5-5d5b-97b8-4a47eefd5d25 | note | Responsibility - Site Supervisor / Site QA
| checkpoint | Exposed Basecourse waterproofed / levelled
adf5023d-bb89-5359-a278-e0488036bb4b | note | I
a0bf61f9-2359-5da6-98d6-dcccf99d1731 | note | Reference or Specification - QMP
972be135-70f3-5b68-8093-d7f3e4cfbfbb | note | Method/Test Required - Acceptable / Unacceptable
e5731728-63d5-5fe7-b1f7-28336c7586af | note | How Often? Per site
b52fe598-19eb-5014-8fbf-bf13d3d52be5 | note | Records Required - Job Sheet record
c5d177d8-8990-553a-b4b0-4221462ce6eb | note | Responsibility - Site Supervisor
| section | 4.0 Membrane (If Required)
| checkpoint | Application as per Design Requirements (Chip size / binder application rate)
583c15fc-df7f-5e3e-a4a3-39577649a44e | note | I
067a3eaa-3c59-54e7-9137-4d5771d93ed8 | note | Reference or Specification - Design Report
e56b41b7-6556-5970-8974-9b5068c60b82 | note | Method/Test Required - Spray Sheet/s
16195792-9dec-508b-8d1d-3e5f6f2e8df6 | note | How Often? Per site
3577ef15-03f8-5850-a79c-9347cd0975c5 | note | Records Required - Job Sheet record
b9d75f4a-8323-551d-896e-834ed132d543 | note | Responsibility - Site Supervisor / Site QA
| section | 5.0 Strengthening Repairs (If Required)
| checkpoint | Delivery temperature - +/- 30 degrees from recommended mixing temperature
351d5799-fe31-517f-af5a-f5c0d8f178b2 | note | T
4eeb35bf-4556-5dde-aa5d-5a30e2a0d5e4 | note | Reference or Specification - NZTA M10: 2020 Notes
3327c1a7-31d9-5945-81b7-58a87a7fa770 | note | Method/Test Required - Temperature Gun Check - Acceptable/Unacceptable
4e796713-5a1d-5d66-b6de-29977f24f5de | note | How Often? Per load
910e079a-de35-5a57-bc1d-61253781f6ed | note | Records Required - Job Sheet record
ab762ed2-df41-59af-8e21-257f61891c48 | note | Responsibility - Site Supervisor
| checkpoint | Structural Asphalt Layer Thickness - Each Layer >55mm with ±10mm nominal thickness
926223c7-1d7f-55b5-a07b-b99528d3b2c4 | note | T
dc98884d-724b-5c6a-9a0c-637b6d18bdc9 | note | Reference or Specification - NZTA M10 2020 10.1 & Table 3.1
9fd39cdc-d8ec-5ce3-8270-774d6559c085 | note | Method/Test Required - Dip checks during paving process / Cores
a4153b81-50a5-5316-be12-53398e74a21d | note | How Often? One test per patch & / or One test per 300m2
c0991e61-0342-5de4-a888-cc2185e22e5a | note | Records Required - Job Sheet record & photograph
7a08ab87-ea9e-5009-966c-887074750793 | note | Responsibility - Site Supervisor / Site QA
| checkpoint | Compaction and Air Voids
a3fcbc42-cf2a-55fb-b8ae-9d06904f39d3 | note | T
9914f104-b957-5f60-89ea-eab837d0d2bd | note | Reference or Specification - Paving SOP
2a1b2772-9bc6-599c-bbc4-cbd5f6773dc1 | note | Method/Test Required - NDM for Quality Control Only
40f8216d-4cc8-5f51-b063-ac2fb005d26a | note | How Often? One test per patch & / or One test per 50m2
6303ac61-a073-55dc-be7b-54b4a63c040d | note | Records Required - Job Sheet record & photograph
b679ec4a-fbf9-5830-ab6b-e7358eb3a886 | note | Responsibility - Site Supervisor / Site QA
| section | 6.0 Pre-Levelling (If Required)
| checkpoint | Delivery Temperature - +10 / -30 degrees from recommended mixing temperature
131994ed-a516-55a1-b26d-dcf61235ab63 | note | T
8e14229a-8897-565e-9074-08c1e6890f3f | note | Reference or Specification - NZTA M10: 2020 Notes
f2113701-9ba2-5d3f-8b64-7f6a1b56e3df | note | Method/Test Required - Temperature Gun Check
a5d5ffab-a640-5143-996e-1008cfcf2875 | note | How Often? Per load
7cc30d20-2262-5892-80a5-cdd2d4271dad | note | Records Required - Job Sheet record
0aebda4f-e367-5216-8454-8791e13c5082 | note | Responsibility - Site Supervisor
| checkpoint | -5mm / +5mm below bottom of the nominal thickness of wearing course specified in Design Report
9b6a647a-bc3a-5235-bed6-8845f7932277 | note | T
49dbea31-65d4-5751-8ed5-8736662c591b | note | Reference or Specification - Design Report
f053f8dc-1306-5081-86f5-1886d9dfdde7 | note | Method/Test Required - Dip checks during paving process / Cores
5452f2c8-ca44-5228-9f78-8c425ce48f30 | note | How Often? Every 15m
629d8f64-3488-5350-9c63-c96621c639d4 | note | Records Required - Stringline Sheet record & photograph
3b38bfa3-8230-5208-80b3-ec52c6f0f8a5 | note | Responsibility - Site Supervisor / Site QA
| section | 7.0 Wearing Course
| checkpoint | Delivery temperature - +10 / -30 degrees from recommended mixing temperature
6f872f9c-af36-5256-bacc-d3767cd15e2c | note | T
c74fe05e-07a3-58eb-b686-c4b1667335be | note | Reference or Specification - NZTA M10: 2020 Notes
5e7ef251-6857-5746-96e6-aa57c9ded494 | note | Method/Test Required - Temperature Gun Check
0ddd6702-dd61-5631-8a7f-68b7adc5eb6d | note | How Often? Per load
468e8150-0322-58a4-8cf5-7c64e48ad9e7 | note | Records Required - Job Sheet record
faff4c48-47a2-567d-8032-b5445f0cf171 | note | Responsibility - Site Supervisor
| checkpoint | -5mm / +10mm nominal thickness specified in Design Report; If applicable all mix is not more than 5mm above lip of channel unless specified otherwise in the Design Report
5ec1ca8d-e237-52fb-a727-2ca4397ea596 | note | T
6dbe44e5-01e3-5af4-b574-8cdba769be91 | note | Reference or Specification - NZTA M10:2020 10.1 & NZTA M10:2020 Notes Table 3.3 & 3.4 or NZTA M27:2020 10.2 & NZTA M27:2020 Notes Table 3.1
f6e408a7-84f9-585f-b340-8a8266274440 | note | Method/Test Required - Dip checks during paving process / Stringline Sheet
f71a61d8-252b-5214-a29b-65149cf1402b | note | How Often? Every 15m
16b3497e-142b-5f92-9c3f-4f6aa3d55959 | note | Records Required - Stringline Sheet record & photograph
804441f2-0ff3-576a-ad1b-2e8184c9e280 | note | Responsibility - Site Supervisor / Site QA
| checkpoint | Compaction and Air Voids (1)
2fab9f12-6bf1-57f8-a333-469d1c975ccc | note | Mat density air voids (+3 and -2) and joint density air voids (+5 and -2) as noted on JMF with the offset (1)
e7c3233d-5582-52e7-995b-4e45ff99a59b | note | T
1bf0bc7f-c182-5cd0-833a-b2848c0bde94 | note | Reference or Specification - NZTA M10: 2020 Table 9.2 + ASTM D3203 or NZTA M27: 2020 Table 9.2
b1d6d6ff-72e3-5939-8ea1-f638a90c4865 | note | Method/Test Required - 150mm Diameter Cores where: 1. >30 tonnes 2. >=35mm lift thickness
63fc0fce-ac00-5229-a290-3acde03d8959 | note | 100mm Diameter Cores where: 1. >30 tonnes, 2. >=35mm and <40mm lift thickness
0937fa2a-d600-5bc1-8379-b959701219d8 | note | NDM (only where accepted by the Engineer in writing along with the testing plan.)
2c4db492-f7d2-5691-aeb2-8ed080deb389 | note | How Often? Mat Cores: Cores to be randomly located using ASTM D5361 in each sublot. 1 core per 300m2 sublot and a min 8 cores each lot
f0dfb116-8d9a-5714-a325-6e9872a1a2c3 | note | Joint Cores: Cores to be randomly located using ASTM D5361 in every 100m of joint.
2f2b76d0-4c58-52f9-a1fc-a9a96365e04d | note | NDM (only where accepted by then Engineer as per agreed testing plan.)
3c62b41d-ee55-5de1-bc12-208fe596e8dd | note | Records Required - IANZ Accredited Laboratory
299f1949-874f-5f57-8073-f0a34bbfa9d5 | note | Responsibility - Site Supervisor / Site QA
| checkpoint | Compaction and Air Voids
f5f32eab-ea3d-5a33-945d-ecea0e4cb47c | note | Mat density air voids (+3 and -2) and joint density air voids (+5 and -2) as noted on JMF with the offset
9c1b31a5-28ae-5fd6-923c-9c215c3a15d2 | note | T
0e5d3342-e9f3-5e41-9702-a6a1d3e25023 | note | Reference or Specification - NZTA M10: 2020 Table 9.2 + ASTM D3203 or NZTA M27: 2020 Table 9.2
42fee68a-dbdf-5155-84be-61c41078dc02 | note | Method/Test Required - NDM for Quality Control Only
e7349063-4673-5c10-9ebd-806ecfee237d | note | How Often? Every 20m alternating wheel tracks
19d04f1c-0d62-505f-8d47-41fdc8d7cd5f | note | Records Required - Job sheet Record
a787d75b-d3f7-52b3-ad49-a18b41370b90 | note | Responsibility - Site Supervisor / Site QA
| checkpoint | Post construction surface condition
f7fc67db-13c8-5e79-8607-b7db6dee8916 | note | I
1fcea953-933b-5002-b881-dbe814b1dc2f | note | Reference or Specification - Design
eaea649d-c0e7-5071-ad45-63bf7d5c6cb4 | note | Method/Test Required - Acceptable / Unacceptable
1b9276a6-ab08-5fb7-b219-6a31b0070319 | note | How Often? Per site
3c278b74-c546-5a2e-9c35-c10e9ec96a66 | note | Records Required - Job Sheet record
96ae3576-2e7d-5e2d-a861-af6ad4062c42 | note | Responsibility - Site Supervisor
| checkpoint | Supervisor to provide an update regarding site completion per shift
4c216096-0e87-53e1-9231-d53b76a89bf2 | note | H
309c288d-8e91-5a79-a3e8-2380dfd09c8d | note | Reference or Specification - Design
076ff0dd-5d92-5918-8cd1-cfb298b7f288 | note | Method/Test Required - Acceptable / Unacceptable
22c565ee-8a3f-5ab2-aab2-b15713491eb8 | note | How Often? Per site
ab8d98cf-ba0f-531b-9941-130b6893da44 | note | Records Required - Email
8adbdc45-e40c-5e7e-925e-b528096857ab | note | Responsibility - Site Supervisor
| section | 8.0 Post-Construction
| checkpoint | Linemarking and RRPM Reinstated - Matches previous linemarking - within 48 hours of sealing
26f66010-2c1f-5193-b755-7da2b6586d7d | note | H
196858d7-ae78-560d-b3bf-3f6d9df8571a | note | Reference or Specification - MOTSAM
4746cf38-c61b-52c9-8829-f5194575146a | note | Method/Test Required - Visual check
fada7c38-fa31-595b-b43f-2084ddf32e12 | note | How Often? Per site
8dccb2b8-51ab-5c96-b30e-3ff055b833a6 | note | Records Required - Job Sheet record & photograph
fa5faa76-b439-5be8-887f-c63eb13001e2 | note | Responsibility - Project Manager
| checkpoint | As-Built records – structural patches
935ea45b-6584-5e50-ae21-93d34b2e5bc7 | note | H
7c9daba6-8ddc-5baa-854b-61ab7ac3c326 | note | Reference or Specification - Design
7a408df1-1295-5e5a-bea5-1b714605afaa | note | Method/Test Required - Record as-built patch dimensions & RPs
64d2438a-6742-5828-b5d3-1b956e19060b | note | How Often? Per site
38b0a551-11c9-5b1c-bb4c-89997dedd85f | note | Records Required - Job Sheet record & photograph
153935c2-7dad-586e-aa78-c9b070321325 | note | Responsibility - Project Manager / Site QA
| checkpoint | Collect RAMM data
bcf21609-1837-59a6-a588-a53202a2ee4d | note | H
058a5f7c-01a1-538e-9bfd-2796241cc6ae | note | Reference or Specification - Comply with Waka Kotahi format
a4a38c8b-0b1a-582e-9f03-014b890ff567 | note | Method/Test Required - Correct data supplied
eaa3f37d-fec4-583c-982a-ce38bdbbba20 | note | How Often? Per site
e8fa2c04-0f73-5027-9ab4-14b6f656ee49 | note | Records Required - Job Sheet record + As-Builts + photographs
ffcc6258-3347-5679-a400-60de354c79ff | note | Responsibility - Project Manager / Site QA
| checkpoint | Compaction as per sample test results
faa49363-a106-5600-b37a-4d8c74a3a9fd | note | H
716b00bc-877a-5b27-ada2-9c9a6851ffc5 | note | Reference or Specification - JMF Design Compaction
d3652934-d117-53ea-802b-816a68ebf02b | note | Method/Test Required - Mean ≥95% ; Minimum ≥92%
58f44573-616f-5a80-a390-b0082d3c6a22 | note | How Often? Every 20m alternating wheel tracks
68fe9569-1e89-56eb-97e0-0fdad5deafed | note | Records Required - Post-Verification Testing and Report from IANZ Accredited Lab
6c555cc4-c940-5da6-8131-19beef47ab9a | note | Responsibility - Project Manager
| section | 9.0 Out Of Season Paving
| checkpoint | Out of Season Paving
df1092ba-0d46-5c88-90a2-d32a548a930d | note | H
f840efb0-c8b3-586f-a6bd-b99f174e14a9 | note | Reference or Specification - Winter Surfacing Site Note
9eca0f66-d4d1-5edd-bfe6-293d09ada857 | note | Method/Test Required - Waka Kotahi Approval
21c0c8d3-1928-536b-afd7-547f18100d23 | note | How Often? Per Applicable Site
55a74489-fd47-5c73-b10c-6c202215f413 | note | Records Required - Copy of Waka Kotahi Approval on-site
0344772a-0682-551a-8258-d792fd478326 | note | Responsibility - Project Manager / Site Supervisor
| checkpoint | Dispatching Temperature compliance
1bbbc46b-f35a-505e-b460-56f41d780c60 | note | T
1abe0390-e45c-53a2-a8d0-90cec27f8fdc | note | Reference or Specification - NZTA M10: 2020 Notes - Table 3.3
313dbd80-484a-53f5-8b73-d8f816153fd9 | note | Method/Test Required - As per Table N4.1: NZTA M/10: 2014
37b25f77-34b7-5180-b98b-29229a33b0ff | note | How Often? Per Load
4f66d4d7-c688-5365-a3c0-c6b0ece7b59e | note | Records Required - Job Sheet record
27f1a569-90dd-5440-885e-2616f5007321 | note | Responsibility - Asphalt Plant Manager
| checkpoint | Arrival and Compaction Temperature: 110-170°C - To be recorded when mix is tipped into the paver.
b8fb8fe1-9d51-56f2-9575-5dfd7d6009c1 | note | Manager to be notified if temperature falls below:
854e129f-6e98-5b97-a877-014a49cde3ea | note | SMA9.5 134°C
49f81d3f-ef5d-505e-9141-dd7aea3c2b5d | note | SMA12.5 134°C
0999946b-ce68-55c4-a1e7-14acfd8ae309 | note | SMA11 134°C
a9eb564e-6f7e-56d3-be86-9dce12defd12 | note | AC20 145°C
9098d435-3a02-5f35-b613-3d814d4596cf | note | AC14 142°C
c86b7995-f621-5d72-94b4-b4c6df8a2f34 | note | If temperature falls below 110°C mix will not be used
a0eccb67-6042-5fe4-a147-777eebe467b9 | note | T
97189927-6a15-5003-be91-6e0b3f582688 | note | Reference or Specification - NZTA M10: 2020 Notes - Table 3.3
b983561a-8520-542b-b6d4-9031654396a3 | note | Method/Test Required - Temperature Gun, Acceptable / Unacceptable
7125037d-25df-52b4-bbf0-82ebe595ad26 | note | How Often? Per Load
c26dc2c5-fcb5-5fe6-8701-dfa0d738e6d8 | note | Records Required - Job Sheet record
26fcfe2a-b929-5dac-8678-3955a2731d8e | note | Responsibility - Site Supervisor / Site QA
| checklist | ITP - Resurfacing Physical Works |  | ITP - Resurfacing Physical Works | 11c501f3-3973-475e-9374-d873aa4ed1ba
| section | 1.0 Pre-Works (Off Site)
| checkpoint | Stakeholder Management Requirements met
514feb31-9900-57d4-87a8-0493114086f0 | note | H
e1ae0b63-4067-56f9-8592-01007f84c8c0 | note | Reference or Specification: CSCMP
382f6237-72ed-5217-a8e5-de23badbb6a1 | note | Method/Test required: Confirm requirements followed
b69db65a-72ae-5a9e-904f-353797cc31ba | note | How Often? Each site
5daf83bd-fef7-51d0-b9fc-7a85bd370d47 | note | Records Required: Copy of stakeholder notification / Photographs of VMS Boards
7781d3d6-3b86-5d3a-9ddc-bdbdcaf00bb0 | note | Responsibility: Project Manager / Renewals Manager
| checkpoint | Confirm if any environmental protection is required
4e81b85c-5e3b-522b-a4ad-a194f31abd3d | note | I
f8403762-7078-52f2-a338-02c98b9b934d | note | Reference or Specification: ESMP
6763a998-4db1-5bf9-a8df-f90fd06fd686 | note | Method/Test required: Record decision
11877c7f-21b3-5356-833f-e4a29538fb93 | note | How Often? Each site
22e661b6-bb81-5f58-a9b4-61539753e690 | note | Records Required: Pre-seal Inspection Form
958d24ac-4e9d-5a00-9aee-c5d76da70220 | note | Responsibility: Project Manager
| checkpoint | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work
1095741a-fab2-59d2-a352-3fafb4d244f7 | note | H
05acbac3-9222-58c0-bffc-117d155a872b | note | Reference or Specification: QMP
c420a46d-b2fb-5b28-8898-c489c22c4b87 | note | Method/Test required: Brief all team members on day’s work plan
280f4f63-5321-5d00-90e3-ff1a754bd580 | note | How Often? Each site
bcb28a12-08b9-5983-8fa1-bbbb13519978 | note | Records Required: Pre-seal Inspection Form
29ac66cb-a92a-5343-bb2a-5f7cf543ebf4 | note | Responsibility: Project Manager
| section | 2.0 Pre-Construction (On Site)
| checkpoint | Job start, identify risks and controls, communicated to team
372af9e1-6473-5edf-8993-a3ca0522718e | note | H
b4d0775b-9174-5a44-924b-22bce35a41db | note | Reference or Specification: HSMP
1fea5a20-4f12-5bad-bc7f-e9f59974991b | note | Method/Test required: Record all risks and controls on Hazard ID following Team discussion
d30282bc-aa17-5ca8-8bb4-a58bfc02a918 | note | How Often? Each site
e96c6583-fbc6-5560-9895-0f9b06625919 | note | Records Required: Hazard ID form
442f38a5-6273-5206-a47a-0c569f704a5f | note | Responsibility: Site Foreperson
| checkpoint | Establish traffic management to plan
422df42b-d6af-5d8c-8c15-0aea2c1be5a7 | note | H
57d28253-685e-5509-8f65-b36ed82b48b0 | note | Reference or Specification: TMP
c7d7ae90-64fc-5b23-b65b-fb475b7755db | note | Method/Test required: Site audit post set up
9e42c8f9-4790-5262-b84c-ba02f020576a | note | How Often? Each site
a6290f6d-ac7c-5bc6-b233-aa5a15609803 | note | Records Required: TTM Diary
acdfa61b-dcd9-580e-8901-6d413786c036 | note | Responsibility: STMS
| checkpoint | Confirm site is on approved programme
486f5ace-fab7-5fc2-bbf9-1bd224e46bf7 | note | H
e72139d6-b145-5b6d-be28-73a90b05908e | note | Reference or Specification: Approved Programme
98b95bca-e55c-5bf1-9b27-b1e54cc617bd | note | Method/Test required: Record as-built site dimensions
2f995590-68d2-565f-be50-11469e8c276c | note | How Often? Each Site
aa11cf57-b7d5-5eef-96f2-9e37d066e304 | note | Records Required: Pre-seal Inspection Form
b3c5e478-6e76-538e-961e-e38a3723689c | note | Responsibility: Site Foreperson
| checkpoint | Confirm site extents (i.e. Check what is marked on the road matches the job sheet / programme details
8cd591a1-c0c0-51b8-9244-f1c3f4d20685 | note | H
67a55671-9978-5eec-9b22-34e7166377c3 | note | Reference or Specification: Approved Programme
a08a323e-5552-5e44-ac67-8ad687ff9bf0 | note | Method/Test required: Record as-built site dimensions
b6396cf9-41a2-5d83-80aa-b2b2895278e6 | note | How Often? Each Site
d98f130a-ea48-54b1-bf06-8caf9c60fffa | note | Records Required: Pre-seal Inspection Form
c89e98b9-1c7c-5d33-889f-3736922a4ebd | note | Responsibility: Site Foreperson / Site QA
| checkpoint | Stockpiled sealing chip is clean and suitable for sealing
be21e7cc-f14e-58c9-9b8c-a583fa6c4896 | note | H
e5e277e1-541c-5741-b13e-1d9a3cb0ab2e | note | Reference or Specification: QMP
ab06bef6-7758-5bf3-a31f-507b8d8b8639 | note | Method/Test required: Acceptable/Unacceptable
37dc2fd1-f83a-501c-b67e-1d8a22157eb1 | note | How Often? Each Stockpile
133fee51-a5ec-5d62-89d4-12be3bb3eb3a | note | Records Required: Pre-seal Inspection Form & Photograph
5cf85885-ca9d-5a7c-b47a-6511cc686fe6 | note | Responsibility: Site Foreperson / Site QA
| checkpoint | Stockpiled sealing chip is the same grade(s) as specified in the chipseal design
db83ce0f-fbb5-53c4-899f-58e02af52cab | note | H
7f93c9d5-e527-5ac7-9d7c-e82ab4e45b8f | note | Reference or Specification: QMP
d991459c-7f98-563f-ba0f-bb4597678f17 | note | Method/Test required: Acceptable/Unacceptable
9cec3ef5-ca6e-514b-83f2-3f630037c3a2 | note | How Often? Each Stockpile
2ab90d87-bab0-53f1-8235-6cfbbb41f379 | note | Records Required: Pre-seal Inspection Form
4920f103-16a5-52e2-9ada-eced370809ca | note | Responsibility: Site Foreperson / Site QA
| checkpoint | Record & photograph environmental protection measures installed
e08dfe05-2e41-581d-9fce-669f71a96348 | note | I
d3703491-18cd-514c-8411-c3e2f35f6eae | note | Reference or Specification: ESMP
84e7fef5-422f-5af8-bc7b-9f0e954f433c | note | Method/Test required: Record temporary measures
dbb42a91-5d90-5a83-a4d2-eb44afb2c3e2 | note | How Often? Each site
89866830-ef4a-53dd-8cb7-b1244aa975ee | note | Records Required: Pre-seal Inspection Form & Photograph
bb42efcf-3c7a-590f-ae65-622ef2c1e1d2 | note | Responsibility: Site Foreperson / Site QA
| checkpoint | Binder application rate
31d6f7d3-af32-5cd4-ab4d-f68331d697c0 | note | T
81331c41-745e-5785-8e9f-82a86f4d57ed | note | Reference or Specification: Seal Design / Spraying Instructions
166f61ea-3cd0-5974-9bb8-037453bbbaba | note | Method/Test required: Confirm seal design requirements from programme
cddaf740-3904-5869-a75c-ea8303584c7d | note | How Often? Per site
660a14c4-f391-5d97-91ed-02418fbcc564 | note | Records Required: Spray Sheet
bfc47693-07eb-5393-a9d2-dc0a42482839 | note | Responsibility: Site Foreperson / Site QA
| checkpoint | Pre-Sealing surface condition
63825ca3-689b-5ae2-9df0-41126ae36d65 | note | I
41a654cb-6c86-5b40-81a7-8c0506ca59b1 | note | Reference or Specification: QMP
3803892d-6166-544e-bf39-818d0042ae50 | note | Method/Test required: Acceptable/Unacceptable
2575e3f0-38f0-5a4e-8ac8-bc6aeabf285e | note | How Often? Per Site
7a4bae46-7cc5-5551-8bc2-74ba80614f0f | note | Records Required: Pre-seal Inspection Form & Photograph
4e3e70ef-6f5b-58cc-ad2a-2fdd696deb15 | note | Responsibility: Site Foreperson / Site QA
| section | 3.0 Construction
| checkpoint | Start spraying Temp >10°C
bb813cd5-bdfd-5d74-8467-d2c84d26aa61 | note | T
3521d8eb-8049-5390-a8f2-662a8b2dc4af | note | Reference or Specification: NZTA P/17
7757406c-ccc2-5815-8d77-8c63020f54c2 | note | Method/Test required: Start >10°C
efd27d66-b105-5c39-9b90-60da5aa76685 | note | How Often? Per site
d6116fac-c4e4-55c2-b0cb-7ed9eb57974a | note | Records Required: Spray Sheet
9e9314f8-ea99-527b-ba11-76b88abf9e51 | note | Responsibility: Site Foreperson / Site QA
| checkpoint | Binder application variation
de88f092-56f7-5269-a824-b7f076452397 | note | T
d90fd9b7-fd1f-5a48-a5ed-a7af5f187577 | note | Reference or Specification: NZTA P/17
4724bf5b-4707-5983-a58d-97a26df72e44 | note | Method/Test required: +/- 4% (spray rate) ; '+/- 50l (tank dip)
e28c2fbf-78bc-570d-972d-0eb2bf2c884d | note | How Often? Per site
f644c823-03cf-5f01-b057-6a5d30087335 | note | Records Required: Spray Sheet
9c25bfa1-ef4a-50ed-b098-394ae898d915 | note | Responsibility: Site Foreperson / Site QA
| checkpoint | Sealing chip application
58bf46f7-3631-56d2-a29d-05870321c645 | note | I
1250e596-91da-5ace-b99c-8b0bb55d1e49 | note | Reference or Specification: NZTA P/17
189e2f74-6682-549b-aa26-80b7fbffd361 | note | Method/Test required: Full and even coverage of sprayed area
d051d9f7-4d7d-560f-93f7-5f184de40863 | note | How Often? Per site
0e615c88-4c58-5aa3-b869-aef574742a6f | note | Records Required: Post-seal Inspection Form
f63d8912-13ec-5aa0-9486-fc80edcc08d4 | note | Responsibility: Site Foreperson / Site QA
| checkpoint | PTR Rolling pattern
474bb046-0c4f-5352-9875-48b76fa17b10 | note | I
d87e1cca-d786-5557-8f84-5544d187a0e0 | note | Reference or Specification: NZTA P/17
2a63f91e-e0bf-5ef7-8472-5e8d2aab3870 | note | Method/Test required: Initial rolling completed along with traffic-rolling under controlled TTM
c118b2aa-adc1-5e38-a54a-7b4d3afc7dac | note | How Often? Per Site
6b1e32df-e7ae-50b2-b01b-26c2e8573bd0 | note | Records Required: Post-seal Inspection Form
ecc8f986-84bc-5183-bf3b-43c73333a33c | note | Responsibility: Site Foreperson
| checkpoint | Traffickating
2f17eedd-1c14-5ee3-b2e6-520538cc6760 | note | I
bb0e2520-ef31-5140-a95d-f0521a291d76 | note | Reference or Specification: Chapter 11 - Chipsealing in NZ
4dfeb8f9-e497-56b7-912e-e86e4fb7ad73 | note | Method/Test required: Initial rolling completed along with traffic-rolling under controlled TTM
220569d7-faa8-56d0-8ada-a728375065d4 | note | How Often? Per Site
a215a066-9bc5-507b-969e-1bc200718129 | note | Records Required: Post-seal Inspection Form
251531fa-20ba-53fb-b02d-de284112e81f | note | Responsibility: Site Foreperson / STMS
| checkpoint | Tagging for line marking
705f2b9f-7dd4-5e9f-a7aa-83889051ea7d | note | I
c5f207a9-78f4-561b-8eab-945e7d7073c6 | note | Reference or Specification: Chapter 11 - Chipsealing in NZ
70e9aeb1-6c4e-58f0-9030-b1943e993e2c | note | Method/Test required: Pre-seal Visual check
fc9f0fac-2cb1-5014-bb03-acc01e400e05 | note | How Often? Per site
f501e1d9-f989-522a-bea6-23debfd7074a | note | Records Required: Post-seal Inspection Form
f4be5c95-bfbe-588c-ae20-d8e4be15dad9 | note | Responsibility: Site Foreperson
| checkpoint | Post-Sealing Surfacing Condition
ccc1d4a3-83ab-5b1f-bbf0-01897f6531d5 | note | I
78ce75f5-5d14-5b0f-815b-e23210d2cedb | note | Reference or Specification: QMP
8d7fb714-cd73-5bb6-a46c-5e6bf07c3246 | note | Method/Test required: Visual check
db82106c-2f07-5ab7-b520-44293891ca29 | note | How Often? Per site
d159eaab-cb01-535c-ad11-949196f03c3a | note | Records Required: Post-seal Inspection Form & Photograph
b6b1b3c4-cabc-5081-b309-1e91d676ce10 | note | Responsibility: Site Foreperson
| section | 4.0 Post-Construction
| checkpoint | Linemarking and RRPM Reinstated, Matches previous linemarking - within 48 hours of sealing
aca83171-09a4-5ca3-9353-e36731410e80 | note | H
9f2d5f41-c7ec-5a4b-ac37-1059350cfbe7 | note | Reference or Specification: MOTSAM
a58910b8-0001-5425-b085-ea741d486c31 | note | Method/Test required: Visual check
1f0576e2-78a3-58e6-81a0-e38799f46b95 | note | How Often? Per site
f7be1a21-ccea-54ea-a72d-53dfb53c1c74 | note | Records Required: Photograph
78ae8dda-a490-5dfa-ac94-40752e6ed483 | note | Responsibility: Project Manager
| checkpoint | Spray Sheet/s Checked & Supplied for Claiming
d6e109a0-a82d-58d7-bade-1185937c2937 | note | H
12512d2d-31b6-570f-bfaf-5edadd2e5736 | note | Reference or Specification: QMP
44de06ad-7231-52aa-a0df-31039a764fd6 | note | Method/Test required: Spray sheet data verified against design/programme
7540dc3c-e6ca-526f-8175-1ac266e766fa | note | How Often? Per site
45c11bd7-d87a-5f88-8dbb-69560eef0fad | note | Records Required: Spray Sheet/s
61c78ccc-c35f-575d-b9fe-ac3c36099eb7 | note | Responsibility: Project Manager
| checkpoint | Collect & Upload RAMM data
9872be1e-2d6c-5fa1-8558-ad3e19dc8043 | note | H
de930a93-34b8-5d74-8cc7-1f71756fce73 | note | Reference or Specification: Comply with Waka Kotahi format
5b9e4a8e-3668-5af8-b238-9f2bf2d814b5 | note | Method/Test required: Correct data supplied
66c48a97-e042-59b4-8fa9-4ed3e13db94c | note | How Often? Per site
b590a342-1510-5d18-8a3c-717e39aa2069 | note | Records Required: Spray Sheet/s & Photographs
40ee1d1f-0b7b-557c-b01b-10265ce39e8c | note | Responsibility: Renewals Manager
| section | 5.0 Out Of Season Sealing
| checkpoint | Out of Season Sealing
606d6a13-e8e4-517f-855f-749cab707094 | note | H
652df943-3eec-5744-b925-c984ae02af6d | note | Reference or Specification: Winter Surfacing Site Note
7e2173e3-d1ef-530a-951a-58be16aae7d9 | note | Method/Test required: Waka Kotahi Approval
b1cbb982-60ef-538e-afcd-b8452eeae752 | note | How Often? Per Applicable Site
2d3aa446-22f2-5835-9148-15df363ef8f3 | note | Records Required: Copy of Waka Kotahi Approval on-site
4499ba86-069d-5732-91bf-9e9669835037 | note | Responsibility: Project Manager / Renewals Manager
| checklist | Production and Testing ITPs |  | Production and Testing ITPs | ed7e3a13-3294-4682-90ab-838745b0937f
| checkpoint | Production and Testing ITPs
| checklist | QMP |  | QMP | 6161efe9-f0a4-47ed-973e-fe443cd024f1
| checkpoint | QMP
| checklist | Verified Program |  | Verified Program | 2fe02575-2c1b-48ff-baa0-0dd27deca0fa
| checkpoint | Verified Program