## Project Structure
QA Folder Structure | [5 empty] | Instructions | Checklists
Site QA
Communal Areas
Yarra Tower
|  |  | Water Meter Room |  |  |  | Water Meter Room
Rough In
Ground Floor
[5 empty] | Food and Drink DDA |  | Rough In
Level 1
Level 2
Level 3
Level 29
Fit Off
Ground Floor
[5 empty] | Food and Drink DDA |  | DDA Fit Off
Level 1
Level 2
Level 3
Level 29
Commissiong
Ground Floor
[5 empty] | Food and Drink DDA |  | DDA Commissioning
Level 1
Level 2
Level 3
|  | Clarmont Tower |  | Level 29
|  |  | GIT Room |  |  |  | GIT Room
Rough In
Basement 1
[5 empty] | Staff Room |  | Rough In
[5 empty] | Laundry |  | Rough In
[5 empty] | DDA |  | Rough In
Ground Floor
[5 empty] | Cleaners |  | Rough In
Level 1
Level 16
Level 21
[5 empty] | Bar |  | Rough In
Fit Off
Basement 1
[5 empty] | Staff Room |  | Staff Room Fit Off
[5 empty] | Laundry |  | LAUNDRY Fit Off
[5 empty] | DDA |  | DDA Fit Off
Ground Floor
[5 empty] | Cleaners |  | Cleaners Fit Off
Level 1
Level 16
Level 21
[5 empty] | Bar |  | Bar Fit Off
Commissiong
Basement 1
[5 empty] | Staff Room |  | Staff Room Commissioning
[5 empty] | Laundry |  | LAUNDRY Commissioning
[5 empty] | DDA |  | DDA Commissioning
Ground Floor
[5 empty] | Cleaners |  | Clearners Commissioning
Level 1
Level 16
Level 21
[5 empty] | Bar |  | Bar Commissioning
Yarra Tower
Corridors
|  |  | Level 3 |  |  |  | Corridors
|  |  | Level 4 |  |  |  | Corridors
|  |  | Level 5-19 |  |  |  | Corridors
|  |  | Level 20-28 |  |  |  | Corridors
Meter Assembilies & Risers
|  |  | Basement 2 |  |  |  | Meter Assemblies & Risers
|  |  | Basement 1 |  |  |  | Meter Assemblies & Risers
|  |  | Ground Floor |  |  |  | Meter Assemblies & Risers
|  |  | Level 1 |  |  |  | Meter Assemblies & Risers
|  |  | Level 2 |  |  |  | Meter Assemblies & Risers
|  |  | Level 3 |  |  |  | Meter Assemblies & Risers
|  |  | Level 4 |  |  |  | Meter Assemblies & Risers
|  |  | Level 5 -19 |  |  |  | Meter Assemblies & Risers
|  |  | Level 20-28 |  |  |  | Meter Assemblies & Risers
|  |  | Level 29 |  |  |  | Meter Assemblies & Risers
Lagging
|  |  | Basement 2 |  |  |  | Lagging
|  |  | Basement 1 |  |  |  | Lagging
|  |  | Ground Floor |  |  |  | Lagging
|  |  | Level 1 |  |  |  | Lagging
|  |  | Level 2 |  |  |  | Lagging
|  |  | Level 3 |  |  |  | Lagging
|  |  | Level 4 |  |  |  | Lagging
|  |  | Level 5 -19 |  |  |  | Lagging
|  |  | Level 20-28 |  |  |  | Lagging
|  |  | Level 29 |  |  |  | Lagging
Drains
|  |  | Basement 2 |  |  |  | Drains
|  |  | Basement 1 |  |  |  | Drains
|  |  | Ground Floor |  |  |  | Drains
|  |  | Level 1 |  |  |  | Drains
|  |  | Level 2 |  |  |  | Drains
|  |  | Level 3 |  |  |  | Drains
|  |  | Level 4 |  |  |  | Drains
Level 5 -19
|  |  |  | 1301 - 1901 |  | From Level 13 - break down into each apartment per level - follows same sequence | Drains
|  |  |  | 1302 - 1902 |  | From Level 13 - break down into each apartment per level - follows same sequence | Drains
|  |  |  | 1303 - 1903 |  | From Level 13 - break down into each apartment per level - follows same sequence | Drains
|  |  |  | 1304 - 1904 |  | From Level 13 - break down into each apartment per level - follows same sequence | Drains
|  |  |  | 1305 - 1905 |  | From Level 13 - break down into each apartment per level - follows same sequence | Drains
|  |  |  | 1306 - 1906 |  | From Level 13 - break down into each apartment per level - follows same sequence | Drains
|  |  |  | 1307 - 1907 |  | From Level 13 - break down into each apartment per level - follows same sequence | Drains
|  |  |  | 1308 - 1908 |  | From Level 13 - break down into each apartment per level - follows same sequence | Drains
|  |  |  | 1309 - 1909 |  | From Level 13 - break down into each apartment per level - follows same sequence | Drains
|  |  |  | 1310 - 1910 |  | From Level 13 - break down into each apartment per level - follows same sequence | Drains
|  |  |  | 1311 - 1911 |  | From Level 13 - break down into each apartment per level - follows same sequence | Drains
|  |  |  | 1312 - 1912 |  | From Level 13 - break down into each apartment per level - follows same sequence | Drains
|  |  |  | 1313 - 1913 |  | From Level 13 - break down into each apartment per level - follows same sequence | Drains
|  |  |  | 1314 - 1914 |  | From Level 13 - break down into each apartment per level - follows same sequence | Drains
|  |  |  | 1315 - 1915 |  | From Level 13 - break down into each apartment per level - follows same sequence | Drains
Level 20-28
|  |  |  | 2001-2801 |  | break down into each apartment per level - follows same sequence | Drains
|  |  |  | 2002-2802 |  | break down into each apartment per level - follows same sequence | Drains
|  |  |  | 2003-2803 |  | break down into each apartment per level - follows same sequence | Drains
|  |  |  | 2004-2804 |  | break down into each apartment per level - follows same sequence | Drains
|  |  |  | 2005-2805 |  | break down into each apartment per level - follows same sequence | Drains
|  |  |  | 2006-2806 |  | break down into each apartment per level - follows same sequence | Drains
|  |  |  | 2007-2807 |  | break down into each apartment per level - follows same sequence | Drains
|  |  |  | 2008-2808 |  | break down into each apartment per level - follows same sequence | Drains
|  |  |  | 2009-2809 |  | break down into each apartment per level - follows same sequence | Drains
|  |  |  | 2010-2810 |  | break down into each apartment per level - follows same sequence | Drains
|  |  |  | 2011-2811 |  | break down into each apartment per level - follows same sequence | Drains
|  |  |  | 2012-2812 |  | break down into each apartment per level - follows same sequence | Drains
|  |  |  | 2013-2813 |  | break down into each apartment per level - follows same sequence | Drains
|  |  |  | 2014-2814 |  | break down into each apartment per level - follows same sequence | Drains
|  |  |  | 2015-2815 |  | break down into each apartment per level - follows same sequence | Drains
|  |  | Level 29 |  |  |  | Drains
|  |  |  | Ambulant 1 |  | break down into each apartment per level - follows same sequence | Drains
|  |  |  | Ambulant 2 |  | break down into each apartment per level - follows same sequence | Drains
|  |  |  | Cleaners Room |  | break down into each apartment per level - follows same sequence | Drains
|  |  |  | Private Dining |  | break down into each apartment per level - follows same sequence | Drains
|  |  |  | DDA 1 |  | break down into each apartment per level - follows same sequence | Drains
|  |  |  | DDA2 |  | break down into each apartment per level - follows same sequence | Drains
|  |  |  | Residental Bar |  | break down into each apartment per level - follows same sequence | Drains
Rough In
Ground Floor
|  |  |  | Male Ammenities |  |  | Rough In
|  |  |  | Female Ammenities |  |  | Rough In
|  |  |  | DDA |  |  | Rough In
|  |  |  | Lobby DDA |  |  | Rough In
|  |  |  | Fitness studio DDA |  |  | Rough In
Level 1
|  |  |  | Male Ammenities |  |  | Rough In
|  |  |  | Female Ammenties |  |  | Rough In
|  |  |  | DDA |  |  | Rough In
Level 2
|  |  |  | Male Ammenities |  |  | Rough In
|  |  |  | Female Ammenities |  |  | Rough In
|  |  |  | DDA |  |  | Rough In
Level 3
|  |  |  | 301 |  |  | Rough In
|  |  |  | 302 |  |  | Rough In
|  |  |  | 303 |  |  | Rough In
|  |  |  | 304 |  |  | Rough In
|  |  |  | 305 |  |  | Rough In
|  |  |  | 306 |  |  | Rough In
|  |  |  | 307 |  |  | Rough In
|  |  |  | Gym DDA 1 |  |  | Rough In
|  |  |  | Gym DDA 2 |  |  | Rough In
Level 4
|  |  |  | 401 |  |  | Rough In
|  |  |  | 402 |  |  | Rough In
|  |  |  | 403 |  |  | Rough In
|  |  |  | 404 |  |  | Rough In
|  |  |  | 405 |  |  | Rough In
|  |  |  | 406 |  |  | Rough In
|  |  |  | 407 |  |  | Rough In
|  |  |  | 408 |  |  | Rough In
|  |  |  | 409 |  |  | Rough In
|  |  |  | 410 |  |  | Rough In
|  |  |  | 411 |  |  | Rough In
|  |  |  | 412 |  |  | Rough In
|  |  |  | 413 |  |  | Rough In
|  |  |  | 414 |  |  | Rough In
|  |  |  | 415 |  |  | Rough In
Level 5 -19
|  |  |  | 501 - 1901 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 502-1902 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 503-1903 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 504-1904 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 505-1905 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 506-1906 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 507-1907 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 508-1908 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 509-1909 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 510-1910 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 511-1911 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 512-1912 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 513-1913 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 514-1914 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 515-1915 |  | break down into each apartment per level - follows same sequence | Rough In
Level 20-28
|  |  |  | 2001-2801 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 2002-2802 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 2003-2803 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 2004-2804 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 2005-2805 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 2006-2806 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 2007-2807 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 2008-2808 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 2009-2809 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 2010-2810 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 2011-2811 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 2012-2812 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 2013-2813 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 2014-2814 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 2015-2815 |  | break down into each apartment per level - follows same sequence | Rough In
Level 29
|  |  |  | Ambulant 1 |  |  | Rough In
|  |  |  | Ambulant 2 |  |  | Rough In
|  |  |  | Cleaners Room |  |  | Rough In
|  |  |  | Private Dining |  |  | Rough In
|  |  |  | DDA 1 |  |  | Rough In
|  |  |  | DDA2 |  |  | Rough In
|  |  |  | Residental Bar |  |  | Rough In
Fit Off
Ground Floor
|  |  |  | Male Ammenities |  |  | MALE AMENITIES Fit Off
|  |  |  | Female Ammenities |  |  | FEMALE AMENITIES Fit Off
|  |  |  | DDA |  |  | DDA Fit Off
|  |  |  | Lobby DDA |  |  | DDA Fit Off
|  |  |  | Fitness studio DDA |  |  | DDA Fit Off
Level 1
|  |  |  | Male Ammenities |  |  | MALE AMENITIES Fit Off
|  |  |  | Female Ammenties |  |  | FEMALE AMENITIES Fit Off
|  |  |  | DDA |  |  | DDA Fit Off
Level 2
|  |  |  | Male Ammenities |  |  | MALE AMENITIES Fit Off
|  |  |  | Female Ammenities |  |  | FEMALE AMENITIES Fit Off
|  |  |  | DDA |  |  | DDA Fit Off
Level 3
301
[5 empty] | Kitchen |  | Kitchen Fit Off
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Fit Off
[5 empty] | Laundry |  | LAUNDRY Fit Off
302
[5 empty] | Kitchen |  | Kitchen Fit Off
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Fit Off
[5 empty] | Ensuite |  | ENSUITE Fit Off
[5 empty] | Laundry |  | LAUNDRY Fit Off
303
[5 empty] | Kitchen |  | Kitchen Fit Off
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Fit Off
[5 empty] | Laundry |  | LAUNDRY Fit Off
304
[5 empty] | Kitchen |  | Kitchen Fit Off
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Fit Off
[5 empty] | Laundry |  | LAUNDRY Fit Off
305
[5 empty] | Kitchen |  | Kitchen Fit Off
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Fit Off
[5 empty] | Laundry |  | LAUNDRY Fit Off
306
[5 empty] | Kitchen |  | Kitchen Fit Off
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Fit Off
[5 empty] | Laundry |  | LAUNDRY Fit Off
307
[5 empty] | Kitchen |  | Kitchen Fit Off
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Fit Off
[5 empty] | Ensuite |  | ENSUITE Fit Off
[5 empty] | Laundry |  | LAUNDRY Fit Off
|  |  |  | Gym DDA 1 |  |  | DDA Fit Off
|  |  |  | Gym DDA 2 |  |  | DDA Fit Off
Level 4
401
[5 empty] | Kitchen |  | Kitchen Fit Off
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Fit Off
[5 empty] | Laundry |  | LAUNDRY Fit Off
|  |  |  | 402 |  | same as 307 (includes ensuite)
|  |  |  | 403 |  | same as 401 (no ensuite)
|  |  |  | 404 |  | same as 401 (no ensuite)
|  |  |  | 405 |  | same as 401 (no ensuite)
|  |  |  | 406 |  | same as 307 (includes ensuite)
|  |  |  | 407 |  | same as 401 (no ensuite)
|  |  |  | 408 |  | same as 401 (no ensuite)
|  |  |  | 409 |  | same as 307 (includes ensuite)
|  |  |  | 410 |  | same as 401 (no ensuite)
|  |  |  | 411 |  | same as 401 (no ensuite)
|  |  |  | 412 |  | same as 401 (no ensuite)
|  |  |  | 413 |  | same as 401 (no ensuite)
|  |  |  | 414 |  | same as 307 (includes ensuite)
|  |  |  | 415 |  | same as 401 (no ensuite)
Level 5 -19
|  |  |  | 501 - 1901 |  | same as 401 (no ensuite)
|  |  |  | 502-1902 |  | same as 307 (includes ensuite)
|  |  |  | 503-1903 |  | same as 401 (no ensuite)
|  |  |  | 504-1904 |  | same as 401 (no ensuite)
|  |  |  | 505-1905 |  | same as 401 (no ensuite)
|  |  |  | 506-1906 |  | same as 307 (includes ensuite)
|  |  |  | 507-1907 |  | same as 401 (no ensuite)
|  |  |  | 508-1908 |  | same as 401 (no ensuite)
|  |  |  | 509-1909 |  | same as 307 (includes ensuite)
|  |  |  | 510-1910 |  | same as 401 (no ensuite)
|  |  |  | 511-1911 |  | same as 401 (no ensuite)
|  |  |  | 512-1912 |  | same as 401 (no ensuite)
|  |  |  | 513-1913 |  | same as 401 (no ensuite)
|  |  |  | 514-1914 |  | same as 307 (includes ensuite)
515-1915
Level 20-28
|  |  |  | 2001-2801 |  | same as 401 (no ensuite)
|  |  |  | 2002-2802 |  | same as 307 (includes ensuite)
|  |  |  | 2003-2803 |  | same as 401 (no ensuite)
|  |  |  | 2004-2804 |  | same as 401 (no ensuite)
|  |  |  | 2005-2805 |  | same as 401 (no ensuite)
|  |  |  | 2006-2806 |  | same as 307 (includes ensuite)
|  |  |  | 2007-2807 |  | same as 401 (no ensuite)
|  |  |  | 2008-2808 |  | same as 401 (no ensuite)
|  |  |  | 2009-2809 |  | same as 307 (includes ensuite)
|  |  |  | 2010-2810 |  | same as 401 (no ensuite)
|  |  |  | 2011-2811 |  | same as 401 (no ensuite)
|  |  |  | 2012-2812 |  | same as 401 (no ensuite)
|  |  |  | 2013-2813 |  | same as 401 (no ensuite)
|  |  |  | 2014-2814 |  | same as 307 (includes ensuite)
2015-2815
Level 29
|  |  |  | Ambulant 1 |  |  | BATHROOM 1 & 2 Fit Off
|  |  |  | Ambulant 2 |  |  | BATHROOM 1 & 2 Fit Off
|  |  |  | Cleaners Room |  |  | LAUNDRY Fit Off
|  |  |  | Private Dining |  |  | Kitchen Fit Off
|  |  |  | DDA 1 |  |  | DDA Fit Off
|  |  |  | DDA2 |  |  | DDA Fit Off
|  |  |  | Residental Bar |  |  | Kitchen Fit Off
Kitchen Fit Off
Commissioning
Ground Floor
|  |  |  | Male Ammenities |  |  | MALE AMENITIES Commissioning
|  |  |  | Female Ammenities |  |  | FEMALE AMENITIES Commissioning
|  |  |  | DDA |  |  | DDA Commissioning
|  |  |  | Lobby DDA |  |  | DDA Commissioning
|  |  |  | Fitness studio DDA |  |  | DDA Commissioning
Level 1
|  |  |  | Male Ammenities |  |  | MALE AMENITIES Commissioning
|  |  |  | Female Ammenties |  |  | FEMALE AMENITIES Commissioning
|  |  |  | DDA |  |  | DDA Commissioning
Level 2
|  |  |  | Male Ammenities |  |  | MALE AMENITIES Commissioning
|  |  |  | Female Ammenities |  |  | FEMALE AMENITIES Commissioning
|  |  |  | DDA |  |  | DDA Commissioning
Level 3
301
[5 empty] | Kitchen |  | KITCHEN Commissioning
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Commissioning
[5 empty] | Laundry |  | LAUNDRY Commissioning
302
[5 empty] | Kitchen |  | KITCHEN Commissioning
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Commissioning
[5 empty] | Ensuite |  | ENSUITE Commissioning
[5 empty] | Laundry |  | LAUNDRY Commissioning
303
[5 empty] | Kitchen |  | KITCHEN Commissioning
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Commissioning
[5 empty] | Laundry |  | LAUNDRY Commissioning
304
[5 empty] | Kitchen |  | KITCHEN Commissioning
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Commissioning
[5 empty] | Laundry |  | LAUNDRY Commissioning
305
[5 empty] | Kitchen |  | KITCHEN Commissioning
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Commissioning
[5 empty] | Laundry |  | LAUNDRY Commissioning
306
[5 empty] | Kitchen |  | KITCHEN Commissioning
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Commissioning
[5 empty] | Laundry |  | LAUNDRY Commissioning
307
[5 empty] | Kitchen |  | KITCHEN Commissioning
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Commissioning
[5 empty] | Ensuite |  | ENSUITE Commissioning
[5 empty] | Laundry |  | LAUNDRY Commissioning
|  |  |  | Gym DDA 1 |  |  | DDA Commissioning
|  |  |  | Gym DDA 2 |  |  | DDA Commissioning
Level 4
401
[5 empty] | Kitchen |  | KITCHEN Commissioning
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Commissioning
[5 empty] | Laundry |  | LAUNDRY Commissioning
|  |  |  | 402 |  | same as 307 (includes ensuite)
|  |  |  | 403 |  | same as 401 (no ensuite)
|  |  |  | 404 |  | same as 401 (no ensuite)
|  |  |  | 405 |  | same as 401 (no ensuite)
|  |  |  | 406 |  | same as 307 (includes ensuite)
|  |  |  | 407 |  | same as 401 (no ensuite)
|  |  |  | 408 |  | same as 401 (no ensuite)
|  |  |  | 409 |  | same as 307 (includes ensuite)
|  |  |  | 410 |  | same as 401 (no ensuite)
|  |  |  | 411 |  | same as 401 (no ensuite)
|  |  |  | 412 |  | same as 401 (no ensuite)
|  |  |  | 413 |  | same as 401 (no ensuite)
|  |  |  | 414 |  | same as 307 (includes ensuite)
|  |  |  | 415 |  | same as 401 (no ensuite)
Level 5 -19
|  |  |  | 501 - 1901 |  | same as 401 (no ensuite)
|  |  |  | 502-1902 |  | same as 401 (no ensuite)
|  |  |  | 503-1903 |  | same as 401 (no ensuite)
|  |  |  | 504-1904 |  | same as 401 (no ensuite)
|  |  |  | 505-1905 |  | same as 401 (no ensuite)
|  |  |  | 506-1906 |  | same as 307 (includes ensuite)
|  |  |  | 507-1907 |  | same as 401 (no ensuite)
|  |  |  | 508-1908 |  | same as 401 (no ensuite)
|  |  |  | 509-1909 |  | same as 307 (includes ensuite)
|  |  |  | 510-1910 |  | same as 401 (no ensuite)
|  |  |  | 511-1911 |  | same as 401 (no ensuite)
|  |  |  | 512-1912 |  | same as 401 (no ensuite)
|  |  |  | 513-1913 |  | same as 401 (no ensuite)
|  |  |  | 514-1914 |  | same as 307 (includes ensuite)
515-1915
Level 20-28
|  |  |  | 2001-2801 |  | same as 401 (no ensuite)
|  |  |  | 2002-2802 |  | same as 307 (includes ensuite)
|  |  |  | 2003-2803 |  | same as 401 (no ensuite)
|  |  |  | 2004-2804 |  | same as 401 (no ensuite)
|  |  |  | 2005-2805 |  | same as 401 (no ensuite)
|  |  |  | 2006-2806 |  | same as 307 (includes ensuite)
|  |  |  | 2007-2807 |  | same as 401 (no ensuite)
|  |  |  | 2008-2808 |  | same as 401 (no ensuite)
|  |  |  | 2009-2809 |  | same as 307 (includes ensuite)
|  |  |  | 2010-2810 |  | same as 401 (no ensuite)
|  |  |  | 2011-2811 |  | same as 401 (no ensuite)
|  |  |  | 2012-2812 |  | same as 401 (no ensuite)
|  |  |  | 2013-2813 |  | same as 401 (no ensuite)
|  |  |  | 2014-2814 |  | same as 307 (includes ensuite)
2015-2815
Level 29
|  |  |  | Ambulant 1 |  |  | BATHROOM 1 & 2 Commissioning
|  |  |  | Ambulant 2 |  |  | BATHROOM 1 & 2 Commissioning
|  |  |  | Cleaners Room |  |  | LAUNDRY Commissioning
|  |  |  | Private Dining |  |  | KITCHEN Commissioning
|  |  |  | DDA 1 |  |  | DDA Commissioning
|  |  |  | DDA2 |  |  | DDA Commissioning
|  |  |  | Residental Bar |  |  | KITCHEN Commissioning
Penetrations
Ground Floor
|  |  |  | Male Ammenities |  |  | Penetrations
|  |  |  | Female Ammenities |  |  | Penetrations
|  |  |  | DDA |  |  | Penetrations
|  |  |  | Lobby DDA |  |  | Penetrations
|  |  |  | Fitness studio DDA |  |  | Penetrations
Level 1
|  |  |  | Male Ammenities |  |  | Penetrations
|  |  |  | Female Ammenties |  |  | Penetrations
|  |  |  | DDA |  |  | Penetrations
Level 2
|  |  |  | Male Ammenities |  |  | Penetrations
|  |  |  | Female Ammenities |  |  | Penetrations
|  |  |  | DDA |  |  | Penetrations
Level 3
|  |  |  | 301 |  |  | Penetrations
|  |  |  | 302 |  |  | Penetrations
|  |  |  | 303 |  |  | Penetrations
|  |  |  | 304 |  |  | Penetrations
|  |  |  | 305 |  |  | Penetrations
|  |  |  | 306 |  |  | Penetrations
|  |  |  | 307 |  |  | Penetrations
|  |  |  | Gym DDA 1 |  |  | Penetrations
|  |  |  | Gym DDA 2 |  |  | Penetrations
Level 4
|  |  |  | Pour 1 APT 10-15 |  |  | Penetrations
|  |  |  | Pour 2 APT 1-9 |  |  | Penetrations
Level 5 -19
|  |  |  | Pour 1 APT 10-15 |  | break down into each apartment per level - follows same sequence | Penetrations
|  |  |  | Pour 2 APT 1-9 |  | break down into each apartment per level - follows same sequence | Penetrations
Level 20-28
|  |  |  | Pour 1 APT 10-15 |  | break down into each apartment per level - follows same sequence | Penetrations
|  |  |  | Pour 2 APT 1-9 |  | break down into each apartment per level - follows same sequence | Penetrations
Level 29
|  |  |  | Ambulant 1 |  |  | Penetrations
|  |  |  | Ambulant 2 |  |  | Penetrations
|  |  |  | Cleaners Room |  |  | Penetrations
|  |  |  | Private Dining |  |  | Penetrations
|  |  |  | DDA 1 |  |  | Penetrations
|  |  |  | DDA2 |  |  | Penetrations
|  |  |  | Residental Bar |  |  | Penetrations
|  |  | Roof |  |  |  | Penetrations
|  |  | Lift Overrun |  |  |  | Penetrations
Claremont Tower
Corridors
|  |  | Level 1 |  |  |  | Corridors
|  |  | Level 2 |  |  |  | Corridors
|  |  | Level 3-11 |  |  |  | Corridors
|  |  | Level 12-15 |  |  |  | Corridors
|  |  | Level 17-19 |  |  |  | Corridors
|  |  | Level 20 |  |  |  | Corridors
Meter Assembilies & Risers
|  |  | Basement 2 |  |  |  | Meter Assemblies & Risers
|  |  | Basement 1 |  |  |  | Meter Assemblies & Risers
|  |  | Ground Floor |  |  |  | Meter Assemblies & Risers
|  |  | Level 1 |  |  |  | Meter Assemblies & Risers
|  |  | Level 2 |  |  |  | Meter Assemblies & Risers
|  |  | Level 3-11 |  |  |  | Meter Assemblies & Risers
|  |  | Level 12-15 |  |  |  | Meter Assemblies & Risers
|  |  | Level 16 |  |  |  | Meter Assemblies & Risers
|  |  | Level 17-19 |  |  |  | Meter Assemblies & Risers
|  |  | Level 20 |  |  |  | Meter Assemblies & Risers
|  |  | Level 21 |  |  |  | Meter Assemblies & Risers
Lagging
|  |  | Basement 2 |  |  |  | Lagging
|  |  | Basement 1 |  |  |  | Lagging
|  |  | Ground Floor |  |  |  | Lagging
|  |  | Level 1 |  |  |  | Lagging
|  |  | Level 2 |  |  |  | Lagging
|  |  | Level 3-11 |  |  |  | Lagging
|  |  | Level 12-15 |  |  |  | Lagging
|  |  | Level 16 |  |  |  | Lagging
|  |  | Level 17-19 |  |  |  | Lagging
|  |  | Level 20 |  |  |  | Lagging
|  |  | Level 21 |  |  |  | Lagging
Drains
|  |  | Basement 2 |  |  |  | Drains
|  |  | Basement 1 |  |  |  | Drains
|  |  | Ground Floor |  |  |  | Drains
|  |  | Level 1 |  |  |  | Drains
|  |  | Level 2 |  |  |  | Drains
|  |  | Level 3-11 |  |  |  | Drains
|  |  | Level 12-15 |  |  |  | Drains
|  |  | Level 16 |  |  |  | Drains
|  |  | Level 17-19 |  |  |  | Drains
|  |  | Level 20 |  |  |  | Drains
Level 21
Rough In
Ground Floor
|  |  |  | Office DDA |  |  | Rough In
|  |  |  | Lobby DDA |  |  | Rough In
Level 1
|  |  |  | 101 |  |  | Rough In
|  |  |  | 102 |  |  | Rough In
|  |  |  | 103 |  |  | Rough In
|  |  |  | 104 |  |  | Rough In
|  |  |  | 105 |  |  | Rough In
|  |  |  | 106 |  |  | Rough In
|  |  |  | 107 |  |  | Rough In
|  |  |  | 108 |  |  | Rough In
|  |  |  | 109 |  |  | Rough In
|  |  |  | Co-Working DDA |  |  | Rough In
|  |  |  | Co-Working Kitchen |  |  | Rough In
Level 2
|  |  |  | 201 |  |  | Rough In
|  |  |  | 202 |  |  | Rough In
|  |  |  | 203 |  |  | Rough In
|  |  |  | 204 |  |  | Rough In
|  |  |  | 205 |  |  | Rough In
|  |  |  | 206 |  |  | Rough In
|  |  |  | 207 |  |  | Rough In
|  |  |  | 208 |  |  | Rough In
|  |  |  | 209 |  |  | Rough In
|  |  |  | 210 |  |  | Rough In
|  |  |  | 211 |  |  | Rough In
|  |  |  | 212 |  |  | Rough In
|  |  |  | 213 |  |  | Rough In
|  |  |  | 214 |  |  | Rough In
|  |  |  | 215 |  |  | Rough In
Level 3-11
|  |  |  | 301-1101 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 302-1102 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 303-1103 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 304-1104 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 305-1105 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 306-1106 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 307-1107 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 308-1108 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 309-1109 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 310-1110 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 311-1111 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 312-1112 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 313-1113 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 314-1114 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 315-1115 |  | break down into each apartment per level - follows same sequence | Rough In
Level 12-15
|  |  |  | 1201-1501 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 1202-1502 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 1203-1503 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 1204-1504 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 1205-1505 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 1206-1506 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 1207-1507 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 1208-1508 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 1209-1509 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 1210-1510 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 1211-1511 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 1212-1511 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 1213-1513 |  | break down into each apartment per level - follows same sequence | Rough In
Level 16
|  |  |  | Demo Kitchen |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | Private Dining 1 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | Private Dining 2 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | Co-Working |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | Resident Club Lounge |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | DDA |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | Cleaners Room |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | Ambulant |  | break down into each apartment per level - follows same sequence | Rough In
Level 17-19
|  |  |  | 1701-1901 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 1702-1902 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 1703-1903 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 1704-1904 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 1705-1905 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 1706-1906 |  | break down into each apartment per level - follows same sequence | Rough In
Level 20
|  |  |  | 2001 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 2002 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 2003 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 2004 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 2005 |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | 2006 |  | break down into each apartment per level - follows same sequence | Rough In
Level 21
|  |  |  | Powder Room |  | break down into each apartment per level - follows same sequence | Rough In
|  |  |  | DDA |  | break down into each apartment per level - follows same sequence | Rough In
Fit Off
Ground Floor
|  |  |  | Office DDA |  |  | DDA Fit Off
|  |  |  | Lobby DDA |  |  | DDA Fit Off
Level 1
101
[5 empty] | Kitchen |  | Kitchen Fit Off
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Fit Off
[5 empty] | Laundry |  | LAUNDRY Fit Off
|  |  |  | 102 |  | same as 101 (includes laundry)
103
[5 empty] | Kitchen |  | Kitchen Fit Off
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Fit Off
|  |  |  | 104 |  | same as 103 (no laundry)
|  |  |  | 105 |  | same as 103 (no laundry)
|  |  |  | 106 |  | same as 103 (no laundry)
|  |  |  | 107 |  | same as 103 (no laundry)
|  |  |  | 108 |  | same as 103 (no laundry)
|  |  |  | 109 |  | same as 103 (no laundry)
|  |  |  | Co-Working DDA |  |  | DDA Fit Off
|  |  |  | Co-Working Kitchen |  |  | Kitchen Fit Off
Level 2
|  |  |  | 201 |  | same as 101 (includes laundry)
|  |  |  | 202 |  | same as 103 (no laundry)
|  |  |  | 203 |  | same as 103 (no laundry)
|  |  |  | 204 |  | same as 103 (no laundry)
|  |  |  | 205 |  | same as 103 (no laundry)
|  |  |  | 206 |  | same as 103 (no laundry)
|  |  |  | 207 |  | same as 103 (no laundry)
|  |  |  | 208 |  | same as 103 (no laundry)
|  |  |  | 209 |  | same as 101 (includes laundry)
|  |  |  | 210 |  | same as 103 (no laundry)
|  |  |  | 211 |  | same as 103 (no laundry)
|  |  |  | 212 |  | same as 101 (includes laundry)
|  |  |  | 213 |  | same as 101 (includes laundry)
|  |  |  | 214 |  | same as 103 (no laundry)
|  |  |  | 215 |  | same as 103 (no laundry)
Level 3-11
301-1101
[5 empty] | Kitchen |  | Kitchen Fit Off
[5 empty] | Ensuite |  | ENSUITE Fit Off
[5 empty] | Laundry |  | LAUNDRY Fit Off
302-1102
[5 empty] | Kitchen |  | Kitchen Fit Off
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Fit Off
|  |  |  | 303-1103 |  | same as 302
|  |  |  | 304-1104 |  | same as 302
|  |  |  | 305-1105 |  | same as 302
|  |  |  | 306-1106 |  | same as 302
|  |  |  | 307-1107 |  | same as 302
|  |  |  | 308-1108 |  | same as 302
309-1109
[5 empty] | Kitchen |  | Kitchen Fit Off
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Fit Off
[5 empty] | Ensuite |  | ENSUITE Fit Off
[5 empty] | Laundry |  | LAUNDRY Fit Off
|  |  |  | 310-1110 |  | same as 302
|  |  |  | 311-1111 |  | same as 302
312-1112
[5 empty] | Kitchen |  | Kitchen Fit Off
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Fit Off
[5 empty] | Laundry |  | LAUNDRY Fit Off
|  |  |  | 313-1113 |  | same as 312
|  |  |  | 314-1114 |  | same as 302
|  |  |  | 315-1115 |  | same as 302
Level 12-15
|  |  |  | 1201-1501 |  | same as 301
|  |  |  | 1202-1502 |  | same as 302
|  |  |  | 1203-1503 |  | same as 302
|  |  |  | 1204-1504 |  | same as 302
|  |  |  | 1205-1505 |  | same as 302
|  |  |  | 1206-1506 |  | same as 302
|  |  |  | 1207-1507 |  | same as 302
|  |  |  | 1208-1508 |  | same as 302
|  |  |  | 1209-1509 |  | same as 301
|  |  |  | 1210-1510 |  | same as 309
|  |  |  | 1211-1511 |  | same as 312
|  |  |  | 1212-1511 |  | same as 312
|  |  |  | 1213-1513 |  | same as 309
Level 16
|  |  |  | Demo Kitchen |  |  | Kitchen Fit Off
|  |  |  | Private Dining 1 |  |  | Kitchen Fit Off
|  |  |  | Private Dining 2 |  |  | Kitchen Fit Off
|  |  |  | Co-Working |  |  | Kitchen Fit Off
|  |  |  | Resident Club Lounge |  |  | Kitchen Fit Off
|  |  |  | DDA |  |  | DDA Fit Off
|  |  |  | Cleaners Room |  |  | LAUNDRY Fit Off
|  |  |  | Ambulant |  |  | BATHROOM 1 & 2 Fit Off
Level 17-19
|  |  |  | 1701-1901 |  | same as 312
|  |  |  | 1702-1902 |  | same as 309
|  |  |  | 1703-1903 |  | same as 309
|  |  |  | 1704-1904 |  | same as 312
|  |  |  | 1705-1905 |  | same as 309
|  |  |  | 1706-1906 |  | same as 309
Level 20
|  |  |  | 2001 |  | same as 312
|  |  |  | 2002 |  | same as 309
|  |  |  | 2003 |  | same as 309
|  |  |  | 2004 |  | same as 312
|  |  |  | 2005 |  | same as 309
|  |  |  | 2006 |  | same as 309
Level 21
|  |  |  | Powder Room |  |  | POWDER ROOM Fit Off
|  |  |  | DDA |  |  | DDA Fit Off
Commissioning
Ground Floor
|  |  |  | Office DDA |  |  | DDA Commissioning
|  |  |  | Lobby DDA |  |  | DDA Commissioning
Level 1
101
[5 empty] | Kitchen |  | KITCHEN Commissioning
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Commissioning
[5 empty] | Laundry |  | LAUNDRY Commissioning
|  |  |  | 102 |  | same as 101 (includes laundry)
103
[5 empty] | Kitchen |  | KITCHEN Commissioning
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Commissioning
|  |  |  | 104 |  | same as 103 (no laundry)
|  |  |  | 105 |  | same as 103 (no laundry)
|  |  |  | 106 |  | same as 103 (no laundry)
|  |  |  | 107 |  | same as 103 (no laundry)
|  |  |  | 108 |  | same as 103 (no laundry)
|  |  |  | 109 |  | same as 103 (no laundry)
|  |  |  | Co-Working DDA |  |  | DDA Commissioning
|  |  |  | Co-Working Kitchen |  |  | KITCHEN Commissioning
Level 2
|  |  |  | 201 |  | same as 101 (includes laundry)
|  |  |  | 202 |  | same as 103 (no laundry)
|  |  |  | 203 |  | same as 103 (no laundry)
|  |  |  | 204 |  | same as 103 (no laundry)
|  |  |  | 205 |  | same as 103 (no laundry)
|  |  |  | 206 |  | same as 103 (no laundry)
|  |  |  | 207 |  | same as 103 (no laundry)
|  |  |  | 208 |  | same as 103 (no laundry)
|  |  |  | 209 |  | same as 101 (includes laundry)
|  |  |  | 210 |  | same as 103 (no laundry)
|  |  |  | 211 |  | same as 103 (no laundry)
|  |  |  | 212 |  | same as 101 (includes laundry)
|  |  |  | 213 |  | same as 101 (includes laundry)
|  |  |  | 214 |  | same as 103 (no laundry)
|  |  |  | 215 |  | same as 103 (no laundry)
Level 3-11
301-1101
[5 empty] | Kitchen |  | KITCHEN Commissioning
[5 empty] | Ensuite |  | ENSUITE Commissioning
[5 empty] | Laundry |  | LAUNDRY Commissioning
302-1102
[5 empty] | Kitchen |  | KITCHEN Commissioning
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Commissioning
|  |  |  | 303-1103 |  | same as 302
|  |  |  | 304-1104 |  | same as 302
|  |  |  | 305-1105 |  | same as 302
|  |  |  | 306-1106 |  | same as 302
|  |  |  | 307-1107 |  | same as 302
|  |  |  | 308-1108 |  | same as 302
309-1109
[5 empty] | Kitchen |  | KITCHEN Commissioning
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Commissioning
[5 empty] | Ensuite |  | ENSUITE Commissioning
[5 empty] | Laundry |  | LAUNDRY Commissioning
|  |  |  | 310-1110 |  | same as 302
|  |  |  | 311-1111 |  | same as 302
312-1112
[5 empty] | Kitchen |  | KITCHEN Commissioning
[5 empty] | Bathroom |  | BATHROOM 1 & 2 Commissioning
[5 empty] | Laundry |  | LAUNDRY Commissioning
|  |  |  | 313-1113 |  | same as 312
|  |  |  | 314-1114 |  | same as 302
|  |  |  | 315-1115 |  | same as 302
Level 12-15
|  |  |  | 1201-1501 |  | same as 301
|  |  |  | 1202-1502 |  | same as 302
|  |  |  | 1203-1503 |  | same as 302
|  |  |  | 1204-1504 |  | same as 302
|  |  |  | 1205-1505 |  | same as 302
|  |  |  | 1206-1506 |  | same as 302
|  |  |  | 1207-1507 |  | same as 302
|  |  |  | 1208-1508 |  | same as 302
|  |  |  | 1209-1509 |  | same as 301
|  |  |  | 1210-1510 |  | same as 309
|  |  |  | 1211-1511 |  | same as 312
|  |  |  | 1212-1511 |  | same as 312
|  |  |  | 1213-1513 |  | same as 309
Level 16
|  |  |  | Demo Kitchen |  |  | KITCHEN Commissioning
|  |  |  | Private Dining 1 |  |  | KITCHEN Commissioning
|  |  |  | Private Dining 2 |  |  | KITCHEN Commissioning
|  |  |  | Co-Working |  |  | KITCHEN Commissioning
|  |  |  | Resident Club Lounge |  |  | KITCHEN Commissioning
|  |  |  | DDA |  |  | DDA Commissioning
|  |  |  | Cleaners Room |  |  | LAUNDRY Commissioning
|  |  |  | Ambulant |  |  | BATHROOM 1 & 2 Commissioning
Level 17-19
|  |  |  | 1701-1901 |  | same as 312
|  |  |  | 1702-1902 |  | same as 309
|  |  |  | 1703-1903 |  | same as 309
|  |  |  | 1704-1904 |  | same as 312
|  |  |  | 1705-1905 |  | same as 309
|  |  |  | 1706-1906 |  | same as 309
Level 20
|  |  |  | 2001 |  | same as 312
|  |  |  | 2002 |  | same as 309
|  |  |  | 2003 |  | same as 309
|  |  |  | 2004 |  | same as 312
|  |  |  | 2005 |  | same as 309
|  |  |  | 2006 |  | same as 309
Level 21
|  |  |  | Powder Room |  |  | POWDER ROOM Commissioning
|  |  |  | DDA |  |  | DDA Commissioning
Penetrations
Ground Floor
|  |  |  | Office DDA |  |  | Penetrations
|  |  |  | Lobby DDA |  |  | Penetrations
Level 1
|  |  |  | 101 |  |  | Penetrations
|  |  |  | 102 |  |  | Penetrations
|  |  |  | 103 |  |  | Penetrations
|  |  |  | 104 |  |  | Penetrations
|  |  |  | 105 |  |  | Penetrations
|  |  |  | 106 |  |  | Penetrations
|  |  |  | 107 |  |  | Penetrations
|  |  |  | 108 |  |  | Penetrations
|  |  |  | 109 |  |  | Penetrations
|  |  |  | Co-Working DDA |  |  | Penetrations
|  |  |  | Co-Working Kitchen |  |  | Penetrations
Level 2
|  |  |  | 201 |  |  | Penetrations
|  |  |  | 202 |  |  | Penetrations
|  |  |  | 203 |  |  | Penetrations
|  |  |  | 204 |  |  | Penetrations
|  |  |  | 205 |  |  | Penetrations
|  |  |  | 206 |  |  | Penetrations
|  |  |  | 207 |  |  | Penetrations
|  |  |  | 208 |  |  | Penetrations
|  |  |  | 209 |  |  | Penetrations
|  |  |  | 210 |  |  | Penetrations
|  |  |  | 211 |  |  | Penetrations
|  |  |  | 212 |  |  | Penetrations
|  |  |  | 213 |  |  | Penetrations
|  |  |  | 214 |  |  | Penetrations
|  |  |  | 215 |  |  | Penetrations
Level 3-11
|  |  |  | Pour 1 APT 9-15 |  | break down into each apartment per level - follows same sequence | Penetrations
|  |  |  | Pour 2 APT 1-8 |  | break down into each apartment per level - follows same sequence | Penetrations
Level 12-15
|  |  |  | Pour 1 APT 9-15 |  | break down into each apartment per level - follows same sequence | Penetrations
|  |  |  | Pour 2 APT 1-8 |  | break down into each apartment per level - follows same sequence | Penetrations
Level 16
|  |  |  | Demo Kitchen |  | break down into each apartment per level - follows same sequence | Penetrations
|  |  |  | Private Dining 1 |  | break down into each apartment per level - follows same sequence | Penetrations
|  |  |  | Private Dining 2 |  | break down into each apartment per level - follows same sequence | Penetrations
|  |  |  | Co-Working |  | break down into each apartment per level - follows same sequence | Penetrations
|  |  |  | Resident Club Lounge |  | break down into each apartment per level - follows same sequence | Penetrations
|  |  |  | DDA |  | break down into each apartment per level - follows same sequence | Penetrations
|  |  |  | Cleaners Room |  | break down into each apartment per level - follows same sequence | Penetrations
|  |  |  | Ambulant |  | break down into each apartment per level - follows same sequence | Penetrations
Level 17-19
|  |  |  | Pour 1 APT 1-6 |  | break down into each apartment per level - follows same sequence | Penetrations
Level 20
|  |  |  | Pour 1 APT 1-6 |  | break down into each apartment per level - follows same sequence | Penetrations
Level 21
|  |  |  | Powder Room |  | break down into each apartment per level - follows same sequence | Penetrations
|  |  |  | DDA |  | break down into each apartment per level - follows same sequence | Penetrations
Camera of drains
Yarra Tower
Ground Floor
|  |  |  | Male Ammenities |  |  | Camera of Drains
|  |  |  | Female Ammenities |  |  | Camera of Drains
|  |  |  | DDA |  |  | Camera of Drains
|  |  |  | Lobby DDA |  |  | Camera of Drains
Fitness studio DDA
Level 1
|  |  |  | Male Ammenities |  |  | Camera of Drains
|  |  |  | Female Ammenties |  |  | Camera of Drains
|  |  |  | DDA |  |  | Camera of Drains
Level 2
|  |  |  | Male Ammenities |  |  | Camera of Drains
|  |  |  | Female Ammenities |  |  | Camera of Drains
|  |  |  | DDA |  |  | Camera of Drains
Level 3
|  |  |  | 301 |  |  | Camera of Drains
|  |  |  | 302 |  |  | Camera of Drains
|  |  |  | 303 |  |  | Camera of Drains
|  |  |  | 304 |  |  | Camera of Drains
|  |  |  | 305 |  |  | Camera of Drains
|  |  |  | 306 |  |  | Camera of Drains
|  |  |  | 307 |  |  | Camera of Drains
|  |  |  | Gym DDA 1 |  |  | Camera of Drains
|  |  |  | Gym DDA 2 |  |  | Camera of Drains
Level 4
|  |  |  | 401 |  |  | Camera of Drains
|  |  |  | 402 |  |  | Camera of Drains
|  |  |  | 403 |  |  | Camera of Drains
|  |  |  | 404 |  |  | Camera of Drains
|  |  |  | 405 |  |  | Camera of Drains
|  |  |  | 406 |  |  | Camera of Drains
|  |  |  | 407 |  |  | Camera of Drains
|  |  |  | 408 |  |  | Camera of Drains
|  |  |  | 409 |  |  | Camera of Drains
|  |  |  | 410 |  |  | Camera of Drains
|  |  |  | 411 |  |  | Camera of Drains
|  |  |  | 412 |  |  | Camera of Drains
|  |  |  | 413 |  |  | Camera of Drains
|  |  |  | 414 |  |  | Camera of Drains
|  |  |  | 415 |  |  | Camera of Drains
Level 5 -19
|  |  |  | 501 - 1901 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 502-1902 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 503-1903 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 504-1904 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 505-1905 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 506-1906 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 507-1907 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 508-1908 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 509-1909 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 510-1910 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 511-1911 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 512-1912 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 513-1913 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 514-1914 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 515-1915 |  | break down into each apartment per level - follows same sequence | Camera of Drains
Level 20-28
|  |  |  | 2001-2801 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 2002-2802 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 2003-2803 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 2004-2804 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 2005-2805 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 2006-2806 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 2007-2807 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 2008-2808 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 2009-2809 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 2010-2810 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 2011-2811 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 2012-2812 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 2013-2813 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 2014-2814 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 2015-2815 |  | break down into each apartment per level - follows same sequence | Camera of Drains
Level 29
|  |  |  | Ambulant 1 |  |  | Camera of Drains
|  |  |  | Ambulant 2 |  |  | Camera of Drains
|  |  |  | Cleaners Room |  |  | Camera of Drains
|  |  |  | Private Dining |  |  | Camera of Drains
|  |  |  | DDA 1 |  |  | Camera of Drains
|  |  |  | DDA2 |  |  | Camera of Drains
|  |  |  | Residental Bar |  |  | Camera of Drains
Claremont Tower
Ground Floor
|  |  |  | Office DDA |  |  | Camera of Drains
|  |  |  | Lobby DDA |  |  | Camera of Drains
Level 1
|  |  |  | 101 |  |  | Camera of Drains
|  |  |  | 102 |  |  | Camera of Drains
|  |  |  | 103 |  |  | Camera of Drains
|  |  |  | 104 |  |  | Camera of Drains
|  |  |  | 105 |  |  | Camera of Drains
|  |  |  | 106 |  |  | Camera of Drains
|  |  |  | 107 |  |  | Camera of Drains
|  |  |  | 108 |  |  | Camera of Drains
|  |  |  | 109 |  |  | Camera of Drains
|  |  |  | Co-Working DDA |  |  | Camera of Drains
|  |  |  | Co-Working Kitchen |  |  | Camera of Drains
Level 2
|  |  |  | 201 |  |  | Camera of Drains
|  |  |  | 202 |  |  | Camera of Drains
|  |  |  | 203 |  |  | Camera of Drains
|  |  |  | 204 |  |  | Camera of Drains
|  |  |  | 205 |  |  | Camera of Drains
|  |  |  | 206 |  |  | Camera of Drains
|  |  |  | 207 |  |  | Camera of Drains
|  |  |  | 208 |  |  | Camera of Drains
|  |  |  | 209 |  |  | Camera of Drains
|  |  |  | 210 |  |  | Camera of Drains
|  |  |  | 211 |  |  | Camera of Drains
|  |  |  | 212 |  |  | Camera of Drains
|  |  |  | 213 |  |  | Camera of Drains
|  |  |  | 214 |  |  | Camera of Drains
|  |  |  | 215 |  |  | Camera of Drains
Level 3-11
|  |  |  | 301-1101 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 302-1102 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 303-1103 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 304-1104 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 305-1105 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 306-1106 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 307-1107 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 308-1108 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 309-1109 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 310-1110 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 311-1111 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 312-1112 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 313-1113 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 314-1114 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 315-1115 |  | break down into each apartment per level - follows same sequence | Camera of Drains
Level 12-15
|  |  |  | 1201-1501 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 1202-1502 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 1203-1503 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 1204-1504 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 1205-1505 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 1206-1506 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 1207-1507 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 1208-1508 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 1209-1509 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 1210-1510 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 1211-1511 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 1212-1511 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 1213-1513 |  | break down into each apartment per level - follows same sequence | Camera of Drains
Level 16
|  |  |  | Demo Kitchen |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | Private Dining 1 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | Private Dining 2 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | Co-Working |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | Resident Club Lounge |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | DDA |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | Cleaners Room |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | Ambulant |  | break down into each apartment per level - follows same sequence | Camera of Drains
Level 17-19
|  |  |  | 1701-1901 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 1702-1902 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 1703-1903 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 1704-1904 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 1705-1905 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 1706-1906 |  | break down into each apartment per level - follows same sequence | Camera of Drains
Level 20
|  |  |  | 2001 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 2002 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 2003 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 2004 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 2005 |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | 2006 |  | break down into each apartment per level - follows same sequence | Camera of Drains
Level 21
|  |  |  | Powder Room |  | break down into each apartment per level - follows same sequence | Camera of Drains
|  |  |  | DDA |  | break down into each apartment per level - follows same sequence | Camera of Drains
BMS Meters
Yarra Tower
|  |  | Y-CWM-B1 - Maintenance Sink |  |  |  | Meters
|  |  | Y-CWM-B2-RW Plant |  |  |  | Meters
|  |  | Y-CWM-B2-RW Plant Auto changeover |  |  |  | Meters
|  |  | Y-CWM-G-Bike Wash |  |  |  | Meters
|  |  | Y-CWM-G-BinWash |  |  |  | Meters
|  |  | Y-CWM-G-Concierge |  |  |  | Meters
|  |  | Y-CWM-G-DDA |  |  |  | Meters
|  |  | Y-CWM-G-EOT |  |  |  | Meters
|  |  | Y-CWM-L01-Office Amenities |  |  |  | Meters
|  |  | Y-CWM-L02-Office Amenities |  |  |  | Meters
|  |  | Y-CWM-L03 Gym/Yoga Amenities |  |  |  | Meters
|  |  | Y-CWM-L03 |  |  |  | Meters
|  |  | Y-CWM-L04 |  |  |  | Meters
|  |  | Y-CWM-L05 |  |  |  | Meters
|  |  | Y-CWM-L06 |  |  |  | Meters
|  |  | Y-CWM-L07 |  |  |  | Meters
|  |  | Y-CWM-L08 |  |  |  | Meters
|  |  | Y-CWM-L09 |  |  |  | Meters
|  |  | Y-CWM-L10 |  |  |  | Meters
|  |  | Y-CWM-L11 |  |  |  | Meters
|  |  | Y-CWM-L12 |  |  |  | Meters
|  |  | Y-CWM-L13 |  |  |  | Meters
|  |  | Y-CWM-L14 |  |  |  | Meters
|  |  | Y-CWM-L15 |  |  |  | Meters
|  |  | Y-CWM-L16 |  |  |  | Meters
|  |  | Y-CWM-L17 |  |  |  | Meters
|  |  | Y-CWM-L18 |  |  |  | Meters
|  |  | Y-CWM-L19 |  |  |  | Meters
|  |  | Y-CWM-L20 |  |  |  | Meters
|  |  | Y-CWM-L21 |  |  |  | Meters
|  |  | Y-CWM-L22 |  |  |  | Meters
|  |  | Y-CWM-L23 |  |  |  | Meters
|  |  | Y-CWM-L24 |  |  |  | Meters
|  |  | Y-CWM-L25 |  |  |  | Meters
|  |  | Y-CWM-L26 |  |  |  | Meters
|  |  | Y-CWM-L27 |  |  |  | Meters
|  |  | Y-CWM-L28 |  |  |  | Meters
|  |  | Y-CWM-L29-Residential Amenities/Irrigation |  |  |  | Meters
|  |  | Y-CWM-R-Pool |  |  |  | Meters
Claremont Tower
|  |  | C-CWM-B1- DDA |  |  |  | Meters
|  |  | C-CWM-B1- GIT Room |  |  |  | Meters
|  |  | C-CWM-B1- Laundry |  |  |  | Meters
|  |  | C-CWM-B1- Staff Room |  |  |  | Meters
|  |  | C-CWM-G- Binwash |  |  |  | Meters
|  |  | C-CWM-G- DDA |  |  |  | Meters
|  |  | C-CWM-G- Pet grooming |  |  |  | Meters
|  |  | C-CWM-L01 |  |  |  | Meters
|  |  | C-CWM-L02 |  |  |  | Meters
|  |  | C-CWM-L03 |  |  |  | Meters
|  |  | C-CWM-L04 |  |  |  | Meters
|  |  | C-CWM-L05 |  |  |  | Meters
|  |  | C-CWM-L06 |  |  |  | Meters
|  |  | C-CWM-L07 |  |  |  | Meters
|  |  | C-CWM-L08 |  |  |  | Meters
|  |  | C-CWM-L09 |  |  |  | Meters
|  |  | C-CWM-L10 |  |  |  | Meters
|  |  | C-CWM-L11 |  |  |  | Meters
|  |  | C-CWM-L12 |  |  |  | Meters
|  |  | C-CWM-L13 |  |  |  | Meters
|  |  | C-CWM-L14 |  |  |  | Meters
|  |  | C-CWM-L15 |  |  |  | Meters
|  |  | C-CWM-L16 Residential Amenities |  |  |  | Meters
|  |  | C-CWM-L16 |  |  |  | Meters
|  |  | C-CWM-L16 - Private dining |  |  |  | Meters
|  |  | C-CWM-L17 |  |  |  | Meters
|  |  | C-CWM-L18 |  |  |  | Meters
|  |  | C-CWM-L19 |  |  |  | Meters
|  |  | C-CWM-L20 |  |  |  | Meters
|  |  | C-CWM-R-Roof Amenities |  |  |  | Meters

## Checklist
type | name | values | prefix | postfix | usage count | user addable
checklist | Meters
checkpoint | Meter ID
checkpoint | Bolts seated
checkpoint | Rubber Centered
checkpoint | Tagged
Section | Water Test
checkpoint | Meter reading prior to test
checkpoint | Meter reading after 5 litre test
checklist | Camera of Drains
checkpoint | Have the drains been inspected via camera
checkpoint | Are the drains clear of debris
checklist | Balconies
checkpoint | DOWNPIPE ON |  | CAN THESE BE REOMOVED FROM ALL FITOFF SECTIONS
checkpoint | D/P CLIPPED
checkpoint | FW installed and clear of debris
checkpoint | O/F installed and clear of debris
checklist | Corridors
checkpoint | Hot Water
checkpoint | Cold Water
checkpoint | Hot Water Lagging
checkpoint | Testing
checkpoint | Pipes clipped
checkpoint | Valves Tagged
checkpoint | Hot Water Meters Installed
checkpoint | Photos must be attached
checklist | Meter Assemblies & Risers
checkpoint | Valves Tagged
checkpoint | Balancing Valve Installed
checkpoint | Flow Isolation Valve Installed
checkpoint | Meters on
checkpoint | Assembly Complete
checkpoint | Hot Water Riser Complete
checkpoint | Pipe Support
checkpoint | Caulk Penetrations
checkpoint | Syfonic System Complete
Checkpoint | Lagging
checkpoint | Lagging Complete
checkpoint | Photos must be attached
Checklist | Drains
checkpoint | All drains installed as per Plan referenced on spreadsheet
checkpoint | Caulking Complete
checkpoint | Photos must be attached
Checklist | Penetrations
checkpoint | Slab Penetrations (All slab penetations installed as per Plan)
checkpoint | Rough In
checkpoint | UN-USED PENO'S SEALED
checkpoint | ROUGH IN COMPLETE
checkpoint | HEADER PIPES FIRE CAULKED
checkpoint | TMV ACCESSIBLE TO A/P
checkpoint | CROSS CONNECTIONS
checkpoint | MIXER STRAIGHT, SET BACK CORRECT
checkpoint | WATER PRESSURE TESTED
checkpoint | ROLL OVERS COMPLETE AND SECURE
checkpoint | AREA CLEAN OF MATERIALS
checkpoint | FW CLEANNED, COVERED AND CLEAR OF DEBRIS
checkpoint | AAV REQUIRED?
checkpoint | FIXTURE SET OUT CORRECT
checkpoint | CLIENT VARIATION CHECKED AGAINST SCHEDULE
checklist-sectioned | Kitchen Fit Off
section | SINK
checkpoint | JOINERY
checkpoint | STONE
checkpoint | MIXER
checkpoint | WASTE
checkpoint | DW CONNECT
section | COOKTOP
checkpoint | STONE/ SPLASH
checkpoint | COOKTOP
checkpoint | CONNECTION
checklist-sectioned | DDA Fit Off
section | BASIN
checkpoint | STONE
checkpoint | BASIN
checkpoint | MIXER
section | WC
checkpoint | TILE
checkpoint | GROUT
checkpoint | WC
section | SHOWER
checkpoint | TILE
checkpoint | GROUT
checkpoint | RAIL
checklist-sectioned | FEMALE AMENITIES Fit Off
section | BASIN
checkpoint | STONE
checkpoint | BASIN
checkpoint | MIXER
section | WC
checkpoint | TILE
checkpoint | GROUT
checkpoint | WC
section | SHOWER
checkpoint | TILE
checkpoint | GROUT
checkpoint | RAIL
checklist-sectioned | MALE AMENITIES Fit Off
section | BASIN
checkpoint | STONE
checkpoint | BASIN
checkpoint | MIXER
section | WC
checkpoint | TILE
checkpoint | GROUT
checkpoint | WC
section | SHOWER
checkpoint | TILE
checkpoint | GROUT
checkpoint | RAIL
checkpoint | URINAL
checklist-sectioned | BATHROOM 1 & 2 Fit Off
section | BASIN
checkpoint | STONE
checkpoint | BASIN
checkpoint | MIXER
section | WC
checkpoint | TILE
checkpoint | GROUT
checkpoint | WC
section | SHOWER
checkpoint | TILE
checkpoint | GROUT
checkpoint | RAIL
checkpoint | BATH
checklist-sectioned | ENSUITE Fit Off
section | BASIN
checkpoint | STONE
checkpoint | BASIN
checkpoint | MIXER
section | WC
checkpoint | TILE
checkpoint | GROUT
checkpoint | WC
section | SHOWER
checkpoint | TILE
checkpoint | GROUT
checkpoint | RAIL
checkpoint | BATH
checklist-sectioned | POWDER ROOM Fit Off
section | BASIN
checkpoint | STONE
checkpoint | BASIN
checkpoint | MIXER
section | WC
checkpoint | TILE
checkpoint | GROUT
checkpoint | WC
checklist | LAUNDRY Fit Off
checkpoint | STAND PIPE
checklist | KITCHEN Commissioning
checkpoint | KITCHEN SINK
checkpoint | SINK MIXER
checkpoint | DISHWASHER
checkpoint | DISHWASHER RAN
checkpoint | HOT PLATE
checkpoint | SINK WASTE
checkpoint | COVERPLATES
checklist | DDA Commissioning
checkpoint | W.C
checkpoint | BASIN
checkpoint | CLEAN BASIN FW
checkpoint | SHOWER MIXER
checkpoint | SHOWER ROSE
checkpoint | SHOWER WASTE CLEANED
checkpoint | TEMP VALVE
checkpoint | AAV
checklist | FEMALE AMENITIES Commissioning
checkpoint | W.C
checkpoint | BASIN
checkpoint | CLEAN BASIN FW
checkpoint | SHOWER MIXER
checkpoint | SHOWER ROSE
checkpoint | SHOWER WASTE CLEANED
checkpoint | TEMP VALVE
checkpoint | AAV
checklist | MALE AMENITIES Commissioning
checkpoint | W.C
checkpoint | BASIN
checkpoint | CLEAN BASIN FW
checkpoint | SHOWER MIXER
checkpoint | SHOWER ROSE
checkpoint | SHOWER WASTE CLEANED
checkpoint | TEMP VALVE
checkpoint | AAV
checkpoint | URINAL
checklist | BATHROOM 1 & 2 Commissioning
checkpoint | W.C
checkpoint | BASIN
checkpoint | CLEAN BASIN FW
checkpoint | SHOWER MIXER
checkpoint | SHOWER ROSE
checkpoint | SHOWER WASTE CLEANED
checkpoint | TEMP VALVE
checkpoint | BATH MIXER
checkpoint | BATH OUTLET
checkpoint | AAV
checkpoint | BATH
checklist | ENSUITE Commissioning
checkpoint | W.C
checkpoint | BASIN
checkpoint | CLEAN BASIN FW
checkpoint | SHOWER MIXER
checkpoint | SHOWER ROSE
checkpoint | SHOWER WASTE CLEANED
checkpoint | TEMP VALVE
checkpoint | BATH MIXER
checkpoint | BATH OUTLET
checkpoint | AAV
checkpoint | BATH
checklist | POWDER ROOM Commissioning
checkpoint | W.C
checkpoint | BASIN
checkpoint | CLEAN BASIN FW
checklist | LAUNDRY Commissioning
checkpoint | STAND PIPE
checkpoint | FLOOR WASTE
Checklist | Water Meter Room
checkpoint | Water Meter Complete
Checklist | GIT Room
checkpoint | GIT Complete
checklist | Staff Room Fit Off
checkpoint | SINK
checkpoint | JOINERY
checkpoint | STONE
checkpoint | MIXER
checkpoint | WASTE
checkpoint | DW CONNECT
checklist | Staff Room Commissioning
checkpoint | SINK
checkpoint | SINK MIXER
checkpoint | DISHWASHER
checkpoint | DISHWASHER RAN
checklist | Cleaners Fit Off
checkpoint | SINK
checkpoint | MIXER
checkpoint | WASTE
checklist | Clearners Commissioning
checkpoint | SINK
checkpoint | SINK MIXER
checklist | Bar Fit Off
checkpoint | SINK
checkpoint | JOINERY
checkpoint | STONE
checkpoint | MIXER
checkpoint | WASTE
checkpoint | DW CONNECT
checklist | Bar Commissioning
checkpoint | SINK
checkpoint | SINK MIXER
checkpoint | DISHWASHER
checkpoint | DISHWASHER RAN