## to_add
Step Id | Warnings | State | Checklist Template | Type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
d68368d4-7305-46c7-99d1-d505c2dbf7c9 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Communal Areas | Clarmont Tower | Fit Off | Level 16 | Ambulant
5b4f7b5d-7cc8-4fb0-b060-eef3923bd5f0 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 1 | 101 | Bathroom
4843099f-f359-4f14-8458-2b00859d6b83 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 1 | 102 | Bathroom
93d47e58-8a52-4344-bdc5-290effb08d2f |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 1 | 103 | Bathroom
ab935b3f-e0f7-4b36-b785-b925b0137bc3 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 1 | 104 | Bathroom
2eb8f218-d6fd-43a3-bed0-47e8783814b3 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 1 | 105 | Bathroom
23b89e89-2101-4f6d-9a9f-6bd68cec870c |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 1 | 106 | Bathroom
cf1de5e9-03e2-4743-839c-c222703f1830 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 1 | 107 | Bathroom
d4df58de-4b2f-4f1c-bc45-16e4048802c1 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 1 | 108 | Bathroom
8f15bd02-6fc6-473d-8dac-436de3efd3ff |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 1 | 109 | Bathroom
df2dbe4d-aa6b-4b33-acc4-c9cffed6f38f |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 2 | 201 | Bathroom
6a34941c-60d8-4e09-ab6f-837ded9c270e |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 2 | 202 | Bathroom
c5588be5-4d72-4b83-8e64-7c0c8177a820 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 2 | 203 | Bathroom
b056959b-9272-4cba-9bc0-8802c26b103e |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 2 | 204 | Bathroom
37aa87c9-983d-4400-ad12-a24e536d1974 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 2 | 205 | Bathroom
9e95fd08-e546-4113-b81c-fbc1eed42330 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 2 | 206 | Bathroom
9f2d59ee-334f-4a9e-9ac3-96d26ac2dec2 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 2 | 207 | Bathroom
f54cb4c3-d7e4-4e30-9279-f409a3333cf6 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 2 | 208 | Bathroom
2533ecd0-f2cc-4363-8d8a-d1283abf871d |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 2 | 209 | Bathroom
234e6378-389a-45f4-87e0-fd3887ad0384 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 2 | 210 | Bathroom
73afdff0-a433-479e-8f62-b652f3ba155a |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 2 | 211 | Bathroom
3ec02a7f-5775-4571-9ae6-028be8c9b7e8 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 2 | 212 | Bathroom
42907479-7136-471c-84a6-bded1e8e3574 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 2 | 213 | Bathroom
a29a614f-c399-46fc-8185-e2806e6d0250 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 2 | 214 | Bathroom
8e3d9b48-9f9c-4284-8355-8327db0d63db |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 2 | 215 | Bathroom
baff9b9b-d11f-436b-9cc8-fca45e8544f6 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 3 | 301 | Ensuite
9abfa9b0-c6ee-4b2c-9d36-d9fb6aecfa3a |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 3 | 302 | Bathroom
814b69bd-049b-4dc0-a844-689643b52a74 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 3 | 303 | Bathroom
c454702a-6f70-4489-b044-bba981b8a4c5 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 3 | 304 | Bathroom
fbf55f8a-86f1-40de-ada1-dd1123d54e7d |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 3 | 305 | Bathroom
455cd382-ef37-4664-90d4-a96df0663d34 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 3 | 306 | Bathroom
1481b33d-b21f-4b9b-a3fa-1229f3ab5b54 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 3 | 307 | Bathroom
12da3938-a0fa-43bc-a0ed-96936954bc20 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 3 | 308 | Bathroom
562603b5-3b38-4c09-af76-a64df11b2e07 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 3 | 309 | Bathroom
eebb2f86-d9b2-42ea-85a8-bc48e1beda3d |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 3 | 309 | Ensuite
2109bab1-428f-4ae9-8c65-159364260ba6 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 3 | 310 | Bathroom
11457e79-88ef-4b9a-a01d-e7638165404a |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 3 | 311 | Bathroom
d1cc6a1c-38e1-4156-b93b-0a3d2553f649 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 3 | 312 | Bathroom
4535b74f-51d3-4c0f-ab52-bc1f1c740b53 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 3 | 313 | Bathroom
301ed65c-8b77-4afd-99ae-cb549b47956a |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 3 | 314 | Bathroom
e186265a-7f5f-420a-9d35-6e3462cd553f |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 3 | 315 | Bathroom
bd120145-2dd6-4add-b2ff-da976744b962 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 4 | 401 | Ensuite
2552af7d-8f08-48b8-bff9-b1a67b2e73da |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 4 | 402 | Bathroom
31137841-6a86-46c3-86a2-489cc44a7a6b |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 4 | 403 | Bathroom
a42a8984-ddaa-44ad-8b99-b3e68bd1d7d4 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 4 | 404 | Bathroom
5cbbc22b-8e3a-4bfa-88e2-630c1dd592c1 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 4 | 405 | Bathroom
9544d38e-47fa-44ee-aa1b-f0264a05cf6d |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 4 | 406 | Bathroom
d75f2413-22b0-4ac1-b9ca-ab29781a25fb |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 4 | 407 | Bathroom
288a8b30-e98b-48a7-b69c-eaba4204b57a |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 4 | 408 | Bathroom
be065081-70d2-4b58-97ca-61bb28a92795 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 4 | 409 | Bathroom
5fe02acf-46f6-40a7-90f5-7ed57882cafe |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 4 | 409 | Ensuite
3c7ed051-5eac-42a7-a6eb-8bfe2aae8f92 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 4 | 410 | Bathroom
95ffed9f-a794-41cf-85f9-6c80598b5b3e |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 4 | 411 | Bathroom
ec3d4115-b765-45e4-8f41-e24523f61c42 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 4 | 412 | Bathroom
a791f782-44b1-45b7-a0df-5e90417009d8 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 4 | 413 | Bathroom
30e1e8ce-c830-4da1-867e-1b28f1f7c1b0 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 4 | 414 | Bathroom
76b7894c-6f5c-4228-9695-623c42bef0d9 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 4 | 415 | Bathroom
966b56e8-cad1-4535-8ce9-34b37781c444 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 5 | 501 | Ensuite
c079a6c1-408a-435d-842b-f2e1f2877fcc |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 5 | 502 | Bathroom
a393c38a-1cd6-482f-b021-dc174e314701 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 5 | 503 | Bathroom
65818709-4b18-4fbf-86e3-fad4a5484b1c |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 5 | 504 | Bathroom
ca1a1e70-750c-4dbc-85d8-7a0b47757551 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 5 | 505 | Bathroom
8dd3d2a8-8a09-436b-9ec9-94612871cad7 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 5 | 506 | Bathroom
c47a1e35-a74d-4b32-ab7d-050c231257ab |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 5 | 507 | Bathroom
2366754a-c0c2-403a-81b7-1b35cf287da3 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 5 | 508 | Bathroom
22bf283c-bdda-4fd5-b4e5-d6517dc85bfb |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 5 | 509 | Bathroom
58e7bc71-da34-46e7-9fdf-4e1474c855c2 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 5 | 509 | Ensuite
d3642efe-7133-441b-97d5-3118f06ff856 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 5 | 510 | Bathroom
9e75a5dc-68bb-410d-bb34-247118fb00ee |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 5 | 511 | Bathroom
55715c7a-3ea7-44f8-b701-a6849238f1e1 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 5 | 512 | Bathroom
9127b696-0092-4a88-ac4d-3f1ba5047b00 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 5 | 513 | Bathroom
e46ba03d-1eb6-4930-9615-82c944e9b94f |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 5 | 514 | Bathroom
0369bbd9-89ed-4210-83d4-1d8760e014cd |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 5 | 515 | Bathroom
ba0f461d-dce3-4152-b002-c1fa56f324ab |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 6 | 601 | Ensuite
ef29bf5d-f9f2-486c-a2af-b9df993b5340 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 6 | 602 | Bathroom
b4a42aa6-58bb-4c63-a9ca-37d21854adbb |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 6 | 603 | Bathroom
14e58f88-b776-49cd-b4c7-9333e466834c |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 6 | 604 | Bathroom
2244db9d-2176-4f56-b4af-05bc1adfabc1 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 6 | 605 | Bathroom
c9ea5923-8e02-4692-84f2-f43fa140c3b5 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 6 | 606 | Bathroom
3c1a7281-d710-44cd-88cc-5587ce5a3a77 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 6 | 607 | Bathroom
2b4df330-8180-47e2-8006-4f88c65ed6aa |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 6 | 608 | Bathroom
a7af0fe9-849e-4d6e-9f7a-fab0f3da7cfb |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 6 | 609 | Bathroom
89037d02-3b54-4a38-98b8-54a1afdf6ed8 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 6 | 609 | Ensuite
d138be04-8b0b-4b92-b408-fbb26b5d24c6 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 6 | 610 | Bathroom
3dcd0ac1-cd43-4660-891c-c08461a64a48 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 6 | 611 | Bathroom
73dd9607-69bf-4240-851a-96def5022414 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 6 | 612 | Bathroom
6ea395f7-188e-47ad-baa0-2f8bdcc07565 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 6 | 613 | Bathroom
3498d386-b169-423d-860c-e9b680b3143c |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 6 | 614 | Bathroom
b34338a0-5580-4a17-afa2-b85ddcfb95e9 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 6 | 615 | Bathroom
dd935240-d6c9-4479-8105-c5846c1b9746 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 7 | 701 | Ensuite
d7dadcf4-795a-416b-808c-e06d1ae4c043 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 7 | 702 | Bathroom
a4e5f863-1fc9-42aa-87e0-f6b1bec42d90 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 7 | 703 | Bathroom
61b4dce1-b92d-45ef-ab90-023dd3ce42ea |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 7 | 704 | Bathroom
1cbe8f50-69e8-48a3-96ce-19a60399a858 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 7 | 705 | Bathroom
d042e1f6-6e03-46e3-8aca-60e792487492 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 7 | 706 | Bathroom
57924313-f511-4454-a099-5dbafffd24cc |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 7 | 707 | Bathroom
931ce711-5b08-456b-b748-95ca70972ba7 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 7 | 708 | Bathroom
c7452131-c18e-49a7-924f-0482fec86016 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 7 | 709 | Bathroom
b2fe8f82-3698-4d34-ad48-63306a355f95 |  | work-in-progress | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 7 | 709 | Ensuite
cc311308-f7a3-42ab-b6cb-a27a61ea2581 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 7 | 710 | Bathroom
f75204da-a679-4c86-ab8e-b9933ce0b44f |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 7 | 711 | Bathroom
c1e21dc4-e71f-484a-ae12-59802478243a |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 7 | 712 | Bathroom
4a4a1741-a067-429a-8f5b-d52779ec2cae |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 7 | 713 | Bathroom
891e7ccd-9d5a-4872-9e65-1e75dd9bcd9c |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 7 | 714 | Bathroom
fc4f622c-5c9c-4179-a659-bd16b3481f29 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 7 | 715 | Bathroom
cb61e3b1-ec02-4116-bcb1-2bee3de98119 |  | work-in-progress | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 8 | 801 | Ensuite
d8f918a2-13cf-4a84-97c7-68f46bbd5a90 |  | work-in-progress | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 8 | 802 | Bathroom
bcb2d1df-7717-4c21-9d54-3c7d8527b618 |  | work-in-progress | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 8 | 803 | Bathroom
7a9a143e-a388-4822-856b-6c6c8d1a39ad |  | work-in-progress | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 8 | 804 | Bathroom
97cea8c5-0410-495c-9177-f6ee5d63869a |  | work-in-progress | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 8 | 805 | Bathroom
c3d82e85-2f67-42e5-8f8d-400244fe3547 |  | work-in-progress | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 8 | 806 | Bathroom
5f70f1ed-11f9-40d7-b568-cf6cdbdd5c15 |  | work-in-progress | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 8 | 807 | Bathroom
f46802e1-ff4d-4687-a685-b3f24f27cdfd |  | work-in-progress | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 8 | 808 | Bathroom
bf716016-0bd0-4fae-a412-b1376e3e8d5d |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 8 | 809 | Bathroom
0dbbeb66-e2f7-450b-81a3-467ad3624d79 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 8 | 809 | Ensuite
9c2f8338-9658-4506-8ffc-7e7dd1f06f4f |  | work-in-progress | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 8 | 810 | Bathroom
6e47ef5a-855f-4a0c-b9f9-62d1d94b8d18 |  | work-in-progress | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 8 | 811 | Bathroom
03e0eb8e-a24e-466f-97a1-2e9dead7d3d9 |  | work-in-progress | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 8 | 812 | Bathroom
19129904-3b5d-4d8e-a2ac-13447fe12b04 |  | work-in-progress | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 8 | 813 | Bathroom
3187094b-b05e-4431-8bb3-d33d384d456b |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 8 | 814 | Bathroom
ff17e2ca-9f48-48b3-b9c9-7d167222e242 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 8 | 815 | Bathroom
be9bc168-7a8a-4255-926e-62fc2277bfd9 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 9 | 901 | Ensuite
9c57acc4-670d-40e5-8e8e-8a6e75cac6fa |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 9 | 902 | Bathroom
87a0c42c-dc8a-4317-9423-9e6abc37d283 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 9 | 903 | Bathroom
c30b589f-6fa5-4d64-a096-94e008c3547d |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 9 | 904 | Bathroom
fcbde484-beb9-443e-9ec0-7be01fffe64b |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 9 | 905 | Bathroom
da5bde4e-6a77-4c39-b793-e73276c5f21f |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 9 | 906 | Bathroom
266e83ad-803b-4287-8c9c-63bbc5f07b71 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 9 | 907 | Bathroom
e0818d63-b681-43d7-94d2-ab004bd2d1b1 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 9 | 908 | Bathroom
b0e1d5e9-2d7d-4c8d-b23a-5c14c116506b |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 9 | 909 | Bathroom
283336e7-d3bf-4a1f-ac72-c45f12cb9a11 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 9 | 909 | Ensuite
0124a087-2572-4efc-b669-df8ea7559658 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 9 | 910 | Bathroom
3b10a9d6-f156-4680-b089-e10710e61d3c |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 9 | 911 | Bathroom
36719b2b-5196-4046-bafb-d3f7e9e16533 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 9 | 912 | Bathroom
14681b17-2faf-4d85-b1d5-90b60b334069 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 9 | 913 | Bathroom
421bee6a-326a-4903-b6b8-249eb5bc7f2a |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 9 | 914 | Bathroom
e3ee3496-e0b7-4d63-ac21-fac47394ebfe |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 9 | 915 | Bathroom
89f17daa-2586-4498-bbfe-6fdf16297616 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 10 | 1001 | Ensuite
27936299-7a84-441c-9e2b-c7288d19adf6 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 10 | 1002 | Bathroom
c4fe343b-b23d-4f93-ae29-56b1103da188 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 10 | 1003 | Bathroom
5eec5744-7e6f-4da4-a8e3-0f6e5e9a46f1 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 10 | 1004 | Bathroom
0583bd2e-31aa-498d-a430-1e4af87fb50f |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 10 | 1005 | Bathroom
f3cfda4b-7e97-4085-a92d-0e46af45cde2 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 10 | 1006 | Bathroom
e07c2b3c-850e-46e4-a8f6-2a4c3764b6ca |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 10 | 1007 | Bathroom
99d2c295-2e4e-414c-a72a-4d2d1eab781a |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 10 | 1008 | Bathroom
16887187-c485-4915-99d9-cb62364e79c8 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 10 | 1009 | Bathroom
bc404eec-9899-47f0-9c2f-d2ee2605f958 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 10 | 1009 | Ensuite
5ace5a6b-053d-489a-83fa-7d11aa5e080e |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 10 | 1010 | Bathroom
055a168e-a1b8-4e85-8ec7-11821a505455 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 10 | 1011 | Bathroom
9285fe72-07e4-44d0-b06c-6b8926b69afe |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 10 | 1012 | Bathroom
c0ccb7f7-dea8-49af-91aa-2f6bd26a978a |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 10 | 1013 | Bathroom
8e551918-fe3f-4de2-976f-7b6de183f446 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 10 | 1014 | Bathroom
6d40c359-520d-45f2-9242-f8317175fc1b |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 10 | 1015 | Bathroom
9f27fd41-ed07-45fd-8238-e0a2fb40fa56 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 11 | 1101 | Ensuite
c7ccad99-4717-4b48-8539-0230648bd439 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 11 | 1102 | Bathroom
61bc22dc-7c15-44f2-8237-bffe56bc491d |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 11 | 1103 | Bathroom
827e37a4-3dc5-4068-9a55-5759b52717c5 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 11 | 1104 | Bathroom
71e56cc5-a031-4628-90ad-4113025384c4 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 11 | 1105 | Bathroom
4f076e5c-017f-4b95-9e46-77f88f532433 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 11 | 1106 | Bathroom
a35108f5-42c4-4015-9294-ea77861f16d7 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 11 | 1107 | Bathroom
1a79aac7-72aa-4bfa-9faa-02b624dce852 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 11 | 1108 | Bathroom
2516d0f4-c441-4c0d-8ca3-88fc79f45f55 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 11 | 1109 | Bathroom
06ea936d-7ca6-42f4-91f9-f2a261d4283e |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 11 | 1109 | Ensuite
5b3974a4-caf5-41f7-a74d-cfc136ae9a26 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 11 | 1110 | Bathroom
441f8789-d711-4be2-8ec5-72d1f621e55d |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 11 | 1111 | Bathroom
6a1ec47c-5717-4a77-b0e5-78c1a3a4c240 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 11 | 1112 | Bathroom
99852b6f-ce18-4f04-b3e4-7038e6d5545f |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 11 | 1113 | Bathroom
ef609c07-949c-4f3f-8d47-955c11c0e524 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 11 | 1114 | Bathroom
53a2130b-a485-438c-a80f-58c4a22b1866 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 11 | 1115 | Bathroom
5a7ccb69-97c5-4251-920a-d993bee6b8cb |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 12 | 1201 | Ensuite
02546ce1-e563-4880-87e7-cc36ac1bd6d8 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 12 | 1202 | Bathroom
35765bac-c4c6-47b6-b1c6-a50c7dfe0da0 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 12 | 1203 | Bathroom
47fa2a6d-af09-421d-a461-3bc637f3b669 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 12 | 1204 | Bathroom
e8f1af07-d3ab-4dc5-b79f-9253377b4b21 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 12 | 1205 | Bathroom
eb5e773a-a52b-4f78-80c0-a9a6a758eca5 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 12 | 1206 | Bathroom
bbb32a76-3abb-49d5-ae8b-7df9a9e2b3b7 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 12 | 1207 | Bathroom
f94031b1-ecf0-4e65-8b3e-f0a4face8a9d |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 12 | 1208 | Bathroom
efb326d5-1e24-41cd-a499-60ddd148ef99 |  | pass | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 12 | 1209 | Ensuite
900cc97d-aff9-45c5-a984-ad50c2509b57 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 12 | 1210 | Bathroom
39a00765-fcfe-4dc2-a665-4736aed15c72 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 12 | 1210 | Ensuite
01c296bf-fd35-4744-8279-eca530c02ca5 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 12 | 1211 | Bathroom
f9e70eaf-2109-45d4-8cda-795625e903fe |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 12 | 1212 | Bathroom
afe5e08c-97d0-49e3-87c7-fd0a08a202cd |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 12 | 1213 | Bathroom
41afeb82-70c9-4e27-bae3-34ba2ccf084e |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 13 | 1301 | Ensuite
894872b2-7311-4833-b4b4-d6f5e253ae68 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 13 | 1302 | Bathroom
e37eb398-f5e4-4e75-96cf-e117497f06a4 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 13 | 1303 | Bathroom
b79fd8c1-e08d-4f48-9992-2307e2388382 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 13 | 1304 | Bathroom
3f310604-e76b-4775-89fc-90961b06ac09 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 13 | 1305 | Bathroom
7a32a0a1-d634-494b-9fa7-21462d1c863c |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 13 | 1306 | Bathroom
8ecae777-06c1-48ec-ba47-9e2d31b649a3 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 13 | 1307 | Bathroom
c75a823a-0c60-457a-996f-b52d5b0ed410 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 13 | 1308 | Bathroom
0b85c8a8-14c5-4c30-82ab-2fcb6fcc22cd |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 13 | 1309 | Ensuite
9890f660-026f-4f5b-8ebe-68659a086cfc |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 13 | 1310 | Bathroom
28253b03-c0d7-4175-a28b-16f81c85d9bd |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 13 | 1310 | Ensuite
0a227fd6-3f69-4437-856d-81e2f441273b |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 13 | 1311 | Bathroom
19299493-0aec-4cc6-9b28-aff3a2b26a0f |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 13 | 1312 | Bathroom
d083ca70-7b31-4eb4-9185-959efac9d656 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 13 | 1313 | Bathroom
8ab6032c-b98f-4924-a799-bb5c6f8e7ff8 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 14 | 1401 | Ensuite
20455115-28e0-44c7-94dc-0f2a7054ce6a |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 14 | 1402 | Bathroom
2b36ade3-a60b-47cf-8e6d-c5f9bcb29d01 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 14 | 1403 | Bathroom
ab0a4875-f4f2-4784-8aa0-286aa8fd5a06 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 14 | 1404 | Bathroom
12ff5136-7bc7-4a1e-9503-e41fb5b0dde3 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 14 | 1405 | Bathroom
bd452deb-5d43-4674-99aa-9f5f3a75681d |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 14 | 1406 | Bathroom
8871a377-a372-4e22-aa9d-cb22d67bdf2a |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 14 | 1407 | Bathroom
6816592b-a834-42f1-a2a1-e1c11a63be2c |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 14 | 1408 | Bathroom
93cad1c2-c35d-4dbd-8afe-d85809122440 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 14 | 1409 | Ensuite
b7cdf7dc-dd81-4665-9a2e-c0cfc0cb8b82 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 14 | 1410 | Bathroom
0db51407-cb74-41d1-b469-9bd290b562d1 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 14 | 1410 | Ensuite
b597fe09-977f-401c-bff4-429b4d22d8ab |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 14 | 1411 | Bathroom
00676ae5-0369-44cc-a7dd-0065dab24d87 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 14 | 1412 | Bathroom
5ae901b8-f2a0-4250-9293-692e8ec914e0 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 14 | 1413 | Bathroom
78e12523-1f24-40ac-8603-e67b7f0a9436 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 15 | 1501 | Ensuite
6440eb8a-6d5e-4546-b772-e682db428cee |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 15 | 1502 | Bathroom
5288839c-61b5-498a-bbff-da7634b178fa |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 15 | 1503 | Bathroom
5cd907ff-5a90-4310-96f2-30e529f05b81 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 15 | 1504 | Bathroom
0cf923af-1c5a-4cfc-8b5c-9b4f3e1f6f40 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 15 | 1505 | Bathroom
6f80655f-a532-473f-81b7-d378f1bd0258 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 15 | 1506 | Bathroom
4c802dae-a12b-4263-a308-4e8d5a882a96 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 15 | 1507 | Bathroom
4e492d70-2f83-4380-9f93-c1eedceccf8d |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 15 | 1508 | Bathroom
c476b0fa-f047-420d-acac-63629cb676bd |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 15 | 1509 | Ensuite
6e9a7e4a-7eea-494f-8024-c3de838cdd10 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 15 | 1510 | Bathroom
9e1bd64f-6729-40ae-a79e-11f54070fca4 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 15 | 1510 | Ensuite
be32427b-e32c-41e6-91e8-72531f0c09cc |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 15 | 1511 | Bathroom
85606bfc-34eb-40c1-8191-689c73192182 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 15 | 1512 | Bathroom
bd866f32-e9a3-4c24-ad2a-5965efd2ec0f |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 15 | 1513 | Bathroom
f30ac78b-239f-4e67-ab2f-d4caad04e46a |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 17 | 1701 | Bathroom
3dbaa0e6-97e2-456d-a6c7-868aff6eb5fb |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 17 | 1702 | Bathroom
c74c6ce3-eaed-4798-aa60-4fe3bb57f9bc |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 17 | 1702 | Ensuite
8ef88289-6a7b-41ac-8c2e-27db0b26dcad |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 17 | 1703 | Bathroom
ee8fffa9-3fea-44b7-a04e-c40a96db3571 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 17 | 1703 | Ensuite
cf191e05-fc30-47ef-9539-0b3bec020ac5 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 17 | 1704 | Bathroom
747ba97a-23cc-4c1a-a26b-653ad1fa3d2e |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 17 | 1705 | Bathroom
3fd148e1-1b6b-491c-9777-4770c1d05983 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 17 | 1705 | Ensuite
cf15c7cc-38f0-442a-8e99-7f32608af429 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 17 | 1706 | Bathroom
a80b804e-8a54-45dc-999a-2cb2e6a26ce3 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 17 | 1706 | Ensuite
4d87f6e8-5889-4bc0-87ca-8bdfd5eb6e32 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 18 | 1801 | Bathroom
3c4037cf-53da-42ff-94e0-57391636c950 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 18 | 1802 | Bathroom
f06a53f1-1d52-430d-bd15-3ee71e395170 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 18 | 1802 | Ensuite
6a72cf2b-52d4-49ff-8488-d4d3cd82c403 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 18 | 1803 | Bathroom
b4a76c75-2d5a-4898-a653-b4a7c86de3fc |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 18 | 1803 | Ensuite
7ad62c37-c1d8-4e75-9610-7c095dac7f0b |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 18 | 1804 | Bathroom
1b508072-5908-462d-914f-8c3c9cb6a060 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 18 | 1805 | Bathroom
bb662783-1b6e-4eb9-8018-8efd537b5042 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 18 | 1805 | Ensuite
b665d30f-3712-48c8-bb0b-c0ae276bfb29 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 18 | 1806 | Bathroom
3b453f16-5ccc-45c4-88b1-e55277e080e1 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 18 | 1806 | Ensuite
e96f2de2-9fde-4f83-8be5-a43b810ed453 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 19 | 1901 | Bathroom
0a76e4b3-ff70-4699-a70e-99a21188f031 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 19 | 1902 | Bathroom
06726d20-cb38-4646-96b2-2bb26b76bfbb |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 19 | 1902 | Ensuite
ef019909-f211-464c-a1b2-33606a34d526 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 19 | 1903 | Bathroom
7c48f455-b8d6-4cee-9f8f-28d6f0f46e38 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 19 | 1903 | Ensuite
bb3762ff-ba7b-48da-a5da-85ca201c0324 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 19 | 1904 | Bathroom
f044b97d-4ba9-4df5-b390-733b3ae68458 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 19 | 1905 | Bathroom
261b64bf-dda9-4ae0-bfb7-b60242cdda6d |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 19 | 1905 | Ensuite
5922f7ef-c2b6-4800-87c6-0d29b5cc9655 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 19 | 1906 | Bathroom
5946e766-d577-4fec-9535-63ab4dbf0145 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 19 | 1906 | Ensuite
89b78ebd-36af-4967-9c17-78464c6c0699 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 20 | 2001 | Bathroom
ac25d421-cf9e-49a6-9c64-5463880a14ee |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 20 | 2002 | Bathroom
577aa04b-9b8c-4e6e-a2ac-679faabc54ab |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 20 | 2002 | Ensuite
d584f806-52a7-4d3d-9223-1ac23853ded8 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 20 | 2003 | Bathroom
56a92848-a82f-4d5b-8aa3-8710ba9ae89d |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 20 | 2003 | Ensuite
593f2830-38c5-4274-8e22-cec31e59fdb6 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 20 | 2004 | Bathroom
14e4c0d8-8892-4e85-a901-f86f8a07f6a4 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 20 | 2005 | Bathroom
27aa4a72-568a-4aef-ac9c-c210ca508801 |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 20 | 2005 | Ensuite
45a97ed3-6473-4b33-99e6-d95afeb4943b |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 20 | 2006 | Bathroom
eb0b2273-2c53-482c-a6cd-eea8e24bdb1f |  | not-started | ENSUITE Fit Off | checklist | FALSE | FALSE | Site QA | Claremont Tower | Fit Off | Level 20 | 2006 | Ensuite