## Sheet1
1.1 | Induction | Prior to Commencing | All personnel on site have been inducted to the Ballarto Rd CHAR(AMP) Lyrebird Dr Project site | Inductions Register | Document review | Site induction signed. | AP | Site Engineer / Site Foreman | 1.1 - Induction | FREQUENCY: Prior to Commencing | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Ballarto Rd CHAR(AMP) Lyrebird Dr Project site | REFERENCE DOCUMENTS: Inductions Register | INSPECTION/TEST METHOD: Document review | RECORD OF CONFORMITY: Site induction signed. | AP | RESPONSIBILITY: Site Engineer / Site Foreman | Date Completed: | 1.1 - Induction
1.2 | Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken | Prior to commencing | All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP CHAR(AMP) SWMS | Health and Safety Co-Ordination Plan | Document Review | SWMS(s) signed | HP | Site Engineer, Site Foreman CHAR(AMP) Superintendent | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken | FREQUENCY: Prior to commencing | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP CHAR(AMP) SWMS | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan | INSPECTION/TEST METHOD: Document Review | RECORD OF CONFORMITY: SWMS(s) signed | HP | RESPONSIBILITY: Site Engineer, Site Foreman CHAR(AMP) Superintendent | Date Completed: | FREQUENCY: Prior to Commencing
1.3 | Check that current revision drawings are being used | Prior to Commencing | Issued For Construction (IFC) and latest available revision used | Project Drawings / Drawing Register | Document review | Latest Revision Drawings | AP | Site Engineer / Site Foreman | 1.3 - Check that current revision drawings are being used | FREQUENCY: Prior to Commencing | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used | REFERENCE DOCUMENTS: Project Drawings / Drawing Register | INSPECTION/TEST METHOD: Document review | RECORD OF CONFORMITY: Latest Revision Drawings | AP | RESPONSIBILITY: Site Engineer / Site Foreman | Date Completed: | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Ballarto Rd CHAR(AMP) Lyrebird Dr Project site
1.4 | Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place | Prior to Commencing | All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified | IFC Drawings CEMP CHMP | Document review CHAR(AMP) Site inspection | Signed ITP | IP | Site Engineer | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place | FREQUENCY: Prior to Commencing | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified | REFERENCE DOCUMENTS: IFC Drawings CEMP CHMP | INSPECTION/TEST METHOD: Document review CHAR(AMP) Site inspection | RECORD OF CONFORMITY: Signed ITP | IP | RESPONSIBILITY: Site Engineer | Date Completed: | REFERENCE DOCUMENTS: Inductions Register
1.5 | Excavation Permit issued | Prior to Commencing | Current Excavation Permit signed and specific for the area where works will be executed. | Excavation Permit | Document review | Excavation Permit # | IP | Site Engineer | 1.5 - Excavation Permit issued | FREQUENCY: Prior to Commencing | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed. | REFERENCE DOCUMENTS: Excavation Permit | INSPECTION/TEST METHOD: Document review | RECORD OF CONFORMITY: Excavation Permit # | IP | RESPONSIBILITY: Site Engineer | Date Completed: | INSPECTION/TEST METHOD: Document review
1.6 | Materials | Prior to Commencing | All subsurface drainage pipes shall have a maximum perforation width of 1.5mm and a minimum length of 150mm/m2 | Project Spec. Cl.3030.05(a) | Document review | Signed ITP | IP | Site Engineer | 1.6 - Materials | FREQUENCY: Prior to Commencing | ACCEPTANCE CRITERIA: All subsurface drainage pipes shall have a maximum perforation width of 1.5mm and a minimum length of 150mm/m2 | REFERENCE DOCUMENTS: Project Spec. Cl.3030.05(a) | INSPECTION/TEST METHOD: Document review | RECORD OF CONFORMITY: Signed ITP | IP | RESPONSIBILITY: Site Engineer | Date Completed: | RECORD OF CONFORMITY: Site induction signed.
2.1 | Excavation of Trench | When placing drainage | The base of the trench shall be sufficiently compacted and not more than 50mm below the invert level of the pipe to be placed. Perforated Pipe Crown level to be minimum 200mm below subgrade level. Grade of trench to be not flatter than 1 in 250. | VicRoads Spec. Cl.702.08 VicRoads Spec. Cl.702.09(a)(b) | Site inspection | Signed ITP | HP | Superintendent / Site Engineer | 2.1 - Excavation of Trench | FREQUENCY: When placing drainage | ACCEPTANCE CRITERIA: The base of the trench shall be sufficiently compacted and not more than 50mm below the invert level of the pipe to be placed. Perforated Pipe Crown level to be minimum 200mm below subgrade level. Grade of trench to be not flatter than 1 in 250. | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.08 VicRoads Spec. Cl.702.09(a)(b) | INSPECTION/TEST METHOD: Site inspection | RECORD OF CONFORMITY: Signed ITP | HP | RESPONSIBILITY: Superintendent / Site Engineer | Date Completed: | AP
2.2 | Use of Geotextile | When placing drainage | Where geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contract with the wall when granular material is placed against the geotextile. | VicRoads Spec. Cl.702.08 | Site inspection | Signed ITP | IP | Site Engineer | 2.2 - Use of Geotextile | FREQUENCY: When placing drainage | ACCEPTANCE CRITERIA: Where geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contract with the wall when granular material is placed against the geotextile. | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.08 | INSPECTION/TEST METHOD: Site inspection | RECORD OF CONFORMITY: Signed ITP | IP | RESPONSIBILITY: Site Engineer | Date Completed: | RESPONSIBILITY: Site Engineer / Site Foreman
2.3 | Installation of Subsoil Drainage | When placing drainage | Ensure bedding of thickness between 25-50mm is placed across the bottom of trench and graded to level. Pipes are firmly in place, slotted pipes positioned so openings are in lower half of the pipe | VicRoads Spec. Cl.702.09(d) | Site inspection | Signed ITP | IP | Site Engineer | 2.3 - Installation of Subsoil Drainage | FREQUENCY: When placing drainage | ACCEPTANCE CRITERIA: Ensure bedding of thickness between 25-50mm is placed across the bottom of trench and graded to level. Pipes are firmly in place, slotted pipes positioned so openings are in lower half of the pipe | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(d) | INSPECTION/TEST METHOD: Site inspection | RECORD OF CONFORMITY: Signed ITP | IP | RESPONSIBILITY: Site Engineer | Date Completed: | Date Completed:
2.4 | Placing of Granular Filter Material | When placing drainage | Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the procedures and reviewed by the Superintendent. | VicRoads Spec. Cl.702.09(g) | Document Review | Signed ITP | HP | Superintendent / Site Engineer | 2.4 - Placing of Granular Filter Material | FREQUENCY: When placing drainage | ACCEPTANCE CRITERIA: Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the procedures and reviewed by the Superintendent. | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(g) | INSPECTION/TEST METHOD: Document Review | RECORD OF CONFORMITY: Signed ITP | HP | RESPONSIBILITY: Superintendent / Site Engineer | Date Completed: | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
2.5 | Flushing Test | After drainage is placed | Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction | VicRoads Spec. Cl.702.09(h) | Site inspection | Signed ITP/ Record of flushing tests | WP | Superintendent / Site Engineer | 2.5 - Flushing Test | FREQUENCY: After drainage is placed | ACCEPTANCE CRITERIA: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(h) | INSPECTION/TEST METHOD: Site inspection | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests | WP | RESPONSIBILITY: Superintendent / Site Engineer | Date Completed: | FREQUENCY: Prior to commencing
2.6 | CCTV | After drainage is placed | All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects. | VicRoads Spec. Cl.702.09(i) | Site inspection | Signed ITP/ Record of flushing tests | HP | Superintendent / Site Engineer | 2.6 - CCTV | FREQUENCY: After drainage is placed | ACCEPTANCE CRITERIA: All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects. | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(i) | INSPECTION/TEST METHOD: Site inspection | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests | HP | RESPONSIBILITY: Superintendent / Site Engineer | Date Completed: | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP CHAR(AMP) SWMS
REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
INSPECTION/TEST METHOD: Document Review
RECORD OF CONFORMITY: SWMS(s) signed
HP
RESPONSIBILITY: Site Engineer, Site Foreman CHAR(AMP) Superintendent
Date Completed:
1.3 - Check that current revision drawings are being used
FREQUENCY: Prior to Commencing
ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
REFERENCE DOCUMENTS: Project Drawings / Drawing Register
INSPECTION/TEST METHOD: Document review
RECORD OF CONFORMITY: Latest Revision Drawings
AP
RESPONSIBILITY: Site Engineer / Site Foreman
Date Completed:
1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
FREQUENCY: Prior to Commencing
ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
REFERENCE DOCUMENTS: IFC Drawings CEMP CHMP
INSPECTION/TEST METHOD: Document review CHAR(AMP) Site inspection
RECORD OF CONFORMITY: Signed ITP
IP
RESPONSIBILITY: Site Engineer
Date Completed:
1.5 - Excavation Permit issued
FREQUENCY: Prior to Commencing
ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
REFERENCE DOCUMENTS: Excavation Permit
INSPECTION/TEST METHOD: Document review
RECORD OF CONFORMITY: Excavation Permit #
IP
RESPONSIBILITY: Site Engineer
Date Completed:
1.6 - Materials
FREQUENCY: Prior to Commencing
ACCEPTANCE CRITERIA: All subsurface drainage pipes shall have a maximum perforation width of 1.5mm and a minimum length of 150mm/m2
REFERENCE DOCUMENTS: Project Spec. Cl.3030.05(a)
INSPECTION/TEST METHOD: Document review
RECORD OF CONFORMITY: Signed ITP
IP
RESPONSIBILITY: Site Engineer
Date Completed:
2.1 - Excavation of Trench
FREQUENCY: When placing drainage
ACCEPTANCE CRITERIA: The base of the trench shall be sufficiently compacted and not more than 50mm below the invert level of the pipe to be placed. Perforated Pipe Crown level to be minimum 200mm below subgrade level. Grade of trench to be not flatter than 1 in 250.
REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.08 VicRoads Spec. Cl.702.09(a)(b)
INSPECTION/TEST METHOD: Site inspection
RECORD OF CONFORMITY: Signed ITP
HP
RESPONSIBILITY: Superintendent / Site Engineer
Date Completed:
2.2 - Use of Geotextile
FREQUENCY: When placing drainage
ACCEPTANCE CRITERIA: Where geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contract with the wall when granular material is placed against the geotextile.
REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.08
INSPECTION/TEST METHOD: Site inspection
RECORD OF CONFORMITY: Signed ITP
IP
RESPONSIBILITY: Site Engineer
Date Completed:
2.3 - Installation of Subsoil Drainage
FREQUENCY: When placing drainage
ACCEPTANCE CRITERIA: Ensure bedding of thickness between 25-50mm is placed across the bottom of trench and graded to level. Pipes are firmly in place, slotted pipes positioned so openings are in lower half of the pipe
REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(d)
INSPECTION/TEST METHOD: Site inspection
RECORD OF CONFORMITY: Signed ITP
IP
RESPONSIBILITY: Site Engineer
Date Completed:
2.4 - Placing of Granular Filter Material
FREQUENCY: When placing drainage
ACCEPTANCE CRITERIA: Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the procedures and reviewed by the Superintendent.
REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(g)
INSPECTION/TEST METHOD: Document Review
RECORD OF CONFORMITY: Signed ITP
HP
RESPONSIBILITY: Superintendent / Site Engineer
Date Completed:
2.5 - Flushing Test
FREQUENCY: After drainage is placed
ACCEPTANCE CRITERIA: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction
REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(h)
INSPECTION/TEST METHOD: Site inspection
RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
WP
RESPONSIBILITY: Superintendent / Site Engineer
Date Completed:
2.6 - CCTV
FREQUENCY: After drainage is placed
ACCEPTANCE CRITERIA: All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(i)
INSPECTION/TEST METHOD: Site inspection
RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
HP
RESPONSIBILITY: Superintendent / Site Engineer
Date Completed: