## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | 36.01 - Conduits | itp |  |  |  |  | 36.01 - Conduits
section | Pre-Construction
checkpoint | 1.1 - Construction procedure submitted to the Client.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl.5.2
checkpoint | 1.2 - Asbestos presence assessment
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl 6.1
checkpoint | 1.3 - Material certifications submitted to the Client.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl.7.1
checkpoint | 1.4 - Drawing versions correct.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - IFC
checkpoint | 1.5 - Certificate of Supply (Authority to Construct) received
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - WCS34
checkpoint | 1.6 - Form 15 for footing design completed
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 2.4.2 MUTCD
checkpoint | 1.7 - Conduit, pit, footing and slab location and finished level surveyed and SI approved.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Hold Point
label | Reference - Clause 2.4.3 MUTCD
holdpoint | HOLD POINT
section | Conduit Installation
checkpoint | 2.1 - Bottom of trench compacted to form a firm uniform surface free from loose material.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Witness Point
label | Reference - MRTS91 Cl.9.1
checkpoint | 2.2 - Boring/Jacking Contractor and equipment approved by the SI and works are carried out by experienced operators.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Hold Point
label | Reference - MRTS91 Cl.8.7
holdpoint | HOLD POINT
checkpoint | 2.3 - Conduit installation approved by Superintendent and conduit will properly drain, contains no blockages and is not lower than pits that they are connected to.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl.9.1
checkpoint | 2.4 - Conduits in roadway backfill:
label | ○ TMR/GCCC/Energex - lean mix BCC – Unbound Pavement or Lean Mix to match existing permeability
label | ○ Passing Test Result: TMR - 95% RDD
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl.13.2
checkpoint | 2.5 - Conduits in footpath backfilled with insitu material, else MRS11.05 Type 2 material where insitu cannot be compacted.
label | ○ Passing Test Result: TMR - 90% RDD
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl.13.2
checkpoint | 2.6 - Conduit and conduit fittings proved by drawing a mandrel of following size:
label | ○ TMR – 95% of ID and 95% of ID in length
label | ○ Energex:- 6mm less than ID and 100mm in length
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Hold Point
label | Reference - MRTS91 Cl 9.1
holdpoint | HOLD POINT
checkpoint | 2.7 - Any joints made in the draw rope shall be capable of resisting the same tensile load as the draw rope without such a joint. The joint shall not appreciably increase the diameter of the rope.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Witness Point
label | Reference - MRTS91 Cl 9.13
checkpoint | 2.8 - Vermin proofing of conduits with unspecified sealing system.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl 10.9
section | Completion Works
checkpoint | 3.1 - Submission of certification package to Energex including:
label | ○ Certificate of Test
label | ○ As-Con Drawings
label | ○ Product Audit
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
checkpoint | Final Verification
note | Responsible Officer
textbox | Print Name:
date | Date:
note | Verifying Authority
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 36.02 - Pits | itp |  |  |  |  | 36.02 - Pits
section | Pre-Construction
checkpoint | 1.1 - Construction procedure submitted to the Client.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl.5.2
checkpoint | 1.2 - Asbestos presence assessment
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl 6.1
checkpoint | 1.3 - Material certifications submitted to the Client.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl.7.1
checkpoint | 1.4 - Drawing versions correct.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - IFC
checkpoint | 1.5 - Certificate of Supply (Authority to Construct) received
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - WCS34
checkpoint | 1.6 - Form 15 for footing design completed
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 2.4.2 MUTCD
checkpoint | 1.7 - Conduit, pit, footing and slab location and finished level surveyed and SI approved.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Hold Point
label | Reference - Clause 2.4.3 MUTCD
holdpoint | HOLD POINT
section | Pit Installation
checkpoint | 2.1 - Soil under pit compacted to 95% RDD
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Witness Point
label | Reference - MRTS91 Cl.10.4
checkpoint | 2.2 - Compact bedding material to density index 60.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl.10.4
checkpoint | 2.3 - Lowest open end of conduits installed in poles and other field equipment enclosures shall be at least 50 mm higher than the surrounding finished surface level
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Witness Point
label | Reference - MRTS91 Cl.10.10
section | Completion Works
checkpoint | 3.1 - Submission of certification package to Energex including:
label | ○ Certificate of Test
label | ○ As-Con Drawings
label | ○ Product Audit
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
checkpoint | Final Verification
note | Responsible Officer
textbox | Print Name:
date | Date:
note | Verifying Authority
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 36.03 - Footing and Slabs | itp |  |  |  |  | 36.03 - Footing and Slabs
section | Pre-Construction
checkpoint | 1.1 - Construction procedure submitted to the Client.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl.5.2
checkpoint | 1.2 - Asbestos presence assessment
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl 6.1
checkpoint | 1.3 - Material certifications submitted to the Client.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl.7.1
checkpoint | 1.4 - Drawing versions correct.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - IFC
checkpoint | 1.5 - Certificate of Supply (Authority to Construct) received
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - WCS34
checkpoint | 1.6 - Form 15 for footing design completed
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 2.4.2 MUTCD
checkpoint | 1.7 - Conduit, pit, footing and slab location and finished level surveyed and SI approved.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Hold Point
label | Reference - Clause 2.4.3 MUTCD
holdpoint | HOLD POINT
section | Footing and slab Installation
checkpoint | 2.1 - Depth, base and sidewalls of footing’s and slab’s confirmed for each location
label | Acceptance Criteria & Frequency (Project Specific) - Verify & Hold Point
label | Check Item - Hold Point
holdpoint | HOLD POINT
checkpoint | 2.2 - Ragbolt/reinforcement assembly inspected prior to concrete pour. Concrete poured in accordance with MRTS70. Concrete inspected to ensure correct vibration, monitor placing time and check that material is placed to avoid segregation. Check surface finish.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS92 Cl.8.3.7, MRTS70
checkpoint | 2.3 - Concrete tested for slump and compressive strength by NATA laboratory
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS70
checkpoint | 2.4 - Form 16 provided to client verifying footing construction completed in accordance with drawings
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Project Specific
section | Completion Works
checkpoint | 3.1 - Submission of certification package to Energex including:
label | ○ Certificate of Test
label | ○ As-Con Drawings
label | ○ Product Audit
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
checkpoint | Final Verification
note | Responsible Officer
textbox | Print Name:
date | Date:
note | Verifying Authority
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off