## Guard Rail W Type Install Rail
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Guard Rail W Type Install Rail and NUCOR Steel Posts |  |  | DN-GD-GP137 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/South Roads | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare the Site |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP137 | NO | R | R | H |  |  | W & I | Supplier
2 | Place Post |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP137 | NO | R | R | H
3 | Erect Guardrail |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP137 | NO | W(10%) | R | H
4 | Attach Terminal End |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP137 | NO | W(10%) | R | H
5 | Finishing |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP137 | NO | W(10%) | R | H
6 | Test and Check |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP137 | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 02/02/2024 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## Guard Rail ‘W Type’ Install Rai
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Guard Rail ‘W Type’ Install Rail and Wooden Posts |  |  | DN-GD-GP138 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/South Roads | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare the Site |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP138 | NO | R | R | H |  |  | W & I | Supplier
2 | Place Posts |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP138 | NO | R | R | H
3 | Erect Guardrail |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP138 | NO | W(10%) | R | H
4 | Finishing |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP138 | NO | W(10%) | R | H
5 | Test and Check |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP138 | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 02/02/2024 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## Guard Rail W Type Repair
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Guard Rail W Type Repair Section of Rail and NUCOR Steel Posts |  |  | DN-GD-GP139 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/South Roads | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare the Site |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP139 | NO | R | R | H |  |  | W & I | Supplier
2 | Assemble Rails |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP139 | NO | W(10%) | R | H
3 | Install Posts |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP139 | NO | W(10%) | R | H
4 | Finishing |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP139 | NO | W(10%) | R | H
5 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP139 | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 02/02/2024 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## Guard Rail W Type Repair WP
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Guard Rail W Type Repair Section of Rail and Wooden Posts |  |  | DN-GD-GP140 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/South Roads | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare the Site |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP140 | NO | R | R | H |  |  | W & I | Supplier
2 | Assemble Rails |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP140 | NO | R | R | H
3 | Install Posts |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP140 | NO | W(10%) | R | H
4 | Finishing |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP140 | NO | W(10%) | R | H
5 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP140 | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 02/02/2024 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## Guardrail Construct Thriebeam
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Guardrail Construct Thriebeam™ Type with Steel ‘I’ Posts |  |  | DN-GD-GP141 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/South Roads | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare the Site |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP141 | NO | R | R | H
2 | Place Posts |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP141 | NO | R | R | H
3 | Installation of 'modified block-outs' and 'back-up plates' |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP141 | NO | W(10%) | R | H
4 | Erect Guardrail |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP141 | NO | W(10%) | R | H
5 | Attach Terminal End |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP141 | NO | W(10%) | R | H
6 | Finishing |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP141 | NO | W(10%) | R | H
7 | Test and Check |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP141 | YES | W(10%) | R | H
11 | Spreading Passes 1-2 |  | XXX |  |  |  |  | - | - | - | -
12 | Test and Check |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 02/02/2024 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -

## Guardrail Repair Thriebe
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Guardrail Repair Thriebeam™ Type with Steel ‘I’ Posts |  |  | DN-GD-GP142 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/South Roads | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare the Site |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP142 | NO | R | R | H
2 | Restore Rail |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP142 | NO | W(10%) | R | H
3 | Restore Posts |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP142 | NO | W(10%) | R | H
4 | Installation of "modified block-outs" and "back-up plates" |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP142 | YES | W(10%) | R | H
5 | Finishing |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP142 | YES | W(10%) | R | H
6 | Test and Check |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP142 | YES | W(10%) | R | H
11 | Spreading Passes 1-2 |  | XXX |  |  |  |  | - | - | - | -
12 | Test and Check |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 02/02/2024 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -