## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - CONOC NETWORK - Guard Rail W Type Install Rail and NUCOR Steel Posts | itp |  |  |  |  | ITP - CONOC NETWORK - Guard Rail W Type Install Rail and NUCOR Steel Posts
checkpoint | 1 - Prepare the Site
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP137
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Place Post
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP137
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Erect Guardrail
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP137
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Attach Terminal End
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP137
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Finishing
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP137
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP137
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC NETWORK - Guard Rail W Type Install Rail and Wooden Posts | itp |  |  |  |  | ITP - CONOC NETWORK - Guard Rail W Type Install Rail and Wooden Posts
checkpoint | 1 - Prepare the Site
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP138
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Place Posts
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP138
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Erect Guardrail
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP138
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Finishing
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP138
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP138
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC NETWORK - Guard Rail W Type Repair Section of Rail and NUCOR Steel Posts | itp |  |  |  |  | ITP - CONOC NETWORK - Guard Rail W Type Repair Section of Rail and NUCOR Steel Posts
checkpoint | 1 - Prepare the Site
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP139
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Assemble Rails
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP139
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Install Posts
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP139
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Finishing
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP139
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP139
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC NETWORK - Guard Rail W Type Repair Section of Rail and Wooden Posts | itp |  |  |  |  | ITP - CONOC NETWORK - Guard Rail W Type Repair Section of Rail and Wooden Posts
checkpoint | 1 - Prepare the Site
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP140
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Assemble Rails
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP140
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Install Posts
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP140
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Finishing
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP140
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP140
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC NETWORK - Guardrail Construct Thriebeam Type with Steel 'I' Posts | itp |  |  |  |  | ITP - CONOC NETWORK - Guardrail Construct Thriebeam Type with Steel 'I' Posts
checkpoint | 1 - Prepare the Site
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP141
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Place Posts
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP141
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Installation of 'modified block-outs' and 'back-up plates'
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP141
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Erect Guardrail
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP141
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Attach Terminal End
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP141
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Finishing
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP141
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP141
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC NETWORK - Guardrail Repair Thriebeam Type with Steel 'I' Posts | itp |  |  |  |  | ITP - CONOC NETWORK - Guardrail Repair Thriebeam Type with Steel 'I' Posts
checkpoint | 1 - Prepare the Site
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP142
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Restore Rail
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP142
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Restore Posts
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP142
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Installation of "modified block-outs" and "back-up plates"
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP142
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Finishing
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP142
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP142
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT