## S109 EW and Drainage Mat R1
Earthworks And Drainage Materials Inspection and Test Plan
Project: Arnold Dam
Number and Revision: DS2672-ITP-S109 - Rev 1
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.01 | General
4.01.01 | IANZ Laboratory | The laboratory shall be IANZ accredited for the specific testing required. The nominated Contractor shall submit details (including certificates, etc) of intended personnel and equipment for approval at least one week prior to the commencement of earthworks. | 14AED/AD4-C - 030.18.1 / 30.17 | IANZ Certification | One Week Prior to Earthworks | R | PE
4.01.02 | NDM Operator and Equipment | Submit details (including certificates, etc) of intended personnel and equipment for approval at least one week prior to the commencement of earthworks. | 14AED/AD4-C - 030.18.1 | Training Records | One week prior to the commencement of earthworks. | HP | ENG
4.01.03 | Earthworks Supervisor | Nominated Contractor shall appoint an experienced full-time earthworks supervisor, whose duties shall include the control of filling operations in accordance with this specification. | 14AED/AD4-C - 30.17 | Approval | Prior to Works | R | PE
4.02 | Buttress Fill Materials
4.02.01 | Buttress Fill Sieve Analysis | Buttress fill shall be granular material obtained on-site either from undercut or from borrow areas. | 14AED/AD4-C - 030.13.1 / 030.18.1 | IANZ PSD | 1 set from the first lift, and 1 set per 500 m3 thereafter. | R | PE
4.02.02 | Buttress Fill MDD | Buttress fill shall be tested for Heavy Compaction test (Proctor Test). Where appropriate, an oversize correction shall be applied to the target density derived from laboratory compaction tests. | 14AED/AD4-C - 030.18.1 | IANZ MDD | 2 sets at commencement of project. | R | PE
4.03 | Drainage Materials
4.03.01 | HDPE Welder | HDPE pipes shall be joined using the electro-fusion method. To ensure the full strength of the pipe is achieved and the connections are of a consistent quality, installers must be properly trained and certified. | 14AED/AD4-C - 040.5.1 | Training Records | Prior to Welding | R | PE
4.03.02 | HDPE Welding Equipment | The HDPE Welder and power supply used for the fusion couplers shall be of a high quality and have the capability of readily fusing pipes of the specified diameter and wall thickness. | 14AED/AD4-C - 040.5.1 | Datasheets | Prior to Welding | R | PE
4.03.03 | Filter / Drainage F1, F2, F3 Weathering Resistance | Zone F1, F2, F3 shall be tested for Weathering quality index | 14AED/AD4-C - 030.18.1 | IANZ Weathering Report | 1 test for each material type | R | PE
4.03.04 | Filter / Drainage Zone F1 Sieve Analysis | Filter / drainage Zone F1 shall be tested for Sieve Analysis and fines testing | 14AED/AD4-C - 030.18.1 / 030.13.2 | IANZ PSD / Fines Test | 1 pre-construction. 1 on initial placement. 2 further samples during placement. | R | PE
4.03.05 | Filter / Drainage Zone F2 Sieve Analysis | Filter / drainage Zone F2 shall be tested for Sieve Analysis and fines testing | 14AED/AD4-C - 030.18.1 / 030.13.3 | IANZ PSD / Fines Test | 1 pre-construction. 1 on initial placement. 5 further samples during placement. | R | PE
4.03.06 | Filter / Drainage Zone F3 Sieve Analysis | Filter / drainage Zone F3 shall be tested for Sieve Analysis and fines testing | 14AED/AD4-C - 030.18.1 / 030.13.4 | IANZ PSD / Fines Test | 1 pre-construction. 1 on initial placement. 3 further samples during placement. | R | PE
4.03.07 | Subsoil Drain Pipes | Subsoil drain pipes shall be DN200 HDPE PN10 pipe. Five rows of 5mm holes shall be drilled at 75mm spacing along the length of the pipe, with the perforated portion of the pipe laid upwards. | 14AED/AD4-C - 040.4.1 | Datasheet / Inspection | Prior to Works | R | PE
4.03.08 | Drainage Outlet Pipe | Where shown on the drawings, all outlet pipes shall be DN630 HDPE PN12.5 pipe with standard dimension ratios as indicated. | 14AED/AD4-C - 040.4.2 | Datasheet | Prior to Works | R | PE
4.04 | Rip Rap Materials
4.04.01 | Rip Rap Source | Only hard, sound rock of uniform quality not subject to deterioration or breakdown will be acceptable. The rock shall be free of defined cleavage planes and should not be adversely affected by wetting and drying. | 14AED/AD4-C - 030.13.5 | Source Properties / Investigation | Prior to use | R | PE
4.04.02 | Rip Rap Grading | Rock riprap shall not be single sized but shall be a well graded mixture designed to ensure that all interstices between large rocks are filled with rock of progressively smaller size. | 14AED/AD4-C - 030.13.5 | On Site PSD / Investigation | Prior to use | R | PE
4.04.03 | Rip Rap Rock Shape | Rock should preferably be predominantly angular in shaped with not more than 25% of rocks, distributed through the gradation, having a length more than twice the breadth or thickness. | 14AED/AD4-C - 030.13.5 | On Site PSD / Investigation | Prior to use | R | PE
4.05 | River Diversion Materials
4.05.01 | Site Derived Granular Fill | River Diversion shall be Site Derived Granular Fill | DWG - 14AED-AD4-111 | Site Records | Prior to use | R | PE
4.05.02 | Bidim | River Diversion Bidim shall be A39 filter fabric. | DWG - 14AED-AD4-111 | Datasheet | Prior to Works | R | PE

## S110 EW General and Setup R2
Earthworks Overarching and Diversion Inspection and Test Plan
Project: Arnold Dam
Number and Revision: DS2672-ITP-S110 - Rev 1
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | Site Requirements
3.01.01 | Construction Pack | Submit a Construction Pack including a Methodology and JESA to the Engineer before works | Downer | Construction Pack | Submit Prior to commencement of works | H | PE
3.01.02 | Survey Setout | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Downer | Survey Records | Prior to Works | H | SV
3.01.03 | Service Location | Complete the Excavation permit process to identify, locate and protect all services. | Downer | Excavation Permit | Prior to Excavation | H | SE
3.01.04 | Internal Permits | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Downer | Internal Permits | Prior to Excavation | H | SE
3.01.05 | External Permits | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | Downer | External Permits | Prior to Excavation | H | PE
3.01.06 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE
3.02 | Hold Points
3.02.03 | Diversion Notice | The Consent Holder shall inform a Compliance Officer of the Consent Authority at least five working days prior to any diversion taking place to allow an inspection of the works to be undertaken. | P&G 14 | Notice | At least five working days prior to any diversion | HP | ENG
SECTION 5 – CONSTRUCTION ACTIVITY – BULK EARTHWORKS AND DRAINAGE
5.01 | Erosion and Sediment Controls
5.01.01 | Certification | Prior to bulk earthworks commencing, the nominated Contractor shall submit asbuilt drawings to the Engineer for approval, and to confirm the erosion and sediment controls have been constructed in accordance with the approved E&SCP and Resource Consent conditions. | 14AED/AD4-C - 020.5.7 | Jet-Grouting Asbuilt Drawings | Prior to Bulk Earthworks | HP | ENG
5.01.02 | Seasonal Restriction | No vegetation removal or earthworks on the site shall be undertaken between 30 April and 1 October in any year, without the written approval of the Engineer. Earthworks in this regard refers to bulk earthworks (cut/fill/waste) associated with the site. | 14AED/AD4-C - 020.5.9 | Hold Point Release | Each Occurrence | HP | ENG
5.02 | Diversion
5.02.01 | Diversion Management Plan | The nominated contractor shall prepare a management plan covering all work below river level and submit it to the Engineer for review. | 14AED/AD4-C - 030.4 | Management Plan | Prior to Works | HP | ENG
5.02.02 | Diversion Bund Methodology | The Diversion bund shall be constructed using site-derived granular soils, with rock rip-rap on both the upstream and downstream shoulders. The nominated Contractor shall provide a method statement for construction of the bund for the approval of the Engineer. | 14AED/AD4-C - 030.13.6 | Methodology | Prior to Works | HP | ENG
5.02.03 | Completed spillway strengthening works | Completed spillway strengthening works (by others) prior to commencement of diversion works must be inspected by the Engineer prior to further work being carried out in the area. | 14AED/AD4-C - 030.3 | Hold Point Release | 48 Hours Notice Prior to Each Occurrence | HP | ENG
SECTION 10 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
10.01 | Site Post Construction Activities
10.01.01 | Construction Record Compilation | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Downer | Records | Post construction | H | SE
10.01.02 | Survey Records | Ensure all items have been surveyed and records are assembled for asbuilting | Downer P&G 20.1 | Records | Post construction | H | SV
10.01.03 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red-pen mark-up copies of the Drawings and Specifications and other design documentation showing any deviations from the specified details and requirements produced in accordance with industry good practice. | Downer P&G 20.1 | Redlines | Post construction | H | PE
10.01.04 | Defect, Snag and Punch List | Update the project Defect, Snag and Punch List Register | Downer | Register | Post construction | H | PE

## S121 EW - Section 1 R1
Earthworks - Section 1 - Inspection and Test Plan
Project: Arnold Dam
Number and Revision: DS2672-ITP-S110 - Rev 1
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 5 – CONSTRUCTION ACTIVITY – BULK EARTHWORKS AND DRAINAGE
5.03 | Clearing, Stripping, and Excavation
5.03.05 | Tree and Bush Clearing | No trees or bush shall be cleared without approval from the Engineer. | 14AED/AD4-C - 030.7.2 | Hold Point Release | Prior to Removal | HP | ENG
5.03.03 | Organic Material Removal | All organic material shall be removed from the areas subject to excavation or filling. Turf, topsoil, and any scrub shall be removed to expose soil containing insignificant amounts of organic material. | 14AED/AD4-C - 030.7.1 | Site Records / Photos | When encountered | A | PE
5.03.01 | Excavation of Upper Dam Shoulder Inspection (Section 1) | Excavation of upper dam shoulder at interface with spillway block and cut-off wall, placement of filter and drainage materials: full-time designer site presence must be inspected by the Engineer prior to further work being carried out in the area. | 14AED/AD4-C - 030.3 | Hold Point Release | 48 Hours Notice Prior to Each Occurrence | HP | ENG
5.03.04 | Topsoil Stockpiling | All significant volumes of topsoil shall be stockpiled for later re-use. Materials containing insufficient amounts of topsoil for practical separation shall be disposed of in dump areas to be designated by the Engineer. | 14AED/AD4-C - 030.7.1 | Site Records / Photos | When encountered | A | PE
5.03.06 | Surface Water Control | All earthworks shall be carried out in the dry. Both cut and fill areas shall be sloped adequately during construction so that they do not pond water and temporary drains shall be provided as necessary to ensure the effective removal of stormwater from the areas of operation into the site drainage system. | 14AED/AD4-C - 030.7.3 | Site Records / Photos | During Works | R | SE
5.03.08 | Water in Excavation | The excavation shall be free of water at all times | 14AED/AD4-C - 030.10 | Site Records / Photos | Daily | M | SE
5.03.09 | Dewatering Sump Backfilling | Sumps formed for the purposes of dewatering shall be backfilled and compacted in layers with suitable fill to the approval of the Engineer. | 14AED/AD4-C - 030.10 | Site Records / Photos | Each Sump | HP | ENG
5.03.07 | Unsuitable Material Removal | Unsuitable material shall be excluded from the construction works and be placed in a disposal area as directed by the Engineer in loose layer thicknesses not exceeding 500 mm and be track rolled with a minimum of two passes. | 14AED/AD4-C - 030.14.7 | Site Records / Photos | When encountered | R | SE
5.03.10 | Bulk Excavation | Excavation within the buttress footprint shall be to intact rock, which is anticipated to be weak siltstone. | 14AED/AD4-C - 030.8 | Site Records / Photos | During Works | I | SE
5.03.11 | Bulk Excavation Protection | No compaction or trafficking on the exposed rock shall be undertaken, as it is likely that the surface will be sensitive to disturbance and deterioration. | 14AED/AD4-C - 030.8 | Site Records / Photos | During Works | R | SE
5.03.12 | Subgrade Inspection | On completion of the bulk excavation, inspection and testing of the subgrade shall be performed by the Engineer. | 14AED/AD4-C - 030.8 | Hold Point Release | 48 Hours Notice Prior to Each Occurrence | HP | ENG
5.03.13 | Inspection Prior to Filling | Before fill is placed in any area, the Engineer shall be notified so that he may inspect the stripping and/or removal of unsuitable materials to see that this prior work meets with the specified requirements. No filling shall be undertaken until inspections have been made and the Engineer has approved the commencement to fill. | 14AED/AD4-C - 030.11 | Hold Point Release | Prior to Filling | HP | ENG

## S122 EW - Section 2 to 9 R1
Earthworks - Section 2 to 9 - Inspection and Test Plan
Project: Arnold Dam
Number and Revision: DS2672-ITP-S110 - Rev 1
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 5 – CONSTRUCTION ACTIVITY – BULK EARTHWORKS AND DRAINAGE
5.03 | Clearing, Stripping, and Excavation
5.03.05 | Tree and Bush Clearing | No trees or bush shall be cleared without approval from the Engineer. | 14AED/AD4-C - 030.7.2 | Hold Point Release | Prior to Removal | HP | ENG
5.03.03 | Organic Material Removal | All organic material shall be removed from the areas subject to excavation or filling. Turf, topsoil, and any scrub shall be removed to expose soil containing insignificant amounts of organic material. | 14AED/AD4-C - 030.7.1 | Site Records / Photos | When encountered | A | PE
5.03.02 | Excavated upper dam shoulder Inspection (Section 2 to 9) | Excavated upper dam shoulder, each subsequent 20m wide section prior to placement of filter and drainage materials must be inspected by the Engineer prior to further work being carried out in the area. | 14AED/AD4-C - 030.3 | Hold Point Release | 48 Hours Notice Prior to each subsequent 20m wide section | HP | ENG
5.03.04 | Topsoil Stockpiling | All significant volumes of topsoil shall be stockpiled for later re-use. Materials containing insufficient amounts of topsoil for practical separation shall be disposed of in dump areas to be designated by the Engineer. | 14AED/AD4-C - 030.7.1 | Site Records / Photos | When encountered | A | PE
5.03.06 | Surface Water Control | All earthworks shall be carried out in the dry. Both cut and fill areas shall be sloped adequately during construction so that they do not pond water and temporary drains shall be provided as necessary to ensure the effective removal of stormwater from the areas of operation into the site drainage system. | 14AED/AD4-C - 030.7.3 | Site Records / Photos | During Works | R | SE
5.03.08 | Water in Excavation | The excavation shall be free of water at all times | 14AED/AD4-C - 030.10 | Site Records / Photos | Daily | M | SE
5.03.09 | Dewatering Sump Backfilling | Sumps formed for the purposes of dewatering shall be backfilled and compacted in layers with suitable fill to the approval of the Engineer. | 14AED/AD4-C - 030.10 | Site Records / Photos | Each Sump | HP | ENG
5.03.07 | Unsuitable Material Removal | Unsuitable material shall be excluded from the construction works and be placed in a disposal area as directed by the Engineer in loose layer thicknesses not exceeding 500 mm and be track rolled with a minimum of two passes. | 14AED/AD4-C - 030.14.7 | Site Records / Photos | When encountered | R | SE
5.03.10 | Bulk Excavation | Excavation within the buttress footprint shall be to intact rock, which is anticipated to be weak siltstone. | 14AED/AD4-C - 030.8 | Site Records / Photos | During Works | I | SE
5.03.11 | Bulk Excavation Protection | No compaction or trafficking on the exposed rock shall be undertaken, as it is likely that the surface will be sensitive to disturbance and deterioration. | 14AED/AD4-C - 030.8 | Site Records / Photos | During Works | R | SE
5.03.12 | Subgrade Inspection | On completion of the bulk excavation, inspection and testing of the subgrade shall be performed by the Engineer. | 14AED/AD4-C - 030.8 | Hold Point Release | 48 Hours Notice Prior to Each Occurrence | HP | ENG
5.03.13 | Inspection Prior to Filling | Before fill is placed in any area, the Engineer shall be notified so that he may inspect the stripping and/or removal of unsuitable materials to see that this prior work meets with the specified requirements. No filling shall be undertaken until inspections have been made and the Engineer has approved the commencement to fill. | 14AED/AD4-C - 030.11 | Hold Point Release | Prior to Filling | HP | ENG

## S111 Drainage R2
Master Inspection and Test Plan
Project: Arnold Dam
Number and Revision: DS2672-ITP-S111 - Rev 1
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 5 – CONSTRUCTION ACTIVITY – BULK EARTHWORKS AND DRAINAGE
5.04 | Placement and Compaction of Fill General
5.04.02 | Surface Water Control | Cut and fill areas shall be sloped and graded adequately so that they do not pond stormwater, and drains shall be installed as necessary on a regular basis to deflect run off from the areas of operation, or to drain ponded water as soon as ponds are seen to develop. | 14AED/AD4-C - 034.14.1 | Site Records / Photos | Daily | R | SE
5.04.03 | Wet Weather | No fill shall be placed during periods of wet weather. | 14AED/AD4-C - 034.14.1 | Site Records / Photos | Daily | M | SE
5.04.04 | Extended Wet Weather Resumption Approval | In the event of fill operations ceasing in any area on account of wet weather or for more than one week for any reason, the nominated Contractor shall obtain the Engineer’s approval of the conditions of the fill surface before recommencing fill operations. | 14AED/AD4-C - 034.14.1 | Hold Point Release | Each Occurrence | HP | ENG
5.04.05 | Compaction Adjacent to Retaining Structures | Rollers shall not be operated within 2m of retaining walls with placement of fill in 200mm maximum thickness lifts and compaction shall be via hand equipment or a small roller without vibration. | 14AED/AD4-C - 034.14.3 | Site Records / Photos | Each Structure | V | SE
5.05 | F1, F2 and F3 Placement and Compaction
5.05.01 | Preparation of stripped ground surface inspection | Preparation of stripped ground surface prior to placement of site concrete must be inspected by the Engineer prior to further work being carried out in the area. | 14AED/AD4-C - 030.3 | Hold Point Release | 48 Hours Notice Prior to Each Occurrence | HP | ENG
5.05.02 | Excavated lower dam shoulder / foundation Inspection | Excavated lower dam shoulder/foundation, each 20m wide section prior to placement of filter and drainage materials must be inspected by the Engineer prior to further work being carried out in the area. | 14AED/AD4-C - 030.3 | Hold Point Release | 48 Hours Notice Prior to Each Occurrence | HP | ENG
5.05.03 | Placement of filter and drainage material Inspection at Upper dam shoulder | Placement of filter and drainage material, a full-time designer site presence must be inspected by the Engineer prior to further work being carried out in the area. | 14AED/AD4-C - 030.3 | Hold Point Release | 48 Hours Notice Prior to Each Occurrence | HP | ENG
5.05.04 | Placement of Drainage Material | Filter/drainage material shall be placed in a way which prevents segregation, contamination or breakdown of particles with the maximum loose lift thickness for filter/drainage materials is 200mm. | 14AED/AD4 -C -034.14.5 | Site Records / Photos | Each Layer | C | SE
5.05.05 | Compaction of Drainage Material | Where space constraints allow, compaction shall comprise two passes with a self-propelled smooth-drum roller without vibration. In areas where space constraints prevent the use of a roller, compaction shall comprise two passes with a vibrating plate compactor or similar. | 14AED/AD4 -C -034.14.5 | Site Records / Photos | Each Layer | C | SE
5.05.06 | Excessive Compaction of Drainage Material | The nominated Contractor shall ensure excessive compaction is avoided as this may reduce drain permeability. The nominated Contractor shall avoid damage to pipes. If pipes are damaged, they shall be removed and replaced. | 14AED/AD4 -C -034.14.5 | Site Records / Photos | Each Layer | M | SE
5.05.07 | Surface Drainage | Construction of drainage works shall be staged such that sub-surface drains do not act as surface drains or can be otherwise contaminated by siltation or vehicle trafficking prior to placement of buttressing bulk fill. | 14AED/AD4 -C -034.14.5 | Construction Pack | Prior to works | M | SE
5.06 | Subsoil Drainage
5.06.01 | Subsoil Drainage Timing | The subsoil drainage system shall be installed prior to the commencement of filling operations. | 14AED/AD4-C - 030.12 | Site Records / Photos | Prior to the commencement of filling | R | PE
5.06.02 | Installation of all new drainage pipes Inspection | Installation of all new drainage pipes in buttress, prior to backfilling must be inspected by the Engineer prior to further work being carried out in the area. | 14AED/AD4-C - 030.3 / 040.4.1 | Hold Point Release | 48 Hours Notice Prior to Each Occurrence | HP | ENG
5.06.03 | Subsoil Drainage Grading | The subsoil drains and collector pipe shall be uniformly graded to ensure they do not hold water and evenly jointed to ensure unimpeded flow. | 14AED/AD4-C - 030.12 | Survey Records | During Installation | D | SV
5.06.04 | Bedding for Pipes | Embedment material for drainage pipes within the buttress shall comprise Zone F3 drainage material. | 14AED/AD4-C - 040.4.3 | Site Records / Photos | Each Pipe | I | SE

## S112 Buttress Fill
Master Inspection and Test Plan
Project: Arnold Dam
Number and Revision: DS2672-ITP-S112 - Rev 1
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 5 – CONSTRUCTION ACTIVITY – BULK EARTHWORKS AND DRAINAGE
5.04 | Placement and Compaction of Fill General
5.04.02 | Surface Water Control | Cut and fill areas shall be sloped and graded adequately so that they do not pond stormwater, and drains shall be installed as necessary on a regular basis to deflect run off from the areas of operation, or to drain ponded water as soon as ponds are seen to develop. | 14AED/AD4-C - 034.14.1 | Site Records / Photos | Daily | R | SE
5.04.03 | Wet Weather | No fill shall be placed during periods of wet weather. | 14AED/AD4-C - 034.14.1 | Site Records / Photos | Daily | M | SE
5.04.04 | Extended Wet Weather Resumption Approval | In the event of fill operations ceasing in any area on account of wet weather or for more than one week for any reason, the nominated Contractor shall obtain the Engineer’s approval of the conditions of the fill surface before recommencing fill operations. | 14AED/AD4-C - 034.14.1 | Hold Point Release | Each Occurrence | HP | ENG
5.04.05 | Compaction Adjacent to Retaining Structures | Rollers shall not be operated within 2m of retaining walls with placement of fill in 200mm maximum thickness lifts and compaction shall be via hand equipment or a small roller without vibration. | 14AED/AD4-C - 034.14.3 | Site Records / Photos | Each Structure | V | SE
5.07 | Buttress Fill Placement and Compaction
5.07.01 | Start of the buttress filling Inspection | Start of the buttress filling operation must be inspected by the Engineer prior to further work being carried out in the area. | 14AED/AD4-C - 030.3 | Hold Point Release | 48 Hours Notice Prior to Each Occurrence | HP | ENG
5.07.02 | Compaction Effort | Compaction of granular earthfill shall be carried out using a 10-tonne (minimum static weight), smooth steel drum vibrating roller, or approved equivalent and shall be demonstrated and conformance confirmed via a compaction trial. | 14AED/AD4-C - 034.14.2 | Site Records / Compaction Trial | Prior to Works | V | PE
5.07.03 | Buttress Fill | Each fill layer for dam fill shall be given the higher of the trail result or four passes with vibration, even if the acceptance standard is met with fewer passes. No pumping of weaving of granular fill is permitted. | 14AED/AD4 -C - 034.14.4 / 034.14.1 | Site Records / Photos | Each layer | V | SE
5.07.04 | Borrow Fill Moisture Content | Prior to removal of material from a borrow area wet or dry the material to a uniform moisture content close to optimum for the material. | 14AED/AD4-C - 034.14.2 | Site Records / Photos | Daily | C | SE
5.07.05 | Placement and Compaction of Dam Fill | Spread out the fill in a layer of uniform loose thickness. Loose layer thickness shall not exceed 300mm for granular earthfill. | 14AED/AD4-C - 034.14.2 | Site Records / Photos | Each layer | V | SE
5.07.06 | Buttress Fill Compaction | Buttress Fill shall be compacted to an average density to 97%MDD and a minimum of 95%MDD for any one test over 10 consecutive test sets. A set of tests shall comprise two or more individual tests made within an area of 0.5m². In-situ moisture/ density (NDM method with laboratory moisture content) | 14AED/AD4-C - 034.14.4 / 030.18.1 | NDM Records | 10 tests (5 sets) per 500mm placed | I | SE
5.07.07 | Buttress Fill Proof Rolling | The deflection of the compacted fill surface for any lift during a proof roll with a 10t smooth drum roller shall be less than 7mm. | 14AED/AD4-C - 034.14.4 / 030.18.1 | Proof Roll | Each layer | I | SE
5.07.08 | Steep Slope Key | Where dam fill abuts sloping ground steeper than 18º (1V:3H), the natural ground or fill being filled against shall be keyed in. The horizontal width of the key shall be equal to the thickness of the compacted layer. | 14AED/AD4-C - 034.14.2 | Site Records / Photos | Each Occurrence | C | SE
5.07.09 | Overfilling dam embankments | During construction, the batters shall be overfilled by a minimum of 1m (horizontal), and this overfill should be pulled up by digger, and used as the final lift(s) of fill on the dam crest. | 14AED/AD4-C - 034.14.2 | Site Records / Photos | Final Embankment Layer | C | SE
5.07.10 | Dam Fill Tolerances and Profiles | The finished tolerances for the dam crest level is -0/+200mm. For upstream and downstream batters finished tolerances are –100/+200mm (vertical height), and the surface shall be visually regular. | 14AED/AD4-C - 030.14.8 | Survey Records | Finished Fill | D | SV
5.07.11 | Completed buttressing works Inspection | Completion of buttressing works to final level must be inspected by the Engineer prior to further work being carried out in the area. | 14AED/AD4-C - 030.3 | Hold Point Release | 48 Hours Notice Prior to Each Occurrence | HP | ENG

## S113 Rip Rap
Master Inspection and Test Plan
Project: Arnold Dam
Number and Revision: DS2672-ITP-S113 - Rev 1
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 5 – CONSTRUCTION ACTIVITY – BULK EARTHWORKS AND DRAINAGE
5.08 | Rip Rap Installation
5.08.01 | Foundation inspection | Prior to the placement of RIPRAP the foundation must be inspected by the Engineer prior to further work being carried out in the area. | DOWNER | Hold Point Release | 48 Hours Notice Prior to Each Occurrence | HP | ENG
5.08.02 | Placement of Rip Rap | Rip rap shall be machine placed such that segregation of breakage of stone does not occur. Dumping and spreading of rock shall not be permitted. Stone shall be released as close to is final position as practical to minimise dragging and rehandling. | 14AED/AD4-C - 030.14.6 | Site Records / Photos | Each Layer | C | SE
5.08.03 | Rip Rap Voids | Rip Rap shall have no significant voids occur in the rock blanket through which underlying material could be washed out. | 14AED/AD4-C - 030.13.5 | Site Records / Photos | Each Layer | C | SE
5.08.04 | Rip Rap Loose rocks | Rip Rap shall create an interlocking mass of rock in which no individual rock is free to move by itself; and | 14AED/AD4-C - 030.13.5 | Site Records / Photos | Each Layer | C | SE
5.08.05 | Rip Rap Protruding Rocks | Rip Rap shall create a shielding effect on the surface of the rock, which avoids high drag forces that occur when individual rocks protrude into the flow. | 14AED/AD4-C - 030.13.5 | Site Records / Photos | Each Layer | C | SE
5.08.06 | Rip Rap Post Installation PSD | The particle size distribution after handling and placement shall conform to the limits set in 030.13.5. | 14AED/AD4-C - 030.13.5 | Site Records / Photos | Each Layer | I | SE

## ITP Register
Inspection and Testing Plan Register
Project: Arnold Dam
Document Revision & Date: Rev: 01 - Date: 29/05/2023
Inspection and Testing Plan Register | [10 empty] | Rev: 01 | Date: 29/05/2023
ITP No. | Sub ITP No. | Master ITP Revision | Current Revision | Discipline | Description | Work Area / Chainage / Lot: | Work Commencement Date: | Work Completion Date | Work Status | Owner | Submission Status | Comments
1 | N/A | N/A | N/A | All | Master ITP | ALL Works
1 | S-101 | 1 | 1 | Jet Grouting | Jet Grouting Materials | All
1 | S-102 | 1 | 1 | Jet Grouting | Jet Grouting Trial | All
1 | S-103 | 1 | 1 | Jet Grouting | Jet Grouting Installation | All
1 | S-104 | 1 | 2 | Pilling | Piling Overarching Inspection and Test Plan | All
1 | S-105 | 1 | 2 | Pilling | Pile Construction Card Inspection and Test Plan | All
1 | S-106 | 1 | 2 | Pilling | Piling First Pile Hold Points Inspection and Test Plan | All
1 | S-107 | 1 | 2 | Pilling | Piling Logging Hold Points Inspection and Test Plan | All
1 | S-108 | 1 | 2 | Pilling | Piling Materials Inspection and Test Plan | All
1 | S-109 | 1 | 1 | Earthworks And Drainage | Earthworks And Drainage Materials Inspection and Test Plan | All
1 | S-110 | 1 | 1 | Earthworks And Drainage | Earthworks Overarching and Diversion Inspection and Test Plan | All
1 | S-111 | 1 | 1 | Earthworks And Drainage | Drainage Inspection and Test Plan | All
1 | S-112 | 1 | 1 | Earthworks And Drainage | Buttress Fill | All
1 | S-113 | 1 | 1 | Earthworks And Drainage | Rip Rap | All
1 | S-114 | 1 | 1 | Wall and Slab | Wall And Slab Materials
1 | S-115 | 1 | 1 | Wall and Slab | Wall And Slab Overarching
1 | S-116 | 1 | 1 | Wall and Slab | Wall And Slab Installation
1 | S-117 | 1 | 1 | Railway Walkway | Rail and Walkway Materials
1 | S-118 | 1 | 1 | Railway Walkway | Walkway Concrete Construction
1 | S-119 | 1 | 1 | Railway Walkway | Welding Finishing and Coating
1 | S-120 | 1 | 1 | Railway Walkway | Rail and Walkway Installation
1 | S-121 | 1 | 1 | Earthworks And Drainage | Earthworks - Section 1
1 | S-122 | 1 | 1 | Earthworks And Drainage | Earthworks - Section 2 to 9