## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-002 - Stripping Topsoil & Topsoil Placement | itp |  |  |  |  | ITP-002 - Stripping Topsoil & Topsoil Placement
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.3 Ensure correct materials are being used
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Topsoil placed on formations and disturbed areas shall be capable of supporting healthy, full cover of grass growth, and contain organic material
label | ○ Topsoil material shall be free from subsoil, tree roots, clay balls, stones, rocks, rubbish, contaminants, weeds, pathogens and toxic levels of any element with a pH in the range of 5 to 8.
label | ○ Imported topsoil shall conform to the material properties outlined in Table 720.042
label | REFERENCE DOCUMENTS: 204.04a
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed, Material Test Report (Import Only)
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
section | Stripping Topsoil
checkpoint | 2.1 Survey Set Out
label | FREQUENCY: Prior to commencing stripping
label | ACCEPTANCE CRITERIA: Area has been pegged out in accordance with the drawings
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Surveyor
textbox | Date Completed:
checkpoint | 2.2 Archaeological monitoring
label | FREQUENCY: Prior to commencing stripping
label | ACCEPTANCE CRITERIA: The Contractor shall immediately notify the Superintendent if an archaeological site is encountered, or if any suspected artefacts are found. A ‘No-Go Zone’ shall be established for identified Cultural Heritage sites that are to be protected during the work under the Contract and in accordance with the CHMP
label | REFERENCE DOCUMENTS: CHMP
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.3 Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation.
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.4 Designation of stock pile area or disposal site
label | FREQUENCY: Prior to commencing stripping
label | ACCEPTANCE CRITERIA: An area for stockpiling has been designated or a disposal site identified
label | REFERENCE DOCUMENTS: 204.05c
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.5 Weed treatment
label | FREQUENCY: Prior to commencing stripping
label | ACCEPTANCE CRITERIA: Site has been inspected for noxious weeds and weed treated if present
label | REFERENCE DOCUMENTS: 204.05c
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.6 Maintenance of stockpiles
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Stockpiles maintained neatly and away from stormwater drains
label | ○ Erosion controls in place
label | ○ Stockpile treated to minimise spread of weeds and pathogens
label | REFERENCE DOCUMENTS: 204.05c
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
section | Placing Topsoil
checkpoint | 3.1 Surface finish of cut and fill batters
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The surface of cut and fill batters to be topsoiled shall be textured by scarifying or horizontal grooving
label | REFERENCE DOCUMENTS: Cl 204.06 (i)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 3.2 Topsoil Placement
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Confirm underlying cut/fill areas comply with Cl204.03 before placing topsoil.
label | – All disturbed areas not paved or landscaped topsoiled to the following depths:
label | ○ batter slopes > 2:1 = 50mm min
label | ○ planting beds = 100mm min
label | ○ verge - 50mm outer edge to 20mm within 100mm of seal
label | ○ all other areas – 75mm min
label | REFERENCE DOCUMENTS: Cl 204.17
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 3.3 Surface level
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Area topsoiled spread, levelled, but not compacted (except verge area).
label | REFERENCE DOCUMENTS: Cl 204.17
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: