## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) | itp |  |  |  | Yes | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | 06ec5267-866b-4c86-9506-97de52634e90
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 18459930-d8bf-5a9f-837c-d390b2aafc2f |  | note | Document Title: ITP-CIV-CPD-Hot Mix Asphalt (Supply and Install)
label | 96144a59-7228-52d2-97d3-3ef13efc2eba |  | note | ITP Description: Hot Mix Asphalt (Supply and Install)
label | e37c4508-a1c3-54d5-8fd7-1924114dc8f2 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | bdaa64c8-ad1c-5707-96b6-6065068d358e |  | note | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
label | c5ffb4aa-5811-5392-8892-37094ef19397 |  | note | Revision Number: 0
label | 55760bfc-5a1e-58c6-ad99-e74343d9714b |  | note | Revision Date: 22/08/2023
label | ab4fc8b6-7d69-57f1-b44a-c71a535cbf14 |  | note | ITP created by: Ahmed ABDELSALAM
label | b2297ecc-bdfc-5a14-a8ef-66431f2d0473 |  | note | ITP approved for use by: Pradeep TALASILA
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 7dc8f174-bddf-5942-9923-024abf4936c0 |  | note | Reference - IFC Drawings Vic Roads 407, Vic Roads 404, Vic Roads 417 AS2150
checkpoint-group |  |  | section | 2. Preliminary Works
checkpoint-status |  |  | checkpoint | 2.1 - Mix Design & Trackless Tack Coat Approval
label | 061e3e14-c08a-5a80-bb7c-51f60aa2c1a0 |  | note | Reference - 407.09, 407.08(d) Mix Design Registration
label | 60958fc8-0679-5380-b4ee-a3fe58a383e5 |  | note | Acceptance Criteria - Mix design and trackless tack coat to be used has been approved by project superintendent, prior to use
label | 9319eba8-f24e-502a-ae42-f2cf6036ec12 |  | note | Method - Approval Correspondance
label | 9fc74144-8674-557b-bd08-35cfb7281eae |  | note | Frequency - Prior to commencing paving
label | f19e3ece-1353-54d0-99ba-e6974d3c1668 |  | note | Category - HP
label | ab8a4d71-01e5-515e-a3fc-e410e5e8c8fa |  | note | Responsibility - Project Engineer/ Supervisor
label | bcc249ef-9117-57d4-abe8-71d8311ac98d |  | note | Verifying Documents - Completed ITP
date | fd1d053b-8aed-5fe4-b2a5-f477ef3c5d4b |  | date | Date Completed:
text | 5870ca28-5bb4-53e6-a8f1-fdba3ec9a203 |  | textbox | Team Binder Approval Number
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Asphalt Placement and Lot Plan
label | fade3785-aa28-5455-bf46-4f60b26424a5 |  | note | Reference - Section 407.17
label | e281b48d-1316-519a-9c91-cb4e2bde76f7 |  | note | Acceptance Criteria - Asphalt placement and Lot plan to be created prior to commencement of works.
label | e388acf8-47a9-57e3-bf10-05c45ddc4e2d |  | note | ○ The location of all joints shall be planned before work commences to achieve the specified offsets between layers and the final position of joints in the wearing course.
label | 0e36a93e-1f67-59b9-b720-542a04914e3c |  | note | ○ Plan to specify start/end chainage, offset/lane and layer.
label | bfea3d18-69d9-5ac1-bab8-f72f6438d120 |  | note | Method - Verify
label | 963bb98b-d955-5956-8ec4-5b80ed598710 |  | note | Frequency - Each lot
label | dc52dc4a-094e-5ceb-8801-49639aeeade7 |  | note | Category - IP
label | 6b9ea933-b49e-5b22-bc0c-48421364a5f5 |  | note | Responsibility - Site Engineer/ Asphalt Supervisor
label | 7de782b9-4b69-5512-bc8e-28d76024f30b |  | note | Verifying Documents - Daily Lot Record
date | 815b8ee1-dacf-509e-a975-cf131cf65945 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Site Inspection and Base Condition
label | c63305a1-2b28-52c0-b77e-31a6c59279ec |  | note | Reference - 407.17 AS2150 10.1 AS2150 10.3
label | 35b682d0-36eb-5910-a673-17611be69fd2 |  | note | Acceptance Criteria - Surface on which asphalt is to be placed is essentially dry and free from puddles, defects (holes, cracks, unstable material and edge irregularities) and loose materials.
label | ccfb2874-e413-575f-9e41-3ac191b15f3a |  | note | Method - Visual Inspection
label | a9dbcca0-d203-5698-8f74-00a96423713c |  | note | Frequency - Prior to commencing paving
label | 27854199-91c6-588c-aced-23422e9df2e8 |  | note | Category - WP
label | 5c9df642-9fd6-56e5-ad17-c7f10fb0d8aa |  | note | Responsibility - Asphalt Supervisor
label | c3a4bc9c-7990-5fa2-8280-799f3cc0ff6a |  | note | Verifying Documents - Completed ITP
date | d82a9faf-e7dc-5397-91f8-a11181b5c4c3 |  | date | Date Completed:
text | 032848f2-d8b8-5f4b-bab0-07091f56d2b7 |  | textbox | Team Binder Approval Number
checkpoint-status |  |  | checkpoint | 2.4 - Ambient Conditions for Placing
label | 39362b2b-f86b-5079-80e5-e71ed0935db3 |  | note | Reference - 407.17
label | dc7184e2-3e25-5f69-b9ce-818edceb8173 |  | note | Acceptance Criteria - The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | 7fe3ea1d-c760-54c1-a861-5ab99623d180 |  | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
label | 3355e62f-17c7-5a97-983f-178261c76866 |  | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
label | 04001dae-9180-53d9-b886-a92c606ffbdd |  | note | ○ Where the above temperatures cannot be achieved, asphalt must be laid under the "Fulton Hogan Cold Weather Paving Plan"
label | fffbf003-3d0e-5bbe-af37-7ac049df9ab3 |  | note | Method - Infrared Thermometer
label | 43d02c54-8036-5e52-8701-59b495c41ffe |  | note | Frequency - Prior to commencing Paving
label | 3bf07dd4-46c0-5bfc-8677-bd96c927587f |  | note | Category - IP
label | 8476cdb2-7934-561b-99ae-3731ccd14cf6 |  | note | Responsibility - Asphalt Supervisor
label | e8d08644-1b0d-51e9-b3b8-d80e1dfd9ddf |  | note | Verifying Documents - Completed ITP
date | c035702a-42c4-567b-858a-b5bc5d2f4ea3 |  | date | Date Completed:
text | ae289b21-2a24-58e4-8ef6-2940ff11881d |  | textbox | Team Binder Approval Number
checkpoint-status |  |  | checkpoint | 2.5 - Planning of Joints
label | ebfc0b11-6cb8-55fa-b182-f9ec952001aa |  | note | Reference - 407.21
label | 8c6f8ca2-7b6c-500e-a8b5-e27e1b3378e3 |  | note | Acceptance Criteria - Runs to be marked to ensure placement of all Longitudinal Joints satisfy the following unless otherwise approved by the Client: Transverse Joints Offset from layer to layer by at least 2m Longitudinal Joints for the final Wearing Course are located on lane lines
label | 71618320-5455-5d0d-b720-ec2567a09bbb |  | note | ○ Longitudinal Joints for Intermediate and Base Layers offset from layer to layer by 150mm, and no more than 300mm from lane lines.Where new pavement abuts an existing full depth asphalt pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150 mm.
label | b3ae3744-5ca8-5114-9416-54d5a785f245 |  | note | ○ At the wearing surface where the new and existing pavement join, a hot applied bituminous crack sealant shall be applied.
label | 1cbbb87b-9b16-547f-a72d-cde8469606e7 |  | note | Method - Measure and mark out runs by tape measure or survey
label | ec630a31-6343-548e-bd5e-b210156620e0 |  | note | Frequency - Prior to commencing paving
label | 79da9765-c3f2-5cbf-aa39-8c9865ea3149 |  | note | Category - WP
label | ea46f3f3-f50f-5a2b-88a4-ceb1d2561cd1 |  | note | Responsibility - PE FHC
label | 876aa49b-309d-5518-9b0a-cfb15938b2e7 |  | note | Verifying Documents - Completed ITP
date | 8e54b79e-94ed-59a5-a07d-428cc1c9ec9a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - Tack Coat
label | 4ca7e6e2-959b-59a3-8464-98c2f0060f47 |  | note | Reference - 407.19 AS2150 11
label | 937eb937-22b4-558d-a0ae-e89d96d2a5c0 |  | note | Acceptance Criteria - Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2. This rate is to be doubled on joints and chases.
label | 356f90e5-b9c4-5699-ae2e-20fa5262379e |  | note | ○ Tack coat must be allowed to fully cure.
label | 98ab737f-96ca-5687-a5c6-edc51691e1c8 |  | note | NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces Photographical evidence must be obtained (with an identifiable landmark)
label | bfb41f3f-8bb0-575c-a3b6-b05da709cc22 |  | note | *from 1st July 2023, "trackless Tack Coat" must be used
label | 4bbb6c28-2641-57b6-a901-049d3eb6f369 |  | note | Method - Spray area and inspect
label | 038b1833-043e-5ae5-8f0c-8e1a2eb0a9e4 |  | note | Frequency - Prior to Commencing paving
label | 44910c3c-0a8e-52e2-9a42-91efeb570f9e |  | note | Category - IP
label | 7284b695-e885-59fa-bb09-782380fa74f4 |  | note | Responsibility - Asphalt Foreman
label | cea1b5cb-3762-5540-8037-6cab4dbca074 |  | note | Verifying Documents - Completed ITP
date | ba775944-c994-5600-b83b-02a6d9b650c5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Submission of Primer Material documents (if applicable)
label | 374a07ee-be35-5c82-8422-ce5d2d46cb3a |  | note | Reference - 408.08 c, e
label | db59a6cf-0fac-5f7f-bf16-5b982de27058 |  | note | Acceptance Criteria - The primer shall be cutback bitumen complying with the requirements of clause 408.08(c) and shall be water resistant, of uniform appearance and capable of providing a strong bond between the bituminous surfacing and the pavement.
label | 6d78d335-6732-5fb2-8529-28a55aec18cd |  | note | Method - Document Review
label | dc7822ff-acd7-5cb6-bb70-ad7ec7a587b2 |  | note | Frequency - Prior to commencing works
label | 34a34b7a-4d7d-57e5-9386-4cad2bb2aee0 |  | note | Category - HP*
label | 9a8e6213-0866-5c9c-afe4-f26beb78ad68 |  | note | Responsibility - Site Engineer/Project Engineer
label | be36a2fa-73c0-5703-b99c-6f74065d2d4b |  | note | Verifying Documents - Conformance Certificate uploaded to TeamBinder
date | 40733b85-ce5d-599e-97d6-7522de9ee34b |  | date | Date Completed:
text | 9e154799-623b-53d4-a37f-c1cdc8157a90 |  | textbox | Team Binder Approval Number
checkpoint-status |  |  | checkpoint | 2.8 - Application Rates for Primer (if applicable)
label | 2c1d0a4d-1d51-5fa0-bee3-b4afcfa53a6e |  | note | Reference - 408.13 a
label | 21fda06a-4cf7-56a9-b2f0-7932193cf6cf |  | note | Acceptance Criteria - At least one week prior to the commencement of work, the Contractor shall submit the initial design rates of application for bituminous material, aggregate, and rates for pre-treatment for review by the Superintendent
label | 94652226-3a76-58aa-93ab-642788441e86 |  | note | Method - Document Review
label | 1328907e-12d6-5c26-85b4-470f6ffe4d8f |  | note | Frequency - Prior to commencing works
label | c42956b7-f006-52c4-a2f6-45151ef13482 |  | note | Category - HP
label | a8fdc5ad-068b-58d8-907a-b512240c526b |  | note | Responsibility - Site Engineer, NA
label | 2b7c30df-2ddd-5508-bf96-65ebe01700e1 |  | note | Verifying Documents - Application Rates uploaded to TeamBinder
date | a087b4f2-8df4-54ee-ab12-a800344d935e |  | date | Date Completed:
text | 910fb660-2bb0-5305-be40-9be3187f5688 |  | textbox | Team Binder Approval Number
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Asphalt Placement Works
checkpoint-status |  |  | checkpoint | 3.1 - Commencement of placing
label | 25fa4f75-ee1d-5704-91a9-ca9786e9d489 |  | note | Reference - 407.23
label | 9aea9c39-1dc2-537e-9e81-36b6c3644364 |  | note | Acceptance Criteria - The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client's nominated authority.
label | 8126cd56-6c63-5513-8012-5631bb514e79 |  | note | Method - Visual Inspection
label | e895648f-0452-5a3e-9124-5f4b4c8443a8 |  | note | Frequency - Prior to Commencing paving
label | 029346a8-779a-546c-919d-313835fa8bd7 |  | note | Category - HP
label | 3760abda-76ba-58b7-a7b2-c2870f9b4145 |  | note | Responsibility - Asphalt Supervisor / Superintendent
label | f8d434cd-d711-5f93-bddd-5a3027a99180 |  | note | Verifying Documents - Completed ITP
date | 794b73c1-5a71-5e40-a8fa-e19ba6a16403 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Delivery of Mix
label | 990ae318-9942-593b-8c2e-13a7a7aca897 |  | note | Reference - Pavement Design Details 407.20
label | 59cbb45d-f919-59a7-8ef3-d706661311dc |  | note | Acceptance Criteria - The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | 65115537-a58a-5329-9822-8fefcee6ce1d |  | note | ○ Base & intermediate courses: 5ºC for conventional binders or 10ºC for PMBs & Class 600
label | 46d1ec28-7631-50fa-a8de-d5f11d6c1456 |  | note | ○ Wearing Course: 10ºC for conventional binders or 15ºC for PMBs
label | 7c405867-0f70-59cc-828d-8f2607c7be4d |  | note | ○ Where the above temperatures cannot be achieved , asphalt must be laid under the "Fulton Hogan Cold Weather Placement Management Plan"
label | 2e048a61-6298-5535-bc94-a1f6e98ad9ab |  | note | Method - Check aspahlt delivery docket
label | 9abd3a3e-37d4-5f95-b923-c7677141bbc3 |  | note | Frequency - Each lot
label | 795c35e8-150f-588a-97d8-7801d764fe78 |  | note | Category - IP
label | b81f920a-b601-5108-b008-144d5124234b |  | note | Responsibility - Asphalt Foreman
label | a51c3068-357a-52f4-a0f7-cc9da29eac48 |  | note | Verifying Documents - Completed ITP
date | 1e92119b-e45d-586d-b70c-8e8d98634e84 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Delivery of Mix
label | 26d98e0e-9a2f-5467-b732-220670bc0823 |  | note | Reference - 407.11 Table 407.111
label | 5c7aee8e-3eaa-53ad-8e9e-48a142076f93 |  | note | Acceptance Criteria - Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
label | 74d7a728-e7e1-5c3f-b437-09edfce92fc2 |  | note | Method - Visual Inspection & Delivery Docket
label | 806ec01d-84c1-54de-8ba7-5b0055ca4b5e |  | note | Frequency - Each load
label | c4c03733-4cdd-5a5e-a48e-0f152a31329a |  | note | Category - WP
label | 8dbbbc70-9e94-516f-8000-3e8183c8b556 |  | note | Responsibility - Asphalt Foreman
label | e9b4bd6a-0069-5c78-8b7c-2567af0dc0a6 |  | note | Verifying Documents - Completed ITP
date | 8c9dbb02-661a-5187-adcb-b847d87e5f59 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Traceability
label | 43d66e52-8a8d-5201-b1e1-97432dff447b |  | note | Reference - Fulton Hogan Quality Plan
label | d3ec92cc-9346-5b5a-b150-1d76c95eccbc |  | note | Acceptance Criteria - Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
label | dc88a8e7-29cf-58e2-bc66-d2c1eabf104c |  | note | Method - Measure and Record on Daily Lot Record
label | 71b1c173-bac2-5e41-88e8-87a5a7b7e65f |  | note | Frequency - Each lot
label | a259f9de-fc7e-568e-8b92-001e0c76feca |  | note | Category - IP
label | 14440865-d54f-5bf6-8fe7-50ea83c69e74 |  | note | Responsibility - Fulton Hogan Foreman/ Engineer
label | 307a6533-56f8-55e4-bb56-96368f86e70d |  | note | Verifying Documents - Completed ITP
date | 0dc3764c-391b-5682-a486-f041867411e5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 - Layer Thickness and Level Control
label | a7ba4f11-6eeb-5eef-a9fc-34eb8dfb29e9 |  | note | Reference - Pavement Design Details 407.25(a),(b)
label | 9073055c-312b-5eca-a312-95fdb24b5bec |  | note | Acceptance Criteria - Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
label | a47fab5d-7b70-5e3c-bb1d-6db5f3434b0b |  | note | Method - Dips using ruler or dip stick
label | 07d1e12d-ad7d-5fa1-a6a4-f9face8fb84c |  | note | Frequency - Regularly during paving
label | f17f3ed6-df65-5044-ad8e-37873aab050d |  | note | Category - WP
label | c1d244f4-1726-53a7-a032-68521de0a1e9 |  | note | Responsibility - Asphalt Foreman
label | 253cce31-6e82-558b-8950-2cda2ffc9675 |  | note | Verifying Documents - Completed ITP
date | b1e151ec-c24b-5b42-94da-27a8927b0d6f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 - Spreading and Paver Stoppages
label | 9d1b0baf-e837-517f-9f0d-cb309023978b |  | note | Reference - 407.25 (c)
label | 5c2860c8-4fdf-5649-9e6e-8577aa1286eb |  | note | Acceptance Criteria - All asphalt shall be spread with a purpose designed asphalt paving machine to form a uniformly smooth asphalt mat complying with the requirements of Clause 407.29 without segregation, tearing or gouging. In areas that are not accessible by a paver placement of asphalt by other means is permitted.
label | a88f5768-fa6d-5853-a5a8-8df0f0f6774c |  | note | ○ The width of a single paving run shall not exceed 6 metres unless paving in echelon is proposed or procedures are in place to ensure that a uniform asphalt layer free of segregation can be achieved.
label | 4a5105e6-3a3f-513a-a0fa-0b6eeba5a7fe |  | note | ○ The Contractor shall conduct spreading operations to ensure that the paver speed matches the rate of supply so that stoppages are minimised.
label | c6d0de29-bbb9-510f-ba65-fb5e061385ef |  | note | ○ If the paver is required to stop and asphalt in front of the screed cools to below 120C, a transverse joint shall be constructed.
label | 09e61437-3044-535c-8556-9f9b415cd292 |  | note | ○ For asphalt work carried out on a road to be opened for traffic at the completion of work each day, each layer of asphalt shall cover the full width of the trafficked area. The requirements of Clause 407.21(f) shall be followed in respect of the treatment required for exposed edges.
label | 4b7391b7-ba04-5aa5-9b35-67678a3b5619 |  | note | Method - Thermometer
label | 77dfb3e3-144f-5516-a2f3-a0377b5c90f4 |  | note | Frequency - If paver stops
label | 59a56ec7-5853-5f27-82e8-da5e42483d95 |  | note | Category - WP
label | 594b57f9-4d40-531c-b953-f261ad0ae945 |  | note | Responsibility - Asphalt Foreman
label | 264c175a-7c2c-52c9-8594-7de2da269297 |  | note | Verifying Documents - Completed ITP
date | ee27abaa-e7db-50d0-a977-0de548efddd2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.7 - Surface Finish of Wearing Course
label | 9cebbd99-8954-5678-981d-967ac7fa48b8 |  | note | Reference - 407.29 (a) (i)
label | 5ed443b1-4fa7-5a0c-b80c-c92409b5f7e0 |  | note | Acceptance Criteria - The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
label | a7c1250c-f23f-5eba-8c69-61fa4a636797 |  | note | Method - Visual Inspection
label | 30746fc8-80db-54f8-a21b-2008070b8bd6 |  | note | Frequency - During paving and after final roll
label | 6bc5fb0e-1f54-5325-8da5-8f86d298f0bb |  | note | Category - WP
label | 692e4c85-7f94-5cb9-a206-2a33aea7c748 |  | note | Responsibility - Asphalt Foreman
label | 3fb545e2-5312-5b39-8188-595e9e1e03d6 |  | note | Verifying Documents - Completed ITP
date | 98617658-b722-5fac-8918-1d2b54b86177 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.8 - Kerb and Channel
label | b26fda89-5cee-56a1-97ff-f766f179859a |  | note | Reference - 407.29 (a)(ii)
label | b8a2c800-b013-587b-af79-2709bd77be0e |  | note | Acceptance Criteria - The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
label | 5291621d-25ae-5f22-a270-15e403e4fedc |  | note | Method - Visual Inspection & Measurement
label | 0229cbb3-eca5-59b4-8acc-d4cf97221502 |  | note | Frequency - During paving and after final roll
label | c98fdce4-9f94-5584-ab54-a14503cb6a9d |  | note | Category - WP
label | 84cd81fb-4331-551b-8c01-5e00337afde5 |  | note | Responsibility - Asphalt Foreman
label | 59a1081d-47bc-520a-9133-ec09db09a2c9 |  | note | Verifying Documents - Completed ITP
date | 26a1238b-8da4-5ce8-8541-fb23f91e682f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.9 - Shape
label | c928f3ef-6786-5e5c-950d-ea8e8ab1a047 |  | note | Reference - 407.29 (a)(iii)
label | 2d812b51-20ee-5bdb-bb02-f24a74d0f2b1 |  | note | Acceptance Criteria - No point on the finished surface of the wearing course shall lie more than 4 mm below a 3 m straight edge laid either parallel to the centreline of the pavement or, except on crowned sections, at right angles to the centreline. For intermediate and base course layers, the distance below the straight edge shall not exceed 6 mm and 10 mm respectively.
label | 892168bb-a599-5085-8cff-4b8b023d4412 |  | note | Method - Visual Inspection & Measurement
label | 7eccdd91-c406-5b1c-a12e-7a68c19b6a56 |  | note | Frequency - During paving and after final roll
label | 31eba65f-693c-52e0-969c-3446f66a0fff |  | note | Category - WP
label | 7a7629b6-8e6e-5da3-896a-6ed1460addc8 |  | note | Responsibility - Asphalt Foreman
label | 8cf1a468-0831-5459-8377-555e0fa27478 |  | note | Verifying Documents - Completed ITP
date | 3f466315-054b-5d7f-ada0-1a2fcb276100 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.10 - Alignment
label | 3aee018f-7e98-52d6-beb7-3ab1c50b1587 |  | note | Reference - 407.29 (a)(iv)
label | 387a5726-b042-5680-9aad-010b768e6277 |  | note | Acceptance Criteria - Where asphalt pavement is not placed against a concrete edging, the edge of asphalt layers shall not be more than 50 mm inside nor more than 100 mm outside, the designed offset from centreline or design line. Within these tolerances, the rate of change of offset of the edge of layer shall not be greater than 25 mm in 10 m.
label | 76f5ec50-237b-5244-bcfb-f830d5a138dc |  | note | Method - Visual Inspection & Measurement
label | dced3035-988e-5531-9fdc-e8a800c54bfe |  | note | Frequency - During paving and after final roll
label | 2612b300-de12-57d1-8a7e-4915cdfc6d60 |  | note | Category - WP
label | afe6ab5f-25a5-52a0-bf8c-6fab8b23ac54 |  | note | Responsibility - Asphalt Foreman
label | d5782e33-0657-5550-b98a-57da0a903e3e |  | note | Verifying Documents - Completed ITP
date | cb9de6a4-be0a-54cf-b2bf-52960a4bda58 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.11 - Width
label | 33971501-8703-54fb-8247-f0fa435bb64b |  | note | Reference - 407.29 (a)(v)
label | 21d52b1a-c8b2-5ed5-b688-3a18968aad0d |  | note | Acceptance Criteria - Where asphalt pavement is not placed against a concrete edging, the width of asphalt layers shall not be less than the design or specified width of layer by more than 50 mm or greater than the design or specified width by more than 100 mm. The average width over any 300 m shall not be less than the design or specified width.
label | b2ca7e75-4ea5-59f4-b184-ffc792b0f657 |  | note | Method - Visual Inspection & Measurement
label | 4e1c76c6-97d3-584f-970e-016f645223b2 |  | note | Frequency - During paving and after final roll
label | 3ad6b409-aaee-5ff8-92a6-2b5c5f3937e0 |  | note | Category - WP
label | 72443c3a-6787-5efe-835d-b1ac33bcae55 |  | note | Responsibility - Asphalt Foreman
label | 7bb8048f-73ad-5419-93b0-baa6cb1a0a71 |  | note | Verifying Documents - Completed ITP
date | 67c952df-bf70-547c-988f-924971ced937 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.12 - Trafficking pavement after placment
label | 607d8302-73e4-5a75-9e50-335555f3c30d |  | note | Reference - 407.28, 404.14
label | 0c6375ab-d0a1-5ce9-8a67-afda11054331 |  | note | Acceptance Criteria - Trafficking or placement of asphalt over previously constructed layers is not permitted unless the majority of the previously constructed asphalt has a surface temperature of 50°C or less and Falling.
label | fbf293fd-1e61-5bb7-af1b-cdc547da8650 |  | note | Method - Visual Inspection & Thermometert
label | 13a51b54-19e1-56a9-b6ae-b5bbfa2944e3 |  | note | Frequency - After final Roll
label | ad3f53ac-4086-55f8-8a49-18260b99feaa |  | note | Category - HP
label | d644e9f5-3bde-5b83-a38b-2f5910da69ec |  | note | Responsibility - Asphalt Foreman
label | a9062faf-3342-53b5-83a4-8298fe1e4bb5 |  | note | Verifying Documents - Completed ITP
date | 21324058-5454-5e26-ada5-36d6be0f6ded |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Testing
checkpoint-status |  |  | checkpoint | 4.1 - Compaction Testing (Open Graded Apshalt)
label | 018957ff-da81-566f-9903-a53327169c07 |  | note | Reference - 417.12
label | 0eaee80d-0424-503c-9a64-f57540c2326e |  | note | Acceptance Criteria - Accpetance of compaction shall be on a procedural basis
label | 81331193-a614-56df-bff3-27f7811336bf |  | note | Method - OGA/SMA Compaction Procedure
label | 0d7c5aa2-dd5e-5482-8af5-8f93959dd881 |  | note | Frequency - Per lot
label | a5ac6dd8-ea1c-59b7-9474-8d94fbbb11b1 |  | note | Category - TP
label | c33bf95a-9868-5040-adf9-5b09664afb5c |  | note | Responsibility - Fulton Hogan Laboratory Technician
label | edc38704-45a0-5fd0-afbf-6ce82ff5d1ba |  | note | Verifying Documents - Completed ITP
date | 05bd7020-6b5c-5af3-ab56-27c10415fae4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Compaction Testing (Stone Mastic Apshalt)
label | 25c5988a-b4c9-5dba-a888-37fc7c9ddcc1 |  | note | Reference - 404.15, 404.14 OGA/SMA Compaction Procedure
label | 68c2f8e9-0686-5fa9-94c9-339eecae0afb |  | note | Acceptance Criteria - Per lot, the Characteristic Density Ratio must meet the minimum limit of 96.0%
label | 8f08c36b-06f1-5054-ac29-bfb5b0b1a6ca |  | note | ○ For layers thinner than 25mm, accpetance may be on a procedural basis
label | c691c499-6b02-5ad8-abd4-a5856758ccff |  | note | Method - Nuclear Density Test, OGA/SMA Compaction Procedure
label | 79e13529-fdbd-58df-b585-a1fd7099bd10 |  | note | Frequency - Per lot
label | cee05e20-5ac5-522e-99e7-25a65a679bf2 |  | note | Category - TP
label | 755f8b19-4db7-5a0e-be30-2289eb4dd550 |  | note | Responsibility - Fulton Hogan Laboratory Technician
label | 4c82f963-124d-5ad5-a529-a85d07329b42 |  | note | Verifying Documents - Completed ITP, Compaction reports
date | d2fbe671-e55c-5f69-a2ed-6f06d99974cf |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Compaction Testing (Dense Graded Apshalt)
label | d52d9d4e-45b0-50ef-9e0a-350c6d3794c1 |  | note | Reference - Section 407.27(a),(c.) 407, Section 173, Dense Graded Compaction Procedure
label | fcc9f695-95ff-5848-a4cb-3d31c32f04a6 |  | note | Acceptance Criteria - Test Lots >500m2, Per lot, the Characteristic Density Ratio must meet the following Minimum Limits:
label | 33ec1528-387b-55b4-bc32-77aca66c8eeb |  | note | >50mm layer depth = 96.0%
label | 82e1b2b7-5266-5455-8499-fea7cdb8113a |  | note | <50mm layer depth = 95.0%
label | 8e17d602-6f86-54b4-9d58-6a0d043eea39 |  | note | ○ Additional Test must be undertaken on the longitudinal joints for wearing courses
label | 633b5fc6-7539-5596-b158-1632c986f075 |  | note | ○ Test Lots 50m2-500m2, may be treated as a small area,in which the mean of 3x test sites must exceed the appropriate compaction requirement by 2.0%
label | 8c5e38e7-d899-5bdf-8bec-af789bec93c6 |  | note | ○ Test Lots <50m2, compaction for all lots shall be accepted on a procedural basis
label | f8074350-1d1f-5dbb-bd72-17c5def92864 |  | note | ○ Mix Types where total contract supply <300t, compaction for all lots shall be accepted on a procedural basis
label | fc53af78-5766-54f3-ba89-ef1f8e49d08f |  | note | Method - Nuclear Density Test, DGA Compaction Procedure
label | bf0aa345-10e2-50f7-87a8-245831188836 |  | note | Frequency - Per Lot
label | ec0fc5d5-7b6a-5e79-a45d-d719e9bb5182 |  | note | Category - TP
label | 0d30aac3-5a38-50a2-b8d9-bd42fea18f7d |  | note | Responsibility - Fulton Hogan Laboratory Technician, Asphalt Foreman / Engineer
label | 584a2597-469f-5a54-ba41-10c72c26e986 |  | note | Verifying Documents - Completed ITP, Compaction rerports
date | a640eca4-7d6a-5c40-87d1-f1ffd52a72af |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Level Conformance
label | 60517cb3-4a14-55e4-9db5-41248989f7ad |  | note | Reference - 407.30, 407.29
label | 375576b5-d90a-5e6c-b7f2-121ce8709209 |  | note | Acceptance Criteria - The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements as specified in 407.30 (b)
label | 3709b035-2468-5af1-99e0-114cad9e164e |  | note | Method - Survey Results
label | 5acd3257-4c7b-50b4-a6de-9c8d7fa4af9d |  | note | Frequency - Each Lot
label | afb827c2-a597-5540-a926-97cdfadc5a53 |  | note | Category - WP
label | 41dec22b-e843-59d0-bd6e-ffb73493d55d |  | note | Responsibility - Surveyor
label | 7e8c4cce-39f0-5ce2-9986-ded67aaff9c5 |  | note | Verifying Documents - Completed ITP, Survey Conformance Results
date | 00c1fdcd-28fd-59d7-b44a-48881e037c8e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 3e0531d0-bd35-5b0d-aa93-23e8bc015c1d |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 0888a47f-243b-53da-9838-ac81a86dbd1a |  | textbox | Name:
text | e37f6d89-abdc-5667-89ea-419fafb4e8db |  | textbox | Position:
date | 564b6603-c18e-52c8-8639-bf5ac51c4988 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-076-CIV-CPD-Pit 5.5 Installation Melbourne Water | itp |  |  |  | Yes | ITP-076-CIV-CPD-Pit 5.5 Installation Melbourne Water Rev 0 | 0a2725d8-24b0-4e13-8100-41f50f8188b1
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | e3c57628-6f1d-5176-8ae6-dc509954ac92 |  | note | Document Title: ITP-CIV- CPD - Melbourne Water - Stormwater Pit Suppy & Installation
label | 2126c640-389c-5eb5-b9a3-b49d96de3f60 |  | note | ITP Description: Melbourne Water - Stormwater Pit Suppy & Installation
label | f21b8290-98d2-54ce-a429-18a093d5980b |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | aec547cc-661c-5036-a1a7-31d495cda8b6 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
label | 4fa0a860-883e-5797-b747-567c5d650977 |  | note | Revision Number: 0
label | a96f086f-a94f-5cbb-a527-db6d2a00ce0c |  | note | Revision Date: 19/09/2023
label | c7a3489d-d019-51d2-a876-9f2c756c8f78 |  | note | ITP created by: Ethan Caruana Smith
label | 5cf49721-7927-57a2-b4b0-9edc6a02989c |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | b1c60354-e36e-516e-89e9-2367a6690213 |  | note | Reference - VicRoads Section 701 (May 2020)
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | c1582f87-eddb-56e5-a144-f9757517b8fd |  | note | Reference - VicRoads Section 705 (June 2021)
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | 911c2c37-f545-500e-8f66-ca00898ad447 |  | note | Reference - Melbourne Water Standard Drawing 7251/08/416
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | e50b7765-f4c0-5d3a-b0a0-a760d0fcc615 |  | note | Reference - Melbourne Water Standard Drawing 7251/08/423
checkpoint-status |  |  | checkpoint | 1.5 - Non Dependent
label | 09f34d79-ebee-5ac0-92e6-bb8785ab9d0f |  | note | Reference - IFC Drawings - Package 36
checkpoint-group |  |  | section | 2. Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Precast Drainage Pit
label | 916c2ad5-f67d-58bb-bea8-18945a1a5300 |  | note | Reference - IFC drawings - package 36, Gestalt Engineers pit L-4/5 & L-5/5 package
label | b89419fc-ddee-5e90-978f-7f9bb77b8e73 |  | note | Acceptance Criteria - Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with design drawings marked as IFC.
label | ec3635ea-f24b-59a7-afc7-2b7dc109eb73 |  | note | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
text | 955ac574-d421-5509-9eab-812f5ffbebbf |  | textbox | Enter: Teambinder Material Approval number
label | 11ea8f81-15c9-5364-b015-38bfbe4ae685 |  | note | Method - Document Review
label | f8d01bb7-0b99-5f58-b98c-291e2513545b |  | note | Frequency - Each lot
label | 105acc12-945f-5257-9d87-694951e9941f |  | note | Category - HP
label | bc0874ba-e0d4-528f-a067-bb9e77c93eeb |  | note | Responsibility - Nominated Authority
label | af01e4ce-85dc-5f69-b512-5d11cafb2b9f |  | note | Verifying Documents - Teambinder Material Approval
date | 09e317a2-3c0c-5ee3-8a35-ef4b687e590b |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Drainage Pit - Step Irons
label | f4262bd5-b71d-5ee4-bdad-976b141648eb |  | note | Reference - Melbourne Water Standard Drawing 7251/08/416
label | 99c3c072-b306-59cb-bdd2-9ac1eab807c2 |  | note | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
label | 96f65e59-12a9-5f2b-8679-86af2b03b11d |  | note | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12 and Melbourne Water - 7251/08/416
label | 2ebbc430-0582-525f-a469-d2543dcd2f2c |  | note | Method - Document Review
label | b12a083a-61b0-5c43-a25e-7a35daf967b5 |  | note | Frequency - Each lot
label | f2d297e1-0ef1-57ed-8b04-7156b71f7dac |  | note | Category - IP
label | 2e9829fe-7db4-5dc1-a900-001b28095bb4 |  | note | Responsibility - Nominated Authority
label | 6a0f24e5-8dcd-5b58-a015-151c2e7d3f5a |  | note | Verifying Documents - Teambinder Material Approval
date | 05325922-87c1-5932-b5da-0f337c6907a3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Drainage Bedding
label | d1028385-1953-58b9-8600-e85c72252549 |  | note | Reference - IFC drawings - package 36
label | 84db88ac-cfdc-5419-bbcd-5535e751e1d6 |  | note | Acceptance Criteria - Pit shall be installed on nominal 50mm thick 200 Sq concrete packers. positioned at 1m centres around perimeter of pit. Underside of pit to be flood grouted with Min 25Mpa grout
text | 8f707b6a-7810-56c9-be84-06ec8ed49e84 |  | textbox | Enter: Teambinder Material Approval number
label | e29664fe-e425-559d-8ffc-d7b42b7f7c62 |  | note | Method - Document Review
label | 2703c418-8f5b-50af-ac66-e0a0140e3c7e |  | note | Frequency - Each lot
label | 5412dd4c-7133-5377-b573-16982f5317db |  | note | Category - HP
label | 06fc958e-d6eb-5008-b86f-214a8b75ad02 |  | note | Responsibility - Nominated Authority
label | 3e703498-7bcf-5661-a15a-d25af367f904 |  | note | Verifying Documents - Teambinder Material Approval
date | f32e883d-835f-548e-be98-13000ab1816a |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Drainage Backfill Material
label | 077dfa6d-76e9-59a5-b57f-0c40b6115b46 |  | note | Reference - IFC drawings - package 36, Melbourne Water Backfilling the excavation - Backfilling materials 6.8.2
label | ee9112d2-991f-5657-a655-56c34e57835f |  | note | Acceptance Criteria - Approved Backfill as per Mebourne Water requirements
text | 54aaa4ea-3197-5699-b279-428553320406 |  | textbox | Enter: Teambinder Material Approval number
label | 64f06ca4-d169-552e-aff1-1fcc7ab54e83 |  | note | Method - Document Review
label | d1180ed7-ac16-5897-a4d8-37771efdfce9 |  | note | Frequency - Each lot
label | 7a55992c-c732-5faf-8531-418e44d5ddeb |  | note | Category - HP
label | 013f3336-3f99-57b5-91e7-df267bf2ca28 |  | note | Responsibility - Nominated Authority
label | abc5b962-894f-5644-8813-8bc2e7e4a8d7 |  | note | Verifying Documents - Teambinder Material Approval
date | 8ea9b4d7-a9c4-5a59-b082-8f9429edee64 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set Out - Pits
label | 44403e7d-36e7-518a-8673-a47aff5de138 |  | note | Reference - IFC Drawings
label | 43ed44bf-2ead-5e38-bf40-6ca2e3e5bbd9 |  | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
label | cf682cba-2cc7-5f35-84d9-d3ae42e89f19 |  | note | ○ Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
label | 5e4bf08c-e956-5da3-8704-4312293585be |  | note | Method - Survey
label | f0ef9ae4-135f-546f-95d8-3ac68c503858 |  | note | Frequency - Each Lot
label | b1edd407-b7b2-5d13-938d-e54ecced551e |  | note | Category - HP*
label | 129501e9-ae0f-5a37-a75f-42fff3869354 |  | note | Responsibility - PE
label | f3856a05-b8d2-5989-94ea-7774dd06ab80 |  | note | Verifying Documents - IFC drawings - Package 36
date | d491d712-c994-5b85-b9f0-bf6682acb8fd |  | date | Date Completed:
checkpoint-group |  |  | section | 5. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Pits - Excavation
label | 0c2939ca-6110-5f57-9510-fa0ed08de4be |  | note | Reference - IFC Drawings
label | 9e908f7f-9216-54cf-9599-e5037d6e3e5a |  | note | Acceptance Criteria - Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
label | adcf51fa-4912-5ad2-9d23-573258405f8f |  | note | Method - Visual inspection, Measure
label | 864f8843-2e7a-50a2-a6a0-e92fc26ea603 |  | note | Frequency - Each Lot
label | 80b22fb7-6cfb-5d71-9aca-b495e05e5b26 |  | note | Category - IP
label | b59bd38f-fe0f-563f-98fb-4f7c9f0f97f3 |  | note | Responsibility - SE
label | c4ce5387-e055-5354-a4f8-fa70e84334ff |  | note | Verifying Documents - IFC drawings - Package 36
date | 08b2b446-8770-57f5-b732-63ef49d15558 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Pits - Placement of Bedding Material
label | 9d3fdfb1-ac2b-5155-a5a7-69a7d4dd67e3 |  | note | Reference - IFC Drawings
label | 0a722592-efc2-5a1c-bfe1-0a8714045184 |  | note | Acceptance Criteria - Underside of pit to be flood grouted with Min 25Mpa grout - As per Design Drawings
label | 2d06cbf4-1910-513b-b3d0-404122933261 |  | note | Method - Visual inspection, Measure
label | a3d9bb56-704a-5e7c-9f2d-a771de6fc91b |  | note | Frequency - Each Lot
label | c5469b6e-a959-5a82-8522-c79ac44b0e17 |  | note | Category - IP
label | 29908fd4-1d7b-5b9c-bda9-e7c703d9a400 |  | note | Responsibility - SE
label | 50e614fd-60ec-5dfe-8fbe-003c1b127616 |  | note | Verifying Documents - IFC drawings - Package 36
date | 9f09e7a9-0499-583b-b778-9af0b17caa49 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Pits - Bedding Testing
label | edeb086a-cb9b-51a3-8fab-91de9a7ed353 |  | note | Reference - IFC Drawings Section 701.20
label | fdcb48a5-15ba-562f-b714-1c63d4ddffd3 |  | note | Acceptance Criteria - 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
label | 1e76e232-bf11-5aad-852c-96fca69f282b |  | note | ○ 28 day compressive strength per sample comply with the design strength.
label | fdcb5d1c-466c-5e7a-b096-9aa420d0941f |  | note | Method - Document Review
label | b2e12546-2bf8-52f8-83c9-49d76fee63b6 |  | note | Frequency - Each Cube
label | 7307767f-a83b-5099-8d35-a9472667a1a5 |  | note | Category - IP
label | bb5ffe56-9f8d-50b0-adc9-c3f117ed329d |  | note | Responsibility - SE
label | 0374d208-0ed4-5dcd-b982-77b08bc5db7e |  | note | Verifying Documents - Compaction test results
date | b606fb68-a8e2-50bf-a5a8-940ebef24a23 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Pits - Placement of Precast Drainage Pit
label | 49265f6c-25d2-58de-9817-1dcf5b1012c7 |  | note | Reference - IFC Drawings Section 701.10
label | 7c1d48f9-3342-5622-8b31-98980e0aecc0 |  | note | Acceptance Criteria - Survey pick-up to verify:
label | 0c3d48a6-b7d8-590c-9103-da76d70d27ff |  | note | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm22
label | 304f1a4a-fe44-52c8-a912-1ca92f8c6438 |  | note | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | aaaba0a9-dffb-5727-9e7a-69ba0a971d5b |  | note | Method - Visual inspection, Measure
label | 4f69d39d-0ed2-5aee-a46d-d147532a8d7d |  | note | Frequency - Each Lot
label | 6eed486a-0c24-59fb-af68-b037e5cb0427 |  | note | Category - IP
label | dc13d830-23e3-55e7-9995-4cf0343756a8 |  | note | Responsibility - SE
label | 77360f2e-03b4-55f1-9ea8-908b27dae955 |  | note | Verifying Documents - IFC drawings - Package 36
date | e12d931f-52c9-517c-84ab-633468ccf3e1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Pits - Cast in Place Drainage Pit
label | a821cfd8-c682-59b2-92c6-8a0826f33ff0 |  | note | Reference - IFC Drawings Section 705.06, Section 610, Section 611
label | 60bbfdbf-c830-540c-a37a-69ef4eb54be3 |  | note | Acceptance Criteria - Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings and in accordance with the requirements of Section 610 and 611.
label | 7e861a5e-0129-5a55-8204-953f34516f69 |  | note | ○ Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
label | 2c6793b1-5449-5664-94ef-aa21c7f56e9c |  | note | Method - Survey, Measure
label | 6a446d34-e813-5a30-921e-2c1dac2cba3c |  | note | Frequency - Each Lot
label | 2736a058-1344-5baa-90d0-1400857e6c41 |  | note | Category - IP
label | 654fd549-92ae-5c1a-9310-f5f8348e455b |  | note | Responsibility - SE
label | 7eeae67a-9d8e-5abc-a916-664e915c5984 |  | note | Verifying Documents - IFC drawings - Package 36
date | d66f85bd-fab2-5da0-887e-cb1f0ced6c95 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Pits - Jointing & Drainage Connections
label | 2dce674a-5fb9-5383-a8bb-86612e8c9c2f |  | note | Reference - Section 705.11 Package 36
label | b824a17b-09c5-5ff9-85ae-eb9de8ba9b09 |  | note | Acceptance Criteria - All connections to drainage pits shall be neatly made in accordance with Section 705.11.
label | 30101334-9fa0-566d-864a-0c8da24d2b60 |  | note | ○ Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
label | 9ce3683e-f0fc-518c-aa0a-d4ef2bc15e12 |  | note | ○ Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
label | a1feba24-9afb-5d40-9b49-2b6cb40f1760 |  | note | ○ Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
label | bebca184-6f42-5079-991c-96c6f1b2dbe3 |  | note | ○ Joints to be sealed with Hydrophilic seal around pipe as per design package 36.
label | 4b0cf15a-ad84-5b24-92a8-e7ebce164a56 |  | note | Method - Visual inspection, Measure
label | 792bf531-e8ee-504a-8275-dd5e554d8285 |  | note | Frequency - Each Lot
label | ebd64f91-ad03-5710-882e-9666080a0366 |  | note | Category - IP
label | 003a1c47-86ff-57f5-87d8-f8ab9ac926ac |  | note | Responsibility - SE
label | 0a821022-c612-5cb5-bc17-0f98284cae36 |  | note | Verifying Documents - IFC drawings - Package 36
date | f04c64af-91c5-5170-b9cb-03d8a8a5e9df |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Pits - Shaping of Floor
label | 7e72d152-c06f-5d38-b17d-b56e36020487 |  | note | Reference - Section 705.13
label | c6cd05d7-dc55-5bc4-9a96-b0e87032dae8 |  | note | Acceptance Criteria - Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with Section 705.13.
label | d2ba10e1-ef92-5522-a325-7a87232bcdde |  | note | Method - Visual inspection, Measure
label | 9b85105a-5d53-5aa0-a4e4-b33246bb398b |  | note | Frequency - Each Lot
label | 0595f479-d14b-511e-b8b7-41820e44e4e6 |  | note | Category - IP
label | be0ec377-5f67-5c0b-b11d-ec2d7af17716 |  | note | Responsibility - SE
label | 8ceceb39-97a6-5405-bdf7-8bcd556dab54 |  | note | Verifying Documents - IFC drawings - Package 36
date | f17c9e78-3f53-5c63-9e00-7dfbfd4092a8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Pits - Step Irons
label | 23e91028-0100-5051-94d0-8151989d2324 |  | note | Reference - Melbourne Water Standard Drawing 7251/08/416
label | 5890e6ae-c811-5cb9-a285-a457550f233f |  | note | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with Melbourne Water 7251/08/416. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser.
label | 344c7e26-8d5d-5567-b587-53c1ba6d3000 |  | note | ○ Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
label | c4506283-117e-55e2-976e-bb75448b85aa |  | note | Method - Visual inspection, Measure
label | 792a3ef2-1d5b-5e3f-941a-8b22529ad790 |  | note | Frequency - Each Lot
label | 6e0b096d-c919-542d-b62b-78dcf167741c |  | note | Category - IP
label | c3eeff11-96b4-5bda-8a29-7a3e77339a75 |  | note | Responsibility - SE
label | 592b35cf-5310-5c79-bd99-bad19663b876 |  | note | Verifying Documents - IFC drawings - Package 36
date | db577629-f8b5-53c0-9352-b20d232ff757 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 - Pits - Fitting of Covers
label | b93ac3ff-7ec5-50fc-8d2b-ed08458cbffd |  | note | Reference - IFC Drawings Section 705.17
label | 527ae9d1-8a2c-51f0-9b02-2edc35d8fc17 |  | note | Acceptance Criteria - Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh shrinkage compensated grout with a minimum of 40MPa.
label | fe1f6e96-ae34-513c-a3f4-bc2dfbd50fe8 |  | note | ○ Height shall be within 10mm of the design level.
label | 63202a48-5697-5839-a2f1-4e615bbd6121 |  | note | Method - Visual inspection, Measure
label | 7e10e9d7-4ae1-5ec7-9513-08b9be286ea7 |  | note | Frequency - Each Lot
label | 0f41a642-6146-56c0-b159-c0428a9faeb4 |  | note | Category - IP
label | 3ff2b377-423e-5886-bb01-6594d97beac0 |  | note | Responsibility - SE
label | 59609a6f-eb1c-5f02-8d83-c5d1f40fd2bc |  | note | Verifying Documents - IFC drawings - Package 36
date | 971584e4-f788-5b0d-ac08-5d558d374cdf |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 - Pits - Pit Lids
label | ccab593c-085e-53ba-909c-1277188d5d55 |  | note | Reference - IFC Drawings
label | c9da3677-6f87-57d6-90dc-215335a14054 |  | note | Acceptance Criteria - Precast steel reinforced concrete drainage lid shall be manufactured, supplied and installed in accordance with design drawings marked as IFC.
label | 215ef3c7-4404-52ce-8684-01064ae61caf |  | note | ○ Stitch pour concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
text | 7e7164b0-7040-5b58-9fa6-9072a98dae4f |  | textbox | Enter: Teambinder Material Approval number
label | dbbd58be-9b7e-57d1-9271-c611d5cdce07 |  | note | Method - Visual inspection
label | 6d3d43ce-0a23-5c70-b128-318a09c0e1eb |  | note | Frequency - Each Lot
label | f2d2a92a-837a-5131-9a55-8ed19fd70564 |  | note | Category - IP
label | 2e2ab60e-6f4b-56fd-8554-e06e7234efbb |  | note | Responsibility - SE
label | ff4aba42-6003-5371-8b34-80639c8be7c3 |  | note | Verifying Documents - IFC drawings - Package 36
date | e95b3511-6858-5c8e-a03d-87570cd32326 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 - Pits - Backfilling Around Drainage Pits
label | 3849641d-55c9-5533-b6ce-c773309f351f |  | note | Reference - Section 705.18
label | cbc770d7-7fad-5e19-acc4-70b362fa0af5 |  | note | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
label | e5ebce4a-4bf1-5b61-9cd4-233e12d39967 |  | note | Method - Visual inspection, Measure
label | 74da5057-2526-544d-b0f5-a8ba8d377f00 |  | note | Frequency - Each Lot
label | f627b31f-60b8-5858-8649-855056204491 |  | note | Category - IP
label | b575ce71-1bc6-5cca-9f2d-32cd4bd95fe6 |  | note | Responsibility - SE
label | 5e053d9e-924b-571d-bfb5-f485c2c755f4 |  | note | Verifying Documents - IFC drawings - Package 36
date | aa4979a4-b2af-5dbf-a54b-d37026013fcd |  | date | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - Flushing & CCTV
label | 00fc293d-c1ea-5633-8433-ef4eec3f6fd5 |  | note | Reference - Section 701.28, Section 701.30
label | 5dfbbb0b-0640-5524-a257-2927b5a48eaa |  | note | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
label | 4f448fa6-dd25-5fc3-93a9-df7788916945 |  | note | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
label | 7bef5cec-511c-5ff0-8b2a-93c520d49c9f |  | note | Method - Record Review
label | ff82b506-1571-5f3e-9d50-895ec5a71390 |  | note | Frequency - Each lot
label | eb6ad45b-4433-54b3-8576-c6f735536b42 |  | note | Category - HP
label | 5357580b-c037-5e0f-9445-6dac4ddad293 |  | note | Responsibility - Nominated Authority
label | ea6a56c5-1534-570f-92e8-7ef56b011993 |  | note | Verifying Documents - This ITP, CCTV Reports
date | 21768c77-37db-5fc0-8ad6-a9ec07e0592d |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 - As Built Survey
label | 0d3a93da-4d59-50ef-a553-58a5d372bfe7 |  | note | Reference - Section 701.10
label | b6004005-e051-5701-88e8-c03ff278f20b |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
label | 0c008f5b-0ed7-561a-a6a4-ed88b4130b28 |  | note | Method - Document Review
label | 4e8b22d0-6beb-5f8f-b2cd-fe38659b8ab7 |  | note | Frequency - Each lot
label | 4e14d7ba-5764-52c0-9223-25ee5c8d8668 |  | note | Category - IP
label | db84c2fe-bfd7-5c59-bbe6-0f09f41bc889 |  | note | Responsibility - SE
label | 44741c84-6599-59ad-aa7c-10dd5d0bc144 |  | note | Verifying Documents - This ITP, As Built Survey Report
date | 9b6fc855-0afa-5117-80c1-ee3b387bb112 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Repairs to Damaged Pipes
label | 47e63eb7-a673-5d00-8340-904650116602 |  | note | Reference - Section 701.31
label | 204eadd3-dbfa-59f7-8d06-046e33caa5ac |  | note | Acceptance Criteria - Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
label | 353ee942-97ad-5ce5-b8d6-039aba0d6c02 |  | note | ○ cracks wider than 0.5 mm
label | 733c914a-5197-5d44-9abc-da3fd9f8eec5 |  | note | ○ spalling of concrete
label | e5127832-790f-5d19-b5dc-7782d3f97aa9 |  | note | ○ exposed reinforcement
label | 68508e22-687d-51d7-b5cf-8b1d85a991b0 |  | note | ○ joints that are not fully engaged.
label | 5ce724aa-1930-50f7-bd09-12dd54787103 |  | note | Any pipes with defects greater than the following limits shall be removed and replaced:
label | 718a06a9-63e3-5a24-98e2-d413cb3da936 |  | note | ○ longitudinal cracks greater than 2 mm
label | f28ea585-511d-5147-8e9f-a2f02b3ae403 |  | note | ○ circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
label | b4f0bbe8-4827-5f79-b63c-3e9ac1d7a28c |  | note | ○ circumferential cracks around part of the circumference with width greater than 4 mm
label | 042c0268-deaa-5ecd-96d2-84f64b5c264c |  | note | ○ penetrations with area greater than 400 mm2
label | 1680f01b-0606-5410-af2b-fff3fe955975 |  | note | ○ pipe joints that are separated.
label | 85202bbb-cbdd-54fa-8c23-5815e0f5eecc |  | note | The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
label | 4320244c-d23e-5a2b-9dc4-da4ccb4f5030 |  | note | ○ hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
label | 6fcd0fa0-9aa1-5efc-8a48-49ba15569a60 |  | note | ○ fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
label | 7debf01f-fbbc-5fbb-a624-89c4965c490f |  | note | ○ spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
label | 72848237-dd25-5c20-bea4-572f5490c11f |  | note | The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
label | dba2ad52-16e3-5d05-a180-04fe36485fd9 |  | note | No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
label | 52a3042b-e040-5229-81cf-88ea6a8eec3b |  | note | All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
label | 79393559-fe44-50bc-a0f0-669d81d86dbe |  | note | Method - Document Review for Repair Procedure, CCTV Report Review, Visual Inspection
label | 5a2c58c8-d4b1-5f62-ad5e-517a03ea044d |  | note | Frequency - Each lot
label | 2c5e6869-2a4c-567c-bb5b-f7d7b15d84dd |  | note | Category - HP
label | 03e18a58-6221-555a-a5e0-7022ffec217c |  | note | Responsibility - Nominated Authority
label | a1908a99-f184-5705-b770-0ba9bbb2d365 |  | note | Verifying Documents - This ITP, Approved Repair Procedure, Post Repair CCTV Report
date | 61a78237-f062-5551-a42d-46d4513bfffb |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | 6510898d-7156-5763-a7bd-cc18a4a8ef88 |  | note | Reference - MRPA Quality Management Plan
label | 7246bc90-d17c-5a37-b3b9-3d7d8d0d6d92 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | b62856b6-f612-5c90-9e9a-747f6889d636 |  | note | Method - Document Review
label | db5ef82d-dcc4-553d-a499-ae1ad56808d8 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 1cd2fada-45ac-519a-9d24-2f9641d77d81 |  | note | Category - HP*
label | c7b2066d-d46a-599a-8f75-d3c326c4db5f |  | note | Responsibility - PE
label | 9d984508-5682-554d-837e-d7bc3ee4e041 |  | note | Verifying Documents - This ITP
date | 6e66ac83-4a21-53a7-a2d3-be8585712d11 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | a00f6dde-44b4-54bf-9300-b9e9ab31af0d |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | c6e3909e-fa5c-58a3-b844-355e4dff5acf |  | textbox | Name:
text | 668d9d76-dd00-5f70-ad8c-b5aaa6e7ff21 |  | textbox | Position:
date | b39d604f-5e64-5528-9a9f-9acf8bacb1cc |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-050-CPD-RAIL-Calder Park-OHLE Installation | itp |  |  |  | Yes | ITP-050-CPD-RAIL-Calder Park-OHLE Installation - Rev 1 | 0d16b7a4-af42-4318-ab53-e8c45b46cb72
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | b7df6a49-54d7-57cf-921e-fb4555682e76 |  | note | Document Title: ITP-CPD-RAIL-Calder Park-OHLE Installation
label | 7fe286bd-4b9c-5eed-b7d2-ddf3c07f550e |  | note | ITP Description: OHLE Installation
label | bbab5c57-2d08-5c1f-828e-0366de5e1730 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 1dcd54fc-d22b-5a20-85ad-abb2ffeadd4b |  | note | Discipline (e.g. CIV/STR/RAIL): RAIL
label | 7926b4ef-e200-52d4-9c92-3845f9bb1ae8 |  | note | Revision Number: 1
label | d90ed7af-faed-5a1e-810c-ce1c3f61f380 |  | note | Revision Date: 24/07/2023
label | 2f11af77-9018-55f6-b9f5-8f2491537e2c |  | note | ITP created by: Kevin Liang
checkpoint-status |  |  | checkpoint | 1.1 - Overhead Line Electrification
label | 775a0b1e-c92a-513d-9a77-f92d7b520c11 |  | note | Reference - L1-CHE-STD-011(1) MEST 000002-02(1)
checkpoint-status |  |  | checkpoint | 1.2 - Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | e7953282-822e-5327-9fbd-3c2884ce06a7 |  | note | Reference - VRIOGS 001 AS 4100
checkpoint-status |  |  | checkpoint | 1.3 - Electrical Networks Standard Electrical Networks Principles and Performance
label | b705f63d-129d-5cad-8efb-461cd91b2213 |  | note | Reference - L1-CHE-STD-015(1) MEST 000002-06(1
checkpoint-status |  |  | checkpoint | 1.4 - Fabrication of Steelwork
label | 5c16f59e-2a3b-5d51-873f-cf6afd16d0bc |  | note | Reference - VicRoads Section 630 January 2023
checkpoint-status |  |  | checkpoint | 1.5 - Electrical Networks Standard Electrical Networks Principles and Performance
label | 08177b38-c8cf-564c-892c-bd6d722802ea |  | note | Reference - Structural Steel Work - Fabrication and Erection
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Structural Steel Components and Fasteners
label | 029dfd34-b50a-569f-a7cd-05f7c012e070 |  | note | Reference - IFC Drawings
label | 5632fa21-5519-5876-998d-8751084f31b6 |  | note | Acceptance Criteria - Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
label | ab2345a8-6516-54e6-927f-7934525af411 |  | note | • Typically this consists of but not limited to:
label | 635ba4f0-5ea2-5762-a404-ab1e43c40894 |  | note | i. Completed fabrication ITP
label | 5e5ca6e7-c2eb-5bb9-9ecb-319799692cee |  | note | ii. Weld Procedure Specifications
label | 0a69420e-903a-51f9-9178-36c66a3e19d4 |  | note | iii. Weld Procedure Qualifications
label | 9ecffd6c-7482-5b95-b1fe-28a0b367cd9b |  | note | iv. Welder Qualifications
label | f946d9d7-1ec7-597f-87f5-9eac157dae47 |  | note | v. Material Certificates
label | e01955a7-113e-5b4f-a2c4-291b7bf8d187 |  | note | vi. Coating certificate(s)
label | 0dad601c-c8f7-5d83-8421-091e4e82ce80 |  | note | vii. Non-destructive Testing (NDT) Reports (if any)
label | 9d0c5e70-dde3-56d2-90bb-f5c85dd3a178 |  | note | viii. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
label | 749f4d78-0637-5bb4-963b-bf4857d9a10e |  | note | • Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1111 and AS 1112
label | 8d4ebc6c-440e-5fb9-b3db-b63033213f51 |  | note | • Bolts, nuts and washers for Property Class 8.8 bolting shall be supplied in accordance with AS/NZS 1252.
label | 20560b8d-5917-5ca1-814e-88d6f183e0ad |  | note | • All bolts nuts and washers are hot-dipped galvanized.
label | c8a61a7e-4572-5ff6-a50a-133136a4be54 |  | note | Collate: Structural Steel Quality Assurance Documentation.
label | 8a7df7f4-f2a1-57fe-a976-9a46b57545e4 |  | note | Attach: Collated QA documents in ConQA
label | 05f6388b-487f-5e03-a925-85fb9d5cc326 |  | note | Method - Document review
label | dfbcf741-d246-529e-8a59-0380af6f5546 |  | note | Frequency - Where applicable/ Each element
label | faf9a59f-2fce-54a9-9522-9adafb711d4b |  | note | Category - HP
label | 133b2be5-8601-5b00-8896-3244d9565109 |  | note | Responsibility - PE
label | ee4ef774-5114-53de-a293-a92c6e939b68 |  | note | Responsible person - MRPA Engineer
label | a673634f-12f3-57f7-aee0-baf4dd58a2fc |  | note | Verifying Documents - This ITP Signed Off
text | 21797d05-10e4-56c3-b344-a68dde6480e0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Bolted Connections Using Direct Tension Indicators (DTIs)
label | 698738ba-468a-5f98-9679-f91e263f6116 |  | note | Reference - AS4100 Clause 15.2.5.3 (a), AS5131 Clause 8.5.7 (a)
label | 5e8fdc3a-377a-50ea-8157-0db5c8c753d9 |  | note | Acceptance Criteria - Direct tension indicators (DTIs) shall not be used unless approved by the Nominated Authority and accompanied by:
label | 0c423b1e-6833-500d-a588-0d17bef07db7 |  | note | i. technical data sheet or information on the product
label | acd47a5e-a2f0-513e-b729-ff4a033bde82 |  | note | Method - Document Review
label | f2f07875-8fb1-531f-a95b-ae21b656d50d |  | note | Frequency - Where applicable/ Each element
label | 47e25988-cd98-57a2-b86e-48ef806931dd |  | note | Category - HP
label | 1227b6f1-fad6-5d05-ae58-c2547960b6c7 |  | note | Responsibility - PE
label | 5300020b-6bec-5ce4-89b3-78238718ec4f |  | note | Responsible person - MRPA Engineer
label | d795bd97-50e2-5afc-8636-77e048c4e6cf |  | note | Verifying Documents - This ITP Signed Off
text | f2fc33fd-12f0-514c-b017-98cfec7cce33 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Overhead Wiring Small Parts Steel and conductor wires
label | 16162b97-9eac-5ebd-8b10-8d8db1f30b51 |  | note | Reference - Relevant MTM Standard Drawings
label | f38b1f7b-8983-5daa-a886-8ffe59c0d1b3 |  | note | Acceptance Criteria - Overheading Wiring Small Parts Steel to be procured as detailed in the drawings and as per relevant MTM Standard Drawings.
label | 12368912-23c3-58fd-878e-7137edfb4868 |  | note | • Deliveries are to be inspected to match the purchase order
label | 91f21825-3a45-5a2c-b9c3-8e9ff3a684da |  | note | Attach: Purchase order/Delivery dockets/Certificate of conformity
label | b51576b3-0083-57d3-a4da-f1a0f37b67c4 |  | note | Method - Visual Inspection and measurement
label | 6f2fe054-11a6-5da6-8f05-c271329b8ddc |  | note | Frequency - Upon delivery
label | 9a9ae8cf-589b-527f-9f82-463adc2b871a |  | note | Category - IP
label | 3b5d102a-2a2d-550c-89b5-c9d88bc5d296 |  | note | Responsibility - PE
label | d2b4931d-222f-5c52-9b6a-52185b512e35 |  | note | Responsible person - MRPA
label | 5f9347ac-56b2-541f-989b-490e654de5d7 |  | note | Verifying Documents - This ITP Signed Off
text | ed8f0551-649b-510d-85a0-4a0477377ce9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Grout
label | 16af3265-c4ba-5307-8917-132b741b0650 |  | note | Reference - IFC drawings
label | 63fef92b-a720-5223-ba1e-24d604d9459c |  | note | Acceptance Criteria - All grout under base plates shall be CONBEXTRA C or equivalent as approved. Approved grout to be Flowable shrinkage compensated with minimum 50 Mpa compressive strength.
text | 736c1915-f532-50df-bace-8e911ed4e1b1 |  | textbox | Enter: Teambinder Material Approval number
label | 80c87a6b-04aa-5906-bb55-0e4dd31f45fb |  | note | Method - Document Review
label | 4e488029-e58f-511c-bc6d-9ce332d0a827 |  | note | Frequency - Where applicable/ Each element
label | e904aa7f-86e1-5c81-af4e-c2b3a4e92814 |  | note | Category - HP
label | 79af41c1-3775-575d-9146-48753e39c0ea |  | note | Responsibility - PE
label | 5bd590e0-a147-5589-8269-588e9d8d9187 |  | note | Responsible person - MRPA
label | 9cff3a7f-18d9-51b3-bad7-9fa4afaefd4c |  | note | Verifying Documents - This ITP/Material Approval
text | 5349b714-ce56-5515-a8c6-38c47f49cf75 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Installation Methodology & Works Method Statement
label | c6587f6a-a357-5edf-bde9-03b72fe60ccf |  | note | Reference - AS5131 Clause 11.2.3
label | 8df0a5dc-e910-5e44-a3f4-ce954288e1e6 |  | note | Acceptance Criteria - Details of how the Structural & Architectural Steel will be Installed will need to be privided including the following:
label | 226c4203-33a4-5c22-875c-72287ce67144 |  | note | – Transported to site;
label | 035476c6-c2c0-5c61-a1ec-9294a0c7b031 |  | note | – Handled on site;
label | bfebf7ee-1afe-56cb-866e-a4a3a8aa94d2 |  | note | – Installation Procedure (subcontracor ITP's);
label | 87fb6b1a-d92c-5a3d-ab47-96a69d25180d |  | note | Submission of Work Package Plan and MRPA approval and acceptance.
text | bb7ce7a4-5cb9-580e-a381-3e0c0969a9d5 |  | textbox | Enter: WAP number
label | 67879b4c-cc69-51ef-b074-21e640d73b84 |  | note | Method - Document Review
label | fe395e54-c5cb-5e85-ab45-dc862e65cd87 |  | note | Frequency - Prior to Works Start
label | 06bb3c0d-0308-506b-88b1-f70b645b233b |  | note | Category - HP
label | 03578780-31fd-523c-9d11-3f9c16e4d1e5 |  | note | Responsibility - MRPA/CAT5
label | afe8ccae-6cb9-5bc8-a904-ee1905908194 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 3500f4d0-88ed-5646-936a-5daa2484e8c0 |  | note | Verifying Documents - This ITP Signed Off
text | c8c4e938-babd-5ad7-b897-66c4bd018026 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Approval of IFC drawings
label | 368e71de-5229-5aac-9a5d-dff973d76941 |  | note | Reference - Contractor Design Management procedure.
label | 7455b354-e835-57d9-8785-a417392ab4dd |  | note | Acceptance Criteria - Ensure correct and most recent revision of IFC design drawings are used for construction.
label | 9d83171d-72ba-51bf-80ad-71c1a3479543 |  | note | Method - Document/Drawings Review
label | c8117857-4586-536a-b053-7499a310d477 |  | note | Frequency - Prior to Works and at regular intervals.
label | 6606ad9b-2ba4-5d58-a610-c60c577db098 |  | note | Category - HP
label | 8900b961-9aa2-5f2a-9ad4-34a0d13e74ae |  | note | Responsibility - MRPA/CAT5
label | 3bdf8cd2-edcf-5538-81c2-7889f14f4cd7 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 8e5d91ff-6f63-5be4-adfc-457d932b6f3d |  | note | Verifying Documents - This ITP Signed Off
text | 880c9916-b058-5360-a555-0431c8be69c4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Cantilever assembled.
label | b850281a-3bc0-54a2-8a57-5e8c4546fb6b |  | note | Reference - Cantilever assembled as per IFC design.
label | 0618ae21-d518-56d9-8955-1b2a1b8b1ec1 |  | note | Acceptance Criteria - Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
label | 4a1f8606-369c-52a3-9f59-208154f61410 |  | note | Method - Visual, Document Review
label | 68669a8b-cee3-5b90-9d21-7f142c2b6857 |  | note | Frequency - Each Task prior to works start.
label | 6a92ed3f-c499-583e-8d0d-5d3a4f3453e5 |  | note | Category - IP
label | d3fad57c-002a-522c-b4c4-3e028e709cfa |  | note | Responsibility - CAT5/MRPA
label | 699579d4-0032-555f-8f81-2b8dcd88b034 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 003bc675-31a9-5700-b3ea-13ad08a6ce08 |  | note | Verifying Documents - This ITP Signed Off
text | 1925b685-0a9a-5940-8e82-12e40e52d9dd |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Mast Installation
label | d7fa4e75-f469-5ebc-81f4-87706b0cc63e |  | note | Reference - Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
label | 4bd483c3-e3c9-5aca-b9d8-be3ce2ec148b |  | note | Acceptance Criteria - Work instructions in accordance to IFC design
label | 164f2b7b-93c7-56eb-b74c-aae44483a219 |  | note | Method - Measure, Visual
label | 55954879-c213-5dc8-8484-8997d9c968bf |  | note | Frequency - Each OHLE Structure
label | e5c5d5e6-12cd-50e0-b9aa-dae80c849b46 |  | note | Category - IP
label | 90803712-af54-5e9a-9960-b619c0bafdb0 |  | note | Responsibility - CAT5/MRPA
label | bae94ef2-b026-5f87-b2c8-709d4f3d0e58 |  | note | Responsible person - MRPA/CAT5 Engineer
label | e3944dd8-bddc-5fba-80ad-a08a8389b0bb |  | note | Verifying Documents - This ITP Signed Off
text | 185e3853-3b16-5fd8-8036-33e82070735c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Cantilever installed.
label | 72916c76-b4c0-5610-a03e-d6a497b0b3db |  | note | Reference - Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
label | 2937d25a-6369-5345-a242-76e5efca9317 |  | note | Acceptance Criteria - Work instructions in accordance to IFC design
label | ae493b9b-a16c-5eeb-b0ec-f310510fd231 |  | note | Method - Measure, Visual
label | 8da15e91-9ceb-5b6c-9b7a-ffd9363377b1 |  | note | Frequency - Each OHLE Structure
label | 270fe969-e7d3-52be-99f0-ae19c188da46 |  | note | Category - IP
label | 1191c96f-1b99-59b5-90b9-72d440521b2e |  | note | Responsibility - CAT5/MRPA
label | 1a171ecb-2900-52a9-b704-33364a87b3cc |  | note | Responsible person - MRPA/CAT5 Engineer
label | a4619230-92ba-56a6-b7c6-2ee082f5dd14 |  | note | Verifying Documents - This ITP Signed Off
text | e876fabf-0620-57d8-b177-a3d4ef33efc5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Bearing type Joints TB Friction type joints TF
label | 5423b22f-52ba-53d2-855f-ac5ee8aaa96a |  | note | Reference - IFC Drawings
label | 573fad50-0d61-5bd4-8258-b4262d7dbe57 |  | note | Acceptance Criteria - BOLTS DESIGNATED TB & TF ARE TENSIONED AS PER AS 5131 and Table 8.5.6
label | 9fa1d3e7-495f-5740-a080-a6deff8bcd6c |  | note | – Bolt mark ups (in case of partial tensionening) should be visible for inspection
label | 6addbb4c-2134-58ac-928c-3d5aebcafda8 |  | note | – DTI squirts are to be visible for inspection
label | 6f02c5d0-2904-58ad-b685-2f8427d4d845 |  | note | Method - Visual
label | 8c6997de-b5dc-54e1-ab9f-968e9aeedf3c |  | note | Frequency - Where applicable/Each element
label | 93083ea4-055a-5c8f-90a3-f64fd557388b |  | note | Category - IP
label | 6ab03fce-e0d3-5242-848d-0cae03130dd4 |  | note | Responsibility - PE
label | 43fc32e5-896d-5442-a921-a59c2152e505 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 882665a2-68be-5e5c-9925-f66895636292 |  | note | Verifying Documents - This ITP Signed Off
text | 289b128e-cc79-5baf-9560-c4dbd08ea339 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Install SPS to correct height / position relative to track
label | 98eeb97b-55c3-5e5d-a63d-6f74b05346de |  | note | Reference - Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | d49bc80d-a8fa-5fc6-b0a3-891f4f7cc8ea |  | note | Acceptance Criteria - Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly.
label | ffc8eb28-0fe8-5436-938a-16daafa0a6ce |  | note | Method - Measure, Visual
label | a0e53f07-4bc6-56f8-82d8-38d6cea891c1 |  | note | Frequency - Each OHLE Structure
label | 89afd2e7-b989-53bd-822b-ae8eb97c176b |  | note | Category - IP
label | 4142806a-586a-553d-aa0c-3817ec479052 |  | note | Responsibility - CAT5/MRPA
label | 5342fb19-ee01-5b87-b0e5-ecf2b262b8c1 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 12cdb7dc-6e9d-5c57-a4f4-f747226f1b76 |  | note | Verifying Documents - This ITP Signed Off
text | caf7854a-3ef9-5e58-a8b0-cb96905f317e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Cantilever checked once installed.
label | 1d1e9baf-cf72-5ac7-acf9-689f4fffc6f4 |  | note | Reference - Cantilever checked as per IFC design drawings/MTM design range. Completed check sheet. CAT5/OHLE/CHK002
label | 60910551-84f1-5a67-a641-fbfd061eeb36 |  | note | Acceptance Criteria - Supervision checking to ensure that equipment is installed correctly.
label | aa35198b-efd7-508a-9532-0bb25081ff9f |  | note | Method - Measure, Visual
label | 5e068f40-e647-5429-a91a-afee2528e43c |  | note | Frequency - Each OHLE Structure
label | 175d8d21-7874-5005-b2f4-5907c7e057b1 |  | note | Category - IP
label | 5753d68e-1701-5c40-9c46-9660f5652712 |  | note | Responsibility - CAT5/MRPA
label | 072c91cc-ca8f-5d0d-b286-5216c49eafbf |  | note | Responsible person - MRPA/CAT5 Engineer
label | 8793ebca-4e73-544b-b07b-cf2a834632ba |  | note | Verifying Documents - This ITP Signed Off
text | 63ab84da-706f-55f9-91cf-a26a1003da38 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Base Plate Grout
label | 03cede83-307e-56ad-8ccf-75b63c65f8c2 |  | note | Reference - IFC Drawings
label | 9e171f96-5e9b-52a7-9b63-eb78f777b9a7 |  | note | Acceptance Criteria - Grout to be mixed as per manufacturer TDS.
label | aaf273a0-14bf-5430-8ddb-307cdbc70e28 |  | note | • Grout to be poured under base plate as per IFC drawings. Grout over pour is to be 6mm and cover area with Nom 50mm offset around the base plate.
label | c97fb2f9-f1df-5eb1-9535-cc73fd2225bf |  | note | Method - Visual
label | 8acb541d-f163-5920-88c8-7a8805e98d69 |  | note | Frequency - Where applicable/ Each element
label | e39559b0-e518-5720-b2c4-ef1288522170 |  | note | Category - IP
label | 7e36eb3f-15f3-5eda-9284-b2aa411ca2b9 |  | note | Responsibility - PE
label | 16d8ecfa-b5c2-5654-af1c-891dca27e6dd |  | note | Responsible person - MRPA/CAT5 Engineer
label | 4c091ce7-10b6-5890-be1e-a8c42a0232ce |  | note | Verifying Documents - This ITP Signed Off
text | 493d12cd-88c9-5e3d-9fce-7add77cfe733 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Installation of wire supports at the correct height and stagger
label | 539adbc3-dcf4-55ee-be2a-325571885060 |  | note | Reference - Install as per design
label | f69c7e4a-89e9-5854-ab64-106f8e7445fa |  | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
label | e99b72a1-7ad6-549f-b16f-04a4876f67a6 |  | note | Method - Visual
label | 36980f2f-bc58-5250-8346-3504777c7855 |  | note | Frequency - Each OHLE BWA Structure
label | d94c9af4-dddd-5192-b51a-c0dda5f3283b |  | note | Category - IP
label | 6845e37e-314d-563a-8c8f-5f225055964c |  | note | Responsibility - CAT5/MRPA
label | f6ed7c85-c1e6-5534-b7fb-cf5e6abc171f |  | note | Responsible person - MRPA/CAT5 Engineer
label | 7459bd7c-eabb-575a-85ca-b5fac33eac47 |  | note | Verifying Documents - This ITP Signed Off
text | cf0923e4-7127-5b39-9d22-5097963929dc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Install to correct tension
label | 782f3c8c-be77-5b78-9018-6e8e58a79fe2 |  | note | Reference - Install as per design
label | 7669bb2b-579d-580c-a199-73394edd8584 |  | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
label | 98b9bbde-42c8-52a4-9dea-ac8ce0e49df3 |  | note | Method - Visual
label | 34e054d9-fb74-5655-a983-e1f4d20bfc62 |  | note | Frequency - Prior termination
label | 113a1880-5aaa-58e0-90ee-c47659cf4bdb |  | note | Category - IP
label | ad11b4f3-8db6-5730-8b1e-3d67c693489b |  | note | Responsibility - CAT5/MRPA
label | 26b458b2-78e9-5eb0-bf17-88fdfcf6f51d |  | note | Responsible person - MRPA/CAT5 Engineer
label | da636222-c2a3-57bb-ad69-2fd8c2f56435 |  | note | Verifying Documents - This ITP Signed Off
text | 6570bee7-7c2e-5dc3-9ef9-186528384b97 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Defects/Temporary Works
label | b7fdcbb1-c935-54f3-9e03-139089ec12bc |  | note | Reference - IFC wiring layouts, cross sections and design drawings.
label | a331a43b-777a-5c6f-9fa7-0d269661b744 |  | note | Acceptance Criteria - Ensure all Defects/Temporary works are capture and closed out correctly.
label | 71d61591-7fe3-552f-9bc5-f2414166c90a |  | note | • Defect list to be provided at the end of Occo identifying planned work to rectify
label | 7a67192f-51df-512a-a193-dd0c62120e27 |  | note | • Attach Design mark up, Defect list, temporary bond register, and approved TW design
label | 8a1da561-485a-532b-a3ce-0ea94ea5000a |  | note | Method - Document Review, Visual
label | a9eca315-b848-5ef5-af84-69891bc8424e |  | note | Frequency - Each OHLE Structure
label | 4a478cd6-a6ab-5d50-b011-52df20e93f48 |  | note | Category - IP
label | 82272085-0e5c-5298-b092-111f410bc0d1 |  | note | Responsibility - CAT5/MRPA
label | bb855b39-aee0-59ad-841f-ef4a5e4f0924 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 1c15292f-aa0f-5156-b2e6-a69ec820e23c |  | note | Verifying Documents - This ITP Signed Off
text | d99ccbce-7b98-5cf4-903f-72a867c542a4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Relevant documentation readily available. (As-built Survey)
label | a67cccf8-2a0d-5571-bd79-8cbf5c1980f8 |  | note | Reference - As built drawings and check sheets to accordance to MTM Design spec.
label | eb4f5970-6170-542c-be3b-03bfd0571f48 |  | note | Acceptance Criteria - Ensure delivery of relevant documentation to client.
label | 21dd5b86-030d-5d7e-926c-fe2a023f4d73 |  | note | • As built drawings and check sheets.CAT5/OHLE/CHK/002 check sheets.
label | a3c24381-e773-5a9f-89e3-7135dd09e59d |  | note | Method - Document Review, Visual
label | 12870edc-9409-5622-a011-eec68ce26af3 |  | note | Frequency - Each OHLE Structure
label | 1a3336ce-fb6f-5921-a6a9-ca628ac26423 |  | note | Category - IP
label | 41378d87-fec4-52bd-9b0f-47dc5501dff3 |  | note | Responsibility - CAT5/MRPA
label | 11adcea8-0168-568f-9074-00f930ead2b7 |  | note | Responsible person - MRPA/CAT5 Engineer
label | f0f70156-0135-5099-a9f5-c407ef1af77c |  | note | Verifying Documents - This ITP Signed Off
text | 0927b0a2-775a-5e13-91e3-c79ea5f94406 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | e55c9aba-0ac2-5905-9535-e7e494f72dbe |  | note | Reference - MTM Quality Management Plan
label | 208b0531-628b-532b-b163-79daa7369fd7 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | e091dedd-d16b-585a-9122-05ae465f02c3 |  | note | Method - Document Review
label | 85031bd7-60d9-5ae9-92ea-6eb70c964bff |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 4552a864-685b-546a-8df6-0e34156576c4 |  | note | Category - HP
label | 8ca1cd12-9e96-558b-a39c-f36f5f68b8ce |  | note | Responsibility - CAT5/MRPA
label | 7e7f0af0-24f5-5303-9d15-2cba98f82752 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 5fad917a-8b9f-56eb-b182-59cd7ce74386 |  | note | Verifying Documents - This ITP Signed Off
text | aadf3dfc-60a4-545a-b43b-9fb73f545a9b |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | a8f47ae1-9e40-58c8-9e85-fffeff467ee2 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 2230d07b-e89a-59a5-a6b2-64156b49655c |  | textbox | Name:
text | 8a49cbd4-0edf-5503-9a02-a05e2b7fe0da |  | textbox | Position:
text | 34f1fedc-b615-5efb-b162-42491ff8e638 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation | itp |  |  |  | Yes | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | 1c13b79f-05b4-4abd-b61f-9be7a4ee36b9
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 54cbbd25-0217-5f93-8c04-32ab25705d02 |  | note | Document Title: ITP-048-CIV-Calder - Stormwater Drainage Supply & Installation
label | 42c73e1f-b4fe-5e17-a4e6-fe786d9930e6 |  | note | ITP Description: Stormwater Drainage Supply & Installation
label | 1072443b-4ce6-5d29-99dd-1e5558e3eec9 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 97538d00-08c4-5a58-9b5e-371d88c3ab2b |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 0b1049cc-c86a-56cf-a523-601b79eabb9d |  | note | Revision Number: 0
label | c5684dc8-88cd-5f91-a657-01aa964aac1f |  | note | Revision Date: 19/07/2023
label | 2c42a650-f171-5637-9c8a-f3c8221f848a |  | note | ITP created by: Ethan Caruana Smith
label | 3a4fd5a2-f344-530b-8cff-3ad6650804a5 |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 049d257f-d67a-5254-9e87-432b7942d94f |  | note | Reference - VicRoads Section 701 (May 2020)
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 1373b251-3ace-5e65-b601-89dd12746253 |  | note | Reference - VicRoads Section 705 (June 2021)
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | 290abb78-b920-58d1-882c-07f26b057f92 |  | note | Reference - IFC Drawings - package 13
checkpoint-group |  |  | section | 2. Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Drainage Reinforced Concrete Pipes (RCP)
label | 5133ef34-9f0e-5f1c-a55a-73ea66b52c6f |  | note | Reference - Section 701.04, Section 701.05, Section 701.09
label | 60fa969a-ef98-52e5-badc-796c6863f8f3 |  | note | Acceptance Criteria - Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with AS/NZS 4058 and Sections 701.05 & 701.09
label | 1d9b6d4d-27f2-5f39-b007-284f3632a292 |  | note | • Precast reinforced concrete box culverts shall comply with the requirements of Section 701.04
label | 04545dc0-1ab0-591f-8f08-70a29a845bb5 |  | note | • Rubber ring joints shall comply with the requirements of AS 1646
text | 38bbd1f4-2d65-5143-a9b1-6247293e3f6f |  | textbox | Enter: Teambinder Material Approval number
label | 93b9fe18-2b6f-5666-a865-555cefa2e92c |  | note | Method - Document Review
label | d79391aa-d611-5d18-aaa6-c67571466739 |  | note | Frequency - Each lot
label | 594117ee-77f5-5ab2-bb85-e26d59148d12 |  | note | Category - HP
label | bf3f0b6e-d05d-5464-8cf9-3c441e8eaa6e |  | note | Responsibility - Nominated Authority
label | 4878f0ce-de8f-51a7-82a5-2415a004563d |  | note | Verifying Documents - Teambinder Material Approval
text | 769d6910-4e6b-5e3d-a923-aa280010a925 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Drainage Flexible Pipes
label | 2719ec57-48eb-52f2-bf32-78fbf41e4fec |  | note | Reference - Section 701.08
label | 54afc51d-7959-5eca-a6ca-cee0aada02ec |  | note | Acceptance Criteria - Flexible pipes shall be supplied in accordance with 701.08
text | 1893723f-e63d-5060-b679-921de47f50ee |  | textbox | Enter: Teambinder Material Approval number
label | 5ad4e039-2896-55b3-8b69-ba5ce5ccb4d8 |  | note | Method - Document Review
label | 28c02fcd-976e-5151-b77e-bc0f9325dffb |  | note | Frequency - Each lot
label | a488a7ae-65cf-59ac-aa33-b0dcf57394c9 |  | note | Category - HP
label | cf212d1a-bc40-53da-b07b-9a464ca7db40 |  | note | Responsibility - Nominated Authority
label | 50a55385-8b8e-5017-90fc-cc6b36b4393b |  | note | Verifying Documents - Teambinder Material Approval
text | dfe786c1-a388-5026-97c3-63068e294d77 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Precast Drainage Pit
label | f0d33795-6cf4-5e2c-89b2-cb962804e517 |  | note | Reference - Section 705.07, Section 705.04, Section 705.09
label | 4259a9fd-ffa0-506a-b45d-85fb802bb345 |  | note | Acceptance Criteria - Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09
label | 0fbdbc27-1134-5b87-83d7-3d91964e65f6 |  | note | • All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
text | 5ff9ae96-528a-53c9-8c59-720be22cbb93 |  | textbox | Enter: Teambinder Material Approval number
label | 83dae22d-3dd4-539c-8ad9-b87f915e213b |  | note | Method - Document Review
label | b05605b5-c370-548e-a9bd-8a5b67ae4d42 |  | note | Frequency - Each lot
label | 9862f83a-a3a7-5540-ad14-a1b7d1b9ce5b |  | note | Category - HP
label | ce3276fb-1124-57dc-973d-69937c3ceade |  | note | Responsibility - Nominated Authority
label | 254f27fc-ce7e-51b3-b351-efb9371d71a8 |  | note | Verifying Documents - Teambinder Material Approval
text | 6deee45d-38ca-55a0-9dd0-bafda30155c6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Cast in Place Drainage Pit
label | b0c6263a-4906-5eeb-bed0-6a05159afefb |  | note | Reference - Section 705.06 IFC Drawings
label | 4c574fbf-66de-5d27-adc5-9762d785a5ce |  | note | Acceptance Criteria - Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings.
label | 7356e754-fcfb-5158-b07d-ab82d4f69446 |  | note | Method - Document Review
label | c8012b05-25d5-55fc-a331-524090c05bca |  | note | Frequency - Each lot
label | 2cd6f092-3b20-573f-8a36-6f31eb417ee7 |  | note | Category - HP
label | 1552e327-2f0f-5c95-8180-dd0104a1610f |  | note | Responsibility - Nominated Authority
label | 8583b9f9-0559-5e0c-9103-743cc4278ea2 |  | note | Verifying Documents - Teambinder Material Approval
text | adb3fb5f-7143-5e51-a951-971fe87f493f |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Drainage Pit - Step Irons
label | de1765f1-a411-599f-ab5a-14b9678c3e3a |  | note | Reference - Section 705.04, Section 705.12
label | 3e26662e-84bf-510e-b3f6-d42424d71596 |  | note | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
label | bee12f83-908c-5b48-82cd-93c14abc4787 |  | note | • Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12
text | ba8abbd4-9dc4-55f9-80ee-e47b2f3f5d49 |  | textbox | Enter: Teambinder Material Approval number
label | 99b5df9e-9c16-547b-8db6-0e7acb88655f |  | note | Method - Document Review
label | 6272a703-8f4d-5f92-a46f-463b35b49417 |  | note | Frequency - Each lot
label | df43af24-e5f9-578b-a8d3-ea92460ea8a4 |  | note | Category - HP
label | 022e485b-8cd8-5a48-bfcd-facc399c0a54 |  | note | Responsibility - Nominated Authority
label | 0177011a-dcb4-5593-9ecf-79e631c2132f |  | note | Verifying Documents - Teambinder Material Approval
text | e7f9e350-cb0a-507b-870f-3d7359d1e940 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Drainage Bedding Material
label | 92e4115c-4958-5781-b554-bf6a0f20ebc2 |  | note | Reference - Section 701.09
label | 424a6ae9-cf56-542a-a746-425541df9ac4 |  | note | Acceptance Criteria - Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
text | b7242711-1be5-5a69-a5ac-d51aae795379 |  | textbox | Enter: Teambinder Material Approval number
label | 8d2e688d-6ca9-52a8-88f4-53fe73f2d64f |  | note | Method - Document Review
label | a0500e5d-b26a-544a-99ad-58f9d349ad7c |  | note | Frequency - Each lot
label | a2331930-1dea-5021-a18b-54000a2ea669 |  | note | Category - HP
label | 8d52516d-7bc1-5423-9d05-8301e55b1d82 |  | note | Responsibility - Nominated Authority
label | 66026fc8-7e6c-56ba-be5c-c1ebfc74f4e0 |  | note | Verifying Documents - Teambinder Material Approval
text | df192745-9d6d-55fc-a48f-006c81689cff |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Drainage Backfill Material
label | a5660455-5648-51f1-b7fb-301f2a5deba1 |  | note | Reference - Section 701.09, Section 701.19
label | eb8c7bb1-a2ea-5db9-a7ec-0c8b9eaecb67 |  | note | Acceptance Criteria - Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
label | e757e716-dab5-5cd7-895a-67df1ae343c8 |  | note | • Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with Section 701.19
text | 61bf1fb8-75bd-5da6-8e72-349d8471ce1d |  | textbox | Enter: Teambinder Material Approval number
label | 864c98a8-82bb-565f-a93e-7b180f524d1c |  | note | Method - Document Review
label | 22480f11-8375-57bb-852a-5c1c1528c943 |  | note | Frequency - Each lot
label | 7b9585be-690d-5fb7-b91a-397f553be0af |  | note | Category - HP
label | 5f601394-7c21-52f9-8574-5e16fd000b39 |  | note | Responsibility - Nominated Authority
label | 16fe453e-e1eb-55ec-b9b6-45254763d6a4 |  | note | Verifying Documents - Teambinder Material Approval
text | 8eba1970-91ea-5481-8588-8c186a8afb48 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries-Documents
checkpoint-status |  |  | checkpoint | 3.1 - Subcontractor ITP (where required)
label | 0362af02-66ae-56aa-b8e3-143176e6cebc |  | note | Reference - Subcontractor ITP
label | 74fe2701-1e67-5a33-a25f-d5999fd059bf |  | note | Acceptance Criteria - Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
label | f4da3484-f959-5392-9bc5-df6fa0c81d53 |  | note | Method - Document Review
label | e4b52356-3e31-5a47-80de-822155694525 |  | note | Frequency - Each Lot
label | 741383f5-65b6-5f2e-b248-01222b681a81 |  | note | Category - HP*
label | 9d7642fa-522e-5a59-95a5-399135116f82 |  | note | Responsibility - PE
label | e0f5210b-b100-5b1c-825c-947dbf860573 |  | note | Verifying Documents - Refer to ITP
text | 4587736f-0ffe-544c-8863-dc96ee2c1506 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 4. Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set Out - Pits & Pipes
label | 70d94c64-0326-55f9-aed8-1e9443ff6694 |  | note | Reference - IFC Drawings Section 701.10
label | dd704398-4feb-5fd9-b7de-203238535d62 |  | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
label | 64d2893b-b9d5-5492-9634-59836d22c7a4 |  | note | • Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
label | 4d466f72-d787-5032-9238-749becd181fb |  | note | Method - Survey
label | 9756bab9-b149-5172-baf5-acee85f08548 |  | note | Frequency - Each Lot
label | 7d36971f-7c74-5382-98c2-bc8555c48b17 |  | note | Category - HP*
label | 8fc73ffc-44c2-519d-b384-d4c9b16b960b |  | note | Responsibility - PE
label | a721a0a8-2053-5220-8bf4-ddb3321ce645 |  | note | Verifying Documents - IFC drawings - package 13
text | 1af63d70-f385-5962-b8f5-e5fcb3ce30b0 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Pits - Excavation
label | caa95059-ace6-5199-9990-4ad82c896447 |  | note | Reference - IFC Drawings Section 705.05
label | 0df875a6-d97e-58ed-abce-9e62aba8665f |  | note | Acceptance Criteria - Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
label | 005a2253-2af7-535b-b65c-d6f3aac7dcf4 |  | note | Method - Visual inspection, Measure
label | f0847ad8-fdc3-539b-9b13-d8141a2ac768 |  | note | Frequency - Each Lot
label | c320091e-83a4-50b1-960e-e9b2d0dc85ce |  | note | Category - IP
label | fba45ade-d691-57f9-b739-4c15f3139464 |  | note | Responsibility - SE
label | 0a3be269-25d8-5ce4-961b-34baa0fee62b |  | note | Verifying Documents - IFC drawings - package 13
text | 3f0fbeb9-cbf6-56bd-b405-b218c9fb5303 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Pits - Placement of Bedding Material
label | 609fab17-84d4-5385-b21c-c8c916a554e2 |  | note | Reference - IFC Drawings Section 705.05
label | f3e827c5-5f0a-5493-89aa-233561c74707 |  | note | Acceptance Criteria - Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness:
label | e9d78fb0-ba1d-5577-8796-a215571d5375 |  | note | • > 80mm for clay foundations
label | 8a7ca185-d9f1-571e-8179-dcfdbff540a0 |  | note | • > 150mm for rock foundations
label | e2ca7365-89fc-5740-88bb-0a1fe4cbb501 |  | note | Method - Visual inspection, Measure
label | 9b82bc28-c862-5f94-93af-31ff125b58b6 |  | note | Frequency - Each Lot
label | c3b42d33-2e82-5270-b05c-286292481427 |  | note | Category - IP
label | bda556e7-9678-564a-af54-601482fe6436 |  | note | Responsibility - SE
label | f466157f-630c-563e-b50f-0bf19e6e8284 |  | note | Verifying Documents - IFC drawings - package 13
text | 4011c2ae-7d9f-50c9-b6a9-a9c1e6354ce3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Pits - Bedding Testting
label | 30c88298-f054-5a0e-9947-59bb39746955 |  | note | Reference - IFC Drawings Section 701.20
label | efbe308c-b7fd-5388-9e83-ef80f4c80a3f |  | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
label | d8170177-29fc-5785-9e23-84c3c2dafca8 |  | note | • Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | 29cc3f78-d7a9-56f9-89f3-a7e26d461c1c |  | note | Method - Compaction Test
label | 71aa1913-9300-510d-8913-56147226a8fb |  | note | Frequency - Each Lot
label | 7d473651-ab4c-56ab-86a1-2838bfdb5322 |  | note | Category - IP
label | e253adbc-c019-509f-9768-640f74766ada |  | note | Responsibility - SE
label | 00cc67cf-1598-58e7-b016-820aa2cb6e15 |  | note | Verifying Documents - Compaction test results
text | 181ec86c-9008-519a-8cfd-3f9fc4eb1ff1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Pits - Placement of Precast Drainage Pit
label | 8445a6b9-8a3d-514e-8157-37f9148cb128 |  | note | Reference - IFC Drawings Section 701.10
label | c6fb90dd-63b7-5bc1-a6bf-1c2728b8b0fb |  | note | Acceptance Criteria - Survey pick-up to verify:
label | ccfdefae-6536-5657-9d8b-dcd0e4f4e530 |  | note | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
label | 0bc0715d-666a-5418-93bd-ab4ddbc06334 |  | note | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | 42ae0187-5739-5608-b095-b759dd7ba63c |  | note | Method - Visual inspection, Measure
label | 3d954ba7-3fca-5eeb-bdfb-8de74a14d406 |  | note | Frequency - Each Lot
label | c6f71124-5932-5f7e-a29c-414e6a2fc497 |  | note | Category - IP
label | 4fa75a0f-ad76-5d98-bb8f-4493b007fd6f |  | note | Responsibility - SE
label | e3910c1c-1b87-513a-873b-512a664cf162 |  | note | Verifying Documents - IFC drawings - package 13
text | 173c371a-c9c3-5cdc-b815-cce2a719bfc8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Pits - Cast in Place Drainage Pit
label | 11b9adce-0de9-5265-981f-52b43044d990 |  | note | Reference - IFC Drawings Section 705.06, Section 610, Section 611
label | 66eb6791-a02b-5420-a903-48a950aef3e5 |  | note | Acceptance Criteria - Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings and in accordance with the requirements of Section 610 and 611.
label | 602e3814-ca47-5c16-9e5b-6384a1a445b4 |  | note | • Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
label | 1842684d-4e3f-5baa-b3a7-6face97eea13 |  | note | Method - Survey, Measure
label | 6a0db754-2204-5b87-b445-f024a2c0ebb7 |  | note | Frequency - Each Lot
label | fb5c4c5a-ebe5-5a27-be94-7fb7c2f09259 |  | note | Category - IP
label | 11db52ba-3dd5-5b3c-82db-c3e00b0c96d3 |  | note | Responsibility - SE
label | d2bd30c4-1f9f-52fe-ab8f-97a31689a72a |  | note | Verifying Documents - IFC drawings - package 13
text | 18e8b6c4-67ec-563b-816d-88c9c5d15c75 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Pits - Jointing & Drainage Connections
label | aef13145-6a72-51e8-a6c1-a49a24fa9dd2 |  | note | Reference - Section 705.11
label | 26eee097-7ab9-533a-bb3e-15befbbf2076 |  | note | Acceptance Criteria - All connections to drainage pits shall be neatly made in accordance with Section 705.11.
label | a6d44c82-1458-5642-91dd-3f7239a9abe1 |  | note | • Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
label | a97984fa-5060-54a3-9cca-10a4c5b9f7ab |  | note | • Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
label | 4aa122b2-4eb3-5fbf-b6c1-3d502ab6295d |  | note | • Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
label | 85ebb87e-6876-54ab-a791-198b255482c0 |  | note | Method - Visual inspection, Measure
label | 2c0242e6-09e0-5907-9326-7f28423d5aa4 |  | note | Frequency - Each Lot
label | 12165db4-9657-537a-89fa-762c3e28be9e |  | note | Category - IP
label | 776ac49f-e001-513f-8e2b-e2e218704adf |  | note | Responsibility - SE
label | a68b4be4-f8fa-5ace-9228-c4a1650de199 |  | note | Verifying Documents - IFC drawings - package 13
text | 90747576-042a-5739-a315-5d5c7ba662eb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Pits - Shaping of Floor
label | 11a21eee-7f8d-5091-8e87-a3fe26b4dcb0 |  | note | Reference - Section 705.13
label | c3844a26-6931-5129-85bd-f4947853cc6f |  | note | Acceptance Criteria - Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with Section 705.13.
label | 5fbcb750-2786-58ba-8e35-42be64ef7263 |  | note | Method - Visual inspection, Measure
label | 2f1c57e7-accf-5775-bcb9-21bdb4d2a645 |  | note | Frequency - Each Lot
label | 012e16f5-31dc-5eed-8a04-7e6e01bdd01c |  | note | Category - IP
label | 5279eeef-cf53-5055-a392-30e38e8e1431 |  | note | Responsibility - SE
label | 771a23d8-b310-5318-8cd3-28c3c1246ca3 |  | note | Verifying Documents - IFC drawings - package 13
text | b5efdb44-349e-5ed2-8fea-848691c36cd7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Pits - Step Irons
label | 40a287a2-a3d8-56ec-ade2-04c5881fbb4e |  | note | Reference - IFC Drawings Section 705.12
label | 20ceb859-c1dc-5169-aec8-a34318bd7296 |  | note | • Brimbank City Council Engineering Detail 275
label | 724e50b7-ddaa-5fdf-b350-a980cb98fb73 |  | note | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser.
label | 01ab8bb9-deea-5046-bafa-1bcd43095040 |  | note | • Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
label | 98f31534-53ac-502c-92ef-e19653b495cc |  | note | Method - Visual inspection, Measure
label | 169e9152-ac78-5188-8233-9a9bcd1bd1f3 |  | note | Frequency - Each Lot
label | 64427089-cd42-5da3-8cf0-83a58241e5d2 |  | note | Category - IP
label | 9b336f7f-c7b9-573e-bc89-19582b1842cd |  | note | Responsibility - SE
label | ad0afc5b-c6c1-5289-8523-68eb0d7aaa29 |  | note | Verifying Documents - IFC drawings - package 13
text | 3fea7099-4584-58e1-b04c-6222185ca8cc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 - Pits - Fitting of Covers
label | c974319c-a80a-55a8-90df-55f9cbf46fd6 |  | note | Reference - IFC Drawings Section 705.17
label | fa4568e0-8706-57b9-8ea3-66e2b131097e |  | note | Acceptance Criteria - Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement and sufficient water to produce a mix of suitable consistency.
label | 7e734e95-8d50-516c-b6c2-0d4f5d0d3ad0 |  | note | • Height shall be within 10mm of the design level.
label | 8cac3de9-c7b1-558e-9c08-87c7c76f56ca |  | note | Method - Visual inspection, Measure
label | 1bd06876-0670-5640-bc1e-97a7286bd1f2 |  | note | Frequency - Each Lot
label | e5b15a2b-280c-5f2f-8a8d-87edfee396e3 |  | note | Category - IP
label | fe506aea-af53-5eb5-9e98-071f3f1ebfc1 |  | note | Responsibility - SE
label | e2be20f2-4046-54c3-b10b-b0045cef53f5 |  | note | Verifying Documents - IFC drawings - package 13
text | 6a2b9740-d520-5755-bbcc-ac7a97bb5da0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 - Pits - Pit Lids
label | 0c45472c-5923-5b1c-86cd-21d85703da0a |  | note | Reference - IFC Drawings
label | fbc0a655-d3d6-501a-8f7c-d9bb2e23d3b7 |  | note | Acceptance Criteria - All stormwater pits shall be provided with a locakable pit lid minimum Class D with in-fill material or fibre glass Terra Firm Enduro or similar.
label | 87cac1bf-cfc6-5b7f-b83e-af51beb10ab6 |  | note | Method - Visual inspection
label | c8be6773-b101-516a-8195-b8d4743f95f8 |  | note | Frequency - Each Lot
label | 12853f30-dfc1-521a-af48-b297d4951952 |  | note | Category - IP
label | 0003b34d-d6c8-5bd7-8814-0f49cbb1aa69 |  | note | Responsibility - SE
label | 10e02d3c-da54-5add-9402-954722e52bde |  | note | Verifying Documents - IFC drawings - package 13
text | 36a30aad-afd0-5ecc-b140-9b244fb9e3b7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 - Pits - Backfilling Around Drainage Pits
label | 178e5b87-8106-5221-99a2-27e38afb9038 |  | note | Reference - Section 705.18
label | b131c02f-261d-57dc-b77a-974334f5c1f4 |  | note | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
label | cf2f2e73-08ae-50a3-9747-02ccf0ee94e8 |  | note | Method - Visual inspection, Measure
label | 6f61a433-63f9-55f9-867b-f61365bd85b5 |  | note | Frequency - Each Lot
label | 8ddcaab2-879c-5d47-b0d3-3f8344c33171 |  | note | Category - IP
label | 990993e6-7ca6-5e0c-b636-2ede6d5f79dd |  | note | Responsibility - SE
label | 58ed6474-63ee-503a-8879-c22329a96c36 |  | note | Verifying Documents - IFC drawings - package 13
text | c24005f5-35c8-5c2a-a895-2c956031df36 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 - Pipes - Trench Excavation
label | 70f598f8-8a81-51da-ba68-7e612d466779 |  | note | Reference - IFC Drawings Section 701.15
label | 3e383ca7-800f-530d-889d-6edad882bd3f |  | note | Acceptance Criteria - Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
label | da5cd7e0-3e89-54a4-b0a0-849a087fc333 |  | note | • > 300mm, < 600mm for RCP
label | 35dcaf5f-7278-551a-aef4-1ef908d3cfb7 |  | note | • > 150mm for Flexible Pipe
label | 939af018-0859-54ad-8d35-62179dd2f936 |  | note | • The base of the trench shall be compacted to refusal using mechanical plant.
label | afae5658-0092-52f5-9523-dd40c21b40ff |  | note | Method - Visual inspection, Measure
label | 6fe0ddd4-9fff-5ff9-a084-181a9f1bae48 |  | note | Frequency - Each Lot
label | 517bd21e-590a-57a8-a514-212e98cfb3c1 |  | note | Category - IP
label | cd68f300-3f13-5e97-a37d-f1d9e118998d |  | note | Responsibility - SE
label | 30de6eda-2a4b-53a4-bd58-e87c077dab9d |  | note | Verifying Documents - IFC drawings - package 13
text | 84b39d09-9072-509e-8217-361460d00cd1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 - Pipes - Bedding Placement
label | 39b60e51-97dd-55a5-9364-7ca2537d65df |  | note | Reference - IFC Drawings Section 701.16
label | c4a65476-e603-538b-84f6-fd22522a704f |  | note | Acceptance Criteria - Bedding material shall be provided and placed in the full width of the trench to the below minimum:
label | cd28d9ca-ab30-5164-8c8f-ebe9298a09dd |  | note | • > 100mm where D<1500mm
label | af9f4397-ef7a-59fc-8e41-e9dadf561ca0 |  | note | • > 200mmwhwere D≥1500mm
label | 73d173e5-cf31-5f96-841c-ba95e5df225f |  | note | • Bedding material shall be placed and compacted in layers <150mm loose thickness
label | 5f7b10ac-fad9-5b93-a873-db644544b6c8 |  | note | Method - Visual inspection, Measure
label | a57efc41-4bc3-5d88-b84e-04b49aceed04 |  | note | Frequency - Each Lot
label | 07897e3a-db62-5748-935c-407b60db9a71 |  | note | Category - IP
label | c706220d-d9f2-5fb6-9eeb-d061b57cc91b |  | note | Responsibility - SE
label | ea9b5601-a046-5122-9ee9-c8bd1c3e7a20 |  | note | Verifying Documents - IFC drawings - package 13
text | df3c6be1-a4d0-50c3-824a-93e0069aa5d9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 - Pipes - Bedding Testting
label | fd0dd52e-857a-58e2-8649-bd8cfc704be3 |  | note | Reference - IFC Drawings Section 701.20
label | 2b30d468-d416-594a-a02a-335673a91ec8 |  | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
label | 0333d10c-86fe-53d3-9d6c-5a23e873a324 |  | note | • Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | 71405129-e773-5876-bd01-f48f9913bf23 |  | note | Method - Compaction Test
label | fe6f172a-98a1-50d8-8c3b-e4a8518cab43 |  | note | Frequency - Each Lot
label | d35efc8a-9dbe-5f16-81b4-484747d42ba4 |  | note | Category - IP
label | 972fd341-9d18-5f52-9ecb-53a24adf158a |  | note | Responsibility - SE
label | 6b8ca982-9103-56b3-9bf0-48fcf9a024d5 |  | note | Verifying Documents - IFC drawings - package 13
text | b2c83092-6cc7-569c-af07-f30299d1c5d7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 - Pipes - Placement of Pipe - RCP
label | 79d8d38a-8c0b-570f-b2c0-0dcc098127d6 |  | note | Reference - IFC Drawings Section 701.17, Section 701.20
label | bae2843e-abe2-5339-a10c-aaa431adfbc1 |  | note | Acceptance Criteria - Laying of pipes shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and pipes are not damaged. Laying of pipes or box culverts shall commence from the downstream end.
label | 8bfb2d50-bc59-504b-ac94-4444a189b866 |  | note | • Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered.
label | d5cfe77b-5ea8-5053-8c24-6936ab3955a4 |  | note | • Gaps between spigot and socket are in accordance with the manufacturers specifications
label | 32855b46-f922-5c71-bc08-3dc9943694e9 |  | note | • The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length
label | cb9033b3-5d19-563c-af50-19ac6dad9df9 |  | note | • Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
label | b25b3778-9de8-5ec8-92f2-098c4b9a581c |  | note | • The spacing for multiple row culverts shall be as shown in Table 701.171
label | 4a7b9c53-4688-5330-9298-59628ac15ded |  | note | Method - Visual inspection, Measure
label | 71644f2e-28ba-5aa0-9925-174ea148acf1 |  | note | Frequency - Each Lot
label | 8b2f2ee0-b87a-52cc-baee-41b1509db581 |  | note | Category - IP
label | 10359d91-0351-586c-bd3e-9e290ab0ea9e |  | note | Responsibility - SE
label | 70a78be1-2032-529a-abc6-448e838bc2fb |  | note | Verifying Documents - IFC drawings - package 13
text | e4ddb5ec-2cde-5844-aa05-b29ba0066518 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 - Pipes-Placement of Pipe - Flexible Pipe
label | b0c2ab9d-57ef-5ded-bd87-5d462dd85064 |  | note | Reference - IFC Drawings Section 701.17, Section 701.22
label | e5938a38-d81a-5eb0-b450-73409eaabd4a |  | note | Acceptance Criteria - All buried flexible pipe sections supplied shall be assembled in accordance with the manufacturers specifications.
label | f768b84b-7c54-5236-889f-b1e3b4476fab |  | note | • Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
label | 3a05e9d5-9e77-5e8e-b599-40d900b42864 |  | note | Method - Visual inspection
label | a8adff73-e9f9-59fe-817d-d5fe06bfd66e |  | note | Frequency - Each Lot
label | 0c4031c2-804b-5b2d-ab33-78dd4d74afd3 |  | note | Category - IP
label | 5ee5fd6a-571c-5017-bbc8-e7e41cbc80d2 |  | note | Responsibility - SE
label | 35add517-2564-5d1c-8c5b-598fd9a4982a |  | note | Verifying Documents - IFC drawings - package 13
text | 6bd024ef-bd3f-526e-ac5f-13faab451d91 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 - Pipes - Lifting Holes
label | 9f8fea2c-7e03-5cb7-b418-e0678490dce8 |  | note | Reference - Section 701.18
label | 9441d552-ba94-5e23-8e17-a4e17b05e6c0 |  | note | Acceptance Criteria - Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
label | 18c2728b-2318-5b6f-8a38-ed0c0966679c |  | note | Method - Visual inspection
label | 4a7e31f8-4d8f-5369-be55-ebe430fb3c3b |  | note | Frequency - Each Lot
label | 97a30247-b025-5c03-ba08-c60ab50b72eb |  | note | Category - IP
label | 62dad747-3607-5570-9953-4f90c2f600a7 |  | note | Responsibility - SE
label | 73edc9ce-b190-59b3-96d5-7a2a7f4bfe68 |  | note | Verifying Documents - IFC drawings - package 13
text | 7f98c8f4-ed28-5bd9-85c2-1d7a63cd6758 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 - Pipes - As-built survey pick-up
label | 65fdd3d3-74b9-5c3d-ac92-a9b001b83678 |  | note | Reference - IFC Drawings Section 710.10
label | 4618d72f-c6c3-5b83-a951-b278234fa0ed |  | note | Acceptance Criteria - Each run of underground drainage shall be Survey verified prior to backfilling.
label | f45f9038-e968-52e2-9528-597f2c8c9ece |  | note | – Offset pits to kerb +/- 20mm
label | 69c4d7c0-316d-51b2-85cb-7691b8f5d11a |  | note | – Plan location pits not adjacent to kerb +/- 100mm
label | a0ef3f04-dcc0-59a9-aa86-aab81cccb5d3 |  | note | – Invert level of pipes at pits +/- 50mm
label | 9fa74f1a-7edc-5d7f-a50f-4764f6e59cb7 |  | note | – Departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
label | 15298798-008a-5250-8001-f19077b40ae3 |  | note | Method - Survey
label | cc50fb2d-9898-5685-9469-49c0814208f0 |  | note | Frequency - Each Lot
label | 04be207a-fdc3-5150-8148-4758b722583a |  | note | Category - IP
label | b886bd9e-2a22-5165-8ab8-8116b0a6d842 |  | note | Responsibility - SE
label | 69b97f1a-6cd7-5db9-b3b9-ff441fb04c83 |  | note | Verifying Documents - IFC drawings - package 13
text | 86c1c59a-15f4-5a3d-93db-c181d3d47b0a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.19 - Pipes - Backfill Placement
label | 96c3e9ad-2cf2-5da0-bc7e-b2c75dec5bcc |  | note | Reference - IFC Drawings Section 701.16
label | f5f8ae20-1eab-5d73-9a60-08db62f9a929 |  | note | Acceptance Criteria - Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
label | 1dcca698-0276-51bf-9c7f-904510874eec |  | note | • Filling shall not be placed within 2.0m of the open end of the pipe where a further section is to be placed.
label | 52a13dd8-f804-5253-a677-74458ba968eb |  | note | Method - Visual inspection, Measure
label | a5a123bf-c02c-5a61-8fa4-d5b8329843ac |  | note | Frequency - Each Lot
label | 620523bb-cb8a-5503-921f-ba0c1b50f821 |  | note | Category - IP
label | 21a28aab-c82e-5f7f-9a55-473cf9814576 |  | note | Responsibility - SE
label | d78ec0b4-ea00-5a74-b460-10451afce3a6 |  | note | Verifying Documents - IFC drawings - package 13
text | b9786838-80ea-5cf2-9292-e42323a83b22 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.20 - Pipes - Backfill Testing
label | 8811f545-8abb-5afe-88ce-e518460342bb |  | note | Reference - IFC Drawings Section 701.20, Section 701.29
label | dd8b82cb-edc1-51c2-8e40-5358f688259b |  | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
label | 5d9fc6f0-26a4-5fe1-9f56-27a0df218c6d |  | note | • Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | e956664b-a745-58b3-ac97-e575abf8c622 |  | note | Method - Visual inspection
label | 83d8a346-7eff-5697-b8be-515e585d7c0b |  | note | Frequency - Each Lot
label | 79333351-1ce3-5a6e-bc64-51c117c2376a |  | note | Category - HP*
label | a0ac511d-0776-5f38-aba3-ddf6079c7af2 |  | note | Responsibility - PE
label | a4d07d83-1238-553e-96be-e6d1e7055b4d |  | note | Verifying Documents - Test Report
text | 9e7bc270-69ba-507c-9581-2692faef88cd |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - Flushing & CCTV
label | 17cf6dc4-ffd9-58f3-8caa-43599bf28176 |  | note | Reference - Section 701.28, Section 701.30
label | 7a2e3fc4-2ec3-5d1f-9de3-f1c2d3f09c11 |  | note | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
label | 0196d779-71f3-5cb1-96fc-6489ea45a624 |  | note | • All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
label | 1bb3880f-6316-5a42-86f3-06eed6286cf8 |  | note | Method - Record Review
label | 3a614928-5cf0-5b09-8fd2-5980501e453a |  | note | Frequency - Each lot
label | 2ae0775d-f109-56e2-8b17-4477a4d707e5 |  | note | Category - HP
label | 8107d998-7373-5889-a53d-f261c7e3375c |  | note | Responsibility - Nominated Authority
label | 6b5144ec-2e05-589c-884a-15b88d90b78e |  | note | Verifying Documents - This ITP, CCTV Reports
text | 018228e7-c6cc-5d84-a54c-2a9283fbd8b2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 - As Built Survey
label | 5ae75aaf-1fc7-55ef-8422-197163abcd43 |  | note | Reference - Section 701.10
label | eb0c283b-efc6-50fd-b6fd-e44f5ca7a3f3 |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
label | 0daf43af-98e3-513e-9b61-8c5691b72d87 |  | note | Method - Document Review
label | aef88904-4655-56cd-9810-656ff45a04ea |  | note | Frequency - Each lot
label | 226820df-c873-550b-8a08-e0160c39bd54 |  | note | Category - IP
label | eac9f31f-3456-5e13-b090-746d8ad12d4a |  | note | Responsibility - SE
label | 44f70784-c4e8-5fcb-b1c0-ff5d37e03d7c |  | note | Verifying Documents - This ITP, As Built Survey Report
text | fd5647ac-8aaa-53c5-b3b1-9c7146501133 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Repairs to Damaged Pipes
label | 5c826723-4332-59bb-9928-c29a9ae8d1f8 |  | note | Reference - Section 701.31
label | ac6f870a-0c4e-5988-99d9-f52cb15564c7 |  | note | Acceptance Criteria - Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
label | bc855816-e88d-5e84-b6dd-1c24e3b48324 |  | note | • cracks wider than 0.5 mm
label | 8b6ec901-b873-59bd-a22d-c069b359394f |  | note | • spalling of concrete
label | ee7a57f0-f606-5fb8-b3a3-27a20a7fcc4d |  | note | • exposed reinforcement
label | 9ff6ace4-128e-58d6-bc9e-dad75573ee49 |  | note | • joints that are not fully engaged.
label | 3433a168-f529-522d-9b6d-665d1f2f9877 |  | note | ○ Any pipes with defects greater than the following limits shall be removed and replaced:
label | e9759370-b10d-56d8-8795-8cc307a6b86e |  | note | • longitudinal cracks greater than 2 mm
label | 06dbd597-5fb9-5295-b0aa-779fed4bfd60 |  | note | • circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
label | 175fd7da-d28f-549c-9b99-d0081892e58b |  | note | • circumferential cracks around part of the circumference with width greater than 4 mm
label | 5d0f3aef-6020-5939-a10d-e17701662b55 |  | note | • penetrations with area greater than 400 mm2
label | e10ab73e-53a4-5d2e-bae1-3b6de360d7bc |  | note | • pipe joints that are separated.
label | 59be98db-ed65-556e-8cf6-dbb1a2061371 |  | note | ○ The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
label | d88d4f68-1c3f-56b2-8991-66bd8b000fae |  | note | • hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
label | 88f9cc79-2105-5f81-bbe9-95e6f077588e |  | note | • fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
label | e6e48f47-bb14-5765-bea0-b4226013acbd |  | note | • spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
label | 86306aea-5613-5599-936d-9057b2570dc9 |  | note | ○ The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
label | e5ec0a41-5042-515d-9654-20ca187032e8 |  | note | ○ No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
label | 6c1c8195-eb9a-50c0-a326-17a106e6d995 |  | note | ○ All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
label | 5605e607-91ad-5733-bd00-f14e7e0b3534 |  | note | Method - Document Review for Repair Procedure
label | 137d3468-82d7-5237-b61f-da1ab4ecadaa |  | note | • CCTV Report Review
label | 547350de-2c03-5f8a-84e3-101ac965cad2 |  | note | • Visual Inspection
label | 4b666407-894c-52c9-a93c-952380abc867 |  | note | Frequency - Each lot
label | d2f08c4f-eddc-55ca-a910-080b21951b32 |  | note | Category - HP
label | db8ddab2-4209-5b17-b27a-77a46540bede |  | note | Responsibility - Nominated Authority
label | cafa6c1c-4aae-5ee3-9a3f-42ae8f8509ee |  | note | Verifying Documents - This ITP
label | e2e61f29-fb84-5a37-a460-a408025f1528 |  | note | • Approved Repair Procedure
label | 509ccef0-d07c-5800-9610-be976114bee3 |  | note | • Post Repair CCTV Report
label | d443fb15-0d16-550f-83f0-bd8026e838f1 |  | note | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | c7d5bb2b-f955-580a-a40a-08c3a1b4a4fc |  | note | Reference - MRPA Quality Management Plan
label | c8117e65-da6f-5d0c-b479-bca64f7a29b4 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | b4f7b8ec-2715-5aa0-918c-c35edcb1eb64 |  | note | Method - Document Review
label | 2c361a9d-44dd-5fd9-9279-71b9efba6107 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | af3425ee-b8f6-52bd-9bdd-48c0763597f0 |  | note | Category - HP*
label | 8bd8b407-dd98-50f3-af31-9b68a7f6e7c2 |  | note | Responsibility - PE
label | c028964f-9a00-5716-86a3-cc4329510172 |  | note | Verifying Documents - This ITP
text | 6c0773a2-4df4-5eae-9cdc-b6c2bd9bc598 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 07c78d4d-dac2-5838-aa89-0901f8469d86 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 01cb9db2-ff5c-5467-8414-8baf551cf698 |  | textbox | Name:
text | 2a3c7cfe-f7cb-5b59-98e2-1fc8d6afb192 |  | textbox | Position:
text | 0948c33f-18de-5c78-830f-2a6705494b3a |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-123-STR-CPD-Steel Structures Installation | itp |  |  |  | Yes | ITP-123-STR-CPD-Steel Structures Installation Rev 0 | 1df3141c-6415-4af6-bfc8-a45ca11c7620
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 7f0acb72-414f-5901-bb57-a5ed8cb2da00 |  | note | Document Title: ITP-123-STR-CPD-Steel Structures Installation
label | 9d4635c3-ceb9-55a4-8b54-d1b416363c7a |  | note | ITP Description: Steel Structures Installation
label | fba1f99a-5789-5064-b1fa-a9d0df33377e |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 2e8a937b-996d-53ab-8107-f4b7c65301ca |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 53287cdf-d79d-5fac-a449-32915ca80a79 |  | note | Revision Number: 0
label | 2c674c35-09a0-5825-96b4-04ba0b88974b |  | note | Revision Date: 19/01/2024
label | a43a2585-0c22-57bf-8ab2-55d59783ba7c |  | note | ITP created by: Andrew Carlini
label | f4743796-2c93-5270-a545-c4a726dd4633 |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 9b30d034-08fe-58a6-9791-c2d50e575da1 |  | note | Reference - VR Section 610 Feburary 2020
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 6ca9fe65-3e60-598f-99e2-3884ef249eb8 |  | note | Reference - VR Section 630 July 2022
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | 9e927761-0e67-5d24-aebb-38f106953a94 |  | note | Reference - VR Section 631 June 2017
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | ac2e2dde-71e6-56c4-9c9d-59f647e66ca4 |  | note | Reference - IFC Drawings
checkpoint-status |  |  | checkpoint | 1.5 - Non Dependent
label | 8ff3430d-ca40-5311-8e63-08062cb89f9f |  | note | Reference - AS4100
checkpoint-status |  |  | checkpoint | 1.5 - Non Dependent
label | b873a1d3-158d-51e9-874e-da17eb36eb37 |  | note | Reference - AS5131
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Structural Steel Components
label | 386cb4de-b409-586b-8fc2-d65b855caa89 |  | note | Reference - IFC Drawings MRPA Quality Management Plan
label | be42078c-ae3e-5ded-a239-0eac19c6738c |  | note | Acceptance Criteria - Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
label | 557bb190-7849-5a41-bef3-faea0ef87846 |  | note | Typically this consists of but not limited to:
label | dcb7b46f-8551-5829-ad2d-64b8b293829a |  | note | i. Certificate of Compliance
label | 983617d9-0837-5573-8d3b-33fee62aa6ed |  | note | ii. Completed Fabrication ITP
label | b4703bfa-4aaf-5499-b6cc-d4a136ab807b |  | note | iii. Weld Procedure Specifications
label | 574c188f-3f54-5cfa-8cf9-b14fb6e7138f |  | note | iv. Weld Procedure Qualifications
label | cf333f05-2cf7-5b0d-856e-3e99b8de2544 |  | note | v. Welder Qualifications
label | 2671acfc-f7b6-56d0-80e7-1eec73220d21 |  | note | vi. Material Certificates and traceability
label | ab496b32-2a02-51f8-a855-6d46f33b4ccf |  | note | vii. Quality Assurance check sheets
label | 9f1101c1-c7ca-5fdd-b045-3af04fefede3 |  | note | viii. Welding Consumable batch certificates
label | 3835af73-ad8e-5227-82cd-23c76a26f8ae |  | note | ix. Coating certificate(s)
label | bdbf3c66-4e60-5444-862e-6bb3a537e74a |  | note | x. Non-destructive Testing (NDT) Reports
label | 3d48a566-f9d1-50fc-a4d9-1012ec3519b9 |  | note | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
label | d0a64262-e69b-510a-8249-7f1f1eeca57a |  | note | Collate: Structural Steel Quality Assurance Documentation and upload in a TeamBinder Lot.
text | 22beee02-530c-50ab-b77f-144aa6d06d78 |  | textbox | Enter: Teambinder Material Approval number
label | cb5e8b9b-b6d7-58de-8ffa-c968239485e6 |  | note | Method - Document Review
label | 2a694e98-c09e-500c-855f-004436b0e421 |  | note | Frequency - Each component
label | 99259af1-f3f4-54cd-876c-987f5f7aeaa0 |  | note | Category - HP
label | 032823eb-b536-5e65-97cf-922fc475d343 |  | note | Responsibility - Nominated Authority
label | 1400d87d-568e-5cee-bc25-093848b89d15 |  | note | Verifying Documents - Conqa HP Release
date | bf23a436-34c2-5d88-b56d-b8e2a2f06079 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Fasteners
label | 2c852c56-ec3b-5d59-a44d-49f432559714 |  | note | Reference - Section 630.20 IFC Drawing
label | b36a8b5d-a9b9-51f5-98d4-5941df4be969 |  | note | Acceptance Criteria - Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1111 and AS 1112
text | 557b257d-e04a-5cc5-b40c-9b07ada54eda |  | textbox | Enter: Teambinder Material Approval number
label | ec3f65eb-0f19-5c38-80c9-2080b4fe378f |  | note | Method - Document Review
label | 2d91e464-c381-5f69-950e-88a527064dc6 |  | note | Frequency - Each component
label | 11ade83e-89b2-599a-a9ec-79848c7ba681 |  | note | Category - HP
label | b90f6634-ddec-5b7b-8c25-37c9d3501f6c |  | note | Responsibility - Nominated Authority
label | c934b913-6e96-54dd-8ed5-30e2c3a3feba |  | note | Verifying Documents - Conqa HP Release
date | de465c85-7603-5df2-87d4-b6f64d2ed8b0 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Base Plate Structural Grout or Mortar
label | e1357a8f-5acb-5f58-b1a1-dd7acd8097b2 |  | note | Reference - IFC Drawings Section 610.33
label | ce0ec526-4db8-5c4e-a253-18e87d6b5290 |  | note | Acceptance Criteria - Product to be selected based on the following criteria:
label | 3d7134e1-bb47-5b5b-aa16-6ab657f2e604 |  | note | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout
label | e9aeacf1-cc3f-53c9-a87d-6daed291d45b |  | note | ii. have the required strength at 28 days as noted on the IFC drawings, but 40MPa minimum
label | 1c6179d7-5865-581a-ab96-9c9ecfabc379 |  | note | iii. have a flowable consistency
label | d801ccfc-1f52-5e3c-b9f7-4e46397820af |  | note | iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings
label | 96315f92-629d-5e07-9648-da2327dbfd90 |  | note | v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings
text | 6fc74ce7-5635-5054-8fbb-2687bbbbc6a1 |  | textbox | Enter: Teambinder Material Approval number
label | f68345eb-50f4-5b49-a930-2eb332d7ab66 |  | note | Method - Document Review
label | 27e19123-68b3-5e38-b087-b1e36d3be374 |  | note | Frequency - Once, for each product, prior to placement of product
label | e33a9a5c-85ca-5379-914f-de941460b5c8 |  | note | Category - HP
label | 44cca2e8-d716-53d8-bf98-9bf0cd2b764d |  | note | Responsibility - Nominated Authority
label | e23ca34e-b3d6-56d3-86f0-52a495942ac5 |  | note | Verifying Documents - Conqa HP Release
date | 83daca93-15bd-5718-a125-7004df6ec529 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Procedures
checkpoint-status |  |  | checkpoint | 3.1 - Handling, Transport and Erection of Structural Steel Element
label | c27da26e-872a-58a7-ab1d-81dd02eb989d |  | note | Reference - Section 630.09 AS5131
label | 24e5bb95-6185-5e42-a217-8ffb466d8e89 |  | note | Acceptance Criteria - Methods of handling, transporting and erection of the steelwork shall be such that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
label | 03f1833d-4fd2-5fe5-9f27-15ca75772cce |  | note | An installation methodology and ITP in accordance with AS 5131 shall be submitted prior to installation. As a minimum, the installation methodology shall include the following procedures below, when appropriate:
label | 67115cec-b382-549b-b654-1103c76579eb |  | note | (a) Lifting procedures for each component; transport to and handling on site
label | 949b5325-f95a-5bd6-a7c0-4077a64ba5db |  | note | (b) Bolt tightening procedures for snug tight bolting
label | 8a3673fe-2683-5907-b0e5-866af6ddd4eb |  | note | (c) Procedures for grouting of base plates
label | 6ae20a54-6566-5b20-9130-ba8f7e3f640e |  | note | (d) Procedures for ensuring that components are erected in the correct sequence and position.
label | 6cc0565e-3217-5aea-ad13-6f260fb6a564 |  | note | Attach: Subcontractor Installation ITP and Procedures
text | f6b95129-d757-562e-94b3-d8a91a0280d1 |  | textbox | Enter: Teambinder Approval number
label | 910365b4-ef97-56aa-8458-1ba74fcf35a6 |  | note | Method - Document Review
label | f4c91c51-58b3-55d3-9582-65d80a853552 |  | note | Frequency - 4 weeks prior to installation
label | d56f5f70-d899-5ec8-8f2c-e4d001648d6f |  | note | Category - HP
label | 217ace62-d0ee-50c4-b3d0-1633f1b97db6 |  | note | Responsibility - Nominated Authority
label | 96992859-aa47-53e3-b9f3-943ee6fac94a |  | note | Verifying Documents - Conqa HP Release
date | 3f4f711e-ac9e-5a50-806d-5f41c6970e95 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - IFC Drawings
label | cb4db0e8-555c-59a4-8017-32737f4abc65 |  | note | Reference - MRPA Quality Management Plan
label | e4b29ddd-211c-5430-bfbc-88db27e9c526 |  | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 88253430-3499-524d-a118-8531321d3a85 |  | note | Method - Document Review
label | e08377c4-f477-5313-9406-845c4f3d906e |  | note | Frequency - Prior to starting Works and at regular intervals
label | 208f99ab-6648-5400-a693-968ddff65f25 |  | note | Category - HP*
label | 83e5d418-4d94-5a9e-a54c-042f8fcae7e3 |  | note | Responsibility - All
label | 277a8edc-e918-5ac0-8cfc-541feafc97ea |  | note | Verifying Documents - This ITP Signed Off
date | 59159f2d-c211-52fe-a6a9-597e2bdace39 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Materials Inspection Checklist
label | 4f000aad-e89d-5422-8585-246d4c52abb1 |  | note | Reference - IFC Drawings Section 630
label | 67986ac7-a075-54ef-a7d9-b4dd7a9fcfac |  | note | Acceptance Criteria - General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion.
label | 22db09af-b88e-567e-a190-54f3495222cd |  | note | Method - Measure, Visual
label | cf07d1bc-6574-59de-83ec-05e8cd30bf7d |  | note | Frequency - Each component
label | 4f9a3e76-dcff-5bc6-b955-f462bbaa7f8f |  | note | Category - IP
label | ea1e7494-195b-5dfd-a55c-81a84554456d |  | note | Responsibility - SE/PE/SPE
label | d6f197ed-d214-52ab-b7ac-eb8ade069885 |  | note | Verifying Documents - This ITP Signed Off
date | 21df9057-478d-50c5-ad1b-0ed4f95200a9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Materials Inspection Checklist
label | ce997a86-63f9-563b-ad2d-4051d4432056 |  | note | Reference - IFC Drawings Section 630
label | 34d8281c-383c-5d0d-b6e3-0c08db6c1601 |  | note | Acceptance Criteria - Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
label | 6f086a13-50ea-5633-8190-cd2c8ff52f48 |  | note | ○ Where bolted faces are sloping at 1:20 or greater, tapered washers must be used.
label | 58ee46a3-4bc4-534e-8790-bafb80434b66 |  | note | Method - Measure, Visual
label | 609244b6-b91a-584f-b8c5-2ae8f37a9a9f |  | note | Frequency - Each component
label | 3f2e2ab3-2a67-5cab-9360-0754706b87f0 |  | note | Category - IP
label | 774d186e-bdc3-5e6d-820a-505f5d603bb2 |  | note | Responsibility - SE/PE/SPE
label | c40e572b-c979-596f-a51f-7db11cd1d4e3 |  | note | Verifying Documents - This ITP Signed Off
date | f9e34c59-6c96-5c3f-a85c-69a9851a4fd3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Materials Inspection Checklist
label | dad4ed97-1a68-5541-b630-2aadc712787a |  | note | Reference - IFC Drawings Section 631
label | a89eecff-c662-56ae-a4bf-ecf8228fa33f |  | note | Acceptance Criteria - Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
label | c932b7f4-da44-543d-bea3-fc222135a8f4 |  | note | Method - Measure, Visual
label | 33b15db8-97ae-58ff-bf73-cf6a7dcdd261 |  | note | Frequency - Each component
label | d27590ca-a814-584e-8627-69a556bd4c38 |  | note | Category - IP
label | 54110120-d1b4-5124-ad3b-21b469f36238 |  | note | Responsibility - SE/PE/SPE
label | 33458bdd-1555-52ca-9f4b-fd2d1addbaf3 |  | note | Verifying Documents - This ITP Signed Off
date | d956be1b-13db-5ab3-86e5-8d7fee145714 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 - Materials Inspection Checklist
label | 67ad0293-e9f9-57dd-a3b9-843442b5913b |  | note | Reference - IFC Drawings Section 631
label | f91d2ec6-81fa-5136-b6bd-abd483d32e50 |  | note | Acceptance Criteria - Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects.
label | 5fcb9142-54da-5db8-b362-382142ab7c7b |  | note | Method - Measure, Visual
label | 3682ac07-7925-5acd-8aef-bb3e53824dbf |  | note | Frequency - Each component
label | 19641c94-bb56-5cf7-8576-5293adf727a6 |  | note | Category - IP
label | d3aaea78-1cf4-5fa5-adc4-0e12450b0049 |  | note | Responsibility - SE/PE/SPE
label | b5568d45-a75c-5f1f-8c2a-9d34a7d83b30 |  | note | Verifying Documents - This ITP Signed Off
date | 0c6328f1-64aa-53a1-bf13-480ab81cc97c |  | date | Date Completed:
checkpoint-group |  |  | section | 5. Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Bearing / Mounting Surface Preparation
label | 2afa281f-5003-5e46-9236-c3a4102eb3f3 |  | note | Reference - IFC Drawings Product TDS
label | 0f1f7570-53e6-5b60-a6eb-06e710d8c24f |  | note | Acceptance Criteria - Ensure the bearing surface is clean and free from any loose particles that will prevent solid seating of the parts.
label | 7f81d13e-89be-5de6-904e-0eb86f8af2b6 |  | note | Method - Measure, Visual
label | 2299fb70-97ec-5921-b398-8600f620c232 |  | note | Frequency - Where applicable, each installation location
label | 125620f6-fb18-5521-810b-1d084f8a0730 |  | note | Category - IP
label | 7929ff0a-39ec-5432-bad7-6f00f10a62f4 |  | note | Responsibility - SE/PE/SPE
label | f0272597-7597-520e-ac8b-e26f75a38793 |  | note | Verifying Documents - This ITP Signed Off
date | 59b235a1-c347-5d30-9197-4364ee5c6d5f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Structural Steel Handling
label | 2742ca97-e9b5-57e5-9e59-804fde619cd6 |  | note | Reference - Section 630.09, Section 631.14
label | f0a77c94-f4fe-5ef1-ab86-81ccbf38403f |  | note | Acceptance Criteria - The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
label | 087c6d14-6e99-5619-8802-f635ce804dd0 |  | note | Method - Visual
label | 3bcb82ac-95c7-501c-9100-7a9e1c64ef6b |  | note | Frequency - Each component
label | c8a50446-7935-52db-ab24-4d99f7aeb15b |  | note | Category - IP
label | 5f08bd1e-a592-5c09-b894-c9d89c6a96a4 |  | note | Responsibility - SE/PE/SPE
label | c2315561-660b-5b66-a18b-7335e6b8a1bc |  | note | Verifying Documents - This ITP Signed Off
date | 88877cfc-37dc-50ec-a7e4-a2952f8d3456 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Structural Steel Erection
label | d4e1fa2b-780d-51fe-b173-9967e22f45d4 |  | note | Reference - AS4100, AS5131 Section 630.12
label | f7f34220-8eac-542f-89d0-f16931f544dd |  | note | Acceptance Criteria - Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6.
label | a7e74712-c249-5683-9033-2e61d9fc7e85 |  | note | ○ Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
label | a6f3e8d9-7b47-5da5-a42a-a0bbe18ff84a |  | note | ○ Where a misalignment is found, only rheaming, milling, drilling or machine flame or plasma cut are allowed. Internal surface of the hole to remain smooth and free from burrs.
label | d4d520fb-40f9-562e-a841-781053b9442b |  | note | Holes shall not exceed the greater of:
label | 048dff5b-135c-5584-978f-4a8a04aa95bc |  | note | ○ 1.25 x bolt dia. OR bolt dia. + 8mm
label | 91ada7b7-8128-5cd0-9432-feb36ebfc07e |  | note | Slots shall not exceed the greater of:
label | ddf6dadb-dce7-55a7-a854-947afcdfec9b |  | note | ○ 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
label | 056d1f63-6bfe-552f-8750-b1dd638321a7 |  | note | Method - Measure, Visual
label | e4d88e25-0677-5203-bd56-416b2f3ba8c3 |  | note | Frequency - Each component
label | 3404b260-4b48-54cb-9039-065a3be08474 |  | note | Category - IP
label | 0c82539f-72a1-5b5b-b590-1d8468c4c0a8 |  | note | Responsibility - SE/PE/SPE
label | ea52c1c5-922f-513b-81e1-656fb26acdf4 |  | note | Verifying Documents - This ITP Signed Off
date | 92e5a991-a449-5fbb-857b-2d7b7da831df |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Fastener Tightening - Snug Tight Condition
label | 3e20bc9b-18a9-504d-8373-23a599000bd6 |  | note | Reference - IFC Drawings Section 630.09, Section 630.21
label | 143a57da-c9c1-535e-9e7d-09c9b6cc20ce |  | note | Acceptance Criteria - Place bolts, washers and nuts as detailed on the IFC Drawings.
label | c6e8ebd6-dc32-5140-b0e8-2a02ca3f5195 |  | note | ○ For posts base plates, the arrangement is to be (from the base plate):
label | 9fac47de-cbf9-5045-9f54-c22cf8d3f2b7 |  | note | – Base Plate
label | ab4d5022-f2c3-528f-b7d9-36972bee996e |  | note | – Washer as specified
label | 2a4e6622-029e-5a5b-9fc1-5ce2fc3a18f7 |  | note | – Lock Nut as specified
label | 99dd6a6f-72bc-5a54-adfc-600409df1573 |  | note | – Nut
label | 56fffbaa-68ac-5d53-abcb-eade881ff979 |  | note | – Bolt protrusion (1 clear tread)
label | ddc74648-c9bb-51ab-9c05-19064ea63d44 |  | note | Method - Measure, Visual
label | 08eb3a5a-1c84-5f2b-aff1-2c17103884fc |  | note | Frequency - Where applicable, each bolted connection
label | 6fc3db50-6eb3-5d11-8e42-c6929473cccd |  | note | Category - IP
label | 45002d3f-fe07-5833-a65e-36e1d49ffe4c |  | note | Responsibility - SE/PE/SPE
label | 148a76fd-8c69-5293-921b-de75817db7d6 |  | note | Verifying Documents - This ITP Signed Off
date | 9be6faf6-6ef4-50cb-9543-cef8a8f2aae7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Fastener Tightening - Snug Tight Condition
label | 9c3f7547-8bf1-518c-a886-e2188c29bcff |  | note | Reference - IFC Drawings Section 630
label | 98d67950-552d-5d1e-a18c-a2027c24d19f |  | note | Acceptance Criteria - Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter.
label | 59135a55-2a18-5f2f-a3a3-709d7f2486f9 |  | note | ○ Tapered washers shall be positioned if specified.
label | 4c6b8fad-990d-53fb-8015-7413cd139f23 |  | note | ○ Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
label | 89f537e3-4858-5070-96aa-6f2f48b0283b |  | note | ○ Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | c92ca887-b1bc-5294-ae3d-9066bed4084a |  | note | Method - Measure, Visual
label | 57b6ec54-0912-57c4-ace7-a3a52db72b4b |  | note | Frequency - Where applicable, each bolted connection
label | 40ef4eff-5087-5439-9adb-bc5cdefd8d4e |  | note | Category - IP
label | 1765641d-d4d1-5edd-9ccb-c6d54a3d3ba0 |  | note | Responsibility - SE/PE/SPE
label | 89fa5c54-0e90-584b-8db0-b0f12d068edd |  | note | Verifying Documents - This ITP Signed Off
date | 9996c53c-8747-5328-8d8d-871de10bea66 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Survey Conformance
label | 766001b9-3aa6-590f-93f9-3ed1c93a694b |  | note | Reference - IFC Drawings AS4100, AS5131
label | a9edc816-55e3-5cb3-b78a-961bbd70fd92 |  | note | Acceptance Criteria - Grouting of base plates and/or tensioning of bolts shall not commence until verification that the Works meet level and location requirements within the tolerances below:
label | 714b5aef-f595-566d-872e-c88d74c4ce12 |  | note | ○ Departure from RL = ±10mm
label | 074db8c6-c45c-5db7-bbbd-2e4914dd80d3 |  | note | ○ Departure from plan position = ±6mm
label | e6503ee3-df14-5040-b211-5126f80c71fd |  | note | ○ Departure from alignment = ±6mm
label | ca37f49c-d532-5463-9276-e871c3cb0127 |  | note | ○ Irregularities in alignment = 25mm in 30m
label | 6a00b89e-7a3d-5617-8f59-6566c411602d |  | note | ○ Projection of bolt = +25mm, 5mm
label | acf37470-f182-5dff-b9da-9c96fad32edb |  | note | ○ Location of beam = ±3mm
label | 2a27026a-e015-5ce7-bd71-a57c0fffcf01 |  | note | ○ Location of column = height/500, 10mm max.
label | aecb1ded-085c-5624-866a-265ab21753e2 |  | note | Method - Measure, Visual
label | 7bb0d227-9e3b-5aa5-96eb-63833617e8af |  | note | Frequency - Each element
label | fd624e7e-f6f2-5140-9346-883c93b0ee41 |  | note | Category - HP*
label | e64a0ce5-184d-5114-916e-05e6e5689d23 |  | note | Responsibility - SE/PE/SPE, Surveyor
label | d8e602c3-148e-5833-a6f4-c0c88bcf74db |  | note | Verifying Documents - This ITP Signed Off
date | c8c444ac-faad-5a09-b0f5-472ee1c4a200 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Base Plate Formwork Construction & Placement
label | 8adfa90e-9885-58b1-86ee-8369381493d0 |  | note | Reference - IFC Drawings
label | 3e165aa8-85ce-55d3-aca8-5500866747ac |  | note | Acceptance Criteria - Dimensions as per drawings to achieve the profile. Formwork rigid, sufficiently braced to support the pressure of the grout/mortar product and sealed to prevent leaks.
label | 9ab83a76-53a7-529e-a3ab-7d37faf9e15a |  | note | Method - Measure, Visual
label | 04eea8d6-46a2-591b-bbd6-aab210f57960 |  | note | Frequency - Each post location
label | d4649068-d7c9-5701-bdc7-452af1ef3159 |  | note | Category - IP
label | 29669910-a25b-5b26-b08c-702d25b0f9b5 |  | note | Responsibility - SE/PE/SPE
label | e616adfe-0a86-50c7-b1ab-9a53b8e27d47 |  | note | Verifying Documents - This ITP Signed Off
date | 10fbc612-9309-54df-b594-fafb5ac6b4a2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Pre-soaking Concrete Surface
label | 46d026c1-e458-5fb1-81f9-254c5fc08f60 |  | note | Reference - Product TDS
label | 3115dee7-531e-5159-817e-f6dc35de8f8b |  | note | Acceptance Criteria - Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS.
label | 66d843db-66f0-5bf6-aa4d-a68dc6794010 |  | note | ○ Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower.
label | 479cfa53-8824-5bad-b18c-657ebf44980d |  | note | Method - Visual
label | 45ca3240-c12a-55f2-9f0e-bfc8a48024e7 |  | note | Frequency - Each post location
label | 5f495512-a26e-55e9-9041-51041de681ed |  | note | Category - IP
label | 02300d91-2786-5cae-b851-47b283383aff |  | note | Responsibility - SE/PE/SPE
label | c4c4c544-2b26-586f-adb2-f398adfe6ef9 |  | note | Verifying Documents - This ITP Signed Off
date | c81f35c4-d3c2-5181-a331-cec62d780d69 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 - Weather Conditions
label | 3a679cf1-ec33-5bc3-a447-b832356c1910 |  | note | Reference - Section 610.17 VR Table 610.171
label | f83f4036-5fa9-5e7b-81fb-d25f22d6207b |  | note | Acceptance Criteria - Do not commence grouting operations if inclement weather is forecast and the Works cannot be protected.
label | f013f583-99e0-5db0-9fed-c8f8d3aa71c4 |  | note | ○ The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | d61451e6-b7bb-5383-bbec-2e22b2752d24 |  | note | Record: Required information on the Grout Pour Record.
label | 87dc4192-75f4-522c-b257-56047f5af7ff |  | note | Method - Measure, Visual
label | c7341fd3-fae3-5311-9c74-dabf4a095e61 |  | note | Frequency - Each lot
label | 43155bc2-1938-55c4-8ae0-34b854239920 |  | note | Category - IP
label | 1206eb64-a8a9-50dc-b5de-16fac5d6e6ba |  | note | Responsibility - Supervisor, SE/PE/SPE
label | ca675b39-7a65-52f6-b9b0-d17278348cc0 |  | note | Verifying Documents - This ITP Signed Off
date | a17f8054-cda9-5088-a930-0513704b0640 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 - Mixing Product
label | fd15659b-935a-59ef-96ce-f1e143cdabf9 |  | note | Reference - Product TDS Section 610.28
label | b59dc752-39a3-5abb-b97c-f8b12b03f48c |  | note | Acceptance Criteria - Size of mixer should match the application.
label | bc11ba33-65fa-5f3c-b5df-8f2043e1d362 |  | note | ○ Only whole bags to be mixed with potable water.
label | cb3cbe6b-63b0-5c4c-855a-17c7c0e75cbc |  | note | ○ Volume of water matches the required amount for flowable consistency and accurately measured.
label | c7a70830-dea4-5492-9d9b-d21ca2d350f8 |  | note | ○ Product poured into the mixer slowly.
label | 495a09f0-e409-5189-8672-411853e7206b |  | note | ○ Mixing time as per TDS so that a smooth, even consistency is obtained.
text | 48da0737-b44a-5de0-9605-a90f6aed88ff |  | textbox | Enter: Required information on the Grout Pour Record.
label | c7cb3007-22dc-5a5a-bbce-395582e75767 |  | note | Method - Measure, Visual
label | df953686-ac34-5802-bbe4-a7c83933b69c |  | note | Frequency - Each lot
label | a7d8527a-0793-530c-ae4e-512386f2fead |  | note | Category - IP
label | 5bfc1aa2-ed2b-5e69-b568-3776c828381b |  | note | Responsibility - Supervisor, SE/PE/SPE
label | 6b7d4197-b3b2-5440-8ce1-74c3f32d96e4 |  | note | Verifying Documents - This ITP Signed Off
date | ebd43256-32a0-57fa-9e50-a6529301598e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 - Product Testing - Compressive Strength Cubes
label | 19555d57-eae5-5fea-b307-77ebe8a08b77 |  | note | Reference - Section 610.28, Section 610.33
label | 289b7826-1136-529b-843d-604a41000713 |  | note | Acceptance Criteria - Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
label | a7bceed6-f1c9-5060-b0c9-abf7c83b08a9 |  | note | Testing is to be in accordance with the following frequencies:
label | 85de1ecb-635e-5fcb-a7db-13408ae061be |  | note | ○ First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | 369ad864-a848-51ff-924b-77cca4e11ca1 |  | note | ○ Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
text | 54de32be-7580-5025-9169-1a5d8b100799 |  | textbox | Enter: Required information on the Grout Pour Record.
label | 76bd9101-935e-5bb3-9643-d0e739c6f81f |  | note | Method - Test
label | 25779521-ffa1-5254-83b2-e79b91278e57 |  | note | Frequency - Each lot
label | da16f1cc-59f6-58aa-9ff0-251c315004da |  | note | Category - IP
label | 1f0422ea-4036-59e2-b2cf-3e39b45d0ace |  | note | Responsibility - Supervisor, SE/PE/SPE
label | 0ae6f809-c8b6-54c5-9bf2-a809ad6e72e9 |  | note | Verifying Documents - This ITP Signed Off
date | 4a86010f-f651-50e8-a262-7a14d5a6eeec |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 - Placement & Compaction
label | b98a523f-35fe-5424-bc20-ea4d03c7ef69 |  | note | Reference - Product TDS
label | 76df2bd5-b437-54f4-9742-606a27c24a46 |  | note | Acceptance Criteria - All batches are traceable.
label | 2bc44f61-e071-53f6-b748-72e2388e3965 |  | note | ○ Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
label | 3ec5fcd8-dcfe-518e-9d97-b52c4eeca2dc |  | note | ○ Product should flow to all areas and self consolidate.
label | 7a6533d4-29fe-53c5-b793-6feae40340e3 |  | note | ○ Product that stiffens or is showing signs of stiffening shall not be used.
text | f664e322-fc18-57b4-99bb-0e7cebcfbc99 |  | textbox | Enter: Required information on the Grout Pour Record
label | fb083370-7b80-5bb9-9818-5b95b6358877 |  | note | Method - Visual
label | c38e0eeb-186b-5ffd-a911-ebdeb49f90b9 |  | note | Frequency - Each post location
label | 71a9a1d7-f56e-50a7-ae37-5503623bbf38 |  | note | Category - IP
label | 83c946ff-424e-51ad-b2a4-b1b19e8acc54 |  | note | Responsibility - Supervisor, SE/PE/SPE
label | ea505bcc-0b10-5f4c-882a-59076f12139d |  | note | Verifying Documents - This ITP Signed Off
date | 071c8d3c-893d-55e1-a9fc-795905749dfc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 - Surface Finishes & Protection of Works
label | d27b358a-70f7-554b-8cd0-c38ee4b743b8 |  | note | Reference - IFC Drawings Section 610.17
label | 4cf83fc4-1848-5645-9225-b194d5784060 |  | note | Acceptance Criteria - If shaping of the unformed surface is required, shape prior to the product fully hardening.
label | 64573f24-fe65-5b62-b98d-5b84b35aa58b |  | note | All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 44b8fab7-d961-5c12-93a7-54bbab750dde |  | note | Method - Visual
label | aa5f4379-fc28-53b0-96df-7a78489079ce |  | note | Frequency - Where applicable, each post location
label | 49527e5a-9deb-50d8-ab90-e4bbc983529a |  | note | Category - IP
label | b8381f31-e271-5723-8511-6fb8818cd54c |  | note | Responsibility - Supervisor, SE/PE/SPE
label | 738c78b9-e7c4-5e3c-9d66-6fd2deff8b8f |  | note | Verifying Documents - This ITP Signed Off
date | ea3505ae-2661-5db9-840d-fbb02720214d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 - Curing
label | 807b7090-b1cb-5755-b7a7-29c58998df9e |  | note | Reference - Curing Methodology 610.23 Table 610.231
label | 0e6478f5-55b2-5a69-9a8b-d90a0e3448e6 |  | note | Acceptance Criteria - Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | e3691bb9-ce82-51aa-af54-4bfab672e139 |  | note | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | dc19c9b2-1bcd-5577-8dfc-ab7ad2ca4d51 |  | note | Method - Visual
label | 0a5d074e-bd92-5ff0-aa95-67c7ad46e49e |  | note | Frequency - Where applicable, each post location
label | c5dfa289-97de-55b6-b084-4a349a2e0c50 |  | note | Category - IP
label | a3c4d4af-ed22-5f03-a950-df64d36ae8d9 |  | note | Responsibility - Supervisor, SE/PE/SPE
label | ebdd5ba8-5165-5cf5-b33a-2e96363888da |  | note | Verifying Documents - This ITP Signed Off
date | 8a6bbabf-eaca-5538-b195-8335fd537481 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 - Architectural Steel Erection
label | ce7af396-8002-5d3a-a9ab-eb689545033b |  | note | Reference - AS4100 Clause 15.2.3, AS5131 Clause 11.5.7, 630.12
label | fe0899a8-aa27-5b32-89c3-4f2fbda7cce0 |  | note | Acceptance Criteria - Place steel component into position, ensuring that it is plumb, level and square
label | 51548781-8130-501b-a89f-034cb9a7324b |  | note | ○ Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diamter of the bolts can pass through freely
label | 1efe4eda-b24e-5999-9afd-9ce95699bf37 |  | note | Method - Measure, Visual
label | 166f965a-a35f-5148-a71e-14152fb3287a |  | note | Frequency - Each component
label | 2a06ea5e-c9ab-5758-996f-9fa045e375a5 |  | note | Category - IP
label | fa185166-5464-59a5-abe4-d19a4f09b2aa |  | note | Responsibility - SE/PE/SPE
label | 6e5b3863-2084-5cfc-ad29-29fb012d8129 |  | note | Verifying Documents - This ITP Signed Off
date | 6bdf96a2-4f71-557a-a3c9-415840caf374 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 - Architectural Steel Erection-Fasteners
label | fee1aa2d-7d0a-5e9d-bb78-d7e50b8bafde |  | note | Reference - IFC Drawings Section VR 630
label | d893d6dc-7e20-5688-a920-d20190c9e0ce |  | note | Acceptance Criteria - Place bolts, washers and nuts as detailed on the IFC Drawings.
label | ed029fa2-de55-505d-9225-a758de558e08 |  | note | ○ For architectural/Security screens, the arrangement is to be (from themounting post):
label | 78ac8e13-1405-5b9c-84c2-8298697fefc1 |  | note | – Post
label | c56ed942-9b81-5af6-8e26-253814a49856 |  | note | – Washer (s) as specified
label | b2334368-b6d2-5f00-a2c4-2124258e8866 |  | note | – insulating washer
label | 49d8f78d-884b-562f-be89-47c24fb5f987 |  | note | – insulating bush
label | 3b3eec00-3056-544a-abf2-b15061f358e8 |  | note | – Insulating washer
label | 8042356e-13e6-5a16-b6ff-7970bb600499 |  | note | – washer as specified
label | ae4d2906-6ece-5276-88fe-e08ee412348b |  | note | – Lock nut
label | c62eef13-a35b-54a1-a0ab-17a3b837086f |  | note | – Nut
label | 1f9b0e8b-738c-5957-87a0-f61be1632d22 |  | note | – Bolt protrusion (1 clear tread)
label | e670be5f-ce22-55b1-9e57-c6c32a7de7b1 |  | note | Method - Measure, Visual
label | ccb207e4-5779-5cca-b0eb-45db6a82661d |  | note | Frequency - Where applicable, each bolted connection
label | 3ecad6c5-2a9b-55d4-89c0-7281810d356e |  | note | Category - IP
label | 09837ec6-e643-5d43-ae5b-c72eea741eb3 |  | note | Responsibility - SE/PE/SPE
label | 27ae87ef-89ed-57bc-9b3d-a0186663308c |  | note | Verifying Documents - This ITP Signed Off
date | 6e38f2f8-c42a-5657-9f79-b5e3ad3e4d4a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 - Installation of Electrical Isolation Materials
label | 6f3de21f-6fd2-5ba2-82af-bbc6eb906d16 |  | note | Reference - IFC Drawings
label | b02c1ae9-3dfd-5863-8055-546a7b59468d |  | note | Acceptance Criteria - Installation of Electrical Isolation Material in locations specified on the IFC drawings (where applicable).
label | 13586dd7-f3c5-552c-ace9-d4ab3e6a4f8c |  | note | Method - Visual
label | ccbf4985-988e-5d9e-a175-7e8033274ae8 |  | note | Frequency - Each component
label | e1d0c510-7c5d-5f37-8190-aed1766e3ae3 |  | note | Category - IP
label | 7178e14b-b663-58a0-8675-c1d9e1c39b00 |  | note | Responsibility - SE/PE/SPE
label | e6ffff8c-5a7d-545c-b0a8-94dd4e157f99 |  | note | Verifying Documents - This ITP Signed Off
date | 5c94300d-567b-5239-b5c4-0141b405bb74 |  | date | Date Completed:
checkpoint-group |  |  | section | 6. Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - Inspection of Coating
label | 1b185e08-d2f4-594f-bfdc-82fb6c0f88a7 |  | note | Reference - IFC Drawings Section 630
label | ff53b66f-96fb-52fc-8964-8dd227907c7c |  | note | Acceptance Criteria - After installation Works are complete, inspect the steel element for damage to the coatings.
label | e6aa1427-8606-532d-b7d8-8da8a8e6e12d |  | note | ○ Where damage exists, it shall be repaired using an approved repair procedure.
label | fe8bfb44-9db8-5731-91a0-9dbea4dcb4bf |  | note | Method - Visual
label | 0dbffd90-1668-5df8-a55e-c926d52892a1 |  | note | Frequency - Each component
label | cb6b787f-8f82-5f3d-aa18-94b19921891b |  | note | Category - IP
label | 8fd7373a-9c36-5581-bbed-c49135b388be |  | note | Responsibility - SE/PE/SPE
label | fd7b4a71-8524-5b0e-9d93-9c67143e3d1b |  | note | Verifying Documents - This ITP Signed Off
date | 65661022-dcf4-5d39-9574-3f161751acdd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Compressive Strength Test Results
label | a2a3a8f3-bedd-527d-9a76-a6538d0314fe |  | note | Reference - IFC Drawings Product TDS Section 610
label | 219023e7-6580-5e8f-a465-178d2051b09e |  | note | Acceptance Criteria - 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
label | a053c285-65db-5748-9cfb-0eb5ee85e7b5 |  | note | ○ 28 day compressive strength per sample comply with the design strength.
label | ec7c453d-2193-54f6-8c20-1d65051a1bc0 |  | note | Attach: Compressive Strength Test Results
label | 3df64b69-e141-561e-a8c8-b9d1f225e777 |  | note | Method - Document Review
label | 7e15ff47-c12e-53eb-bc60-797938f753cc |  | note | Frequency - Each Sample
label | e959681c-199e-56e9-927d-50bb14d19baf |  | note | Category - IP
label | 62b79638-69b6-5e34-94e3-ddffd0d75b88 |  | note | Responsibility - SE/PE/SPE
label | 55e6b076-dcc3-589e-83b4-3615d588ea8f |  | note | Verifying Documents - This ITP Signed Off
date | 1a59ccdf-5e03-50c2-90eb-f174a05a3cc9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - As-built Survey
label | 81f21c27-16dd-5806-b2a8-a7fc36811e8d |  | note | Reference - IFC Drawings AS5131
label | 8719bc39-eba2-5c2b-9729-4e56a45c23d3 |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | c81873d3-44b0-55cd-8f70-8b7c59a05e08 |  | note | ○ Departure from RL = ±10mm
label | ba2c6767-eab8-5f23-846b-3f799facc5db |  | note | ○ Departure from plan position = ±6mm
label | 788bbf07-b14a-535b-ba75-6969901474af |  | note | ○ Departure from alignment = ±6mm
label | 2b6307df-ca5c-50fb-9a90-e07b238ee98e |  | note | ○ Irregularities in alignment = 25mm in 30m
label | d16154a5-528b-5eef-b60d-c1c98557b8fe |  | note | ○ Projection of bolt = +25mm, 5mm
label | cb74fa95-234a-5e9f-8650-1bf11a19722e |  | note | ○ Location of beam = ±3mm
label | 5f5eea9a-7384-500b-923e-45b36148694f |  | note | ○ Location of column = height/500, 10mm max.
label | 862e60bb-fd2c-5f1c-95b7-16b6f21795c5 |  | note | Attach: Survey As-builts / Survey Report
label | 07635867-456f-5669-a41f-add1a67e90f2 |  | note | Method - Document Review
label | f108318e-f613-5e27-a634-7749f4fe7b3c |  | note | Frequency - Each element
label | 761aaf26-f703-58c6-8688-eef1c8e2e10d |  | note | Category - IP
label | 7b702585-edba-5e5d-b0b1-dbb2c5f51b6b |  | note | Responsibility - Surveyor, SE/PE/SPE
label | a36b402d-c979-5a8b-89e9-d71f8cf49380 |  | note | Verifying Documents - This ITP Signed Off
date | f86c8767-0f96-5913-885e-17c8592414d1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | 8ca66df8-6ff9-535a-af5c-a8631b5dd8f9 |  | note | Reference - MRPA Quality Management Plan
label | 0605dc92-e8b6-522c-b638-22f46e5839ae |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | f96f9e74-ff1d-5ab3-8d05-4d8d70e3aa2e |  | note | Method - Document Review
label | ca18dc1b-c8f6-5ad7-91a8-4e2d750995d2 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 0e66a7f0-b212-5a74-aecb-3b85ee059703 |  | note | Category - HP*
label | 89d7a28a-2ddf-5b6e-873e-72b05ea46764 |  | note | Responsibility - SE/PE/SPE
label | 69ef7be9-0192-5f6f-aac5-bc9f6fe68d02 |  | note | Verifying Documents - This ITP Signed Off
date | b1f39810-c423-549c-8d5c-e8b5671a8ccf |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 4b19b077-dee9-5f92-af13-cdadf2597b31 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | a0cd4f04-4647-5cd8-8e2e-8510c782ba4a |  | textbox | Name:
text | 1e854934-4981-5c32-99d4-6ea431a15733 |  | textbox | Position:
date | 1ffb7afd-41b9-5421-887a-ae8a324a4f35 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-126-CIV-RSS Wire Facing Wall Main | itp |  |  |  | Yes | ITP-126-CIV-RSS Wire Facing Wall Main Rev 0 | 20fcc269-03f4-4aa1-9f9e-ca0852db184d
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | e67349da-cb94-5052-866a-49430878e1aa |  | note | Document Title: ITP-126-CIV-CPD-Wire Facing Wall Main
label | 6bec8604-3593-57fa-8375-0484bf9864e6 |  | note | ITP Description: CPD-Wire Facing Wall Main
label | ac690495-eb99-57dc-af99-c98e370b53f8 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | e72ec9fd-432b-5e81-87ff-96da785eac20 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | f4d648f6-cc0e-5032-9153-4abbf67c3503 |  | note | Revision Number: 0
label | ed4f39e5-f7bf-5975-8af3-558b4612457c |  | note | Revision Date: 01/12/2023
label | fe17837a-4afb-5b33-8d49-ac518bbddef2 |  | note | ITP created by: Matthew Dib
label | fab9e5be-ac7d-5b93-8cea-d992c4839ea5 |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | c6ac2dd0-f740-54c0-bf2b-f1d98628adcd |  | note | Reference - VicRoads Section 682 November 2018
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 46ca9f13-7c04-5343-a856-d7b72b7208ca |  | note | Reference - VicRoads Section 204 December 2015
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | a72d5392-25ca-5f0d-8c70-f80f8c2f0c5f |  | note | Reference - IFC drawings
checkpoint-group |  |  | section | 2. Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Select fill
label | df49bfcc-9d51-5410-8287-61d770f3f2c3 |  | note | Reference - IFC Drawings VR 682
label | ecd53213-f24a-5c3e-8772-6c6daa01f191 |  | note | Acceptance Criteria - Select fill shall comply with the requirements of the RSS designer:
label | 2231807c-1461-525d-a018-86fbc5133a5e |  | note | ○ UNIT WEIGHT (Max): ≤ 16 kN/m³
label | b36ceae5-db32-504c-b2e4-6d528c5f07d0 |  | note | ○ COHESION (Min): ≥ 0 kPa
label | 3fe0dc2f-28b6-51fc-9e09-ed99c8a2c9b2 |  | note | ○ INTERNAL FRICTION ANGLE (Min): ≥ 36°
label | 760bcf52-5045-571e-9052-971c426a8b44 |  | note | Gradation:
label | afa19003-602d-55e7-8862-0040b223f9b3 |  | note | ○ 150mm : 100% PASSING
label | 445f4a5a-d08c-5e2e-ab2f-e2e0ae5f693d |  | note | ○ 37.5mm : 60 TO 100% PASSING
label | c72fe095-9b0f-5e80-be63-4200496831c0 |  | note | ○ 9.5mm : 25 TO 100% PASSING
label | ba3190eb-9ddf-5b15-ba53-8c15e8cade4e |  | note | ○ 2.36mm : 15 TO 100% PASSING
label | 51f4e327-c4fa-51de-8bad-6c44a11391aa |  | note | ○ 0.6mm : 10 TO 100% PASSING
label | ad8e6874-f4f2-5ca3-8c20-d16c4236029f |  | note | ○ 0.075mm : 0 TO 15% PASSING
label | 1919f5d4-ec7b-5bc4-8fd7-fb46858f8438 |  | note | Electrochemical Properties:
label | 8009bc81-ce18-5dbf-9b3a-f7a3de320a08 |  | note | ○ pH: 5 - 10
label | 5c3c0feb-f3fd-5db8-a0c3-81b2ca1828a6 |  | note | ○ RESISTIVITY >1000 Ω-cm
label | d1ba29a5-b85a-5c63-a59e-6360ba1601a6 |  | note | ○ CHLORIDES <200 mg/kg
label | 4c0fb4e1-1f3d-58f1-b6dc-26a6e9d712ee |  | note | ○ SULPHATES <200 mg/kg
label | 8b95c4c1-90d5-5604-9663-d3ee3429d08e |  | note | ○ ORGANIC CONTENT 0%
label | c42fcebc-f614-5bab-a23a-7495c38af174 |  | note | Structural Properties:
label | 074659eb-ae54-541e-8541-fa5b1a6c7206 |  | note | ○ LIQUID LIMIT ≤ 30%
label | 8bf3db07-2ad4-50d1-99b5-afd0fe73b0fa |  | note | ○ PLASTICITY INDEX ≤ 12
label | 809709f3-ef34-5ccf-b1f3-1d73c2d4c3ef |  | note | The select backfill must meet the minimum requirements of Vicroads Type A filling
label | 0a058390-aa9e-59d9-bf35-2f5984d0fe69 |  | note | Reference: Material approval in Teambinder
label | 87388311-7a09-57e0-a0c7-84fb1264f08d |  | note | Method - Document Review
label | 8045e7a4-3f7b-52f3-b91d-45a5ddd5a5ca |  | note | Frequency - Each material specification
label | ecc0b059-a55b-50c6-9a3f-78c838462f1e |  | note | Category - HP
label | d546782a-b404-5d29-8190-49e0ab605490 |  | note | Responsibility - Nominated Authority
label | 3918a403-55e6-5e43-8aa3-0d4441301731 |  | note | Verifying Documents - Material approval
date | 128964b9-782f-5e8f-a61d-3900859635d3 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - General fill
label | 97841cca-3fe2-5e68-986b-8f55d9301598 |  | note | Reference - IFC Drawings VR 204
label | 20eff7fb-26a1-597e-b73e-471bcdd31ad3 |  | note | Acceptance Criteria - Backfill behind the reinforced block shall be Vicroads Type B or better in accordance with Vicroads standard specification 204:
label | e405eb8f-2a0d-59df-9ec2-8223e36b8182 |  | note | Select General fill shall comply with the requirements of the RSS designer:
label | 8d08ffa2-3149-5caf-b514-d9d6832d3410 |  | note | ○ UNIT WEIGHT: ≤ 19 kN/m³
label | 0b2e8bc1-5c95-5a60-870b-4f55c79240a8 |  | note | ○ COHESION (MIN): ≤ 2 kPa
label | a8f873ac-6f13-5a16-b4fd-4571885692fc |  | note | ○ INTERNAL FRICTION ANGLE (Min): ≥ 30°
label | 99cfbee1-d8a3-5903-ba53-377fecc4f7fd |  | note | Reference: Material approval in Teambinder
label | 6b044baf-0910-522e-b70a-7283c7395369 |  | note | Method - Document Review
label | aa379bda-40d3-5813-83f8-02802b02f52d |  | note | Frequency - Each material specification
label | a1bd387b-9c67-5ace-8fae-60913f5a3ec1 |  | note | Category - HP
label | 5cd679c9-de67-5e7e-8fd9-84d1928dc45d |  | note | Responsibility - Nominated Authority
label | 5fa06900-88e8-5664-9c3b-d7e6a8a57acf |  | note | Verifying Documents - Material approval
date | 29a485f7-27a9-5698-a8c2-706828986b28 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Cobble stone backfill
label | 045416ff-a80a-5e10-80ab-598b681c5fd7 |  | note | Reference - IFC Drawings VR 801, VR 715
label | c2154e04-ad95-5b58-bb4b-f65d6917caa6 |  | note | Acceptance Criteria - Cobble stone backfill shall have a minimum dimension of 100mm, and maximum dimension of 150mm.
label | dc0893fb-005f-51c3-aa8d-0915a0d1317f |  | note | ○ Cobble shall comply with the material requirements of 'sound' rock as specified in VR section 801:
label | d44f88dc-e783-52ee-9d08-d6e2fdf5d09e |  | note | ○ Cobble shall comply with the Los Angeles Value (LAV) for requirements for Gabion Fill.
label | dc245c2d-de88-516b-9aec-1c4b640af2f2 |  | note | Reference: Material approval in Teambinder
label | 30b349d2-7079-5c5b-9666-203f22fec602 |  | note | Method - Document Review
label | 0c0dbf59-13b0-5594-bf5a-5908e0774ee3 |  | note | Frequency - Each material specification
label | 8f60e789-cbb4-5cbf-8558-1656dc99e4f8 |  | note | Category - HP
label | f86a11ac-d5c6-58b0-aad0-c54e4d37acab |  | note | Responsibility - Nominated Authority
label | 4ef9cd7d-202b-539f-a930-886c58e3d719 |  | note | Verifying Documents - Material approval
date | af986bcc-7420-5737-a002-25fa52b57ab5 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries-Documents
checkpoint-status |  |  | checkpoint | 3.1 - Wire Facing Units
label | f7b5abbf-6a93-577a-8b8d-c22860c607a0 |  | note | Reference - IFC drawings
label | 371e0df4-1895-573c-94c8-a21da9a2fc0b |  | note | Acceptance Criteria - Supplier is required to provide the following Quality Assurance documentation, typically this consists of:
label | 2ed5272f-95c9-5755-9902-85bee09dd3f7 |  | note | i. Inspection & Test Plans
label | b48550d4-51de-5e74-a0d2-32ddba6221ff |  | note | ii. Manufacturer Accreditations
label | 5063f330-309c-524e-af70-d3de9dd02bb1 |  | note | iii. Material Certificates & Test Reports
label | 1499e239-b7a9-59b2-a04b-5afd078a0e5b |  | note | iv. Welding Records
label | e52a839b-19da-5e0d-bdad-7341bfef2083 |  | note | Method - Document Review
label | e85ed771-85f2-5833-86c5-94a08f984abc |  | note | Category - HP
label | 30cb87e8-6e95-5b50-add8-75cdf0481171 |  | note | Responsibility - PE
label | f64c111d-1ddb-5d21-951f-0e6ceee844a0 |  | note | Verifying Documents - MDR
date | 36cd100b-93ee-5ee4-acf3-85c919e9a6c8 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Foundation
label | 63edfce5-dffd-52f5-9c7e-a9e0f1dab053 |  | note | Reference - IFC Drawings MRP-080-C-SME-DRG-34-CPV-CSF-3007, MRP-080-C-SME-DRG-34-CPV-CSF-3012, MRP-080-C-SME-DRG-34-CPV-CSF-3013
label | c5a2194a-acfa-5bc4-aea0-19015da379ae |  | note | Acceptance Criteria - Foundation material under RSS shall adhere with minimum design bearing capacity.
label | 84b5af9f-63b9-517c-9fc0-578d6495a29a |  | note | ○ RW1: 200kPa
label | 43e547a8-a46f-5014-b6a8-b7a7098c57ce |  | note | ○ RW6: 250kPa
label | 90ecc310-9eaf-5a09-8c09-bd3cc0b45780 |  | note | Method - Test, Document Review, Visual
label | 16f8938f-0257-56e7-8417-2cb701b35dfc |  | note | Frequency - Each retaining Wall
label | 95eb317d-558e-5aa1-9dec-a284e9ae5f3d |  | note | Category - HP*
label | 0e488050-736e-5db6-b2b9-2d8dbb5bca28 |  | note | Responsibility - PE/Geotechnical Engineer, Foundation geotechnical assessment
label | 954c62cc-caa7-5690-b2f7-9a2541b7c426 |  | note | Verifying Documents - This ITP Signed off, Test results
date | 6a44e54f-fd16-5fb1-8fa6-64e7a61ded82 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Foundation
label | 8dc4c542-c8c3-5ec9-b3e5-9d1c63ba4ffb |  | note | Reference - VR 204.12, VR 204.11
label | 0c8cedb6-5e09-54c7-a1f8-0d6f04faae16 |  | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be test rolled in accordance with VR 173
label | b431af38-20ce-5d77-829c-8f3dc1e62a70 |  | note | ○ No Fill shall be placed against or within 3 meters of a structure until the foundation for the fill has been reviewed by the superintendant
label | a5ba8e03-e87f-5d78-a25a-99874d7bb884 |  | note | Method - Visual
label | 19347de5-bd1e-537c-83ce-f9177c498492 |  | note | Frequency - Each retaining Wall
label | 95f716dc-054b-5850-9656-1d7db5aa3d4f |  | note | Category - HP
label | 76bb130c-cc7b-50df-a129-849b7c20ae36 |  | note | Responsibility - PE/Nominated Authority
label | a2a226be-873e-5920-8c4c-00bae8dc0709 |  | note | Verifying Documents - This ITP Signed off
date | 796ff18e-8184-5338-b72b-f705c0e5e85f |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Wire Facing Unit Installation
label | 7090db04-75a8-5d9d-9c27-9d216defb572 |  | note | Reference - IFC Drawings MRP-DPK-080-00-CSW-0033-0-1201, MRP-DPK-080-00-CSW-0033-0-1206 VR 682.20
label | 91d375ad-447b-5f12-a411-978fe471d1d2 |  | note | Acceptance Criteria - The level and alignment of lift of wire units shall be checked progressively after placement of each lift and prior to placement of the lift to ensure compliance with the dimensional and positional tolerances stated in the design.
label | 1d92f260-552d-583c-a615-19a183a465b3 |  | note | ○ The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions.
label | 14c47cd7-57fa-5020-9451-a515b504e47b |  | note | ○ Refer to checklist for row of wire units
label | 96dbcf35-0567-5b30-a58d-41e47f7c2308 |  | note | Attach: Lot map
label | c7a7720c-a766-50ee-b58a-8d8a8c94c442 |  | note | Method - Visual Measure
label | 224164c8-3537-587b-a1ef-89bdcd7e8de3 |  | note | Frequency - Each row of wire units
label | d73f455e-d2e4-568b-85e2-f5542ac935c9 |  | note | Category - HP*
label | ffe86b16-bb78-5aa8-ab1f-4ada79c679ed |  | note | Responsibility - SE/PE
label | b6fcd04e-7668-5c31-a2be-c0de18412d5f |  | note | Verifying Documents - Inspection record checklist: CHK-00X-STR-CPD-Wire Walls- Wire Face Wall Installation
date | 88459560-122d-5ba3-b9b2-ea806bde8946 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Fill
label | d84c1668-098b-526a-a389-d6c12d566e9e |  | note | Reference - VR682.16
label | c2d3ca8e-c798-5cd7-ae86-78818bbfc9dd |  | note | Acceptance Criteria - The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance.
label | 71cc1bfe-8872-5f52-88c5-8519a5db708d |  | note | ○ No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed.
label | c254f7ef-d9f5-5e18-aff1-2d62a5df42ed |  | note | ○ Refer to checklist for each fill layer
label | d36d458b-2c58-5e2a-9359-848b7713b118 |  | note | Attach: Lot map
label | f8b09cac-9200-5613-ad18-dab6c454f408 |  | note | Method - Visual, Test, Measure
label | 0cb0dde7-bd67-5c50-a735-534a277006cd |  | note | Frequency - Each layer of fill
label | cdfd88fd-4db6-5144-925b-b41d073cdf98 |  | note | Category - HP*
label | 71bfc595-9d8d-5072-9ee1-963bcf6a5d4d |  | note | Responsibility - SE/PE
label | 5311d01b-d544-51ea-8264-5bf8c3f21bc6 |  | note | Verifying Documents - Inspection record checklist: CHK-009-STR-CPD-RSS Walls-Fill Placement
date | 7cfdea52-7e00-5185-ae56-b0bb164afcc2 |  | date | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - As-built Survey
label | 95e92a3a-3091-51cc-a4cc-2333953fd728 |  | note | Reference - MRPA Quality Management Plan, IFC Drawings
label | a57cedb2-eda8-5439-b2b7-84cbb886802b |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances as per IFC drawings.
label | 8aecb37d-94cc-53cd-925b-64816afd2d2f |  | note | (a) Plan position shown on the drawings, at base of wall shall not exceed ±15 mm;
label | 231592d5-1896-5d1d-b040-631de4d82162 |  | note | (b) Relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall;
label | 2f06e5b2-f634-5883-8ee2-37edf86458ca |  | note | (c) Local deviation of the wall face measured at any location with a 3m straight edge shall not exceed 15mm;
label | d5556de6-336a-53f5-ba04-5dcdb47b0fc8 |  | note | (d) The tolerance on position measured at the top of the wall face shall not exceed 5mm per 1m of wall height;
label | d62deb4c-c673-590a-aa6b-f0f09a7c5a4b |  | note | (e) The wall level shall not deviate from the specified level by more than ±20mm;
label | ff94ffcd-66fe-5a3c-8289-b17dd3fa4347 |  | note | (f) Variation in gap width between facing panels shall not exceed 5mm per metre length and 10mm over the full length of the gap.
label | 7cb5e9ab-8e6d-5e8b-a95c-5cddd3e394a9 |  | note | (g) The levelling course level shall not deviate from the specified level by more than ±3 mm;
label | ecf142ba-6d21-51c2-b049-88d9cffeb7d2 |  | note | (h) The vertical deviation of the soil reinforcement shall be within +1% (upwards) & -0.3% (downwards) of the soil reinforcement length, relative to the connection height unless noted otherwise
label | c1a81816-46b5-587c-aa09-41429d058e2f |  | note | Attach: Survey As-built / Survey Report
label | d0a7c0fc-43d3-5cff-bd1a-5b4a5c8fc0ad |  | note | Method - Document Review
label | c6e96205-64ab-57c4-b0f1-13e11dc1825a |  | note | Frequency - Each element
label | ccecc883-30ec-5d16-89b3-21fce9c6e3a5 |  | note | Category - IP
label | 1371d605-8a2b-5996-8e0b-03a4b8439836 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | dda04bb9-699c-51b5-ba9c-cc582979f8f8 |  | note | Verifying Documents - Survey Report
date | 911ce21f-838b-51ab-aa9f-7d0a9123d6b3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Wall Post construction monitoring
label | 1a01004b-2773-5ecb-9fea-28166b958bbf |  | note | Reference - IFC Drawings VR 682.20, VR 682.151
label | 3c1d2b30-4d0e-559e-98f6-1a99c13c2ceb |  | note | Acceptance Criteria - The Contractor shall take measurements of the position of the RSS at the points defined in clause 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period.
label | 7553ae5a-9b42-51b3-a34a-186c80390a96 |  | note | Method - Measure, Survey
label | 5250961a-e8fa-56a8-acbc-d7b4c08d7f15 |  | note | Frequency - Each wall
label | 9fae5879-ddbb-58e8-8b9e-d07f7bb70d6d |  | note | Category - IP
label | d96bb50b-09ca-5f99-a56b-f647e4d089d5 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | cb91a2f9-7387-5b08-8ca2-21b145706851 |  | note | Verifying Documents - Survey Report
date | 5e7e77d0-b489-5d3b-8f75-d9eb7cd1b618 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | 70da3a7f-81b1-5be0-a295-e3e97442b098 |  | note | Reference - MRPA Quality Management Plan
label | 873d6cc1-7f15-51fc-9079-043a0198b7cb |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 6ae7a1d6-fcae-5da4-b32e-ba1f6e88cd1f |  | note | Method - Document Review
label | d2f9202d-d384-544a-945e-4bcefbc4b456 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 7dc6fc13-b20d-57c3-a895-6755dd575479 |  | note | Category - HP*
label | ab6b51d5-a2f9-50e7-beb4-c52eefa78951 |  | note | Responsibility - SE/PE/SPE
label | eaf0e954-3c77-5f07-9111-9a4b36628244 |  | note | Verifying Documents - This ITP Signed off
date | 486972d2-98d0-5df6-869f-db31e7a351cd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | d8864831-53ae-5565-87a3-cbbc3f57970a |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 900aa6c4-1a44-5754-9253-231658e2de9e |  | textbox | Name:
text | 2b8ba198-d19d-564e-b50d-e1dec23f9e73 |  | textbox | Position:
date | 8409a9e6-8849-50b2-97bf-7ea7bd6a542b |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-132-STR-CPD-Structural Concrete Crack Repair | itp |  |  |  | Yes | ITP-132-STR-CPD-Structural Concrete Crack Repair Rev 0 | 242bfef4-0ac6-43d0-b8af-7dd00ac6e8e1
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 631da067-37a1-570f-90cc-d2792eefb791 |  | note | Document Title: ITP-132-STR-CPD-Structural Concrete Crack Repair
label | 8d1e1e1e-ae45-5ae6-a0b0-4b3134b3a92a |  | note | ITP Description: CPD-Structural Concrete Crack Repair
label | 8a159ef0-42df-5805-9602-38805374a9b4 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | c28c640f-8366-5749-a793-7cfdd8fbe924 |  | note | Discipline (e.g. CIV/STR/RAIL): 132-STR
label | 08c26f47-4618-5352-b73b-1b312288b094 |  | note | Revision Number: 0
label | c250d177-b2ee-597d-989e-db04c78faa2b |  | note | Revision Date: 7/02/2024
label | 3bca33b5-a1b0-52ba-8328-03b09ff31512 |  | note | ITP created by: Andrew Carlini
label | d649edb8-e703-51c3-8643-9eda3de8d987 |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 9e94c57a-bd87-5917-afeb-726d24274351 |  | note | Reference - VicRoads Section 610 June 2019
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | e8bdf75e-3b1f-5d20-81fc-929fa2c75f6b |  | note | Reference - VicRoads Section 687 August 2018
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | 2b9c0113-788f-5ba6-8488-1fca5dffc87c |  | note | Reference - VicRoads Section 686 November 2018
checkpoint-group |  |  | section | 2. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 2.1 - Assessment of Cracks
label | 5717e585-c90a-5fb3-a904-a6bc3f053121 |  | note | Reference - 687.01, 610.24 (b)
label | 4269348b-980d-599b-b412-267961f4978e |  | note | Acceptance Criteria - The assessment of the cracked concrete structure shall be undertaken by a technical specialist with a minimum of 5 years practical experience in the diagnostic assessment and investigation of concrete structures.
label | d08a0a7b-870c-52c0-aeb8-35b3725f8b84 |  | note | ○ Cracks to be determined either as active or inactive.
text | db06a38c-125d-5366-a7d4-ce2a4b13a851 |  | textbox | Enter: Teambinder Correspondence Approval number
label | 4a394877-f6c6-50c7-859f-7d2f5b766c4b |  | note | Or
label | 0e86ac97-43ef-5800-adfe-263b9fc3fc41 |  | note | Attach: Correspondence
label | 3acd207f-6fba-5e7f-99ec-624aec4f2fdb |  | note | Method - Visual, Measure
label | 27ae4607-d409-5475-866d-af2e49bc447c |  | note | Frequency - For each element, prior to Works commencing
label | 1c2fa1d7-d36e-5e9f-a71f-b70124e910b7 |  | note | Category - HP
label | 39051c03-7f19-580f-94b3-874da9095976 |  | note | Responsibility - Nominated Authority
label | c3fd7225-cd35-5377-907f-73045b7a43b2 |  | note | Verifying Documents - ConQA Hold Point Release
date | ca1ed8af-607c-5977-a682-23a1d417aaa0 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Work Procedures
label | 22754a73-15f3-5069-b293-cb05c6309991 |  | note | Reference - 687.01, 687.09 (a), 610.24 (b)
label | e397430e-5d96-55af-b2ca-1fd0453e9a19 |  | note | Acceptance Criteria - The Contractor shall submit a crack repair procedure/procedures for review to the Nominated Authority.
text | 44131421-42c4-59c5-b4b9-69576f139806 |  | textbox | Enter: Teambinder Correspondence Approval number
label | 6895b9ff-5bc1-5aa5-85cf-fc47694a83cd |  | note | Method - Visual, Measure
label | f1f5e79b-57b6-5e45-9ff8-960a0407b97c |  | note | Frequency - For each repair methodology, 14 days prior to Works commencing
label | 7752aac9-3f4d-5ed6-8e11-ed21d1e69e4b |  | note | Category - HP
label | fe5257d3-ad08-5420-8f87-3ae390938b10 |  | note | Responsibility - Nominated Authority
label | 555e6b91-a102-5028-8638-c87d714e63d9 |  | note | Verifying Documents - ConQA Hold Point Release
date | 81ed4305-ee6e-56bc-ab5f-8ee535bd6ea8 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 3.1 - Flexible Sealant Selection - Active Cracks
label | 991fbdf5-31b7-5cb2-86d4-cc405869487c |  | note | Reference - Product TDS 687.05 (c)
label | 663dacc6-ad41-5df8-8253-914f867b6e05 |  | note | Acceptance Criteria - Product to be selected based on the following criteria:
label | cf4e93c2-0bc3-52d9-b1c5-1e32e2619fe6 |  | note | i. provide for a minimum expectant movement of ±25%;
label | 68ce6b0f-4822-5e11-a992-59e340c80b7f |  | note | ii. Whether or not the repair/sealant is subject to traffic (trafficable or non-trafficable)
text | 5532b2db-b40e-50c6-a9d4-b55fa85915c9 |  | textbox | Enter: Teambinder Material Approval number
label | ea7ee059-aa50-57c7-b923-28792f4376fa |  | note | Method - Document Review
label | dd79e41a-0b62-5028-9069-1dcd28788fcb |  | note | Frequency - For each product, prior to Works commencing
label | f2007281-fead-586d-99f0-357bfae25c12 |  | note | Category - IP
label | 91b84bc4-a005-5d26-9a48-93acc194e0c9 |  | note | Responsibility - Nominated Authority
label | 81b36935-b41d-5dc0-a95d-a86a2e92af47 |  | note | Verifying Documents - This ITP
date | 67ebb1b9-240b-5648-a790-dab699f6c4f2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Epoxy Mortar or Paste Selection - Inactive Cracks
label | 3d3f3190-4581-57dd-a5da-ab3162fef5cf |  | note | Reference - Product TDS 687.05 (b)
label | 6cca2e14-9ec8-5ad0-9db9-827786181439 |  | note | Acceptance Criteria - Product to be selected based on the following criteria:
label | 44f236a3-6a6e-5603-9fe5-bd671cbb4d50 |  | note | i. compressive strength @ 7 days ≥60MPa;
label | 0e53d026-9802-5b45-b0f0-ac18ed7cd825 |  | note | ii. tensile strength @ 7 days ≥25MPa;
label | 45002782-d983-5ce8-a129-01438c43a710 |  | note | iii. flexural strength @ 7 days ≥30MPa;
label | b7fae06c-396d-5deb-a25f-faaa792e2ea6 |  | note | Note: For the routing and sealing, injection nipple/entry port placement and surface sealing applications only.
text | bb832ac1-d1d0-5cbf-bd50-0cace5445656 |  | textbox | Enter: Teambinder Material Approval number
label | 27dc14c4-51c6-5dbd-95e4-370e463401c8 |  | note | Method - Document Review
label | e0738c00-582a-5ba5-ab4c-3c7653f209fe |  | note | Frequency - For each product, prior to Works commencing
label | 474d24ac-08af-50ac-abe5-7c77c3dc4faa |  | note | Category - IP
label | 2710710d-c186-55d8-a473-fcaeb4432cf0 |  | note | Responsibility - Nominated Authority
label | cd4193d3-c2f5-58aa-8457-4a0b73984fd8 |  | note | Verifying Documents - This ITP
date | ab2fcc17-72b6-5ef1-b9d0-077e17ad0088 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Epoxy or Polyurethane Resin Selection - Inactive Cracks
label | 5bf219e0-686c-569f-b680-a823c0f5b980 |  | note | Reference - Product TDS 687.05 (a)
label | 006606f6-1265-519e-8a34-4a2bfbd3f9ba |  | note | Acceptance Criteria - Product to be selected based on the following criteria:
label | 10c25e4d-9051-5788-b201-ca7dee49c488 |  | note | i. viscosity @ 20°C - 23°C 650cps max.
label | bc0ba4fe-bdc8-521d-b72a-afb8a1158c69 |  | note | ii. compressive strength @ 7 days ≥60MPa;
label | 73c15f2a-30a2-5dbb-b98b-2358eecbfcd1 |  | note | iii. tensile strength @ 7 days ≥25MPa;
label | 054dcccf-553c-5b88-a0d7-457f285c0107 |  | note | iv. flexural strength @ 7 days ≥50MPa;
label | f5669c28-b996-5c84-b5e8-6bf5ced76395 |  | note | v. adhesive strength at crack edges @ 7 days ≥2.5MPa (or concrete failure)
label | a7222112-b37a-525d-b5b3-99cf0cb23c97 |  | note | Note: For the resin injection or gravity fed applications only.
text | 9e8f8aa7-7892-5000-b6eb-3a5ae5a62265 |  | textbox | Enter: Teambinder Material Approval number
label | 73755444-44f6-531b-97cb-7272f275c6ab |  | note | Method - Document Review
label | e9e51a07-aa89-5b33-9f0c-580af8c6dbf9 |  | note | Frequency - For each product, prior to Works commencing
label | f7789e42-3122-525e-8081-ddea1e0f7bf8 |  | note | Category - IP
label | 665573f4-a97c-529b-8948-1675cac3b67e |  | note | Responsibility - Nominated Authority
label | 35cc4bf1-3af5-59a5-931b-d93b66c082b2 |  | note | Verifying Documents - This ITP
date | 6c4dbe27-0eb9-5828-9657-af91c1467241 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Silane Selection - Inactive Cracks <0.2mm Width
label | c6a40cfd-aa90-5430-8f40-f284270435b0 |  | note | Reference - Product TDS 687.12, 686.05 (h) (i), 686.05 (c) (iii) (1 - 5)
label | 98cca28b-e17c-5727-aee2-544122fde75f |  | note | Acceptance Criteria - Product to be selected based on the following criteria:
label | 60834746-9fd1-574f-acc2-f37a0437f542 |  | note | i. active ingredient: ≥95% (penetrant)
label | d3e34639-aa2e-5cb3-bc88-99f8ca824265 |  | note | ≥80% (solid silane)
label | 13423a92-6b22-5cdd-ab84-bedb4c33c26b |  | note | ≥80% (silane crème)
label | 6b904a89-e09d-54b1-9a3f-f79d9ff6cb29 |  | note | ii. penetration depth: 5mm min.
label | 4e3bb0e2-6308-53db-8bc9-1263b5ae8b08 |  | note | iii. contain a fugitive dye to enable coated areas;
label | 6037ea27-aa44-5e39-966e-d04270a88c65 |  | note | iv. be compatible with a film-forming top coat;
label | ef22c34b-d26d-552c-a775-8c3b8bbb6897 |  | note | Note: For the protective coating of inactive cracks ≤0.2mm in pre-stressed elements and exposure classifications B2, C & U only - 0.2mm cracks are acceptable in other precast elements and exposure classifications.
text | 64430763-f625-54e0-ac4b-81ef7a90cebc |  | textbox | Enter: Teambinder Material Approval number
label | 10cc313e-baae-5fa9-9bf2-be4992c1b8c6 |  | note | Method - Document Review
label | 66642803-ec52-545b-8b5b-37464f2e389d |  | note | Frequency - For each product, prior to Works commencing
label | 87aa0d2c-ca77-57d1-af7b-5390fe8afa5f |  | note | Category - IP
label | 9bad495f-235c-5145-ba98-e02f72067730 |  | note | Responsibility - Nominated Authority
label | 2038f8d1-dc92-5879-ac4c-2bea69cdd497 |  | note | Verifying Documents - This ITP
date | 9c43fd95-a7eb-50d8-b142-ce3740667310 |  | date | Date Completed:
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Contractor Competency
label | f3d48307-be87-57db-87ee-a5c3b794401d |  | note | Reference - 687.04
label | 8c06ed92-be37-52ee-be88-e1f4009a12e7 |  | note | Acceptance Criteria - Personnel undertaking the concrete repair works shall have a minimum of 5 years experience in application.
label | 805e8ed1-37a2-59c4-b5ca-832789ad1b22 |  | note | ○ Documented evidence to be available.
label | d0ac6d21-a049-512b-8d3e-2fd3ab212507 |  | note | Method - Document Review
label | ae0d3e71-c268-5b0f-999f-2db29e88ca64 |  | note | Frequency - Once, for each personnel, prior to starting Works
label | ccbc71f5-e039-554e-be78-abd52b69626b |  | note | Category - IP
label | 1449c3d2-d8ee-5359-9f59-e1a0dbd49923 |  | note | Responsibility - SE/PE/SPE
label | 7bdd4e57-ff92-5d62-ba61-5153d794a5c8 |  | note | Verifying Documents - This ITP
date | 7705d710-647c-506d-8ff7-4315611e0722 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Injection Equipment
label | a5cec70a-157f-5695-8285-b46918ebb666 |  | note | Reference - 687.06 (a), 687.09 (c) (iii)
label | 03918125-72df-5453-86db-7e3c6366cd17 |  | note | Acceptance Criteria - Injection equipment to be simple, easy to handle guns with pressure regulation or limitations in the operating range and be simple to clean and maintain.
label | 52c940a2-9ea3-58b0-a36e-04fc15a99b06 |  | note | ○ Nipples/entry ports to have shut off valves or at least the ability to be capped to prevent leaks or air travelling back into the crack.
label | ee9c2bee-332d-5650-b9d2-9d839c1824d9 |  | note | Note: This ITP does not cover special purpose, multi-component injection pumps.
label | ed1dc177-6ba3-5e6d-8f86-916f1dd91119 |  | note | Method - Visual
label | 6cf294a0-b8af-5c93-a0c2-0d6f6255f467 |  | note | Frequency - Once, prior to starting the Works
label | 8b91e47d-5f61-5f23-a7ba-884318c48446 |  | note | Category - IP
label | cec8ab32-a0ca-58cf-8a88-a548565e078f |  | note | Responsibility - SE/PE/SPE
label | c119738b-a543-5b2b-bed3-ea3f58eba34e |  | note | Verifying Documents - This ITP
date | 0af4b517-d255-5014-b237-2d638e6329bb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Weather Conditions
label | 93229e9c-be27-5239-b7c0-00f60001d450 |  | note | Reference - 687.05, 687.09 (c) (i)
label | 0ef5cc60-a60c-5612-9173-42d497de0f36 |  | note | Acceptance Criteria - Repairs are not to be undertaken when the ambient temperature is below 5C or 5C on a falling thermometer, or above 35C.
label | 3a735064-0004-5267-80ba-9437b840aefa |  | note | ○ Cooling the materials is allowed should the need arise if temperatures inadvertently rise during the repairs.
label | eadbb762-2f81-5d8e-aa51-df77bb39a26b |  | note | Method - Visual, Measure
label | 0dc7a707-b92f-5f4b-a6cb-72756db8f64a |  | note | Frequency - Prior to each repair
label | b37e296c-d3cd-5e68-8e26-a418db075fac |  | note | Category - SP
label | 4e1eba8b-b97f-5b55-a777-7b920290b69e |  | note | Responsibility - SE/PE/SPE
label | ed11f65b-aab4-5bb2-bc0d-cae0a45771b1 |  | note | Verifying Documents - This ITP
date | fb5362b3-46f2-592a-80a2-8a54b33b8133 |  | date | Date Completed:
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Surface Preparation
label | 47fb3ea2-6eb3-5597-9139-c82252373963 |  | note | Reference - 687.08
label | 0326cb44-8224-5187-9693-3cfc6e6efa18 |  | note | Acceptance Criteria - Cracks and surfaces located within 50mm each side of the crack to be cleaned of all loose particles, dirt, dust, curing compounds, grease or efflorescence by appropriate means.
label | 060d98d9-11d6-525e-8d35-706957864637 |  | note | ○ Where cracks and surrounding areas have been moistened during the cleaning process, sufficient time or accelerated drying-out needs to occur unless the crack repair materials are water tolerant.
label | acd66f7a-39d0-52d5-9510-ca62e5bae71b |  | note | Method - Visual
label | 756a00fc-d7e4-55e2-b78b-fe17a7f50e8e |  | note | Frequency - Each crack
label | e71980e4-8a9c-5c07-a633-66bc0a8ba50a |  | note | Category - IP
label | dd321ae7-2b2f-54d4-ba6a-3111fba32a07 |  | note | Responsibility - SE/PE/SPE
label | 36e16b9a-6b8f-5094-9bf1-9801d157d54e |  | note | Verifying Documents - This ITP
date | 8d56db4f-fc95-5ce8-8af7-f16e8bb99347 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Active Crack Repairs - Route & Seal Method
label | 6aa06162-11bc-530e-b505-a66afd809cc0 |  | note | Reference - Crack Repair Work Procedure, Product TDS 687.10 (b) (ii), 687.15 (a - d)
label | 5ee8bbcc-063e-5e69-bb04-d472d3bdd9bc |  | note | Acceptance Criteria - Approved procedure to be followed, steps to witness:
label | 6988f117-0cef-5f04-93c5-9e6ed7eac73b |  | note | i. All materials in date and mixed as per the Product TDS;
label | 0679d88d-21bd-51bd-937c-35b2ce2254da |  | note | ii. Saw cuts to be at a width to depth ratio of 2:1 and rectangular in section;
label | 4f2ce46f-abd3-555d-9c53-2f98e304016f |  | note | iii Surface dust to be removed;
label | ccac4838-ea01-5532-9685-45744aef5508 |  | note | iv. Bond-breaking tape to be placed at the base of the chase/reservoir to limit sealant interface to 2 no. faces;
label | 0836a506-c24a-562a-83bd-243ed5991805 |  | note | v. Where required, masking tape to sides of the adjacent surface to create a neat finish;
label | 041b006e-2252-51dd-8abd-d239b3bf2948 |  | note | vi. Sealant gunned or tooled into the saw cut to completely fill the void;
label | 54674928-fb77-55c7-931f-5cfbb84b05a2 |  | note | vii. Product shaped with a suitable tool to recommended profile;
label | 97183bd6-702d-55f8-a50b-df2f6f8fc40d |  | note | iix. Repair to be protected from damage or adverse weather while curing;
label | 2ea60739-831f-58fb-8c0c-fbfcd19a9616 |  | note | Method - Visual
label | df23ce35-01fb-58c1-a067-079496a8af1b |  | note | Frequency - Each active crack
label | 1b150d36-c8a0-5f33-9e3d-ae47808ef985 |  | note | Category - WP
label | ded4e10a-5d92-5081-b839-eb2d71d81e81 |  | note | Responsibility - SE/PE/SPE
label | aed8cf86-9f69-5c8b-a254-f930b4d984a2 |  | note | Verifying Documents - This ITP
date | dc163beb-c101-569e-9b21-c2469c4f2b28 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Inactive Crack Repairs - Route & Seal Method
label | 602e717b-2b3c-5093-bd9b-b338ef16014f |  | note | Reference - Crack Repair Work Procedure, Product TDS 687.10 (b) (i), 687.15 (a - d)
label | 960b8bd6-7eb0-544e-b101-8182e8d26207 |  | note | Acceptance Criteria - Approved procedure to be followed, steps to witness:
label | 221d7d38-3cb8-55fe-8d99-db10edc81575 |  | note | i. All materials in date and mixed as per the Product TDS;
label | 30e12a6f-9d09-5fa5-b888-abb7e1c205de |  | note | ii. Saw cuts to be at a minimum width and depth of 10mm and V-shaped in section;
label | 67a5f286-162e-591d-aee8-c97fdfda4f58 |  | note | iii. Surface dust to be removed;
label | 7a2323ba-6b0e-5d19-9595-90cbb6fb2ff1 |  | note | iv. Epoxy mortar / paste placed into the saw cut to completely fill the void;
label | 167c5e62-59c7-502b-8172-07c928741f45 |  | note | v. Product finished flush with the surrounding surface;
label | b2e37944-6e14-5dd7-b459-6d31f2b210fb |  | note | vi. Repair to be protected from damage or adverse weather while curing;
label | 536e20df-ac59-57b8-9e76-16a3898130aa |  | note | Method - Visual
label | bbd83ff4-6a87-55f4-9380-b75ae71c2134 |  | note | Category - IP
label | 7c90ac40-829d-57a1-92db-12c5172542ed |  | note | Responsibility - SE/PE/SPE
label | 88fd1163-0144-5993-8e85-0c70597335ed |  | note | Verifying Documents - This ITP
date | 2ec0e8ee-12e3-514a-8bf5-e6017c935a13 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Inactive Crack Repairs - Gravity Fed Method
label | 21e5c28d-4897-51bc-b8e8-cb156939729a |  | note | Reference - Crack Repair Work Procedure, Product TDS 687.11 (b) (i - ii), 687.15 (a - d)
label | 5508f3bd-0cab-59d5-b4d2-c994f8171f90 |  | note | Acceptance Criteria - Approved procedure to be followed, steps to witness:
label | 56af1bf0-8523-5f29-be6c-f1471b4c954f |  | note | i. All materials in date and mixed as per the Product TDS;
label | bcd236a4-e953-55af-9885-f7b378b55b0f |  | note | ii. Where required, a water-tight reservoir, to be created with silicone or polyurethane sealant;
label | bb6aecc7-67f8-522e-b68a-801d4ce34f1f |  | note | iii. Epoxy resin to be poured onto the crack and either sufficient amount contained in the reservoir (if used) or worked back and forth by suitable means (such as a broom) until no more material can be absorbed;
label | 595a6645-ca02-5155-b15a-f549875ed6d6 |  | note | iv. Excess material and reservoir can be removed as the epoxy resin gels;
label | 3bca6743-2203-5e28-adcd-ab737ee2c13d |  | note | v. Repair to be protected from damage or adverse weather while curing;
label | 05c16dbe-3481-5f8d-9faf-ec6ff358a4a3 |  | note | Method - Visual
label | b2861216-cc27-5b57-beb9-742a90e69954 |  | note | Category - IP
label | ac90d54f-79d5-51e2-878f-d565187e9249 |  | note | Responsibility - SE/PE/SPE
label | 93efaec5-b39f-5476-a713-a72e5915ec63 |  | note | Verifying Documents - This ITP
date | f24bb8de-9196-57ea-873e-b361fc7c622a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Inactive Crack Repairs - Injection Method
label | 6940607b-6ed4-5221-9a24-565b84f246df |  | note | Reference - Crack Repair Work Procedure, Product TDS 687.09, 687.14 (a), 687.15 (a - d)
label | 5e2e51bd-4bd1-56ea-851d-3b3c4639df66 |  | note | Acceptance Criteria - Approved procedure to be followed, steps to witness:
label | e52a1303-9b2c-5b56-954a-dabb96469d51 |  | note | i. All materials in date and mixed as per the Product TDS;
label | 1b29ee94-0529-5b02-a15e-dda44ed3a732 |  | note | ii. Each nipple/entry port coated in epoxy mortar or paste to create a water-tight seal to the entire perimeter;
label | cbaab2b7-4425-58dc-9478-f9a094a89c09 |  | note | iii. Nipple/entry port placement central over the cracks at 200mm spacings maximum (where cracks are through the full section, nipple/entry port placement shall stagger);
label | e649767a-8f37-5b36-9196-fd5ec9bdf803 |  | note | iv. Epoxy mortar or paste applied to the surface of the crack in between nipples/entry ports and the full height of the crack if within tolerance to eliminate resin leakage);
label | 2da9f489-211a-50ae-8f53-317ec4239f93 |  | note | v. Once the epoxy mortar or paste has fully set, connect the injection gun to the lowest nipple/entry port (for vertical cracks) or at one end of the crack (for horizontal cracks);
label | dc5f234d-7f9f-5c84-87f8-920d52d76e72 |  | note | vi. Initiate the injection, applying pressure until resin can be witnessed entering the next nipple/entry port;
label | 39ef2894-574c-533f-b098-9dba8a670f25 |  | note | vii. Stop pressure and close the valve of the engaged nipple/entry port and connect to the nipple/entry port where the resin appeared, working either upwards (for vertical cracks) or along the crack (for horizontal cracks) until all nipples/entry ports have been filled;
label | ecac0df4-bf1d-5a26-9018-c8b01ca9f408 |  | note | iix. Repair to be protected from damage or adverse weather while curing;
label | a3f58259-c967-564b-b715-9597635f1302 |  | note | Method - Visual
label | 133ad420-f699-5368-9388-adc6dc48f698 |  | note | Category - IP
label | 0dd6f304-9926-57cc-b054-d00198557394 |  | note | Responsibility - SE/PE/SPE
label | 051a8a35-fc99-52d2-8beb-74f8f5c6adbc |  | note | Verifying Documents - This ITP
date | e19e43d5-b691-5500-8f0d-346f73f8f4fc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Inactive Cracks <0.2mm Width Repairs - Penetrant Coating Method
label | 9376df2d-302c-5d79-92b7-e4c42c087b83 |  | note | Reference - Crack Repair Work Procedure Product TDS 686.07 (a) (i)
label | 1bf07fa8-e06b-5a0f-873c-eea5cb14f521 |  | note | Acceptance Criteria - Approved procedure to be followed, steps to witness:
label | 9bd08c8a-06ec-56f4-8dd9-891cebdec19f |  | note | i. All materials in date and mixed as per the Product TDS;
label | 15d8354a-8bf0-5550-8655-59d1d8db8fba |  | note | ii. Silane to be applied with an airless sprayer (for penetrant) or brush (for Solid Silane or Silane Crème) , working from low to high areas and approximately 150mm beyond the extent of the crack;
label | b6264939-2caa-5850-a594-a70ec864473f |  | note | iii. Application rates to be as per the TDS for each type of product ensuring wet appearance;
label | a9415c42-bb89-5de5-8352-186d29ef97cd |  | note | iv. Re-coating if required;
label | 05c4bf1c-308a-5653-a76e-113970911025 |  | note | v. Repair to be protected from damage or adverse weather while curing
label | 18c3ba6f-15f9-5ba9-bfdf-08ae0f0637a5 |  | note | Method - Visual
label | c96ea42f-5e58-536e-a4cd-e85c3b3f622a |  | note | Category - IP
label | 7422f4ff-d39a-5ad3-976a-e69cdf384039 |  | note | Responsibility - SE/PE/SPE
label | 4fdb7ea7-9158-52ff-a5b0-19c169337814 |  | note | Verifying Documents - This ITP
date | 6f5e5150-1677-5980-ac50-4bd7f7a5a70e |  | date | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Curing & Finishing
label | 09725799-2f86-5df1-b995-1019265a3efa |  | note | Reference - Crack Repair Work Procedure Product TDS 687.15 (a - c)
label | 452f24b9-427c-564d-a6f4-9b4f26af625c |  | note | Acceptance Criteria - After the repair materials have cured in accordance with the manufacturer's recommendations, any surface seal, nipples/entry ports and repair materials can be removed by suitable means.
label | 413b175b-7514-5bf9-8433-af86c8cbf659 |  | note | ○ The surface shall be ground smooth, leaving no traces (indentations or protrusions) of a repair and if the repair location remains exposed, a fairing coat can be applied where not being coated with a pigmented coating system.
label | 2dc6fee6-200c-55d2-8c2e-773b094fe860 |  | note | Method - Visual
label | 6d18e846-e41e-5f62-9bc2-f7de86c7643c |  | note | Category - IP
label | 256a50ee-72af-533c-869f-db19e58209c8 |  | note | Responsibility - SE/PE/SPE
label | debc2476-46e0-5ebb-adfc-5df22fba17a6 |  | note | Verifying Documents - This ITP
date | d96fb820-b638-5f33-bddb-117a61b3bac9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Repair Verification
label | 4e80b5ff-c816-58e0-b479-59f5c0e64422 |  | note | Reference - 687.16
label | 257d7525-0a07-5076-802f-5151049c3afe |  | note | Acceptance Criteria - After 7 days minimum, 75mmØ core samples shall be taken to verify cracks are fully sealed.
label | ac57d4f7-b4fe-52d3-bcab-bd1983ce3c04 |  | note | ○ Cores to be located in conjuction with a covermeter to avoid reinforcement and approved by the Nominated Authority.
label | d3a92884-0476-5926-bd24-377ef7790936 |  | note | ○ 2 no. cores for the first 25m of crack and an additional 1 no. core sample for each 50m of crack or part thereof.
label | a01d4b87-1ec4-55ab-b16c-821add892cfe |  | note | ○ Core holes to be filled as per the cementitious repair ITP.
label | a60c82be-4f31-58f9-b88c-41fdfe9bb984 |  | note | Attach: Photographs of Core Samples
label | 90fff03d-6b75-5e79-9689-0cc0898b3aeb |  | note | Complete: Structural Concrete Cementitious Repair ITP
label | b5dcafed-7b73-5676-976f-5d8b648f3428 |  | note | Method - Visual
label | 871ea712-f76f-529d-b6c2-4feb0acae562 |  | note | Category - WP
label | bbb0463c-c6c9-551b-973d-777fdb174eb2 |  | note | Responsibility - Nominated Authority
label | 9677719d-f299-5a63-967c-44aa8b3f8d32 |  | note | Verifying Documents - This ITP
date | ac317d51-b26c-5178-bbc1-9818ddc0ccf9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | ee2ee4cc-4390-531e-b2f4-7319addd07cf |  | note | Reference - MRPA Quality Management Plan
label | e72fbe6f-71c5-55db-aa91-b6d932b5c872 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 3cefec86-54c6-5c90-b034-d92939cea48b |  | note | Method - Document Review
label | dda5c6ee-b087-51a2-be30-38631eaac0de |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 97e40316-95f5-5c1d-877f-bbef510c84ca |  | note | Category - HP*
label | 38adbabc-ce83-5baa-bf7a-f28b82829890 |  | note | Responsibility - SE/PE/SPE
label | d5eaa0f1-0ad0-5b1c-827e-c0511ccd614c |  | note | Verifying Documents - This ITP
date | a781c536-c3dd-5a08-a90c-3e90f18e9f2b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | dd54137c-b0dd-5dc9-8c86-a08aa6e142db |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 5af36060-900a-545a-90c1-58437b1b0753 |  | textbox | Name:
text | e70e19c5-f246-5e24-8222-ae1abf7f4dd9 |  | textbox | Position:
date | becd476f-1f16-576e-80f0-ff1734c970f1 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-017-STR-Structural concrete | itp |  |  |  | Yes | ITP-017-STR-Structural concrete Rev 0 | 2a70391f-9ded-4f5d-ab83-2ef16dd16621
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | bd2f342b-2be8-5aba-9837-122d3d938d35 |  | note | Document Title: ITP-017-STR-Structural concrete
label | 18ba4e21-4f7a-56bd-b21f-649a5cc6ea8e |  | note | ITP Description: Structural concrete
label | 03bd451d-59ca-571e-b698-366dc73e3e3a |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 7562d660-4a1b-55da-b44e-d89f81c18e92 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 8a8eabe3-8819-585b-b4ff-c137687235b9 |  | note | Revision Number: 0
label | 8c4da1d5-4bdb-5381-93c6-2a034cf69134 |  | note | Revision Date: 01/12/22
label | aceac5f1-98b6-526b-9a97-bf0680adaa03 |  | note | ITP created by: Victor Mira
label | dbf9186d-ca8d-5993-97c2-86665d1d9fbc |  | note | ITP approved for use by: Victor Mira
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | a33417e6-0864-5f4a-b996-7c8b2116b784 |  | note | Reference - VicRoads Section 602 October 2007
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 6726a6ee-d123-5efc-bd95-8fb217e75f18 |  | note | Reference - VicRoads Section 610 February 2020
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | a2be94c9-1730-553a-9d50-3864c01bff6c |  | note | Reference - VicRoads Section 611 November 2018
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | 211a0d04-0b40-5a16-9512-8867837574f6 |  | note | Reference - VicRoads Section 614 June 2017
checkpoint-status |  |  | checkpoint | 1.5 - Non Dependent
label | d6b3b71d-b93a-5b9b-a887-901f97d53eb0 |  | note | Reference - AS3810.1 2018
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Concrete Mix
label | af792a71-d68b-5c03-8c49-31792bcac9d8 |  | note | Reference - 610.07 Table 610.071 IFC Drawings
label | 39e8755f-8b8a-5422-98c2-d6228b95faf9 |  | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
label | f4e5337a-81bf-57b0-a7cc-5fa684604457 |  | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | 4e96c0ea-1bb9-5fb6-98fa-cdc5aadefde9 |  | textbox | Enter: Teambinder Material Approval number
label | 62ff8715-b665-5541-b9d1-2ef8bedbfbf7 |  | note | Method - Document Review
label | cda4958b-83d7-54cc-85f9-f2384103dc2b |  | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
label | 7ffefa04-1a9f-553b-8360-33406abbc467 |  | note | Category - HP
label | 81946e21-0d37-503f-900c-d1d1861e4a40 |  | note | Responsibility - Nominated Authority
label | 355b529f-ac42-5f88-aa36-8daf43830bb2 |  | note | Verifying Documents - ConQA Hold Point Release
date | 77fae47c-c9d1-5808-8251-4604ee94704f |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - ACRS Certification (for Reinforcement)
label | 72768f61-777d-5ea0-a394-621888cebf9f |  | note | Reference - 611.05 (a)
label | e1a6fef2-8fcf-5ce4-89da-4991328f203e |  | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
label | 09d3cdc8-fb72-5519-a7ca-24e34744e9a6 |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | 8b2d496e-2598-5b43-9e88-177f504e21ac |  | textbox | Enter: Teambinder Material Approval number
label | e3a8a0bf-bf38-51f0-89dc-337b39d0f9df |  | note | Method - Document Review
label | bd956417-ea07-556d-899f-e782d4d5704d |  | note | Frequency - Once for each supplier, 14 days of award of contract
label | ee813f9b-f6b7-5f1e-ad3f-8c3706f3c9b5 |  | note | Category - HP
label | 15214f2b-9fb8-5258-a438-2de5d09f7a72 |  | note | Responsibility - Nominated Authority
label | 1dcb3acf-817a-5b75-a97f-d2b63ae19692 |  | note | Verifying Documents - This ITP
date | 3813b8df-8aa9-55d3-9d6c-26c19e4f1c69 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Bar Chairs/Aspros Certification
label | 96ffcb57-b13f-58dd-8d31-4bca6ab76ef3 |  | note | Reference - 610.26 (a)
label | c84467f9-10a3-54fd-afb2-ca7f4c2d05cf |  | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | 2a9cd5b1-0b60-5165-ae86-a958412673dc |  | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
label | 048b6ba5-2de1-5815-b287-006f0d2407a4 |  | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | 176d1058-5c86-5a25-a03a-2625d5c3a96c |  | textbox | Enter: Teambinder Material Approval number
label | 10c9a689-32ca-562a-8ee7-005085339104 |  | note | Method - Document Review
label | 9d4b1e3c-3b58-5f0c-a2b8-6b26489f44b9 |  | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
label | 25614107-9de5-5ba6-88d4-033e60b3289d |  | note | Category - HP
label | 40fb5f17-ed0b-5305-b93a-45d206d5045e |  | note | Responsibility - Nominated Authority
label | 23da94e2-0a0d-558f-a75d-d24ce99a4df4 |  | note | Verifying Documents - This ITP
date | 438fde43-95d9-53b2-a805-38e05fc6f864 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Evaporative Retardant
label | 06726874-9d7b-5d86-b1af-38e5ea938382 |  | note | Reference - 610.17 (f)
label | 171a7547-9956-53a6-9f90-a80f1d5ba929 |  | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | 68731a50-7b6c-5aed-872a-ce6801075ba7 |  | textbox | Enter: Teambinder Material Approval number
label | 352c0bb5-ec52-5249-a13c-a2e79c2caa8d |  | note | Method - Document Review
label | 94f47226-c5e7-5706-814f-a4d0c3e88b4f |  | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | 6c22f27a-2022-53fd-b616-54861a9c6d9f |  | note | Category - HP
label | 93a9b5b3-fa07-592d-96a9-46720bad301d |  | note | Responsibility - Nominated Authority
label | 19792e76-310c-5cfb-b9ef-84a64f59b25e |  | note | Verifying Documents - This ITP
date | 236c96d9-ad3c-5808-be3f-49c4899ec9d7 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Curing Compound
label | ec132ec9-3357-5fb9-9cb3-b520c73c9233 |  | note | Reference - 610.23 (d)
label | b0517335-80a4-5e92-8586-57c5f4325e7c |  | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
text | 23d39d3f-2c06-5cfa-b7a0-c141b822ce29 |  | textbox | Enter: Teambinder Material Approval number
label | 66d1f230-00ec-5ce5-a5b3-1ac1455d5b5c |  | note | Method - Document Review
label | 0844324a-2720-5454-a529-de33f300035c |  | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | f1f9e1d5-adea-5aba-acf5-bb99f674eded |  | note | Category - HP
label | d7b64b1b-69b7-50cc-9ad8-a09396b658d4 |  | note | Responsibility - Nominated Authority
label | e28cc53a-39af-5a1d-9ff9-8a23881ede44 |  | note | Verifying Documents - This ITP
date | aa3ede60-1046-5f14-aba2-9b36132d2fce |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements
label | 6f0dee6f-c325-595e-8668-74cd7a78947f |  | note | Reference - 610.18 (a) (i)
label | 8fa2facd-1f9c-5b54-8122-a90384232d74 |  | note | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
text | 72974378-f9d5-5a67-a6bf-08a29f853e84 |  | textbox | Enter: Teambinder Approval number
label | ee1e022a-1bcb-572a-9f56-1aafda43a17d |  | note | Method - Document Review
label | d99c0510-42d9-5cb4-a928-577c8c619216 |  | note | Frequency - Once, 4 weeks prior to placement of concrete
label | 7d6baefa-f631-5cf8-a338-4059830482be |  | note | Category - HP
label | 8848b448-2835-5bf5-9bf6-b3756d3d1466 |  | note | Responsibility - Nominated Authority
label | 7cb37875-225a-5d65-b803-02a435515a05 |  | note | Verifying Documents - ConQA Hold Point Release
date | 1910cb2b-3de9-5def-9888-8dd01dd88b24 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Concrete Sampling and Testing Procedure
label | 2b8831b1-77cc-535a-8d71-ddd3b0801a83 |  | note | Reference - 610.18 (a) (v)
label | 43543c6f-e549-5430-aab2-c6aa05f60cd4 |  | note | Acceptance Criteria - Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
text | 12b26039-afe6-5ec2-8ea1-940e73f74e28 |  | textbox | Enter: Teambinder Approval number
label | 0ea987db-fed6-5d93-80d0-e3a2d8d54d9a |  | note | Method - Document Review
label | 87eef7cb-3dfa-5b6e-9e78-fa2b804922b3 |  | note | Frequency - Once, 4 weeks prior to placement of concrete
label | 495afd3d-3374-5d42-a4ac-b05213ad2451 |  | note | Category - HP
label | 5c14e1c2-8951-53be-a4fa-80fd665553b1 |  | note | Responsibility - Nominated Authority
label | a81c876f-c1a7-5073-8a8f-794e20e7fdc7 |  | note | Verifying Documents - ConQA Hold Point Release
date | 6b9d5f0b-438b-59f3-aead-ecf3023c88b8 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Concrete Placement and Compaction Toolbox Meeting
label | a7ad7e3d-2612-57e7-949c-f61750406a08 |  | note | Reference - 610.18 (a) (iv)
label | 799675f9-e35e-5f72-a154-e07d9f7754a9 |  | note | Acceptance Criteria - Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
label | f6107bd6-5b86-5bdd-97f2-b0a8dd0917ea |  | note | ○ Minutes of this meeting to be submitted to the Nominated Authority.
text | 7850de00-2428-5bb5-8018-342969936bb1 |  | textbox | Enter: Teambinder Approval number
label | 25ee5c32-a41d-5212-b09c-d8197850b019 |  | note | Method - Document Review
label | 88ee11c1-10a7-58aa-90fc-5b7fd00bead5 |  | note | Frequency - Once, 4 weeks prior to placement of concrete
label | 1e010b08-8c18-5849-9e7b-77bcf386cccb |  | note | Category - HP
label | 38221f17-2f48-5626-8352-e11a5b468f1d |  | note | Responsibility - Nominated Authority
label | f55b6d97-2142-5444-9477-be8233999bcf |  | note | Verifying Documents - ConQA Hold Point Release
date | c617e6bd-89b7-50e4-9ebd-6b93839c4273 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Hot and/or Cold Weather Concreting Procedure
label | 13f63b4e-20b5-517f-82d4-04e10b38c424 |  | note | Reference - 610.17 (a)
label | 70cef88f-0e31-5dd7-bd71-192f9ea7d67b |  | note | Acceptance Criteria - Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
text | 13b6bd3b-64dd-540d-b6cb-aa4aa0551425 |  | textbox | Enter: Teambinder Approval number
label | ce145703-2f39-5d35-a764-be367d5ca49c |  | note | Method - Document Review
label | ad6946e1-f83f-5b04-b25c-3f16a658915f |  | note | Frequency - Once, 2 weeks prior to placement of concrete
label | 3d208da1-5435-5716-8318-efbaaf461b4a |  | note | Category - HP
label | 4ae7970a-6167-5fbe-9d17-fbe63791eed3 |  | note | Responsibility - Nominated Authority
label | cdd171d8-03dc-5a20-9899-c9718510cabf |  | note | Verifying Documents - This ITP
date | a5aede70-0d8d-58ae-83de-0b6f6b6695fb |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Curing Methodology (for Concrete and Grout)
label | 934109d3-a2c4-55a5-8ba0-f1e631c1d148 |  | note | Reference - 610.23 (a)
label | 78b7b89e-253e-504b-a195-c3d5a25ee8aa |  | note | Acceptance Criteria - Curing methodology/procedure to be submitted for review to the Nominated Authority.
text | 2e951641-d335-5613-a83c-40a4127d6a15 |  | textbox | Enter: Teambinder Approval number
label | 3b55396b-82c1-55f0-bd82-30a80cb2cf77 |  | note | Method - Document Review
label | a1153721-646a-54ad-8928-474f89f50a38 |  | note | Frequency - Once, 4 weeks prior to placement of concrete
label | 4dccc7b0-3949-5f9d-a3e2-75ac4aa7fffb |  | note | Category - HP
label | 7b0b46c4-0a56-5e97-8aaa-6a3c7b74f870 |  | note | Responsibility - Nominated Authority
label | aa733904-62c6-5e9e-8b39-a222d19722e8 |  | note | Verifying Documents - ConQA Hold Point Release
date | 515e6cab-9be9-5328-bf10-cab0f7bb7bc8 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Concrete Drilling Procedure
label | b0124a09-4156-5edd-aa12-9643ea5629cc |  | note | Reference - 610.46
label | aac9e1e3-b0f9-5d63-bc9d-0dde4813efb4 |  | note | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
label | 3fc774ca-7b70-56f5-9f93-8d1333b9593d |  | note | ○ The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
text | 220f4370-3447-5f5a-8927-857d857cf168 |  | textbox | Enter: Teambinder Approval number
label | 6a1934c0-7a07-54b6-a483-79aa6a43fb9a |  | note | Method - Document Review
label | da65ad6d-2e84-56c3-aa31-7d0d77c7e6f2 |  | note | Frequency - Where applicable, once, 2 days prior to drilling
label | 809095fd-2f4e-52c9-9b46-50830182d739 |  | note | Category - HP
label | bb1fe959-9574-56ca-adbf-d386ff08e56c |  | note | Responsibility - Nominated Authority
label | 4ac8bb90-0624-503a-a927-cff682fd5808 |  | note | Verifying Documents - ConQA Hold Point Release
date | c1c90ab1-f924-5be3-8c01-8dbaa6417f75 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Temprature difference measuring-Calibration
label | ca8007da-5bc2-58ac-9fd3-2dbac012e938 |  | note | Reference - MRPA Quality Management Plan
label | db2fff19-2231-5727-a30b-b79c0f2d000e |  | note | Acceptance Criteria - Calibration records are valid and up to date.
label | f0e85fc2-0ee6-5f3d-8b07-e32f343033ef |  | note | Attach: Calibration certificate
label | 4ee0ce6d-6e3e-56c9-900b-8aa83c67d252 |  | note | Method - Document review
label | 95791d7d-56f0-52e6-8953-08a083f4c497 |  | note | Frequency - Where applicable
label | 2f1446a3-f86a-5833-8415-7e6ce03b686b |  | note | Category - HP*
label | fdb2e59f-0732-590f-b1aa-42b6c519cf9f |  | note | Responsibility - PE
label | 69cf74cd-9d7b-5b7a-805e-44e1ecdbc923 |  | note | Verifying Documents - This ITP, Attached calibration certificate
date | a112c65d-25bf-5a56-9126-8d634c2de457 |  | date | Date Completed:
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - IFC Drawings
label | 08985e92-41e8-5590-acbf-ccc138f0e75b |  | note | Reference - MRPA Quality Management Plan
label | cdcebd6d-6a43-544e-b3d0-4d6ea3429b95 |  | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 77afa9cc-2f69-57ee-9941-ac8b4cf1309d |  | note | Method - Document Review
label | 1d46c227-e343-53ee-87db-b9741734abd8 |  | note | Frequency - Prior to starting Works and at regular intervals
label | 6004b695-26ef-50a0-93d3-21edeb5b5b14 |  | note | Category - HP*
label | 60dfd7bd-e3fd-58fb-9866-6b852c90247c |  | note | Responsibility - All
label | b6bc1b2a-860e-505b-acba-ea4ff0434ac9 |  | note | Verifying Documents - This ITP
date | da7b5284-837f-50c8-9b9e-793b94daf882 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Survey Set-out
label | c8eeed26-e399-51d4-9899-ff6258f17eff |  | note | Reference - IFC Drawings 610.47 (a) Table 610.472
label | ca9d9bb5-8846-5deb-88c9-a6a2e1d9fbd2 |  | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
label | d00fba9a-d7c7-5e4b-a141-0a23d08e2d58 |  | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
label | b51b0d18-7ec9-5aef-9bbb-835fcfb05541 |  | note | Method - Measure, Visual
label | c1a55da6-eca0-5908-8120-2b72dac9117c |  | note | Frequency - Each element
label | a7e7b5e4-7966-5d28-8ea3-8670c9591d33 |  | note | Category - IP
label | e7f5a275-74df-51b7-bc8f-1c950a6d0134 |  | note | Responsibility - Surveyor, SE/PE
label | 987d7d15-df2d-57f0-9244-6329b38ebd2e |  | note | Verifying Documents - This ITP
date | 4a61840a-4b4d-5b9f-b93c-3a647961368f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Excavation support
label | 69255910-e8b2-50dc-825b-d0f8767315a4 |  | note | Reference - 602.02
label | a5d28ae2-3dfe-553a-b524-b954428ec64f |  | note | Acceptance Criteria - For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
text | 5ad4d986-adc9-5e8e-90fb-5d507f3b4a41 |  | textbox | Enter: Teambinder Approval number
label | 1b26676d-8f15-5cd2-a241-8a6ec8d1f2a9 |  | note | Method - Document Review
label | f6cd4ed3-289d-56d3-866e-a0d7ca16eb55 |  | note | Frequency - Where applicable, not less than 10 business days prior to excavation
label | 2e7e5cc6-dfb2-57b5-9eea-c4a98b4aa8c6 |  | note | Category - WP
label | a504382b-5e07-5d39-b131-1196fb122d78 |  | note | Responsibility - SE/PE/SPE
label | 697577d2-f191-5978-b81b-49229f84a4e1 |  | note | Verifying Documents - ConQA Hold Point Release
date | b1449a57-6df5-504b-8528-9b19b9f3cb80 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Excavation Inspection
label | 782e87e4-e521-5e6f-9a81-3470e31fb56d |  | note | Reference - 602.03
label | fd8902f2-623a-5049-bd59-2116b1e7fd5f |  | note | Acceptance Criteria - Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
label | 3d1b5ae5-e441-5597-ad85-2cb9ae18f8df |  | note | Method - Visual
label | c9a04a34-b27b-5ee4-a272-dd393045812e |  | note | Frequency - Where applicable, prior to placing blinding concrete
label | bb8d47ba-53d0-59ad-a9d8-2feada695639 |  | note | Category - HP
label | ccc3c39f-6351-5c4a-8779-c6ed18b814a3 |  | note | Responsibility - Nominated Authority
label | b10a50b6-9e57-5e71-9be1-c2c06a9a93c1 |  | note | Verifying Documents - ConQA Hold Point Release
date | 3d202c56-c644-527c-9f4e-d5eb00295886 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Formwork Design and Construction
label | 6992fab6-91d1-5920-88ee-fe71a370fcf8 |  | note | Reference - IFC Drawings 614.04, 614.05, 614.06
label | dc50f857-58c7-5b58-bd67-9fdd994f2736 |  | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete.
label | 1cae2217-9e6f-5bd6-8b94-9ac62cb1419a |  | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
label | 2fa71bc5-f741-5e4b-b802-6547ef100770 |  | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
label | 32eea5ab-9cb2-5f02-b2a3-9ecf708e64fa |  | note | Method - Document Review, Visual, Measure
label | 4c212454-4e45-5022-a5ca-e5f800f99b08 |  | note | Frequency - Each type of element
label | 0a364115-461f-5c9a-bb93-d9541b18966a |  | note | Category - IP
label | b1764228-e6da-5ec7-b622-200fe7775b6c |  | note | Responsibility - Temporary Works Designer, Proof Engineer, SE/PE/SPE
label | df8fc66d-d343-555a-ab21-42c70601923b |  | note | Verifying Documents - This ITP
date | acf821dc-99bd-595f-a097-f4b764583bac |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
label | e1151143-12d0-5f0f-8b4b-83471f13c246 |  | note | Reference - 614.08
label | 3bc86840-b2c7-5ce0-8aa7-6a61bf691dd6 |  | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | e50801f7-300d-5181-bc0c-72ea905bfff6 |  | note | ○ Walls with heights greater than 2.0 metres
label | 0cbde7c5-9442-50f0-97ef-b2ddae304fba |  | note | ○ Any member for which self-compacting concrete is proposed.
label | 9d840773-ca73-51f0-bf57-6f3579c4111e |  | note | Attach: Attachment A
label | df7cb9cf-a712-5fdd-8332-4a786e2bc334 |  | note | Attach: Attachment B
label | 45970928-51c7-53a3-a999-ac84cb277443 |  | note | Method - Document Review, Visual, Measure
label | 8bf9982a-2f49-547f-8226-ca6a2f3f50d0 |  | note | Frequency - Each element (where greater than 2m)
label | e9a52113-cab1-5616-a61a-e85ad1cfd10a |  | note | Category - HP
label | 405e5502-e915-50cc-8b32-ea426f3fa2ff |  | note | Responsibility - Temporary Works Designer, Proof Engineer
label | 7f6440d5-0110-57d4-b52b-51bc5def21c0 |  | note | Verifying Documents - ConQA Hold Point Release
date | 8e1ad566-dce0-5418-a67d-942b8b7a83ac |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
label | 7fc846b8-83f0-535d-a458-9717630993b9 |  | note | Reference - 614.08
label | 343eb449-d7c2-5dec-bce5-fbabcd3d9ac8 |  | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | 70bc9941-ba5f-5432-8b4d-776ac67fd013 |  | note | ○ Walls with heights less than 2.0 metres
label | 01d8e9cc-7535-5501-af10-feaf5e659b6b |  | note | Attach: Attachment C
label | f33eb1f1-39ba-5c58-99ef-153c7f65f931 |  | note | Method - Document Review, Visual, Measure
label | d260fc5d-fee3-59f3-8981-d7d711d27764 |  | note | Frequency - Each element (where 2m or less)
label | 5f4edf48-b916-5799-b884-ab2beedda29a |  | note | Category - HP
label | 02fc7e83-4813-5e0b-865d-8e2e49d9131b |  | note | Responsibility - Temporary Works Designer, Proof Engineer
label | cb29eb19-fbb1-5b18-b032-fbb8705d34da |  | note | Verifying Documents - ConQA Hold Point Release
date | 1af32547-6d7e-5648-849f-32d7b88402d4 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Pre-pour Survey
label | 82ca1b88-6124-50bc-bc89-9bf2baff9e79 |  | note | Reference - 610.47 (a) Table 610.472
label | 35dc7ea2-ba90-5560-b8c7-16252c71fa03 |  | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
label | cd1a441c-c9ae-519d-88cd-410479ab2722 |  | note | ○ Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
label | de95a010-e6a4-510b-84a4-55d3afa69b7f |  | note | Method - Measure, Visual
label | a86d4634-67f0-54f7-8baf-b2ae3a014671 |  | note | Frequency - Each element
label | 2d82a8e1-d072-5d5d-b909-d990769db065 |  | note | Category - HP*
label | 9d674c77-fe39-5ace-be87-2b71c6c2cf2c |  | note | Responsibility - Surveyor, SE/PE/SPE
label | e48e0187-7e0f-525a-a4e5-064f4a52dae6 |  | note | Verifying Documents - This ITP
date | 695cf60b-766c-5f46-be3c-b24b70de8274 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Reinforcement Placement
label | deb12f6a-7611-5653-8150-1d09167a414d |  | note | Reference - IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
label | b9e008f2-adb0-597b-ae2f-3392b4f814ec |  | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | f0f0a982-18bb-57ab-b5f5-9507d8645d3f |  | note | ○ Projecting reinforcement is the correct length and location.
label | 26065dcc-57ac-5aca-b0f4-c63c1dbed064 |  | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
label | 99c7009a-e59e-5e8f-9c50-4969adbc7adf |  | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | 565d1e09-369a-5ff6-bf87-bc6501516c56 |  | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | 0d4ead09-bad7-5781-b1e3-c6e7b92bfe35 |  | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | 677af706-807a-5e99-be85-8f7d35a1ef30 |  | note | Method - Measure, Visual
label | 774bff88-b2c1-54f2-9f5e-84cb2e2c0739 |  | note | Frequency - Each element
label | 6f446826-98a3-5b23-a4fe-63aef42a1735 |  | note | Category - IP
label | 780cdf86-a958-5f1b-aeb2-c5856fc52a1a |  | note | Responsibility - Foreman, SE/PE/SPE
label | e0076e08-9e7a-53c0-a8a1-79b3086a1191 |  | note | Verifying Documents - This ITP
date | 47f6e7fc-7dbd-544e-8159-0c1e72273cad |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Cast-in Items
label | a4d7cf9e-9de1-5917-b256-589917818501 |  | note | Reference - IFC Drawings 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2
label | de0da661-529d-58c8-a4f9-24e164b3ec8e |  | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | 086eaaa1-b6ed-5283-9ee4-4ecd9d47c117 |  | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | 27d14032-5c08-582d-bf2e-f1d1109490bb |  | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | 22934175-cca8-5bdf-ad32-3f8628dd813f |  | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
label | 2c186d2c-d61d-5cf8-9571-566e23cbe6ef |  | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | 50af0a90-4e70-55d9-b429-50b8f442ec3f |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | 6d8b7121-7f89-5030-bfa8-26c5d2470166 |  | note | ii. Running dimensions of a group of the above = ±6mm
label | 387e02be-109c-50d4-9c56-ab7d8667235a |  | note | iii. Ducts and conduit location = ±12mm
label | c0e2ba68-b1e1-5dd8-baac-b41d9c919de4 |  | note | iv. Diameter of ducts and conduits = ±3mm
label | ff1d88b8-006e-57f4-8ed4-dea959cfa19c |  | note | Method - Measure, Visual
label | 1e0128cb-047c-567e-b220-e5b46a06abf7 |  | note | Frequency - Where applicable, each element
label | fffe0ba9-50a9-5ed4-8138-2973b9c0d3a3 |  | note | Category - IP
label | 9d986076-e3ce-5c4f-8b84-7506c32b13c6 |  | note | Responsibility - Foreman, SE/PE/SPE
label | f5f63297-6ba8-5598-9c78-bf3184f4698b |  | note | Verifying Documents - This ITP
date | 275c07bd-c852-5234-9b91-77e023db73d9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Thermal Differential Monitoring
label | 397735ac-941d-5b40-82aa-c7968ceed093 |  | note | Reference - 610.22
label | 910bde99-0cb0-51b0-80b4-d1939c97f24a |  | note | Acceptance Criteria - Thermal differential monitoring thermocouples installed.
label | f4685eff-d330-5ac0-b872-4924d1f55d67 |  | note | Only applicable if the element has:
label | bf230c6e-b9ee-59c6-be4c-c9297890a64a |  | note | i. the smallest sectional dimension exceeding 500mm
label | 635a1951-6bbf-5ed2-be96-c2d77bf1730f |  | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
label | 2b69b6c0-0769-568e-914c-35c8280c2729 |  | note | Method - Measure
label | 76e67f84-591d-5d88-a630-f7af27b8b880 |  | note | Frequency - Where applicable, each element
label | b780ff0d-6f4f-574a-b854-63fa92181f39 |  | note | Category - IP
label | 7ab19ff9-4bad-5ddf-bb48-f1709aaad098 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 150bd8eb-7c56-5b13-97a7-39e69a42242d |  | note | Verifying Documents - This ITP
date | b4b43339-fae3-5681-a569-e0e2f2cd9bbf |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Pre-pour Inspection
label | d06ab918-50f1-5e75-9176-43f07b153979 |  | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
label | 3bfa1b03-a7ca-5bc6-b77a-9b56603b345a |  | note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | 25a3af25-2f5c-5b2c-9a2f-d12a648b05b3 |  | note | ○ All foreign material has been completely removed from the forms.
label | a0415887-23ee-5026-952e-5f25dd20cd4d |  | note | ATTACH: Pre-Pour Checklist
label | 8b1df1ce-4c47-5a2f-a15e-6897aa90327d |  | note | Method - Measure, Visual
label | e2894fde-6936-52ef-b6c4-10f5c47d7b87 |  | note | Frequency - Each element
label | 59f31472-618e-5a5d-aad8-5f819f60986f |  | note | Category - HP
label | fa14fadc-5063-539f-9292-c6e5c54fa337 |  | note | Responsibility - Nominated Authority
label | 09aa7ab0-2888-580d-8dda-257d113a0d26 |  | note | Verifying Documents - ConQA Hold Point Release, Pre-pour checklist
date | 5f8440eb-74f5-51ce-80af-7e28659f4afc |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.9 - Weather Conditions & Evaporation Limits
label | cb3be6fe-0efb-5bb4-b5b3-25a9791b2a08 |  | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
label | 08060fb9-e746-5068-998b-4474d18fee38 |  | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | ff9ba82f-7ecc-53f9-8aa7-c57e8ad2e6bd |  | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | f71b56d7-ae8e-5302-a92e-c2fd79089907 |  | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 50cf4f19-659b-591b-92bf-cf1be29a0138 |  | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | 819b53d1-d113-5b6a-8e04-263c5975e50b |  | note | Record: Required information on the Concrete Pour Record.
label | 8e3ff3c9-6a6b-58a0-ba12-e9a20820dd82 |  | note | Method - Measure, Visual
label | a68c298b-2d4e-5ef2-aa9c-a15b06bc43d9 |  | note | Frequency - Each element
label | 863f5644-0fd5-5cf5-8fe9-c0c897edf891 |  | note | Category - IP
label | c5ac1501-d470-5b53-a879-ce7081c13693 |  | note | Responsibility - Foreman, SE/PE/SPE
label | d2b2a2f8-380d-59f0-bdcd-64d0e32a448d |  | note | Verifying Documents - This ITP, Concrete Pour Record
date | be085f5e-c691-562b-9ab0-574e81097714 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 - Concrete Testing - Sampling Frequency
label | 4ad2afdd-1f90-5b3a-9d86-f0aa25ccd1d0 |  | note | Reference - Site Sampling & Testing Procedure 610.16 (b)
label | c962228a-40e4-5d14-a24d-e24c5e3ffcc0 |  | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 02a00e98-0feb-56bd-b008-207b3713f4f4 |  | note | 0m³ to 10m³ = 1 sample
label | 92af27fe-36c4-5f08-a77f-a1a3f43d9b86 |  | note | 10m³ to 25m³ = 2 samples
label | 5ca6740e-d399-566a-a8dc-f823c626ac19 |  | note | 25m³ to 50m³ = 3 samples
label | 20d0c58f-3c65-5be1-92e2-87303eda064d |  | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | aebe5f9f-fc03-56ec-90e1-db4186d27fcc |  | note | ○ For each additional 50m³ and additional sample shall be taken.
label | c2c359ba-781e-5f33-9496-b84b66a12356 |  | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | 0682f843-6fad-5dab-8f53-614616fcb8ed |  | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | 6de72ba8-822a-5c10-a96c-9368407b94fb |  | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | 94197f89-6929-5a19-b036-ca5306922f3f |  | note | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
label | e696e884-27de-5951-817f-30c45ae6ac66 |  | note | Record: Required information on the Concrete Pour Record.
label | 7b132439-ebf7-52aa-9b2e-28e81af49494 |  | note | Method - Test
label | 7fab640e-e381-52ca-b692-543d8defd33e |  | note | Frequency - Each element
label | 84d7372e-839c-5d28-8624-222adfdfeb50 |  | note | Category - IP
label | 665e0fed-6445-5835-9194-0302b4c89681 |  | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
label | 07ad0d22-9ee7-5624-8ade-684fc69f60c8 |  | note | Verifying Documents - This ITP, Concrete Pour Record
date | 0213828d-8336-55e6-9113-ed217596084b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 - Concrete Testing - Slump
label | fb24c2fb-c477-5774-8b70-13fe4366957d |  | note | Reference - 610.16 (c)
label | 948bffd2-6986-5fa0-a668-086b7523d200 |  | note | Acceptance Criteria - Slump testing tolerances =
label | 5c5d4cf4-77d4-5cc2-8155-d237cb8a825d |  | note | <60mm = ±10mm
label | 357be78f-14c6-5039-a5ec-eeecff4eb5b4 |  | note | ≥60mm to ≤80mm = ±15mm
label | 9db45a0e-7582-5dae-ae4b-a1d02708065d |  | note | >80mm to ≤110mm = ±20mm
label | 85941b4e-2640-5d0c-bf29-8224d358343e |  | note | >110mm to ≤150mm = ±30mm
label | d83eeb38-aa4b-501a-b8e2-a82bd81663d9 |  | note | >150mm = ±40mm
label | 99901afc-b24a-57d0-a54c-1dc897f1ae56 |  | note | Record: Required information on the Concrete Pour Record.
label | 8942ac95-5e16-5bfa-a650-a5ff640f8d2a |  | note | Method - Test
label | fc87e65a-0270-5915-b745-181f1e50de6d |  | note | Frequency - Each sample of Standard or Superplasticised Concrete
label | 0010d650-9bfd-5a0f-8994-41810f5a1ad4 |  | note | Category - IP
label | 8df1c006-5799-587c-b5ba-00b6e4e081b7 |  | note | Responsibility - Concrete Tester
label | 368dc4bd-158f-568d-95a0-d4c7eb23c9a4 |  | note | Verifying Documents - This ITP, Concrete Pour Record
date | 96fee3a2-f6d2-54fe-85a0-bfc060f4909c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 - Concrete Testing - Spread, Passability & Viscosity
label | 9bda63d0-8ade-5e9a-add3-f71514472598 |  | note | Reference - 610.13 (b)
label | 318237df-1f37-5bde-8b19-76a9f23a352c |  | note | Acceptance Criteria - Spread range = 550mm to 750mm
label | ea60c3bc-0812-5036-aadf-41d89bb63fb1 |  | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | 6dcece7b-eb6c-566c-b83b-4f986ed1ff7d |  | note | ○ Passability = ≤10mm (aggregate height differential)
label | 5e8ce836-41cc-5591-8341-21e5d9f5d2ad |  | note | Record: Required information on the Concrete Pour Record.
label | bc201295-5c10-5032-8f59-6aaeab0ded37 |  | note | Method - Test
label | a80b0f59-1852-5c8f-87cb-1948ec25647f |  | note | Frequency - Each sample of Self-compacting Concrete
label | 558cd712-7d5b-53a5-adc3-22604cba7c7e |  | note | Category - IP
label | 8f241bed-8f22-5058-a6be-3e74726b6de6 |  | note | Responsibility - Concrete Tester
label | f1214410-0e2a-55c0-b69f-24246da0ed16 |  | note | Verifying Documents - This ITP, Concrete Pour Record
date | 9c5abe86-563c-5691-a8af-1ba32eef4590 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 - Concrete Testing - Compressive Strength Cylinders
label | 063de718-2cda-54d2-9820-9a0ff689bac8 |  | note | Reference - Site Sampling & Testing Procedure
label | 863d64eb-9444-5271-a746-cf4acc85b3a3 |  | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
label | 78eb0c1d-98d5-5fc2-bf27-3b153fe017d5 |  | note | Record: Required information on the Concrete Pour Record.
label | a371f7a1-6334-51f5-bb35-73ac4be1a66c |  | note | Method - Test
label | 42f7d305-3201-5ac6-8a43-3b5f0cf0af1f |  | note | Frequency - Each sample
label | 4e6f79f2-1430-5186-b3b5-325fd0094776 |  | note | Category - IP
label | 54e1ad28-32ff-50ee-bb51-3fd2f3abd2e5 |  | note | Responsibility - Concrete Tester
label | 9547cb4d-2067-5fde-b911-86f9e2bf9664 |  | note | Verifying Documents - This ITP
date | 80f31e03-672e-50e2-819e-ecf9f4ca4bdd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 - Supply & Discharge Rates
label | 7335262d-8603-5d64-87a9-8006e1bbb4ab |  | note | Reference - 610.13 (a) & (f)
label | 4d674a14-ca76-58e4-bea8-515dd92ac63f |  | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | ebd153f9-3a47-52e2-a2f4-9a6222ff8e86 |  | note | ○ No water is to be added once discharge commences.
label | e55b380e-5e8f-535d-a8d6-eeddcec20879 |  | note | ○ Maximum time between batching trucks is 25 minutes.
label | 453ccce0-d4a8-543e-a8e2-9348a19bfc69 |  | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
label | ec1fd5e7-6d6d-57e7-84d2-32cbca3c89da |  | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
label | c8a3ff8d-10d6-50f5-bdd6-11fe3696bbd3 |  | note | Record: Required information on the Concrete Pour Record.
label | b6154554-e649-5987-a2b1-2b0fbf7545e6 |  | note | Method - Measure, Visual
label | 5554939c-abf0-5d32-bf63-16fe689a52fd |  | note | Frequency - Each load
label | 0d129dea-9024-52de-ac63-415e4c65ff6e |  | note | Category - IP
label | 1ee61008-7499-56fb-b8e5-6e419af92686 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 94dd52ac-12df-5410-aac7-642feddb55c7 |  | note | Verifying Documents - This ITP, Concrete Pour Record
date | 283e92e5-bbe5-52b4-8c79-b156db9c44ce |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 - Placement & Compaction
label | 8e1e9b65-83c9-57b4-a3d6-2765d295fd9c |  | note | Reference - Placement & Compaction Work Procedure 610.18 (a) & (b), 610.18 (d) (i)
label | d99fd762-3e51-527f-bfdf-60cc4962cd87 |  | note | Acceptance Criteria - All concrete batches are traceable.
label | d8993057-103c-5d49-8b49-414aeeadfd7f |  | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | e5abd859-b5e3-59e2-b1a4-bd8a81d23922 |  | note | ○ Concrete is not dropped freely from a height exceeding 2m.
label | 10ff67d6-2735-50bc-bd1e-701901d11d49 |  | note | ○ Concrete is not moved horizontally by use of vibrators.
label | 3d320554-2deb-5d09-80de-bf3219d4a6a1 |  | note | ○ Adequate compaction is ensured
label | 3f51e5c2-0e63-5803-be64-dd825c533387 |  | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
label | 5254aa8a-25db-5f3a-bba2-32d8ac476bbb |  | note | ○ Concrete layers are not more than 350mm
label | 003f75ec-dc00-5cb5-a616-3b21ee32f9f9 |  | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
label | 91870db5-6acb-5c63-bb5c-0214a8973069 |  | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | d3a667ba-944a-58f5-9f86-c5fb83b45160 |  | note | Record: Required information on the Concrete Pour Record.
label | 15b90f95-9259-5adf-bdd9-0bc11fea00d0 |  | note | Attach: Concrete Pour Record
label | f3e54e65-b9e3-51fb-8af1-9b7e31570e44 |  | note | Attach: Concrete Dockets
label | f21ddfca-5292-5352-87b3-06476ac3cc4d |  | note | Method - Visual
label | 90bf0f99-fe51-5948-8009-5e6c73b5333b |  | note | Frequency - Each load
label | 9ac93b9f-ee5d-59d7-a62f-d8c3933dc9d7 |  | note | Category - SP
label | a0827916-e68f-58ab-84ee-d75c64407f17 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 7bc9cf34-fe19-5295-9cb6-11c2eb4a0531 |  | note | Verifying Documents - This ITP, Concrete Pour Record
date | bf73b4ce-bf10-52f9-ae4f-45302bedad55 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 - Surface Finishes
label | c2f4f34a-01c1-526c-9729-430a9cb6d329 |  | note | Reference - IFC Drawings 610.31, 610.20
label | a5130cd2-c6d7-5958-83eb-de9d1145bff1 |  | note | Acceptance Criteria - Surface finish as per IFC drawings.
label | 29cd02fc-8c56-5a12-8249-a0b65b7e575f |  | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | 24fce402-2638-5243-ae1b-1328ba040ed3 |  | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | 707bd167-02dd-50b8-b741-8e4f39787cf2 |  | note | Method - Visual
label | ef2261d4-c6a3-5540-a341-6f0525da5b9d |  | note | Frequency - Each element
label | cee6fc5b-b6d9-591a-b6e0-b91ff32a6f79 |  | note | Category - IP
label | 7aa5369a-bfaf-5b59-bb22-76720c8c7e8f |  | note | Responsibility - Foreman, SE/PE/SPE
label | d4098df4-5092-5003-b494-19d59f20523e |  | note | Verifying Documents - This ITP
date | 6c95a393-a515-5d37-814a-11195890b97e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 - Curing-Top Surface
label | 8d0a0cc0-55a5-508c-8ada-c15d12dd8940 |  | note | Reference - IFC Drawings
label | bad83a98-5d8c-5015-b463-3f1ef75c57bc |  | note | Acceptance Criteria - Top surface of the pier and abutment walls shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pier and abutment walls may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
label | eefac5ca-e123-50fe-b81d-fbb873196d32 |  | note | Method - Visual
label | c686c905-d612-5d99-bde5-eef1736fc035 |  | note | Frequency - Each element
label | d3674589-e6c2-5980-a854-595cd4926269 |  | note | Category - IP
label | 74261da2-4dde-5e88-b798-07209b84a1c9 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 6182e521-d5f3-56c5-8e3f-101d56efb4bc |  | note | Verifying Documents - This ITP
date | ecc7bee0-daaa-52f7-b889-e759082f1d27 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 - Curing after formwork removal
label | f69680aa-6d4a-51c5-a1bf-b9da4976a09a |  | note | Reference - IFC Drawings
label | e9c727d1-9627-55c0-adf9-feb295082aa5 |  | note | Acceptance Criteria - After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
label | c4b02c50-9770-5279-994e-339e517ed6c7 |  | note | Method - Visual
label | 8d75b0c0-7bc9-5f2f-b752-4e82aa99d228 |  | note | Frequency - Each element
label | 97025ec5-fcfc-5622-892e-f0f80c88d6c8 |  | note | Category - IP
label | abd1775e-b613-5c14-bbf0-ddb96d16f282 |  | note | Responsibility - SE
label | 8c266d3c-5201-58e8-b658-6fb1361bda1d |  | note | Verifying Documents - Thip ITP
date | 8a88867e-aafe-5b1f-8184-140e0c4f7f5b |  | date | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Thermal Differential Monitoring
label | 80eebdb7-43ca-5a9c-a2c9-1668ff3fb56d |  | note | Reference - 610.22
label | 8165a423-0566-56f0-a581-0bff214f729a |  | note | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C.
label | 4810ae44-5637-55b6-afba-91bfa71f70ae |  | note | Only applicable if the element has:
label | ff6d7f73-ed5e-58b7-ba55-35826ef27c21 |  | note | i. the smallest sectional dimension exceeding 500mm
label | ae5798a8-b4d2-5d04-8bf0-9b59ff50875a |  | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
label | bab713ff-1c25-5879-8b10-f05be62ad4df |  | note | Attach: Thermal Monitoring Report
label | 2e805cd2-d14b-5ac8-9e44-c721f4956890 |  | note | Method - Document Review
label | 208d0c2a-2ea2-5db2-bf41-639a344d3e16 |  | note | Frequency - Where applicable, each element
label | 95f2572a-5abb-586d-abae-416c73ac5111 |  | note | Category - IP
label | 2679f548-e358-55f0-b601-e75cbaf1d212 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 2a7d40b0-1fb3-502d-bd51-aa9aefbd91f3 |  | note | Verifying Documents - This ITP
date | d43d66e2-4e91-5976-8192-de94b9649440 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Early Age Compressive Strength Test Results - Removal of Formwork
label | 82297998-d225-5be6-9d08-bde36dfdde70 |  | note | Reference - IFC Drawings
label | 1232cf2b-36ed-5382-9e8b-dec9367a1634 |  | note | Acceptance Criteria - Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
label | 172242ac-03f0-5774-a31c-215af8fb6bd4 |  | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | cd3a09e8-cd6c-5380-88e7-7485cd301f46 |  | note | Method - Document Review
label | 5b4b6084-3e12-5805-b2ed-cf6f3182a247 |  | note | Frequency - Where applicable, each element
label | 5f3efa09-70d0-5b95-ba01-760dde92c6f4 |  | note | Category - IP
label | f7164271-a7c5-5bcb-b927-a1393eb927a7 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 93f702cb-2e01-5c2d-b8f8-51cda0499ccd |  | note | Verifying Documents - This ITP
date | 87fdff22-0d6a-516c-a383-b03c15d80c09 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Surface Inspection - Cracks
label | f60a97bf-c945-5151-8967-63c068e16538 |  | note | Reference - 610.24
label | 47bc89ca-8557-5808-95bd-c71e90d13950 |  | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1)
label | 0fc8188b-b98d-5445-8208-463ab143782a |  | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | e1d9fe28-2d8e-5ecf-bf2e-61bdbbdcd64d |  | note | Method - Visual, Measure
label | ec4d7096-b630-5ee7-8c78-ccf8fbac598e |  | note | Frequency - Each element
label | 0bf06c9b-746b-55be-9d93-3021d4cd3e51 |  | note | Category - IP
label | d1a46fe3-96ac-537f-88c2-3e68d48d3fe8 |  | note | Responsibility - SE/PE/SPE
label | 3bb14dfa-9c82-5d6e-ad93-69ef41d4dabb |  | note | Verifying Documents - This ITP
date | 41c81185-9838-5345-b6fc-9b6482b7a233 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 - Surface Inspection - Surface Finish
label | 4da581e9-cfb0-5375-a097-84362cbb8b7f |  | note | Reference - IFC Drawings 610.31 (a) - (n) 610.32
label | 78997794-01d3-570f-8960-49d1e9370ead |  | note | Acceptance Criteria - Comply with the IFC drawings and specifications.
label | f5082051-b67f-5a7c-bb07-6284ab5179c0 |  | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | 780b9b73-a5b7-50b6-8f2d-34e43170306b |  | note | Method - Visual
label | ba0ddd49-ac6b-50db-802e-8b9cb6544029 |  | note | Frequency - Each element
label | f6195762-893f-5b43-867b-9c722786cdb3 |  | note | Category - IP
label | ecd5548d-9ba8-5e52-8ff8-293ad12c9337 |  | note | Responsibility - SE/PE/SPE
label | 57618440-3400-5466-becb-2326706510e5 |  | note | Verifying Documents - This ITP
date | 9f91df0d-5e0a-520d-9f65-33dbb3cf76ee |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 - Measurement of Concrete Cover
label | 5541add6-8343-55da-80c9-84bdf2645d32 |  | note | Reference - 610.34
label | 9e27ad70-4418-5ff8-8cf1-b431da9e91bd |  | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
label | 683d06d4-b072-570f-bf80-79f0493a0b00 |  | note | ○ Minimum 10 no. measurements recorded in each area.
label | 7074cae0-c04c-5aef-b162-d95c9c045b35 |  | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
label | 63b703fc-d1d4-5d07-bac8-82c82b6d6e5c |  | note | Attach: Covermeter Check Record
label | dbe34793-6ca2-50b7-a25c-178f25552b8e |  | note | Method - Measure
label | c4ae64c5-4b60-5f70-90d1-0eeef70e41ee |  | note | Frequency - Each element
label | d3da17db-e652-5a4d-88b8-5a0eeaf88434 |  | note | Category - IP
label | daba4809-869e-5c42-84c5-ce1856a4a541 |  | note | Responsibility - SE/PE/SPE
label | e0e65985-aa6b-5b8e-8c23-f3cf50419a95 |  | note | Verifying Documents - This ITP
date | 2969845c-f5c2-59f3-8055-15ef47270ee9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 - Early Age Compressive Strength Results - Placement of Fill Against Concrete
label | 2f8306f9-d9df-5dc3-9cfa-0cc6cf767d74 |  | note | Reference - Early Loading and Trafficking of Decks and Approach Slab Procedure 610.35
label | 2960618a-c208-5c6c-b67a-26b358cc1366 |  | note | Acceptance Criteria - Fill is not placed against concrete within 14 days of pour.
label | 0202a066-cdb3-53d9-81c7-0af7bd394218 |  | note | ○ Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
label | 9f921509-b1e3-5f15-9cba-4321d69751eb |  | note | Attach: Concrete Test Results or Maturity Test Results
label | 8413bf00-512c-594e-a447-39ec5ebab5b1 |  | note | Method - Document Review
label | e86794a7-5fbb-57c0-9d71-65814fc6691b |  | note | Frequency - Where applicable, each substructure element
label | 282f84f9-a6ab-5809-bb70-3946de3b5fd1 |  | note | Category - SP
label | bdca7e56-433b-5f98-a763-11e3b74fda41 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 6579b3a5-71d6-5f2f-b6a6-61131bd3cbea |  | note | Verifying Documents - This ITP
date | 90cb266e-d217-5e9a-889b-e960755399a9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 - Compressive Strength Test Results
label | e0f4bc45-292e-5dbe-be28-7f5f5a997eb2 |  | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
label | 3f64b684-fe4e-533e-b0c8-657f86a13768 |  | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | f63c5b92-43d5-50de-8c0d-3aa1f14ad48a |  | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | a0876829-e1c4-5029-ac8b-6e731939d8b5 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | da4f064c-422f-52c3-9325-f39452faea91 |  | note | Attach: Compressive Strength Test Results
label | f383909c-919e-5774-bda9-1a90c516ce8c |  | note | Method - Document Review
label | 05d394d4-c2ef-55e8-917d-bcc5f18ea216 |  | note | Frequency - Each cylinder
label | d33ab4b3-2261-5451-8914-23558a93450d |  | note | Category - IP
label | edf9b540-a936-5511-b7de-b32ac3a64dd3 |  | note | Responsibility - SE/PE/SPE
label | 8aa98d85-f73b-5987-848a-b78ca35980ba |  | note | Verifying Documents - This ITP
date | 75ca58b6-3aa3-5fa7-bd85-4f835de93271 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.8 - As-built Survey
label | 9db57ddc-f047-508a-82a4-ff4231cd12b1 |  | note | Reference - IFC Drawings 610.47 Table 610.472
label | 26d62b63-9eda-5b17-808a-cf5f39a91d1f |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
label | f84701b1-c18b-51e3-9d4f-084f24367d14 |  | note | Attach: Survey As-builts / Survey Report
label | a7b81fff-e6e4-5db4-ac1e-aedfbe3e5fbf |  | note | Method - Document Review
label | af40485f-35b7-5636-a991-4a7dc3c36e26 |  | note | Frequency - Each element
label | 0dec67f9-b1a3-5317-b3ba-d63f80ebba6c |  | note | Category - IP
label | 3761847d-9c0a-55a9-a8d0-1e0fccab30f9 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 61be9adb-a3f3-50c1-b0af-11bc06d772cd |  | note | Verifying Documents - This ITP
date | 695a3189-96db-5a8b-9c91-aa90a30597da |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.9 - Non-conformance Report (NCR) Closure
label | d8452e65-edf5-5d82-97fc-84c366a3fce0 |  | note | Reference - MRPA Quality Management Plan
label | a782ab54-e1b5-5f4e-b0f7-053f8dcc23b0 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 8121c4f7-0b55-51f3-b70a-5471c061b0c3 |  | note | Method - Document Review
label | c9d3b1ee-f639-5af0-adff-38fc9546f689 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 7c4740ce-f2b3-5b9e-968f-30aaf0987623 |  | note | Category - HP*
label | ee704a48-08b2-521b-a9f0-2b294a564801 |  | note | Responsibility - SE/PE/SPE
label | 7083280b-6284-5d5f-9ede-632b2764194b |  | note | Verifying Documents - This ITP
date | 6645cbec-7345-55ce-ad58-042479e64d01 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | f36e5999-b796-5e9e-88e9-0ddc5b2fdc33 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 15277e10-5889-53b3-90f5-fe4922615102 |  | textbox | Name:
text | 6c88b4e4-c408-56dd-b217-65f693ea5198 |  | textbox | Position:
date | 285d6882-d8fd-5434-b76f-8f7c75cb31b5 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-124-STR-CPD-Precast Super T Installation | itp |  |  |  | Yes | ITP-124-STR-CPD-Precast Super T Installation Rev 0 | 40e3383c-b5b9-41c5-af93-683f05f9e2b2
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 4e30ad57-09e3-5e2c-bc5c-025e8c844cda |  | note | Document Title: ITP-124-STR-CPD-Precast Super T Installaton
label | 20326507-7fe6-5b88-a232-3a6eb3c1ed5f |  | note | ITP Description: CPD-Precast Super T Installaton
label | 4a9740f1-bb31-57b8-9195-ba7e4707cbb0 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 1bc452a5-8f7c-5229-abc5-b8d126f233af |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 46b2e39d-5ce9-56c7-96ea-4392e7a2494b |  | note | Revision Number: 0
label | e194c0e6-ecd4-53c6-9ddc-2b6ff85a9335 |  | note | Revision Date: 19/01/2024
label | 2410c9db-e37f-5df1-b0b4-19b4679b2ae1 |  | note | ITP created by: Andrew Carlini
label | 82bb3bf5-2e76-5a34-94d0-63c3e40edd65 |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | c20badeb-fdd3-5216-b9ab-fc02e144a73f |  | note | Reference - VR 652 June 2010
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | d79e449d-31db-515f-b339-c3d2104979d0 |  | note | Reference - VR 656 June 2010
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | 49f7c010-6c9d-5304-8f7e-484d67d19cda |  | note | Reference - VR 610 February 2020
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | 92c1c9d4-d1c9-5be9-b376-3f0cc003990f |  | note | Reference - VR 620 May 2009
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Epoxy bedding
label | 43116f19-e9e9-5104-874f-97b2b4783900 |  | note | Reference - IFC Drawings
label | d4ac5f06-cc34-54cb-b1e8-bd9157daeae0 |  | note | Acceptance Criteria - Product to be selected based on the following criteria:
label | 708d6335-11e1-50c6-a65a-1919b9bd843b |  | note | i. minimum compressive strength requirement as the Expoxy beeding is used to ensure the taper plate fullyengaes with the Girder.
label | 00ab7680-86c6-5d19-876b-752635c1619b |  | note | ii. Can be applied in IFC specified nominal thickness (1mm)
text | 84715a2e-b8dd-59ee-b04a-e33598b97f31 |  | textbox | Enter: Teambinder Material Approval number
label | 96202eb2-cb05-5fc6-ac12-e9808093e22d |  | note | Method - Document Review
label | 9ea8e314-2b37-5b29-91cf-fbdf95c2235c |  | note | Frequency - When applicable
label | a4ce9e78-e682-5eb4-998f-334c7907e39c |  | note | Category - HP
label | 63a35460-55fc-5dbe-adc1-ac5583286e22 |  | note | Responsibility - Nominated Authority
label | c42a213f-6459-574f-b975-50f71c5dd204 |  | note | Verifying Documents - ConQA Hold Point Release
date | 65a5bab0-f45e-57fa-b505-ed77fee3cf25 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Bolts
label | f34a31c8-6fc7-5be2-b50f-0adebfc2dda2 |  | note | Reference - IFC Drawings
label | ef80bfd3-db68-5002-8263-b5bd641f9326 |  | note | Acceptance Criteria - M16 property calss 12.9 Zinc Coated countersunk socket cap screw
text | b0c66f1e-f14b-5fb4-b6ce-e8dad737db84 |  | textbox | Enter: Teambinder Material Approval number
label | 11c4270c-f740-5ceb-b25f-2353f76960f0 |  | note | Method - Document Review
label | d92afa3c-ab12-543d-b5a8-23c84786bcae |  | note | Frequency - When applicable
label | c887a6c9-76ad-561b-8cca-f8c95233cb93 |  | note | Category - HP
label | 7d224455-55f7-5a51-a3cf-3e9eb09e49d6 |  | note | Responsibility - Nominated Authority
label | 29276b7e-05ff-5708-b244-c5a06626f961 |  | note | Verifying Documents - ConQA Hold Point Release
date | 52097e09-0158-5247-8971-7fc7592c69fc |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Precast Elements
label | f8736d9a-4c9d-5049-93e6-0db8d4b1a446 |  | note | Reference - IFC Drawings 610.47 (a) Table 610.473 (Feburary 2020), 620.03
label | 2ba94a44-68a5-5b01-a611-f9ef36d12fc1 |  | note | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | f66bfaee-f48f-5787-9785-ed31fa407499 |  | note | i. Certificate of Compliance / Birth Certificate
label | d32f8106-6e11-5894-9d77-a4d554eeaf80 |  | note | ii. Compressive strength test results
label | c86abbfb-dd77-52f1-93ad-5252f2a70d38 |  | note | iii. Precast Lifting Design
label | 49c14a80-e8df-53a9-8552-bba1daa0a20c |  | note | iv. Pre-pour check sheet / ITP
label | 76507e9c-eb20-5905-a236-326dd7550fdb |  | note | v. Pre-stressing check sheet / ITP
label | a9c25dc7-7a04-5025-801a-022f632472fb |  | note | vi. Post-pour check sheet / ITP
label | bbc0622f-0b1c-50c8-b54e-3efd9bcad0d8 |  | note | vii. Covermeter check record
label | 0b391110-141f-5b09-8ef2-3b4c626974b2 |  | note | viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates
label | 4a9cf96f-aa95-5b7d-984c-a9e516c57b86 |  | note | Note: Different revisions of 610 have different clause numbers
label | 45762fb1-73bf-5e51-87f7-b0305de38564 |  | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder
text | 19ad5f38-739a-5c87-95df-f5cb5c4a4c79 |  | textbox | Enter: Teambinder MDR Lot number
label | c845fe18-f658-5342-b493-613e39335f21 |  | note | Method - Document Review
label | c4cf0f46-5d7c-551e-8f6b-07326f2aa654 |  | note | Frequency - Each element
label | 539cfce9-1fb7-55c8-b3ba-ae4a549d45b7 |  | note | Category - HP*
label | e72f3919-9f89-58da-ada0-0944baea92d4 |  | note | Responsibility - PE/SE/SPE
label | 05415a6b-b833-5c08-9dc9-9563b391225d |  | note | Verifying Documents - This ITP
date | a14fd5ee-b5be-5275-97df-d41c56fce610 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Elastomeric Bearings
label | 954af94f-d711-56b5-8552-375bf4471bc6 |  | note | Reference - IFC Drawings 652.02, 652.03, 652.04 AS5100.4 Appendix C and D
label | 2cb3ab83-0033-5ea6-9335-d68268bcfee0 |  | note | Acceptance Criteria - Elastomeric bearings are to be manufactured to the requirements of the IFC Drawings and AS5100.4.
label | e68c632d-40b0-51e2-af61-94c814f230f3 |  | note | Tolerances:
label | 5fcf271e-ed0e-5d57-b2ca-d6b7ff38a151 |  | note | ○ Dimensions in plan = +4mm, -2mm
label | 1a7f2b9c-fb06-50fb-9e63-91b39f526a00 |  | note | Thickness =
label | dcbdd342-61b9-58af-b755-52ff1229dd1f |  | note | ○ ≤100mm = ±2mm
label | dcf87b9a-eecf-5b11-a3e3-88b59c691fcc |  | note | ○ >100mm ≤ 150mm = ±3mm
label | 59af6d3a-afad-5f74-8f02-34c3ee90b173 |  | note | ○ > 150mm = ±4mm
label | bbfa9a71-a496-5ec2-9e3b-5e348c185e12 |  | note | Testing:
label | f7c03baf-adf1-54fb-bd57-69da01abdbb0 |  | note | ○ Each bearing tested under compression
label | 6ee0ff99-dd7f-54fd-b6ff-a57d7aac6838 |  | note | ○ Batch tested for shear stiffness
label | 7595462a-dd71-5250-bf4f-474becc1d405 |  | note | Attach: Elastomeric Bearing Test Reports
label | d1bb83ed-90ab-56fc-aaf9-0e5a57fe8558 |  | note | Attach: Elastomeric Dimensional Records
label | 65b64446-28b3-589b-8084-7f0dfca04251 |  | note | Method - Document Review
label | 6b84ef73-ca43-5c5b-929f-eddf574e1790 |  | note | Frequency - Each element
label | 3cf1c858-cbca-56ea-80d4-61be871f146e |  | note | Category - HP
label | 39f8dc45-4b29-540a-8303-e5f4910caff5 |  | note | Responsibility - PE/SE/SPE
label | 7b40b088-ab9d-5937-8f3f-729793baebbc |  | note | Verifying Documents - This ITP
date | fa6ee6cf-9b04-5482-9637-8342598db676 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Tapper plates
label | e0f2aa94-548b-50e9-ba38-8ca9ba85af1c |  | note | Reference - VR 620.05
label | 892bb7cf-ec63-5db8-b229-390d627a26e8 |  | note | Acceptance Criteria - Material for sole plates and bearing retainers shall be of structural grade steel complying with the requirements of AS 3678. All surfaces and edges of sole plates shall be finished smooth and bearing surfaces shall have a maximum out of flatness of 0.4 mm.
text | 4ec2db97-ffef-564c-8948-05e5599ab463 |  | textbox | Enter: Teambinder MDR Lot number
label | 0a5a7489-915f-5689-95ae-ef3f91b9b523 |  | note | Method - Document Review
label | 5e2326b5-a4cd-573d-b886-04db39420783 |  | note | Frequency - Each Plate
label | 08e002af-cfb0-5fc8-849b-eca20b3ed0c1 |  | note | Category - IP
label | 06c981ed-f218-5e15-9090-95d370ab0841 |  | note | Responsibility - SE/PE
label | 641fa1df-42a8-5e8b-822e-e7611b4eed45 |  | note | Verifying Documents - This ITP
date | 77669dcb-4c33-5207-9430-8ea9d709e42a |  | date | Date Completed:
checkpoint-group |  |  | section | 4. Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Bearing Plates-Check
label | b3ed7087-1b8a-582f-9d7b-bcb2dec9f29a |  | note | Reference - IFC Drawing
label | 8e0fd19c-ed03-5875-9c25-6a6b21ec4b66 |  | note | Acceptance Criteria - Bearing Plates shall be inspected after fixing to girders and prior to the erection of the girders.
label | 122b2fb8-171d-513e-8abd-539ebd6c807e |  | note | ○ Ensure the plate and plate orientation are correct
label | 1eac4ebe-9870-56cb-afd2-f75097fd31af |  | note | Method - Visual
label | 58695601-1c58-5f9b-ae58-56c40378fecc |  | note | Frequency - Each Tapper plate
label | 88de9300-5bb3-5267-bc91-c385e3bf4327 |  | note | Category - IP
label | 14635378-a828-5962-96f2-764f6dc63cf2 |  | note | Responsibility - SE/PE
label | 0e3d0f21-04a9-50dd-b1ac-281fdf1d6165 |  | note | Verifying Documents - This ITP
date | d5164eb9-49ce-50fc-b100-f0a04ad2d44c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Crosshead / Pedestal Tolerances
label | a98d4e03-579e-52fc-b30f-77dff740d712 |  | note | Reference - Survey As-builts / Survey Report
label | f59752e5-6d91-5d48-bacb-cbab4b6bf0dd |  | note | Acceptance Criteria - Re-check that the As-built dimensional tolerances comply with the requirements below:
label | ee41bf26-344b-5220-9462-efdcbb092bcf |  | note | ○ Reduced level ±2.5mm
label | dd7732f5-6099-5571-9b99-93bd87f7736d |  | note | ○ Variation from grade across the width of individual pedestals shall not exceed 1 in 200
label | 67cedd8a-4f56-5d45-a048-6fda1ab23911 |  | note | ○ Deviation from flat surface ±1mm
label | 17355081-64ae-5f03-b90b-9f6db2a5c380 |  | note | Method - Document Review
label | ec495866-1016-5e1d-ab05-1af75a0ad9d3 |  | note | Frequency - Each element
label | 6f98e726-c462-5fa7-bafd-fd9655323ce1 |  | note | Category - IP
label | 0bbc1d0d-dc8a-5d97-bcab-d7062817c62d |  | note | Responsibility - PE/SE/SPE
label | c52ee3bf-95c5-5b45-aa1a-d2531307c6a5 |  | note | Verifying Documents - This ITP
date | d9665077-f55a-5863-8be1-563cc4c4b9e8 |  | date | Date Completed:
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Falsework Design and Certification
label | 2a79ae6c-6cab-5915-b2ec-93eb29a13857 |  | note | Reference - 613.04 Temporary Works Design
label | 2c117a57-b99d-5be9-beef-7dae21518920 |  | note | Acceptance Criteria - The Falsework drawings submitted shall state all design assumptions and shall include a statement of the loads and any dimensional changes due to loading in all members of the falsework. The drawings shall be fully detailed including all member sizes and materials, dimensions, levels, erection procedures and other relevant details including bracing, connections and foundations, to ensure that erection and inspection of the falsework can be undertaken without reference to any other documentation.
label | 3d75bd32-2766-5807-a0df-a8b9844aa99c |  | note | Attach: Temporary Works Design
label | 96ca2fa3-59b2-5ef0-81a7-90cb108c64dc |  | note | Method - Document Review, Visual, Measure
label | f6755e5f-fbda-5c49-87a1-dc1815cb7f5f |  | note | Frequency - Each element
label | 3f8a4923-ad9b-580f-8a0b-34032e6ddd0c |  | note | Category - HP
label | 6c3ebc0d-a18d-5aae-8f4f-4529af63ba65 |  | note | Responsibility - Temporary Works Designer, Proof Engineer
label | 6673e548-4993-5d36-b551-7bb396a7d993 |  | note | Verifying Documents - This ITP
date | 8433b7b4-dd76-57a5-9a2e-f5f136e588f5 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Flasework Certification - Falsework Inspection
label | 7597b88b-18bf-501d-ae76-7b25a281ea7e |  | note | Reference - 613.04 Temporary Works Design
label | 05cb3fe6-07b8-5e7d-b7cc-31b468925b90 |  | note | Acceptance Criteria - The application of any permanent load shall not proceed until the signed Certificate of Compliance - Falsework Inspection of the constructed falsework has been reviewed and accepted by the Nominated Party.
label | 225a86ad-080a-5388-b1b0-6d89dbc896bf |  | note | Attach: Temporary Works Permit to Construct, Apply Load and Remove
label | 5196b8ce-5e5a-5bca-b621-ee9aa34a040f |  | note | Method - Document Review, Visual, Measure
label | f49c3dd2-d9b1-560a-875a-bc534be22a3f |  | note | Frequency - Each element
label | b17a8d59-1747-59a3-bbbe-dfc85bacc25c |  | note | Category - HP
label | 3ff9803f-182f-5521-ac0c-56b6be755c86 |  | note | Responsibility - Temporary Works Designer, Proof Engineer
label | 2d23d448-286c-5bc2-95d6-c7ab98a882d7 |  | note | Verifying Documents - This ITP
date | 3f7dfbaf-331d-5bc2-8d1b-9ae3c63c0f79 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Precast Handling
label | 5910027f-086a-5877-b9cf-7e447a420e45 |  | note | Reference - 620.07 Crane Lift Study
label | 4fd2a61b-123b-560a-a997-a65ed00bd171 |  | note | Acceptance Criteria - Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | 3075365a-f422-5d64-b249-0c78eeddaa3f |  | note | Method - Visual
label | 62384675-6bb7-59b3-ac0d-7850c237de53 |  | note | Frequency - Each element
label | aa256a52-6d10-55f6-9862-977dc8909433 |  | note | Category - IP
label | 65950e3e-87e5-5c92-a782-721e932e32d9 |  | note | Responsibility - SE/PE/SPE
label | 83732e52-53dd-58af-8ea8-c17e978d4ec1 |  | note | Verifying Documents - This ITP
date | 2b4d38bc-500a-53b2-9246-f0c0f9d14162 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Elastomeric Bearing Placement
label | a440ec42-7290-55ba-873f-fdbeb887673a |  | note | Reference - IFC Drawings VR 656.05
label | ce0cdd4e-e9fd-5314-b6ee-6ae313063bf4 |  | note | Acceptance Criteria - Place the elastomeric bearings to the survey marks to achieve compliance with the IFC Drawings and tolerances.
label | 45400d05-5d7d-5261-9c0a-7f4f29f2424e |  | note | Tolerances:
label | 5898f97e-8786-5adf-b813-ba1ff285179c |  | note | ○ Plan position: ±2mm in any direction
label | bead8a06-04d4-519c-9a7e-2ab2308cac7d |  | note | ○ Level: ±2mm
label | c9408230-10da-5b9d-a519-e718ec7033ac |  | note | Record: The elastomeric bearing ID onto the Red-line Drawings or Survey Report
label | 76932087-83b1-5aff-a478-bfcb61c00417 |  | note | Method - Measure, Visual
label | 2163b904-8545-57eb-806b-1c41485ec3d5 |  | note | Frequency - Where applicable, each bearing location
label | 9ef051b3-9b9a-53a3-8d3d-b7e306d577e8 |  | note | Category - IP
label | 4ecccc33-db58-5df0-9002-8e29fa041d0e |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 840b8fd2-b41e-5be8-9217-6389caa55b66 |  | note | Verifying Documents - This ITP
date | 41d12878-ca94-5df9-8145-649eac52bbfd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Precast Placement
label | 7d728a3c-8663-59ab-ad7e-881659a6827e |  | note | Reference - IFC Drawings 610.27
label | 740e5e11-85f9-5ca6-ad97-683b26f7696e |  | note | Acceptance Criteria - Precast elements shall be placed onto the bearings/bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings.
label | 0eaf3f5f-70fb-5171-9333-94924ebce9fd |  | note | ○ The nominal gap between elements is as per the IFC Drawings.
label | 8b809e97-c271-550c-bcc1-6589c7da7cb8 |  | note | Method - Measure, Visual
label | 6b94aaa6-44ec-5220-9dcd-90dd39c87a68 |  | note | Frequency - Each element
label | a72cd012-6db5-5ff1-9380-8b96febc8776 |  | note | Category - IP
label | b9abf54d-527e-55ff-a5d3-b20e48e2ea76 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 444143e5-4557-5be8-9d8a-0d3b74bf004d |  | note | Verifying Documents - This ITP
date | 13883bf3-27ad-50c7-a4d0-2325e770c9b8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Precast Traceability
label | c6a40ab3-03f8-5621-9d13-9da1d88fe090 |  | note | Reference - 620.09
label | bb823412-34f1-535e-91ac-1bf4439e6ba7 |  | note | Acceptance Criteria - All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
label | c0f97941-280d-5c42-a948-9524d58ef410 |  | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
label | 296c564d-0853-58f2-a7bd-6a7f60c86d39 |  | note | Method - Visual
label | d441a393-8c0f-56da-a7c8-3b8404391cda |  | note | Frequency - Each element
label | 24b21494-c668-5b33-9ade-8f10255efda2 |  | note | Category - IP
label | 7e2fd1b5-c425-5ba7-a657-a9f7578e5331 |  | note | Responsibility - SE/PE/SPE
label | aa458cd9-ccab-5120-88fa-bb36c720c368 |  | note | Verifying Documents - This ITP
date | 689416bf-2e16-5e7e-905a-2f181844c98a |  | date | Date Completed:
checkpoint-group |  |  | section | 6. Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - As-built Survey
label | e5a1fa4b-4310-55d3-90e5-15a11f1f1f8f |  | note | Reference - IFC Drawings 610.47 (a) Table 610.472 (Feburary 2020)
label | da62e1dc-c3e7-5a3b-8dd4-d2192e94a57f |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with specified tolerances.
label | cd9b6839-0d5b-52f1-a7ca-ab900160e253 |  | note | Attach: Survey As-builts / Survey Report
label | 859cb749-f1b5-5751-bd69-c36f158fab42 |  | note | Method - Document Review
label | dc19203f-e87f-55f5-9909-dbab3b0f7538 |  | note | Frequency - Each element
label | 51cc4032-d41b-5abe-b0a4-4eb2fca9e525 |  | note | Category - IP
label | 9407c706-67a0-5952-88da-5b93b4dddaf4 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | c9aee547-f758-585f-a870-ce65ff8400a4 |  | note | Verifying Documents - This ITP
date | 767b467d-01ea-59d0-b315-e9a3a76276fc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | 182f04e6-c392-5c4f-8c8d-b8cb84ee5fcf |  | note | Reference - MRPA Quality Management Plan
label | 551dc544-47e7-5fd8-89db-3fc076099ce2 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 359584d3-7e3c-5c3f-be71-fda13f6838eb |  | note | Method - Document Review
label | a61dc3d8-08d0-54c1-acd5-b547db68f781 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 62df03aa-cd33-51d1-98dd-8d5b5ed4eb5d |  | note | Category - HP*
label | 7d6eec41-3e7d-5e1a-9357-c0c8cc6ef017 |  | note | Responsibility - SE/PE/SPE
label | 09a6f7c3-f36d-565e-95c2-eba7cae40085 |  | note | Verifying Documents - This ITP
date | a17ef0af-3174-5bd9-884b-b5bf0cf09570 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 1efa8641-bc6e-5e7d-87c6-3dd32e5c0b84 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 700c9bb4-2979-52c6-88b5-d9f566303ea6 |  | textbox | Name:
text | 76635bbd-f048-5c63-b24e-03eff142d6ec |  | textbox | Position:
date | 368751fe-511a-55ee-b610-21bd94f01346 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-121-STR-CPD-Grout Pedestals & Bearings | itp |  |  |  | Yes | ITP-121-STR-CPD-Grout Pedestals & Bearings Rev 0 | 486706cb-0fd3-41ef-86bf-b4d28bcefea9
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 08814c56-325e-59fe-89a5-ffc4953e79f5 |  | note | Document Title: ITP-STR-CPD-Grout Pedestals & Bearings
label | b35788b6-d954-5fe8-8c65-bca83b54bd94 |  | note | ITP Description: CPD-Grout Pedestals & Bearings
label | b9621cde-10d0-5e91-8284-7a4bf7b4ac9c |  | note | ITP Number: 121
label | 323d07ab-589f-5f84-a860-b5608d6c378e |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | b88f4b54-fb74-554b-8322-8ac43db86660 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 60057c2c-8cc5-5078-894e-fc896f4bc1b4 |  | note | Revision Number: 0
label | 11dcb7c3-c418-57bc-b52e-679a4a4913d9 |  | note | Revision Date: 19/01/2024
label | 4e54fc55-4e8f-5c55-96c2-1ef04a36ca4e |  | note | ITP created by: Andrew Carlini
label | da2f3bda-7490-5fb0-a428-dc9579d6725b |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 47f28304-2040-5ec7-98e4-1f9e0eabd492 |  | note | Reference - VicRoads Section 610 Feb 2020
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Product Selection
label | 5e9e32de-ecec-578f-8cc9-a8fa92363929 |  | note | Reference - IFC Drawings 610.28, 610.33
label | 898a8e84-f212-58c0-bed4-140b95cac752 |  | note | Acceptance Criteria - Product to be selected based on the following criteria:
label | dc16ee35-bd61-51b3-8bb0-9dcba16c3a0e |  | note | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout OR a single component low shrinkage mortar
label | c73518ce-20c7-50bd-8a71-e5ca0bb2daff |  | note | ii. have the required strength at 28 days as noted on the IFC drawings.
label | 51148651-2f4f-57a1-8604-d239dd9264f9 |  | note | iii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings.
label | a3bd0b6f-80ec-544f-953a-bc9a62961074 |  | note | Note: Pedestals 200mm or greater shall be constructed from concrete - use ITP-STR-Structural Concrete instead
text | 5155439a-4d9a-58b0-8ef9-e8548a679e63 |  | textbox | Enter: Teambinder Material Approval number
label | 5bf9a5fe-43d1-5228-9a23-7f050e8ea776 |  | note | Method - Document Review
label | 39d117c9-699c-5a02-9f00-9c57e44f2907 |  | note | Frequency - Once, for each product, prior to placement of product
label | 58052465-d194-5e76-b894-490693124469 |  | note | Category - IP
label | 41f72756-5fb1-5a08-93a1-5530e04c9c46 |  | note | Responsibility - Nominated Authority
label | fa14f771-94d6-5e21-962c-8172ec0705c5 |  | note | Verifying Documents - This ITP
date | cdd1926f-c1b9-50fe-9fbc-54a73ecd4696 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Curing Compound
label | b646eeae-9e6a-5d65-98ca-dc14a4f24c15 |  | note | Reference - 610.23 (d)
label | 2db66a3c-bfb2-50d2-bce9-0758532bdff6 |  | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | aeeec999-98ad-5e15-bf10-03cd85a9dfa4 |  | note | Note: This may be the same product used for the concrete curing
text | c76ae6c1-e866-5c6d-80c8-5c0b4af96c7b |  | textbox | Enter: Teambinder Material Approval number
label | 318a9c61-aa48-5faa-9cd2-de167625834f |  | note | Method - Document Review
label | 9c0f16f4-b630-5f29-878d-acb2cbb5c724 |  | note | Frequency - Once, for each product, prior to placement of product
label | 07f1a7b0-840d-576d-ae00-151c6c876d88 |  | note | Category - IP
label | eb568ecf-cdc0-57e1-a13e-abb59ac15504 |  | note | Responsibility - Nominated Authority
label | a81774fc-9b02-54bb-906d-9594e758e66e |  | note | Verifying Documents - This ITP
date | 1cbfc00a-614c-5b83-875a-c0da855544bd |  | date | Date Completed:
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Curing Methodology (for Concrete, Grout and Mortar)
label | 8d23e36d-7e4e-5bfe-acad-490d83506a4c |  | note | Reference - 610.23 (a)
label | ea1caed0-f0ba-5fb1-b763-258a7c95da3a |  | note | Acceptance Criteria - Curing methodology/procedure to be submitted for review to the Nominated Authority.
label | f6004601-aa9e-5b9a-8556-751b7eaf73f5 |  | note | Note: This may be the same document used for the concrete curing.
text | d57f30a1-c3f6-50d4-93bc-24d242237b08 |  | textbox | Enter: Teambinder Correspondence Approval number
label | f5c5da43-dd49-5d8d-804e-2e0709e89169 |  | note | Method - Document Review
label | 67a08bc2-baf2-5ebe-9287-71521ef07ef1 |  | note | Frequency - Once, 4 weeks prior to placement of product
label | f78fbbb2-a9e2-5466-b2cb-20ecf991c262 |  | note | Category - HP
label | 0ddd3134-0e2f-5c3e-959f-ae010edce4a0 |  | note | Responsibility - Nominated Authority
label | d4353884-a8e1-5ed3-b540-38f1726abf28 |  | note | Verifying Documents - ConQA Hold Point Release
date | c2b04e3a-88eb-51a2-b9fd-47d8ce5f19f2 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - IFC Drawings
label | 3bb92d15-6439-50d5-870d-6d1056d3a740 |  | note | Reference - MRPA Quality Management Plan
label | 1d5155ae-3c28-51d6-b439-45e4bd4af72a |  | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | ce4d98a2-3fd3-59c8-b5c4-d9384b60c528 |  | note | Method - Document Review
label | 88970b81-faa6-52b2-9197-42716c112850 |  | note | Frequency - Prior to starting Works and at regular intervals
label | a4f4912b-bef6-51ec-b2cb-50a89b08e35f |  | note | Category - HP*
label | bb1fc0e7-c5bd-5704-b1c0-a66ed04f2082 |  | note | Responsibility - All
label | a172a42c-f1ce-5248-8bfd-42ea12849a0d |  | note | Verifying Documents - This ITP
date | d9892098-d137-5836-9b56-066c76bf4a07 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Survey Set-out
label | 3f2fddd4-a3c1-5e8a-a203-a1012775cacc |  | note | Reference - IFC Drawings 610.46 (a), Table 610.462 (Nov 2018), 610.47 (a) Table 610.472 (March/June 2019)
label | 5b5b9cd7-bc1b-52df-8a91-6b910fcc4e4b |  | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element.
label | c2db3dfb-dab7-5373-9f95-e357e0b5ea2d |  | note | Note: Different revisions of 610 have different clause numbers
label | b0d9c523-6f2e-5ed6-b78e-ec448cab029c |  | note | Method - Measure, Visual
label | 3256ca51-c9ed-5a45-bd59-cb2da384dd93 |  | note | Frequency - Each element
label | 19fd1581-be84-5140-95d9-9354c7761916 |  | note | Category - IP
label | 8ea849b5-c92f-5a2b-8254-bf581199dc79 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | e5703f02-91ec-5b73-a6ab-592314cff871 |  | note | Verifying Documents - This ITP
date | 8ec6aa2d-1e7d-5802-ba4b-20956eba984b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Construction Joint
label | ffdb4775-71af-5b0b-85be-55115bb467b9 |  | note | Reference - IFC Drawings 610.20 Fosroc Renderoc BB TDS
label | c8da7205-4de8-57dc-bef7-638c012ee07c |  | note | Acceptance Criteria - Existing construction joint rebate is roughened / scabbled and set to 20mm minimum below top of the crosshead / abutment.
label | 899567fc-165e-59c6-babc-ecda361c5e9c |  | note | ○ Concrete substrate surface saturated with water for 3 hours minimum prior to pouring product.
label | 6b08134b-3a3e-5681-849b-8b33ecdbc677 |  | note | Method - Measure, Visual
label | 07f02a97-2d26-5b3d-909b-6755a09df628 |  | note | Frequency - Each element
label | 8ffc68fe-7d0e-547a-bee2-074fe91b30f3 |  | note | Category - IP
label | 939f82c7-2e1d-5554-89c9-3387e4eefca5 |  | note | Responsibility - SE/PE/SPE
label | 8d3c2b74-0fc7-5083-b861-afbb7e2a88a2 |  | note | Verifying Documents - This ITP
date | e5aff094-d94d-51d8-bfab-47e8b8f9c80d |  | date | Date Completed:
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Formwork Construction & Placement
label | b04740d4-9114-5b56-a15b-868a0851200e |  | note | Reference - IFC Drawings
label | f3f7d09f-3358-51b0-8610-d4291d584acc |  | note | Acceptance Criteria - Dimensions in plan as per drawings (typically +50mm all around).
label | 84b58138-bd9f-5760-8236-60493f15411d |  | note | ○ Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks.
label | d70800bd-3339-557a-8671-349dff358bb9 |  | note | ○ Any cast in componentry (ferrules, conduit etc.) secure.
label | dc7f82ba-1d6d-5a53-ae80-bb50fe552c30 |  | note | Method - Measure, Visual
label | 5131f81d-ea47-5fd1-8564-3fb91762cebf |  | note | Frequency - Each element
label | d90445ca-3074-58ce-8c20-bfebe916a1fb |  | note | Category - IP
label | 8fbef92b-7479-5892-aab2-09562c250850 |  | note | Responsibility - SE/PE/SPE
label | 865eac12-1fed-53fd-9b48-afdde09bedd8 |  | note | Verifying Documents - This ITP
date | 280e7a0f-55df-54a6-881b-3b5c6b1fd578 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Pre-pour Inspection
label | d65b0443-e813-5525-9187-67e7f411f678 |  | note | Reference - IFC Drawings 610.18
label | e41e07de-a4b2-508d-b8f3-f994ea440736 |  | note | Acceptance Criteria - Formwork location and RLs comply.
label | f87d7193-bf84-5e4e-b08b-e5c4a673a7f3 |  | note | ○ Any reinforcement has the required cover.
label | 761a5bf5-96a7-5f41-aff7-f3eee0561321 |  | note | ○ Area is clean, concrete substrate surface saturated with water for 3 hours minimum prior to pouring product.
label | ebb8b60e-eda8-59b8-8651-b709b410496e |  | note | Method - Measure, Visual
label | 89ed09de-24d9-5a83-9d53-c06a424da0f6 |  | note | Frequency - Each element
label | b1ca772d-7de1-5867-a001-1e1b61837fb3 |  | note | Category - IP
label | a706cd8d-96f7-5b85-9076-9c9e3ab9ceca |  | note | Responsibility - SE/PE/SPE
label | fb7f42ee-351b-5058-9cbb-06942e801198 |  | note | Verifying Documents - This ITP
date | b5f63541-5918-5e5f-8ce6-35513af9c346 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Weather Conditions
label | 5787d4f4-74d2-59c0-b166-7d324fc1cc71 |  | note | Reference - 610.17 610.17 (a) & (e) Table 610.171
label | 0d284465-b7e5-5bb5-8db5-3876c3df37cf |  | note | Acceptance Criteria - All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 92db101e-f037-51ac-bf1b-99607ad54212 |  | note | ○ The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 1bdf2663-30bb-5fb8-a054-0fccd5c4850a |  | note | Record: Required information on the Grout Pour Record.
label | 02613f08-e46f-50ef-b558-065a226e918e |  | note | Method - Measure, Visual
label | d7f99928-ac0a-5dce-af5a-b03a8b1ef1bf |  | note | Frequency - Each element
label | 83b97806-70e6-58da-be04-4f955fc404e7 |  | note | Category - IP
label | 8092aeb0-214b-5a69-92fc-ae44ac8cd01a |  | note | Responsibility - Foreman, SE/PE/SPE
label | ed48f924-a25c-59e3-b0f7-3a256df489d9 |  | note | Verifying Documents - This ITP
date | 6908a249-f376-508d-aa9a-ba286835e228 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Mixing Product
label | 6c31f4c9-a0ed-5e62-a9d2-c541d788dd8e |  | note | Reference - Product TDS 610.28
label | cccb1905-0f94-5d49-8e5f-5d301c3263b2 |  | note | Acceptance Criteria - Size of mixer should match the application.
label | c8d6847a-a750-5319-bed8-689d3de400e9 |  | note | ○ Only whole bags to be mixed with potable water.
label | d74e1a18-e04c-5352-a0ce-cd6942abec62 |  | note | ○ Volume of water matches the required amount for flowable consistency and accurately measured.
label | 41ba46bd-bb79-5b75-8ede-0c03eaa6ebd1 |  | note | ○ Product poured into the mixer slowly.
label | 72b20d1d-4dff-5147-8459-d67777fd5f7d |  | note | ○ Mixing time as per TDS so that a smooth, even consistency is obtained.
text | 9ec75bec-e8bf-5ec7-9d6a-4a58004a6688 |  | textbox | Enter: Required information on the Grout Pour Record.
label | 749c4721-a4f5-5d08-a41e-f7a45c04ec2b |  | note | Method - Measure, Visual
label | cb0157eb-bb32-5c0f-9c59-8476947455b6 |  | note | Frequency - Each batch
label | cc6512f2-90da-5e53-a062-72f08c4506b7 |  | note | Category - IP
label | 95aa8fe9-54d5-5692-b951-78193fd00033 |  | note | Responsibility - SE/PE/SPE
label | 8cb463c7-4ffd-50ae-bad9-8a4df7990940 |  | note | Verifying Documents - This ITP
date | 0517cb28-bf1e-500a-bccb-c0dbdb5a3217 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Product Testing - Compressive Strength Cubes
label | 4e54cdfe-c29c-596f-9385-a2afcc82bd60 |  | note | Reference - 610.28, 610.33
label | f9304faf-6d41-5f3c-b05e-3b00d599c182 |  | note | Acceptance Criteria - Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
label | d0e66ae1-c350-5948-8bd5-15424ba86003 |  | note | ○ Testing is be in accordance with the following frequencies:
label | 6993151e-e413-5c63-a7ff-d430260665e5 |  | note | ○ First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | 359edb9e-8001-56c0-a71a-e06ea13a5240 |  | note | ○ Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
text | 3a4ae9f6-2ff2-5c7f-bf1c-4420c6955b7b |  | textbox | Enter: Required information on the Grout Pour Record.
label | ff22c1e9-f025-5e59-8452-6db741fde58f |  | note | Method - Test
label | 442077eb-ebd2-5a56-bc89-aea23bb65ce7 |  | note | Frequency - Each element
label | dc34f1af-431d-59d6-a83a-ccb6d777fdbd |  | note | Category - IP
label | cf092b39-2f8d-5b43-998a-418d723ecf40 |  | note | Responsibility - Tester, SE/PE/SPE
label | f8e4ea9c-cb2b-5dee-aff7-32b87fbc146e |  | note | Verifying Documents - This ITP
date | 3a38d5c4-ae93-5cf4-ae59-80e3c1de186c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Placement & Compaction
label | 769ccf39-38cf-5147-af3a-99371ccc2018 |  | note | Reference - Product TDS
label | 631a505f-fdbc-5047-a00d-36912be0de82 |  | note | Acceptance Criteria - All batches are traceable.
label | f51f375b-2b96-5bf9-bd91-bb94d13166f1 |  | note | ○ Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
label | 07aa46cc-78bc-5e72-8f0c-c63499e4e3f7 |  | note | ○ Product should flow to all areas and self consolidate.
label | 1b5adad3-0c7a-52d5-bc9a-41494a628c29 |  | note | ○ Product that stiffens or is showing signs of stiffening shall not be used.
text | 9b141031-c302-5341-a815-e0996a78500f |  | textbox | Enter: Required information on the Grout Pour Record
label | af779cfe-c395-5b17-b9a6-58d43a5d5d09 |  | note | Method - Visual
label | 288c68aa-a5fe-548a-8848-05963508ff92 |  | note | Frequency - Each element
label | 99e0f8db-dd65-58f6-a13c-dbf2a0b31abf |  | note | Category - IP
label | 66921a70-f379-55a0-814d-20f86d12bea9 |  | note | Responsibility - Foreman, SE/PE/SPE
label | c05ea0eb-904c-5d26-b023-9fa8be24406c |  | note | Verifying Documents - This ITP
date | fbf63707-c4e3-515c-9e3b-dc06e4332cb4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Surface Finishes
label | 6ad086c0-7faf-50e8-be76-09e4e493a7bc |  | note | Reference - 610.28
label | b26c306d-120a-592c-b7c1-dadb1c401460 |  | note | Acceptance Criteria - Surface finish shall be flat with a surface roughness of an amplitude of approximately 0.5mm - 1.5mm, likened to 40 grit sandpaper.
label | 6cc052b9-9766-5e06-97c9-193654da6cc1 |  | note | Method - Visual
label | 1b7d022b-1fbf-5d34-b2ab-7dd4fb7b07a9 |  | note | Frequency - Each element
label | b2b857bb-1e43-5030-924d-116c53109bdb |  | note | Category - IP
label | 5a369663-005b-50fb-b970-a3bb32269fac |  | note | Responsibility - Foreman, SE/PE/SPE
label | ac33b703-5887-5547-a543-38ed59394f60 |  | note | Verifying Documents - This ITP
date | 03726ee4-05b3-5a5e-97c6-1fd9546d8300 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Curing
label | f4230b7e-0d8d-52b6-b887-8a9a432d0bf7 |  | note | Reference - Curing Methodology 610.23 Table 610.231
label | d7831af3-542c-593d-b4d7-3725ee96a392 |  | note | Acceptance Criteria - Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | 4f0bf8db-75df-5086-bdc9-01546b037310 |  | note | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | cc3dd402-29be-55e8-9e6f-4db85234ba2f |  | note | Method - Visual
label | 573dd916-cdb8-582d-be83-d8e5e20db330 |  | note | Frequency - Each element
label | 7513f740-fd8d-5721-a0c4-48b2cfdcecb9 |  | note | Category - IP
label | 734fdc82-cb36-59d9-8238-f60530ba9b59 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 16ecd117-dd27-5d06-b7e6-70c02132b83f |  | note | Verifying Documents - This ITP
date | 0b22a83d-b5b8-55d0-9edf-7824a99f85cb |  | date | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Compressive Strength Test Results
label | 15e938e2-54b2-5819-9dee-2eb13a5d3679 |  | note | Reference - IFC Drawings, Product TDS
label | cfdc2f6e-f1f1-5c43-a94b-e7d1fa5feac5 |  | note | Acceptance Criteria - 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
label | 8643f4ce-4219-58f2-9d62-ce85299d5e36 |  | note | ○ 28 day compressive strength per sample comply with the design strength.
label | 89681cb5-09ca-5a21-8639-86a1180a5ec2 |  | note | Attach: Compressive Strength Test Results
label | cf407bfc-c22e-51ee-8cc6-5aeb9fc536c5 |  | note | Method - Document Review
label | fd753140-c061-5752-b033-1aa9a67cc53d |  | note | Frequency - Each cube
label | e8c1a335-7bfa-5108-bb44-3c0af9aaeeb2 |  | note | Category - IP
label | 839b1b12-4afb-54a9-9c13-c7f352e236aa |  | note | Responsibility - SE/PE/SPE
label | d36250c8-3369-5842-8e3d-fa2375009a32 |  | note | Verifying Documents - This ITP
date | 79b77633-93a5-5667-b74b-4d1c274c8bb0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Surface Inspection - Cracks
label | 7308da1a-e512-5e74-a20a-a259d794921b |  | note | Reference - 610.24
label | c60e5a04-cdd3-5845-a8c4-c5be22923aaa |  | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1)
label | e567c59f-d159-5eb9-ae83-cb279bd196f4 |  | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | 8053f03f-17df-5d6d-a9fd-4d3f4a61f4a1 |  | note | Method - Visual, Measure
label | 22ee1c20-34c6-5f92-bc51-3e5ab862aecd |  | note | Frequency - Each element
label | 4276d6ac-ce4b-5a29-aeae-ab16bb7a2308 |  | note | Category - IP
label | da318bee-97d0-5ab6-b19b-79b9bb2cc92a |  | note | Responsibility - SE/PE/SPE
label | 801d7990-c157-504f-af91-4ac05309582e |  | note | Verifying Documents - This ITP
date | ad485846-b847-52c0-98bd-e2c226c685e7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Surface Inspection - Surface Finish
label | 76488c40-7944-5b49-910b-3f255fd916b5 |  | note | Reference - IFC Drawings 610.31 (a) - (n), 610.32
label | dd17e992-a9e1-5f7b-9268-2357bb72ca0c |  | note | Acceptance Criteria - Comply with the IFC drawings and specifications.
label | ecf32577-7124-56a3-9caa-6b4eed65f885 |  | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | 780d6f58-eabb-5a0c-b7a2-99752d76d0ef |  | note | Method - Visual
label | 18333753-f2f4-536c-b99d-e6c1e4382be6 |  | note | Frequency - Each element
label | fed9f6de-15d9-5163-87a4-ab47ea364cf5 |  | note | Category - IP
label | 86afebf2-f67f-5cd0-812c-b920c9cd9822 |  | note | Responsibility - SE/PE/SPE
label | 877912ae-7638-5ad0-8945-973ae86aad75 |  | note | Verifying Documents - This ITP
date | 5ae6fe32-5351-52a5-9777-4aafa2a62da6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 - Measurement of Concrete Cover
label | c4f0f327-4aac-5356-ba76-3ec955f6ea56 |  | note | Reference - 610.34
label | 1dc7dd31-359f-55f2-9f59-41db29e0190e |  | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
label | 50aac30e-28fe-5cb4-a7f3-4d609a3f54e8 |  | note | ○ Minimum 10 no. measurements recorded in each area.
label | e46989f9-acaa-5668-a23b-dd0e69520447 |  | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
label | d0cf5f61-d395-538d-82b4-080d2800a981 |  | note | Attach: Covermeter Check Record
label | bd2a5d23-cc37-516a-af26-a0c7e6da87cd |  | note | Method - Measure
label | 3948fa03-7c3e-5105-b00b-fea73d172a09 |  | note | Frequency - Each element
label | ea177b7c-bbaa-50b7-9931-d28a5694ef31 |  | note | Category - IP
label | 4f5b092a-f64b-5f16-b239-4e9f5292aac0 |  | note | Responsibility - SE/PE/SPE
label | a23a0d7b-b585-5083-a2f2-9375a4bec7c7 |  | note | Verifying Documents - This ITP
date | 33c0ee9b-81ad-576e-ab96-2bcc80213a20 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 - As-built Survey
label | 3531dc5c-5ea9-58e6-a8db-952eb3fb5e30 |  | note | Reference - IFC Drawings 610.47 (a), Table 610.472
label | 1586b1c9-7faa-5262-8a8a-d4e1ec3e644d |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances below:
label | a3d24cf7-f3a8-566a-9768-196676a302af |  | note | ○ Reduced level ±2.5mm
label | 9925e5b9-e51a-51d4-93df-e814627ac8bf |  | note | ○ Variation from grade across the width of individual pedestals shall not exceed 1 in 200
label | 90d15f94-b964-53b5-a8c3-3d64efbe8969 |  | note | ○ Deviation from flat surface ±1mm
label | 4a8e1723-c630-51eb-9cd9-483c4de4b608 |  | note | Note: Different revisions of 610 have different clause numbers
label | 1f38e466-b4d1-5f1b-8888-ba94d6ff3a36 |  | note | Attach: Survey As-builts / Survey Report
label | 54ab0f91-7c8b-5f1b-9aa1-7818390157bd |  | note | Method - Document Review
label | bc2d727d-8f4c-5756-8269-420434b0e85d |  | note | Frequency - Each element
label | 52670ba1-fdf2-58f8-a66f-980f4ec27d93 |  | note | Category - IP
label | c48e5ef0-86bd-556c-9a85-0901052cceb3 |  | note | Responsibility - Surveyor, PE/SE/SPE
label | 77456f19-a522-5df1-8294-bf620930d5a4 |  | note | Verifying Documents - This ITP
date | 64f55d70-74de-55b8-85f1-d69fb9cf27be |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 - Non-conformance Report (NCR) Closure
label | 011b2a17-bd35-59bd-9e19-d7f25e564a4b |  | note | Reference - MRPA Quality Management Plan
label | 4cfb7446-d587-545f-8379-505592a41d98 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 90b164b7-21f0-51d4-9077-43baba6d40ad |  | note | Method - Document Review
label | 5300e428-f6e3-57b0-a34d-a3ed58209806 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | f725fa7a-7da0-5b6b-8682-b6013973d95b |  | note | Category - HP*
label | 3233d283-6872-5ea3-92df-945814dd2e58 |  | note | Responsibility - PE/SE/SPE
label | bf3b69c9-369a-53cf-89bf-6335a89dd916 |  | note | Verifying Documents - This ITP
date | 8e855e76-d921-5a94-817c-ebc797b1b48a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 0bdc67cc-f3ea-5bef-aff7-0591adaa72ee |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | b21dfa14-2034-5262-9ed7-942b80d44c45 |  | textbox | Name:
text | b97377f8-ea00-5cb6-8afe-e0bdefe4112d |  | textbox | Position:
date | 92eaaed0-5aaf-5a80-86d3-d14b912989f3 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-113-CIV-CPD- Jemena Conduit & Pits (Supply & Install) Rev1 | itp |  |  |  | Yes | ITP-113-CIV-CPD- Jemena Conduit & Pits (Supply & Install) Rev1 | 4937393f-35e8-4f5d-be6a-ac0667322b1d
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 53fe9999-79d4-5a51-a5a8-3bd2d49de341 |  | note | Document Title: ITP-113-CIV-CPD-Inspection & Test Plan - Conduit & Pits - Rail (Supply and Install)
label | 66d6d135-9169-5833-86b1-4f5a180666f6 |  | note | ITP Description: Conduit & Pits - Jemena HV relocation
label | 425e115b-9611-5c53-9a2c-be512e83db0d |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 275f2cd3-afa5-5e49-8521-497565a896a8 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 9996c7a4-5773-5508-bd31-dd0640c0f968 |  | note | Revision Number: 1
label | dff8a319-7e69-5f31-a8fd-819965ef06c4 |  | note | Revision Date: 8/12/2023
label | 0a3d1610-38ac-5f66-8e33-95d9d863221d |  | note | ITP created by: Lachlan Morris/Pat Sabaruddin
label | 4829db38-56fb-53bd-b72a-12e6716c5b3b |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - IFC Drawings
label | 0aceb62a-1522-5afb-bbce-39d796bacba0 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
checkpoint-status |  |  | checkpoint | 1.2 - VESI D&C Standard
label | 0c8db75f-edcf-5be7-b06a-cdb3bb9fe5f8 |  | note | Reference - VESI_URD_003
checkpoint-status |  |  | checkpoint | 1.3 - Plastic Industry Pipe Association - Industry Guidelines
label | f37d66e2-9cfb-5bad-ae1d-053cfc282a78 |  | note | Reference - PIPA POP 003
checkpoint-status |  |  | checkpoint | 1.4 - Australian Standards
label | aab62cff-8294-5d4c-9d89-5d7abd3c02b5 |  | note | Reference - AS 2032, AS 2053, AS2648.1
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Conduits
label | f5f33d93-648c-56bf-8498-70e6270127d4 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003; cl4.4.2, cl5.8.2 AS2053
label | dd84aa1a-4142-514d-a2f6-ecbee434a3f1 |  | note | Acceptance Criteria - HV & Comms: Conduit sizes as per IFC and VESI 4.4.2 CONDUITS USED WITHIN THE VESI NETWORKS SHALL BE HEAVY DUTY SOLID WALL, ELECTRICAL CONDUIT TO AS2053.
label | 2c77cc61-821e-59f3-b451-71b6b713b335 |  | note | ○ HV & COMMS CONDUITS TO HAVE A max BENDING RADIUS AS PER VESI_URD_003 - 5.8.2
label | 46347979-2439-5cdb-a64f-ba57e0561b60 |  | note | ○ Inspect materials upon delivery and attached delivery dockets.
label | 80b462a1-6c47-5f0a-a89e-6d762bb3d21d |  | note | Method - Visual, Document Review
label | 9a2f3396-0f10-538f-9774-8231a167c433 |  | note | Frequency - Each Material Type, Each Delivery
label | 99b5b451-0db3-55dc-acc3-2b68c9306188 |  | note | Category - IP
label | e3e033d8-3882-5806-97fc-7f196df2f093 |  | note | Responsibility - SE/PE
label | 42d2c485-4f29-56c8-927c-db35ea8919c9 |  | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
date | 3f5e9be0-7e06-5ded-a971-18e9a1de396e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Pits and Pit Lids
label | a0211734-41ca-5348-a1a6-b62bd88c1ac5 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | 0f4884f2-3661-51d1-a0ce-3543bb3b18a9 |  | note | Acceptance Criteria - Pits:
label | fac9277e-4066-5a95-92ca-4579933d2240 |  | note | ○ Pits to be used and installed as per IFC drawings and manafacturer requirements
label | a5624844-f73e-5973-99c6-23417286959c |  | note | ○ Inspect materials upon delivery and attached delivery dockets.
label | aa229adc-4a74-57bf-8ec0-3d4f568723c6 |  | note | Method - Visual, Document Review
label | 0a774e07-6486-58a1-bdbb-8663a3c4683b |  | note | Frequency - Each Material Type, Each Delivery
label | c968b835-6aec-51ec-bff7-0ea05ab7abf1 |  | note | Category - IP
label | 550f821f-2c51-5e23-a97b-33e3c33bb0c9 |  | note | Responsibility - SE/PE
label | 628f80ac-6b3a-570c-a6c0-b47808434476 |  | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
date | e4a1c952-4f96-5d36-8d14-5c1f4d32ffab |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Warning/Marker Tape
label | ef787d9d-ecb4-547e-9317-52fa61c753d8 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, AS/NZ 2648.1, VESI_URD_003 -5.5.2
label | 9f3e70a9-7a69-537a-8db7-730fb864b100 |  | note | Acceptance Criteria - Warning/Marker Tape:
label | b84dfb06-1828-5f09-a2ad-385dd1e5eb33 |  | note | Above HV:
label | 707c6847-a0a2-545a-8b9f-f365fdbee496 |  | note | ○ Orange 150 or 300mm width marker tape compliant with AS/NZS 2648.1 shall be used
label | 6c3a2d8a-5026-5f1b-a94d-8acfa230e7ef |  | note | ○ Inspect materials upon delivery
label | c1536669-4242-5693-8613-765e3bc2206b |  | note | Method - Visual, Document Review
label | 7694a862-262b-5a51-80b9-316b35c0a480 |  | note | Frequency - Each Material Type, Each Delivery
label | 01e1c786-0b71-5314-9029-c7f04b087b6b |  | note | Category - IP
label | c7663192-47cc-5745-87d9-29245fb3c600 |  | note | Responsibility - SE/PE
label | a70cd9ea-77b3-5bae-b381-831590808cee |  | note | Verifying Documents - Attach Material Conformnace Certs
date | ee8ac25d-87e3-573a-9386-28a2cf5f2f9d |  | date | Date Completed:
checkpoint-group |  |  | section | 3. Prelimnaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Services
label | d71fb84b-ea60-576b-a0e2-8238e822a1ff |  | note | Reference - VESI_URD_003 4.4.2, 5.10
label | d961c62a-4437-5806-9dbc-2052d0c6e899 |  | note | Acceptance Criteria - Clearances are requried between individual electrical assets and between assets of other authorities.
label | 7d4029f1-bbd4-5c1f-8a7b-f9d7af21a59f |  | note | Method - Visual
label | 219bedc4-3ce3-5604-887d-a4586425dc09 |  | note | Frequency - Prior to commencement of works
label | 831d9e6f-5383-5be6-8aa2-ddfdcdba9d4f |  | note | Category - IP
label | 4c96fbca-0d99-54cb-9628-392b6c5a2d90 |  | note | Responsibility - SE/Site Supervisor
label | 876ba946-0b1c-5cf7-acde-13a1d6dae305 |  | note | Verifying Documents - This ITP
date | 4b0d2633-266e-5c18-8fe1-8fac0b76143f |  | date | Date Completed:
checkpoint-group |  |  | section | 4. Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-out
label | deb2444b-2860-5c2e-adaa-c2e076d8c26d |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | 8c3cd768-a361-52f0-8f80-6059e9ac6b08 |  | note | Acceptance Criteria - Survey to set out trench alignment and pits, and establish construction control (alignment and level). Survey to mark out existing services.
label | 76dc6408-8b5d-548b-bf41-75b66391cb8d |  | note | Method - Measure, Visual
label | 35d84cf9-2264-58eb-9925-d03676a3dcb9 |  | note | Frequency - Each element
label | 4ae62148-28db-55b0-8b6e-514feb538040 |  | note | Category - IP
label | 09365510-8805-5e39-8f71-b30c076a7fa8 |  | note | Responsibility - Surveyor, SE/Site Supervisor
label | 8c6f11fa-55dc-5fac-b10a-35ac5f4643b1 |  | note | Verifying Documents - This ITP
date | c3fd09e6-6265-5c42-88ee-20a36de961c6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - IFC Drawings
label | 64bfd49d-2c2c-501b-a8af-02eb00bb4b78 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | 828e6179-1251-5093-a14b-8a45e2ccc078 |  | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | cd37071f-0d28-5e69-b5fa-a0d60973a4d1 |  | note | Method - Document Review
label | 5a57059d-123a-5e5d-91f8-ba08e3ed6445 |  | note | Frequency - Prior to commencement of works and at regualr intervals
label | 292826d4-1800-5d15-8e33-887439cf0327 |  | note | Category - IP
label | 61a7c5df-c836-5197-aa2d-3a94361eb7e7 |  | note | Responsibility - SE/Site Supervisor
label | 28d9ae57-5b2b-5d50-b347-d344507a925e |  | note | Verifying Documents - This ITP
date | 1ef87dc9-b95a-51d9-b588-ef53bff7da0b |  | date | Date Completed:
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Trench Excavation
label | 1705a4ca-3185-5b8a-b4a6-1360db33eec4 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003
label | 458a6cae-2dc6-51b6-8bd1-8812022c8c9b |  | note | Acceptance Criteria - Trench profile and depth as per IFC drawings.
label | 5ccad464-5f30-5a7f-844c-654416e0a9c1 |  | note | ○ Depth of trench is to be sufficient to allow for the minimum cover as per IFC from the top of conduits.
label | 845abd5c-871b-589f-8c02-9d077bf0f5a3 |  | note | ○ Cl5.3.2 Within the VESI networks, cabbles shall be buried up to a maximum depth of 1400mm (max trench depth of 1500mm).
label | d96bb569-5e61-5f6a-b896-92a1f634ec69 |  | note | ○ The bottom of the cable trench shall be level across its width and free from any protrusions and rubble that could cause damage to the conduits.
label | 0198e6c9-c61b-5f6f-891b-ac0fbdbd6068 |  | note | Method - Measure, Visual
label | fd800739-ae59-573b-b2c0-73f0b23fe1a3 |  | note | Frequency - Each lot
label | e9fadfb0-c7c0-5da8-b752-acb7132f911f |  | note | Category - IP
label | 028de31d-7ea4-5f23-ad25-fed0e95f4970 |  | note | Responsibility - SE/Site Supervisor
label | f7e75c6a-ae00-5dc7-afe6-9331d1a8bc7b |  | note | Verifying Documents - This ITP
date | ebb7d2ff-cd54-5816-b2e2-25af3257358b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Placement of Bedding/Embedment and Backfill of conduits
label | 40f9eb0d-b858-5e99-bd28-af2458002898 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003 - 5.7, VESI_URD_003 -5.4.2.2
label | 4215b288-ee30-5a53-89f4-aabeff4763ac |  | note | Acceptance Criteria - Measure, Visual
label | 9549ed48-f22d-5e49-aaa0-a673eae24a3a |  | note | Method - Measure, Visual
label | 82b4dc85-31ba-5977-becd-3d9c45d13dcb |  | note | Frequency - Each lot
label | 2e21899c-cc1a-5d3d-81e1-5917a0201b42 |  | note | Category - IP
label | 5622f178-29d2-5001-a138-376e46842c11 |  | note | Responsibility - SE/Site Supervisor
label | 7b8952c6-ccab-5594-8595-aecd587bce92 |  | note | Verifying Documents - This ITP
date | 24958e79-725c-52cc-9b1d-5dafe63acb8c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Conduit Placement & Configuration
label | 68bef158-7d09-5ae6-9368-d005efb75c1c |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003
label | 0578ace6-d5e1-53cd-8440-d7ab5134082a |  | note | Acceptance Criteria - Conduits are configured in accordance with IFC drawings and meet cable separation requirements.
label | 818995a1-0a1e-5d22-8bb8-425b9c915efa |  | note | ○ VESI 5.10.1.3 Where shown on the approved plan or by prior written approval conduits may be stacked in vertical alignment.
label | 8ab68478-fc99-53fc-a921-3e02581cf91d |  | note | ○ VESI 5.8.1 Conduits are to be provided with suitable non-perishable, watertight, endcaps or plugs. For any
label | e29afb79-9923-5c17-a62a-e1f37283b612 |  | note | Method - Measure, Visual
label | cb0a9069-f532-5075-9207-d7510a566236 |  | note | Frequency - Each lot
label | 3cddc9d1-08fd-56a8-b090-8b4a552f4138 |  | note | Category - IP
label | 389ed160-0e74-5a9e-9b3b-52bd3e24ce72 |  | note | Responsibility - SE/Site Supervisor
label | 677c4513-34c8-5827-94b1-8342268ac5e3 |  | note | Verifying Documents - This ITP
date | c7bb86f0-6c61-5f6c-ae92-bd5fe6f95b4c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Joints
label | d80cd435-4e25-5e77-aaf6-25084a616c47 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003 -5.8, AS2032.
label | a1895306-938c-5774-b588-3d83b46118fd |  | note | Acceptance Criteria - All conduit joints shall be made by utilising the spigot and socket ends.
label | 0f9200fe-7a9d-55dc-b29d-b2ed8dffdd63 |  | note | ○ Conduits are to be joined using solvent cement and comply with AS2032.
label | c1ec70f4-063d-50c7-a8d1-704ac265b831 |  | note | ○ Socket ends to be placed firmly into the spigots prior to backfill.
label | f973d731-8735-5767-8483-21f154717368 |  | note | Method - Visual
label | 73cc208e-4583-5ce0-b13b-6d6d939f31cc |  | note | Frequency - Each Joint in each trench
label | 45a1a0e9-cf5d-55e1-88bf-744542f23527 |  | note | Category - IP
label | ce5d52b5-f736-525e-98ac-f5fbee4ad295 |  | note | Responsibility - SE/Site Supervisor
label | acc4cd62-e796-5a87-b9b6-f186031524a1 |  | note | Verifying Documents - This ITP
date | cb7a8939-cdd1-5ca7-a3d7-eaeeff531f90 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Conduit Inspection
label | f9598065-57f2-5c72-a320-09ae26442927 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003
label | 7177e53f-c0b9-53d8-be05-f1f345b883fd |  | note | Acceptance Criteria - Inspection of conduits undertaken by VEDN accredited contractor
label | 8df668ec-95e7-5003-9e61-1eefe26ff8c9 |  | note | Method - Visual
label | 978cc1b3-0e86-598b-a54a-3e10d586e18c |  | note | Frequency - Each lot
label | 5ca33ec5-d29f-56f0-8c7b-14140bbddf6c |  | note | Category - HP*
label | c0e39564-3671-5c68-99ba-8242346b82d4 |  | note | Responsibility - SE/PE
label | 26c80910-2c78-5749-b42b-5d6f93b266fb |  | note | Verifying Documents - This ITP
date | d22f3412-4dcc-5ef5-8976-2fe0baa24192 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Marker Tape
label | 36ae0b47-b725-5d1a-9384-489a75ba690b |  | note | Reference - VESI_URD_003 -5.5.2.2
label | 0a020f5f-c3e7-59f7-932f-b1dccb101bbe |  | note | Acceptance Criteria - Marker tape shall be installed no closer than 150mm to the cover slab or conduit and no closer to the final surface level than 250mm.
label | 839ae883-23ef-5240-bcd1-0906e1c1c0bc |  | note | ○ Marker tape should be located no deeper than 600mm from FSL.
label | f014d2de-4331-5852-ba71-3e071cb15cd5 |  | note | ○ Tape to be one continuous length.
label | 8ea540c6-817f-5ca5-81a5-40d5d77dd56c |  | note | Method - Visual
label | 4b9d5669-efcf-5a2d-93bc-dd7e9eda45bc |  | note | Frequency - Each lot
label | 486b97f8-6141-5e36-a9c8-723779140706 |  | note | Category - HP*
label | 330e28ea-a1db-51d4-99bd-2993b8612e0e |  | note | Responsibility - SE/PE
label | 607c10fe-1fe6-52c3-92e5-7f45ea72c754 |  | note | Verifying Documents - This ITP
date | ad38cb7c-67e2-5fd7-a171-4d85b8e1bad3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Pit Installation
label | 202123b5-f511-5dfb-91b4-144b15fe5c2e |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003; cl5.9
label | 0f78317a-cb84-5427-9f3d-cda988431604 |  | note | Acceptance Criteria - Comms and electrical pits to be installed as per TC-2203
label | 09c31809-a4b3-59b0-8136-eebdc84d521b |  | note | ○ Pit chamber floor to be 100mm lower than the underside of the lowest conduit. Entry conduits installed 75mm into pit.
label | 76ca8c22-4e30-567a-b35a-40478b543045 |  | note | Bedding: 50mm crushed rock bedding
label | 69560cf4-eb52-52c8-b442-e4490cb7e1a8 |  | note | Backfill: Crushed rock is to be compacted in 150 layers arround the pit to bring the surface back to existing levels.
label | cbbcae4d-0024-52e1-8e9d-e9dae19d7a6d |  | note | Method - Visual, Measure
label | c0ae4c46-71e5-50ad-a0e2-8216131a6817 |  | note | Frequency - Each Pit
label | f2e08056-7a78-5b76-b553-98de1a72b250 |  | note | Category - IP
label | acdd25ad-67ed-506a-a48f-daf6bcef5900 |  | note | Responsibility - SE/Site Supervisor
label | ca087882-fc44-5036-80a6-dee65337de21 |  | note | Verifying Documents - This ITP
date | bad39874-0be6-589d-a3f0-c2ba9fb2f95d |  | date | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - As-built Survey
label | a33ba74c-c868-53fd-a695-2aecf70d4e1c |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | b2fc6b79-bcab-5ff8-b3c0-e2c3f151ee97 |  | note | Acceptance Criteria - Survey report to include but not limited to:
label | 438b656b-7d86-588f-9ad0-c7ee1e3d25e0 |  | note | – Cable pit locations (Corners)
label | 289ae640-91f2-52b3-b8f8-04703abe8f77 |  | note | – Pit dimensions & pit lid type
label | fba4294d-2433-59c7-80b5-ea680d51f7b5 |  | note | – Changes of direction
label | e56a2654-b19f-579b-8bdb-093879a7546a |  | note | – Spare Conduits
label | 572ee01e-aaaa-5439-afe1-11dbe3bb31ca |  | note | – Conduits labelled as per trench profile
label | 428c6f11-4888-5482-94eb-5eeb0630c0f0 |  | note | – every 10m
label | 2e6bf8bf-2c09-52e0-9ad9-14fb7a5c72b5 |  | note | – Other significant points of the cable route
label | 826bcfe7-18ed-5cdb-9d5d-783585ddf0b8 |  | note | ○ Attached Survey Report
label | 0360bd15-a23f-5e47-851b-a3ca1d3f4238 |  | note | Method - Document Review
label | 31fb8c82-0297-5259-a919-2de01518da09 |  | note | Frequency - Each Lot
label | ea708d54-3e53-5c7f-914f-fd14cc812ac8 |  | note | Category - IP
label | 1db48b5b-877f-5143-b24f-d8e85f42d713 |  | note | Responsibility - SE/PE
label | fa890235-1c98-5704-a9e0-08ae167ff77a |  | note | Verifying Documents - This ITP
date | 5e8d5221-cd60-591c-a210-140132032736 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Handover
label | ede0bd7b-fea8-5714-95f0-5546fe60302e |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | 9a9ba09d-1a81-5b88-9b66-65914d20fadb |  | note | Acceptance Criteria - Jemena Audit form complete
label | 94cc8b64-61b5-5ca7-b6f7-024f48c8e0dd |  | note | Method - Document Review
label | 86cbaab9-6862-5122-9c65-7977fd30e8b6 |  | note | Frequency - Each Lot
label | ca439f3d-da9d-5865-b934-7bae68686d61 |  | note | Category - HP*
label | 31aac4c9-e96c-53d4-abcf-a8e7da616dd4 |  | note | Responsibility - PE, Jemena
label | 798f187f-e4d5-5bd8-9900-961e984f238e |  | note | Verifying Documents - This ITP
date | d006002c-b1cb-5804-8b36-077b2bb288b2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | 8b72af64-8a93-5793-9757-2831469b7463 |  | note | Reference - MRPA Quality Management Plan
label | e4a40f2a-b838-5503-9be7-c77ef0b89e99 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 6a4ca620-a052-5ba7-9cc7-0cbcd035cc4c |  | note | Method - Document Review
label | 044ee160-e9e6-5be3-8c80-1ded70ba3249 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 90b7772f-b099-54db-911d-54801ca9dc5d |  | note | Category - HP*
label | 7341df55-548f-5352-910a-a89bebbaa804 |  | note | Responsibility - SE/PE/SPE
label | 2fe02882-fc04-52af-8f74-29f5735b01de |  | note | Verifying Documents - This ITP
date | 3a34bb5f-8b39-5df4-9773-07cddcad6774 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 339c5638-ffb7-5747-bb49-2600f321a2ea |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | f1add705-614a-5aee-96e8-a5c1cb52afe7 |  | textbox | Name:
text | 8515a0db-c0b0-5e75-8031-b62535e86d98 |  | textbox | Position:
date | b796480f-38d4-5b8f-add2-daa37bdc4227 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-047-CIV-CPD-Type B FIll - Road | itp |  |  |  | Yes | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | 51c5fee6-4576-467f-8804-773232db449e
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 238556f2-d3ed-5e38-8819-595bae5bb9ac |  | note | Document Title: ITP-CIV-CPD-Type B Fill - Road (Supply and Install)
label | 81e5da89-722d-5bee-b7dc-d250fba7279d |  | note | ITP Description: Type B Fill - Road (Supply and Install)
label | 5cdb59e4-d014-50a1-bf0e-1336da646ba5 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | d3f3e526-429c-566f-bbd5-34cdf01a9821 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
label | abd8a9d9-f56a-5b5b-a672-295fda6b7aaa |  | note | Revision Number: 1
label | 40222268-4f3d-5113-b7a4-14074b27f432 |  | note | Revision Date: 25/10/2023
label | 493eec9b-49c6-5401-87f9-d957f9f1f1df |  | note | ITP created by: Matthew Dib
label | ab42a86f-254d-55d4-a7ff-6a2f1ae0fbcd |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | edc683c8-f320-55b9-834f-c07f3134b756 |  | note | Reference - Reference Documents:
label | 6e638777-99c5-5d30-a075-9b8b0b9b8ad1 |  | note | • IFC Drawings
label | 40837480-245a-5b56-a9ee-e3f3ce03cc5b |  | note | • VicRoads Standard Section 176 (10/9/2008)
label | a5a69f99-ae40-5245-a663-a3712ee6d651 |  | note | • VicRoads Standard Section 204 (29/12/2015)
checkpoint-group |  |  | section | 2. Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 - Material Supply
label | 5bca1668-9f42-5837-9e42-e66adb23a36e |  | note | Reference - General Notes on IFC Section 204.4 c), 204.06 e)
label | 22c27b38-db86-5311-81f6-88d111d60441 |  | note | Acceptance Criteria - Free of topsoil, deleterious &/or perishable matter and maximum particle size ≤ 150mm. Swell < 2.5%. CBR >2%. Material classified as expansive or silt, either before or after compaction, shall not be used as Type B.
label | 0692d139-f06f-516b-ab89-b5f24a72010a |  | note | Method - Doc. Review
label | 2f3e0c7f-bf6d-5ca2-a4fd-9cdf93388967 |  | note | Frequency - Prior to Commencement
label | 008aa88b-46f1-5fd6-989b-081ab234573d |  | note | Category - HP
label | d0dbadd4-555c-57ff-a969-8a6f9667cf92 |  | note | Verifying Documents - NATA Test Certificate
date | 084d9e2e-edc3-5058-996d-51ebddc9adf1 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 - Survey Set Out
label | b66f58f6-cef8-5082-acff-4b9298880e99 |  | note | Reference - Design Drawings
label | 0ebadef1-db0c-5bf3-84c0-c1ea3251b301 |  | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
label | c10f054b-d450-5ce8-af36-eb7d7d391067 |  | note | Method - Visual Inspection
label | 0847cf5d-2649-566f-ba96-fde0e4c6fdbd |  | note | Frequency - Each lot prior to commencement
label | 098f8d9b-9b7f-5591-96c3-390b459c6dba |  | note | Verifying Documents - Signed ITP
date | ef60b33b-f6be-577f-bf69-2d1483de5bb8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Pre-Commencement of Fill Works
label | e3039a71-713c-53f1-9af6-05562d6272d1 |  | note | Reference - Section 204.10 (b)
label | d3bfd620-fa0d-5cc6-b51f-c285af4dbfe8 |  | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | ec640253-d01b-5781-94da-a82eecd2ea37 |  | note | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
label | 4e4ea450-8446-5edb-ad83-a54974b78c11 |  | note | Method - Visual Inspection
label | d0150e17-9256-547f-ab34-41c47529f16c |  | note | Frequency - Prior to commencement of fill works
label | a386c6c4-5ec2-51ed-b113-07002385d512 |  | note | Category - HP
date | e6572f72-131f-55e2-aa3e-2105bbc3f657 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Placing of Fill
label | 7d9fdeda-899d-51e9-aec9-dbfe8f115cb9 |  | note | Reference - Section 204.10 (d) (iii)
label | f92d7b5d-bc50-5dbd-9ec7-32f4d64f6346 |  | note | Acceptance Criteria - Type B material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm unless dispensation granted by superintendent.
label | 86f976d1-155c-55a7-9c2d-57ed4afdcca2 |  | note | Method - Monitor
label | 971e86c9-19b0-524e-a66b-c41cc36d39bc |  | note | Frequency - Each layer
label | f56628d8-dd7d-5216-82b4-2836d290a22e |  | note | Verifying Documents - Signed ITP
date | 3b1c324f-a7d7-558b-8cab-cc99d716052a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Keying of Layers
label | f0afdd0c-e977-5331-9ae1-56af5e71f307 |  | note | Reference - Section 204.10(d)(i)
label | d54e699d-8a3f-5542-8ea9-a182bf0d121e |  | note | Acceptance Criteria - Each layer of fill shall be keyed into the layer above by creation of a textured surface.
label | 5a91d9fb-6c7f-506b-9770-0e88fd10b298 |  | note | Method - Monitor
label | 4b942366-bc01-5f26-a4a1-5aebff614754 |  | note | Frequency - Each layer
label | e2bb6d05-4def-5368-bca7-8edf66877833 |  | note | Verifying Documents - Signed ITP
date | c9d555b7-6f4b-589d-a84a-3e4117a1d401 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Test Rolling
label | f493f69c-e8ca-5361-900e-ccc72642aef3 |  | note | Reference - Section 204.12, 173.03
label | 53a9c0bd-81fe-54da-aa45-9dc31c1aa494 |  | note | Acceptance Criteria - All layers of fill and cut floor level to be test rolled in accordance with section 173.
label | d7a90d11-1fdb-5d79-b83f-fd0143bb4001 |  | note | Method - Measure
label | 5ddb319f-a801-50c9-b315-756e65662db4 |  | note | Frequency - Each layer
label | 302117d3-3235-53fe-b064-b2475393ff1a |  | note | Category - HP
date | ece8beec-e611-5cc0-abc0-74473f4b54dc |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Post Compaction Testing
label | 3bc8ac1d-5a0a-5de8-843d-a9722f7278c3 |  | note | Reference - Section Table 204.131, 204.13, 204.14
label | 2013c772-f4a3-5ce2-8498-ec3c87bd33ad |  | note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level
label | 310298ae-e1e8-5a2c-b0e2-75a06ad3d1a2 |  | note | Scale B: Characteristic Density Ratio 98%.
label | 0258f297-895e-5171-9ab7-cb0df3d61d76 |  | note | Attach: Compaction Test Result:
label | 00a4815c-97b7-5700-85ed-74fe92c0cd72 |  | note | Method - Doc. Review
label | 3e1f624a-12e2-5188-9d1c-738367d55eb4 |  | note | Frequency - Initially test every lot until three consecutive achieve passing results. If achieved, minimum frequency of testing from Table 204.142:
label | ca5cab5b-f876-512b-b59d-7d55994c3b2e |  | note | ○ Placed within 400 mm of top of Type B: Test every second lot of like material and work
label | f9e2c15e-51d3-582d-bb5e-c7a535e5dabb |  | note | ○ Placed more than 400 mm below top of Type B material: Test every third lot of like material and work
label | 5b666f8c-ead5-5dd8-809f-0423141ee744 |  | note | Verifying Documents - NATA Test Certificate
date | 0004700b-db54-5d70-a993-3ea51a41cca5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 - Preparation of final surface
label | 922f2e93-472d-5bcb-bb03-e6af5ce713c6 |  | note | Reference - Section 204.15, 204.03 (g)
label | cdb7532a-2d15-5c1c-b11f-eb4a454f43d0 |  | note | Acceptance Criteria - The top of the Type B material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
label | 4ed21aac-3691-52b8-9035-782109d3f6d8 |  | note | Method - Measure
label | ff9e752b-a906-59f0-a4c2-4428f536f81e |  | note | Frequency - Top layer
label | 8280b1da-7862-51dd-99ce-9c66983d3ac7 |  | note | Verifying Documents - Signed ITP
date | 2846b091-b387-5b2b-bc3b-5a4a483e0c7b |  | date | Date Completed:
checkpoint-group |  |  | section | 5. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Survey Conformance As Built
label | 51a6e5c6-33f2-5461-85cc-a34d4d4e8ba3 |  | note | Reference - Section 204.10(h)
label | 5bc82fd6-fe59-5fde-93a3-e737b5ffde31 |  | note | Acceptance Criteria - The Contractor shall establish a procedure to verify that compacted layers do not exceed the specified maximum thickness. Verification records must provide evidence of measurements taken at least every three layers in consistent locations across the filled areas, and must be retained with the lot records.
label | 2d739730-aaf9-5c24-8b49-82fcbfc48fcb |  | note | Method - Review
label | 14dada8c-29a9-5bd2-a31e-a5a0c16aedfc |  | note | Frequency - Every 3 layers
label | 62fbedcf-dee2-58b6-8460-f416461b8ed8 |  | note | Verifying Documents - Survey Thickness Conformance
date | b209403a-1809-561e-a38e-a01e7c751ee7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 6a73f30b-f38b-5841-81cb-d23808f59b39 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 7a6529d3-4dbf-5e67-9db7-dde56f98c9d7 |  | textbox | Name:
text | 4e6cd2a3-baed-5525-8d19-28adc8275395 |  | textbox | Position:
date | b16e5600-a36b-524c-b0d3-76c612120908 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-046-CIV-CPD-Type A Fill - Road | itp |  |  |  | Yes | ITP-046-CIV-CPD-Type A Fill - Road Rev 0 | 5619ea3c-44b4-4e95-b2c1-4e01cb32eab8
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 04dff166-9dd8-5bc0-a59a-6d9dfeab4b8a |  | note | Document Title: ITP-CIV-CPD- Type A Fill - Road (Supply and Install)
label | 2e328150-ad80-516e-90ef-cfa5581b235b |  | note | ITP Description: Type A Fill - Road (Supply and Install)
label | 618d6363-7516-56a8-bc30-f93990bc1cb0 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | c6fc5f5e-87ab-5ed9-9037-9a2da1063ac2 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
label | 9d8abf76-5441-508f-b4ab-ff9c7bf139bd |  | note | Revision Number: 0
label | 47651862-5031-5637-9ace-f624191e10e5 |  | note | Revision Date: 12/07/2023
label | 1dc6e926-8224-5b5f-98bc-351e3c12570b |  | note | ITP created by: Matthew Dib
label | 1b7a676d-c1ab-5969-ab57-fc41ae66b9c7 |  | note | ITP approved for use by:
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 76b0e669-abb6-57da-93a9-d2f32151a410 |  | note | Reference - IFC Drawings
label | 17f45917-1af6-5194-8ce2-c7eb44b5d63e |  | note | • VicRoads Standard Section 176 (Sept 2008)
label | 45139a27-a71a-59d0-8b16-e6cb4d8e27c3 |  | note | • VicRoads Section 204 (Dec 2015)
label | 9792e7d1-e930-5283-a6bc-3abe30abbce2 |  | note | • Code of Practice RC500.20
label | 034472c1-2d1e-5515-b42a-6e878b689075 |  | note | • Code of Practice RC500.5
checkpoint-group |  |  | section | 2. Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Material Conformance
label | 425d55c8-ac7a-5e3c-80a0-5a62732e1bb3 |  | note | Reference - Section 204.04 b) Table 204.041
label | 12bc2454-34ed-533c-903a-799dc417c27c |  | note | Acceptance Criteria - Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
label | 8b2ead9f-fbbd-57c1-ad67-49349d13ca4b |  | note | • Assigned CBR≥6%
label | 44a7512a-e04c-59a8-8f07-c3a5f3cfa629 |  | note | • Swell ≤ 1.5%
label | e7cedf62-c5d0-5880-9958-7cd69517a655 |  | note | • Permeability ≤ 5X10-9 m/s
label | 5b61e4c9-7631-5c03-8df6-c276a4bf0594 |  | note | ○ Grading:
label | ced8d0d9-6123-5eeb-a7a9-b008fd82c536 |  | note | • 75.0mm 100%
label | 7fe02200-0009-5e62-ba49-ad35ec2a67d2 |  | note | • 4.75mm 40-80%
label | 542a4241-58d6-5ff8-b8c1-ce46563063c8 |  | note | • 0.075mm 10-40%
text | 645f5910-ebe2-5f3e-bba0-aca3bde3739d |  | textbox | Reference: Material approval in Teambinder:
label | 262ef993-9f76-5abe-bc43-69c339a4526c |  | note | Method - Document Review
label | b15c6888-c8dc-554a-a7b3-b54199b8d25d |  | note | Frequency - Once, for each material type
label | 3e70129f-1de4-5578-84f7-25616b289e6a |  | note | Category - HP
label | d83b16af-9fee-5b03-992c-bcaadfd21eb1 |  | note | Responsibility - SE/Nominated Authority
label | 36dbf726-fae6-51be-8cbb-75c96e139482 |  | note | Verifying Documents - Supplier Material Conformance Certificate
text | f10e62c9-3d93-585e-99e9-23ab1a25c3d6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 - Pre-Commencement of Fill Works
label | b7c34647-c4b8-5264-b632-643e8b90fe78 |  | note | Reference - Section 204.10 (b)
label | 83cec521-af0a-5bf2-8ac8-9d3d7c3774c4 |  | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | dc9ce301-7dc7-5746-b571-f1848c0bb5ba |  | note | • The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
label | 34e9a4d4-1068-5b00-8e19-607ce8381364 |  | note | • No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
text | cb38de53-c079-589b-a94a-edff130e8c5b |  | textbox | Reference: Fill foundation Preparation Lot Number:
label | 6dda44b0-7bb0-5bed-abcf-ab16a75ca024 |  | note | Method - Visual Inspection
label | 34151bf9-2f53-5ba6-bf60-cec811a9f0d3 |  | note | Frequency - Prior to commencement of fill works
label | e4fce539-17cb-587d-be43-2286b784a8f9 |  | note | Category - HP
text | 48a92bbd-9539-549e-be85-560f16c08a9d |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set Out
label | e5ebfe17-8862-5c5f-a8a4-18a59590cf51 |  | note | Reference - Design Drawings
label | 87f58417-3fbf-587c-b476-4c591f6869f7 |  | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
label | 8ff901ff-a5e3-565c-8f67-35d13ab31e01 |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | a6a95aba-ee65-5d8f-8cfd-49e14ec1dd08 |  | note | Method - Visual Inspection
label | a7c46065-950b-5a4e-9ec0-e40ab55b67a6 |  | note | Frequency - Each lot prior to commencement
label | b1bcb0f0-33d6-5450-adb8-b842858a8243 |  | note | Category - HP*
label | 6bb44688-09a3-5e41-913c-78a76f2d5dc3 |  | note | Responsibility - PE
label | 99750622-1290-5176-bca3-ab3e16be00a3 |  | note | Verifying Documents - Signed ITP Lot Map
text | e6f517fe-6fd6-51b1-aa95-41757524b20f |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Type A Fill/Verge Activities
checkpoint-status |  |  | checkpoint | 5.1 - Placing of Fill
label | 1daa79f5-f303-59e0-b236-475956a18fcc |  | note | Reference - Section 204.10
label | f67b7119-aa2e-5ad1-91e9-e3bb89aac3db |  | note | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm unless dispensation granted from superintendent.
label | 24a89339-3559-5662-bb67-6c574010486c |  | note | Method - Visual
label | 5d5a3776-69f9-50fa-80a0-ab756f9973ce |  | note | Frequency - Each Lot
label | ab05be17-4baf-56cf-b638-c38289087017 |  | note | Category - WP
label | ee424c06-5c39-5370-a601-9bee8d4afdf6 |  | note | Responsibility - SE/Site Supervisor
label | d080f5fd-2fc8-5584-8b91-5aad8ad54dab |  | note | Verifying Documents - Sign ITP
text | 8aaba3a5-1d61-5166-900f-113b3023cc3c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Test Roll
label | d9ee110f-b472-56b7-b77f-125fb67633a6 |  | note | Reference - Section 173.03 Section 204.12
label | 3244da56-85d2-5017-93b6-ee8b6b7a15c6 |  | note | Acceptance Criteria - Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
label | 4ed78b09-a3f7-519f-8c54-47b8a50c6088 |  | note | Method - Test Roll as per 173.03
label | a138b451-7031-5529-96fd-3d301e729252 |  | note | Frequency - Each Lot/Layer
label | e89a4c19-1c76-5077-af45-5e27c9c23033 |  | note | Category - HP
label | d38ec773-74f1-55d9-b9a2-9cd5db202597 |  | note | Responsibility - SE/Nominated Authority
label | 02981694-87c2-5256-a20c-8e49c5c786ee |  | note | Verifying Documents - Sign ITP
text | 5ce69613-8788-57ef-96d9-3662c9721deb |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Compaction Testing
label | 2345172b-c4dc-5fc0-b677-86c1770cc283 |  | note | Reference - Table 204.131 Section 204.14 c) Table 204.142
label | efdc2cf0-ac0f-5777-a2c0-3797e550db0c |  | note | Acceptance Criteria - Testing as per 204. Ensure testing is tracked and reports available.
label | dc464198-3c8d-525a-83c1-23cd01bcf2cb |  | note | ○ Standard Compactive Effort
label | 5d77e4ed-762f-5225-887d-5e901b3d85a4 |  | note | • For work to be tested for compliance with Scale A or Scale B compaction requirements, the number of tests per test lot shall be six.
label | 3e931e7c-7501-52db-87cd-3557f35faf15 |  | note | • For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
label | f68ca55f-d106-59ab-bc60-0e4104f87a4c |  | note | ○ Compaction and Moisture content
label | 0a4fbbda-42df-5b44-a819-f1b90582b889 |  | note | • Scale A: Characteristic Density Ratio 99%.
label | 246b59c3-8506-54d3-8b45-eea82a6debc8 |  | note | • Scale B: Characteristic Density Ratio 98%.
label | 98efe837-3fdd-5f78-9647-31295b0d6c7f |  | note | • Scale C: Mean Value of Density Ratio: 100%
label | e1c3675a-45b0-5a5e-8bb9-38e2771004a4 |  | note | • Lot size - the leser of one day's production or 5,000sqm
label | f2210a02-c083-5746-b46f-95aed580c343 |  | note | • Testing of every lot shall continue until three consecutive lots of like material and work have achieved the specified requirements in the first test. After satisfying this requirement and establishing a compaction procedure to the satisfaction of the Superintendent, the Contractor may seek the Superintendent’s agreement to reduce the frequency of testing of subsequent lots to every second lot of like material and work.
label | 08382353-c5fc-5872-9c71-070d54672054 |  | note | ATTACH: COMPACTION TEST RESULTS
label | 3bbbe73a-e118-5eb1-b8d7-dd31ac7607e6 |  | note | Method - Review Document
label | 70d3700f-88ef-5b56-bd3b-957b1bdcb693 |  | note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
label | 08a3226f-b143-5885-9c8d-2e331a76ea1e |  | note | Category - IP
label | c921312c-d068-589c-bd92-701fb5c52a6b |  | note | Responsibility - SE/Site Supervisor
label | a6e81cf5-5b8a-58bc-8b44-14e84b9f13ab |  | note | Verifying Documents - Sign ITP, Attach Compaction Test Report
text | ab47b4c7-fac8-5ba2-9bc4-23109f0e52ba |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Preparation of final surface
label | 9b24c781-0301-52f6-ab67-e82459f83e53 |  | note | Reference - Section 204.15, 204.03 (g)
label | d9b583c2-9cc2-5001-b028-5c0e42ac694a |  | note | Acceptance Criteria - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
label | e3862c83-ee01-5b3f-b68b-7542e6c9df6f |  | note | Method - Measure
label | ed4f6255-30b0-5f65-a6a2-8962ba80f072 |  | note | Frequency - Top layer
label | 8e9aadf0-3e0f-5adf-ac0c-832a23cadccb |  | note | Category - IP
label | 30467f77-3fb7-5cb7-962c-19975dfb9ced |  | note | Verifying Documents - Signed ITP
text | 04698542-b2f2-5ed2-bd23-77bde2230d16 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Post Compaction Material Property Testing
label | 360219e7-8bcc-589b-bf63-614e39f7cd68 |  | note | Reference - Table 204,041 Table 204.141 Section 204.14 a) or b)
label | c5851ff8-f55e-5ff4-8560-417a2be0e0e7 |  | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
label | d92164c7-d89d-587f-86da-e5e329550b1d |  | note | • CBR ≥ 6% and Swell ≤ 1.5%
label | 97818fc0-114a-535d-9fb6-993420c0fc26 |  | note | • Max Permeability = 5X10-9 m/s
label | 2b096aa2-ef1a-56dd-aa12-65a76eab51e1 |  | note | ○ Grading:
label | 96800a91-c8a3-58c7-884b-de2bd9442ebb |  | note | • 75.0mm 100%
label | afb008c9-0036-516e-b8cf-9c4861a3c406 |  | note | • 4.75mm 40-80%
label | 9c590be7-6107-5620-8381-a9436bbbede2 |  | note | • 0.075mm 10-40%
label | 7f6e35a9-9a2b-5143-ac14-0a4dac96d6bd |  | note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | ffadd300-21a0-5226-a4c1-7e0bbabc0ff4 |  | note | ○ Scale B:
label | 40489fb7-1139-5dd5-a504-6fb97d8a396c |  | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | a7c3fa0a-ac3b-5b31-ae34-a32cb9fc650a |  | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | 576fd385-bcd2-5b04-9904-40894963473f |  | note | Attach: Post compaction test results:
label | 1045710d-9dd8-56e0-990d-aeec79925c14 |  | note | Method - Review Document
label | b7948c2e-3816-5d25-b402-62acc2fb9b9b |  | note | Frequency - Refer to Section 204
label | ff151421-d598-5dec-9c60-a8d5fe8bdfca |  | note | Category - IP
label | f9cc41c8-e8e0-546a-90db-cb38e4a7fcf2 |  | note | Responsibility - SE/Site Supervisor
label | 9faa9b84-20a6-50fe-a579-9c01ba4ddff1 |  | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
text | 10a98b07-9aa8-55e9-bd5e-e3d392607aaa |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Survey Conformance
label | be92c2fb-eb93-510d-ad19-d3aed14f3092 |  | note | Reference - VicRoads 204.03f,g and h
label | 5f6f6e39-fec8-5bac-8c43-0d16dc135843 |  | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | 127f48d8-796d-5558-8212-47324ccbf5a0 |  | note | ○ Level tolerances Scale A:
label | 4f6d068e-bd29-5623-9272-2ac784007c7a |  | note | • Range x = +5, -15mm
label | a90325d6-4ea5-5351-8008-7ab3ae0b1e48 |  | note | • Max S = 12 mm
label | 50e2cc4d-ccb9-5215-988d-37906fe414ad |  | note | • 80 measurements per lot
label | b5784200-319f-5d39-9358-fdbc4472de9f |  | note | ○ Level tolerances Scale B:
label | 1e48be07-2ece-59d0-a181-865f69f8893e |  | note | • Range x = +5, -25mm
label | 6bf99577-f270-5b07-be2b-6e781f5d3a49 |  | note | • Max S = 15 mm
label | 78e5e603-bcd8-5b88-9c2c-c59ba999fc93 |  | note | • 40 measurements per lot
label | 6be9b64d-98f4-5ca9-8e9f-8b6dae2b0327 |  | note | ○ Level tolerances Scale C:
label | 831a17ba-ddee-558a-82c1-ad599c8374ec |  | note | • Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | 7ee7365c-1cea-5223-b01a-771287295a7d |  | note | Method - Document Review
label | 764939f0-487d-5636-b284-ba7d78a18c19 |  | note | Frequency - Top of Type A/Verge
label | 3ec689ef-8188-5e9b-bbd1-584980ac0572 |  | note | Category - IP
label | 306d8828-0fd1-5736-a4b1-146ccef0a809 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 0f69f592-453b-5ba1-b218-17af3155d40d |  | note | Verifying Documents - This ITP, Survey Conformance Report
text | 144a076e-6143-5229-9c59-99f9713efa54 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | 2a4e9695-02e3-5f4e-955c-f1cedfae2ddb |  | note | Reference - MRPA Quality Management Plan
label | 0ac6cd56-1ef4-51e4-88c4-29eb5eed1866 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | f1071e79-8b53-52ee-8683-6eec9fb98b76 |  | note | Method - Document Review
label | c2bc63fb-e42b-5ff0-a010-8fcf91dafb47 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 1ae8b622-83df-5c63-9ec3-331070490178 |  | note | Category - HP*
label | 7679b883-4ef0-5bf0-b1f7-f2a5f757dcf3 |  | note | Responsibility - SE/PE/SPE
label | 12643d86-9f7a-5016-b432-f3636c1a94af |  | note | Verifying Documents - This ITP
text | 97088407-c4b8-555b-b8e1-74b7a73d71ab |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 0ae9d3e5-fa94-57b3-9ab4-9dd60cdd2481 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | c34cd726-4ca4-55d1-86af-c46580d04874 |  | textbox | Name:
text | ebc653a5-e87e-5d4d-8970-33127db15e24 |  | textbox | Position:
text | 360777e6-6e81-5d3a-96a4-efae52176481 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-flat |  |  | checklist | CHK-006-STR&CIV-Material Inspection-Precast Panel | itp |  |  |  | Yes | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | 5b7df678-e46c-4437-a67a-50283502bd28
checkpoint-no-status |  |  | checkpoint | CHK-006-STR-RSS Walls-Material Inspection-Precast Panel
label | bce219b7-b6fa-509a-89b5-80ff6d021552 |  | note | Document Title: CHK-006-STR/CIV-Material Inspection-Precast
label | 62961c05-6e52-5a63-b493-048af47a0ceb |  | note | ITP Description: Material Inspection-Precast
label | 1ce143f2-b648-518a-a1db-efc1c77eb957 |  | note | Discipline (e.g. CIV/STR/RAIL): STR/CIV
label | 950d4f02-af4d-5973-8fd3-59ffecf085a5 |  | note | Revision Number: 0
label | 9764aeab-0311-54b9-84e6-b971cd585867 |  | note | Revision Date: 10/01/2023
label | 1ded3da7-3f02-5fbc-9bc2-21a0425b650f |  | note | ITP created by: Ethan Caruana-Smith
label | e2410e60-86e2-54b8-925a-ccfc60b3f660 |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1 - Delivery Details
label | 344ce80b-5753-5523-99ce-a6912c3581d2 |  | note | Acceptance Criteria:
text | a629c0de-2f33-5d5b-9801-eef0646c48e9 |  | textbox | Enter: Delivery Docket Number:
text | ed7ab148-de7b-54b3-b413-51c9c9dce335 |  | textbox | Enter: Delivery Date:
text | ddedbcb2-125b-5b85-81e2-ec3c935c43df |  | textbox | Enter: Element ID (s):
label | 911be025-2d1e-53c1-8338-e99cd948bf6b |  | note | Attach: Delivery Docket and packaging Slip
label | 0abd2359-95c6-5244-b6de-bc4255069a93 |  | note | Method: Document Review, Visual
label | 5579b877-be7b-53ef-9bec-0c58b7f9e63c |  | note | Frequency: Each Delivery
label | 629ea501-4efe-56f3-9aff-dd2395b02250 |  | note | Category: IP
label | 9307766b-5bb3-5a46-9bbe-d1950bfcefb5 |  | note | Responsibility: PE/SE
label | 71260619-b205-5ca3-b0fb-7c403992e3e8 |  | note | Verifying Documents: This Checklist
text | e641c54a-db88-5a91-b836-ff6697681389 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2 - Packaging Inspection-Quantity
label | 76bf541e-3bfb-549d-9e9b-a9b1fcd55d29 |  | note | Acceptance Criteria: Does the number of packages in the delivery match that listed on the freight list/packaging slip?
label | 88a4e3e5-040b-5011-a92b-395c8276f2aa |  | note | Method: Visual
label | bcc67610-b032-5fa3-9471-d264cd7ea468 |  | note | Frequency: Each Delivery
label | e557bc2f-fdfa-5169-a109-7ca26a5b001a |  | note | Category: IP
label | 73c1b1ed-5ec6-50fc-8072-c59d35d829da |  | note | Responsibility: PE/SE
label | fd0d2c3f-cf93-5fce-a58c-d760a84fc116 |  | note | Verifying Documents: This Checklist
text | 140fa2d4-5566-520f-a50c-02b817f55816 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3 - Packaging Inspection-Delivery Contents
label | 718f4e51-e2b5-52ab-bf55-0233fdd7bd68 |  | note | Acceptance Criteria: Do the contents of the delivery match the freight list/packaging slip?
label | 23f60db6-3ee5-5b2d-ab6c-fd7bffb8a9b2 |  | note | Method: Document Review, Visual
label | 8e04e7cb-e915-5601-9abe-816ead3a9461 |  | note | Frequency: Each Delivery
label | cc95b07b-7874-5dbc-aad4-a218ec958020 |  | note | Category: IP
label | cce42478-14e2-5252-adc0-705f2506bf9b |  | note | Responsibility: PE/SE
label | 5bca7a69-a2d7-5106-9e2a-72a8ea0c2b85 |  | note | Verifying Documents: This Checklist
text | 2bf60b37-269f-541d-be21-67294c071223 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4 - Packaging Inspection-Birth Certificate
label | 35276d7d-24e2-5302-8605-48974734332f |  | note | Acceptance Criteria: Is the delivery accompanied by Precast items Birth Certificates?
label | 3c50eace-c753-54a6-8660-e9ab5f91cc31 |  | note | ○ Precast components are to be marked on the birth certificate.
label | 3f02192b-5489-5330-9035-2bc61686b8e2 |  | note | ○ Cast date and lot are to be marked on the birth certificate.
label | 6c87b04e-a44a-5f8a-80b1-48ee2c1b6b6b |  | note | Method: Document Review
label | 71133996-3eb3-5aed-bd0d-8473062cc67a |  | note | Frequency: Each Precast item
label | e347bacc-d21b-554d-a5eb-63c78e225738 |  | note | Category: IP
label | a458bbf2-2456-544d-815e-4a116ce3fcf7 |  | note | Responsibility: PE/SE
label | f454f1c5-4c26-5b5c-b7e2-7e726824dac6 |  | note | Verifying Documents: This Checklist
text | a8077aba-0b0f-5c84-9b5b-0a2020cb087d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5 - Packaging Inspection-Transport
label | 208f2510-4016-5f4c-841f-c52ca7b1c3bb |  | note | Acceptance Criteria: Is the condition of packaging acceptable.
label | fc0a0845-30af-564b-ab57-b6a1815f2676 |  | note | ○ Precast items are protected from damage during the transport
label | 4a5e3b29-eee2-5e84-85c0-054fbacaf1c3 |  | note | Method: Visual
label | d3a33d85-a83d-53e9-9b70-e491657a3295 |  | note | Frequency: Each Precast item
label | 4eecb52b-2993-522e-9bfe-aa789a6b9534 |  | note | Category: IP
label | 805c2a14-74b4-533a-ae3c-2a408f40b3e3 |  | note | Responsibility: PE/SE
label | c20d38ea-0fcc-5cff-badf-4eeab1b27ab2 |  | note | Verifying Documents: This Checklist
text | b42deda3-3aaa-59a9-8819-0bb96f1ae887 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6 - Fault IDs:
label | af9bf072-4f51-521f-94a1-83f10f055a9a |  | note | Acceptance Criteria: For each precast type delivered, check for the following:
label | 8541fd75-648b-55c4-afaa-ef964e5ff77a |  | note | 1 - Identification markings match the element type
label | c316d1fe-42e7-5560-ab05-b043d1ca8cf5 |  | note | 2 - Element fabricated as per drawings
label | 82259ea4-a5a5-59a9-8a2a-0616685da0f7 |  | note | 3 - Cracks
label | 851b6e38-d72c-541e-b19b-799c7d6b0ab1 |  | note | 4 - Spalling/Damage to concrete surface
label | 826a8a98-4894-558b-a698-aa0c9e299923 |  | note | 5 - Exposed Reinforcement
label | d78fc058-a6a2-5d28-a4a9-509d269f2086 |  | note | 6 - Damage to Anti-Graffiti coating
label | d1970c36-8287-543c-9c5d-d9c365cfee96 |  | note | 7 - Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design
text | 262ffce6-2486-5b9d-b791-74d50d690fa8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Check for Faults - 1
label | 37482a30-1ad4-560e-8366-0ec4902552f2 |  | note | Reference: Item 6 on this Checklist
label | a65fdb1d-405a-5dc2-8fc2-375fe1f58e75 |  | note | Acceptance Criteria: For Each Precast type delivered:
text | 32800972-51f6-548e-9949-1f21a90503fd |  | textbox | Enter: Panel Identification:
text | 1bb34d5f-0a39-5091-9332-cf51e2cf6299 |  | textbox | Enter: Quantity:
text | c0b0aa8b-f59a-5943-b388-2dc4539679cd |  | textbox | Enter: Fault ID if any:
label | e7dbac52-3713-5b16-8ccc-0f6a360c87b5 |  | note | Method: Visual, Measure
label | fdbb5875-a28c-51aa-83f8-5763c3c8a6fb |  | note | Frequency: Each precast type delivered
label | e75086b1-a267-5767-a15c-d07a2118f337 |  | note | Category: IP
label | f930b2e1-c860-512b-80f7-89c775e2caa1 |  | note | Responsibility: PE/SE
label | a56cfd6a-d90c-56b1-86cd-4a9b472fdb5f |  | note | Verifying Documents: This Checklist
text | 98e84f62-b5d5-5e6f-87a6-b459537b992d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Check for Faults - 2
label | dd3718ae-8a31-5703-bac3-58a624e8c7c8 |  | note | Reference: Item 6 on this Checklist
label | a511ad41-f344-538e-9ab7-597f812f962e |  | note | Acceptance Criteria: For Each Precast type delivered:
text | 0550e532-2b50-54a3-ad43-daa88b8ecd56 |  | textbox | Enter: Panel Identification:
text | 4d792993-ce62-5455-904a-40089d3bb480 |  | textbox | Enter: Quantity:
text | 66d327e0-5346-5fee-885f-4d4c074c33b9 |  | textbox | Enter: Fault ID if any:
label | 14125e41-4a60-52d7-b020-9ba921fba05b |  | note | Method: Visual, Measure
label | e8062087-ac7b-5c23-956c-211db93a9bf1 |  | note | Frequency: Each precast type delivered
label | 8e0f2283-293b-501a-906d-8d31b5cfb5ab |  | note | Category: IP
label | 6ba7b633-d848-5a01-9f5b-68d5b5515d5b |  | note | Responsibility: PE/SE
label | acbd4257-5087-5db4-85b2-d05d2c8a618a |  | note | Verifying Documents: This Checklist
text | 25d8f4b2-9d6e-59aa-8e6f-8927df7f9e21 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Check for Faults - 3
label | 335bf7cb-77dd-565b-ac96-d07bafaf09be |  | note | Reference: Item 6 on this Checklist
label | e42fad3a-7a16-5e73-99a8-ae631da951a1 |  | note | Acceptance Criteria: For Each Precast type delivered:
text | fa43809a-d1a3-59cf-9517-28d0d61431ed |  | textbox | Enter: Panel Identification:
text | 0d0e22cf-8cf1-5325-aed6-4594fe24eb82 |  | textbox | Enter: Quantity:
text | 83dd9ba2-8bda-5467-ad0e-0731b8785de9 |  | textbox | Enter: Fault ID if any:
label | 4edd7b19-5fc0-5466-baa8-d8cec5e4feb0 |  | note | Method: Visual, Measure
label | d4ce2b9b-4c0b-56e5-97b6-a7a41d948ac1 |  | note | Frequency: Each precast type delivered
label | 688102aa-fe76-543f-b031-56e3e0ace731 |  | note | Category: IP
label | d9ceb319-3444-523b-a41a-cf92b3bfe3bf |  | note | Responsibility: PE/SE
label | 3109b6ba-21c0-5356-8bbf-fea3086df10f |  | note | Verifying Documents: This Checklist
text | 87c2f0ee-2ad9-52d8-95d4-ec5cc9283fc5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Check for Faults - 4
label | 0d302f9d-fbf9-532d-9af0-e11652c024d5 |  | note | Reference: Item 6 on this Checklist
label | 06df5cff-6cb5-526c-ae61-8d74a1bc003d |  | note | Acceptance Criteria: For Each Precast type delivered:
text | 147f2266-9a23-5470-8f93-39abf8296e05 |  | textbox | Enter: Panel Identification:
text | 26223c47-0c3d-566e-969c-d937ddeb75b5 |  | textbox | Enter: Quantity:
text | 1a730ba1-1f74-5103-84c6-9cc1cf71ae43 |  | textbox | Enter: Fault ID if any:
label | 3f54e94b-763e-5f68-ab61-bef25e849b27 |  | note | Method: Visual, Measure
label | 4233fa42-2ed0-504f-b5b9-78b3fd5d7214 |  | note | Frequency: Each precast type delivered
label | 546e4603-0b33-5b75-816c-5bd8d1d66f17 |  | note | Category: IP
label | 4eaf04c8-1dfe-5073-9a20-5cfaba5aead9 |  | note | Responsibility: PE/SE
label | ec2151c7-b2e7-5e62-9da8-4e5fe60437ff |  | note | Verifying Documents: This Checklist
text | f9aca46b-b30d-5027-8165-b291842bd845 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Check for Faults - 5
label | 849d9e62-b59a-53c0-84c1-97ee3f200dc8 |  | note | Reference: Item 6 on this Checklist
label | c98474e7-58ce-506c-b9cb-5a55bcec9e6d |  | note | Acceptance Criteria: For Each Precast type delivered:
text | 78352b2b-44b5-5ace-9f97-3af61f839659 |  | textbox | Enter: Panel Identification:
text | dce07498-f44f-5b95-aba0-51daf463fe2e |  | textbox | Enter: Quantity:
text | dde847dc-9ef9-5a83-b463-c1ea08bf8887 |  | textbox | Enter: Fault ID if any:
label | 7c0b39d2-b830-5219-8000-3e13af81b9e7 |  | note | Method: Visual, Measure
label | 61812628-a897-5161-8c0e-d00f22b6819e |  | note | Frequency: Each precast type delivered
label | 49b629f6-453e-5b61-851f-32f2ebac15de |  | note | Category: IP
label | 0565b5a9-e2f9-5a0d-af6c-0019e6f3beb6 |  | note | Responsibility: PE/SE
label | 93cc506e-37fc-51ad-9936-80129e34717a |  | note | Verifying Documents: This Checklist
text | 9499e010-7f54-5b56-ad3a-6fdc667b1797 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | a83172ee-8ad7-5893-bc6f-92943ea5b3d0 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | c19cd29a-ae10-5504-8728-2f3c5f66ebc4 |  | textbox | Name:
text | fb7803d9-b823-5eb4-a4ff-cc4ffe6ae410 |  | textbox | Position:
text | a3c967d9-8366-56f9-b8b5-c56c995b9989 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-075-CIV-CPD-General Concrete Melbourne Water | itp |  |  |  | Yes | ITP-075-CIV-CPD-General Concrete Melbourne Water Rev 0 | 74111725-680b-468e-ad41-fa0b1e69f627
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 4653338a-7c87-5de1-9e96-050800a934eb |  | note | Document Title: ITP-CIV-CPD-General Concrete_Melbourne Water
label | 2c8ebae9-1631-5b4a-8390-e575f194791a |  | note | ITP Description: General Concrete_Melbourne Water
label | 8c5635f0-b5b2-5dba-9335-d2c71c523617 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 96a735d9-ade2-593d-9e67-5c38492996d4 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
label | 9fd33d7d-c743-5be7-acf6-569a0a6ab542 |  | note | Revision Number: 0
label | e711c6a0-fe85-576e-a4d9-1a3a6b298d8f |  | note | Revision Date: 8/09/2023
label | 93b81387-33b3-5eba-b8e3-b4af2d532fa8 |  | note | ITP created by: Ethan CARUANA-SMITH
label | 97691837-5713-5d0d-8d89-a10b06b1ee46 |  | note | ITP approved for use by: Pradeep TALASILA
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 72745b8b-7131-5c73-8ce7-4bb15a65468b |  | note | Reference - VicRoads Section 703 June 2018
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | ed0f88e5-53e8-5e86-b792-97c373330e06 |  | note | Reference - VicRoads Section 812 July 2016
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | 70cf5ff7-9404-5d5d-97ba-5137ecb7c2d2 |  | note | Reference - Melbourne Water 7251/08/420
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | 119c0fe3-9dea-59e5-9ba8-2a3dbfbab6a1 |  | note | Reference - AS1379-2007
checkpoint-status |  |  | checkpoint | 1.5 - Non Dependent
label | 0fa8810a-d67f-5b7a-b2d8-cc1637518d1b |  | note | Reference - AS3610-2018
checkpoint-status |  |  | checkpoint | 1.6 - Non Dependent
label | af529cd3-139f-5279-bb48-2c7ca12ff740 |  | note | Reference - AS4671-2019
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Bedding Material / Base Layer
label | 000b2f2f-07fc-5547-adc3-f86538ed7475 |  | note | Reference - IFC Drawings 703.21 812.04
label | 37723d0c-8cd2-5c53-9d2a-798a692d843e |  | note | Acceptance Criteria - 20mm Class 3 bedding material conforms to specified requirements applicable to the class of product as detailed on the drawings.
label | 830fb834-790a-5501-8d63-29211a470663 |  | note | ○ Material is registered with VicRoads in accordance with Code of Practice RC500.02.
text | 1aeec655-e4dd-511e-8c76-9f9616760ef7 |  | textbox | Enter: Teambinder Material Approval number
label | fef6f844-7b68-5b89-9a1c-061c0edbae90 |  | note | Method - Document Review
label | 4c2212d6-66da-5e7d-9960-06bb16f9a24f |  | note | Frequency - Once, for each mix design, prior to placement of material
label | e27abaa2-b4e4-5a46-a110-bbb6f6b285df |  | note | Category - HP
label | 80fd637d-05da-5ffb-9c9a-b59343e3bdac |  | note | Responsibility - Nominated Authority
label | efd081f5-a691-5ea5-a1c1-3320b9d134b9 |  | note | Verifying Documents - ConQA Hold Point Release
date | 17c92423-a231-50d4-ae0c-8bc6cdc1cd58 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Concrete Mix
label | 3549c91a-6bfc-59a5-8c99-dbc21c880ccc |  | note | Reference - IFC Drawings 703.05 (a), 703.07 MRPA Quality Management Plan Melbourne Water 7251/08/420
label | 147e4a36-a043-510b-978a-101c2dd405f3 |  | note | Acceptance Criteria - Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings.
label | 9fd2837b-b60a-5c07-a802-4f6e111dc17f |  | note | ○ Paving concrete mix conforms to AS1379.
label | 26c36394-822d-5216-8bb0-045faab09950 |  | note | ○ SUP concrete mix is registered with VicRoads.
label | e0c5565d-187e-5749-820f-77a33dbebf17 |  | note | ○ No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
text | ed07b331-94a4-5247-9321-d194fb74c54c |  | textbox | Enter: Teambinder Material Approval number
label | 44033910-9938-57b4-9d8a-540b5e9352fe |  | note | Method - Document Review
label | e6255a53-c78e-55d1-92a4-c604d2afc8a0 |  | note | Frequency - Once, for each mix design, prior to placement of concrete
label | c2d83749-8997-5ac0-a835-a9b14ca55307 |  | note | Category - IP
label | f14b06ff-3761-5e78-bbe5-d61553fa1df5 |  | note | Responsibility - Nominated Authority
label | 6badb348-4ede-5591-a507-1c8942597e33 |  | note | Verifying Documents - ConQA Hold Point Release
date | 1edc6470-d241-51f2-b955-76b3545a5686 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Reinforcement Certification (or ACRS Certification)
label | e665e891-8633-59d1-819a-f9b652aef5fb |  | note | Reference - 703.13 MRPA Quality Management Plan
label | a008af05-3b71-5d8c-9e95-c83c99731cfa |  | note | Acceptance Criteria - Reinforcement shall comply with AS4671.
label | 53eeb21c-ff0e-5113-900b-2182aa13b204 |  | note | ○ Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification)
label | 97e788b6-b399-53bd-aa27-5103778be240 |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | 956f52f8-5eb6-5033-b9cc-e4d44659b096 |  | textbox | Enter: Teambinder Material Approval number
label | 023fdb67-16e5-5dd3-a110-440775551479 |  | note | Method - Document Review
label | 39fec9cd-23f0-55ed-9753-419f3ef722c9 |  | note | Frequency - Once for each supplier, prior to placement of order
label | f0dc7e99-d74e-56ad-bc10-108b5bedc4e0 |  | note | Category - IP
label | 98d7a4b4-ddb1-5a16-bca3-0a0bb407f9f2 |  | note | Responsibility - Nominated Authority
label | 2dbc8386-2826-5a09-80fb-c4adbd82f693 |  | note | Verifying Documents - This ITP
date | 65eebc14-14b3-598b-b1e8-aff40358df74 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Evaporative Retardant
label | c24808b2-4dc1-5b39-951e-39154010778e |  | note | Reference - 703.09
label | 2c90d8fd-e342-562c-bad4-0e7e89b042d7 |  | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | f1aac25a-eb60-5c40-8b80-cbd7b5f7f567 |  | textbox | Enter: Teambinder Material Approval number
label | 8946d981-e225-578d-8fcd-26cd79d77e2a |  | note | Method - Document Review
label | 8b96c432-b018-5c6f-a7d4-b9030b76d20e |  | note | Frequency - Once, for each product, prior to placement of concrete
label | 247034e3-4323-5cb4-829e-924d68f99e86 |  | note | Category - WP
label | 8b4d24d4-8e78-5005-aed1-572d09c2e957 |  | note | Responsibility - Nominated Authority
label | c141e75b-9c41-5a7c-8940-10e843116eb4 |  | note | Verifying Documents - This ITP
date | e45414b9-bf15-5881-b63a-b17880b7b919 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Curing Compound
label | b30f00c3-a226-55f6-939e-21fad51b14ca |  | note | Reference - 703.10 (a)
label | e62feeac-b3c5-5c72-83b0-ccd4e8ff327f |  | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
text | b02faaea-7141-5cb4-b514-6f6527a51f37 |  | textbox | Enter: Teambinder Material Approval number
label | 1b197ab3-65d1-5395-add4-5b82e95b84ee |  | note | Method - Document Review
label | e33c3bd5-a67f-50d0-8c6c-50c14f5b4be5 |  | note | Frequency - Once, for each product, prior to placement of concrete
label | bdd78c48-6a51-5194-830a-56722dfc41c3 |  | note | Category - IP
label | da489684-a85d-559a-afe9-62cce8821365 |  | note | Responsibility - Nominated Authority
label | 06cadd2b-8fb7-53c9-84e4-d239247bc0c8 |  | note | Verifying Documents - This ITP
date | 7aec5318-e7cc-5371-b74b-ca7cfbbaad94 |  | date | Date Completed:
checkpoint-group |  |  | section | 3. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 3.1 - IFC Drawings
label | 6426a222-bb73-5463-8f9f-b7150c566942 |  | note | Reference - MRPA Quality Management Plan
label | 5f2f9d68-2b89-556a-9931-acc8ad30fb07 |  | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | b6269227-a153-544d-8cc7-2645f996af9c |  | note | Method - Document Review
label | 67aecb2e-7848-5192-b226-8212f2faba6d |  | note | Frequency - Prior to starting Works and at regular intervals
label | e299f28a-0b14-5c3e-989c-e84fb597a36c |  | note | Category - HP*
label | 3d7f7aca-9d0f-5f64-a0d7-4c323448a6ba |  | note | Responsibility - All
label | ac4c7f16-a084-51d2-b15d-8a8ea74e00cb |  | note | Verifying Documents - This ITP
date | cb0d2c9b-56b8-5721-aa85-1efae77ccd87 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Survey Set-out
label | 69cb26f0-6a7a-5b47-bfb1-148d5fc35ac6 |  | note | Reference - IFC Drawings 703.17
label | 08d12c2c-d8a5-5f03-ba57-056b68b99a60 |  | note | Acceptance Criteria - The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | d9d886a2-9f1e-5d6e-a583-98dbfcb01133 |  | note | ○ The Nominated Authority will review and confirm the set out.
label | 6b90438e-d1ee-50dd-805a-766021c97909 |  | note | ○ Maximum deflection angle of 18 degrees
label | 88018fd4-c958-540a-a810-f1b5c8727f60 |  | note | Attach: Survey Report
label | 56765df2-1b26-5121-b6dc-9074eaa1b82b |  | note | Method - Document Review, Measure, Visual
label | 7996c7e5-3c86-50ef-a0f0-26d21da70c35 |  | note | Frequency - Where applicable, each lot
label | 6aef585e-ce2e-57e6-9ab3-65b1b2453349 |  | note | Category - HP
label | 719c928f-0687-5695-982c-3125ab2f036d |  | note | Responsibility - Nominated Authority
label | fe0b739e-c78e-5076-9fb6-a0a203b6f5e1 |  | note | Verifying Documents - ConQA Hold Point Release
date | 11a66558-217b-5df1-94a1-2c856d46250c |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Excavation
label | 88fed95d-3c22-5995-885c-6a46d88820c7 |  | note | Reference - 703.20 Melbourne Water 7251/08/420
label | 048e5428-e37c-5658-bf0a-e5f3b3a3c0ff |  | note | Acceptance Criteria - Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
label | 9d9a2648-32d8-502a-b897-e0950228d75f |  | note | ○ Excavation to allow for a minimum of 50mm reinforcement cover on earth face and a minimum of 375mm from pipe joint.
label | a39f535f-391f-5604-a7ed-f675e697f1f1 |  | note | Method - Visual, Measure
label | b3071921-0cc9-5f8a-8726-098cf294f7d8 |  | note | Frequency - Where applicable, each lot
label | c6a2a243-ad38-5325-8429-fd28a37bc708 |  | note | Category - IP
label | 3bd4d08a-0714-51d5-b683-bf876af50816 |  | note | Responsibility - SE/PE/SPE
label | dda87f13-9415-56f1-b248-e9c3b53a6a87 |  | note | Verifying Documents - This ITP
date | 6ac3921b-e04d-5a7f-b15e-2a927e005b67 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Bedding Material Placement & Compaction
label | 8371f887-92bd-568b-adda-1ce8934c5102 |  | note | Reference - 703.21
label | 8580478f-2eea-5fe8-aa98-7359e8fffb92 |  | note | Acceptance Criteria - Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings (equal to or greater than the relevant Council drawings).
label | 00b6303d-518f-554e-af21-c379b0056f25 |  | note | ○ Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
label | f2132e71-974a-520b-b7e2-bb7bd3d310bd |  | note | ○ The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
label | 1737aa7d-579d-5319-a515-15f6f9e1e0c1 |  | note | ○ All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
label | d173d864-7990-5e9a-b63e-101fa4485f57 |  | note | Attach: Bedding Material Delivery Dockets
label | 73ac1954-9cdd-5b72-ac05-9691e3922004 |  | note | Method - Visual, Measure
label | dffae503-2944-5ece-8fa3-090880e954b9 |  | note | Frequency - Where applicable, each lot
label | 94a7661a-085e-54f9-b031-91644baea92f |  | note | Category - IP
label | 481a9273-0620-5438-ae22-bcf0affc90f7 |  | note | Responsibility - SE/PE/SPE
label | 6a3dc31f-c074-5bca-bea7-e09d16b3e7e9 |  | note | Verifying Documents - This ITP
date | 35c4f32c-f1b0-5817-8419-250b4dc9ceb3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Formwork Construction & Placement
label | 8d7d287e-b762-564b-96fd-bf486e9044d8 |  | note | Reference - IFC Drawings 703.12
label | 86253e6b-2590-5029-a152-eea93f28784c |  | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete.
label | be9f6c12-1f73-5d54-adb9-bfbb41e5732b |  | note | ○ Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional comformance.
label | ee35bfb9-f10a-5e2b-a906-757dba06d37b |  | note | ○ Joints in formwork shall be constructed such that loss of mortar is prevented.
label | 872170fa-6ce8-5db3-91ff-fda55367a102 |  | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | 9e9998e9-e179-5cbd-b343-6fbca1c877a3 |  | note | Method - Visual, Measure
label | 96c60c44-d739-581a-a239-75b34b996583 |  | note | Frequency - Each lot
label | f7de3048-1c93-5fec-8af9-178c9a1d02cb |  | note | Category - IP
label | f170cf69-34f3-500a-9243-22bf5a78421f |  | note | Responsibility - SE/PE/SPE
label | fd97d0fc-e41a-5d49-9909-f85ae5028f6b |  | note | Verifying Documents - This ITP
date | a3471baf-5305-5dc1-8e97-5e3764b6f033 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Construction Joints & Matching Exisiting Surfaces
label | aa44e527-4c7f-58d2-ba11-5320dbe921d8 |  | note | Reference - IFC Drawings 703.24
label | 288f78d8-d194-557b-b3cf-d6e586bf486f |  | note | Acceptance Criteria - Where applicable, construction joints shall be placed where the new construction ties into existing structures.
label | 959e43f5-124e-5149-ae7e-b15b9f517e42 |  | note | ○ Consult the relevant Council Standard drawings for the joint detail, these may require:
label | c81b2168-2ff9-5672-a828-45dced7d9ece |  | note | i. Concrete cutting of a shear-key
label | b20a8be7-a71e-58d1-bcf9-f603a7c72c28 |  | note | ii. Surface roughening
label | ae2872ac-3c07-5c83-83c7-ad9a9b9e9442 |  | note | iii. Drilling and insertion of dowel bars (may also be galvanised)
label | 3f918921-dedb-57f6-9fe7-a2ce3134a923 |  | note | iv. Cutting a groove for sealant
label | 3a33104f-ed7c-5893-a0d2-9e7a991bf8c5 |  | note | ○ Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
label | b03ca746-b82e-5623-8459-e8551be9f76a |  | note | ○ Transitions between different profiles shall be made in accordance with the drawings.
label | c6312b00-bd9e-5d61-a308-30a7884324a5 |  | note | ○ Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
label | 1d245dc2-329b-505f-9135-09467e26cecb |  | note | Method - Visual, Measure
label | f97bf05a-530c-55bc-8a5f-bc07d141c466 |  | note | Frequency - Where applicable, each lot
label | e75c3338-6768-5b0d-b569-39298390ea13 |  | note | Category - IP
label | 465a0a85-d5b3-53b2-908f-897f1bce0426 |  | note | Responsibility - SE/PE/SPE
label | 4c298354-991a-5582-bddb-5303a0833a65 |  | note | Verifying Documents - This ITP
date | 1c78c08a-204e-5c30-8ad5-2f985e8b30a1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 - Isolation Joints
label | d85f4770-8333-5195-991c-b99ef3d200c5 |  | note | Reference - IFC Drawings 703.26 (c)
label | c49034ad-231c-5711-a4e5-ad9f121c37de |  | note | Acceptance Criteria - Where applicable, isolation joints shall be placed:
label | ed655f84-3bef-5ff5-802b-df3fa6274fda |  | note | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
label | 816763fe-8d67-5739-b450-b097534f2a74 |  | note | ii. at any location marked on the drawings
label | 556e00dc-b395-5b57-a6a6-2912ba01078a |  | note | ○ The joint shall be made with a compressable material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
label | db77ad3c-4d18-5f45-b6b9-497b53f2e8e8 |  | note | Method - Visual, Measure
label | f0549619-c033-5529-9324-2c9d40fbc1c0 |  | note | Frequency - Where applicable, each lot
label | 34dbe71a-b52c-58ce-8d85-71d5f66b1b5f |  | note | Category - IP
label | b77bbf58-4758-5103-bbee-297e04fb9af7 |  | note | Responsibility - SE/PE/SPE
label | 102cfa30-7fc0-59be-becf-9c66ae7e8c60 |  | note | Verifying Documents - This ITP
date | ef1b48e6-d303-5161-8f7b-94979808d2ee |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 - Reinforcement Placement
label | 8308e378-01ae-5694-8920-4c5584db78fc |  | note | Reference - IFC Drawings 703.13 Melbourne Water 7251/08/420
label | d68b1e85-1012-5191-8519-ce64b12ebe9c |  | note | Acceptance Criteria - The correct mesh type and location as shown on the IFC drawings.
label | 2101b24b-b8f0-54a5-b663-5e71bdc9574c |  | note | ○ Any splice lengths achieve the minimum length and are in contact for this length.
label | a4ed0c8c-3e5d-5466-9e37-19549c617229 |  | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | 9ad68f9a-dd1c-5664-adfd-786865cc47a7 |  | note | ○ The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
label | d9cadece-a5e9-5787-a559-5fc80e2638ea |  | note | ○ Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall not be used to support steel reinforcement.
label | 4071fb6d-2c4c-5916-a531-1bc107208b98 |  | note | ○ Minimum cover of 50mm at edges has been achieved (including tie wire locations).
label | aada9b25-0a60-5a90-b5b0-8ada5b3c8eaf |  | note | Method - Measure, Visual
label | 962b5467-8790-5045-bf64-0bff9724741b |  | note | Frequency - Each element
label | 043f19fe-c3e6-5d3c-b40e-9f6c8e9395c1 |  | note | Category - IP
label | 3feb5d1b-f8f4-5385-98f1-0afe0739c75b |  | note | Responsibility - Foreman, SE/PE/SPE
label | f3d4073e-215d-5829-ba13-9acfd0365362 |  | note | Verifying Documents - This ITP
date | a6087e27-d0eb-5ac8-a36b-ff4de91a9aec |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 - Pre-pour Inspection
label | a244640a-fb13-5bdd-8a5e-11fdc618ab07 |  | note | Reference - IFC Drawings 703.15, 703.21 Melbourne Water 7251/08/420
label | ca104637-bcf4-52f6-a618-cdef96323376 |  | note | Acceptance Criteria - Inspection to ensure that forms, reinforcement dowels and other embedments conform to the requirements of the specifications and drawings.
label | 0c7d075a-2a1b-5596-8306-234ff6301a5a |  | note | Method - Measure, Visual
label | 043f2d96-4791-5ff8-bdb6-bc8d51777598 |  | note | Frequency - Each lot
label | 26457566-8a53-5f6e-8392-e52ff8523e9c |  | note | Category - IP
label | e1b09f05-8858-55b5-8b08-052359e59820 |  | note | Responsibility - SE/PE/SPE
label | 879202db-fff5-5206-b247-b13a64554175 |  | note | Verifying Documents - This ITP
date | 395b1cf6-e685-5db6-b6fc-0f4f5dc51d1c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 - Weather Conditions & Evaporation Limits
label | 19ca0386-37fa-5419-bce5-718cc8a9b9ac |  | note | Reference - 703.09
label | 7e184674-74b7-5b97-a840-8f88e01796aa |  | note | Acceptance Criteria - Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
label | 3d6ce1cf-06a3-515c-bd3d-83c7fe978852 |  | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 889ed53c-3a15-5a0d-92ac-a35d7abd74d0 |  | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | a61203d8-38bb-554a-b4f6-087312bc6786 |  | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | 7b689208-c841-5b60-923f-7cdcf6b2172d |  | note | Record: Required information on the Concrete Pour Record.
label | 62fbc996-9d37-5248-bc11-870f24382907 |  | note | Method - Measure, Visual
label | 14bea358-8c47-5e55-b394-490bef268424 |  | note | Frequency - Each lot
label | 60aa04d7-b2cf-5814-a143-67a45bad6101 |  | note | Category - IP
label | 66c0b56e-f58d-5a2d-bbb5-893dcda751e7 |  | note | Responsibility - Foreman, SE/PE/SPE
label | ef9efe39-f788-5d7a-8528-0e170bbf0101 |  | note | Verifying Documents - This ITP
date | 2f44cbe0-4a3a-5acb-afbd-4f930cf098f6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.9 - Concrete Testing - Sampling Frequencies
label | d98ce424-59fe-5925-820b-79284d6efe56 |  | note | Reference - 703.11 Melbourne Water 7251/08/420
label | f0bee053-69ec-5c15-bb3b-0640d14560fd |  | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 1f5402d6-5742-55a4-a089-15cfc2f06122 |  | note | ○ 0m³ to 50m³ = 1 sample
label | 446cbb7c-f234-5b85-828a-8c6b4f7089d3 |  | note | ○ Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
label | ce83dcae-45db-537b-9305-f0b8e1cf907d |  | note | ○ Compressive strength cylinders = 2 no. 28 day strength.
label | 72917c0c-1f26-5335-b5d2-e1c1d65a71cf |  | note | Record: Required information on the Concrete Pour Record.
label | d280b638-70e3-5bf5-9df6-594fe023e94e |  | note | Method - Test
label | d960cea9-9ffe-54ab-b4f9-338f7d171ad6 |  | note | Frequency - Each lot
label | 67288153-515d-51ad-9c14-370d5a76ee44 |  | note | Category - IP
label | 8389a154-0b81-5650-9adb-0a8a913810a5 |  | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
label | 590d7036-5595-5244-b503-445906639905 |  | note | Verifying Documents - This ITP
date | 8768c1b5-5630-5cb6-9da5-b23c47be2be6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.10 - Concrete Testing - Slump
label | 528124a4-5dc5-5aa6-8b14-c892e5e595bd |  | note | Reference - 703.11 Melbourne Water 7251/08/420
label | d423b738-a635-5cb5-9823-c8a2f6138b1d |  | note | Acceptance Criteria - Slump testing tolerances =
label | ae97dee9-a785-5d58-ae34-c30842045627 |  | note | <60mm = ±10mm
label | 4331b4a6-e9f4-5d1f-9861-88a091c44b2d |  | note | ≥60mm to ≤80mm = ±15mm
label | c28eb7d5-e77b-5759-80c1-73a4c112a61f |  | note | >80mm to ≤110mm = ±20mm
label | 0de3aa26-0a08-54ce-a053-495fef32d1ce |  | note | >110mm to ≤150mm = ±30mm
label | 66621cdd-166d-5332-90f0-80f5351098bf |  | note | >150mm = ±40mm
label | aa738e69-d42c-597f-9eaa-c9d67023661e |  | note | Record: Required information on the Concrete Pour Record.
label | 73adfe84-de97-55f9-bc2b-ebc8e8e46553 |  | note | Method - Test
label | 603868d1-e59e-52a5-a820-cbc4c1015194 |  | note | Frequency - Each sample
label | 5bf9762c-542b-5d2e-9431-3464cb98f6a3 |  | note | Category - IP
label | 482372f1-b8bc-5677-9ba9-c9b075dd2bf5 |  | note | Responsibility - Concrete Tester
label | c929f9f5-6a7d-56f1-b423-083b550f808e |  | note | Verifying Documents - This ITP
date | 0a82b0cd-cadd-52c2-a934-410c5f6d1ab6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.11 - Concrete Testing - Compressive Strength Cylinders
label | c7ef0792-b734-5b82-92b5-a3860ddb3d93 |  | note | Reference - 703.11
label | d6e185d2-2fae-58a1-a97a-0008bdb8a69e |  | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
label | 1bb5da0a-d100-5fa8-9da3-4d40e80c8589 |  | note | Record: Required information on the Concrete Pour Record.
label | 8cd0bd27-870b-509b-9bd5-398e8c17bbe9 |  | note | Method - Test
label | 3fb3f7bb-0b3f-5815-992e-4d202e52da83 |  | note | Frequency - Each sample
label | dc76acdd-f211-5c45-9c72-415d7f37554d |  | note | Category - IP
label | 01e9c024-4d5c-5bff-93f4-59dc95ae0d39 |  | note | Responsibility - Concrete Tester
label | 3b4c6965-543b-51dc-abfa-82e401ab8365 |  | note | Verifying Documents - This ITP
date | 93087e4f-51c8-5891-a0bb-ad43802471aa |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.12 - Supply & Discharge Rates
label | 6fb3abab-a840-5754-8d04-348f737be34a |  | note | Reference - 703.08, AS1379 Clause 4.4.1, AS1379 Clause 4.2.3, AS1379 Clause 4.2.5
label | 36509d34-09c7-5a82-8e8c-b397ef25dbc3 |  | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | 98aeae15-a5fa-5ff8-b091-29dc302b1dd1 |  | note | ○ Maximum elapsed time for discharge (including compaction) is 90 minutes from batching.
label | 4c69807b-765d-5d8d-9265-a37526ae916b |  | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
label | 6b0edb11-f3f1-523d-99d2-c87794d0d46c |  | note | ○ If water is added once discharge commences, the volume shall not exceed the water-cement ratio for the mix design and the water volume is recorded on the concrete pour record.
label | 6c6dbaf8-6eba-5cf2-bca4-8f2e881eb282 |  | note | Record: Required information on the Concrete Pour Record.
label | 9eada15b-fedd-528b-8c52-7f427289459a |  | note | Method - Measure, Visual
label | 4691718a-b21d-5afb-9b5d-eee2d82460ef |  | note | Frequency - Each load
label | c5cd3177-4560-544c-884b-c66e1755f694 |  | note | Category - IP
label | 48f288f4-9b26-5926-8e3b-9b6bc4fd069b |  | note | Responsibility - Foreman, SE/PE/SPE
label | 53d2e5cb-d21e-5a1f-acdd-531c6468cfb3 |  | note | Verifying Documents - This ITP
date | 7daf97e5-9ba3-57c1-ad54-d32fb0a99742 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.13 - Placement & Compaction
label | b27dd459-89ef-58b0-8a82-fe5cf2063a72 |  | note | Reference - 703.08 Melbourne Water 7251/08/420
label | 19b55af9-38e4-53bd-b243-07b79741c69d |  | note | Acceptance Criteria - All concrete batches are traceable.
label | 7015a62c-16cc-52a0-9c6e-26b2716ca899 |  | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | 15161386-a02b-5c3f-b029-4fa966a30012 |  | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
label | 066766a7-cfdc-59eb-acca-5a0caa074d0e |  | note | ○ Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
label | 92165207-171e-52dd-a9d0-274d4e4cb075 |  | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | d410a271-e5f4-562f-8870-c184a556f7fd |  | note | ○ Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
label | 473a5b13-44d5-5c9f-a728-f7777967efe1 |  | note | Record: Required information on the Concrete Pour Record.
label | 4e150ffc-54da-549b-b679-39d8361ba6f7 |  | note | Attach: Concrete Pour Record
label | 66b3af8d-e511-58cd-8f89-2fe6587a06f8 |  | note | Attach: Concrete Dockets
label | 3ca341bb-3165-57e8-9d7f-dd591c06f8c0 |  | note | Method - Visual
label | 2f54d2af-0eef-5ea7-8bc6-2554f3acf1e2 |  | note | Frequency - Each load
label | 393d0cf6-cd84-59e1-9459-5e2a9c8351bb |  | note | Category - SP
label | 5c82ce43-b46e-53be-94ed-cab8e98708b0 |  | note | Responsibility - Foreman, SE/PE/SPE
date | 4fcaeb62-0176-51e3-ac14-954d3c169129 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.14 - Surface Finishes
label | c921b68a-d071-537a-9050-2635be562d23 |  | note | Reference - IFC Drawings Melbourne Water 7251/08/420 703.25
label | 23c4abbd-c5f0-5199-9ab4-0aabc533857f |  | note | Acceptance Criteria - Surface finish shall be as per the drawings or; as a minimum, finished to grade and cross section with a wooden float to produce a lightly textured non-skid surface.
label | 621219f2-c9d7-5759-8917-12576a59db7d |  | note | ○ All outside edges of slabs and all joints shall be finished with a suitable edging tool.
label | 6aebeeae-df98-53c7-a2a2-93bf8a7ecf3c |  | note | Method - Visual
label | f6e1ad3d-498b-5788-adfa-316b3b22cdb1 |  | note | Frequency - Each lot
label | da599b8d-3df8-5b48-8a65-cca4012bbd15 |  | note | Category - IP
label | f5c91fd6-aa06-56d4-8917-0a1d70598808 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 5ad6836d-3d72-5300-a56e-9464ed1322ec |  | note | Verifying Documents - This ITP
date | 51663458-9de4-5f04-8924-91a9e360dc86 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.15 - Marking of Conduit Locations
label | 43d5e2d5-5782-595c-956f-02f755509060 |  | note | Reference - IFC Drawings Relevant Council Drawings 703.28
label | 5ea2b454-847c-5801-9cb5-ae104e82254b |  | note | Acceptance Criteria - The positions of any existing conduits passing under edgings shall be marked by a chase in the edging immediately above the conduit together with the nominated identification mark shown on the drawings.
label | 799a9754-1635-553f-a72f-9a0b2a360de2 |  | note | Method - Visual
label | cd25786a-0f88-5e1c-b573-55adbb306467 |  | note | Frequency - Each lot
label | f6a7c4cb-d795-5750-b5c0-f5050468af68 |  | note | Category - IP
label | 8b69f2d9-8df2-5000-a0bd-3afeb25831b4 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 63bf04b3-d8a8-5421-8484-4c873e7f448b |  | note | Verifying Documents - This ITP
date | ebca278e-7d6d-5a1e-bc9a-5308c60dcbbd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.16 - Crack-control Joints / Weaken Plane Joints
label | 7f0bdf1e-0e5a-5f38-a923-7dc5006780b6 |  | note | Reference - IFC Drawings Relevant Council Drawings 703.26 (b) (ii)
label | c090ae0b-e7b6-5792-bb49-18baaf0028cb |  | note | Acceptance Criteria - Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
label | db77e76a-b06c-5ea6-9cd7-ea52c4cada4d |  | note | Method - Visual
label | dca562b6-1a21-567e-9b84-7aab3b92954b |  | note | Frequency - Where applicable, each lot
label | 182e0ea0-b7ae-593b-8be8-70b045a8dc2f |  | note | Category - IP
label | 44be92cb-9edd-592f-9551-5ec5370e8833 |  | note | Responsibility - Foreman, SE/PE/SPE
label | c4ee80c7-cd7d-5f25-b8b4-bd46cbd9a4f5 |  | note | Verifying Documents - This ITP
date | a960470f-d947-5cae-9006-4b0d01e203d7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.17 - Curing
label | 5c270ddd-2f04-56ed-86b2-1572a26e0a05 |  | note | Reference - 703.10 Melbourne Water 7251/08/420
label | d4c0072c-c72e-5b3e-bffc-5d3e031ce5d9 |  | note | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
label | d213cf11-213d-51b7-a599-a9cb11650045 |  | note | ○ Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
label | f969856f-3815-570b-9851-9b7fe1fcdac1 |  | note | ○ The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
label | 4c109aad-8c84-5259-8742-0b2410e2bd84 |  | note | ○ Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
label | da8dcaa5-a5b9-5e21-93df-de3bca9ec82d |  | note | ○ Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
label | 7cd5f37e-38f4-5d85-b3bd-25b16b58ee16 |  | note | Method - Visual
label | ca60aa9c-bb81-54a7-9f22-8abf3631193c |  | note | Frequency - Each lot
label | d955f8fb-a138-5267-84ff-6601923754ad |  | note | Category - IP
label | 96f461f2-1988-574f-8f64-ebdd8d55afb1 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 5cf74e6c-a932-5a62-a691-d45df054b3ba |  | note | Verifying Documents - This ITP
date | 4c5ab4f8-8dc4-539b-8723-02622188bdaf |  | date | Date Completed:
checkpoint-group |  |  | section | 5. Post-construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Protection of Newly Poured Concrete
label | 10c0234b-1833-5f35-b4d5-56c104cd3265 |  | note | Reference - 703.27
label | bdd86b18-daa5-54f9-b731-751e20a99763 |  | note | Acceptance Criteria - All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | f87b4e7a-e2be-5cd5-9398-72a15f13807f |  | note | ○ Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | ecb23cb1-d0f0-5603-bf4f-21f9818a4b63 |  | note | Method - Visual
label | 0e3108a0-c1b6-54ae-bdf6-70538cbda2f0 |  | note | Frequency - Where applicable, each lot
label | 3a1b5ca1-12c7-56a1-a6db-692bc69380e2 |  | note | Category - IP
label | f6f3564f-d1b5-5270-aa1e-adc24f141231 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 5171a3f9-7c4c-5f47-a581-7b12a04ac20c |  | note | Verifying Documents - This ITP
date | 57a474ab-1eef-51a7-bf4d-7332655ffc16 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Stripping Formwork
label | a1a8f5ea-6f91-5b3a-bbe4-fe38b6901808 |  | note | Reference - 703.12 AS3610
label | 522c0bd0-0645-5930-a22d-f4a5d3489ae6 |  | note | Acceptance Criteria - Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
label | 6fbb5c6d-e115-5695-8a36-17f2f194da45 |  | note | i. 2 days for vertical formwork on external surfaces; and
label | 4251cc87-90f5-5579-8b32-f1030f8d1e94 |  | note | ii. 1 day for vertical forms on permanently hidden surfaces
label | 630bd564-2707-51bd-bd2d-4cff0a3fd5aa |  | note | Method - Visual
label | 3f9f9a1a-efcd-5738-8890-ebad80708f31 |  | note | Frequency - Each lot
label | af83a91c-8ac1-5449-987f-7371f975bacb |  | note | Category - IP
label | 6bd31d00-a7c7-51f4-861d-b2f98512b895 |  | note | Responsibility - Foreman, SE/PE/SPE
label | f62c063e-64b2-58e9-9bae-7ce2a26100ee |  | note | Verifying Documents - This ITP
date | 36c6fba7-b60c-5a7b-a795-b9b6b7255d37 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Backfilling & Pavement Restoration
label | dd7ccb08-000a-57eb-9ffd-849c40c53364 |  | note | Reference - 703.29
label | 897594b7-1773-5a40-97a7-1e1977508a88 |  | note | Acceptance Criteria - At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
label | 50f35e5d-7192-5353-995e-abb235d1ea12 |  | note | Method - Visual, Measure
label | b493dcda-ab59-5dbc-bebf-8cd4e7b9e686 |  | note | Frequency - Each lot
label | d1429f3f-23e5-5892-8ba5-c2146150cb1f |  | note | Category - IP
label | 8f7f669b-d256-5b58-8029-22d2a5b6563c |  | note | Responsibility - Foreman, SE/PE/SPE
label | 0963c900-b4f1-5ba9-8881-d276e7b79294 |  | note | Verifying Documents - This ITP
date | bec9c22f-9ea5-5101-9d75-fa4febb00f6b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Surface Inspection - Cracks
label | aca1e765-8336-53e9-bf20-34af0d1eaf61 |  | note | Reference - 703.3
label | 87d7b69e-ae59-5021-b6aa-7f7883ab61eb |  | note | Acceptance Criteria - No cracks greater than 0.2mm. If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | c43eb3b5-f8d4-5a74-8765-5af2821d3efa |  | note | Method - Visual, Measure
label | a9d67844-258b-574c-acd0-07e5d06b5a4d |  | note | Frequency - Where applicable, each lot
label | 00b75b23-5265-5774-bbeb-49b96fab25ca |  | note | Category - IP
label | ee6b867d-1929-5137-867c-0119ff861870 |  | note | Responsibility - SE/PE/SPE
label | cc3c2026-c5c6-53ff-b758-e104189cb4be |  | note | Verifying Documents - This ITP
date | d63741f2-69eb-50b3-b909-0c152bb297d3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Surface Inspection - Surface Finish
label | a8b78811-9c2e-59e0-92c5-a1c315ce3952 |  | note | Reference - IFC Drawings Melbourne Water 7251/08/420 703.25, 703.10 (a) AS3610 Clause 3.2
label | 0fecb972-94bf-5d45-a9f6-15fd9071ccdd |  | note | Acceptance Criteria - After finishing, all work shall present a consistently neat appearance of uniform colour.
label | 2dc522be-a23a-5c55-b874-d2959aa85058 |  | note | ○ All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
label | 6c323a7f-a3cb-5423-a5e7-cfe135e0b1fc |  | note | Class of finish:
label | 8633039f-567f-5763-b2aa-7152a03c1c81 |  | note | Permanently hidden surfaces = Class 4
label | 3da6f88f-de9b-5c4c-b5c3-2b4db01ab231 |  | note | All other surfaces = Class 3
label | f8e551ab-bec2-526b-ae1e-554cd5d829b3 |  | note | ○ At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface.
label | b99c5a52-7ddd-5632-a609-4fcfc5cbe91d |  | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | 8766675d-3f84-5f13-be10-a2f986ad2319 |  | note | Method - Visual
label | 4df2cbd1-2bec-576c-b6ea-6cb93e26f8d3 |  | note | Frequency - Each lot
label | 5f0536e0-60a7-5786-82bc-976dd4bcde7f |  | note | Category - IP
label | 8be7b73e-4ad0-54ce-912b-66bdb0037b9d |  | note | Responsibility - SE/PE/SPE
label | cb827e1a-da58-5f09-ac2f-61823e19a26e |  | note | Verifying Documents - This ITP
date | a009e4e0-626e-5291-9b10-0c2f77f43cf5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Compressive Strength Test Results
label | c1a62914-e43e-53aa-8a1c-f5515c8516e9 |  | note | Reference - IFC Drawings Melbourne Water 7251/08/420 703.11 Table 703.111
label | b4ac3812-9c66-5151-8827-d2b8d3bc7105 |  | note | Acceptance Criteria - 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 0ec09cc0-84c2-50f9-af94-561277e9cbd6 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | edde4d09-be4e-515b-a472-08c2bcecd3a0 |  | note | Attach: Compressive Strength Test Results
label | 182e237b-79bd-55ae-b8f4-6040d025f67e |  | note | Method - Document Review
label | 219135da-4469-534f-aed6-bc74b8e44fd0 |  | note | Frequency - Each cylinder
label | 5322fe31-ca18-5cd2-9e90-5d1d8fabfda5 |  | note | Category - IP
label | 04cf2143-f324-59c5-b9f2-191ccc116616 |  | note | Responsibility - SE/PE/SPE
label | 2388493a-6eb6-5c78-878b-a709348e8992 |  | note | Verifying Documents - This ITP
date | 13131217-957f-5b87-9bd8-c8dfa66541cc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - As-built Survey
label | 3c30e129-fd9c-5089-ac9d-c596c8e9153f |  | note | Reference - IFC Drawings 703.15
label | 8b416ff7-1d58-5659-a760-d6db554616c2 |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | e951980c-76ec-50b4-893f-70ef9243b734 |  | note | Departure from RL = ±10mm
label | 780aaba6-762d-5d1d-b60b-c11deb6ce60b |  | note | Departure from alinment = ±10mm
label | e42b2f86-f6db-5651-8415-32c7fd09791b |  | note | Rate of change of deviation from RL or alignment = 10mm in 10m
label | 509d7b98-012e-5b6d-8579-dd7bc2cac945 |  | note | Irregularities in alignment = 5mm in 3m
label | 57866689-af7b-53e1-bb79-2a8f7bfeabb7 |  | note | Section dimensions = ±5mm
label | 7f0996dc-2efa-5810-a25d-555e499a4586 |  | note | Section dimensions (less than 25mm) = ±3mm
label | bb54b6ce-d5a6-54a9-a728-719f9091c25c |  | note | Width of pavement = -5mm, +15mm
label | 59fb6bc8-9bb8-5773-8c4e-1c4a7e7698aa |  | note | ○ Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges.
label | e6ae771b-744f-5a12-b093-23efc741cff1 |  | note | Attach: Survey As-builts / Survey Report
label | 83688ee6-aa62-58fc-819f-b752284bcf20 |  | note | Method - Document Review
label | f18a4b6e-4111-5eb7-8db3-bc5ce1fcc69e |  | note | Frequency - Where applicable, each lot
label | 38dba314-bd66-5f54-8a8e-572aef000f8e |  | note | Category - IP
label | 06d5c049-3e81-5870-b18e-8b164f5c1ad6 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 80faa364-a96f-5dfc-b519-39c56df243a7 |  | note | Verifying Documents - This ITP
date | 723364f3-9ef7-57c0-a133-703005f6bbe3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Non-conformance Report (NCR) Closure
label | ce0d933c-11a3-52f5-8731-f5c2cd66663f |  | note | Reference - MRPA Quality Management Plan
label | 44e2b881-d6f9-5b9a-9568-d0a40a4af45a |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 6820194a-614b-5438-a5e5-81126d806673 |  | note | Method - Document Review
label | 1c52f84f-18fa-5870-acc6-01289750d702 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 3348193c-6c6d-5ee3-98d6-76ccf2ebc590 |  | note | Category - HP*
label | 2df30883-7872-578d-b288-89e422cdc93e |  | note | Responsibility - SE/PE/SPE
label | 697f27df-2170-5b5f-b752-11ac5bc6f795 |  | note | Verifying Documents - This ITP
date | ca7b9721-1489-52c1-9fb5-a9e57506a612 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 8217accb-e5b9-5c67-8adf-84f47a8d9d24 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 1b8e50b8-4942-5883-872c-8522a9e1850d |  | textbox | Name:
text | 5077af21-7b71-5b9b-a8f9-dc425c1d7b34 |  | textbox | Position:
date | 12a7bc41-a47c-574f-b3e0-43b812c9ffa3 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-flat |  |  | checklist | CHK-010-CIV-CPD-Wire faced wall Installation | itp |  |  |  | Yes | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | 7b8afe80-1608-43c5-8a6e-b6353d90782f
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | fdd374af-847a-5f33-b017-e4483e5d7aa3 |  | note | Document Title: CHK-010-CIV-CPD-Wire faced wall Installation
label | 1057eb5e-31d7-5a09-beb3-01bcd50101e1 |  | note | ITP Description: CPD - Wire Faced Wall Installation
label | f8ead154-fb53-5746-aad4-91427d843f75 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 220a7ed1-35a2-5f8e-9b55-40b30ebf2ccd |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 11c08af7-8314-53c7-98a3-959b0de8f1ee |  | note | Revision Number: 0
label | b0f7bf73-c5cb-5755-9387-2f8c6abb48c5 |  | note | Revision Date: 1/12/2023
label | 5958646a-cab0-5910-acbd-4d0cdbd190f6 |  | note | ITP created by: Matthew Dib
label | 7bec2bca-798e-5ea3-afe7-8b87e42b10ce |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1 - Wire Facing Units-survey set out-Tolerance
label | 1b752fad-8cb2-5d55-af6f-8a4d5b05f580 |  | note | Reference - IFC Drawings MRP-DPK-080-00-CSW-0033-0-1201, MRP-DPK-080-00-CSW-0033-0-1206 VR 682.20
label | 68982d74-a860-5fc3-8d3d-9742aef53968 |  | note | Acceptance Criteria - Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
label | 46317428-c782-5d63-9a7c-0d0dc811f7c9 |  | note | Method - Measure
label | 3d45eb0e-ea66-566e-bd0e-08d1050521a9 |  | note | Frequency - Base course units
label | 565e0fda-3b51-5883-8d8b-f9c115f88874 |  | note | Category - IP
label | c3752e6d-5fcb-5c92-a060-087b7bf7d7d3 |  | note | Responsibility - Surveyor/PE
label | 881d800a-c1b7-5d7d-b23b-a5ef0cbb0550 |  | note | Verifying Documents - This Checklist
date | bef1d5b6-a514-5674-8a3f-371f0848c876 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2 - Wire facing installation
label | aed0dcb6-b869-5b3e-821e-ea0a9d4c03c2 |  | note | Acceptance Criteria Wire facing units are to be installed as per IFC Drawings and specified schedule.
label | a0e439e6-7da4-5018-9b13-ced43fe0b084 |  | note | – Connect adjacent wire facing units with stainless steel zip ties
label | 3534ffa6-c3b0-5088-bb61-4cc122d6bd92 |  | note | – Attach grid-strips at locations shown in Drawing 1957 for appropriate quantity given in elevations. Bottom layer of grid-strips to be attached with stainless steel zip tie shown in Drawing 1955
label | a6717d77-d9c9-5959-a181-f9401e838601 |  | note | – Cut the half-height panels at top of wall to correct height (refer Drawing MRP-DPK-080-00-CSW-0033-0-1953)
label | ca600287-a9c6-5937-90d2-a7a9024fae50 |  | note | Method - Visual, Measure
label | aba8e130-c8c8-513c-9f8b-32c643fafc5d |  | note | Frequency - Each wire facing unit
label | 8b8941bd-1d79-5b91-a0d8-a0b9ea6378ab |  | note | Category - WP
label | 1c1a6c28-9d11-531c-8ebc-e771ce544c3d |  | note | Responsibility - SE
label | 2d407d1b-29a5-5517-8615-67b28ee0b0ff |  | note | Verifying Documents - This Checklist
date | 289f1b67-9f75-57fc-83b7-416227854f45 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3 - Wire facing installation-Abutment interfaces
label | b7b18c69-98da-59ee-823a-20451a13ae4e |  | note | Reference - IFC Drawings MRP-DPK-080-00-CSW-0033-0-1106
label | d186c03c-0309-50bd-bedd-cda1d9e61471 |  | note | Acceptance Criteria - Cut any transverse wires as required for bends at abutments and wingwalls (refer Drawing 1955).
label | 8808b7ba-2b6c-541c-8e7f-62c8979eb08c |  | note | – Wire facing unit to be in contact with rear of panel (RW01) and side of wingwall (RW06).
label | d3a8c469-4a52-5fbb-a5b7-7cac30e4a1f1 |  | note | – Geofabric to extend along abutment as shown in Drawing 1106.
label | 96c819ba-6583-52e4-b718-646882d3fab1 |  | note | Method - Measure
label | e5a2f0ed-66d9-5191-a385-006df302b277 |  | note | Frequency - Where applicable
label | 766a1370-ebbd-5e0f-a7ce-966a0d786d66 |  | note | Category - IP
label | 0b850fa1-d911-5394-892d-c4c84b03de23 |  | note | Responsibility - SE/PE
label | 8101c466-4f5f-55ac-a225-08cbdb3a0c8b |  | note | Verifying Documents - This Checklist
date | 170cb56a-c5e8-5a7e-9fa1-4af5330302da |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4 - Geotextile - Installation
label | dcb48184-e5a0-521a-a23f-edce0e2ca93f |  | note | Reference - IFC Drawings MRP-DPK-080-00-CSW-0033-0-1955
label | bebb6fbd-f2ff-5184-aeaf-1c13d259dbdd |  | note | Acceptance Criteria - Install geotextile between cobble and select fill for all panels
label | 18b4fbe6-22e7-590e-95a7-459269d5870b |  | note | Method - Visual
label | e814c9cf-ad1a-5343-9b84-fab885468a92 |  | note | Frequency - Each wire facing unit
label | 56218383-32a8-58af-9e92-12a83001c56c |  | note | Category - IP
label | 36b6e610-b35d-5190-9af5-499009e2346c |  | note | Responsibility - SE
label | dc7303ab-68c1-5619-a7cf-db2634b3283c |  | note | Verifying Documents - This Checklist
date | 6a55a9a7-7479-5c4d-9358-61a1f492b0c5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5 - Wire facing installation-Survey reference points
label | c2e20c05-49c3-5306-9234-3c585ccf0c30 |  | note | Reference - VR 682.21
label | 12f406ff-24b5-5cad-abc6-25d821ed3e24 |  | note | Acceptance Criteria - To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS
label | 8c2859f4-818e-5146-b379-fb8803854d67 |  | note | Method - Visual
label | 7294b8de-8dbf-5bf1-a752-f4af36861589 |  | note | Frequency - Each course of wire facing installation
label | 0cc5ccf9-adec-57a0-abfa-83e9a25f21db |  | note | Category - IP
label | 5b73fefc-8dc4-5ac4-80e6-0f86f5071003 |  | note | Responsibility - Surveyor/SE
label | 7c414f4d-c7f3-5394-8b1b-211a14043c77 |  | note | Verifying Documents - This Checklist
date | 10339e29-68d5-5eb6-8428-cf904c4af324 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Panels installation-Conformance Survey
label | 5dfd4f02-59fd-55e0-930a-c94d9e02664c |  | note | Reference - IFC Drawings VR 682.06, VR 682.17, VR 682.20
label | f15c3a06-472c-5f8a-a583-5ded4e2a9024 |  | note | Acceptance Criteria - The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The
label | 75851f61-8154-5f71-8226-548b19ae8bdf |  | note | – Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
label | 0f9c6e11-224c-564c-b647-feded3678f46 |  | note | ○ Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall
label | 7c47e8c1-3781-5d4d-a72c-6cb7cdfba77b |  | note | ○ Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm
label | 66facd51-f982-52c6-89d7-8ac691c5e741 |  | note | ○ the wall level shall not deviate from the specified level by more than ±20mm
label | 7b18faf9-d6a1-56c8-88c6-12718b75b6bf |  | note | ○ the tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height
label | 63e6d3ee-1955-5c06-b4c0-a8d83c1e56c5 |  | note | ○ The wire facing walls shall be vertical when measured at the corresponding point for each row of wire facing units.
label | eeea2d85-6939-525a-937e-ab5f4f5911c3 |  | note | Attach: Survey Report
label | 1ee148f2-f150-5e24-93b3-30775fbc153a |  | note | Method - Survey, Measure
label | 8b6de733-36b0-5727-8624-3119ad22972b |  | note | Frequency - Each course of panel installation
label | ed4a0d08-201f-589d-94f6-371fd840f3df |  | note | Category - HP*
label | 775d7948-11c5-5c6e-91a3-2dc9c9fe38ad |  | note | Responsibility - Surveyor/PE
label | 1ab680d5-0b9d-5d0e-b467-fbb2b7117eae |  | note | Verifying Documents - Survey Report
date | 37993514-6637-5985-8845-a4156a48dcb8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 14f481db-ed7d-5c6c-aa54-454d61efb091 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 92f87b57-45b7-53a2-99da-6aac87fb1a0b |  | textbox | Name:
text | 53d99209-d921-5bd4-9926-2ec6a807d604 |  | textbox | Position:
date | 880fc71a-1b50-5262-ae16-30a96f01d413 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-049-CPD-RAIL-Calder Park-OHLE Wire Regrading | itp |  |  |  | Yes | ITP-049-CPD-RAIL-Calder Park-OHLE Wire Regrading - Rev 1 | 7efa8c2e-b70e-48d9-bb2d-4b498511bc9a
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | a32b4918-940b-59df-b037-fa678be9004c |  | note | Document Title: OHLE-ITP-MRPA-Calder Park-OHLE Wire Regrading
label | b24f3662-d736-5c6d-8c24-1d295100b84e |  | note | ITP Description: OHLE
label | 25492ccc-2582-53b0-8943-12fa0f2c38ee |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | ad3f5baa-9994-5773-8391-035c461cc5bb |  | note | Discipline (e.g. CIV/STR/RAIL): OHLE
label | 2ff6095e-5e05-59bc-8c1a-3f3a106d120f |  | note | Revision Number: 1
label | 7b1e0a27-d0fd-585b-ab34-32628600583d |  | note | Revision Date: 24/07/2023
label | 76f350fc-106a-58a1-9353-3bfa21a11786 |  | note | ITP created by: Kevin Liang
checkpoint-status |  |  | checkpoint | 1.1 - Overhead Line Electrification
label | b0e71249-5732-5839-8aa7-204459f9897d |  | note | Reference - L1-CHE-STD-011(1) MEST 000002-02(1)
checkpoint-status |  |  | checkpoint | 1.2 - Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | 7779b8a7-1e6b-53c9-8f90-7b8dbcb2306a |  | note | Reference - VRIOGS 001 AS 4100
checkpoint-status |  |  | checkpoint | 1.3 - Electrical Networks Standard Electrical Networks Principles and Performance
label | 030b68d1-71cd-5c0e-9f23-0387c5c47313 |  | note | Reference - L1-CHE-STD-015(1) MEST 000002-06(1)
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Procurement Materials delivered/collected to stores/Site.
label | 54441720-fbb6-54e2-8cc1-9ca4f15bccfe |  | note | Reference - Contractor - Site Material Control procedure.
label | c0bce270-39db-5290-9909-bc2c47a7b758 |  | note | • Cat5 Material received -Calder Park Tracking sheet
label | 3b6ef55b-9201-5c65-a128-3585c4986c4e |  | note | Acceptance Criteria - Ensure materials are delivered/collected as required.
label | f4ee23b4-670b-593e-a89a-961727b3bc66 |  | note | • Certificates of Conformity provided by MRPA
label | bd78a38b-586f-5ad2-9406-72a4423dad64 |  | note | Method - Document Review
label | caab6fb3-90b0-5893-a66d-d122f9b1eee7 |  | note | Frequency - Once for each supplier, prior to works start
label | f955e49b-709c-51b7-bd0c-72cb3503037e |  | note | Category - IP
label | 30a7aad7-fe4b-5159-b948-7cb08e009544 |  | note | Responsibility - MRPA Issue, CAT5 Receive
label | bb90ef3a-5489-539e-a3ec-461a9040c153 |  | note | Responsible person - MRPA
label | 3ad1ec87-e13a-5674-9029-aa29982fd44b |  | note | Verifying Documents - This ITP Signed Off
text | df87d913-b5da-5e87-8523-c5a62b89408c |  | textbox | Date Completed:
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Produce Work Package Plan
label | 647875d4-ab8c-5fa6-8e49-391202f8d49d |  | note | Reference - Work Package Plan
label | b7610fde-5ea1-56cc-a47e-805de3163062 |  | note | Acceptance Criteria - Submission of Work Package Plan and MRPA approval and acceptance. Ensure work is carried out in a safe manner.
label | def1689c-a197-56e6-aa61-18cc255c16bc |  | note | Method - Document Review
label | e2870b42-77a5-5e1b-84d1-5d9ad90f550d |  | note | Frequency - Prior to Works Start
label | 47a18377-211b-5f96-9465-1915acc64675 |  | note | • TBC in accordance with MTM Standards
label | c9c74a07-8335-5d37-b59c-c4950b67d386 |  | note | Category - HP
label | c95f874b-9c52-57d4-a123-382c705256e6 |  | note | Responsibility - MRPA/CAT5
label | 6358471a-4c1a-5c3b-b892-558e74d1ce70 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 2860e522-3ee5-5c5e-a9f2-a0971b13b4ad |  | note | Verifying Documents - This ITP Signed Off
text | a0b619fa-dc12-5c02-b0dc-232aa45ee6a2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Approval of IFC drawings
label | 25dbfc00-e399-5ca6-abde-bdd51077fc7f |  | note | Reference - Contractor Design Management procedure. MRP-DPK-060-00-ETN
label | c269feec-0bfd-5bcd-a7ae-31831e3339eb |  | note | Acceptance Criteria - Ensure correct and most recent revision of IFC design drawings are used for construction.
label | 404e5e9a-64ee-5f13-af6d-60a00acf2835 |  | note | Method - Document/Drawings Review
label | d9b6a5e5-4e8f-5d34-8329-36b075237912 |  | note | Frequency - Prior to Works and at regular intervals.
label | 158fd854-05e8-5929-b1ff-e8ff8acf739c |  | note | • TBC in accordance with MTM Standards
label | f782056f-48db-56be-b252-bb05cab118de |  | note | Category - HP
label | c870d3db-8fde-5b4b-951d-4fdb1182d6c6 |  | note | Responsibility - MRPA/CAT5
label | bef60c99-85cf-5472-8b1c-1100aa422779 |  | note | Responsible person - MRPA/CAT5 Engineer
label | a50307b9-ad1f-5342-8248-d328ef67cd0f |  | note | Verifying Documents - This ITP Signed Off
text | 4699bce0-8eec-568f-8233-df558510a9b4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Task Specific Permits
label | f5693ae4-51d0-5bdc-b68c-01197ecbde09 |  | note | Reference - Working at height permit. OHLE SWMS
label | be6a0bfa-dd26-5850-a84b-e6a0ccba74dc |  | note | Acceptance Criteria - Ensure all task and activities have relevant permits issued and received.
label | 3eac8767-508d-59f4-9ee7-be71a87a6bbd |  | note | • Task Permits to be generated and signed off by appointed person.
label | 2547ba90-72b5-58a6-8515-04a29f67b073 |  | note | • Task specific documents - MTM to issue permit to enter/Isolation permits etc.
label | ec1b4d5c-2480-5ec2-9cd1-e3f9b8b800c8 |  | note | Method - Visual, Document Review
label | bd3bdf82-9a9d-5848-a0c7-3c9a5b8d5558 |  | note | Frequency - Each Task prior to works start.
label | 6620f226-5971-5a24-af39-b497cb6a2c99 |  | note | • TBC in accordance with MTM Standards
label | 40a14e7f-b66b-5731-91c6-ab61c1901611 |  | note | Category - IP
label | 6e65d00b-e6e7-5885-93fc-6577fc136f31 |  | note | Responsibility - CAT5/MRPA
label | 69bdd03a-23f7-564d-bf66-f14fd2b487f5 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 4bdad0fd-9bed-5fd3-b8ba-3d3c30b28a64 |  | note | Verifying Documents - This ITP Signed Off
text | 561ca558-88d3-5449-8222-081dd03ace9c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Cantilever assembled.
label | c6f514ff-5b85-5b76-ae5f-db71e1a92cc2 |  | note | Reference - Cantilever assembled as per IFC design.
label | 54410576-e071-54ff-b894-47642dcfb53c |  | note | Acceptance Criteria - Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
label | 7f70a447-3296-5b97-8bd5-2048bdd1bbe2 |  | note | Method - Visual, Document Review
label | a7662440-4f59-5384-9cc0-c18322251eed |  | note | Frequency - Each Task prior to works start.
label | 1717de01-4438-5896-9e4a-6cc21c133f83 |  | note | • TBC in accordance with MTM Standards
label | 66fb8fcd-5d20-5803-947d-2c01af582821 |  | note | Category - IP
label | 49523014-be97-58e2-8c29-29682e00ef57 |  | note | Responsibility - CAT5/MRPA
label | ec8d59bc-7c66-5544-9eef-38c773955d85 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 81932f57-0373-533d-bf5d-69ce22f26c5c |  | note | Verifying Documents - This ITP Signed Off
text | 63e8aec9-4f7f-5b12-b365-f2664527ba8e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Pre-Installation check
label | a91c08d8-6384-5fa7-8087-08a9303875c0 |  | note | Reference - IFC wiring layouts, IFC cross sections and BOQ.
label | e3b8e6f6-0331-5c47-9aa5-1c9618f488c3 |  | note | • Engineering Drawings Management Policy (IFC/As-built) L1-CHE-MAN-001
label | 4d69206f-9f12-5690-97ef-16cb37c70214 |  | note | Acceptance Criteria - Ensure that locations matches most relevant IFC drawings
label | 2679c460-2750-5b67-aaf7-ceb62daf332b |  | note | Method - Visual, Document Review
label | 0e3016a0-62c0-5177-949f-8ce5a19f84d5 |  | note | Frequency - Each Task prior to works start.
label | 5e5f481c-b1ff-5c60-af3d-4f1b54ea2fee |  | note | • TBC in accordance with MTM Standards
label | 27998cf5-0dc6-5138-847c-2ae77523d8fe |  | note | Category - IP
label | 7ba89816-325d-5da0-b30c-b8a1dd8c3559 |  | note | Responsibility - CAT5/MRPA
label | 04ebf7e0-da85-5683-8f77-13716a65ffc9 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 61814104-be95-57a7-b96d-314684428da6 |  | note | Verifying Documents - This ITP Signed Off
text | 88c96d68-69d4-520d-8f87-9c05a72db722 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Cantilever installed.
label | 46babaf0-d542-598d-b243-d16c8d31c5af |  | note | Reference - Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
label | a0e36c4d-6bf9-510d-b641-fbdd9f666b6a |  | note | Acceptance Criteria - Work instructions in accordance to IFC design
label | f1dda229-c289-5dc6-b5bc-bc493e5eb90b |  | note | Method - Measure, Visual
label | 4b902408-c214-568f-833f-f2ffe38b040e |  | note | Frequency - Each OHLE Structure
label | f0dce753-f7e9-5016-ac82-1dcf63e778ea |  | note | Category - IP
label | 87b88d2d-ef3f-55d8-a17d-484bec024cf9 |  | note | Responsibility - CAT5/MRPA
label | dc03a787-ba63-5fe8-a9cc-39c40e54c438 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 8c039af6-eaec-53fe-8fae-14f26be2a424 |  | note | Verifying Documents - This ITP Signed Off
text | cbdf85a3-28cc-5a29-a0f1-c6d557a5142f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Install SPS to correct height / position relative to track
label | 3f49ec51-9932-514f-9d17-d8b2047e4e26 |  | note | Reference - Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | dcbc225e-93bf-5ae4-91a4-f1431fdef5ff |  | note | Acceptance Criteria - Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly.
label | e995ab48-9f4a-5fdc-a87c-8c29d0047dbc |  | note | Method - Measure, Visual
label | c5ee7828-1c17-5ea1-ae0a-201fc80dd52f |  | note | Frequency - Each OHLE Structure
label | bab6a7d8-c23b-504b-9816-35f7129d979e |  | note | Category - IP
label | 53bc6145-954b-5c67-91c5-7df31f70320e |  | note | Responsibility - CAT5/MRPA
label | 82b42f6e-d39a-53e6-ad04-6eaf22c66661 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 908bbc34-b7b1-568a-8f29-656ca5be4740 |  | note | Verifying Documents - This ITP Signed Off
text | 05777c99-1d8c-5e24-a52d-0175c6596b40 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Cantilever checked once installed.
label | acf75bd7-67eb-5787-a3e7-c23d8f3be8ab |  | note | Reference - Cantilever checked as per IFC design drawings/MTM design range. Completed check sheet.CAT5/OHLE/CHK002
label | 10373dc7-d52e-5cb4-8e0c-a2eeba8b1597 |  | note | Acceptance Criteria - Supervision checking to ensure that equipment is installed correctly.
label | 3e19309a-fb3a-5912-9c71-1862aa63d414 |  | note | Method - Measure, Visual
label | 9a8f3773-f711-5484-935f-a0025e4efe38 |  | note | Frequency - Each OHLE Structure
label | 3eef33ed-d060-5161-818a-67b77e065384 |  | note | Category - IP
label | 80e4972f-c054-579d-a4ec-64409289227d |  | note | Responsibility - CAT5/MRPA
label | 59773a61-49cc-5c46-8218-8c175358af61 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 262efde4-d01c-5504-a1b4-d422bb6fc0a4 |  | note | Verifying Documents - This ITP Signed Off
text | fd70e711-a0cf-5756-b39e-9479e50515b7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Installation of wire supports at the correct height and stagger.
label | 0cfcd28f-03ee-56d3-9c6e-12b45a52ecf5 |  | note | Reference - Install as per design drawings.
label | e4efe236-000d-534c-8644-905b6ae8c1e6 |  | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
label | 5bcca83a-6398-53fc-9a89-0f11b0d4e902 |  | note | Method - Visual
label | 03b9fe89-920c-5c59-bd3d-3194104e6528 |  | note | Frequency - Each OHLE BWA structure
label | bb3c2c82-e2a7-5e35-9c20-b9cad02f8ec2 |  | note | Category - IP
label | 1c77a65b-a7b8-5fa5-b9e5-f764a2da5b8e |  | note | Responsibility - CAT5/MRPA
label | 9fab31a5-26b9-5f93-ba2c-af1437e999c1 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 3a6c2ea2-2def-5657-81c8-767ff34c380a |  | note | Verifying Documents - This ITP Signed Off
text | a15d33f4-22a2-5f9b-b57d-1f8b9ba971b2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Installation of small parts
label | 01a6bf55-fe0e-5dae-8cea-a806ac0f6a33 |  | note | Reference - Install as per design, use span/ambient temp. tension charts.
label | ff75c1b3-9a05-5327-a803-83a409b6f2a3 |  | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
label | 5fe3c8d8-b4c5-538e-b3c6-70bd9f1b32e4 |  | note | Method - Measure, Visual
label | bae12386-ad01-5f14-ae96-021dd9689cda |  | note | Frequency - Prior termination
label | 049e82bc-b4c4-5efc-9ffc-ea355c0bd9a1 |  | note | Category - IP
label | 300b6b3a-112f-5c8b-a643-8f261499ad9b |  | note | Responsibility - CAT5/MRPA
label | 3d3a7935-ef13-5990-8128-3867d448141c |  | note | Responsible person - MRPA/CAT5 Engineer
label | bac1c9f5-f9e6-5bc6-b914-80fc885e216c |  | note | Verifying Documents - This ITP Signed Off
text | 8adb4494-5bf8-5d89-8fc3-a087a0ae59cd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Complete Clearance Checks
label | 96e12612-ca9c-5885-b9ac-ea845f610e0b |  | note | Reference - Install as per design, use span/ambient temp. tension charts.
label | 8d8dd6ad-0c7c-5279-bfd3-9e5298846e68 |  | note | Acceptance Criteria - Visual inspection for clearance and wire staging from Hirail EWP
label | d4940203-2538-59aa-acc6-f58d35656e06 |  | note | Method - Measure, Visual
label | e87512dc-8f7d-55cd-9cb9-9f8a70d2416c |  | note | Frequency - Prior termination
label | e0f6ce63-5600-59a5-a195-1c99018bf51a |  | note | Category - IP
label | 15a4daf7-81fd-56af-91a2-8b51fd545ce5 |  | note | Responsibility - CAT5/MRPA
label | 0ecd002e-102c-5c4e-b7f6-d82cd9dcabf7 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 28ff49eb-cb96-5369-a071-2264c7ce497a |  | note | Verifying Documents - This ITP Signed Off
text | 2a42cc65-30bf-5c9d-a604-923a29fc6dc1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Complete Pan Run Test
label | 81a48cdb-b208-58b7-8f97-d9992f0d3c0c |  | note | Reference - Install as per design, use span/ambient temp. tension charts.
label | 65116da3-f7c2-5698-bea3-4cd747d22d13 |  | note | Acceptance Criteria - Check for wire take up, clearance, stagger limits and pantograph interaction to the contact wire
label | 04e8a10e-15e7-50a2-8ec0-2506a6f4ba73 |  | note | Method - Measure, Visual
label | 27fc42ac-2c22-5399-b825-773b5a6d4b00 |  | note | Frequency - Prior termination
label | 3b7fe085-bbd2-50df-b813-7e8473721916 |  | note | Category - IP
label | 596278d9-8f1c-58bc-8afc-d3eff7febff7 |  | note | Responsibility - CAT5/MRPA
label | cc9798b7-c56e-5b0b-9612-51270f42fbbd |  | note | Responsible person - MRPA/CAT5 Engineer
label | 9b901689-cef1-59e9-9587-5de88a4d0297 |  | note | Verifying Documents - This ITP Signed Off
text | bd832821-46fb-53de-bc27-03938d98398e |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Defects/Temporary Works
label | eec8f481-2a40-502f-bc3b-44b3db3ac3b3 |  | note | Reference - IFC wiring layouts, cross sections and design drawings.
label | 98ef030a-e015-59fc-861a-d66f37749259 |  | note | Acceptance Criteria - Ensure all Defects/Temporary works are capture and closed out correctly.
label | e6cb15dd-ea29-5e22-94d3-6602589e7e20 |  | note | • Defect list to be provided at the end of Occo identifying planned work to rectify
label | 640fe297-343f-55d0-9da0-a273f1af8169 |  | note | • Attach Design mark up, Defect list, temporary bond register, and approved TW design
label | 4de6b930-d150-57d4-adf4-34d54d0e6d5d |  | note | Method - Document Review, Visual
label | d9f9dedd-c24d-53bf-b0dc-cb2364dce366 |  | note | Frequency - Each OHLE Structure
label | 3c96d655-8276-5b16-8eb8-982d5b411e5a |  | note | Category - IP
label | 90f688aa-dd5a-5007-86f8-604832b8845a |  | note | Responsibility - CAT5/MRPA
label | f2cf3eaa-589b-5e8c-8be7-7d4c955441bb |  | note | Responsible person - MRPA/CAT5 Engineer
label | e76874d9-3dcf-5f2e-9e56-653fda0eab08 |  | note | Verifying Documents - This ITP Signed Off
text | 52c032e1-d094-5125-9a04-2b491f96d651 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Relevant documentation readily available. (As-built Survey)
label | 73fd6133-97c5-5748-b0e1-5c77ae4044cc |  | note | Reference - As built drawings and check sheets to accordance to MTM Design spec.
label | 90fca279-7bd9-5a24-ae89-1645d315c920 |  | note | Acceptance Criteria - Ensure delivery of relevant documentation to client.
label | 8f162cbd-862c-53e5-ba1f-e5836b38d5d9 |  | note | • As built drawings and check sheets.CAT5/OHLE/CHK/002 check sheets.
label | 26fe2918-5922-5ca0-966c-04d0b2be1918 |  | note | Method - Document Review, Visual
label | 9adac229-0d5e-5586-bb68-e2e8fc5630f2 |  | note | Frequency - Each OHLE Structure
label | 298e6225-2bdf-51e5-9c2a-5fe7706f7151 |  | note | Category - IP
label | 5f7262c5-45a7-5c09-9b34-c6efe70a3d5f |  | note | Responsibility - CAT5/MRPA
label | 2a95a4ec-feb4-53a3-8be8-9d26485dda4f |  | note | Responsible person - MRPA/CAT5 Engineer
label | de63686d-8807-57c4-a5ce-245df97f28d9 |  | note | Verifying Documents - This ITP Signed Off
text | 8ac3918d-1b09-5b6e-9c72-ddc29fd4ca8d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | 34ef5da5-0fd8-5c77-a52f-1f90a7f17d3d |  | note | Reference - MTM Quality Management Plan
label | e30c34da-27c4-5d0d-8323-6e6871e15db0 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 20fdd725-2040-5c87-814d-52fc7256a97a |  | note | Method - Document Review
label | 50b5cab6-21ae-5c0a-8081-ab21758dac42 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 3e43dfd8-96ac-552e-b248-e9fb750b7f5a |  | note | Category - HP
label | d6071b4b-2cfb-5ef2-abe4-cadbdf8a2a75 |  | note | Responsibility - CAT5/MRPA
label | 57deea1c-4c99-5837-83d7-970e1b715070 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 121d5590-2517-53cb-bbc6-6938e940adc5 |  | note | Verifying Documents - This ITP Signed Off
text | 687d1eb8-2574-5c17-a9df-7c2123e8bf5d |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | 9b47ebcf-8d0c-5760-aaac-2b4d451d3fac |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 6819ad12-5e86-5f4f-a24e-08239dab2609 |  | textbox | Name:
text | 7b5045be-d17f-5b25-b8da-95c5214d527c |  | textbox | Position:
text | 49fce55a-18dc-5059-9808-a61c0ae69067 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-045-CIV-CPD-Subgrade Preparation - Road | itp |  |  |  | Yes | ITP-045-CIV-CPD-Subgrade Preparation - Road Rev 0 | 9430c0e8-7582-45cd-bdc8-07b023f65665
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 7528f190-4343-5025-8b1e-528d2d9de0f6 |  | note | Document Title: ITP-CIV-CPD-Subgrade Preparation - Road
label | aaa761ab-3732-580d-9648-a5cd54f95c3b |  | note | ITP Description: Subgrade Preparation - Road
label | aab28051-4d93-54b3-b9ab-33ceaa561a9d |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 5c1d458b-4804-521b-9d62-ba7b625d9a5d |  | note | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
label | 437a1dda-629e-52a0-a8b0-041f8633de3c |  | note | Revision Number: 0
label | 60823dcb-b438-5709-8bc9-c8433430c392 |  | note | Revision Date: 12/07/2023
label | a034d993-29b4-56be-ad05-f59c38b94c9c |  | note | ITP created by: Matthew Dib
label | 1ec0b0cc-c1f5-56ae-8819-961862550527 |  | note | ITP approved for use by:
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 8001842c-e8f6-57fb-b222-6919b0f65418 |  | note | Reference - VicRoads Section 204
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 0b420d85-5188-58ba-ac75-13e88ef529d3 |  | note | Reference - VicRoads Section 173
checkpoint-group |  |  | section | 2. Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Non Dependent
checkpoint-group |  |  | section | 3. Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 - Non Dependent
checkpoint-group |  |  | section | 4. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-Out
label | 92b8bc7c-0f24-5f3f-8d04-19e7fafeb1cd |  | note | Reference - IFC Drawings
label | 69784157-e96d-5af0-a8c3-23c13af41a7d |  | note | Acceptance Criteria - Area has been set out in accordance with the drawings
label | ff167d6c-9f9e-5592-83a3-fdff8f3589db |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
label | 3d41f110-1874-5e5b-9fc0-17cb21b10254 |  | note | Method - Verify
label | f5973371-b5eb-5762-bbc6-fb5d33154ed3 |  | note | Frequency - Prior to commencement of excavation
label | c8bfbfd9-1af2-56f2-bb39-627c5e221c96 |  | note | Category - IP
label | a9f9025a-de76-5f2b-b26a-50fd2d30869a |  | note | Responsibility - SE/Surveyor
label | 013ee332-2057-5223-a622-210662cf1ab3 |  | note | Verifying Documents - This ITP
text | 4e8b7852-b687-5215-a0c4-da98a49cf4f6 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Inspection of Subgrade Material-Subgrade Material Properties
label | 2bdd789a-590b-550e-9877-560dadc46cd6 |  | note | Reference - Section 204.06 (c) Section 204.06 (e) IFC Drawings
label | ae0922c9-49c6-59c7-836d-69f6aacee5d7 |  | note | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
label | 592e1378-f6da-5917-b7c5-f14a0fc5ea75 |  | note | • Assigned CBR ≥ 2.0%
label | 753d4573-6990-5138-9b66-4f45131492e4 |  | note | • Assigned Swell less than 2.5%
label | 8bddbe8c-736c-579f-9c5a-00ffd80d1a99 |  | note | • If parameters are met, rip and re compact to a depth of 150mm.
label | 78fc6b54-23d9-51c4-b940-c7fc22f262c2 |  | note | • If assumed design parameters not met, remove 400mm of material and replace with conforming Type B fill.
label | 3badb9dd-e517-528a-9b45-d84c6c65f2c0 |  | note | • If existing material needs to be removed and replaced with Type B Fill, ITP-CIV Type A/B Fill - Road is to be utilised.
label | ecf92566-2511-5e3c-bb1c-2333101b8f72 |  | note | Attach: Laboratory testing Verification:
text | 9e84f50b-1a6b-52a6-936f-53c051b760cf |  | textbox | Enter: Type A/B fill Lot Number:
label | 55d72201-f997-533f-9d5e-23be8434b22c |  | note | Method - Verify-Document Review
label | b38f8eba-0704-5b66-8017-2847545f72b7 |  | note | Frequency - Each lot
label | 5f14b3dc-576a-55fe-9a2c-ecdcc7fee1d9 |  | note | Category - HP
label | 52ee2822-4898-58a8-a671-054db7a9d298 |  | note | Responsibility - PE/Nominated Authority
label | 8792767d-86cb-5c6c-9322-56454fb74e15 |  | note | Verifying Documents - This ITP/Test Report/Referenced Lot number
text | ef8771b3-be1f-532d-b8ec-1311e5e3b26b |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Material classified as silt
label | 47c295e5-d53c-5a3d-a69c-d45140037f47 |  | note | Reference - Section 204.04 b)
label | 9f071f05-e20a-54e7-a056-6f89f7791b07 |  | note | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
label | 70e04e18-557a-558c-8d71-cfbd719636e1 |  | note | Method - Document Review
label | 61dec7c8-c92d-5362-a773-10b7b0a7999a |  | note | Frequency - Prior to commencing
label | ba41a107-e41f-5fcb-96a7-c3cdb6951451 |  | note | Category - HP
label | 42a3433c-dfa3-542f-aacb-e1822486378c |  | note | Responsibility - SE/Nominated Authority
label | e0ad02b7-e98e-56bd-a674-652e4b9c2789 |  | note | Verifying Documents - Superintendent satisfied with Stabilisation, Signed ITP/ records
text | 642aac42-4690-574d-8057-d68303bb2756 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Acceptance of Rock Subgrade (where applicable)
label | 76b47cd4-cc3b-5c7e-8d87-f08bcf9d4089 |  | note | Reference - Section 204.06 f)
label | 64fc65df-f123-5d91-88dc-0572cd2ea923 |  | note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | a6015c38-efbf-59e0-a517-764dff1cac5d |  | note | • Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | c38d6e61-adb1-5559-9d5e-62bce7fb5db4 |  | note | Method - Site Inspection/ Document Review
label | b31b64af-b876-5e40-9dd1-9751636574e6 |  | note | Frequency - Prior construction of the regulating layer
label | 77763d8a-60ce-5aaa-8330-e248b24ae92b |  | note | Category - HP
label | 6c53df8b-354d-5e58-8d6f-531e41aede24 |  | note | Responsibility - SE/Nominated Authority
label | b7aeb5ac-2283-560d-95d3-52cdc0f6a486 |  | note | Verifying Documents - This ITP
text | 0f1c4a40-bf8d-5e15-92eb-cfb1e25f2ce7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Unsuitable Material
label | 28637f27-eaf7-5be4-88da-777592a2daf8 |  | note | Reference - Section 204.07 d)
label | 4ee12dad-2e21-58a0-b273-0c7dbb8c729a |  | note | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
label | 6a657f8e-ae64-5f69-99a7-7e1e1b9866dd |  | note | Method - Visual inspection
label | ab393f88-697d-547c-891a-6d7e78973f03 |  | note | Frequency - Each lot
label | 77bad8b5-45a8-5f90-9c35-d663e4f73afc |  | note | Category - HP
label | 79f88cef-cac3-5aec-985f-506b9bbcf11a |  | note | Responsibility - SE/Nominated Authority
label | 341c15c8-e2e0-5dd3-b553-1cd4cc68d14e |  | note | Verifying Documents - This ITP
text | 25d2ce05-845f-5da8-89be-97ff1260146e |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Groundwater
label | ef343f13-e50b-5da7-8a84-e093c4d5a21c |  | note | Reference - Section 204.06 h)
label | 553a028e-a3f3-5266-bba5-6377136eed5f |  | note | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | 4224f83f-f9cb-5cff-89fe-b1c8fae0c323 |  | note | • The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | c5fcd095-4929-5abc-97ab-e5fe82d60455 |  | note | Method - Visual inspection
label | cb35badf-1863-5735-b1c1-ae4e765516b4 |  | note | Frequency - Each lot
label | a6f3a1bb-a48f-56d2-b31a-07b7f663ae6c |  | note | Category - HP
label | e8ec8778-934e-5ac4-b845-7d428923cdc7 |  | note | Responsibility - SE/Nominated Authority
label | 321c9b77-559f-5c77-8850-2e0d0029e0b2 |  | note | Verifying Documents - This ITP
text | 5cc29c93-d7de-5004-bc70-edbf8bd26523 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Cut to Fill Zones
label | ef28fff6-7581-5a5c-ab8f-4b05185198c4 |  | note | Reference - Section 204.06 g)
label | 3740c484-3c6b-54eb-8dab-33ba06d58700 |  | note | Acceptance Criteria - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A/B material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A/B material.
label | d2067d64-9d70-5c10-a702-ce2fda4178e0 |  | note | Method - Site Inspection
label | 271825e0-9032-5c98-9acf-c4eaae8913d0 |  | note | Frequency - Each lot
label | d7fa463f-ff5d-555e-9341-fcaa58cf3328 |  | note | Category - IP
label | 62bf0744-cfab-555e-8ea4-d9958fe4b7e2 |  | note | Responsibility - SE/Site Supervisor
label | d21ae106-4872-528c-9664-04246baf6f04 |  | note | Verifying Documents - Sign ITP
text | b7853a3f-89bc-5801-a22c-68fc8e9429d2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Proof Roll
label | 5f3b3b00-da79-5f70-bc4b-e313b36e579d |  | note | Reference - Section 173
label | c4e504ad-695b-522c-b17a-cdcad9f2b836 |  | note | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | 508d3ee8-213d-5ad1-92a6-28c55123ebb8 |  | note | Method - Visual inspection
label | d5ffe7ed-e254-53b0-8069-3c6fcdcc8987 |  | note | Frequency - Each lot
label | 145e8b0f-9872-570e-b580-d47b7bda2c4e |  | note | Category - HP
label | c1ee7c7f-c73e-5f50-9a3b-a4dbb871bdf7 |  | note | Responsibility - Site Engineer/Superintendent
label | f8adeb94-f708-594a-9294-8b10a7ce524d |  | note | Verifying Documents - This ITP
text | e8841163-2d3a-5df2-8ae8-8b18e8c3f3dc |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.8 - Compaction Testing
label | d57adf16-9421-572e-b4b8-dbd82f284b34 |  | note | Reference - Table 204.131
label | e3dbf970-9030-5587-b14e-b74169b5bc7a |  | note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and
label | b4804177-9c95-573b-a756-31886a0486b0 |  | note | • Ripped and re-compacted material below Cut Floor Level
label | db61d721-c6bc-5d4f-a6a5-55b15a87f3cd |  | note | • Scale B: Characteristic Density Ratio 98%.
label | b1e2ed62-9bb6-5bb2-b4b5-7ed16ddf8a4b |  | note | Attach: Compaction Test Result:
label | ddc47195-8f0c-5643-bbef-4e37faa0410c |  | note | Method - Document Review
label | 69930ca9-0e1d-55ff-a6f9-30d727e58333 |  | note | Frequency - Each lot
label | d3d77cbc-48e6-56f9-a13e-105eff55b590 |  | note | Category - IP
label | b9a7605a-22a6-58d9-a440-590963cc44a0 |  | note | Responsibility - PE/SE
label | 89aa4ba2-bf69-581e-881f-28a966fd5d40 |  | note | Verifying Documents - Test Records, Lot Register
text | 6f29cbb8-4dd8-5399-beff-85aa39d1a2c5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 - Post Compaction Material Property Testing
label | 4ae9b3e7-8a12-54d1-99bd-faa1cdf30a9b |  | note | Reference - Table 204,041 Table 204.141 Section 204.14 a) or b)
label | f5710c54-1e84-5b92-a5f7-830085788686 |  | note | Acceptance Criteria - Material Properties:
label | ad89f386-e9d4-5372-a868-7501995be6f4 |  | note | • CBR ≥ 2% and Swell ≤ 1.5%
label | c2117359-31fd-5765-889a-e7bee849a3f2 |  | note | • Max Permeability = 5X10-9 m/s
label | f24e6698-1386-5684-8536-ba05524ad8e4 |  | note | ○ Grading:
label | c58faac6-e896-525c-a11d-55fd4d1a335d |  | note | • 75.0mm 100%
label | db326a2f-d598-5bfe-b546-f5ef655ae1e6 |  | note | • 4.75mm 40-80%
label | b0499f27-fb8b-5ad8-85de-454ec66c0d61 |  | note | • 0.075mm 10-40%
label | 7c059b4b-9219-5f86-96dd-eff2cc5ae94f |  | note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | 38d1faac-8ac9-5314-adde-4296e4e314e8 |  | note | ○ Scale B:
label | 8afa9151-0146-5863-8d72-841d801468c2 |  | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | 7c34bbba-08e2-5054-a1b8-c61bbc2bb70d |  | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | b7a7f372-b7b6-5ae6-a786-987a3bd8efa5 |  | note | Attach: Post compaction test results:
label | 062f77fc-d78d-5c47-accd-8dace84592d7 |  | note | Method - Review Document
label | 51f8bee4-78a0-5201-ac8e-2233a55008ff |  | note | Frequency - Refer to Section 204
label | 2cd4ef93-85d9-5248-a4a6-539e9e5531c9 |  | note | Category - IP
label | c9482379-d5c9-5c2d-8d50-965324b74aca |  | note | Responsibility - PE/SE
label | fc808f2e-1cdb-557e-b086-3b82c92e0284 |  | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
text | eff53af4-12f9-5149-be92-f8bd6bcd573e |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post Construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Survey Conformance
label | 20060779-5a77-5092-a6e5-776a091596b1 |  | note | Reference - VicRoads 204.03f,g and h
label | 7eed938e-9995-501a-8e5e-5519c55c9e4d |  | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | 1387e5f0-f68f-5c45-b871-376cc627e08e |  | note | ○ Level tolerances (Scale B):
label | 35e26a69-1726-587b-809c-4f2b298e5382 |  | note | • Range x = +5, -25mm
label | 6bcc3e01-eab6-54a4-bf72-89385e157d83 |  | note | • Max S = 15 mm
label | 38ee0337-3c92-5ac5-aae1-6f4b2e1c27e9 |  | note | • 40 measurements per lot
label | bb92d6a5-2093-59f1-9499-c35b6b5307ca |  | note | Method - Review Document
label | a828d010-5c8f-5e91-8047-93f965d5abf3 |  | note | Frequency - Each lot
label | f3c686bf-6e0b-5acc-b9a5-848b18ffb438 |  | note | Category - SCP
label | 3d276712-2c98-546e-8762-4841d5a5806f |  | note | Responsibility - SE/Surveyor
label | 574bf915-86aa-51a6-8b38-61942295620c |  | note | Verifying Documents - Sign ITP, Attach Survey Report
text | a448b87e-fc1e-5e41-bf7d-a0b4996be48f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 25c9af64-aa07-5448-8829-5645b0a39ac1 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 490ce730-3f19-599e-8aee-2917414efb0e |  | textbox | Name:
text | 496d3e96-9853-5840-8843-b9f1cabca955 |  | textbox | Position:
text | f9b058e4-08e6-54d4-b8bb-1fc719ff9336 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-flat |  |  | checklist | CHK-009-CIV-CPD-RSS Walls-Fill Placement | itp |  |  |  | Yes | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 1 | 993c9fc6-174a-4a27-9b6e-1ab1d06b864d
checkpoint-no-status |  |  | checkpoint | CHK-009-CIV-CPD-RSS Walls-Fill Placement
label | 6128f4a3-3107-522a-a68e-c4a22df59cce |  | note | Document Title: CHK-009-CIV-CPD-RSS Walls-Fill Placement
label | 6dba2edf-05ee-58aa-87b7-414470589d6c |  | note | ITP Description: RSS Walls-Fill Placement
label | 36ad6b0f-fd9c-523e-bcd0-ead7a2b1dce0 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | e7909d05-ea40-5202-bf76-77004b896022 |  | note | Revision Number: 1
label | 7362251c-9954-597c-b25a-9aea862c72d2 |  | note | Revision Date: 14/12/2023
label | c19d2176-023b-59b6-b5c0-8805fcc6e4d0 |  | note | ITP created by: Matthew Dib
label | 7a6b3ddd-aef9-5a46-8f16-60b1ff9ef102 |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1 - Soil reinforcement-Straps
label | d60805f8-a405-5cc9-b4ec-a315a232b02c |  | note | Reference - VR682.08, VR682.17 IFC Drawings
label | 73271751-92ca-5fdf-a1f6-19a256df29c3 |  | note | Acceptance Criteria - Reinforcing elements shall be placed on top of the compacted fill material and connected to the wall panels.
label | 0c470ae9-30d9-588d-90fe-0bad01488f8c |  | note | ○ Any twists, kinks, sags or deviations in the reinforcing elements shall be removed prior to the placement of fill material on the reinforcing.
label | ff291c56-0dce-52f4-ad24-547fc2a54f9d |  | note | Method - Visual
label | d198d0b3-123f-5284-8462-30139c5d56b1 |  | note | Frequency - Each strap
label | 4e42d951-8098-5339-a32c-38c566536cc0 |  | note | Category - IP
label | c84ba2ed-be4d-51f1-9d88-fcd71716b8b2 |  | note | Responsibility - SE/PE
label | 0a69a04c-5974-5af5-a75b-9795c9daedbf |  | note | Verifying Documents - This Checklist
date | 178b72f4-5655-5ec7-9832-07309096f21c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2 - Soil reinforcement-Straps
label | ad48b446-877e-57dd-8210-9c1c7c6b8593 |  | note | Reference - Installation manual
label | 9f978d62-5d35-5a33-af84-70291df38868 |  | note | Acceptance Criteria - Correct number of reinforcing element shall be attached to each panel/wire facing units
label | bd9a335a-26ba-511e-ba1d-2969d6ffb571 |  | note | Method - Visual
label | c5a0d7f0-bb3e-59de-9941-d5c631a032ad |  | note | Frequency - Each panel/wire facing unit
label | f10102c1-3726-5188-b88e-13d1a95726ac |  | note | Category - IP
label | 9cdc77a8-72ab-5588-a42b-1b7c15e2b556 |  | note | Responsibility - SE/PE
label | dc27f563-1d9b-5842-8e6b-da474ad15aee |  | note | Verifying Documents - This Checklist
date | 6e9bba0b-4374-59f5-9b7a-4e0f343c3b9f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3 - Pre-cast Panel Soil reinforcements-Bolts Connections
label | 249a1359-c368-5599-8c3d-7d84dbd3eda2 |  | note | Reference - IFC Drawings
label | 7390482d-8928-5e11-9db6-b368325d8271 |  | note | Schedule of lenghts:
label | 23d25e56-69f2-5982-9882-8e9e03b1314a |  | note | ○ MRP-080-C-RFL-DRG-33-CPV-CSW-1403, 1502, 1602, 1702, 1803.
label | cd7be197-2495-5c9c-9c8f-70ac11fa7cc1 |  | note | Connections arrangement:
label | 612d52bd-0050-5b65-b646-1702c7fa29af |  | note | ○ MRP-080-C-RFL-DRG-33-CPV-CSW-2101
label | b1c535b1-2dd6-5528-ae07-01fe89f7ddf0 |  | note | Acceptance Criteria - Grid Strips are to be installed at the back of each panel in correct length and to the correct anchors at the back of each panel
label | fe73e879-b8f7-5471-8832-1ce320feb9a0 |  | note | ○ Finger tight nut or use a wrench so thread emerges from top of nut
label | 0ed778ce-7964-50f0-adb6-358f0f3da33d |  | note | Method - Visual
label | e29aeefb-88aa-5c48-a2fa-e5126b3b838b |  | note | Frequency - Each Fill Layer
label | 1816ff78-c827-5edd-aaf6-1fe064e0ff67 |  | note | Category - IP
label | 4503002e-98a8-518b-bd6c-6318830f38c1 |  | note | Responsibility - SE/PE
label | 1654bd29-7401-596e-a7a6-967c88191ea9 |  | note | Verifying Documents - This Checklist
date | ffb122ea-e330-507d-bb1a-5cfcc445f3e6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4 - Wire Wall Soil reinforcements-Connections
label | ae02d538-801d-5536-83e5-22c001674688 |  | note | Reference - IFC Drawings
label | da2ac41b-8106-5882-bdeb-1874ee77ad41 |  | note | Schedule of lengths:
label | 1512097a-f5cc-5046-a24c-cadc0a74dc7f |  | note | ○ MRP-080-C-RFL-DRG-33-CPV-CSW-1301, 1302, 1303, 1801,2802
label | aa53b998-c915-547b-81de-0181c78a7619 |  | note | Connections arrangement:
label | f40a33d5-e3f8-5011-a77a-3c2d48ecd6e8 |  | note | ○ MRP-080-C-RFL-DRG-33-CPV-CSW-1956
label | d6cc7480-186d-574f-a021-f3367a258427 |  | note | Acceptance Criteria - Grid Strips are to be installed to the wire facing units in correct length and to the correct locations based on the number of grid-strips.
label | 16261944-b73a-5ff1-90c5-1b643239ec81 |  | note | – The first layer of grid-strips are to be ziptied or connected via hog rings to the facing units.
label | bf78e160-f0e5-5ab6-b13d-84fedf97607f |  | note | Method - Visual
label | ff507bc2-fdf5-5347-a1ab-db858ae698ba |  | note | Frequency - Each Fill Layer
label | fd23094b-1b9a-5b9b-9017-4da30e901502 |  | note | Category - IP
label | 9e5bd7d6-9494-5c09-b174-02e7653c8be3 |  | note | Responsibility - SE/PE
label | bf174fe5-f75c-50b9-be9b-e38a97891276 |  | note | Verifying Documents - This Checklist
date | c19c7d90-c0e8-5629-8d0e-7d0db78604f7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5 - Soil reinforcements-Plan arrangement
label | a9242f7a-5dbe-5f17-b536-d12e7b6668f6 |  | note | Reference - IFC Drawings
label | 6239cfcc-04d4-5eb8-9f61-a825daf3a627 |  | note | Arrangements:
label | 78f118d9-e0be-5383-bff1-4ad8c8a58649 |  | note | ○ MRP-080-C-RFL-DRG-33-CPV-CSW-1101 to 1105 VR682.06
label | 34e7e53a-d1bb-53c1-b8e5-5b7a3dad0baa |  | note | Acceptance Criteria - Plan positions of Grid Strips are to be as IFC Drawings.
label | 47ae5370-8e3c-545c-ad98-9a42e04c2eb7 |  | note | – Grid Strips to be placed perpendicular to back of panel where possible.
label | e388c0d2-b118-58e7-89e4-2cd14ea5b2e0 |  | note | – Grid strips shall not overlap
label | aaf9549d-88dd-508f-9132-afd761374dd7 |  | note | Method - Visual
label | 48e339f8-f315-5cdf-a18b-951e00856685 |  | note | Frequency - Where applicable
label | 7475d940-d07b-525a-b793-14b035894031 |  | note | Category - IP
label | dd4147ad-0eb8-5f2d-b4fb-de145cd52d6c |  | note | Responsibility - SE/PE
label | 4ee9b0da-1fb9-580f-8170-6ce722b30649 |  | note | Verifying Documents - This Checklist
date | b20afd70-bc10-5582-bd0a-aa4f99ca8e89 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6 - Soil reinforcements-vertical/horizontal deviation
label | bd6bfa2a-bf95-5bd0-b13d-1d2040f18194 |  | note | Reference - IFC Drawings MRP-080-C-RFL-DRG-33-CPV-CSW-1101, 1901 and 1904
label | a38b324c-80c3-5aff-845d-92019781aea3 |  | note | Acceptance Criteria - Skew grid strips as required to achieve 100mm clearence from pile sleeves
label | 871fd89f-e1d7-5820-a0d2-b85244a0b93b |  | note | ○ Where grid strips are in the same horizontal plane, ensure 75mm Min horizontal clearance between grid strips
label | 70c56a87-94c7-5eea-ae3a-1c56f7315fc2 |  | note | Method - Measure, Survey
label | a6335da9-8bb9-5690-91c5-9094c7524c5f |  | note | Frequency - Each fill Layer
label | 7d8933b8-f49d-548e-b1f8-9d8fe402a884 |  | note | Category - IP
label | 55381383-bfe3-5575-84ff-fabb97918b4f |  | note | Responsibility - Surveyor/SE
label | 69133933-a711-5956-b2ef-fb8067a5c1e9 |  | note | Verifying Documents - This Checklist
date | c72defd8-1804-5a38-8261-d2a249fc6941 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Soil reinforcements-clash with drainage
label | 4f69f8a2-386c-5408-9571-7fcb1bf9cfa2 |  | note | Reference - IFC Drawings MRP-080-C-RFL-DRG-33-CPV-CSW-1109, 1901 and 1904
label | 132f5f24-dd6d-5dd4-ab94-cc06c0097d2f |  | note | Acceptance Criteria - Avoid clash with stormawater pipe as per IFC drawings
label | 8ffcc24f-0631-531a-a188-2f2afb7fbcbc |  | note | – RW02 column 1-27 and 30-41: Top layer of grid strips to pass over stormwater pipe. Other locations to pass underneath.
label | cbd65d2a-0ab0-50bc-b21b-ef312f3e5634 |  | note | – RW03 column 1-23 Deflect top layers of grid-strips below stormwater pipe at maxmum 1:3 slope, column 24 pass over stormwater pipe.
label | 3875e196-6d6d-5e67-bb76-6e449a493115 |  | note | – Set Out invert levels of stormwater pipe before commencing straps and fill placement for RW02 and RW03.
label | fe05194c-4836-5f55-9446-4a2dd335fa23 |  | note | Method - Visual
label | 612fc2ab-8236-5a11-ab38-b64a1fd99edc |  | note | Frequency - RW02 and RW03 stormwater and grid-strip interface
label | f23dfbe0-ef6e-5d5a-a618-5afca5e7307a |  | note | Category - IP
label | 0508d2c8-9c52-5794-9e7b-c697a861ca01 |  | note | Responsibility - SE/PE
label | 8906d973-dfb9-5c7b-bc86-1d011ea057de |  | note | Verifying Documents - This Checklist
date | c30a3bbc-b21d-526f-8f40-8d529d0cacac |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 8 - Cobble-Placement
label | d130864b-f0a9-5685-9421-2f54b2d6babb |  | note | Reference - MRP-080-C-RFL-DRG-33-CPV-CSW-1955
label | 48366bd2-a4d1-5c09-b829-510d3fad2ac2 |  | note | Acceptance Criteria - Cobble to be placed a minum of 300mm from face of wire basket
label | ce95bb0d-bd67-55ec-8e16-c3ea844d2cb1 |  | note | Method - Measure, Visual
label | 9e358e6f-e6aa-51fb-83ca-48d1b3e47bce |  | note | Frequency - Each fill layer
label | 85f3a64b-a862-5c46-93d1-c84e123cdba7 |  | note | Category - IP
label | 3f8efc8f-23f7-5a57-8897-e9ba1efdc517 |  | note | Responsibility - PE/SE
label | a432700c-673d-5f4a-b144-44dfbf39f93b |  | note | Verifying Documents - This Checklist
date | ce050bd3-b30b-5da3-a7bc-c97fc5ab90d7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 9 - Geotextile-Placement
label | f33b881c-2c55-51b3-b494-2ac23cad0376 |  | note | Reference - MRP-080-C-RFL-DRG-33-CPV-CSW-1955
label | b6dac1f1-0684-5ae2-bd78-dee06e52eded |  | note | Acceptance Criteria - Lay geotextile between cobble and select fill for full length of wall.
label | 032b9fa7-32b7-5283-b708-80b8f2783d7a |  | note | Method - Measure, Visual
label | d2d2e750-6ea0-557a-a9bc-f06e98177424 |  | note | Frequency - Each fill layer
label | 476981a4-2610-5ab4-bd58-032ad2dad45b |  | note | Category - IP
label | cf7a5c3f-2e6e-519b-8a25-b191fbac0b25 |  | note | Responsibility - PE/SE
label | 7df2834b-b72d-5703-8628-54c8f89eab39 |  | note | Verifying Documents - This Checklist
date | 585eb0c2-907a-53d0-9cb8-d173bd4cd167 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 10 - Fill-Placement
label | 471b2c37-7c37-5544-9841-d8088539ddfe |  | note | Reference - VR204.10
label | 0f09e942-23a2-5d8b-8cb5-b5a91088fe96 |  | note | Acceptance Criteria - Select backfill shall be placed in accordance with Vicroads section 204.
label | b567547c-eb3d-53a3-891c-22371361d944 |  | note | ○ Fill layers to be spread and compacted in layers not exceeding a compacted thickness of 200mm.
label | 5354f0be-adc7-545b-9c65-2697c632a7c8 |  | note | ○ Fill dispensation to be granted by superintendent to increase thickness layers.
label | 1b05b719-5726-54a2-a18b-aeed9adc5075 |  | note | ○ All RSS fill layers to be spread from face of panel to tail of soil reinforcing straps.
label | 4766305d-fe1e-53aa-9d0c-b046df69e5cf |  | note | Method - Measure, Visual
label | 7d45538f-da57-50cd-aeaf-8fc41f61639e |  | note | Frequency - Each fill layer
label | 7209ead3-dadb-503f-924b-3d9cff0df53d |  | note | Category - IP
label | a5484e94-c6f4-5be5-9d9e-e4d42897386e |  | note | Responsibility - SE/PE
label | 96be064e-d4b8-54fb-bc98-387e66b280af |  | note | Verifying Documents - This Checklist
date | 534a3e6c-7bb7-5853-9b64-cf3dbcdbf6eb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 11 - Fill-Placement compaction
label | 95e818d5-c4e3-529f-a3cc-9911463bc3ef |  | note | Reference - 204.111
label | fd364887-67be-5614-888a-429774bdff4a |  | note | Acceptance Criteria - 0 - 0.15 m Light weight hand operated DPU
label | 47ad0faf-41c3-5794-a7d1-a7d289ecef62 |  | note | ○ 0.15 - 0.30 m Less than 5T Roller
label | 7be34670-926c-5c11-be75-65860a33106f |  | note | ○ 0.3 - 1.2 m Less than 10T Roller
label | 5a98d96c-914d-5e4f-91e3-6795b91d19e9 |  | note | ○ >1.2 m Less than 35T Roller
label | 0aa3f36b-49f8-50b1-b190-d9a42288b12d |  | note | Method - Visual
label | 26e19376-08ac-5af1-88f1-fc6b07b8e43d |  | note | Frequency - Each fill layer
label | baea6dd6-2f59-5cdf-8484-6a361e9a9f4f |  | note | Category - IP
label | ed113193-c55e-54ca-919d-5d0b3e572057 |  | note | Responsibility - SE/PE
label | 265a7e41-7bc5-5d3f-9d66-f37daa4a005d |  | note | Verifying Documents - This Checklist
date | f0c967e2-572e-5c62-91b5-ed0767183116 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 12 - Fill Test roll
label | 011fe456-bdd0-559f-a7e8-f748c1a28b06 |  | note | Reference - VR 204.12
label | 082ed73f-d00d-5c11-8a92-0f1100b6da5c |  | note | Acceptance Criteria - All layers of fill shall be test rolled in accordance with VR 173. The contractor Shall provide for the superintendent to be present during all test rolling
label | f1ceaa4a-09c4-54c5-be62-22f1a19c127c |  | note | ○ Static Smooth drum roller with a mass >12T; or
label | 2a30f1bf-d0b5-57fa-8426-b1bba4f58154 |  | note | ○ Tandem truck or water cart with a mass >20T.
label | 7b8a2758-d036-5d54-b609-f82ed26a2b75 |  | note | ○ No visible deformation or springing during test roll.
label | 55e28608-5364-5408-97d8-3e1badeca676 |  | note | ○ Unstable areas rectified as per agreed method.
label | f2649f78-ae11-5dbf-b777-859228b8a552 |  | note | Method - Visual
label | 46db0bc7-3913-56c8-a60f-9ea1dc4f448b |  | note | Frequency - Every Fill Layer
label | 778ca5a3-d109-535c-aa39-695a1cd0a16e |  | note | Category - HP
label | f8e2bad6-3b67-5277-a524-66a4ae92de0e |  | note | Responsibility - Nominated Authority
label | bb0cb5fb-eb82-58fd-a740-5c92dceb1621 |  | note | Verifying Documents - This Checklist
date | d62caf52-98bd-56dd-95f0-6cd20e6927a9 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13 - Select back fill-Compaction Testing
label | 3bbd2159-d374-53b7-b602-f198b12fd06d |  | note | Reference - IFC Drawings VR 204.14, VR 682.16
label | 95cb8874-4f05-5117-917f-c20e8e1ae734 |  | note | Acceptance Criteria - Testing frequency shall be in accordance with Vicroad Specification section 204.14
label | b5ea2ff9-aaac-5ec3-8bfe-ca6f2142b477 |  | note | ○ Moisture content shall achieve minimum characteristic value of density ratio: 98%
label | ceb9f121-cb15-5bba-b1b8-2d66c1e0e7fc |  | note | ○ Moisture content of backfill shall be maintained evenly at all times. Moisture content shall be +0%/-2% of the optimum moisture content. Any backfill material exceeding the optimum moisture content must be allowed to dry.
label | 19acfb2e-e00f-5357-8983-76a46208e150 |  | note | Attach: Compaction test results
label | 870fa792-e1b6-5423-b14a-537b5d8c35da |  | note | Method - Documet review
label | 6af77cbe-b281-54e1-94e6-92db214bb08a |  | note | Frequency - Each Fill Layer or every second layer as agreed
label | 64a80d5b-fc90-5025-bd63-8424fea6fe0d |  | note | Category - IP
label | 81d13e27-9ebe-50d3-8bce-9d3574831205 |  | note | Responsibility - Nominated Authority/PE
label | b91a40eb-f90b-5faa-9bd3-e2e032a94470 |  | note | Verifying Documents - Attached Test Results
date | 9b40d4b6-62af-5520-ba03-e814bfee8ed9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 14 - Select back fill-Test frequency
label | d271d5b8-b2cc-5561-89d1-30058465d0b9 |  | note | Reference - IFC Drawings VR 204.14, VR 682.16
label | d04e6c7a-0139-5860-86b6-fb9133944053 |  | note | Acceptance Criteria - After three consecutive lots of like material have achieved the specified requirement, reduce frequency of testing of subsequent lots to the minimum requirement specified in table 204.142:
label | 5e7169ec-7654-5c5b-93fb-74c40727cade |  | note | Method - Documet review
label | eea5eef2-66e0-5f80-a84a-10fa3cb5e273 |  | note | Frequency - Each Fill Layer or every second layer as agreed
label | af9a6bc8-2582-549a-9721-fd2971a6562a |  | note | Category - IP
label | 1abee40c-62c4-5798-8fde-cf0481b813a1 |  | note | Responsibility - Nominated Authority/PE
label | 04c938de-8deb-52c1-8b50-e18f51fb7e2a |  | note | Verifying Documents - Referenced Lots in This Checklist
date | b605e041-c5cb-587b-8a3c-ad0fec0e1bd2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 15 - Survey Conformance Asbuilt
label | 1e027606-a4df-5fe0-b108-efa459bcd56e |  | note | Reference - Section 204.03 (d, g & h), 206.16
label | e0bc5b00-8a0f-5bad-96c1-5c94cfaf9189 |  | note | Acceptance Criteria - Scale B:
label | 66b42cec-f181-5fa9-9b8a-bb22364acc9a |  | note | ○ Min. No. of Measurements Per Lot: 40
label | 8a602622-04ee-56a2-a501-13bc48ec90a3 |  | note | ○ Tolerance: mean value of readings +5mm to -25mm and Maximum Standard Deviation to be 15mm
label | 4a50c9a7-72e3-5c29-9796-8c7bb3db70e1 |  | note | Method - Review
label | fe66ba3b-3e55-5164-a559-d7ffd528a29b |  | note | Frequency - Each lot
label | ebcf7edc-fa10-5ebc-af9e-98d803080b80 |  | note | Category - IP
label | b05ef320-b1b3-5610-8f81-f636f80d97f0 |  | note | Responsibility - SE
label | 4fea5c88-2792-506d-bd65-3b42a285ba50 |  | note | Verifying Documents - This ITP
label | 071dc0c7-68ca-558a-960d-a68fd96110c7 |  | note | Attach: Survey Conformance As Built
date | af89178e-08da-5a57-983f-17a91c7c2e6e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | a3a59414-d8bf-5eab-98c5-136b2bf13b5f |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 72473e6a-d86f-51db-aab5-ee7ed0f7b596 |  | textbox | Name:
text | f183d421-b4c1-5d76-818e-cfb6111f09fc |  | textbox | Position:
date | 1fdfdcc1-e2bb-5ee5-b38b-45469fe422aa |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-013-STR-Pile Cap Construction | itp |  |  |  | Yes | ITP-013-STR-Pile Cap Construction Rev 0 | 9de8b40d-9d90-49d5-852b-38b3d9c5d155
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | b76f9ee3-6550-570c-88e2-b5e9e34f72cd |  | note | Document Title: ITP-013-STR-Pile Cap Construction
label | d29037fe-84bb-5299-8a2c-f75cb7226076 |  | note | ITP Description: Pile Cap Construction
label | 78986eca-a3df-51d1-935b-28675262f3ea |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 1d299b58-4271-52d6-8a4b-b80dae86c8f2 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | edccbb10-a0b4-54bb-8951-64b46ebb7194 |  | note | Revision Number: 0
label | a38ee1eb-73c8-54ef-8656-a21060eb378a |  | note | Revision Date: 01/12/22
label | 5a7009d5-182d-5789-90f1-6373a6253935 |  | note | ITP created by: Victor Mira
label | 20dfea2c-7100-5ecc-af75-cd27d13841bd |  | note | ITP approved for use by: Victor Mira
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 0f5741f7-e7ab-50f1-ac27-fb94c3246fcb |  | note | Reference - VicRoads Section 602 October 2007
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 7fb2f478-d6fc-51c6-80bc-7b453ad8e7cc |  | note | Reference - VicRoads Section 610 February 2020
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | a271af53-4f1d-5300-a24e-c7f1bb4be358 |  | note | Reference - VicRoads Section 611 November 2018
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | b97a3ea1-7284-5d18-8c1c-6924c5a66d58 |  | note | Reference - VicRoads Section 614 June 2017
checkpoint-status |  |  | checkpoint | 1.5 - Non Dependent
label | 7e01e8ec-6dbc-5d73-9dec-8c055c4cb047 |  | note | Reference - AS3810.1 2018
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Concrete Mix
label | 3cf2244c-d220-5722-acdc-dc8b7819cc96 |  | note | Reference - 610.07 Table 610.071 IFC Drawings
label | 2580ab94-90ed-5777-b0ed-8e925256dd21 |  | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
label | cb680efb-7b83-56bf-9ca3-be897acce3d2 |  | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | accebecf-c99c-5cd2-a432-8395c5db0a5b |  | textbox | Enter: Teambinder Material Approval number
label | 4629a1dc-dcdd-537f-8248-bfae61ea8b85 |  | note | Method - Document Review
label | fa725204-c7bd-574a-b1f7-a252c5be2a83 |  | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
label | 32596c90-5acd-5d30-bd91-bc37e46282d2 |  | note | Category - HP
label | 59630ed5-16a1-51c8-aeff-d66499189d47 |  | note | Responsibility - Nominated Authority
label | c7a20219-6170-58a6-aaf0-b56b25845a1e |  | note | Verifying Documents - ConQA Hold Point Release
date | 1b66efa6-a1c9-5267-86a7-f92b7d5b007b |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - ACRS Certification (for Reinforcement)
label | 6cc984d7-15cf-5e89-9ab2-59e7dbec0a4f |  | note | Reference - 611.05 (a)
label | b0f0897a-cb3b-5816-8e1a-610e0b7955bf |  | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
label | c028a1a1-7245-5137-a7de-cd5d8c76025f |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | d5efe286-a4f2-52eb-ac8c-4b1286ab8817 |  | textbox | Enter: Teambinder Material Approval number
label | d2d146ca-5e86-569b-aa4b-eb4df2d41f20 |  | note | Method - Document Review
label | efa0f029-c0be-5125-ab34-f2bc6d7b781c |  | note | Frequency - Once for each supplier, 14 days of award of contract
label | 7517f28f-bb98-50e9-b17c-f54483f5343f |  | note | Category - HP
label | a67468eb-05f0-55d9-8892-e0d604cb79d5 |  | note | Responsibility - Nominated Authority
label | 4b6b05b3-05f3-548c-a0bc-b6a12854a227 |  | note | Verifying Documents - This ITP
date | d25a5e16-5aba-58c2-9a7c-0b9ec6f6757b |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Bar Chairs/Aspros Certification
label | 70809ac3-0957-5818-863d-05b17fb635f7 |  | note | Reference - 610.26 (a)
label | 3fc9448b-f331-554f-b0fe-cd97912bed0c |  | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | 69019490-7bf4-5cc4-81af-70dd19675f41 |  | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
label | 682350b9-ce7c-5279-a02e-0638eab95411 |  | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | ec5322fd-6ab7-5646-849e-2beb63163757 |  | textbox | Enter: Teambinder Material Approval number
label | a33b4369-9444-5847-b06a-2c8da099a983 |  | note | Method - Document Review
label | d10234b7-4db6-5979-b537-b5d200905e67 |  | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
label | 6449c61e-fc4d-5f8c-ae69-61860d44197a |  | note | Category - HP
label | 0990a72b-4550-5192-8262-eda3c8720edf |  | note | Responsibility - Nominated Authority
label | 2fcac8eb-ad7c-5324-b3da-29397a67f705 |  | note | Verifying Documents - This ITP
date | 18046d2d-b053-55f1-b9f8-9888e11ebe0c |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Evaporative
label | 9074f8f9-e096-5887-a3ba-b3c888c0a32e |  | note | Reference - 610.17 (f)
label | 59ba2c3d-fc99-54a9-af27-ffa6ac46a8e2 |  | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | eb5e2d52-40f2-5e72-8a5e-d988f40591e2 |  | textbox | Enter: Teambinder Material Approval number
label | 0c42f92a-e0d1-5aab-abb8-cf3edf20fbd4 |  | note | Method - Document Review
label | c01a3c6e-7d65-54f0-aa83-b3e78a62d533 |  | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | 55a16ca7-6c8e-556e-b604-eeca98ae5d8d |  | note | Category - HP
label | 07368ecc-c017-5847-950e-faffa4e80b2c |  | note | Responsibility - Nominated Authority
label | 80fe0c20-7b4a-53e3-bc6e-46c60234e5a6 |  | note | Verifying Documents - This ITP
date | 18571657-f2f8-5c3b-8070-d0fdf2628b8b |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Curing Compound
label | 6af0458c-e8f7-5c71-ae26-de8fda22de90 |  | note | Reference - 610.23 (d)
label | 296c096d-bf2a-5ab4-b7b1-3fa8301f02e2 |  | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
text | 9306bb59-96ce-52f9-8147-bafb0049920c |  | textbox | Enter: Teambinder Material Approval number
label | 5f166212-c2b6-58ad-837d-f152f85887de |  | note | Method - Document Review
label | e0f89fe1-a8f8-539b-8ccf-4504d49bfe30 |  | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | 8ac8ad10-eef1-5019-9b6f-5e808030dd84 |  | note | Category - HP
label | 764b6ded-af58-5685-a67c-b2d43e9fb259 |  | note | Responsibility - Nominated Authority
label | a3f6028b-5de3-586b-b384-aa81d530e294 |  | note | Verifying Documents - This ITP
date | fe7894e0-7266-54a1-a3fc-5ac6d6fb1728 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements
label | 2bd834ed-545a-597d-9427-87e15422fad7 |  | note | Reference - 610.18 (a) (i)
label | 4b7e03a6-a7aa-5b7a-a6bd-58c660d082e2 |  | note | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
text | b352c7be-2a07-5561-b7e5-72001087c825 |  | textbox | Enter: Teambinder Approval number
label | 0b980fcc-e178-5a49-96c8-cd0bb900f4bc |  | note | Method - Document Review
label | a6edfbe2-be13-5531-a684-10504a4e620e |  | note | Frequency - Once, 4 weeks prior to placement of concrete
label | 0132bef7-49a1-5bf2-8b8b-f3f0007591d3 |  | note | Category - HP
label | 1874cf6e-9165-5f32-93ff-a39e79ff187d |  | note | Responsibility - Nominated Authority
label | 584c6ffc-f7e1-5f23-a4dc-28215667f24e |  | note | Verifying Documents - ConQA Hold Point Release
date | 4cfede23-c845-5899-8acf-15f889db3051 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Concrete Sampling and Testing Procedure
label | b4f3e60c-479d-5346-80df-1509b7a12346 |  | note | Reference - 610.18 (a) (v)
label | e39b8ab5-e531-5fab-866b-dec2846a0187 |  | note | Acceptance Criteria - Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
text | b0529034-af9e-53ee-a7ce-3596333b3730 |  | textbox | Enter: Teambinder Approval number
label | 10ee9594-e491-5742-8a1e-ec4e087ab578 |  | note | Method - Document Review
label | c2633d02-6a68-57df-bb61-20b737f5466c |  | note | Frequency - Once, 4 weeks prior to placement of concrete
label | 194ca65c-9fe7-539f-8abf-f6aaec6c4460 |  | note | Category - HP
label | b9a6b667-062f-5d48-9fc8-95285f4e4254 |  | note | Responsibility - Nominated Authority
label | 32060d29-9a30-54f9-9fe7-f4fd80ee02e7 |  | note | Verifying Documents - ConQA Hold Point Release
date | fc1475fd-9e93-534e-b1c4-a72c7c0f8d85 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Concrete Placement and Compaction Toolbox Meeting
label | 7380a063-6226-5302-84b9-8d1897d7108e |  | note | Reference - 610.18 (a) (iv)
label | baa00dd5-1761-5af0-9d77-e3107aa3ca94 |  | note | Acceptance Criteria - Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
label | 320097d9-b6da-538a-81a1-4a5a4bcb6c58 |  | note | ○ Minutes of this meeting to be submitted to the Nominated Authority.
text | d9cccf81-4031-55e5-8b3f-fb941feec5b1 |  | textbox | Enter: Teambinder Approval number
label | 2d5980c7-998c-5544-8d8f-36c0d3166347 |  | note | Method - Document Review
label | ab7a88e5-42d1-51db-8554-9feee6b8e722 |  | note | Frequency - Once, 4 weeks prior to placement of concrete
label | 48c60485-5969-5a06-89ed-57b4463f9997 |  | note | Category - HP
label | 846bfe9a-7509-5249-80ca-45171eb9214e |  | note | Responsibility - Nominated Authority
label | 7d687890-caf4-53b4-828a-2ddefe4aefa8 |  | note | Verifying Documents - ConQA Hold Point Release
date | 549bfe1d-cea6-50a5-807f-d598fe8b8230 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Hot and/or Cold Weather Concreting Procedure
label | 0d501701-05a3-5a64-b681-c859efd1c04d |  | note | Reference - 610.17 (a)
label | 699fab8f-23a3-548e-8bef-f0d41ba99a38 |  | note | Acceptance Criteria - Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
text | 59ec0686-4c0c-52bf-842f-441d46ab34f3 |  | textbox | Enter: Teambinder Approval number
label | 77e9c4ed-6472-5e3d-b78c-a72b31677c3b |  | note | Method - Document Review
label | 081c4e59-470b-57f8-8115-e52211dec9f7 |  | note | Frequency - Once, 2 weeks prior to placement of concrete
label | fc85752e-c3ab-5ac3-bded-1b65021ddc13 |  | note | Category - HP
label | b00f614d-20b4-516e-a008-32a713e64616 |  | note | Responsibility - Nominated Authority
label | b917221e-15e5-5f97-a426-3028c875a3a4 |  | note | Verifying Documents - This ITP
date | 51eb5497-de31-5f7a-bab6-01abe62608c4 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Curing Methodology (for Concrete and Grout)
label | 94d73e3b-b00f-5442-a9b8-789b6abd3c58 |  | note | Reference - 610.23 (a)
label | 6323a75e-668b-543c-8e85-d7d51d620348 |  | note | Acceptance Criteria - Curing methodology/procedure to be submitted for review to the Nominated Authority.
text | 2fb5cb9c-60e7-5162-a9fc-6379c723ebbf |  | textbox | Enter: Teambinder Approval number
label | 43904c1f-d932-52e7-80e5-c3b6a0a1c95b |  | note | Method - Document Review
label | 86c7e5fd-3fc1-5d53-9a0d-6ff7f92a65c8 |  | note | Frequency - Once, 4 weeks prior to placement of concrete
label | be5598f5-351c-5351-9552-46ab4228a783 |  | note | Category - HP
label | 43f9ecd5-9cf5-511a-9374-e4dc26ddff0c |  | note | Responsibility - Nominated Authority
label | b57375de-51a8-51d1-a62b-365ef3d1cc84 |  | note | Verifying Documents - ConQA Hold Point Release
date | 51b34793-0bec-5439-9283-c90e9c7def6f |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Concrete Drilling Procedure
label | 89e55657-778f-5da0-af96-1ffd33bc026e |  | note | Reference - 610.46
label | 715fc275-8630-50a9-9422-332b7d44df0b |  | note | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
label | 5217868f-d2ed-54cb-9bbc-da530f17fbe2 |  | note | ○ The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
text | a5d7fefb-045e-55c0-99d0-c4e584601cd4 |  | textbox | Enter: Teambinder Approval number
label | d0e1d2ad-0173-5a8e-90a4-228da9f33c5a |  | note | Method - Document Review
label | 1695843a-4434-5bbc-86db-95e7d135c97f |  | note | Frequency - Where applicable, once, 2 days prior to drilling
label | 6ab3ff0d-5ba1-58f2-8036-e595f1a750bc |  | note | Category - HP
label | f6197e72-424e-5b0f-bba8-69e615873d95 |  | note | Responsibility - Nominated Authority
label | 19ab114c-c6d3-525f-8acc-d1637ceb47fd |  | note | Verifying Documents - ConQA Hold Point Release
date | cf181aef-6019-5ae2-8b72-a67b2711b87e |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Temprature difference measuring-Calibration
label | 646e3eaf-758d-586b-b1f4-a79a9ed928f9 |  | note | Reference - MRPA Quality Management Plan
label | d96c29c2-4cb6-511e-8a9f-4aac577eab1c |  | note | Acceptance Criteria - Calibration records are valid and up to date.
label | a08eddb9-08bf-5cb7-814e-5a6be59c72c1 |  | note | Attach: Calibration certificate
label | ee1a809f-ddd6-5103-b24c-1e504aebfe36 |  | note | Method - Document review
label | 6a056a8f-30a1-5f3b-bf9b-c9c175e0058f |  | note | Frequency - Where applicable
label | dffa94ff-9545-52cb-ab0a-06ecfd371780 |  | note | Category - HP*
label | 5d5c7574-6a5a-563a-91df-f1db124d2dfc |  | note | Responsibility - PE
label | 62590a6a-547f-5e6b-84c5-9062e2fd1a73 |  | note | Verifying Documents - This ITP, Attached calibration certificate
date | dccbda64-41cd-5c48-8c40-6596d3c3aefb |  | date | Date Completed:
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - IFC Drawings
label | 1540b0c7-cd8a-58a5-9755-76f2cbccb7fb |  | note | Reference - MRPA Quality Management Plan
label | 80745837-3583-5072-bb00-22743b6e4933 |  | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 091f6b0c-1cac-5070-96ef-a14af4ab4abf |  | note | Method - Document Review
label | 129df37b-109b-5c42-9e5f-7563ab0a561e |  | note | Frequency - Prior to starting Works and at regular intervals
label | 41494368-88c9-51be-971b-364238a0ff69 |  | note | Category - HP*
label | e2fe1d61-0979-5cfe-97d4-992336e73603 |  | note | Responsibility - All
label | 7af73bb1-972b-599d-8aa8-2e514893266e |  | note | Verifying Documents - This ITP
date | 8280f773-82ec-5687-bdcc-d6c2c578e4a5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Survey Set-out
label | b7aca6d8-365c-52c1-a56f-063d4fb586ba |  | note | Reference - IFC Drawings 610.47 (a) Table 610.472
label | 5ff7306c-b73f-52ef-a5d3-adea4cd04996 |  | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
label | 3ec72587-1ffb-50b7-a2eb-1d981a14fe4e |  | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
label | ee79a0b4-1683-5536-8cd1-1bc56fc9c44a |  | note | Method - Measure, Visual
label | 98af64ea-20ba-53c5-8fa5-0aaf076ba63d |  | note | Frequency - Each element
label | 5d238f95-2c1a-5b62-b8c9-ef63c690fa66 |  | note | Category - IP
label | 962f6639-8402-558f-8bf3-a272c5274ab1 |  | note | Responsibility - Surveyor, SE/PE
label | 5eb0b3d1-6fad-5b84-b57c-74ea2dc3ae1e |  | note | Verifying Documents - This ITP
date | 2f373f45-d385-5ef0-803e-b028dbe50931 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Piles
label | ce56de83-348d-5c5a-8972-982fa3c07113 |  | note | Reference - IFC Drawing
label | bff61097-843d-57d3-878b-6d31f5a3a42f |  | note | Acceptance Criteria - Related piling Lots are closed.
label | 31a854e7-0822-5729-8119-3a265a9abc6a |  | note | – Pile design strength is achieved.
label | 7901a989-c897-5430-84fa-3e0e0665c9c4 |  | note | – Integrity and Dynamic tests performed and interpreted.
label | 42f94a00-ff80-5387-80a4-77f344a9728a |  | note | – Pile is broken back to the design level.
label | 87aa9c76-e7d7-543b-948b-d0439d46bd69 |  | note | – As-Built Survey performed.
label | 3b93f889-05d5-5cba-8efc-86770c7013ea |  | note | – Related piling NCMs are closed.
text | 2fc96764-ff04-5809-ab5d-2e5a301de077 |  | textbox | Enter: piling Lot numbers:
label | 6de37380-7587-5b84-ab1b-6af4974ccde0 |  | note | Method - Document Check
label | 2dffbd70-a31f-5d56-956e-da0a11dd858f |  | note | Frequency - Each Element
label | 6323edcc-20df-581e-8f13-66f24a1e1e5e |  | note | Category - HP*
label | c260e47a-1be5-5820-85a2-f7ed1779e67a |  | note | Responsibility - PE
label | 6230556d-36de-5cae-9924-cf02febfc012 |  | note | Verifying Documents - Piling Lots
date | d1a039f2-fdf3-5b3c-949d-64198d575fab |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Excavation support
label | 473a62bf-cb27-5d1b-bd9e-0031e2a84179 |  | note | Reference - 602.02
label | fffebd69-fe33-5a74-b41d-22c4955a998f |  | note | Acceptance Criteria - For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
text | 3f2ea74e-00be-55d9-9b34-31997dc46740 |  | textbox | Enter: Teambinder Approval number
label | 81672a6e-54f1-5332-a6f6-ff261cc97b6c |  | note | Method - Document Review
label | 2a4fb53a-baf5-5253-b51a-b0223350bb5a |  | note | Frequency - Where applicable, not less than 10 business days prior to excavation
label | 571d866d-ea61-54b0-a049-6556e2094a31 |  | note | Category - WP
label | 9e466b8b-ed41-55c1-a8c2-37aee3e458b5 |  | note | Responsibility - SE/PE/SPE
label | ce94c0ed-3797-5a37-baf8-89cd9193d8b7 |  | note | Verifying Documents - ConQA Hold Point Release
date | 6b23ebed-6c51-537b-b7c6-03622c29446e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Excavation Inspection
label | e52058a6-6406-54f4-afc8-4a2c52eefb24 |  | note | Reference - 602.03
label | 73d273cd-591b-549c-91d7-a1a668a3e76f |  | note | Acceptance Criteria - Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
label | 2e632299-657c-5082-9c51-d160396aaff6 |  | note | Method - Visual
label | 2cdcba21-cff4-5793-8122-104b233977b9 |  | note | Frequency - Where applicable, prior to placing blinding concrete
label | 1748932c-6489-5fbd-86d3-0a918ed53b10 |  | note | Category - HP
label | bfa7c08f-a66b-551b-824b-89b727667ae6 |  | note | Responsibility - Nominated Authority
label | d6dd5d2b-c766-5edf-af8f-2d5d8b0fc303 |  | note | Verifying Documents - ConQA Hold Point Release
date | f6c1d094-088a-59c6-acf4-a101da1cee45 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Formwork Design and Construction
label | ee14acdd-abb8-5cb5-9e8a-a5e90c1a25ab |  | note | Reference - IFC Drawings 614.04, 614.05, 614.06
label | 7bb0d6b6-4a81-512c-8a32-91da2b29b112 |  | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete.
label | 4869a5b9-23ac-5b93-9d5d-65fbc8e9e1ad |  | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
label | 92caecbe-5839-5dc0-972a-986e6baf712b |  | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
label | abcb44fc-16fa-5d71-9bf7-0744fc75cdd1 |  | note | Method - Document Review, Visual, Measure
label | e58fddec-506d-5d47-8c35-c75c3474d88d |  | note | Frequency - Each type of element
label | f7aef27d-c581-5219-a191-2f1539e6fe58 |  | note | Category - IP
label | 8469ce25-204c-551f-9310-93e033da5604 |  | note | Responsibility - Temporary Works Designer, Proof Engineer, SE/PE/SPE
label | 60a2b6f9-6a06-518a-8a9f-5c02af1e2177 |  | note | Verifying Documents - This ITP
date | 85a751d8-6ab5-5526-ab45-95b7bb17b615 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
label | b75d1d6f-4e50-54c4-bc36-61113a185ff2 |  | note | Reference - 614.08
label | 0d3da601-40f0-5d7c-b626-eabf17cec194 |  | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | a8bff38d-8908-56c6-a597-ab09e670abea |  | note | ○ Pile caps with heights greater than 2.0 metres
label | b02f211d-7465-5a63-8ff5-879900be13e6 |  | note | ○ Any member for which self-compacting concrete is proposed.
label | 0fb06854-ee09-5042-b6ed-1d30be919732 |  | note | Attach: Attachment A
label | 0d94b082-0262-5556-8b5f-9465939c310f |  | note | Attach: Attachment B
label | 38e7fb90-8a79-554f-9956-f9a1ecefd889 |  | note | Method - Document Review, Visual, Measure
label | 15a4c63c-c27c-506d-b463-c85b5a2228a3 |  | note | Frequency - Each element (where greater than 2m)
label | 584e3447-16da-52e7-89dd-1ce8a9f5aa71 |  | note | Category - HP
label | 8e9e9df8-70b8-5fb3-b11a-6f4338f1d78a |  | note | Responsibility - Temporary Works Designer, Proof Engineer
label | 104d6fd5-b639-5755-9e73-f62cb2bdfc91 |  | note | Verifying Documents - ConQA Hold Point Release
date | f4d7c82f-40fb-5423-8f3d-9536013995a7 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
label | f64dd90f-71f8-5a00-9eb4-8f795e0af5c3 |  | note | Reference - 614.08
label | 5053e5d4-a0a1-55fe-8380-b15c0b783f4e |  | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | 74605a5c-0c54-5877-8f0f-b02394db3b00 |  | note | ○ Pile caps with heights less than 2.0 metres
label | bfd3fe0d-b98d-559a-b139-571cea655454 |  | note | Attach: Attachment C
label | 28e62420-d110-5811-be0b-f5e848cb07c5 |  | note | Method - Document Review, Visual, Measure
label | e5033dc9-9230-59f9-83b8-37da58c3a58d |  | note | Frequency - Each element (where 2m or less)
label | 8c770cab-9741-5194-a7c0-09eb5e298ba1 |  | note | Category - HP
label | 166de3eb-0dd4-56d7-b7e8-bc793a5826f7 |  | note | Responsibility - Temporary Works Designer, Proof Engineer
label | f7a1360d-db88-5548-b8ee-5d01f5708d58 |  | note | Verifying Documents - ConQA Hold Point Release
date | 06d84021-d002-5fc6-bbb7-86beef5d9ac9 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Pre-pour Survey
label | a99407d0-a94f-5929-91d0-72359c3406b6 |  | note | Reference - 610.47 (a) Table 610.472
label | d872d2a6-40b7-5f73-9ae6-3208f10ae758 |  | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
label | d06676c9-e69f-5712-93a5-e7009ffddc21 |  | note | ○ Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
label | 9632e181-a44c-5fb6-9a5c-a1172970db3e |  | note | Method - Measure, Visual
label | 7799b699-d162-5250-a672-aa5ac1bb7039 |  | note | Frequency - Each element
label | e904b780-bff2-5603-ab1e-2131a5925781 |  | note | Category - HP*
label | dbbde62a-3384-5625-86b1-5cf906e0004f |  | note | Responsibility - Surveyor, SE/PE/SPE
label | c84b2609-5ad3-5b41-9a77-563d7c7268cf |  | note | Verifying Documents - This ITP
date | 4c910ed9-3477-5709-ab94-96d09c9ecc97 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Reinforcement Placement
label | 4378e09c-8945-59b0-a868-ee2eab31b6ff |  | note | Reference - IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
label | 01a64174-dc6d-5939-ab01-d8dc61cc3acf |  | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | f84d1f21-0a2f-53e1-9a0a-1077bbcedb29 |  | note | ○ Projecting reinforcement is the correct length and location.
label | f87ef64f-6437-509b-aaae-3196451c8ef1 |  | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
label | 5c6e745c-6f8e-57ea-87d0-cd7c0df966b1 |  | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | 2f444baf-4bb3-5e31-8ff3-2dab581e2033 |  | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | 6bbc5e65-29dc-5540-aabd-74f3c4248283 |  | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | b110b408-1a96-5b31-bc80-1c2b45278b9b |  | note | Method - Measure, Visual
label | 9192e9ea-fa61-53f7-b942-f969543f77a3 |  | note | Frequency - Each element
label | c819da1f-735a-5dfb-be3e-d6e88b7f83d2 |  | note | Category - IP
label | e1412ba7-7dad-5716-a4cc-6a9884b8bfff |  | note | Responsibility - Foreman, SE/PE/SPE
label | 9a662646-c7e1-5d35-baad-76bd38bb9280 |  | note | Verifying Documents - This ITP
date | 89a5a293-ae17-5477-bf77-6c9ae6dc3d2d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Cast-in Items
label | b69ee3e8-e948-5cfb-a0e5-df0ef6cb0cfc |  | note | Reference - IFC Drawings 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2
label | 23a74c39-1dcf-52c5-a09d-e4e5cbe6eb05 |  | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | 15cd577c-e882-54df-92e2-1da60dbe07d0 |  | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | ddec8060-91f5-5e9c-b433-f47779fb7982 |  | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | f9568cbd-3024-54df-8c16-e3ba2bb8e403 |  | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
label | 608b2af3-cc1e-5cc7-9d06-a163931179c6 |  | note | ○ Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | 896a5e35-0e0d-5961-ba5d-f49884fe0519 |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | 2da04cb0-f3db-5def-b0f2-251b4646f5e0 |  | note | ii. Running dimensions of a group of the above = ±6mm
label | 4ea0805b-6c1f-57d5-b671-e013ea8396d0 |  | note | iii. Ducts and conduit location = ±12mm
label | 88340149-aa34-5a8f-843e-69d94a5fa9d6 |  | note | iv. Diameter of ducts and conduits = ±3mm
label | 2e3549ee-8120-5e19-9dcf-9e148e9a4cf0 |  | note | Method - Measure, Visual
label | c1782abb-ee0f-5455-9704-8e62b03eed95 |  | note | Frequency - Where applicable, each element
label | 5dbe7fc8-e0ce-580a-ba7a-409c390427c8 |  | note | Category - IP
label | 7e5317af-ab6c-509f-b668-73116e5e4fc9 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 6e7d220f-99b9-50f8-b69a-eea079eb86fa |  | note | Verifying Documents - This ITP
date | ab622eec-8e22-5e2d-8e7c-0e9c3c8df5ed |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Thermal Differential Monitoring
label | f4890f00-2642-5e54-b6ba-e69bd11be12b |  | note | Reference - 610.22
label | cd2062e9-3c36-5954-a746-64f715bbf2ae |  | note | Acceptance Criteria - Thermal differential monitoring thermocouples installed.
label | fde46802-fe87-52c0-8e8d-7e43bc0814ef |  | note | ○ Only applicable if the element has:
label | e7b5af4a-5f9d-5291-b185-d49c36e1d094 |  | note | i. the smallest sectional dimension exceeding 500mm
label | d7ffb95f-ea2e-537b-a377-6500cb5d1453 |  | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
label | 6f2126a7-c3ef-5744-b988-bd6818e1d9fa |  | note | Method - Measure
label | 118e6066-08fb-52f6-b87f-f9ef85faf567 |  | note | Frequency - Where applicable, each element
label | 300e3467-f35c-596e-88e0-b664d303a71d |  | note | Category - IP
label | d6c105e7-0f93-5e16-adc7-2836c9e5be02 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 35eacf51-0940-5d49-b6e9-73c356f440c3 |  | note | Verifying Documents - This ITP
date | 211b1577-fe3e-518c-84b2-b5c53e1d1173 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 - Pre-pour Inspection
label | 41d29ca3-45cd-5c70-a029-8de4b6fa6a1f |  | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
label | c8a99d00-2216-53a0-bdc5-ad542030bdc1 |  | note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | 535c439e-08c1-5535-9b37-5e39f7dd2956 |  | note | ○ All foreign material has been completely removed from the forms.
label | ecbb3f3f-3906-5af5-8cc0-16377829cade |  | note | ATTACH: Pre-Pour Checklist
label | fb36b252-9d6f-54da-9672-fb12856024b1 |  | note | Method - Measure, Visual
label | 17e03bf8-af0a-5f12-b95c-103b59091e24 |  | note | Frequency - Each element
label | 4b0cb181-6c8f-592f-a935-0667b0ab5d32 |  | note | Category - HP
label | 1ef8a458-92c6-56db-84a5-3faa667b3ca3 |  | note | Responsibility - Nominated Authority
label | 67993e98-ea77-5778-8e1b-4eaeceed87db |  | note | Verifying Documents - ConQA Hold Point Release, Pre-pour checklist
date | b918298d-e4c5-5527-8e33-d7cf90cd567a |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.10 - Weather Conditions & Evaporation Limits
label | a8c40b62-0976-5c45-9f03-4779d3701f15 |  | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
label | 82183335-c96a-5e0e-89a9-ba2678951b15 |  | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 8acf73fe-94ce-54c5-80b6-249d3ae4e521 |  | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 2f6d7f9c-2872-5e50-aa48-c74bfa27f379 |  | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 7b8ce12a-516f-563f-9a12-03b3cb86092f |  | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | 5143b7ab-c1d7-53cd-b02c-01734b577225 |  | note | Record: Required information on the Concrete Pour Record.
label | b59ce63f-242a-54cf-bf1e-e542997f23ce |  | note | Method - Measure, Visual
label | 5321d005-9796-5ce3-920e-94a9662cd57b |  | note | Frequency - Each element
label | 09dc37f6-df12-59d9-b327-24f35652d8b2 |  | note | Category - IP
label | 4c82f5bc-ed26-54cb-a89f-6b32612f5cbf |  | note | Responsibility - Foreman, SE/PE/SPE
label | 67d2519a-9055-5d74-b422-f0ec9ac68132 |  | note | Verifying Documents - This ITP, Concrete Pour Record
date | a6b4641b-ebb7-53b4-8f83-5ff6d4267483 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 - Concrete Testing - Sampling Frequency
label | 3034a109-0638-570b-ad2d-c825d1f4320d |  | note | Reference - Site Sampling & Testing Procedure 610.16 (b)
label | 71afce13-1f63-5887-b685-56a7a80eb5a0 |  | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 48db1ef0-276f-54fe-8315-b5d5141d66f1 |  | note | 0m³ to 10m³ = 1 sample
label | 08e7e0e3-5db4-5140-9b52-4f8039b5fbef |  | note | 10m³ to 25m³ = 2 samples
label | d8ccc0ef-4b60-5b43-b3a1-4731090fd64f |  | note | 25m³ to 50m³ = 3 samples
label | 7f5a0c5c-3f52-5627-8c4e-744c3fdf73b1 |  | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | 16b84793-f55a-5265-85c2-520cf49e5041 |  | note | ○ For each additional 50m³ and additional sample shall be taken.
label | 871a3f71-3868-58a2-9fed-259d6879e52a |  | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | e0a2c5d1-1641-5d45-b609-cd3ff31e6842 |  | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | 29d9d342-9374-59ad-be4e-9d7245115443 |  | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | e77ead74-a759-5cee-b4e2-377b55602fcd |  | note | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
label | 936828e2-f8ae-55a6-8179-c9520c66d7ee |  | note | Record: Required information on the Concrete Pour Record.
label | 629c2ec8-7c4e-559a-8021-6e2c62cf995c |  | note | Method - Test
label | 56c668bb-8fd2-5252-b930-4148d0706ca4 |  | note | Frequency - Each element
label | e48bc97f-c416-52c7-bfaa-eccdfbd3ab88 |  | note | Category - IP
label | fcfbfab6-ca11-5973-b3a2-90f3031383a7 |  | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
label | fb8f56ae-df30-52b8-948a-a7b5b12a4c91 |  | note | Verifying Documents - This ITP, Concrete Pour Record
date | d5e87554-2fc1-5f61-a560-fd83af2b728c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 - Concrete Testing - Slump
label | a2fa0aa9-c4cb-502b-89c5-f29661ac0507 |  | note | Reference - 610.16 (c)
label | 84d15b00-1a8b-5b82-86c0-359cf884f2c2 |  | note | Acceptance Criteria - Slump testing tolerances =
label | 401655b8-8852-5005-ab04-6c15ed311bfd |  | note | <60mm = ±10mm
label | 0d78a74a-10d0-5f1e-9dca-28e752af56de |  | note | ≥60mm to ≤80mm = ±15mm
label | 85f5b767-595c-5adf-a116-4e93269f6c06 |  | note | >80mm to ≤110mm = ±20mm
label | 6cdb05c5-e20d-54f4-ac37-3b8318a6b9b2 |  | note | >110mm to ≤150mm = ±30mm
label | 208289b2-7156-5d58-8ca0-c911fbe544c2 |  | note | >150mm = ±40mm
label | 8a0e710a-0166-5d5b-9791-d936526ff554 |  | note | Record: Required information on the Concrete Pour Record.
label | b73144f1-b0d8-5c04-b073-3303632cd1b0 |  | note | Method - Test
label | 5f55b06f-1130-5982-99e8-d70db83ef0a7 |  | note | Frequency - Each sample of Standard or Superplasticised Concrete
label | fa4b836c-6960-57e6-9b5a-ce8366a46785 |  | note | Category - IP
label | 1811fa8c-189b-5d71-80d0-3eda99de3cd7 |  | note | Responsibility - Concrete Tester
label | 91c74100-e02a-50dd-931a-472ea84bf93e |  | note | Verifying Documents - This ITP, Concrete Pour Record
date | 4ce4bcfb-8beb-5c83-95fb-5fc880e02cc4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 - Concrete Testing - Spread, Passability & Viscosity
label | c0e12a74-9a00-593b-8b87-86d6bd06014b |  | note | Reference - 610.13 (b)
label | 3ed50975-59b5-51c4-81cc-f296f5471f66 |  | note | Acceptance Criteria - Spread range = 550mm to 750mm
label | 9506dafb-8a83-5925-9ad9-15f4183d9ea8 |  | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | 4126827b-0f1b-5a35-8a3d-70f0faae4385 |  | note | ○ Passability = ≤10mm (aggregate height differential)
label | dd550d0d-ace2-5850-814a-a9622182be5e |  | note | Record: Required information on the Concrete Pour Record.
label | 1e8b7d91-fefc-52df-885e-2dd859818aa1 |  | note | Method - Test
label | 01231750-6566-5f00-a6fa-34f0ce5bbc39 |  | note | Frequency - Each sample of Self-compacting Concrete
label | 4ab981ee-373a-5833-8b9f-6bcf618a48a7 |  | note | Category - IP
label | 16eeb615-b682-51c2-b07c-2126ea7d3028 |  | note | Responsibility - Concrete Tester
label | 7f117fe6-ffd0-5de8-8630-e195cbc13ae1 |  | note | Verifying Documents - This ITP, Concrete Pour Record
date | b2b05077-753f-5ba6-aa12-161275a12f26 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 - Concrete Testing - Compressive Strength Cylinders
label | 45355b5e-dfa1-5ec1-a5b1-5e3a7d74fc09 |  | note | Reference - Site Sampling & Testing Procedure
label | 19d6e2c2-559e-5743-9242-16b2711b7626 |  | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
label | 13d8b997-04a7-5c8a-bbcd-fb216041327c |  | note | Record: Required information on the Concrete Pour Record.
label | 0c6735a0-a0a5-5075-80ae-dda5988e6773 |  | note | Method - Test
label | 45eddb79-843a-5e6a-a232-c8609a1ed665 |  | note | Frequency - Each sample
label | 1d8f0875-a4ac-53dc-b3f8-69a5557dc4f2 |  | note | Category - IP
label | 66a01360-f414-5245-8931-ed5e0f83ba68 |  | note | Responsibility - Concrete Tester
label | 6daddfdd-42ac-5b3b-bcc8-a1806dd3eb32 |  | note | Verifying Documents - This ITP
date | 514a107f-bf4f-5868-8646-2ef0e9758528 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 - Supply & Discharge Rates
label | 0582a8b7-437f-580e-9ac0-7c086cba4ece |  | note | Reference - 610.13 (a) & (f)
label | 2219f57a-c71d-588b-9966-c409e2bb75a0 |  | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | cc362360-0f48-54bc-97b9-e202e1d24fb8 |  | note | ○ No water is to be added once discharge commences.
label | 435603f0-db94-5b0d-8d8d-00ac8d92a80f |  | note | ○ Maximum time between batching trucks is 25 minutes.
label | 7b9e402b-2151-5938-8969-6c6344cddb91 |  | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
label | fa28731b-3f8d-5777-a38f-b4b6424f1f79 |  | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
label | 2a405657-5f61-5d73-9d7c-128472c062ae |  | note | Record: Required information on the Concrete Pour Record.
label | 7bdcbd4a-3955-5b89-9d22-899ef69eb9ac |  | note | Method - Measure, Visual
label | 35d6e0ac-16f4-5dab-a36a-7fa49ed86678 |  | note | Frequency - Each load
label | d6946aa6-3c17-5c38-9f54-dd8969ae6860 |  | note | Category - IP
label | 0d62d52b-069e-59ba-9e83-474409430edd |  | note | Responsibility - Foreman, SE/PE/SPE
label | 33a1d9f4-7a79-51a5-b45d-0e7cb84f1745 |  | note | Verifying Documents - This ITP, Concrete Pour Record
date | b2d0297e-27ed-515f-8175-9d0f7f0050bd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 - Placement & Compaction
label | b5648c58-b171-521e-a82b-03ebd8604112 |  | note | Reference - Placement & Compaction Work Procedure 610.18 (a) & (b), 610.18 (d) (i)
label | 1b630365-0be0-5ebe-bdbf-4b994f4640fd |  | note | Acceptance Criteria - All concrete batches are traceable.
label | 379993a3-1dac-5f00-9470-486904171265 |  | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | 6bcf79cd-9bed-5b70-b7f3-a108758ef8c3 |  | note | ○ Concrete is not dropped freely from a height exceeding 2m.
label | 2858e83c-dfc4-5a59-992f-c6209a373ad2 |  | note | ○ Concrete is not moved horizontally by use of vibrators.
label | 4b1e1f85-5d95-5a7c-b72b-4b061b58c960 |  | note | ○ Adequate compaction is ensured
label | 4c45567a-8990-598f-921e-6c660be27765 |  | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
label | 777c7603-0e9b-5482-b252-15b9f1730c9f |  | note | ○ Concrete layers are not more than 350mm
label | accf71f2-1915-56c7-86a9-2f25b7501a25 |  | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
label | 20683ca7-cfce-516f-adc8-644400562f6f |  | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | 9162c6fb-f850-5233-bdb5-08f985165851 |  | note | Record: Required information on the Concrete Pour Record.
label | 625da546-2d1b-5ef7-845a-f5065d7a9bba |  | note | Attach: Concrete Pour Record
label | 78f85f75-0609-5801-8dff-bc8c5ec9aefe |  | note | Attach: Concrete Dockets
label | 37d3d183-8354-54be-8405-a727b31da6b0 |  | note | Method - Visual
label | eb37767e-b227-5d6a-8b95-d0006c777629 |  | note | Frequency - Each load
label | deaeb97b-ba1a-5181-85f8-06393f0684ec |  | note | Category - SP
label | 401d20c5-b00c-5ca7-9855-31a39957642d |  | note | Responsibility - Foreman, SE/PE/SPE
label | 00ee48b7-6469-54bb-8395-269657525742 |  | note | Verifying Documents - This ITP, Concrete Pour Record
date | fadaf0c1-3216-58ea-b5a7-c829f4e010db |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 - Surface Finishes
label | 6355f7dc-7bc2-5bb7-9bc1-6f40542900a1 |  | note | Reference - IFC Drawings 610.31, 610.20
label | 7479f192-fbb0-501f-afd6-964cb495a127 |  | note | Acceptance Criteria - Surface finish as per IFC drawings.
label | 5d64487b-dcdb-5431-ad7e-ca466d391ea7 |  | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | 15e2b136-d745-566b-8180-fc347df70c21 |  | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | 97202b55-616f-5810-9b7d-da0393b51e19 |  | note | Method - Visual
label | eb184f26-4225-59b6-b8bf-5f2be711d64e |  | note | Frequency - Each element
label | 86ea79b3-7bc3-557f-bb39-bee9a45c27c4 |  | note | Category - IP
label | 2d3c8c66-12d9-53cc-a647-fcf79becada0 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 2d0e9fa1-5620-5891-9b72-11c93df4ca67 |  | note | Verifying Documents - This ITP
date | a687575f-20b0-5ef7-9d0f-8f45752cdc6c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Curing-Top Surface
label | 13be2619-659f-5bb1-9f9a-946c29cb05eb |  | note | Reference - IFC Drawings
label | 76d3daa5-9b7f-5c8d-941b-38468b204c7b |  | note | Acceptance Criteria - Top surface of the pile cap shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pile cap may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
label | 243e0bc4-e912-5f3a-8eff-470ecf4c8259 |  | note | Method - Visual
label | af3a782b-b20e-5e9b-a6bf-e7dd7770ba82 |  | note | Frequency - Each element
label | 4883a6ec-2bb1-51cf-b3c8-b927dc48f354 |  | note | Category - IP
label | c6ad498a-22e1-5e3a-a35d-758d3b77d7f4 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 5fd42851-a595-5107-abe6-c803254ac45e |  | note | Verifying Documents - This ITP
date | a94b1557-cf1a-5e6c-bf9c-252dad34e183 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Curing after formwork removal
label | 21d6d226-092c-51fd-acac-fb6943748897 |  | note | Reference - IFC Drawings
label | 05c67cb6-2cef-526c-8cee-63ddbecba166 |  | note | Acceptance Criteria - After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
label | 24222837-3dcb-5c0b-9444-91bc44ead9df |  | note | Method - Visual
label | 2ae02e88-a45d-5c4b-824f-c67775185831 |  | note | Frequency - Each element
label | c24035c5-5922-57f5-8bfd-9fd73e906edc |  | note | Category - IP
label | cd00b31d-5b9e-5093-a425-e01026354624 |  | note | Responsibility - SE
label | d47cafe5-4e50-54cf-8cc9-fd11c480c8b2 |  | note | Verifying Documents - Thip ITP
date | 846bd7df-d78d-52b6-b08f-9b385b9913e5 |  | date | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Thermal Differential Monitoring
label | 49a4f569-6426-5052-8215-a7a550524361 |  | note | Reference - 610.22
label | 6803119b-0c04-5102-941b-34c0b38027fb |  | note | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C.
label | d3447717-f45c-5cf4-a97d-da21a706defd |  | note | ○ Only applicable if the element has:
label | f564492b-d806-53a7-9eb5-f11bcf2cf43b |  | note | i. the smallest sectional dimension exceeding 500mm
label | 7c2acd5f-aab4-5b18-a1d5-39e53a396bad |  | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
label | 84656e60-59e4-55fc-9216-e22137928495 |  | note | Attach: Thermal Monitoring Report
label | 642152e6-acfe-58a6-9143-b348db3a1ba7 |  | note | Method - Document Review
label | 5e0e5ab1-03c4-5ce1-80ed-bad27bed295a |  | note | Frequency - Where applicable, each element
label | 181e16c9-9e6d-5404-a617-b3fd98aea1b7 |  | note | Category - IP
label | e19c64d5-9841-58a8-b25c-309e45f37ac0 |  | note | Responsibility - Foreman, SE/PE/SPE
label | eddee7ae-c807-5625-91c4-bb48f5980c07 |  | note | Verifying Documents - This ITP
date | 7c546729-dfbc-5d93-9106-cef23b00e01c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Early Age Compressive Strength Test Results - Removal of Formwork
label | b1839de0-aad7-5c89-b5af-5cdd56a8e527 |  | note | Reference - IFC Drawings
label | 31235bad-4746-56fa-8d6c-c5f61e1d818b |  | note | Acceptance Criteria - Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
label | 27b10b27-4630-5312-a2c1-49ee06c71126 |  | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | 041194e9-805e-5534-b21a-56ee623ec9a0 |  | note | Method - Document Review
label | b7c1ab59-90e9-5a51-ae94-288af35acd5e |  | note | Frequency - Where applicable, each element
label | 7d449959-c7f4-5995-9309-250e63cffd4c |  | note | Category - IP
label | da781b6b-865f-5025-a16d-18fdad3c7ffe |  | note | Responsibility - Foreman, SE/PE/SPE
label | f5bf6538-7141-5161-9021-971aa326c3ee |  | note | Verifying Documents - This ITP
date | 4e45d1a1-9783-55f1-b719-dd9ed470cb51 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 - Surface Inspection - Cracks
label | 219a59bb-5f28-551a-a3c4-a3c82f6597d4 |  | note | Reference - 610.24
label | 20c7baea-12a0-5ce7-ab0a-eefc8f99a48c |  | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1)
label | 238e9255-24a6-547f-b879-feb3d9f0932c |  | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | 04336ac8-d272-55ad-a73e-50fb3e128a77 |  | note | Method - Visual, Measure
label | 2fdf18be-c1ab-5192-8ee6-b250c60168af |  | note | Frequency - Each element
label | 570b678d-aa9c-5b98-abe7-9e6dac53373e |  | note | Category - IP
label | a6c1b2e2-a1d6-5fa5-89af-47fd40e3bb43 |  | note | Responsibility - SE/PE/SPE
label | 6be41d90-2cf6-5519-827c-3cc1c78cc47b |  | note | Verifying Documents - This ITP
date | 936d1bd9-0eff-50e6-a829-9137fcdbb5c4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 - Surface Inspection - Surface Finish
label | 31f17bff-3ea9-582b-a919-41adaa52a305 |  | note | Reference - IFC Drawings 610.31 (a) - (n), 610.32
label | 883b3ca3-a4f5-52e6-943b-dd5991381288 |  | note | Acceptance Criteria - Comply with the IFC drawings and specifications.
label | 78cc79a9-92e1-50f9-aa81-0d7df020ac58 |  | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | 2ab94267-f210-5c68-9f89-734c487ba7dc |  | note | Method - Visual
label | c6a82e19-0d4e-52dc-b8e1-401a83f05928 |  | note | Frequency - Each element
label | 4ab9aba0-9ce1-58d4-ab5f-7c78efa6f8b6 |  | note | Category - IP
label | 8fc72889-f2bb-5355-b5ff-76d7b2727a45 |  | note | Responsibility - SE/PE/SPE
label | 090c23b2-95c5-591b-b2a7-2743971545e1 |  | note | Verifying Documents - This ITP
date | a2a82405-f652-512c-b44c-ae01e39fb348 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 - Measurement of Concrete Cover
label | e969d2f5-6fe3-50af-941c-a3f4fab62921 |  | note | Reference - 610.34
label | e10d4206-134e-54f7-b2ad-24453d106c33 |  | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
label | f079e596-f63e-5dba-bedc-20d97d4c39de |  | note | ○ Minimum 10 no. measurements recorded in each area.
label | 7d62d88a-6506-542e-8958-e688a0630aa9 |  | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
label | 3c795a0b-4aa4-5934-8bdc-3f3fcc9d5b03 |  | note | Attach: Covermeter Check Record
label | 4bfc4b40-8c7f-5c9c-b2d8-84605e9058e4 |  | note | Method - Measure
label | 05a723bb-1748-52bf-9601-435f763f6a4f |  | note | Frequency - Each element
label | 8967682f-9155-5aa7-b533-ebffc838dad0 |  | note | Category - IP
label | c927b98e-98ae-5b5c-91d9-ce1af02fe628 |  | note | Responsibility - SE/PE/SPE
label | 196c16fd-bdd2-5530-ac92-92df3f681c89 |  | note | Verifying Documents - This ITP
date | 88a89b35-84c8-56ce-ae45-6583631cc3f9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 - Early Age Compressive Strength Results - Placement of Fill Against Concrete
label | bda1604d-9bc3-5f9f-b991-eab0cc41b4fe |  | note | Reference - Early Loading and Trafficking of Decks and Approach Slab Procedure 610.35
label | e44b34b5-0e2e-5f9e-972a-810de2d6bf5a |  | note | Acceptance Criteria - Fill is not placed against concrete within 14 days of pour.
label | 04c038b2-ad7d-5acd-b853-91348b1f9854 |  | note | ○ Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
label | cb87583c-6d80-5ea0-b9be-d1aaf29a8ca2 |  | note | Attach: Concrete Test Results or Maturity Test Results
label | bfde790e-60a5-5ba8-83a8-87f4f498ae79 |  | note | Method - Document Review
label | dbd9dcf0-3b6d-5ca4-8844-08e9d7514742 |  | note | Frequency - Where applicable, each substructure element
label | 94fa8a84-dd8e-5964-bd99-ab274a1f77a1 |  | note | Category - SP
label | 7aba84ea-bcb6-546c-9bd4-594a7cd90c76 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 8f00e205-b5b5-5c58-8d04-e259eff27f93 |  | note | Verifying Documents - This ITP
date | a51068c1-2ff9-5470-9a8b-21ee195988dd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.9 - Compressive Strength Test Results
label | 3c3208e1-fc32-5e28-9549-759e35270b12 |  | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
label | d4716329-02c0-5d9e-99d1-200312fd2c58 |  | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | ace3186e-cd35-525f-8855-d85f6223ec1f |  | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 7eef129c-355b-5eab-8425-c17f38486946 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | cb683cae-4f89-5887-8574-cc6ff4788a53 |  | note | Attach: Compressive Strength Test Results
label | 35009282-4848-565e-8a3c-570387c83f61 |  | note | Method - Document Review
label | e0aba5ff-3f8c-5eac-a1db-2f54236db636 |  | note | Frequency - Each cylinder
label | 0634216f-d8f3-5eea-acb8-e08d1a2f40e2 |  | note | Category - IP
label | 990ca89c-1c82-56b1-b0eb-7a3fe54e8572 |  | note | Responsibility - SE/PE/SPE
label | e138a501-8905-5a6b-bc82-f06a30e91d5c |  | note | Verifying Documents - This ITP
date | bbda4e90-f6a9-532e-85c6-a74b559c00f8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.10 - As-built Survey
label | 5244eb9f-7ef5-55e7-9541-07b150ef2983 |  | note | Reference - IFC Drawings 610.47 Table 610.472
label | ba11d60c-7545-5c81-8157-20f1ef5453f7 |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
label | a1e86ece-acb0-5e78-a4a8-5caecbe3d8ed |  | note | Attach: Survey As-builts / Survey Report
label | 6261e3db-48a8-594d-91e1-7e57a7311bcd |  | note | Method - Document Review
label | 81ebc053-a218-59d6-87cf-e36fa6f812f7 |  | note | Frequency - Each element
label | aaa07c9e-42c0-5547-8647-4a0e74a9b524 |  | note | Category - IP
label | 0a13c4af-3419-537c-8784-03a234edde56 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | d0a950bb-9306-590a-a985-dac8c6906c47 |  | note | Verifying Documents - This ITP
date | 57114000-394e-5750-a33b-be29a41769f5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.11 - Non-conformance Report (NCR) Closure
label | 0040cc55-1b3a-55e5-90cb-2a0702932c55 |  | note | Reference - MRPA Quality Management Plan
label | e4915ef0-4f05-50f1-b3f6-ddf21086b1a8 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | f6bbc6c7-7dd2-589e-82d3-c0e0a12a3475 |  | note | Method - Document Review
label | 00abf5d7-6adf-59b1-97d1-dfa29940d39a |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | fb389238-485f-5b73-9d32-7d0647236add |  | note | Category - HP*
label | d112b900-a84a-5b9d-9dfb-774367ea479f |  | note | Responsibility - SE/PE/SPE
label | a748f516-002c-5747-9546-7d4582b279de |  | note | Verifying Documents - This ITP
date | 61ac4572-49db-5bd6-ad28-f9a8f80ecc78 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 191365ff-d1c0-5fe6-9306-9d98a37c9d76 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 2a7b588d-8d08-51b1-9572-48235c78d9b4 |  | textbox | Name:
text | 1bb15fe2-3362-5ac6-9b9a-d0f52035fb5d |  | textbox | Position:
date | 1d08114d-b49d-51ed-b1bd-e65401bce7c7 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-054-CPD-Subsurface Drainage (Supply and Install) | itp |  |  |  | Yes | ITP-054-CPD-Subsurface Drainage (Supply and Install) - Rev 0 | a8308ae8-b213-4b0a-8084-93b1ace135c7
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 5e756c66-1426-56ad-bf7f-1753be386bc2 |  | note | Document Title: ITP-CIV-CPD - Subsurface Drainage (Supply and Install)
label | 73872110-eeed-568c-904c-9ee0962d7bf2 |  | note | ITP Description: CPD - Subsurface Drainage (Supply and Install)
label | 7fadb68e-8521-588f-bd62-ea9b74570bdf |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 9b621f6c-1c7a-5cf1-914d-42a5b9ddaaba |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 67320dad-d3c2-56b5-8786-0005fbe7f61c |  | note | Revision Number: 0
label | c4bd4f24-ab79-5d8b-b974-2ef4aac0c609 |  | note | Revision Date: 27/07/2023
label | b30ab790-24ed-503a-b68b-c2c2fde9a83b |  | note | ITP created by: William McCuskey
label | ec15eb94-ec94-5b28-ac8b-9ee20565fcca |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 78b41507-92ed-5564-bfd9-55c03a69c0c5 |  | note | Reference - VicRoads Section 702 (May 2019)
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | b210e6dd-638b-545b-a55a-77e6ef489c0f |  | note | Reference - VicRoads Section 204 (Dec 2015)
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | c66b22bf-ea71-5a53-b2df-34ee787eb1ac |  | note | Reference - VicRoads SD1611
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | c648f746-be2f-5579-b820-f820befa2368 |  | note | Reference - VicRoads SD1051
checkpoint-status |  |  | checkpoint | 1.5 - Non Dependent
label | c705426b-171e-5974-80ad-5540e80d5731 |  | note | Reference - VicRoads SD1631
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Drainage Pipes
label | b5796c7a-541f-5723-9f2d-215166b00127 |  | note | Reference - IFC Drawings Section 702.04
label | b59b964d-521a-59e4-9fba-8c40dc4e1df2 |  | note | Acceptance Criteria - Subsurface drainage pipes:
label | 5bf33e40-132d-57c1-8ad1-f08f630c4473 |  | note | • Category 1, 100mm DIA Class 1000 corrugated perforated plastic pipe - with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
label | 6fe38e57-e807-5ac4-bf19-21b4adc60b77 |  | note | • Attach: Material Approval Ref Nos
label | be3b896d-f3c6-50b6-a212-c6c75d13b7b2 |  | note | Method - Verify, Document Review
label | ab29a124-7cf2-5af0-80d0-ec1615c7fea7 |  | note | Frequency - Each Lot prior to work start
label | e0a2a39a-e518-5e4e-9997-9ca32b6c200e |  | note | Category - HP
label | 0b05d7b5-87de-5d95-8771-0e3865fb76ca |  | note | Responsibility - Nominated Authority
label | 8df53096-0a8f-5576-aa62-3a60a7305861 |  | note | Verifying Documents - Conqa HP Release
text | f558844e-4de4-541c-8734-37d18c21271b |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Granular Filter Material
label | 6779b815-7d29-5755-a92e-c96f3784728c |  | note | Reference - IFC Drawings Section 702.05 Table 702.051
label | dad02bcd-59a4-5e88-9b37-ce100f6c57e0 |  | note | Acceptance Criteria - Granular filter material:
label | 5b88e3b0-5c50-5ae3-b27e-fd7b1eda594e |  | note | • Filter sand to be as per IFC drawings and comply with Table 702.051 and Section 801. Supplier to be accretied with Vic Roads.
label | d593be4c-2e48-56b9-b702-4c0f5b45efb6 |  | note | • Attach: Material Approval Ref Nos
label | 1e2016a8-85e4-5f7f-b748-5d420fd01a6f |  | note | Method - Verify, Document Review
label | 8ea1b184-d0d4-558a-ba31-80173c07d358 |  | note | Frequency - Each Lot prior to work start
label | 5dedc4f4-3633-57d2-82a0-a00432f60603 |  | note | Category - HP
label | dcbf3c06-0aac-5896-b0b3-88a90a5b4c89 |  | note | Responsibility - Nominated Authority
label | a371b996-a5f2-5d58-ba51-d11d5b68e904 |  | note | Verifying Documents - Conqa HP Release
text | 4e16d30d-4ab9-503d-bf2a-6cf8608c36ff |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - No Fines Concrete
label | 46b59dd1-10ec-512e-92e6-4cb8142855b5 |  | note | Reference - IFC Drawings Section 702.05
label | 984fa64e-635d-5c1e-84cb-956ca8cddcca |  | note | Acceptance Criteria - No Fines Concrete:
label | bea200ad-41ea-5d1c-90d3-def04ad1f310 |  | note | • Shall comply with 702.05 (e)
label | 0c1d1023-3442-588c-a5f0-946ec6e83b67 |  | note | • Attach: Material Approval Ref Nos
label | 20db4eed-3d07-5d5d-8c37-80cf5fa0f39d |  | note | Method - Verify, Document Review
label | be96de49-b1af-56fa-bbfa-c34228cdf7f9 |  | note | Frequency - Each Lot prior to work start
label | 00d61619-bd12-59d1-b1c9-e6d44cbbd858 |  | note | Category - HP
label | 1e334a40-5ed7-5d87-be37-1f4f44ee2d3c |  | note | Responsibility - Nominated Authority
label | 75ef8396-3798-58e8-83c5-81a00e143355 |  | note | Verifying Documents - Conqa HP Release
text | 1e2f92c6-a897-5c63-82cd-9cb3a010e5af |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Geotextile Filter
label | 6975b730-6514-574a-847f-c07265b61c08 |  | note | Reference - IFC Drawings Section 702.06 Table 702.061
label | e1dab299-9d25-5c3b-9514-a9ea410354c8 |  | note | Acceptance Criteria - Geotextiles:
label | b81b089c-1d18-5e17-ae36-3af162afbc38 |  | note | • Shall comply with 702.06
label | c41b3eb6-c018-519b-993b-9b3b9b8dc359 |  | note | • Attach: Material Approval Ref Nos
label | 8bfb0f32-0505-568a-8690-62fbb2046471 |  | note | Method - Verify, Document Review
label | 966e471d-df32-5d4e-a83c-1122b2ef1022 |  | note | Frequency - Each Lot prior to work start
label | f4824265-b9a1-5d20-abc7-ff9b44526a5d |  | note | Category - HP
label | 36750d5c-b5df-567e-8413-7aac74f38d75 |  | note | Responsibility - Nominated Authority
label | 9a3434a4-ee45-5b34-8ade-c75e4a715500 |  | note | Verifying Documents - Conqa HP Release
text | 12efcc18-34f6-50c9-92bb-9596ceabd1e9 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - SSD Pits, Pit Lids, Flushout Risers
label | 5c6b4fc4-4d62-5dea-8df9-da2c691fc597 |  | note | Reference - IFC Drawings SD-1051 SD-1611 SD-1631
label | 5b389cc5-140b-5d97-8ce9-856b0e6907a6 |  | note | Acceptance Criteria - Subsurface drain pits: shall be Type S1 (as per SD 1611).
label | 1c2f7ac6-ec6b-5b2a-a3b0-55b4ccaf9fbe |  | note | • Pit Lids shall be: Type M3 circular lid (as per SD 1051) for Type S1 pit.
label | fa557a01-170a-594d-864d-bc00b8cf478b |  | note | • Flushout risers: As per SD 1631
label | 6019bf60-d1f3-56ee-ae61-85c769e9ff96 |  | note | • Attach: Material Approval Ref Nos
label | 4a6d949e-972c-53d7-b435-d4411b183324 |  | note | Method - Verify, Document Review
label | 52c285b4-ecd9-5fa1-9884-df41f4a40ce2 |  | note | Frequency - Each Lot prior to work start
label | 867df89c-512e-5d3d-9d34-60e57b063665 |  | note | Category - HP
label | c0a20f3f-6a6d-5c95-a5e0-931049ee4b54 |  | note | Responsibility - Nominated Authority
label | 8d1bb047-85db-5bf9-a3e4-5af829ba59ee |  | note | Verifying Documents - Conqa HP Release
text | d3e2311a-4415-51ac-a4b4-d0a0bec6641d |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Documentations
checkpoint-status |  |  | checkpoint | 3.1 - Check for correct documentation
label | 2fd21618-982d-5eb3-a309-4854d0b4bb90 |  | note | Reference - IFC Drawings
label | 934924aa-1824-59e4-b2c8-1fd9bb5f90d7 |  | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | 27b65153-7293-5189-bc5f-a3fe349e9804 |  | note | – using the correct and complete set of drawings
label | 9cf63416-89b3-513c-a9dd-baca03312615 |  | note | – all drawings are the latest revision
label | 13f4817e-20fa-5c01-a9b8-136cc4e8437f |  | note | Method - Visual inspection
label | a6d9adf8-d0e4-55a9-a441-8f39c43fb9c1 |  | note | Frequency - Prior to commencing any activity
label | 7d80d9f9-abf4-531d-aba3-a5f7c124ffbe |  | note | Category - WP
label | ae54de58-32a0-5554-a4ae-f1059be70202 |  | note | Responsibility - SE/Site Supervisor
label | 9a6da605-2cf7-5923-b8ad-1107cee1c93e |  | note | Verifying Documents - This ITP Signed-off
text | 25148f33-f8c7-55da-9d6a-2ec3343457ce |  | textbox | Date Completed:
checkpoint-group |  |  | section | 4. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set Out
label | d888693a-661e-56b1-951e-7c66537b9931 |  | note | Reference - IFC Drawings Section 702.03
label | 83035189-e0e3-5b71-a892-4596c5fae006 |  | note | Acceptance Criteria - Survey to set out Subsurface Drainage line.
label | 153f7e79-367a-545a-aeb1-6b4e8d58c87c |  | note | Method - Visual inspection
label | bc1869bf-402c-56c5-97be-a667477b3970 |  | note | Frequency - Each Lot
label | 14e3dbda-a02f-5154-93fa-4c52479cfa5f |  | note | Category - IP
label | 3110ac88-9619-5fcc-b1e7-92121e2eeb2e |  | note | Responsibility - SE/Site Supervisor Surveyor
label | 41f41eaf-e3f7-5812-9782-8e0a505634e1 |  | note | Verifying Documents - This ITP Signed-off
text | 6c5d890b-5b97-51e6-a663-db355449eed3 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Trench Excavation
label | a70f40e5-c83c-5092-af9b-687336db85c2 |  | note | Reference - Section 702.08
label | c1972e48-14a2-5347-a70a-f8efa7b71d62 |  | note | Acceptance Criteria - The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe.
label | 1f8c4e72-ae3e-51a8-a24e-f09f72ce93d4 |  | note | • There shall be no departures from the grade of the base of the trench that would allow ponding of water.
label | a7594d55-9149-536c-a372-5c39d05e9ce0 |  | note | • Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed.
label | 3e680e9d-54ed-594a-a285-c9578648464e |  | note | • The base of the trench shall be inspected by a superintendent to verify compliance with 702.08 prior to placing beding in completed excavations.
label | bf24e9e5-2f4f-55d4-b834-378b9bf2d314 |  | note | Method - Visual Inspection
label | 71f94bb1-ab95-5798-ae7a-760e6fa2e3ba |  | note | Frequency - Each lot
label | 113f10ca-be7c-5ba9-b72c-cfaf36aa5b2a |  | note | Category - HP
label | ac4291d0-514c-5c55-87b2-1a340f68746b |  | note | Responsibility - SE, NA (Nominated Authority)
label | e2cd5145-e123-546c-a217-d743c0be25cb |  | note | Verifying Documents - Conqa HP Release
text | 50b66fa8-2394-5832-8011-24d090010baa |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Placement of bedding
label | b705b011-c4c7-566a-bfe3-88f4f70d48b9 |  | note | Reference - Section 702.09 (c)
label | 640a8ee6-9ed2-5220-9725-d461f324b59c |  | note | Acceptance Criteria - Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level.
label | 89c4c992-717e-58f9-9a9a-9ecf7fa7e5da |  | note | • Attach bedding material delivery dockets
label | 67f5b9d7-ac2f-58c0-9806-f5bf16ca17de |  | note | Method - Visual inspection
label | a2cf62e6-3529-55a4-af59-43bdfb7c4c20 |  | note | Frequency - Each lot
label | bec0046c-b2d9-5e19-8c71-eae115a3eca8 |  | note | Category - IP
label | 1a2791c7-5180-5028-9e80-9fa5a3f5366d |  | note | Responsibility - SE/Site Supervisor
label | bef3cdfb-41fa-5a3d-be76-d2b0fc53db1a |  | note | Verifying Documents - This ITP Signed-off
text | dde6bb55-f4fb-568a-bbbb-bfa81a73a63b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Pipe and Geotextile Installation (if required)
label | 033d5c9d-d831-5a78-91a9-3ec4ce74268c |  | note | Reference - Section 702.03, Section 702.09
label | fd373f6e-6746-54bc-8906-673a59283596 |  | note | Acceptance Criteria - Pipe shall be placed centrally in the trench on the prepared bedding and held firmly in place. Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped in accordance with specified requirements.
label | aea4b5bd-5941-5867-bf1f-3fa36768f8cd |  | note | Attach Suburface pipe and geotextile delievery dockets (if applicable)
label | f28fbfe0-cd9b-5c39-932a-606cc405e543 |  | note | Method - Visual inspection
label | e5663bc4-61f3-50a7-bc21-d7c6ca51513c |  | note | Frequency - Each lot
label | 7519a3c7-9cab-5059-9d88-547e9951e09d |  | note | Category - IP
label | 6e3ad5b5-4d75-5c5f-b14d-a3ab4ff75622 |  | note | Responsibility - SE/Site Supervisor
label | 4b15a022-df71-5e5c-b7fa-d355262c2eac |  | note | Verifying Documents - This ITP Signed-off
text | 89544609-bb53-5633-b9d9-818a589bf8f8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Backfill Installation (Granular Filter Material)
label | a63ccf80-1165-5629-a90a-756a1962ceb8 |  | note | Reference - Section 702.09 (g)
label | 2d981ce4-a03b-5246-89b5-12dc73f81e94 |  | note | Acceptance Criteria - Material shall be placed moist and compacted in layers not exceeding 300mm.
label | 8de61911-e80c-5d78-940a-d87043b46a70 |  | note | • The method of compaction shall be in accordance with the procedures and reviewed by the NA.
label | 78e06ee3-78bf-54c0-9f96-8288788fbc29 |  | note | • Attach Backfill Delivery Dockets
label | 653253c0-fb8d-532b-ae11-e5d2f8a49dac |  | note | Method - Visual
label | ebfbd0ef-a68c-5eb7-964c-8eb30e4689fa |  | note | Frequency - Each lot
label | 69191e75-fad4-5cf8-9472-af01739c487d |  | note | Category - HP*
label | 1c932b2d-a6b7-5b1b-bb56-f22ac93114d1 |  | note | Responsibility - SE, NA
label | 86c676dd-4534-5203-8b6f-6149d9264544 |  | note | Verifying Documents - This ITP Signed-off
text | 423a13d0-ca67-5727-9392-ebc99af2295f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Backfill Installation (No Fines)
label | 74acda89-7936-5a8c-8fc4-23c756fc8add |  | note | Reference - Section 702.09 (g)
label | f6085be0-f146-54a6-af4e-54417cc92429 |  | note | Acceptance Criteria - All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing.
label | cea87425-1c26-544f-b900-673131d0b962 |  | note | • Attach Backfill Delivery Dockets
label | 2359108a-063c-5d17-924c-fd29799c5c52 |  | note | Method - Visual
label | 83759285-96ac-586c-85e2-4abd1b459878 |  | note | Frequency - Each lot
label | 4c972846-af50-55df-99e3-c358c9d69b0c |  | note | Category - HP*
label | c3624f7e-616a-590d-93c0-573c4789f896 |  | note | Responsibility - SE, NA
label | cc7dc6ec-a691-5c59-a28b-dfb78094c16a |  | note | Verifying Documents - This ITP Signed-off
text | 3b319340-47c3-5043-a165-aeacec418bed |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Install Pits and Flushouts
label | eb52c2d6-8ac5-5746-a0ec-2ee48969ea31 |  | note | Reference - Section 702.10
label | 6e148972-a161-5be8-814a-77252d24f099 |  | note | Acceptance Criteria - Subsurface drains shall have access points at the start and finish of each run.
label | f746ce8b-a7dc-5da9-9d4d-d63708011f3d |  | note | • Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings.
label | 5e596683-69fc-5fe1-b6ff-7e90f625dac9 |  | note | • Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings.
label | c6075ac1-ca70-51e1-9431-63fedb0ec56e |  | note | • Attach Pit and Flushout Delivery Dockets
label | 8047eb38-f5d9-5478-bf18-0b8b6094aee6 |  | note | Method - Visual
label | c540bead-2874-56c5-af4d-a235c932ca24 |  | note | Frequency - Each lot
label | 2ecc4d8d-6ca7-55df-afa6-01d776bbc20d |  | note | Category - WP
label | cc5351f2-b788-5e44-a7cf-e2cb752ebde8 |  | note | Responsibility - SE/Site Supervisor
label | a7517441-2bc1-5a16-9109-1600758d17d5 |  | note | Verifying Documents - This ITP Signed-off
text | de5d8165-62c3-5c35-af53-ad38fdb95981 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Marker Points
label | e047c081-f1dd-5f9e-8f7c-bb7934ed2ab3 |  | note | Reference - Section 702.11
label | 3d0cbebe-6d20-56d0-9acd-93af052b2166 |  | note | Acceptance Criteria - At all fill batter and drain outlets, supply and erect marker posts as shown on drawings
label | d575821b-c29b-53dc-a2c1-a687e0205b76 |  | note | • Attach Marker Post Delivery Dockets
label | 502e7323-e708-5d20-b9ae-acbe1d09cef1 |  | note | Method - Visual
label | 187abe52-5a65-5c5f-b084-69762e84edf5 |  | note | Frequency - Each outlet
label | 70f4068d-661a-50d0-82a5-74c852be709f |  | note | Category - IP
label | 3329a9cf-c213-5e6a-b4b4-f27156365c76 |  | note | Responsibility - SE/Site Supervisor
label | cbac4167-5bfb-51c6-8557-2d520df43e35 |  | note | Verifying Documents - This ITP Signed-off
text | 715a474e-b1eb-5b53-be00-39cbf91a97f6 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - As Built Information
label | 85c26b24-727b-50ee-8de6-3c6d8317d8c7 |  | note | Reference - Section 702.03
label | a786e809-50ea-55be-ad4c-319cc1c94348 |  | note | Acceptance Criteria - The invert of the sursurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line
label | 1f33915d-3d9a-5387-8ab4-5dd9ae08bff2 |  | note | • Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length.
label | 206579b8-6554-50d6-aa36-0d1531fac5b8 |  | note | • Attach Survey Conformance Report
label | 7a7793bb-6400-5b5f-86a9-fdcb46dd7e8d |  | note | Method - Document Review
label | f76e61d9-05f6-5af7-9e6b-ed385a2adf17 |  | note | Frequency - Each lot
label | db6f68f1-2e48-580a-8ddf-c81c515fee94 |  | note | Category - IP
label | 789dc594-c779-5589-ac3e-dc8f2b636c75 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 3df17ede-d5e5-5ebd-a7d2-b728465e1124 |  | note | Verifying Documents - This ITP Signed-off
text | 31cbdff4-8b28-5c4a-9967-4249661eb4e5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Flushing
label | 7fac7770-1824-5d53-9f6e-f6d169c0802b |  | note | Reference - Section 702.09 (h)
label | 89c741b8-2d9f-562b-9c3f-b3a545855ff0 |  | note | Acceptance Criteria - Flushing test shall be witnessed by the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture.
label | f77cf290-b9fc-57b0-ac44-d76ac248f0c6 |  | note | • Attach Flushing Tests Records
label | ad869ed9-8b52-58fb-b5e4-d5a42ad95a5f |  | note | Method - Document Review
label | b6510b1b-92d9-56dd-a004-f8aebec2c06e |  | note | Frequency - Each lot
label | 51b61388-5855-5f13-b92b-1688d13232e2 |  | note | Category - HP
label | c190dbdc-f065-58d9-bb39-b3590d45b102 |  | note | Responsibility - SE, NA
label | 9b4da817-4475-5425-b940-40e09253dbb8 |  | note | Verifying Documents - Conqa HP Release
text | 76cf8b12-05be-5cb8-8bc4-9f96688e2b8f |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.3 - Inspection of Subsurface Drainage - CCTV
label | 50f09ae0-1760-54f4-ab9e-3833c970dbbd |  | note | Reference - Section 702.09 (i)
label | 15e991a3-07af-5e10-b6aa-9c6c6230535d |  | note | Acceptance Criteria - All subsurface drainage lines shall be inspected, after the flushing test as per clause 702.09(h), and prior to placement of asphalt by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is free from obstruction and to check for visible signs of defects.
label | 7cef991c-1b5a-5b41-ad05-5bcfeb64979d |  | note | • Attach CCTV Inspection Record
label | 72847521-4d11-5acd-aaf1-e224600441f8 |  | note | Method - Document Review
label | 23ca1eb0-1c8f-5155-bf22-43cbc5a3cda8 |  | note | Frequency - Each lot
label | d3998dc4-6389-5d01-b944-4c263846f273 |  | note | Category - HP
label | ff23ec9e-9d32-5c58-83f4-7afd16bada64 |  | note | Responsibility - SE, NA
label | ccf4b25b-7b8e-55b0-a858-6e14888220fd |  | note | Verifying Documents - Conqa HP Release
text | b4011a66-7aa9-5513-ae59-84f65eebad8f |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | 35fa8fb7-10d6-5a7c-9a8a-30f5f24da95a |  | note | Reference - MRPA Quality Management Plan
label | 8f6ffcdd-295d-5834-bc64-bc8fc44b9856 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed in CAMs.
label | e47a01ba-0c65-5d72-bd15-72c8a055a60b |  | note | Method - Document Review
label | 5ad6364a-8853-5592-a982-cd4ccb6ee130 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 40ecc591-f9fb-59a4-8dec-eb011bc621a3 |  | note | Category - HP*
label | 1b33d991-0b38-5b86-b47e-e8932df24bc2 |  | note | Responsibility - SE/PE/SPE
label | 45a4651e-2ddc-5cbb-8c88-1da11aa260cb |  | note | Verifying Documents - This ITP Signed-off
text | 39cee6ae-fb96-55d5-93d4-5dd3033dbd3b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 1906eb47-6ddd-522d-8aac-61c67e65097e |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | edd5b7dd-7068-53aa-9fa5-c796b85993d3 |  | textbox | Name:
text | 288f74df-e006-5904-846f-15d1971cee2b |  | textbox | Position:
text | 1942fac1-7484-583c-bf81-e53d5cdf2c73 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-flat |  |  | checklist | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation | itp |  |  |  | Yes | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | b070ead5-3321-4740-9077-afccf5184d85
checkpoint-no-status |  |  | checkpoint | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
label | 60628a10-36c3-5717-a94e-cba0e4963c02 |  | note | Document Title: CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
label | 7f185b64-4be8-53f9-ba49-19249c95a3cc |  | note | ITP Description: RSS Walls - Panel Installation
label | a57300cb-ac92-5703-a886-542912e0d281 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | a4ebe98e-b2ba-57a7-923b-97f01270e155 |  | note | Revision Number: 0
label | 841a0393-beab-5097-b02b-e7f212bad102 |  | note | Revision Date: 06/11/2023
label | c46adb0f-d479-54e7-85f1-7be0a8b501c8 |  | note | ITP created by: Matthew Dib/Jason Quan
label | fb1c9a3f-e81c-5ec0-9789-5d4689fa09a0 |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1 - Panels-survey set out-Tolerance
label | ec5c0bf7-11f8-5abb-a3cf-72663c7a9a97 |  | note | Reference: VR 682.20 IFC Drawings MRP-080-C-RFL-DRG-33-CPV-CSW-1001 and 1202 to 1205
label | 98312932-a44d-5ffb-a9eb-538b01bcf311 |  | note | Acceptance Criteria: Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
label | 135cc316-6a97-5e2b-a404-dde9f038be6c |  | note | Method: Measure
label | 522488ac-c6bd-5d26-a467-ca8e217afce6 |  | note | Frequency: Base course panels
label | 91d06444-0ff3-52f9-9612-38b2dc1578ea |  | note | Category: IP
label | 6d5b175c-ed52-5d4c-ad93-4328bb8616cc |  | note | Responsibility: Surveyor/PE
label | 58b763c9-0f26-5de3-972a-0a28e146ec78 |  | note | Verifying Documents: This Checklist Signed-off
date | 740f46ec-6adb-560c-8e71-6b80f6ddabec |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2 - Mark-up panel for construction team
label | fc30ab54-9bc1-5ef8-89e4-a3da88e46ac2 |  | note | Reference: Construction Manual
label | 647c88ae-771b-5b2c-9fbf-124036b85870 |  | note | Acceptance Criteria: Mark number of strips per row on the back of each panel. Mark design location (Wall number, row and column) as per elevation drawings on the back of each panel
label | 7c9b37cf-4f51-5ef0-9d6f-508986b738a6 |  | note | Method: Visual
label | 2ef95ede-fe73-5675-ba20-57d5e5c9d35b |  | note | Frequency: Each panel
label | 5702c218-3d46-5990-b1fe-febcd5f47cb2 |  | note | Category: IP
label | 90a89d60-0ab6-5de2-b8fb-be8f8ada4604 |  | note | Responsibility: SE
label | ec306520-4e89-54e5-8b1b-eee571f9be03 |  | note | Verifying Documents: This Checklist Signed-off
date | 4689fe11-c498-5a4e-b62c-76dc673f33e8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3 - Panel installation
label | 078b4f66-2ce3-5cfa-a4b7-402931178a61 |  | note | Reference: IFC Drawing:
label | 27559ff0-7bfb-545e-a0df-23ca6cff4992 |  | note | ○ Instructions: MRP-080-C-RFL-DRG-33-CPV-CSW-2003
label | 57e65f2b-d31d-5882-bc78-e6137256042f |  | note | ○ Weephole Locations: MRP-080-C-RFL-DRG-33-CPV-CSW-1401, 1402, 1501, 1601 and 1701
label | 1d1e5660-7a5a-509f-8c70-ea5d27df247a |  | note | ○ Archtectural pattern drawings: MRP-080-C-RFL-DRG-33-CPV-CSW-1404 ,1503, 1603 and 1703
label | f00e53e3-d374-5126-8e8d-c48dc3bc512e |  | note | Acceptance Criteria: RSS Panels are to be installed as per IFC Drawings and specified schedule.
label | ee535164-40b9-50d9-8f16-704c908bd0fe |  | note | – Check for correct architectural pattern
label | f464d46b-746c-54e6-ab63-cf08e31d26a1 |  | note | – Check for Weephole Locations
label | 895dec39-4a52-5663-a82c-f280c528f466 |  | note | – Check the 1 in 40 slope is to be maintained
label | 693c030e-7c10-53eb-81d3-defd6ad133e9 |  | note | Method: Visual, Measure
label | 1f19cc13-4b35-5e41-bfe6-89a47ed50062 |  | note | Frequency: Each panel
label | bb2265da-d911-5ca4-b18e-238e266fa647 |  | note | Category: WP
label | dbaff399-13ad-550c-8e4e-6cf95a23036d |  | note | Responsibility: SE
label | aed3e718-9a41-535a-a79d-78b1bac3e92c |  | note | Verifying Documents: This Checklist Signed-off
date | 17899be1-1760-551e-b17f-dc1a815d2489 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4 - Bearing Pad Installation
label | 21d82eeb-ce61-5b61-bc45-535fbeaee529 |  | note | Reference: IFC Drawing: Instructions: MRP-080-C-RFL-DRG-33-CPV-CSW-2003
label | 8a485805-caee-517c-8f42-8d5eff7aaaab |  | note | Acceptance Criteria: 3X19mm bearing pads must be installed per panel - Centre of the outer bearing pads must be 200mm+/-10mm from the edge of the panel
label | eac3dcdb-de26-587d-9842-339dc55466b6 |  | note | – Check the 19mm nominal gap to be maintained
label | dd417a53-0ec7-5aa1-9013-2d247072893d |  | note | – Install 3 Bearing Pads at rear on top of panels
label | 585dd8a9-54db-51c7-b7a0-c9ddca90e580 |  | note | – Above must be checked with Surveyor prior to backfill
label | 3fd97cfd-7cd4-5b45-a6bb-ac4b8323a265 |  | note | – Note bearing pads shall not be installed under base row panels
label | 579f0991-0306-5447-a29c-e06df963e058 |  | note | Method: Visual
label | 6abf0b61-c07d-53fb-979d-209987467ca9 |  | note | Frequency: Each panel
label | fa828318-1cef-5bc5-aa51-e8aa6cb93b9f |  | note | Category: WP
label | e8a5bc05-9d34-532b-99a8-a76d89e33d9b |  | note | Responsibility: SE
label | 7d9a643a-e8f1-569c-bc29-d700157b7743 |  | note | Verifying Documents: This Checklist Signed-off
date | 6604db6a-03b9-5b55-81e7-87fa03d494d7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5 - Panel installation-Abutment interfaces
label | 352e800a-bafc-54a1-85ab-ecc0c5f1a877 |  | note | Reference: IFC Drawings MRP-080-C-RFL-DRG-33-CPV-CSW-1106, MRP-080-C-SME-DRG-34-CPV-CSF-3023 and 3024
label | 898bf9c8-b7a0-5543-b3da-30688ba7c931 |  | note | Acceptance Criteria: Panel installation and abutment interfaces
label | 5116b153-d451-57d2-9c41-3768e167ef4b |  | note | – 20mm nominal gap between panels and Abutment wall is to be mainatined
label | a8ee7baf-d9ff-5316-b007-11061af970a8 |  | note | – 150mm wide x 6mm Folded Galvanized plates (Grade 250) drill and fix to as per IFC drawings with Galvanized M12x75 Long Excalibur screwbolts at 500 CTRS Typical each wall.
label | 95f986c0-c7a2-5466-ae2a-cbf69a031947 |  | note | – 600mm wide BITAC tape installed
label | c7f53298-83f0-5795-942c-6aae7ee00f7a |  | note | Method: Measure
label | cefa7bda-1a64-51e0-aa91-99a7a4f7aa24 |  | note | Frequency: Where applicable
label | d696292e-67e2-5cc2-8b0d-aa5f93d910bb |  | note | Category: IP
label | 45879306-2b62-5096-82c3-506d328b9704 |  | note | Responsibility: SE/PE
label | 27e852c2-c95a-5773-8f62-b5a80be7b1d8 |  | note | Verifying Documents: This Checklist Signed-off
date | d4749aa2-1e9e-598e-93e5-0acf8a55b665 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6 - Filter fabric -Installation
label | 95298764-d327-5a7e-bb49-ab8bf3427380 |  | note | Reference: IFC Drawings MRP-080-C-SME-DRG-34-CPV-CSF-2003 VR682.11
label | 1b6bad61-be78-5a54-95bf-dad7600b0f91 |  | note | Acceptance Criteria: Install Filter Fabric against all vertical and horizontal joints
label | b378caaa-e060-58a0-8693-64f8f1c44ba7 |  | note | Method: Visual
label | 0c7283fb-b5b9-5a88-be7a-96ad1e995168 |  | note | Frequency: Each course of panel installation
label | c756ea8e-5ea4-58a6-8095-d7f23d96e046 |  | note | Category: IP
label | 29f142e4-9cc4-560a-be13-a72017ac11f2 |  | note | Responsibility: SE
label | 032371b1-9c07-5b53-88ec-2523b4bc3018 |  | note | Verifying Documents: This Checklist Signed-off
date | b82f27e8-0515-58bb-b65f-622be40e5390 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Drainage-Strip Drain
label | 23bb4b91-c964-57ac-b0ef-30122d75fcb8 |  | note | Reference: VR682.11
label | 6bd07f17-9cb3-537a-98ec-3a2117a0e2c2 |  | note | Acceptance Criteria: Install 300mm wide strip drain between precast wall panel vertical joints. Strip drain to be encapsulated by nonwoven geotextile in accordance with section 682.11 At every vertival joint between panels in RSS wall, ensure no gap is formed bewteen strip drian and RSS panels
label | 9e980d20-e04e-5d08-801a-d0c113b1f52d |  | note | Method: Visual
label | 3a8f8069-a4a1-51d1-9e22-162ef850c459 |  | note | Frequency: Each course of panel installation
label | a3165bcd-f7bd-59a2-8473-9dcc977bc89a |  | note | Category: IP
label | 03a2a280-f041-5474-a18f-fd63515e7947 |  | note | Responsibility: SE
label | feda960a-8da4-578a-a6d0-75e1cfc7847f |  | note | Verifying Documents: This Checklist Signed-off
date | 3060fa38-6c0b-5c2e-b572-2694c5142730 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 8 - Panel installation-Survey reference points
label | 53886d03-d73a-5828-b167-8b345b1785ef |  | note | Reference: VR 682.20
label | 8c127dd4-0f74-5c5f-9338-b01d9466e451 |  | note | Acceptance Criteria: To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS
label | d816a4de-f706-5d24-be67-0f6b2630235a |  | note | Method: Visual
label | bdf2aa53-e9ce-5e3c-83da-2ebb429921d5 |  | note | Frequency: Each course of panel installation
label | d35d7dac-3b40-5c29-99c9-fc5c04e2d372 |  | note | Category: IP
label | cffbaac6-20d2-5f1d-93c7-aa8ebc6a31b4 |  | note | Responsibility: Surveyor/SE
label | f7566f1a-7219-555b-a337-70dafe1c1226 |  | note | Verifying Documents: This Checklist Signed-off
date | 28263e3c-d788-5060-a8ca-900b5d446b0c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 9 - Traceability of precast units and records
label | ea6b0bd5-675e-5dbb-8c33-e02f7c318101 |  | note | Reference: VR 620.09
label | a91b153a-a759-5ee4-a1f8-ae77f445e67b |  | note | Acceptance Criteria: Unique ID of precast panel is recorded.
label | 4cb7f5f0-c032-5163-941f-71c92e77c12c |  | note | – ATTACH: marked-up elevation drawings or installation record with reference to panel ID
label | 3250e66d-a540-592c-a273-06f283d50974 |  | note | Method: Visual
label | f6d0eb82-ba6b-55d0-a508-a7e9e7b4472c |  | note | Frequency: Each panel
label | 35a0b050-7db2-5834-957d-21b1021c69e8 |  | note | Category: IP
label | 1e3e97dc-4304-5ed9-bfb7-21fd43c1fea1 |  | note | Responsibility: SE/PE
label | 22a11466-433b-5a59-bac2-e50260f231d4 |  | note | Verifying Documents: This Checklist Signed-off
date | d826f113-5181-51e5-9482-3400ea09ef02 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 10 - Panels installation-Conformance Survey
label | 86f30299-8e16-5b5d-935e-4421f835f930 |  | note | Reference: IFC Drawings VR 682.06, VR 682.17, VR 682.20
label | 73990e87-4333-54d0-ae26-e4e6b0bba436 |  | note | Acceptance Criteria: The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The
label | b8d95246-73ed-50b9-9d0f-c84e77146467 |  | note | ○ Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
label | f2314fc1-dc19-52fc-915f-7a7d37a026cf |  | note | – Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall
label | dab41d19-6f5a-5207-a4c9-4e50f29fe9a8 |  | note | – Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm
label | b72296e8-876c-535f-9f49-f37c138105c5 |  | note | – Variation in gap width between facing panels shall not exceed 5mm per meter length and 10mm over the full length of the gap
label | b45fb8cc-95e2-5be7-824c-4b4aa3860980 |  | note | – The wall level shall not deviate from the specified level by more than ±20mm
label | b530976d-bb05-556b-bf61-37634ec04971 |  | note | – The tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height
label | 7227af2d-81cf-5599-bbba-44efbf56dbef |  | note | – The verticality of the RSS wall facing shall lean backward at a minimum slope of 1(H) in 40 (V)
label | 143ebc3a-72d5-53cb-9f32-2f461791ec27 |  | note | Attach: Survey Report
label | fc9614ce-63c1-535e-82ee-dbee154fcdfc |  | note | Method: Survey, Measure
label | c16636c5-efce-5f85-9509-a3ac2aaf4acb |  | note | Frequency: Each course of panel installation
label | 18cbf1ba-714d-5333-a8bc-d798c1309f8b |  | note | Category: HP*
label | 75db4a07-8779-558c-9f84-a77000e72e59 |  | note | Responsibility: Surveyor/PE
label | 43c77cf1-fa06-505f-afdb-70ff2bf7faa8 |  | note | Verifying Documents: This Checklist Signed-off
date | bfd2fe17-04e8-54bf-8cd1-7bfe747adc3e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 5b1c94c4-0404-5fb3-8a7e-5850e9b448d2 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 333def9c-7604-5831-b57d-c3a7dac23ff0 |  | textbox | Name:
text | fb32f7be-7bf5-51d2-9196-12f9bbc2b61d |  | textbox | Position:
date | 583928f4-3d30-5bbf-ae8f-4395acba1a69 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-060-CIV-CPD-Unbound Flexible Pavement Construction | itp |  |  |  | Yes | ITP-060-CIV-CPD-Unbound Flexible Pavement Construction - Rev 0 | b6ddc7f6-b6bd-404a-a002-1afc2d27a009
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | ef2320af-26dc-5cdb-8440-e1e8c78c3b3c |  | note | Document Title: ITP-CIV-CPD Unbound Flexible Pavement
label | 2cbeac5b-2b48-5450-8ea9-c52c6d8b1210 |  | note | ITP Description: Unbound Flexible Pavement
label | afdd6abf-7f1e-597f-a368-ed0ab3ce8453 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 3b6e9a75-fea6-52fc-806f-54e714466ffb |  | note | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
label | 7875f11f-5110-5baf-857b-b5ef577d07a6 |  | note | Revision Number: 0
label | 2038d4b2-271f-5dc3-9790-e406677c4285 |  | note | Revision Date: 14/08/2023
label | 63cb63d5-a56c-508c-a594-2fc0447af96c |  | note | ITP created by: Ethan Caruana-Smith
label | 35a8ba9b-bfeb-5080-ad7c-924698de66e3 |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 9255c4c4-eae7-5f64-92e9-4b5440837f47 |  | note | Reference - IFC Drawings
checkpoint-status |  |  | checkpoint | 1.2
label | abc6407d-b876-57e2-bb82-867378991163 |  | note | Reference - VicRoads Section 173 (10/9/2008)
checkpoint-status |  |  | checkpoint | 1.3
label | 929e635c-bb1a-5fb4-9ee0-0f45b42d8276 |  | note | Reference - VicRoads Section 304 (13/8/13)
checkpoint-status |  |  | checkpoint | 1.4
label | 3b425cbc-612c-5694-8139-63d59b27156d |  | note | Reference - VicRoads Section 801 (19/07/18)
checkpoint-status |  |  | checkpoint | 1.5
label | dd274434-1e79-59a4-973a-e498e860c203 |  | note | Reference - VicRoads Section 812 (13/07/16)
checkpoint-group |  |  | section | 2. Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Crushed Rock Mix Design
label | cb7270e0-3687-537c-8e0b-c2089f472990 |  | note | Reference - Section 304.03, Section 304.05, Section 812.04 Table 812.121 IFC Drawings
label | 74f060ed-0c21-5058-aab6-21142e27edc3 |  | note | Acceptance Criteria - All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
text | 1e8b38d9-00d5-5fc6-b622-5623d2e8145f |  | textbox | Enter: Teambinder Material Approval number
label | 6421c17c-5f15-5ac8-9493-043e99e8de75 |  | note | Method - Document Review
label | 9423e754-7887-5b0d-8b91-d9f7677e2e19 |  | note | Frequency - Material conformance as per Table 812.121
label | 8c9bea69-1e3e-5e8a-840a-65b9ebf6d012 |  | note | Category - HP
label | 4c9a7e25-f2f2-5c2b-a001-0c81d51b9c31 |  | note | Responsibility - NA
label | 7719a719-dde4-50bc-99ae-3731de8b907c |  | note | Verifying Documents - TeamBinder Material Approval Number
text | 971649c9-92d1-53a7-a2b4-19c122ec4da1 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 3. Preliminaries-Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Subgrade Preparation
label | 64302fc0-0c83-5f0b-95ef-02bfc2562a1c |  | note | Reference - 304.04
label | a5dc12f6-8494-503a-9d6c-071b45eacdc3 |  | note | Acceptance Criteria - Prior to placing subbase material, the subgrade shall meet the requirements of Section 204.
label | 6cc7dfda-a294-530e-8a3a-d9fffd21c03f |  | note | Reference: Subgrade Preparation/Type fill Lot Number:
label | ce02167f-bbbf-5702-bd74-694ca167ae60 |  | note | Method - Document Review
label | 91b67b0f-8c05-56e1-a25c-75b88bf22d44 |  | note | Frequency - Each Lot
label | fddca177-850a-52ed-9fe4-12e7fb7e6910 |  | note | Category - HP*
label | 9fbd03f2-9838-53b5-a895-97caf6f82257 |  | note | Responsibility - PE
label | e242e0d6-b395-5eef-bbaa-e4f5d4d6fb46 |  | note | Verifying Documents - Underlying layer Lot number
text | 9b8f20d9-215e-5ed5-b438-99239b0c5d57 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Select Scale
label | 3fde8bc7-22bd-5946-a6aa-ef71e7133ce8 |  | note | Reference - Project Requirement Specifications IFC Drawings
label | d86a0587-ab72-5981-93db-b14ab9f556e0 |  | note | Acceptance Criteria - Specify site specific scale:
text | 8c782be8-d468-5003-be22-aa573e784814 |  | textbox | Enter: Site Specific Scale (A, B or C)
label | 1641f9e6-e798-5ffe-809e-1ca2a87987f8 |  | note | Method - Document Review
label | b577eba2-ad0e-51ef-b8bb-b08055150d0f |  | note | Frequency - Prior to Commencement Each lot
label | 5a32cc8f-41e1-5a94-8fbe-9bda50302ff0 |  | note | Category - HP*
label | 08f9b94e-282b-5ee6-95da-9553d8c25671 |  | note | Responsibility - PE
label | d625fedd-7b73-5b0f-bf0c-3ef8b85b6088 |  | note | Verifying Documents - Sign ITP
text | 30200f34-0a82-5dd1-be6a-20af53b1c63b |  | textbox | Date Completed:
checkpoint-group |  |  | section | 4. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-out and Lot size
label | ed8f00ef-e837-5f41-b1ab-fc26f3daa444 |  | note | Reference - IFC Drawings Section 304.06
label | 8f8c696f-79dd-5b2f-b1a2-5c7295a51b83 |  | note | Acceptance Criteria - Lot size shall be the lesser of 4000sqm or a days production.
label | b31d0dd0-a009-5fe1-99a0-8ef3115b7a87 |  | note | ○ Set out pegs are in place and clearly mark out limits of works as per IFC Drawings and VR 304.06.
label | 37ffdf15-a490-5bfd-bcb7-3d307bd041a0 |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | 2b744394-5f69-524e-a441-f64e2ab007b0 |  | note | Method - Survey, Document Review, Measure
label | d45237eb-ad3d-567c-99f8-39409e602e41 |  | note | Frequency - Each lot
label | 4c4dbb3a-e436-5edf-be56-ea23d178efa4 |  | note | Category - IP
label | ceeaae3e-1daa-506e-8e92-aef482aed839 |  | note | Responsibility - Surveyor, SE
label | 63a9f3cb-0c9d-52c9-8cb2-6d5286b14270 |  | note | Verifying Documents - Sign ITP
text | 36fc3025-54a7-57a8-9415-41c21f87e568 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Crushed Rock Delivery Dockets
label | 12718882-db02-5606-a571-0666b70984cf |  | note | Reference - 304.04
label | c6fd7c0e-2dab-5ae3-a795-02d2e6ae82dc |  | note | Acceptance Criteria - A delivery docket for each load shall be issued to the Superintendent at the point of delivery. Check Delivery docket for compliance to the referenced Material Approval (Line Item 2.1)
label | b6149cc5-d08d-5ed4-8bf7-969dfe54af95 |  | note | ATTACH: Delivery Docket(s)
label | 5adf6d2b-a0c9-5aba-ae31-64f268429cab |  | note | Method - Document Review
label | 40b60401-c4f3-5e1c-87af-9e948b3b65af |  | note | Frequency - Each Lot
label | 6847a6a1-3e62-5027-bb94-059d50afb645 |  | note | Category - IP
label | 9cd4855e-c5f1-5cd4-bc12-4ed167abcd16 |  | note | Responsibility - SE
label | 8796dfd3-112d-5e6a-9efa-f462e56c164b |  | note | Verifying Documents - Attached Docket, Sign ITP
text | cf1cf749-a11c-5cdb-a47b-a39c5dddd61d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Placement of Material
label | bcb1ba30-363f-5857-bd1d-a1ecd0c586e9 |  | note | Reference - Section 304.03, Section 304.06, Section 304.08
label | 2c66ba9a-a9d3-5c80-be73-0a397ae01705 |  | note | Acceptance Criteria - Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas.
label | 7f395a4f-604f-5a76-9403-c5d8998abd12 |  | note | ○ Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material.
label | 7c0b8a25-01f3-5dd3-b72e-022a807503d0 |  | note | ○ Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
label | 72266e1e-1033-583f-bcf4-5818a317c007 |  | note | ○ At no location shall water pond on the surface of any pavement layer.
label | 3a035549-0e3c-5170-9f6e-cb3327aa9a1e |  | note | Method - Visual and Measure
label | 1c6fb702-1fe2-5ac8-8a5e-40e5def1affa |  | note | Frequency - Each lot
label | 432f659d-933b-588e-8ee4-900cbbe02782 |  | note | Category - IP
label | c4fbee85-77e1-5034-a521-f2cd7c1340ef |  | note | Responsibility - SE/Site Supervisor
label | 636045f5-15fe-57e0-8cfa-7cdecc87e65e |  | note | Verifying Documents - Sign ITP
text | bbae402b-e9d6-530e-b742-8cefe5ed130c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Construction - Jointing
label | 8f728c6d-963b-5e34-8f97-2aca6616e75e |  | note | Reference - Section 304.07
label | acf792a6-fd49-5145-bb5b-59a2490daf52 |  | note | Acceptance Criteria - The layout of joints shall conform to the following requirements:
label | 7f65d51f-78ba-528a-a922-a374d0a8cdf2 |  | note | (a)material shall be spread in such a manner as to minimize the number of joints;
label | 6792e001-5f31-54f7-8f6a-d08697f60c72 |  | note | (b)for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
label | a655c747-815d-5a27-8f85-09528ababcc2 |  | note | (c)transverse joints shall be offset from one layer to the next by not less than 2 m;
label | 89d2f63d-2602-524c-a9a7-a83e7a1bf470 |  | note | (d)longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
label | a2208e64-d1e8-5345-94f2-ba9119ba8221 |  | note | (e)longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
label | d27a486e-bf12-51d3-83d9-9b9df3cfd012 |  | note | Method - Visual and Measure
label | 49977efe-6632-52e0-944c-7f4a03d22663 |  | note | Frequency - Each lot
label | 11a3c6cd-23ec-5827-9843-707129b0a921 |  | note | Category - IP
label | e0a10294-38d8-57d0-acfb-4ad558dddcd4 |  | note | Responsibility - SE/Site Supervisor
label | ae052435-06ae-5297-9e0b-b240a0c2e4e9 |  | note | Verifying Documents - Sign ITP
text | f9e22e9d-6b78-52bb-b8a0-712758eed998 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Compaction test (Frequency)
label | e5c1edb7-bed6-5983-ab57-d2a5f9be2e36 |  | note | Reference - 304 .11 (b)
label | 3a5c72e8-fbd9-5646-aa27-20290a21afe7 |  | note | Acceptance Criteria - The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification.
label | ba85afe3-76e8-56e9-a84d-2e6217681447 |  | note | ○ The Contractor may reduce the frequency of compaction testing to the minimum test frequency (One per 2 Lots).
label | 015d310c-0b1b-5a36-9590-adc818b57617 |  | note | ○ Scales A and B: 6 samples
label | 34f81167-ed4b-5172-8822-f430f7e2b8d3 |  | note | ○ Scale C: 3 Samples
label | 2f542fc9-ba3a-5027-a797-a3c4bcca31e1 |  | note | ○ Pass: Tested
label | 9d5e4c6a-f243-5ad9-b803-54f994846b2e |  | note | ○ NA: Not Tested
label | 9266e1fd-c224-5914-9886-f72d84d2fd8e |  | note | Method - Visual
label | f105a76f-1891-5063-8277-018b508f804d |  | note | Frequency - Each Lot Where applicxable
label | 55375623-073a-52b7-b5d3-04e7106bd588 |  | note | Category - IP
label | 3774f41d-c8ac-5881-8241-fafeb21e9622 |  | note | Responsibility - SE
label | c3391b2a-c9aa-5433-94e5-33c7bc86901e |  | note | Verifying Documents - Sign ITP
text | 40645c17-0428-56fa-8d44-7c143e802a40 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Post Compaction Materials Testing (Frequency)
label | 06d5a86f-2801-55b5-b77c-dc0b0a612f6f |  | note | Reference - 304.11 (c)
label | 8275823d-28c5-581c-91b3-48e320f8e898 |  | note | Acceptance Criteria - SCALE A:
label | df0a5516-796f-504f-bc54-5490228590f5 |  | note | ○ The first lot of each pavement layer shall be tested for post-compaction grading and PI. If the lot satisfies the requirements specified in 6.1 as applicable, the Contractor may test at the minimum frequency:
label | 49e8bfb4-738b-5948-886c-b512c3b78ade |  | note | Compaction:
label | 845d3c40-9358-584f-a50d-95a9b3ad899d |  | note | ○ Lower Subbase: none
label | 721796a4-dc91-5cbe-8398-0ed5a83679f6 |  | note | ○ Upper Subbase: 1 in 4
label | b86ebbde-90f4-5539-9c91-1434778902ff |  | note | ○ Base: 1 in 2
label | 43fadb60-bb38-5f6b-bc70-7e9252c6779b |  | note | PI:
label | 9ec6b3bb-5cde-54dd-8bb0-ed1d1e5f79b7 |  | note | ○ Upper Subbase and Lower Base: 1 (two samples) in 8
label | 3a4aa8ef-f061-5535-a230-f348eae3de32 |  | note | ○ Upper Base: 1 (two samples) in 4
label | cf2dad95-d715-508b-a689-06d01a09e871 |  | note | SCALE B:
label | df249b67-9751-5f27-94e8-95fb90e714bb |  | note | ○ the first lot of each pavement course shall be tested for post-compaction grading and PI.
label | 163ed4b1-6d6f-5ab4-a69a-4b2ca5b4cb14 |  | note | SCALE C:
label | 495e157a-7355-57a7-a09e-c620d3cd7bce |  | note | ○ Post compaction grading and PI testing is not required (CHOOSE NA)
label | 074437bf-5ccf-5c1f-b6de-f59ebcb15784 |  | note | Method - Visual
label | 577df030-3595-5854-989d-4b4ac33eaa8e |  | note | Frequency - Each Lot Where applicxable
label | 7e75f971-a2e1-5c4f-9484-ce3a556eb707 |  | note | Category - IP
label | f646a15c-161a-5145-9c30-5fa1a49865f3 |  | note | Responsibility - SE
label | 2b030299-c6b9-5ef5-8065-66eea984e9d9 |  | note | Verifying Documents - Sign ITP
text | aa03fa7f-55e1-587c-91d2-090471f1e949 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Proof Roll
label | 4c670494-f690-5b50-810e-b494570a6bb1 |  | note | Reference - Section 304.08
label | 4fd0a818-401e-5e3e-aeb7-406ef6b362eb |  | note | Acceptance Criteria - All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
label | 8c320614-1cce-5fcd-9686-b21ce9ad32f1 |  | note | Method - Visual
label | 9562dd5a-f4ec-5eba-8de4-2bde4a837d12 |  | note | Frequency - Each lot
label | a3592546-ce81-5d32-8c05-77f347e488d5 |  | note | Category - HP
label | 50451aa1-f26c-5901-bdd2-6facbe8a04a9 |  | note | Responsibility - Nominated Authority
label | cd5ec3b1-837d-545b-a085-b6d24852b0a3 |  | note | Verifying Documents - Sign ITP
text | 234bdd0f-6ce6-5392-ad0d-4789896643f6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.7 - Protection of compacted layer
label | 9de1387d-da9e-5443-8866-d2cf11176d33 |  | note | Reference - Section 304.09
label | adcd9f68-6b46-536c-85bf-7ad429565437 |  | note | Acceptance Criteria - The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
label | 1465141b-6e46-5801-96b2-6679fa90e68a |  | note | Method - Visual
label | 44f84631-9610-5022-96fa-789f1ee4da19 |  | note | Frequency - Each lot
label | ec0860e5-2b42-5f33-bccb-8c17271d442e |  | note | Category - IP
label | 57a07243-aa6d-5bf1-a019-6cc45bbb11a3 |  | note | Responsibility - SE/Site Supervisor
label | 27dfa74d-3c27-5935-bb06-661942abc55c |  | note | Verifying Documents - Sign ITP
text | 494d0f6e-c5ed-548f-bce6-34476297cec1 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - Compaction Testing (results)
label | 2242548d-40ec-5a75-a1c2-5ce801574c92 |  | note | Reference - Section 173, Section 304.08 Table 304.081
label | b20d74d0-e862-525d-8587-87cfeb821dfb |  | note | Acceptance Criteria - During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed.
label | 9d04de45-b2ec-5050-8536-04ede1937e2b |  | note | ○ Density Ratio to be based on tests performed with Modified Comp active Effort.
label | 5f56cb8b-14d7-587f-8cf9-75dbe6ad5d3b |  | note | Scale A:
label | 20835722-b854-5339-8cb4-ef3e51a79c00 |  | note | ○ Subbase Layer Characteristic Density Ratio (CDR) ≥ 98%
label | b27f285d-161f-581a-9ac2-ff1da6e298a8 |  | note | ○ Base Layer CDR ≥ 100%
label | eb177e72-a221-53db-8be1-5601cc512574 |  | note | Scale B:
label | 2c10a9d8-c7a0-53bc-b762-f36863dff1d5 |  | note | ○ Subbase Layer CDR ≥ 97%
label | 4bfd70ed-b4ec-5fa3-a291-c3335ce0fbbc |  | note | ○ Base Layer CDR ≥ 98%
label | 63042eec-cb6a-5b54-99e2-056b2996e1b2 |  | note | ○ 6 tests per lot for lots >500sqm. If the lot is < 500sqm, then 3 tests per lot.
label | 9e7a3c9b-e687-5b20-bcaf-56f0d6665a21 |  | note | Scale C:
label | cc214577-2622-5d6e-ba15-94702ad8d3fa |  | note | ○ Mean Value of Density Ratio (3 tests):
label | 4cb065f7-a97e-5366-9ef8-552d0580d99a |  | note | ○ Subbase Layers >98%
label | b0e6fa51-0c88-51c1-9c21-82f03d00efc5 |  | note | ○ Base Layers >100%
label | 56c80dc4-1d4b-586c-988b-9afff67683a6 |  | note | ATTACH: Compaction Test Results
label | 63af89d5-6d7b-5107-b85d-95a4a45b09da |  | note | Method - Document Review
label | 561d7d45-92d8-5d24-8ce0-8782ea1dd555 |  | note | Frequency - Each Lot Where applicable
label | a0f3545d-4bde-53ab-95b9-1492b090b9ec |  | note | Category - IP
label | 276995be-006e-54f0-86eb-990c537d6548 |  | note | Responsibility - PE
label | f6477e74-934c-5ed4-b1b0-159de42d7881 |  | note | Verifying Documents - Compaction Test Rersults
text | 4239c8d9-0e22-5550-b373-b321fa78c676 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Post Compaction Materials Testing (Results)
label | 731d3ff7-2559-54c0-aad4-be2b0b89a328 |  | note | Reference - Section 304.10, Section 304.11 RC 500.02
label | 27189b99-b814-5755-aa37-e802bd3f6d3f |  | note | Acceptance Criteria - Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type.
label | edd68a6c-32fe-5d26-9ea7-50f8aa9e12b6 |  | note | 20mm Class 3:
label | 124262fd-5324-5bd1-879d-1a16f2fc246b |  | note | Grading
label | 0572fd0a-e62c-5d55-a135-c4701c683fa1 |  | note | ○ 26.5mm 100%
label | f6bea2c8-ec7e-54ea-b429-e7ffefe672f6 |  | note | ○ 19.0mm 95-100%
label | 399f3b38-5f14-51c0-813f-11c7d0e46e57 |  | note | ○ 13.2mm 75-95%
label | 491496be-136e-58d2-8302-aa0e4c21c0df |  | note | ○ 9.5mm 60-90%
label | 5780aad9-b3d1-58a7-a4fc-2030f778f9b2 |  | note | ○ 4.75mm 42-76%
label | 0b37b07a-c016-544b-9b4c-18f078808bd2 |  | note | ○ 2.36mm 28-61%
label | b78f1cf6-3527-5bba-870c-9ffed8683269 |  | note | ○ 0.425mm 14-29%
label | 7cf7dce7-d45d-5913-92a2-9c9e388b6655 |  | note | ○ 0.075mm 6-14%
label | e32a840b-9f12-516c-a624-a87791820b02 |  | note | ○ PI between 0 to 10
label | dad2a5fe-0af1-5d1b-9272-2e91f1f2d937 |  | note | 20mm Class 4:
label | 9753c4d7-b0d9-53e7-89f6-c5e8286e4fe9 |  | note | Grading
label | b6081ed9-499d-53b0-ae9c-3999cf4df452 |  | note | ○ 26.5mm 100%
label | 1c23d409-7a0a-5977-88bf-64ed8fc6b327 |  | note | ○ 4.75mm 42-76%
label | c2c8b3f6-63d8-5717-8468-10134b9d8d57 |  | note | ○ 0.425mm 10-28%
label | aabc78da-ed56-5718-855a-c7ef432490a0 |  | note | ○ 0.075mm 2-14%
label | 20d3958b-5a3c-5b71-a5ce-fbc1190bb98d |  | note | ○ PI between 0 to 20
label | 6dd20bde-d680-59b8-807d-448f861263c8 |  | note | ○ PI x % passing 0.425 mm sieve (max) 450
label | d0f04ea2-b903-59ae-a19c-1b2274dc3f74 |  | note | Scale C: Post compaction material testing is not required (Choose NA)
label | 56c0b8df-a95c-59b2-8320-7156be335e23 |  | note | Method - Document Review
label | 9b0694cd-569d-598c-b1ab-8048e9f9b41c |  | note | Frequency - Each Lot Where applicable
label | bdefee9c-c7a6-51d9-9ad0-2350efe46d90 |  | note | Category - IP
label | b2a3c4a2-70ba-53ad-a7f3-94ed4d9e57be |  | note | Responsibility - PE
label | f307566d-a017-56dd-819a-f8e6d484163a |  | note | Verifying Documents - Compaction Test Rersults
text | 91ae96d0-ab72-5b3a-986b-252f7dcbf82e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Survey As-Built - Surface Level
label | 2f177bd5-09e5-5cc2-9f73-a9b4944a6a28 |  | note | Reference - IFC Drawings Section 304.06 Table 304.061, Table 304.062
label | daac33a4-2505-5dc2-bac2-215948de096a |  | note | Acceptance Criteria - No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction.
label | f713b0ed-011b-5dcc-91db-3aaef1714c1a |  | note | ○ Subbase course shall be not < the specified thickness by more than 15 mm.
label | 0c9f80a3-e46e-5888-a959-3ca7ca48eb42 |  | note | ○ Base Course shall be not < the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be < specified thickness.
label | 9e30fc32-4606-5db2-9198-52170d3b71ca |  | note | ○ The combined thickness of subbase and base courses shall be not < the specified thickness by more than 15 mm.
label | 98a82767-7f60-52ca-a42c-5fa125ce0be5 |  | note | Scale A: A minimum of 80 measurements per lot
label | 73192754-d30e-54c2-bb01-2c9c6f256c11 |  | note | ○ Subbase: mean range +4mm to -8mm, maximum Standard Deviation of 8mm
label | 1ad6d947-d6d2-5e85-9f9d-693d8ac8eb72 |  | note | ○ Base: mean range ±5mm, maximum Standard Deviation of 8mm
label | 01a0161b-df65-515d-8d32-ac84bc31439d |  | note | Scale B: A minimum of 40 measurements per lot
label | fae784a6-f3a1-5266-83d6-391aebc9ab07 |  | note | ○ Subbase: mean range +6mm to -12mm, maximum Standard Deviation of 13mm
label | 62fcef04-af3a-5f58-a603-7911a85c6ac0 |  | note | ○ Base: mean range ±8mm, maximum Standard Deviation of 10mm
label | fc7113e9-698c-5381-a95b-98ca9320402e |  | note | Scale C:
label | 80fd02b2-a566-5015-8441-ea674e409f53 |  | note | ○ Lower Subbase (mm) +15/ -25
label | 677164f0-04c0-55fd-9e53-12cd8b1805a1 |  | note | ○ Upper Subbase (mm) +10/ -25
label | fd437000-87e0-5439-ad1b-089e245f1458 |  | note | ○ Base (mm) +/-15
label | 628a2dd0-6740-5b9e-8ec5-a2aa0bc33e87 |  | note | Method - Document Review
label | c39b8114-4091-5992-ac73-3aba3cbf351e |  | note | Frequency - Each lot
label | 16cdada0-abd7-57d3-a1ef-1b40206f7670 |  | note | Category - IP
label | afaef9cd-b082-5e2b-bf21-5b9cc91e940f |  | note | Responsibility - PE/Surveyor
label | 4888d8cd-d316-5b22-8d69-c5e60bc43a02 |  | note | Verifying Documents - Survey Conformance Report
text | 19522a1d-657a-5f6f-89b6-8b9945570eb9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 97701c0f-330d-56ba-a590-f042cb2a259c |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 71328de3-80bb-5389-8ad2-f8e82e3425ac |  | textbox | Name:
text | e565f738-e0ef-5bf5-8937-eae0ef2cad8c |  | textbox | Position:
text | 2fc62b8c-0047-57b0-a093-084902d943a3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Concrete Coatings (Protective &/or Decorative) Rev 2 | itp |  |  |  | Yes | ITP-STR-Concrete Coatings (Protective &/or Decorative) Rev 2 | c8409d6a-b18f-4202-9dde-fd86fdcd29b5
checkpoint-group |  |  | section | 1 - Referenced Documentation
checkpoint-status |  |  | checkpoint | Reference Documentation
label | aef1223d-f79a-5030-a0ce-8978a26e2e15 |  | note | Document Title: ITP-STR-Concrete Coatings (Protective &/or Decorative)
label | 5e5b7f30-2ff4-5737-95bb-f2bf73e8bb21 |  | note | ITP Description:Concrete Coatings (Protective &/or Decorative)
label | fddb0f0e-2c9f-5923-992c-f6908314ac4f |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | f1fb85f5-dfd5-5cc8-8bf9-16ce7d674548 |  | note | Revision Number: 2
label | 2eb2c232-903a-5d57-a46a-319b6f656df9 |  | note | Revision Date: 11/12/23
label | eb25a5fe-7f70-5d11-a37c-b68eaa0cff21 |  | note | ITP created by: Mike Freeman
label | 4b124020-3f1b-5d23-88e0-e5b5b6c0eeb0 |  | note | ITP approved for use by: Mike Freeman
label | 3c967fb4-cb91-5cd8-b255-f7c819954281 |  | note | 1.1 VicRoads Section 685 November 2018
label | 2463769d-94ed-598f-aea6-39fe300c463a |  | note | 1.2 VicRoads Section 686 November 2018
checkpoint-group |  |  | section | 2 - Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 - Anti-graffiti System Selection
label | 3b37663a-6459-5d89-ba9d-49871459dabb |  | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (e)
label | 9b960f94-f7cd-5851-942c-dc23a8db4026 |  | note | – – – – – – – – – – – – – – – – –
label | 363b9262-d80f-5552-8bd2-f9af4d910942 |  | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
label | 0c033630-75b2-532e-a40a-0dfd20b44c3b |  | note | i. be either a film-forming or a penetrant system ii. be non-sacrificial, clear OR coloured (as noted on the IFC drawings or specification) iii. be an acrylic copolymer, acrylic epoxy, polyurethane or polyurea type with all coats be of the same brand and compatible iv. be non-yellowing, colour-fast and not subject to fading v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure vi. application thicknesses (film-forming): WFT total = 175µm min. OR WTF per coat = 88µm min. DFT total = 100µm min. vii. adhesion to substrate (film-forming): 0.75MPa min. viii. application rate (penetrants) as per the minimum thickness on the manufacturer's TDS
text | f2f4e320-3caf-59f9-9971-22299d8f6f52 |  | textbox | Enter: Teambinder Material Approval number
label | 66409958-3ffb-56e4-af62-77aaa3dded1f |  | note | – – – – – – – – – – – – – – – – –
label | 8e3a3f8b-a7d0-59a9-8242-4aa7d111d8c5 |  | note | METHOD - Document Review
label | 475cc402-94e9-539a-8015-67cb5d6487e2 |  | note | – – – – – – – – – – – – – – – – –
label | e26b2323-0a64-57ba-a666-8d5a539276d0 |  | note | FREQUENCY - Once, for each coating system, 14 days prior to application
label | f988b2d2-452f-5bbe-9e07-61fd931ee17d |  | note | – – – – – – – – – – – – – – – – –
label | ea8e4110-82d1-5be6-85dd-ab7c4e7f73bd |  | note | CATEGORY - HP
label | e29dbf02-4b12-5959-97ca-355805842f13 |  | note | – – – – – – – – – – – – – – – – –
label | 04663cf2-da7c-5afa-aa15-24a46236805e |  | note | RESPONSIBILITY - Nominated Authority
label | ca69f714-eec9-5b3a-bf20-7b4eedc76898 |  | note | – – – – – – – – – – – – – – – – –
label | 72f4a2eb-623f-51c2-aaad-30a8461828ab |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | 3c5049b8-7654-5728-8d34-556819303106 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Decorative & Anti-carbonation System Selection
label | c849a9ef-b48f-56a1-82d1-c70cd08ad81e |  | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 686.04 686.05 (a) & (b) Table 686.051
label | 5676b11e-3486-5259-96bb-8d20d05e80ec |  | note | – – – – – – – – – – – – – – – – –
label | fe282828-9fab-5285-b268-7e2c0faa62ed |  | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
label | 08560dc4-b8bf-53c7-9263-3000dae5400e |  | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system ii. be water or acrylic based, solvent-free with all coats compatible with each other iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system iv. be non-yellowing, colour-fast and not subject to fading v. be guaranteed to last for 10 years of outdoor exposure vi. application thicknesses: WFT per coat = enough to achieve the total DFT DFT total = 150µm min. vii. adhesion to substrate: 0.75MPa min. viii. able to bridge cracks up to 0.3mm wide ix. able to be re-coated within 24 hours x. have a minimum pot life of 1 hour xi. compatibility to an alkaline surface xii. equivalent air thickness >150m xiii. equivalent concrete thickness >450mm xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s xv. Water vapour equivalent air layer <4m
text | ee4dac17-bae5-52f9-ad6b-391844e39489 |  | textbox | Enter: Teambinder Material Approval number
label | 4b7fb931-1f29-5ab8-aca6-6bf5a2c77410 |  | note | – – – – – – – – – – – – – – – – –
label | 7ec21923-73a3-5b9a-9496-fc97c4c119a1 |  | note | METHOD - Document Review
label | 18eaed65-4fca-571b-8250-405887fb4b90 |  | note | – – – – – – – – – – – – – – – – –
label | f77a47dd-b2b0-5271-a091-c919240b35ff |  | note | FREQUENCY - Once, for each coating system, 21 days prior to application
label | 512663b3-961a-5092-85c4-325404305e27 |  | note | – – – – – – – – – – – – – – – – –
label | 7a4e5c96-85af-57cf-8785-887260f55356 |  | note | CATEGORY - HP
label | b3512bac-ed34-56cf-b5ca-ea4bd5e39dec |  | note | – – – – – – – – – – – – – – – – –
label | 143b9b8f-ffb2-55e5-a5f9-0edf053b0f16 |  | note | RESPONSIBILITY - Nominated Authority
label | b6b8806e-c358-5a05-ba5b-b5915283a686 |  | note | – – – – – – – – – – – – – – – – –
label | 167c2aa1-ad64-54a1-8013-92cfae3f6334 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | d4f73ff4-da3c-5d10-989f-dedbec3dd1a9 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Decorative, Anti-carbonation & Anti-graffiti System Selection
label | 29703d87-02ae-5978-ace7-38076058740c |  | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (b) Table 686.051
label | 00dee783-dce2-574a-9edb-ad1f3480d795 |  | note | – – – – – – – – – – – – – – – – –
label | d303b03b-3f05-5370-a452-450b0ae6a6de |  | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
label | 5c80af5c-f7e3-5634-b701-e892ae62da95 |  | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system ii. be water or acrylic based, solvent-free with all coats compatible with each other iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system iv. be non-yellowing, colour-fast and not subject to fading v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure vi. application thicknesses: WFT per coat = enough to achieve the total DFT DFT total = 150µm min. vii. adhesion to substrate: 0.75MPa min. viii. able to bridge cracks up to 0.3mm wide ix. able to be re-coated within 24 hours x. have a minimum pot life of 1 hour xi. compatibility to an alkaline surface xii. equivalent air thickness >150m xiii. equivalent concrete thickness >450mm xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s xv. Water vapour equivalent air layer <4m
text | 74bbce89-d0f0-5bf5-bca4-7466072fa64f |  | textbox | Enter: Teambinder Material Approval number
label | 88e002d2-5604-5f22-a9a8-9528f52a9db9 |  | note | – – – – – – – – – – – – – – – – –
label | c318e1b5-6532-54ad-8010-a4426ca0b9d8 |  | note | METHOD - Document Review
label | 57652b29-ef8e-5b4e-af7a-536cc83577d6 |  | note | – – – – – – – – – – – – – – – – –
label | d34a0e6a-3de7-53ad-b9c3-4eca7c58dd27 |  | note | FREQUENCY - Once, for each coating system, 21 days prior to application
label | d61855ee-594d-59d0-a077-10b9ccefc828 |  | note | – – – – – – – – – – – – – – – – –
label | 23cf08f7-e5fb-513e-a540-5c564bed3001 |  | note | CATEGORY - HP
label | ee812295-112e-5abc-8225-b4238ca69e62 |  | note | – – – – – – – – – – – – – – – – –
label | 6f85a848-4159-5296-a840-053b0b668d94 |  | note | RESPONSIBILITY - Nominated Authority
label | 80ec1560-5c39-5899-a60a-3ed1ba000753 |  | note | – – – – – – – – – – – – – – – – –
label | ed3f5304-bcaf-57fa-9ad1-f6dcb7e0ac6a |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | 4731a431-da11-5af2-a934-0d846cdfcf89 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Atmospheric & Splash Zone (Dual Protective) System Selection
label | 1e51c382-e31e-52d7-94ac-a095edf5bfbb |  | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (b) Table 686.051 686.05 (c) (i) & (iii)
label | b430a396-243e-5a12-b0a1-96d2d774bb5d |  | note | – – – – – – – – – – – – – – – – –
label | f02cc46f-1d8e-5b1c-b563-64a17facbe04 |  | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
label | 2428d81d-17e1-5fbd-b653-6906e35ecc12 |  | note | i. be a dual protective coating system, consisting of a pore-lining penetrant and at least 2 coats for the decorative/anti-carbonation film-forming top coat ii. all coats to be compatible with each other Penetrants: iii. active ingredients: Silane = at least 95% Solid silane & silane cream = at least 80% Silane-siloxane & siloxane = not specified iv. application rates: Silane = 2 applications of 0.3L/m² min. Solid silane & silane cream = 1 application of 0.4L/m² min. Silane-siloxane & siloxane = as per the rates on the manufacturer's TDS Film-forming coat: v. to be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) vi. to be water or acrylic based, solvent-free vii. to be non-yellowing, colour-fast and not subject to fading viii. to be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure ix. application thicknesses: WFT per coat = enough to achieve the total DFT DFT total = 200µm min. x. adhesion to substrate: 0.75MPa min. xi. able to bridge cracks up to 0.3mm wide xii. able to be re-coated within 24 hours xiii. have a minimum pot life of 1 hour xiv. compatibility to an alkaline surface xv. equivalent air thickness >150m xvi. equivalent concrete thickness >450mm xvii. CO2 diffusion coefficient <2 x 10-7 cm2/s xviii. Water vapour equivalent air layer <4m xix. Chloride diffusion coefficient <5 x 10-9 cm²/sec xx.Water absorption value >0.01ml m-2 sec-1 at 10 minutes
text | b819f756-9628-5857-84e0-8cd04a4c32ef |  | textbox | Enter: Teambinder Material Approval number:
label | 681d98fd-ef2a-5c81-95b6-8ae0388b8a62 |  | note | – – – – – – – – – – – – – – – – –
label | 3c4005f5-41ab-5f45-b26f-21833ce9f1dd |  | note | METHOD - Document Review
label | 2c5cd687-1cc4-5065-8735-934febfdcaa3 |  | note | – – – – – – – – – – – – – – – – –
label | ab79641b-267e-548b-b107-ae552a4c8862 |  | note | FREQUENCY - Once, for each coating system, 21 days prior to application
label | 026b7cc2-0407-50cc-a624-e7ff482b3ae6 |  | note | – – – – – – – – – – – – – – – – –
label | 7ab335ae-2b5d-5020-948d-ca6d976b2350 |  | note | CATEGORY - HP
label | 7194619b-5ba3-591b-81b4-74a6ff5bebe2 |  | note | – – – – – – – – – – – – – – – – –
label | 87ff35f7-fb7a-53ea-a2fa-d18aee498496 |  | note | RESPONSIBILITY - Nominated Authority
label | b77901c4-cb9e-594d-88b2-63a6c79cb0ef |  | note | – – – – – – – – – – – – – – – – –
label | aa9c5a55-63bf-5925-9b46-a07d2c03d98c |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | c0c0887f-82a7-5481-93bf-36326e3d4057 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Quality Documentation
label | f0fd61d5-0f0a-5625-bbda-201de60fe381 |  | note | REFERENCE - 685.05 686.04
label | ed78d374-6956-57f4-9097-5ec8fb0ebc76 |  | note | – – – – – – – – – – – – – – – – –
label | e638b65f-1c34-5d2a-90fd-f3b6a4b1e590 |  | note | ACCEPTANCE CRITERIA - The quality documentation shall demonstrate compliance with the specifications and is to be submitted for review to the Nominated Authority.
text | bd07b42c-dabe-5c66-9203-a3ba243691b7 |  | textbox | Enter: Teambinder Hold Point number
label | 83198e58-7ac5-5e24-b5fd-1d0490121190 |  | note | – – – – – – – – – – – – – – – – –
label | bcb9dfa5-55f9-5f7f-8f23-fd237e4454a1 |  | note | METHOD - Document Review
label | 77ff7db6-56bf-5e77-a7ea-c5bc290e9375 |  | note | – – – – – – – – – – – – – – – – –
label | 76920009-549b-5b1c-a7b6-9012165861d7 |  | note | FREQUENCY - Once, for each coating system, 21 days prior to application
label | d89eb20a-9157-5962-b3bb-4f1c53eb9e31 |  | note | – – – – – – – – – – – – – – – – –
label | 439f340a-80c0-590a-bd53-c58ab2d5e9c9 |  | note | CATEGORY - HP
label | 47390118-1666-5c2d-82f9-5f9fd0245b70 |  | note | – – – – – – – – – – – – – – – – –
label | 8b510f41-43e4-53de-a969-8610f1e4a239 |  | note | RESPONSIBILITY - Nominated Authority
label | c01d2bec-2d80-59db-8537-f3aab176c1a3 |  | note | – – – – – – – – – – – – – – – – –
label | a9c26ec1-e2a1-5e01-8f01-de4afebbe56a |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | cdf31fe3-0e26-5406-9ce4-bd4b58a39426 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Coating Personnel & Equipment
label | f74a4796-e19a-5df6-a706-4fb3c0ec0000 |  | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.16 686.19
label | 4e541b55-1b50-58a8-931f-42f5be6af958 |  | note | – – – – – – – – – – – – – – – – –
label | 533941b6-875d-5ff6-bf9e-d1112ce09536 |  | note | ACCEPTANCE CRITERIA - The coatings supervisor and surface preparation personnel shall have a minimum of 5 years experience and demonstrated competency for the preparation and application techniques. Application personnel require 2 years minimum experience. The supervisor shall remain present at all times. Where spaying is the intended application method, the spray equipment shall be fit for purpose, have an airline filter and the nozzle size should match the requirements of the Product's TDS.
label | 2c049f49-24d9-5332-9a6c-53cc7a37cc50 |  | note | – – – – – – – – – – – – – – – – –
label | 6e3bc3f5-c12a-52d7-83ce-71915f1aea82 |  | note | METHOD - Document Review
label | 5f0a1603-b810-56c0-a21b-2828971068dc |  | note | – – – – – – – – – – – – – – – – –
label | 7c0d68f2-6459-51a4-83be-e92f2dbf6ecd |  | note | FREQUENCY - Once, prior to application.
label | 5397f4d0-973b-52a3-a5d3-01237a0b48c3 |  | note | – – – – – – – – – – – – – – – – –
label | 5a5d536e-afda-5ce3-80c4-684a79ac945e |  | note | CATEGORY - IP
label | 602d15e4-5b20-56c4-95c8-b573c697e23c |  | note | – – – – – – – – – – – – – – – – –
label | 4412e3b4-92e3-5dc1-afe7-fd13b13573c9 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 7006d8b6-49da-55de-8fec-b8143a781f32 |  | note | – – – – – – – – – – – – – – – – –
label | 58e2e183-fd0b-5e40-b2f4-895c82b8da01 |  | note | VERIFYING DOCUMENTS - This ITP
text | 7b4aa9d3-1bbc-5c68-9a9f-97cf6a64aaca |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Protection of Adjacent Works & Property
label | e1bbc22e-a2fc-5e99-a95a-47aa0f93a134 |  | note | REFERENCE - 685.17 686.10
label | 6128f646-baa5-5901-8016-ca487501b9c9 |  | note | – – – – – – – – – – – – – – – – –
label | 356b00de-4bbc-5623-b2dd-fa49d2028a87 |  | note | ACCEPTANCE CRITERIA - Protection shall be implemented for existing coated surfaces, services, bearings, joints, signs and nameplates during the surface preparation, abrasive blasting and coating application processes. No spraying shall be performed within 10m of buildings, footpaths, roadways, pedestrians or vehicles without protective measures in place. Where these instances are expected, the protective methods shall be submitted for review to the Nominated Authority.
label | 46910a1c-1f5f-5530-b2e4-19f32d34519b |  | note | – – – – – – – – – – – – – – – – –
label | fb5ae482-4ee1-50e0-ab57-73f78c7b6886 |  | note | METHOD - Visual Document Review
label | 9647b8c3-2a00-57f7-b0fe-e020c3d955d7 |  | note | – – – – – – – – – – – – – – – – –
label | 59a11c68-3317-5d66-bc5c-e634522f65eb |  | note | FREQUENCY - Where applicable, 2 days prior to application.
label | 8f8266b3-f29d-5978-a709-253964124410 |  | note | – – – – – – – – – – – – – – – – –
label | 0efdc5e1-9166-5627-86c9-a74b55f3c384 |  | note | CATEGORY - HP
label | 2a6b9a94-85a4-515b-b724-2ee805e637e0 |  | note | – – – – – – – – – – – – – – – – –
label | 13aab145-1221-55d8-af44-a4f64468ed42 |  | note | RESPONSIBILITY - Nominated Authority
label | 39996094-e0a0-5b06-9993-b3cfa2b90197 |  | note | – – – – – – – – – – – – – – – – –
label | 0d27194f-7449-597d-acb5-4ef95c0d909a |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | 51d3d5f6-bbcd-54c6-906d-86d895938cd5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Minimum Concrete Curing Period
label | a7e34ee6-2461-5ed2-b4bc-2b2f7932069a |  | note | REFERENCE - 685.08 686.16
label | f938aabc-c330-56a8-ac0f-42ea03200fa2 |  | note | – – – – – – – – – – – – – – – – –
label | 9cad5550-d2f4-5b51-be31-99020cd7c39b |  | note | ACCEPTANCE CRITERIA - Concrete shall not be coated until the minimum concrete curing times have elapsed: Standard cured concrete = 28 days Accelerated cured concrete = 14 days Repaired concrete = 14 days (if repaired with a patching product) or 28 days (if repaired with concrete)
label | d0f82731-bbeb-5486-b977-b54289708d4a |  | note | Note: All durations may be reduced by 50% if the moisture content is less than 10% when measured with a moisture meter.
label | 31662402-a3fb-52eb-8eeb-e2122e36e08c |  | note | – – – – – – – – – – – – – – – – –
label | be15b02f-993a-53ed-9cb3-8aebcbf83e72 |  | note | METHOD - Visual Document Review
label | c0243d7a-17f2-5c83-b037-8014f34bac6d |  | note | – – – – – – – – – – – – – – – – –
label | a258f844-ef3e-5b0b-bdbc-525cbe70c388 |  | note | FREQUENCY - Once, prior to application.
label | 5c48a8b4-2438-520c-a4f4-910c3c0d9a69 |  | note | – – – – – – – – – – – – – – – – –
label | c66d4c94-e2d2-5ba7-9cf8-3b9d39d0f257 |  | note | CATEGORY - IP
label | 0de2e03e-56eb-5c69-a932-5925b6ee495e |  | note | – – – – – – – – – – – – – – – – –
label | e715b4ff-7c24-582a-af6a-98a290ab98fa |  | note | RESPONSIBILITY - SE/PE/SPE
label | 6363067c-ad4d-5e0e-92e8-674a2b783553 |  | note | – – – – – – – – – – – – – – – – –
label | ebade83f-0bf5-5f18-b28e-dd4fcda606b7 |  | note | VERIFYING DOCUMENTS - This ITP
text | 353df5d8-9684-56b8-9c3e-9878e1d134ae |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 - Trial Application (or Past Performance) Inspection
label | d3c7ff00-c1e3-56be-bceb-23bdc20da751 |  | note | REFERENCE - 685.11 686.13
label | 4b49b69d-41e1-50d7-98a7-f77372f0fdef |  | note | – – – – – – – – – – – – – – – – –
label | 3d39eb83-55d4-5c87-9047-abbb5dbbac3c |  | note | ACCEPTANCE CRITERIA - A full coating system, inclusive of any primers, under-coats and sealers, shall be conducted on either a 10m² area of the element to be coated or on a test panel made from the same substrate. Alternatively, close-up photographs or inspection of previous projects, applied by the same coating contractor, using the same system onto the same substrate should suffice this requirement.
label | 83169bdf-21ed-5e20-8342-390ef1ac3caa |  | note | Attach: Inspection Photographs OR
text | 3e9d2ca9-e5f8-52bf-bd7a-b15b5f2bc496 |  | textbox | Enter: Teambinder Hold Point number
label | 299b8972-3487-59cd-812c-5142901020b5 |  | note | – – – – – – – – – – – – – – – – –
label | 0a3ea4f4-72bd-517a-a49c-c5f3674048ea |  | note | METHOD - Document Review
label | 350c91c7-0618-58c0-a829-dfa24d9f17c3 |  | note | – – – – – – – – – – – – – – – – –
label | 7356f9fd-65d9-5d91-a139-038282af2c81 |  | note | FREQUENCY - Once, for each coating system, 7 days prior to full coating application
label | c4a9a30b-e875-5ba3-87c1-70618e15946c |  | note | – – – – – – – – – – – – – – – – –
label | d7923f2f-34d4-536b-8383-5bafaa7bccb1 |  | note | CATEGORY - HP
label | c024f128-508b-53c7-9fea-6c7a55f9874f |  | note | – – – – – – – – – – – – – – – – –
label | f98d9e95-5533-5905-93b7-588deba5ce3e |  | note | RESPONSIBILITY - Nominated Authority
label | 1f94ba7c-3217-5d79-9f64-966b661f2e5f |  | note | – – – – – – – – – – – – – – – – –
label | 1c4b87e2-af07-5d14-b1dc-b82a585ad9b2 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | bf02f5b9-7004-526a-978a-34b85ede9b9a |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Pre-application Activities
checkpoint-status |  |  | checkpoint | 3.1 - Material Records
label | 35101966-2bf6-5930-a65e-5deab8b4b1fc |  | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.10 686.12
label | 96fa0e50-7aea-5871-b29f-04e44e86ea7b |  | note | – – – – – – – – – – – – – – – – –
label | d505a3d6-a154-5925-83a6-62f36cd16350 |  | note | ACCEPTANCE CRITERIA - Materials shall be brought to site in unopened, sealed containers, clearly marked with: the manufacturer's name & address product reference batch number quantity manufactured in the batch date of manufacture
label | ac19da55-ddc6-5dd8-b52a-1e7c1d578315 |  | note | Product beyond the manufacturer's shelf life shall not be used. Each product shall be traced to final location.
label | 8625472c-8aaa-5ffc-af19-e164569bd173 |  | note | – – – – – – – – – – – – – – – – –
label | ef970107-14da-5984-9826-055d9565fa2b |  | note | METHOD - Visual
label | 2dc70e52-04a6-5244-bac9-014a515d6b69 |  | note | – – – – – – – – – – – – – – – – –
label | e2ef4bbb-26c0-5f85-aaed-92da50386b58 |  | note | FREQUENCY - Prior to application
label | 8e145edf-31a8-5fff-ad0d-dd754c2ce15a |  | note | – – – – – – – – – – – – – – – – –
label | 3fb0d648-fd95-5f52-a066-d46d20e6a976 |  | note | CATEGORY - IP
label | a9f0be02-0356-5578-83e5-f97fc2d758cc |  | note | – – – – – – – – – – – – – – – – –
label | b052a95d-af3b-527b-8bbc-992303e616dc |  | note | RESPONSIBILITY - SE/PE/SPE
label | 6c935915-428b-5c93-80a4-cf1e364b490e |  | note | – – – – – – – – – – – – – – – – –
label | df511538-bed5-56cc-9872-7a5498d5e649 |  | note | VERIFYING DOCUMENTS - This ITP
text | 5ba18346-ca87-5f09-8cc5-541260b9f70f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Weather Conditions
label | 7cc4778d-e8e2-523e-b153-d023a44845d0 |  | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.09 685.12 (a) 686.11 686.14 (a) (iii)
label | efd38d17-decd-5323-b370-07903aff5d00 |  | note | – – – – – – – – – – – – – – – – –
label | 3da042e1-006a-5c08-a6d2-038e6f684c41 |  | note | ACCEPTANCE CRITERIA - Coating systems shall not be applied under any of the following conditions:
label | 4f5b5d73-89f0-576d-a9ab-fcb548d6f477 |  | note | i. windy conditions where spray/splatter may be generated ii. when wind-borne debris is likely to contaminate the uncured surface iii. when the ambient temperature exceeds 35°C or is below 10°C unless the Coating System TDS states otherwise iv. when the surface temperature of the substrate is less than 3°C above the dew point or exceeding 40°C v. when the relative humidity exceeds 85% or is expected to exceed 85% within 12 hours of coating vi. when rain splatter, water run-off or water deposits onto the surface and affects adhesion to the substrate vii. when the substrate surface is wet or damp (unless it is required for the coating system)
label | 56eca42e-dc55-5551-b603-08a06cf8f827 |  | note | Weather conditions are to be recorded.
label | 821747d3-dad1-53b4-891c-a7e3bdc0d593 |  | note | – – – – – – – – – – – – – – – – –
label | 915dcfb7-bab9-5b24-b442-4d5840a8e18e |  | note | METHOD - Visual Measure
label | f7c0012d-08ce-5a82-be74-9609263309ba |  | note | – – – – – – – – – – – – – – – – –
label | ed66108d-89aa-51e7-a6ed-a85377a49bff |  | note | FREQUENCY - Prior to application and every 4 hours per shift
label | 54aa65f0-c790-57b4-a6fe-7cad3abe8a5a |  | note | – – – – – – – – – – – – – – – – –
label | ffabc80a-f34c-5543-a038-b1d3f8e3d5b3 |  | note | CATEGORY - IP
label | 4264e16e-932a-5095-9440-993fa47c8e95 |  | note | – – – – – – – – – – – – – – – – –
label | fad6e3e1-6be6-55c0-86dc-3904f6015c6e |  | note | RESPONSIBILITY - SE/PE/SPE
label | f272edcf-fd2f-57d8-9598-01ab60158a40 |  | note | – – – – – – – – – – – – – – – – –
label | 978e1fe7-7690-5747-8707-6d1fb98c3090 |  | note | VERIFYING DOCUMENTS - This ITP
text | 8d43b826-96e0-506f-984b-cf8a138a5b8b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Surface Preparation
label | dbca537b-852b-5b1f-be25-68cd83a5d169 |  | note | REFERENCE - Surface Cleaner TDS Coating System TDS 685.05 686.06
label | 021d7a6d-93ec-5703-bb4d-7d9d7a9c6ecd |  | note | – – – – – – – – – – – – – – – – –
label | f7b78dab-1f16-5584-983b-d337c8b5f8b8 |  | note | ACCEPTANCE CRITERIA - The surface shall be prepared in accordance with the Coating System TDS, but as a minimum, all dust, dirt and other surface contaminants such as release agents and curing compounds shall be removed by appropriate means. The surface shall then be flushed with water. Any concrete defects exposed during the surface preparation shall be repaired accordingly.
label | 31d3349d-b8d4-555a-97ba-903115b761e1 |  | note | – – – – – – – – – – – – – – – – –
label | bd91a4d7-37fc-529a-af42-4c5a0056023a |  | note | METHOD - Visual
label | 46611d0f-d33b-5cfe-b69f-e9672af49f11 |  | note | – – – – – – – – – – – – – – – – –
label | f701f737-91d7-5137-bcc7-f48582e9204b |  | note | FREQUENCY - Once, prior to application.
label | e5707ee2-b394-5304-99a6-b3399b56db1c |  | note | – – – – – – – – – – – – – – – – –
label | 77c321da-e6a9-5e88-a2ae-fcc75e31341e |  | note | CATEGORY - IP
label | 7a951595-b3f1-5a96-aa8d-866ff1a263b1 |  | note | – – – – – – – – – – – – – – – – –
label | aadcfa6c-12ca-5c3d-9b55-baf81bc2e982 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 98e3e415-d865-53c4-b721-4501350ef4c2 |  | note | – – – – – – – – – – – – – – – – –
label | 405761a2-1574-5cca-925e-f393506062cd |  | note | VERIFYING DOCUMENTS - This ITP
text | 9b4cfe5a-9462-511b-880c-5b2571c064c2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Surface Moisture Testing
label | 10947aec-d9e7-529e-a1f9-8f491ad200a0 |  | note | REFERENCE - 685.12 (a) 686.14 (a) (iii)
label | e268f140-919b-532d-ac1b-12c12f120596 |  | note | – – – – – – – – – – – – – – – – –
label | 45bee015-424d-5630-85f0-ad038b8f3884 |  | note | ACCEPTANCE CRITERIA - The substrate is free from back water pressure and the surface moisture conditions shall satisfy the Coating System TDS. Surface moisture conditions are to be recorded.
label | 0e0607b5-6ab7-591d-a44a-517ed2abccad |  | note | – – – – – – – – – – – – – – – – –
label | 3f7e1e23-5e9c-501f-886e-8a39031793ad |  | note | METHOD - Test
label | 61dfdef7-3e01-54e9-a0bd-5d60877bb6c0 |  | note | – – – – – – – – – – – – – – – – –
label | 292fd930-3212-5ab5-a8e9-a176142b308f |  | note | FREQUENCY - Immediately prior to application, test 1m²
label | fc059f19-2fcb-5d90-bbe6-d8635681f77d |  | note | – – – – – – – – – – – – – – – – –
label | 9dba30fb-60e0-526b-ad0f-f5535ffcea94 |  | note | CATEGORY - IP
label | ecafd582-bc41-5b0b-9da7-db038bf9b36a |  | note | – – – – – – – – – – – – – – – – –
label | 1292124c-a916-5829-bd44-ecf5df2611c7 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 0cb1c00b-7f5d-5856-8d86-186f1df20198 |  | note | – – – – – – – – – – – – – – – – –
label | 7a75fa46-520d-5d2d-b610-6d9086b0c9d5 |  | note | VERIFYING DOCUMENTS - This ITP
text | 039bd177-2773-5d2c-94db-ade4ff9ba398 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 4 - Application Activities
checkpoint-status |  |  | checkpoint | 4.1 - Method of Application
label | 399bf443-9ff3-5256-9969-d1fe2e050f13 |  | note | REFERENCE - Coating System TDS 685.07 686.07 686.09
label | ccfbff13-525b-55b5-b8b1-7ccd7d383d0e |  | note | – – – – – – – – – – – – – – – – –
label | 764d7985-4a46-57f9-bb06-3adf3f9ad91e |  | note | ACCEPTANCE CRITERIA - Application should be carried out to the Manufacturer's TDS within 24 hours after completing the surface preparation so that the desired, uniform surface finish is achieved. Re-coating shall be within the recommended timeframe from the TDS and only if any defects or damage to the previous layer have been rectified. For penetrants, the material shall be applied at the lowest point, proceeding upwards to higher elevations and saturated enough so that a "wet look" can be observed for at least a few seconds after application. Times of coating(s), material names, locations coated and volumes used shall be recorded.
label | e8cb1c13-4b54-5f91-a1e3-42ce359bdc3c |  | note | Attach: Coating Application Record
label | a5be0b39-04b7-5275-8975-e4e50b518067 |  | note | – – – – – – – – – – – – – – – – –
label | 310954af-1f13-586e-b35c-9594363dfd2a |  | note | METHOD - Visual Measure
label | 15a7e271-89ef-5ae9-8c7e-e5ad3bd65607 |  | note | – – – – – – – – – – – – – – – – –
label | ef559202-69e9-5b9f-9bd4-3eec456a6fe0 |  | note | FREQUENCY - Each coat
label | ca0a3cc1-bd8d-546c-a61f-f2f348007cd9 |  | note | – – – – – – – – – – – – – – – – –
label | 502aaf74-14f4-552b-884f-44f075939d1b |  | note | CATEGORY - IP
label | 61e537e2-236b-5422-b3f6-7b751039eaad |  | note | – – – – – – – – – – – – – – – – –
label | 6cadd845-43e8-537f-9abd-5c7384f5b449 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 8fa40dbb-0a25-5062-b970-f814be16c355 |  | note | – – – – – – – – – – – – – – – – –
label | 87f219c0-6aee-52cf-a100-c8139dbd1a36 |  | note | VERIFYING DOCUMENTS - This ITP
text | 0dbfdcac-1668-56ea-9383-913e5d5f91f9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Wet Film Thickness (WFT) Testing
label | 014939c2-2ddd-5d1a-9bfa-a81fc78b9a3b |  | note | REFERENCE - Coating System TDS 685.12 (b) (ii) 686.14 (b) (ii)
label | 1cec9b12-e83e-5ea8-92de-ebb5d58adae2 |  | note | – – – – – – – – – – – – – – – – –
label | 020b17c4-8611-5699-838b-9225c721c305 |  | note | ACCEPTANCE CRITERIA - Film-forming anti-graffiti coatings shall have a combined thickness of 175µm, for all other applications, the WFT shall be measured and be in accordance with the Product TDS.
label | 05a18714-4533-5d42-a3a5-3a7c3668df2a |  | note | Attach: WFT Test Results
label | 69a4da54-0614-5fbf-ba2f-e2f5955fa409 |  | note | – – – – – – – – – – – – – – – – –
label | cba610eb-d119-5ad6-80b1-7349563b68ee |  | note | METHOD - Test
label | 9c7740a4-eb70-590b-aed1-d4c7de5c4369 |  | note | – – – – – – – – – – – – – – – – –
label | 519193b0-8f36-5acb-9e97-06eb58638933 |  | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
label | 0e984dba-baf9-5281-86d7-4b1a890a1a8a |  | note | – – – – – – – – – – – – – – – – –
label | 272688dd-993e-5dfd-9b01-a41fc9a26661 |  | note | CATEGORY - IP
label | 672f64a3-a31f-52ca-bbb9-7cb080d415c9 |  | note | – – – – – – – – – – – – – – – – –
label | e64287c3-5bb4-5f60-82d8-7bb7e5f515b2 |  | note | RESPONSIBILITY - SE/PE/SPE
label | f59b4af2-7a77-5959-b646-d3dee2a32c62 |  | note | – – – – – – – – – – – – – – – – –
label | 509b4b02-fad2-5908-b302-a698718ccdfb |  | note | VERIFYING DOCUMENTS - This ITP
text | 83cf7d10-7536-5fd8-8056-7627b372e483 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Inspection & Defect Identification
label | d948b8fa-9e0b-5ced-ade2-5e2c9e2a8dad |  | note | REFERENCE - 685.07 685.13 (d) 686.07 686.15
label | 2b9edd08-65d6-5665-9baa-d2291f279195 |  | note | – – – – – – – – – – – – – – – – –
label | fd139cdf-8528-5e4c-9fbf-06be0ec932d5 |  | note | ACCEPTANCE CRITERIA - The work shall be inspected for uniformity, colour, gloss, opacity and appearance between coats. Defects such as lumps, bubbles, inclusions, ripples, sags, runs and air holes shall be removed and re-application at those areas may be required.
label | 79783ccb-eaa3-541e-985b-f2890653dcfc |  | note | – – – – – – – – – – – – – – – – –
label | 9aa78637-991a-5740-9261-13facf27dbf8 |  | note | METHOD - Visual
label | 844d38ba-23bd-5e1b-8145-7df20db1e916 |  | note | – – – – – – – – – – – – – – – – –
label | 121e75df-e351-5ac0-a705-cf7fff4a0fdc |  | note | FREQUENCY - After each coat
label | e8b4f7c1-3c7f-5296-ba67-d71319c0cfe3 |  | note | – – – – – – – – – – – – – – – – –
label | cbea51f2-4fc4-5efd-a774-84ee67d1f1ee |  | note | CATEGORY - IP
label | 5c936da4-f722-576e-9736-ea1ed48e04a6 |  | note | – – – – – – – – – – – – – – – – –
label | f242d90d-6cf5-5d15-80df-5edfcff0ede4 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 922974f5-2360-5a95-b556-2e3f3e589153 |  | note | – – – – – – – – – – – – – – – – –
label | f458c7a2-8275-53b8-b1de-b7b0b49179fd |  | note | VERIFYING DOCUMENTS - This ITP
text | b3bb8a17-fb90-53f7-a632-43f301a62a4c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Drying and Curing
label | 96676d45-d6d7-5812-ac2f-de8be70e59ba |  | note | REFERENCE - Coating System TDS 685.17 686.09
label | 3ace204d-646c-5b50-85ef-0a627d292691 |  | note | – – – – – – – – – – – – – – – – –
label | b25c651c-12eb-53bf-8ee7-e456bc8e2589 |  | note | ACCEPTANCE CRITERIA - Coatings shall be protected from adverse conditions, dust and debris during the curing period.
label | 1c7235cf-e0d5-5c76-ad9a-05b2e2ccd9b0 |  | note | – – – – – – – – – – – – – – – – –
label | 580139d7-bc2d-59aa-8a31-841591ad53f7 |  | note | METHOD - Visual
label | 5d9403cb-e8fc-5968-b76a-fc3dd86d26bc |  | note | – – – – – – – – – – – – – – – – –
label | 9f5d8955-d688-5b8a-839d-d2dccb456f0d |  | note | FREQUENCY - After each coat
label | 8dd675ab-437c-5d22-ad68-51dde42f32e7 |  | note | – – – – – – – – – – – – – – – – –
label | be2ce64f-a5ec-5712-afc3-ca28ab43a03c |  | note | CATEGORY - IP
label | 74b34841-a5b4-5d66-a379-eb72141eabb1 |  | note | – – – – – – – – – – – – – – – – –
label | a866f9a1-df98-5cbd-95bb-43cc51fd6442 |  | note | RESPONSIBILITY - SE/PE/SPE
label | f9e533da-f8f1-510e-abf2-a146b66087af |  | note | – – – – – – – – – – – – – – – – –
label | f8bae051-226f-55b8-9bc0-4a17995ecbdb |  | note | VERIFYING DOCUMENTS - This ITP
text | f1c4f71e-c08c-5f56-836e-b6ba6ab4e969 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5 - Post-application Activities
checkpoint-status |  |  | checkpoint | 5.1 - Clean-up & Waste Disposal
label | 81a8aceb-21ef-5463-aac9-6810e5294ccc |  | note | REFERENCE - 685.09 (c) 686.10
label | aee9e6fd-a940-58ba-b444-85279a88813d |  | note | – – – – – – – – – – – – – – – – –
label | 77d70ec7-7185-56e3-89f1-0ab432469070 |  | note | ACCEPTANCE CRITERIA - All coating drips, smudges and over-spray shall be removed from all surfaces, including surfaces not being treated. All rubbish and remaining coating products shall be removed from site.
label | a34e1175-a1cc-547d-951b-87755042dca0 |  | note | – – – – – – – – – – – – – – – – –
label | 41e37150-1a3e-59d1-9fcd-7c82cd0543da |  | note | METHOD - Visual
label | 8df81a20-5fdc-5c36-a117-d7f311698fe0 |  | note | – – – – – – – – – – – – – – – – –
label | d30978ef-d8a2-517c-a439-51662c0ae4c9 |  | note | FREQUENCY - At completion of Works
label | 17dc4159-e570-5a17-98f0-2ee05e8fa3d1 |  | note | – – – – – – – – – – – – – – – – –
label | 125dc561-1e3b-5037-b58c-754f0df9cf0d |  | note | CATEGORY - IP
label | 98136a13-8f04-5aef-b254-e54bf50f5df0 |  | note | – – – – – – – – – – – – – – – – –
label | 1527af5f-67ef-518f-9c96-d122408abae1 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 2ce445c1-5047-5b95-8f3f-136248797825 |  | note | – – – – – – – – – – – – – – – – –
label | fae1dd11-81bd-5e4e-b1d0-bb354caf8b89 |  | note | VERIFYING DOCUMENTS - This ITP
text | 0668478d-f306-51f2-9825-4963318d7ecd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Dry Film Thickness (DFT) Testing
label | af8f8292-4f9c-5415-b7f6-5ee1984596ce |  | note | REFERENCE - 685.12 (b) (iii) 686.14 (b) (iii)
label | 8fb30f52-fb28-5cce-b2b7-ed3c14eb843f |  | note | – – – – – – – – – – – – – – – – –
label | f6875188-fea9-511b-99fc-ccdc212520d1 |  | note | ACCEPTANCE CRITERIA - The total DFT of the system shall be tested to ensure that it meets the required minimum application thicknesses: i. Anti-graffiti system = 100µm Ii. Decorative & anti-carbonation = 150µm iii. Decorative, anti-carbonation & anti-graffiti = 150µm iv. Atmospheric & splash zone (dual protective) = 200µm
label | 80064406-a67c-5075-9e39-95335112bab4 |  | note | No more than 15% of the readings shall be less than 90% of the required thickness.
label | 44f2c405-695a-5d9d-b2e2-02f0c3b61097 |  | note | Attach: DFT Test Results
label | b6e2334e-fc3e-596b-9243-ec50e91f0c8e |  | note | – – – – – – – – – – – – – – – – –
label | 7a2a1713-820c-5241-a545-7f981ae2aaa5 |  | note | METHOD - Test
label | a06ebf61-8307-5cd3-9c22-5a6eade39d98 |  | note | – – – – – – – – – – – – – – – – –
label | bfa0d18c-32b5-5052-bf7a-d38c08160e0e |  | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
label | d7291d2c-a1f7-570d-9b3a-fa63f2b53cbc |  | note | – – – – – – – – – – – – – – – – –
label | d4885f7c-13f7-5be8-aace-e07e9a861452 |  | note | CATEGORY - IP
label | 3d20e145-7b99-5630-8c81-e8a2de3eacea |  | note | – – – – – – – – – – – – – – – – –
label | ed0d0402-46bf-5905-949d-b4ab75693179 |  | note | RESPONSIBILITY - SE/PE/SPE
label | c5dfe5a3-253c-5571-b2bd-b554b17f905f |  | note | – – – – – – – – – – – – – – – – –
label | 49a648f9-2081-5443-ade1-bd735a33f6fa |  | note | VERIFYING DOCUMENTS - This ITP
text | b052b3a5-a09c-50a8-b426-84b3f2d25232 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Adhesion Bond Strength Testing
label | 3a98e14d-3d79-5786-8900-a4b1a5bb6444 |  | note | REFERENCE - 685.12 (b) (i) 686.14 (b) (i)
label | 56bdbd80-6208-539f-ae30-3778d6293213 |  | note | – – – – – – – – – – – – – – – – –
label | 3e330636-f68c-54ed-b52d-5033c6b19816 |  | note | ACCEPTANCE CRITERIA - A minimum of 14 days after application, the bond-strengths between: i. the coating system to the substrate, and ii. Separate coating layers shall be tested using 50mmØ aluminium dollies. The subsequent results shall be greater than 0.75MPa.
label | 2c2f1dba-d1f0-5f49-b979-b65e98af6c20 |  | note | Attach: Adhesive Bond Strength Testing Results
label | 1d14b847-ebc3-5175-a10d-10c66af60dab |  | note | – – – – – – – – – – – – – – – – –
label | d21bf8ef-0c41-54c0-b0aa-967f2acf3016 |  | note | METHOD - Test
label | b56f003d-eb48-5e34-86b3-fed06aa1d548 |  | note | – – – – – – – – – – – – – – – – –
label | 903dc1d4-409e-5198-b65d-6409d57658ff |  | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
label | a91635e5-78fd-570e-aebb-d2c320ca2415 |  | note | – – – – – – – – – – – – – – – – –
label | 2f20fcc6-bf06-5b33-a715-964c107a07c1 |  | note | CATEGORY - IP
label | 8bdae910-5d0f-5429-b093-d879051d7212 |  | note | – – – – – – – – – – – – – – – – –
label | 506b4453-8cca-53e9-b59e-b1ecb3d22524 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 9e7f8b01-8a44-573c-b159-cf7a8ffe50ce |  | note | – – – – – – – – – – – – – – – – –
label | f7f68b6b-f8a4-5590-be2b-797f5c8e7425 |  | note | VERIFYING DOCUMENTS - This ITP
text | 93b4c548-f38d-5527-b7fa-d711214305c5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Penetration Depth Testing
label | 966fcf75-813b-54be-885a-7adc7beeece4 |  | note | REFERENCE - 685.12 (b) (v) 686.14 (b) (v)
label | b4afeffa-0838-5c3e-938d-d4dd20eecc45 |  | note | – – – – – – – – – – – – – – – – –
label | 08d1ce56-c2cd-508d-8059-e969e91e0268 |  | note | ACCEPTANCE CRITERIA - Where a penetrant is applied, a 50mmØ core sample, 50mm depth, is to be taken and immersed in a fugitive dye to determine the depth of penetration. The subsequent results shall be: i. Sprayed anti-graffiti penetrants = unspecified (as long as it is visible) ii. Silane, Solid Silane or Silane Cream = 5mm min. iii. Silane-Siloxane or Siloxane = 3mm min.
label | 6bd607e4-ea79-576e-9261-538d67501763 |  | note | Attach: Penetration Depth Testing Results
label | fea6656f-ae8c-5047-96ad-dd9cab32a7cc |  | note | – – – – – – – – – – – – – – – – –
label | c3d68b6d-a40e-5904-9037-a6fa1b557285 |  | note | METHOD - Test
label | 69365936-e10d-5b1a-b723-366836e7d93d |  | note | – – – – – – – – – – – – – – – – –
label | df716e7d-9af7-5bb4-8284-d3f9586a395d |  | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
label | f8d81bdc-0ec8-5982-ad47-767415f77ee8 |  | note | – – – – – – – – – – – – – – – – –
label | d9f0c93e-bc2c-5134-be1b-df83d0e945a6 |  | note | CATEGORY - IP
label | 878c7adb-ca2f-54bb-bf6c-a80dc405c8b8 |  | note | – – – – – – – – – – – – – – – – –
label | de77f407-c61c-5faa-a74b-c0f1e33e5082 |  | note | RESPONSIBILITY - SE/PE/SPE
label | bee967e1-b66d-5dc3-945b-05af3dcf857e |  | note | – – – – – – – – – – – – – – – – –
label | a14b9b8c-aae7-5761-851f-fa7125089393 |  | note | VERIFYING DOCUMENTS - This ITP
text | 30860773-134d-5ca4-bbf8-1518a364dac1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Non-conforming Coatings
label | a96c597c-cc2b-58ac-946d-bdc901d19c63 |  | note | REFERENCE - 685.14 686.17
label | e9491994-de9c-58e1-af6d-ba0be452d4fe |  | note | – – – – – – – – – – – – – – – – –
label | b40106ca-c659-524f-9174-1830843e7a23 |  | note | ACCEPTANCE CRITERIA - Should any of the coating application Work be found to be non-compliant with the specifications, the areas shall be repaired. Such Work may include removal of the coating, surface preparation and re-application. Non-compliant Work includes, coating failure to yellowing, loss of adhesion, penetration of graffiti into the coating, loss of solvent resistance and colour change during the contract liability and/or guarantee period.
label | f79bda69-5ff3-5dee-a5b8-49167bab3ef0 |  | note | – – – – – – – – – – – – – – – – –
label | 5b74aaa9-caa0-5b3e-9eb5-b984ee6e7439 |  | note | METHOD - Visual
label | 762cdfe3-1a0d-503c-961f-bd841551167d |  | note | – – – – – – – – – – – – – – – – –
label | f3426c77-1812-58d0-94ed-6c2eb0a5cb32 |  | note | FREQUENCY - Where required
label | a5b2628c-21fb-54d2-bdfe-0b1800522f0b |  | note | – – – – – – – – – – – – – – – – –
label | a4e37670-4145-56a0-9d02-5d55158bf32a |  | note | CATEGORY - IP
label | b40dcc41-8c5f-53dc-af04-0779221ad7cb |  | note | – – – – – – – – – – – – – – – – –
label | 712b8c87-6e2e-55b3-a0c0-80637b73bb15 |  | note | RESPONSIBILITY - SE/PE/SPE
label | bb39dfb6-a51d-5629-ac0d-ca902d9732ef |  | note | – – – – – – – – – – – – – – – – –
label | 738bfd51-664e-5657-b83d-2ae129fe18bc |  | note | VERIFYING DOCUMENTS - This ITP
text | 0f3419a3-fe68-512d-840d-b2335c11d9d1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Coating Application Guarantee
label | 511d3eed-83fa-5e44-9d25-fcd3d71a6eb8 |  | note | REFERENCE - 685.06 (b) 686.05 (a)
label | 975e5b0e-5b5d-5d7e-81cc-d4750567cd1f |  | note | – – – – – – – – – – – – – – – – –
label | 3d6a661c-3237-578f-a1df-f61de50e5f30 |  | note | ACCEPTANCE CRITERIA - Application shall be guaranteed to last for 10 years of outdoor exposure and for anti-graffiti coatings, have at least 8 cycles of graffiti defacement and removal from the date of application.
label | bbba7dfe-2b6f-566d-82a6-90dd45177011 |  | note | Attach: Coating Application Guarantee
label | 1e845caa-52a6-5806-a53b-9079d0a4c14d |  | note | – – – – – – – – – – – – – – – – –
label | abdc29bb-7b55-5951-aed7-11b6e863791e |  | note | METHOD - Document Review
label | 7030b621-d228-560e-8b3a-0cf76b1d1848 |  | note | – – – – – – – – – – – – – – – – –
label | b482f02a-378c-5d85-be78-4f04ddb173f3 |  | note | FREQUENCY - At completion of Works
label | 4fc87bfd-a5b9-5052-ab58-454966e49846 |  | note | – – – – – – – – – – – – – – – – –
label | 39683206-c572-53e7-baa6-7244ceebfdbf |  | note | CATEGORY - SP
label | e4bdfdc8-5135-50a5-8d5a-29f21e404e4f |  | note | – – – – – – – – – – – – – – – – –
label | a84186db-39d5-5572-ad64-f1313f293e2c |  | note | RESPONSIBILITY - SE/PE/SPE
label | 4ccedf4b-803d-5dd8-ba96-f5dcad60cab5 |  | note | – – – – – – – – – – – – – – – – –
label | 8a3f1fda-30ea-539a-8ba0-452aeb3cc20e |  | note | VERIFYING DOCUMENTS - This ITP
text | 86f62236-9304-5320-9485-1c065b178d1c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Repair to Damaged Coating
label | 8e97eeee-0356-5c47-8ddd-50644ab3e6a2 |  | note | REFERENCE - 686.17
label | c573d9d0-a8a3-51ef-83ce-5de3fc6e85bb |  | note | – – – – – – – – – – – – – – – – –
label | 252d1b5c-40c4-53b8-8bf0-114bddcc67bc |  | note | ACCEPTANCE CRITERIA - Any damage to the coating during the construction period shall be repaired to the full extent of the system requirements.
label | f10f4c1a-eb16-5889-b5ab-8929184f0006 |  | note | – – – – – – – – – – – – – – – – –
label | 406a2312-37ab-52a3-a3ee-75ee9f0636b5 |  | note | METHOD - Visual
label | 1dd4ff43-f5de-598f-a1d5-a5e33152c6dd |  | note | – – – – – – – – – – – – – – – – –
label | 138cb7c2-14d9-5d4b-912d-c8c3176a1f65 |  | note | FREQUENCY - Where required
label | 08ee66d1-f41e-56dd-ad05-eada81f7af72 |  | note | – – – – – – – – – – – – – – – – –
label | 28e1cde7-4674-558f-8ed4-03cb88886a22 |  | note | CATEGORY - IP
label | d3141d50-7ab2-52b5-8f01-7bb613c48a9e |  | note | – – – – – – – – – – – – – – – – –
label | 02c87db3-9384-52e5-b421-e65cc7302bb2 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 1669dda1-7b10-54d2-b127-2c296ad7cfff |  | note | – – – – – – – – – – – – – – – – –
label | e874a2dc-067b-56e5-bf4d-4affae44fbe9 |  | note | VERIFYING DOCUMENTS - This ITP
text | f345431c-c758-52c1-aeb7-399cbcd7f524 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Non-conformance Report (NCR) Closure
label | 6ff28cd4-3162-53cc-a202-95b7540ffcb8 |  | note | REFERENCE - MRPA Quality Management Plan
label | cf625f1b-0df7-5c61-a53d-d72008ff843c |  | note | – – – – – – – – – – – – – – – – –
label | 7a7a56a2-98a8-5449-99f7-177a579a8586 |  | note | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 37b8ad66-81f3-5660-a510-d0ae0562c2fd |  | note | – – – – – – – – – – – – – – – – –
label | a7a23ca3-e4d1-562a-a302-1d13cdf46a1c |  | note | METHOD - Document Review
label | 50d19fd4-4849-574b-b0de-cac105f1ebb7 |  | note | – – – – – – – – – – – – – – – – –
label | 5451cb6d-1b46-508e-80ae-4214e7d59d12 |  | note | FREQUENCY - Once, prior to closure of this lot / element / Work area
label | 98289b5b-efcb-5fc0-94fb-5c5a6b94f6ac |  | note | – – – – – – – – – – – – – – – – –
label | cc005129-4bc9-5715-a369-abdf5a00e671 |  | note | CATEGORY - HP*
label | c561d3f3-c067-5d24-a698-37b4f51ad470 |  | note | – – – – – – – – – – – – – – – – –
label | 5beb6ef1-4c0a-5e63-a31f-55bec922a7d7 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 33822834-08fa-5fb2-b573-5bf85f66292a |  | note | – – – – – – – – – – – – – – – – –
label | 0f74fcef-9de8-5167-9bef-962352ce1d4c |  | note | VERIFYING DOCUMENTS - This ITP
text | 62c50dde-34ed-546a-b02b-0b312b75f346 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 5f51247b-dce1-5fcd-b0d7-dd2b97fa730d |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | de947f70-a5f3-5095-b980-1e28abf6d9ad |  | textbox | Name:
text | 6d05b64a-a81e-5186-a0e9-c5b035c1c512 |  | textbox | Position:
date | 5c664c2b-5c6a-5877-9405-12b16410d981 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-125-STR-CPD-Precast Plank Installation | itp |  |  |  | Yes | ITP-125-STR-CPD-Precast Plank Installation Rev 0 | d76050dc-2499-4299-9ca7-99cef365564d
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 2b1ae403-d883-5d17-97e9-69462e07ad34 |  | note | Document Title: ITP-125-STR-CPD-Precast Plank Installaton
label | 2e360715-79dc-5edf-a30d-46e39bbe15d7 |  | note | ITP Description: CPD-Precast Plank Installaton
label | a0d63bc0-2a26-5591-bf14-92f51e4455a2 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 2a1bd7a3-bc5b-566a-8892-a7c2c2b25c9a |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | d3e88b0d-058b-50e5-b83a-0206fefbddd2 |  | note | Revision Number: 0
label | 14de5a8f-51eb-56d2-ba09-c7db5e4a3009 |  | note | Revision Date: 19/01/2024
label | 48145ebe-1510-51d4-b34b-eb646a11a49d |  | note | ITP created by: Andrew Carlini
label | 6d83cea2-795a-5fd8-963c-364403f82e44 |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | bd7b36c9-d1e0-56bd-bd85-7a8d129a77c3 |  | note | Reference - VR 652 June 2010
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 8a790d94-1783-5f73-8d9b-e74df1ee22c8 |  | note | Reference - VR 656 June 2010
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | 499582b1-4b3f-5c87-83ac-b2252d7e6493 |  | note | Reference - VR 610 February 2020
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | 99db9bd5-04aa-5d6c-a130-1e5e55e44fe6 |  | note | Reference - VR 613 June 2017
checkpoint-status |  |  | checkpoint | 1.5 - Non Dependent
label | 0d939d3f-e5ad-583d-921a-35ae27b01f1f |  | note | Reference - VR 620 May 2009
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Precast Elements
label | 26be249f-e6c5-59d8-ab93-1e8e7adf49d2 |  | note | Reference - IFC Drawings 610.47 (a) Table 610.472 (Feburary 2020), 620.03
label | 9e165151-6449-564c-be48-d0c765960da9 |  | note | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | f83da78a-b395-509d-b9dc-b234805976ca |  | note | i. Certificate of Compliance / Birth Certificate
label | a86048ff-f96c-55d4-bebb-fd118f44d475 |  | note | ii. Compressive strength test results
label | db62cb1d-86da-5506-a047-4ae796798f89 |  | note | iii. Precast Lifting Design
label | 4197193d-0959-5b28-a8c7-02529a05b562 |  | note | iv. Pre-pour check sheet / ITP
label | 1e300acc-014c-54bf-8705-24f8ea9ecc40 |  | note | v. Pre-stressing check sheet / ITP
label | e63d56eb-e4db-5894-90ae-809869eab5eb |  | note | vi. Post-pour check sheet / ITP
label | 7f5dcf2a-04a5-5994-b923-8464505d0daf |  | note | vii. Covermeter check record
label | 13222f9f-c467-56aa-84ca-9d1337f10b2d |  | note | viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates
label | 52f3cdb0-230c-5356-b06d-18036a8e69db |  | note | Note: Different revisions of 610 have different clause numbers
label | be20a7d9-9cec-5b85-891c-0b606f544992 |  | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder
text | 8fad280c-7e90-5462-9126-ec649965cc3d |  | textbox | Enter: Teambinder MDR Lot number
label | d8fcb750-731a-5e04-8774-fe91dd81c35e |  | note | Method - Document Review
label | a30b8a44-2839-5028-b3db-c6b8ef058251 |  | note | Frequency - Each element
label | 4c6a85b8-cf20-5fe2-8209-e3c5ee363d23 |  | note | Category - HP*
label | f6543c4e-a53c-552c-8b1f-142b74643732 |  | note | Responsibility - PE/SE/SPE
label | f51cd75c-51b1-5692-8ca9-74f7e341cc4a |  | note | Verifying Documents - This ITP
date | d2fca6ac-7bf9-5d97-99a1-6e00f18b5c54 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Installation Work Method Statements
label | 2471498b-05a6-5a5e-b1c2-98c7216c1e43 |  | note | Acceptance Criteria - Installation of Precast Plank WMS to be submitted for review to the Nominated Authority
text | 68f494ba-d22d-5064-a37d-b6fc0804b4a9 |  | textbox | Enter: Teambinder MDR Lot number
label | 3b55d0ea-aea6-54e6-b378-61f975e7b1e7 |  | note | Method - Document Review
label | 7c3187d5-7e98-54a0-9c4c-35f2dd1084ad |  | note | Frequency - Once, 4 weeks prior to Instrallation of Precast Plank
label | d34bf418-f5e2-55c8-a22e-6e77aab6d1a0 |  | note | Category - HP
label | 98813a93-2b15-5ea7-a7b5-e4922ce39369 |  | note | Responsibility - Nominated Authority
label | e97c22f7-e826-5201-bc47-d8ec945c8f14 |  | note | Verifying Documents - This ITP
date | a90b7492-864a-562f-8880-e54851ac124e |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - IFC Drawings
label | 4cdaa64f-f7ad-5ed9-95e3-9bccd5fc847d |  | note | Reference - MRPA Quality Management Plan
label | e66994d3-d4a1-5d23-9dff-cd37030e4c66 |  | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | d8908d86-373a-52d7-9a49-4321eec00b61 |  | note | Method - Document Review
label | a93ab8a2-b113-5b58-a217-66bdc5eeae21 |  | note | Frequency - Prior to starting Works and at regular intervals
label | 143bb8f3-9f3f-515e-9d40-62d86ad005fb |  | note | Category - HP*
label | 241130eb-6216-5cb0-9f95-23c7e088a507 |  | note | Responsibility - All
label | fa88ffee-7b7b-5a8d-8321-3d4bfd5e558f |  | note | Verifying Documents - This ITP
date | 52279578-ad62-546e-a184-e57007e57b4d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Survey Set-out
label | bb816f3c-d1f7-5b99-b6ac-83a63f084e46 |  | note | Reference - IFC Drawings 610.47 (a) Table 610.472
label | db90aaef-20a8-51d1-838a-313034fc326d |  | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
label | ba83a9a2-1f8e-56d4-9ecd-2e39726a7801 |  | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
label | a6dbb2bb-7069-588a-bdf0-7e2348da1889 |  | note | Method - Measure, Visual
label | e0129314-8b6f-5b9c-b69a-7a89104e012b |  | note | Frequency - Each element
label | b79056a9-5866-5785-9c8d-36aefae0391d |  | note | Category - IP
label | 4393a3ee-8376-55d1-862f-bec6d9880052 |  | note | Responsibility - Surveyor, SE/PE
label | fcb6e75d-b2ca-5aad-9205-a7a8a42c71c2 |  | note | Verifying Documents - This ITP
date | 0aeed401-ee84-59f4-a5b6-60840f168148 |  | date | Date Completed:
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Falsework Design and Certification
label | f6f5cc29-212c-5fde-81d6-659ab991c91f |  | note | Reference - 613.04 Temporary Works Design
label | a1791891-e3c8-5122-b9ca-530f81aca013 |  | note | Acceptance Criteria - The Falsework drawings submitted shall state all design assumptions and shall include a statement of the loads and any dimensional changes due to loading in all members of the falsework. The drawings shall be fully detailed including all member sizes and materials, dimensions, levels, erection procedures and other relevant details including bracing, connections and foundations, to ensure that erection and inspection of the falsework can be undertaken without reference to any other documentation.
label | e9ce3fc2-59a1-5880-b55e-18c602bfd386 |  | note | Attach: Temporary Works Design
label | eedf22b7-2005-5841-8407-704d9ec770d5 |  | note | Method - Document Review, Visual, Measure
label | 5584cfe4-9dee-5430-9938-bfbb7e60c6da |  | note | Frequency - Each element
label | 9dcec5f2-9bad-52c4-be55-6caef0a87e1f |  | note | Category - HP
label | a7997785-8554-521a-990e-8a105a849aa0 |  | note | Responsibility - Temporary Works Designer, Proof Engineer
label | f513b09d-8591-5c1e-aa99-48cd8641df85 |  | note | Verifying Documents - This ITP
date | a496f733-9ba7-54af-b6b4-b12343978fa0 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Flasework Certification - Falsework Inspection
label | 4182431c-dc1f-5739-ac36-db5686235aa0 |  | note | Reference - 613.04 Temporary Works Design
label | a6e86705-898d-598a-a728-2ba613b368f9 |  | note | Acceptance Criteria - The application of any permanent load shall not proceed until the signed Certificate of Compliance - Falsework Inspection of the constructed falsework has been reviewed and accepted by the Nominated Party.
label | df3c140c-4c67-54d5-95c4-f4f7d5e8f2b4 |  | note | Attach: Temporary Works Permit to Construct, Apply Load and Remove
label | 8552602f-c438-5c2a-8e9b-0496d63bdd65 |  | note | Method - Document Review, Visual, Measure
label | caff009c-e587-5dde-ae53-ed392b9bbe63 |  | note | Frequency - Each element
label | 43fcba7b-160b-50e3-8ad2-54f2de7a6359 |  | note | Category - HP
label | 02836efc-49fe-54c0-a522-584898d952e3 |  | note | Responsibility - Temporary Works Designer, Proof Engineer
label | 6491f349-2fe9-561a-903e-b226a90cca42 |  | note | Verifying Documents - This ITP
date | 937a6c0d-547b-59bc-8eb9-e76beaf89621 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Precast Handling
label | 33be24b5-b9c4-57e3-94f1-99d33b0ef01d |  | note | Reference - 620.07 Crane Lift Study
label | efa65122-1470-5e94-a95c-d772a04f3059 |  | note | Acceptance Criteria - Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | fd7fef2a-3d4f-527a-8222-5040a216e5d3 |  | note | Method - Visual
label | 6ec50a5e-dabf-57f2-bc38-5fe22c5251f7 |  | note | Frequency - Each element
label | 5f4aaf6e-d7fd-5cc2-a60d-8ba237bd5344 |  | note | Category - IP
label | 8e91fb4e-bea9-56ad-b3f6-c75e0482b29f |  | note | Responsibility - SE/PE/SPE
label | 16e2aae0-b8bd-55e5-a6a0-8a707a89727e |  | note | Verifying Documents - This ITP
date | 8b5b3393-f0d7-589f-a430-8a8b384cbfb5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Precast Placement
label | 004fb490-4870-51ac-8b34-27a230305256 |  | note | Reference - IFC Drawings 610.27
label | 039ef6a4-a34f-5be3-84b4-9834292568e3 |  | note | Acceptance Criteria - Precast elements shall be placed onto the bearings/bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings.
label | 37897c04-11f3-518c-abfb-2a81188eb9a8 |  | note | ○ The nominal gap between elements is as per the IFC Drawings.
label | 82cb0e0a-88b2-5b02-80bb-6d5753d23848 |  | note | Method - Measure, Visual
label | 514c4269-25d7-5cca-86a9-77dfc2cd157a |  | note | Frequency - Each element
label | f80e23d1-0ff2-5d31-b13d-09957ab15c85 |  | note | Category - IP
label | 9979d6ad-49e3-5684-a06e-854851c8a656 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 7d0def6e-0147-56a2-9165-c07188896e55 |  | note | Verifying Documents - This ITP
date | 3e068717-4eff-58f0-b527-e7eb3170a10f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Precast Traceability
label | e58fb506-8a74-5b0b-9d02-fa9ef13a1131 |  | note | Reference - 620.09
label | 1c3b99dc-b76a-5595-8869-90c3768540fd |  | note | Acceptance Criteria - All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
label | fb0deaa8-9033-5ca7-9928-e11127b8cd59 |  | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
label | e380b67e-aa7b-51a4-b721-688dfa0b8970 |  | note | Method - Visual
label | d88eba52-2fa8-56f0-a789-87c0924fc078 |  | note | Frequency - Each element
label | 1e6f20b1-161e-5ab4-9cd7-5e3b87cb8d16 |  | note | Category - IP
label | b78195d5-9fd8-5985-925d-bd0f888c4ace |  | note | Responsibility - SE/PE/SPE
label | fbba969a-743d-5f49-b82d-4a5e48e8245f |  | note | Verifying Documents - This ITP
date | 9076ff5b-5e9c-523a-b274-66f1857b1963 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Platform and Stitch Pours between Planks
label | 47ce4841-65bd-510a-9875-ae550d0163fe |  | note | Reference - Structural Concrete ITP
label | 4f683277-482b-5a02-a9f7-b788cc6d5a0a |  | note | Acceptance Criteria - Precast elements shall be stitched together, either by the Stitches or by the Platform pours. Related Stitch and Platform Structrual Concrete Lots to be closed out.
text | 44bdb619-e125-54b3-9400-36c4d737d803 |  | textbox | Enter: Teambinder Lot number
label | 62e6f2b1-d83b-5403-9dcc-5b7ac0319a2c |  | note | Method - Document Review
label | 191eae18-6561-59d4-b041-d1c8cd21ead8 |  | note | Frequency - Each element
label | e14389f7-8520-5090-877d-d31e13a17f6a |  | note | Category - HP
label | c7974377-0bd8-5909-ab04-5da299122396 |  | note | Responsibility - SE/PE/SPE
label | 3e6b4a7c-bb94-5747-af2e-fd8b5c94e9e8 |  | note | Verifying Documents - This ITP / Structural Concrete ITP
date | d5e446c6-b986-5ba1-b4c3-b8aec49068e4 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - As-built Survey
label | 7775d68f-b077-5c04-acf9-aefe1f159ea4 |  | note | Reference - IFC Drawings 610.47 (a) Table 610.472 (Feburary 2020)
label | 5f298755-217c-5fdc-ac41-47ad8ed6b522 |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with specified tolerances.
label | f639301e-f2f3-572a-ac99-6ac540a922ca |  | note | Attach: Survey As-builts / Survey Report
label | dfa942a0-cd5e-52f5-ab3c-4c1aa1817fcb |  | note | Method - Document Review
label | 56c08418-4e48-58cf-a0a5-1587eb0042c9 |  | note | Frequency - Each element
label | e961ccba-b47f-5397-a110-9cab9b6a8dcc |  | note | Category - IP
label | 52636941-18a7-5440-96c6-e6732add34e8 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 5eccd729-0a0f-5ba2-9162-db16fa36f010 |  | note | Verifying Documents - This ITP
date | ae359cc1-a627-56da-ab93-dee89ea124ad |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Non-conformance Report (NCR) Closure
label | d8739096-ab34-5a20-be4d-f4e70e34352e |  | note | Reference - MRPA Quality Management Plan
label | 78af91bd-a77e-5ebd-bf44-39a5761bd359 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | b8d78380-783a-5ccf-9795-fea2eca58d7b |  | note | Method - Document Review
label | 1af32bc4-3c75-58ca-980f-9c369f82c357 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 86becf8d-014a-5b84-930c-185e496fe3be |  | note | Category - HP*
label | 51f6eb19-4752-5efb-98c9-03cb080f00a6 |  | note | Responsibility - SE/PE/SPE
label | 71be903c-589f-5c95-9122-24c2fff47c60 |  | note | Verifying Documents - This ITP
date | 295f1dcf-5135-528c-a780-fd6b7b752092 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 37b29a00-1444-5165-9166-73206833a3f5 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | bda98452-6fd6-5e79-8e79-06fbc0394f8f |  | textbox | Name:
text | 6bbb70d4-1f04-5da6-86c2-cb16c2f347b5 |  | textbox | Position:
date | b07c3c06-13f1-5379-a011-7dcd16f92ab1 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-102-STR-RSS Wall Main | itp |  |  |  | Yes | ITP-102-STR-RSS Wall Main Rev 0 | da5eeacb-db22-4790-b6c8-27e706de65ff
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | f6416660-44c7-5779-b6ca-913cc18d8029 |  | note | Document Title: ITP-102-STR-CPD-RSS Wall Main
label | 91c07c9a-c670-5f63-8269-75ddb5132189 |  | note | ITP Description: CPD-RSS Wall Main
label | ddc2e889-e5d9-5ed4-ae61-d1fca5036399 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | ee9c28d7-05a2-5daa-84d0-9394778f3fdf |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | f2ee3417-c9f5-542c-b13f-fe1ce928afea |  | note | Revision Number: 0
label | a7a2c228-f1c9-5fc8-bb5d-1559f258a6c9 |  | note | Revision Date: 09/11/2023
label | b5578fa3-a3f1-5f2c-86e2-6c7ef654d73c |  | note | ITP created by: Matthew Dib/Jason Quan
label | c515b9b8-4f43-57f8-9d41-ec84fcfb420c |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 2def75d5-310e-5d44-83aa-26b0bedc8b7b |  | note | Reference - VicRoads Section 682 November 2018
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 31911aca-dac9-57c9-aa3e-939895d4f9df |  | note | Reference - VicRoads Section 204 December 2015
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | 5d592d65-53f3-56ff-8691-3d441b3983ee |  | note | Reference - IFC drawings
checkpoint-group |  |  | section | 2. Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Concrete-Leveling Pad
label | 8a0363bb-545e-5f9d-830e-a843736fc7f6 |  | note | Reference - IFC drawings
label | 985767b3-9946-5ef0-9ecb-bd1a0320aacd |  | note | Acceptance Criteria - Concrete compressive strength grade must not be less than N25 for levelling course and backing blocks;
text | 8eedd003-4cef-5797-b372-893488c4e7ea |  | textbox | Reference: Teambinder MA number:
label | d8434fcc-b9bd-51ad-a618-2390ea781b12 |  | note | Method - Document Review
label | beb745a5-5e09-51c2-a29a-950a73dbf176 |  | note | Frequency - Each element
label | 3d6fbe01-aa97-5497-ba72-63db28462577 |  | note | Category - HP*
label | 88d002f7-7121-54dd-aebf-f2e9c73b44ef |  | note | Responsibility - PE/Nominated Authority
label | 55978f6d-9721-56a3-bb69-54859ca22fef |  | note | Verifying Documents - Material approval
date | 4da07b9d-a629-5e49-b6e2-b9077aeb0be4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Select fill
label | 3ded5562-5a87-576a-90b7-dc63dcf5b35e |  | note | Reference - IFC Drawings VR 682
label | 8b8ae7fe-27cf-5e24-9a19-9ec11646f527 |  | note | Acceptance Criteria - Select fill shall comply with the requirements of the RSS designer:
label | 72270269-06d9-55a3-8f3d-66abb07c052c |  | note | ○ UNIT WEIGHT (Max): ≤ 16 kN/m³
label | c1e2666e-ba9e-5d10-a4d4-d36c492ccba4 |  | note | ○ COHESION (Min): ≥ 0 kPa
label | 0472e86e-3a5b-5607-b02c-4522c8478e91 |  | note | ○ INTERNAL FRICTION ANGLE (Min): ≥ 36°
label | 695c7f44-8a3a-5349-881b-f9c1cd16fdf8 |  | note | Gradation:
label | fff0eea0-6aaf-5cd4-b467-6882652254c0 |  | note | ○ 150mm : 100% PASSING
label | 6cd73d49-9e6b-5110-94a8-2d241d0e976c |  | note | ○ 37.5mm : 60 TO 100% PASSING
label | 28843e24-e9a2-5184-bed6-62da1e98bc34 |  | note | ○ 9.5mm : 25 TO 100% PASSING
label | 5fd28a37-a11e-553a-bcd8-e4cf1e6d8a40 |  | note | ○ 2.36mm : 15 TO 100% PASSING
label | 6dda1d4f-9b32-5c5e-a851-0d33c712e700 |  | note | ○ 0.6mm : 10 TO 100% PASSING
label | f1366295-5587-5f66-b712-afe4a7c3e281 |  | note | ○ 0.075mm : 0 TO 15% PASSING
label | 032e8721-eb61-5ebb-ad9e-08d647ab3a00 |  | note | Electrochemical Properties:
label | 4edd9d38-fc68-5de8-b375-234b6c1b4908 |  | note | ○ pH: 5 - 10
label | bcb194f6-c795-5e9d-9c10-0255ee3fed2f |  | note | ○ RESISTIVITY >1000 Ω-cm
label | cd2bf118-d3b4-5e09-81e6-601845540743 |  | note | ○ CHLORIDES <200 mg/kg
label | 7c26dc2c-729d-524e-9d4b-0b0a145aab2e |  | note | ○ SULPHATES <200 mg/kg
label | 98863680-2c15-584b-81c4-68a05bfe3ea5 |  | note | ○ ORGANIC CONTENT 0%
label | 3149739d-66d8-50f0-9f5a-cd4427feb150 |  | note | Structural Properties:
label | c509e7bb-060b-505c-ba8d-889760462e4b |  | note | ○ COEFFICIENT OF UNIFORMITY ≥ 5
label | bb8bc0ae-5ea7-5955-b4d9-b7b102cfbbf8 |  | note | ○ LIQUID LIMIT ≤ 30%
label | bbaeaafa-3dae-5b4d-bd29-153f72d0649b |  | note | ○ PLASTICITY INDEX ≤ 12
label | b5d1774e-a1ed-5f72-9dbf-fbbab37f9a20 |  | note | ○ The select backfill must meet the minimum requirements of Vicroads Type A filling
label | cae1100c-2512-5fc4-840e-c0dfa10eae34 |  | note | Reference: Material approval in Teambinder
label | 8d90fffc-23ef-52f8-8675-d4bf295c070e |  | note | Method - Document Review
label | 44e3ba5e-cae9-5666-8623-2ada9be65902 |  | note | Frequency - Each material specification
label | 0d390af3-3b5b-5580-b316-3d657525ad6d |  | note | Category - HP
label | 4b78af60-c2a9-52d2-9050-fd965e5ab6a9 |  | note | Responsibility - Nominated Authority
label | dcf4753b-9f97-52a0-920e-9e5c0cc352cd |  | note | Verifying Documents - Material approval
date | e7df57bc-ff43-5962-b5ed-c7e60e26d4f8 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - General fill
label | f52822f9-0ed3-5227-ba23-2404ad0ba99e |  | note | Reference - IFC Drawings VR 204
label | 225a0a2d-4d33-5854-a6cc-074f17594d2d |  | note | Acceptance Criteria - Backfill behind the reinforced block shall be Vicroads Type B or better in accordance with Vicroads standard specification 204:
label | 481894bf-bc43-5691-8c04-67cdc3c122c1 |  | note | ○ Select General fill shall comply with the requirements of the RSS designer (RW05-RW06):
label | b72605e7-26cf-5593-9800-7031ad01e164 |  | note | ○ UNIT WEIGHT: ≤ 19 kN/m³
label | 95666c3b-eeab-5fa4-8dbe-52b5db960ef6 |  | note | ○ COHESION (MIN): ≤ 2 kPa
label | 66fc399b-3dfd-5b42-9d2b-884f4ee14ecd |  | note | ○ INTERNAL FRICTION ANGLE (Min): ≥ 30°
label | b3831307-3dcf-5970-8995-7e175fc7a266 |  | note | Reference: Material approval in Teambinder
label | d88a87f0-77ea-51d8-a1b7-3874c0958c40 |  | note | Method - Document Review
label | 8cd5de8e-aef6-57bd-9771-4d5e2bdd1eb7 |  | note | Frequency - Each material specification
label | 664d4530-9266-58c6-8fbe-91324f04d008 |  | note | Category - HP
label | 4e152af4-075a-5221-bec5-ddbf62220a73 |  | note | Responsibility - Nominated Authority
label | 0fbbf8f1-fb1e-5e1e-ae0e-b32e796bf33a |  | note | Verifying Documents - Material approval
date | b05bca9e-c008-5b61-a40e-144e681880a4 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Perforated Pipe-material
label | 301ae42d-c64c-5e32-acd0-f59715ca2660 |  | note | Reference - IFC Drawings
label | 5561e744-a5fc-5afe-b2e1-13e538df6ce4 |  | note | Acceptance Criteria - Perforated plastic pipe perforations shall be a maximum width of 1.5mm and minimum length of 150mm per m2
label | b6a3dc0a-15aa-57e7-af8d-242809fd3168 |  | note | Reference: Teambinder MA number:
label | 6c95df93-5d75-53d8-968e-7e07b86bc046 |  | note | Method - Document review Measure
label | de7646ba-e1e0-5465-adfc-3dfc973d77df |  | note | Frequency - Each wall
label | 7bf5ef62-fc84-5634-8177-dbc3d0036258 |  | note | Category - HP
label | b0f83887-31b8-5f12-b61b-678e6204487f |  | note | Responsibility - Nominated Authority
label | 5ddcb906-5eb3-5e06-bcd1-c565bbac8709 |  | note | Verifying Documents - Material approval
date | 3bbe7983-fa5a-5023-8c31-0779067e082f |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries-Documents
checkpoint-status |  |  | checkpoint | 3.1 - RSS Panels
label | 02482ce7-24da-5402-8f81-7d3b5142ef03 |  | note | Reference - IFC drawings
label | 739d670c-e6ce-5aad-9f20-cfdae2f72967 |  | note | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | 5b2ab3c5-852d-50c3-ad58-dcd87da74bd7 |  | note | i. Certificate of Compliance / Birth Certificate
label | 9cd1ce78-f519-592f-be14-f33db81cb26f |  | note | – 1. Concrete strength;
label | 9739040d-3045-5b6c-9332-a89c8b8b0277 |  | note | – 2.Date of manufacture;
label | fdeae804-b199-5feb-92b7-21d9c7afccfe |  | note | – 3.Unique Identification number;
label | 878059be-fe8a-5a21-a597-935fcfb4cae8 |  | note | – 4.Mass;
label | 7ac6cedf-06fa-50ae-bcc6-b2cd67d1516d |  | note | – 5.Confirmation of number, type and capacity of lifting inserts;
label | 77e7856e-a19d-5a0d-9998-829c4c259912 |  | note | – 6.Quality assurance sign-off.
label | 0bc6dbc0-6973-5a93-b1be-39f36076c50c |  | note | ii. Compressive strength test results
label | 554405d2-8808-5422-9a9c-eae07d6d1b1a |  | note | iii. Precast Lifting Design
label | bdddeab2-3386-5990-af69-723b44a99894 |  | note | iv. Pre-pour check sheet / ITP
label | 52399325-3421-5750-9475-3983f5565339 |  | note | v. Post-pour check sheet / ITP
label | ee7b6ffc-be4d-5da6-bc5a-5216c48ed4db |  | note | vi. Covermeter check record
label | 1f941374-83e8-5946-a0c1-c5ce2f661818 |  | note | vii. Record of dimensional measurements
label | c41cafed-bee2-52b8-8337-94b8c8662fdb |  | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder pre-cast supply Lot (don't attach it here)
text | 77674e63-24f0-53df-9f28-9868bd45e910 |  | textbox | Reference: Precast panels MDR Lot in TeamBinder:
label | ce14dd84-b1f1-5c71-a32b-754d00c95bb8 |  | note | Method - Document Review
label | 407009a9-f554-52ae-a945-276158c59005 |  | note | Frequency - Once for each type of panels
label | 8cb3594c-9a84-5b72-870c-d167eecf1615 |  | note | Category - HP
label | 022a492e-40a5-5580-a703-ad7fd8abac5d |  | note | Responsibility - PE
label | c9ec7aa8-ab9e-57d6-a82c-f9e3e414844d |  | note | Verifying Documents - Precast panels Birth certificates and MDR Lot
date | 56790282-28c8-577a-ab63-1b2d4d0c368d |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Foundation
label | acb670cf-3fd5-5e14-a0ee-2bf50b19e738 |  | note | Reference - IFC Drawings MRP-080-C-SME-DRG-34-CPV-CSF-3007, MRP-080-C-SME-DRG-34-CPV-CSF-3012, MRP-080-C-SME-DRG-34-CPV-CSF-3013
label | 410e0616-1ab2-5829-84f9-e162915a72ea |  | note | Acceptance Criteria - Foundation material under RSS shall adhere with minimum design bearing capacity.
label | 87a1ec6b-4412-52f5-8931-4831069d206d |  | note | ○ RW2: 150 kPa
label | a85f4dda-83f3-516b-9a92-54f481d59bd4 |  | note | ○ RW3: 200 kPa
label | cc2cad46-bec4-57c3-a91d-5f78066af540 |  | note | ○ RW4: 200 kPa
label | 16902fb9-7516-5840-b7f6-250aa0001ce5 |  | note | ○ RW5: 250 kPa
label | 4b4f0d2c-53fb-53ca-81eb-302419aee36c |  | note | Method - Test, Document Review, Visual
label | 3c7d0e60-7398-5582-b2ee-8902c476489f |  | note | Frequency - Each retaining Wall
label | 4da1cda0-a5ad-53a4-87e1-eff47361c08a |  | note | Category - HP*
label | 6d97841b-276b-55e4-a450-ae703fd21bf3 |  | note | Responsibility - PE/Geotechnical Engineer, Foundation geotechnical assessment
label | 4b52cd11-bb1a-5e2b-a4b1-d96990706fae |  | note | Verifying Documents - This ITP Signed off, Test results
date | 53339517-6403-5f12-8b79-1d6e4ae33a45 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Foundation
label | 1d175881-2ff6-572f-8673-62c1ccba2b4f |  | note | Reference - VR 204.12, VR 204.11
label | f2b63a55-8346-5cd6-9a0d-59f782108a19 |  | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be test rolled in accordance with VR 173. No Fill shall be placed against or within 3 meters of a structure until the foundation for the fill has been reviewed by the superintendant
label | fcd5e6b0-68a2-53cd-9a05-c24412f7d9fa |  | note | Method - Visual
label | 69661b69-68a6-54bb-af3c-fef858e9b711 |  | note | Frequency - Each retaining Wall
label | 6d84f289-4e25-5fe9-8991-3408ef0c6a09 |  | note | Category - HP
label | 38773d48-2b2b-5afe-8855-e37ec7485fe9 |  | note | Responsibility - PE/Nominated Authority
label | 00374869-0578-5a21-a7a4-3a2f71ae9f8d |  | note | Verifying Documents - This ITP Signed off
date | 8247d857-acfe-5565-a01b-d15f7a5f3102 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Levelling Pad-Survey Set out
label | 8e04f549-681d-54f1-ae4c-dacd5ad0bead |  | note | Reference - IFC Drawings VR 682.20, MRP-080-C-RFL-DRG-33-CPV-CSW-1202 to 1205
label | 7c7a221f-c077-59f4-b6e7-46d0444d9ac4 |  | note | Acceptance Criteria - Survey to set up and validate all works meets levels and locations with the right tolerances as per IFC Drawings and Vicroads Specification. Levelling course level shall not deviate from the specified level by more than +/- 3mm
label | 066621d1-2e50-5a41-969e-243907b547ec |  | note | Method - Measure, Visual
label | 76154bb0-a254-5d9e-ac52-3c2ca370504a |  | note | Frequency - Each retaining Wall
label | 5c55c148-72fd-5395-8810-3f7fee3ebe85 |  | note | Category - IP
label | df6d9aee-248c-5be8-866d-a858f9ed6174 |  | note | Responsibility - Surveyor, SE/PE
label | b1563a43-002d-5f3c-bf04-3cadca848518 |  | note | Verifying Documents - This ITP Signed off
date | c7cb9c18-c4cd-556b-ac05-496de7165f42 |  | date | Date Completed:
checkpoint-group |  |  | section | 5. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Form Levelling pad
label | 8b10c758-5970-5044-937d-c35759210845 |  | note | Reference - IFC Drawings MRP-080-C-RFL-DRG-33-CPV-CSW-1202 to 1205
label | 47dd3a6c-5565-5a3a-8e85-949d61f943a2 |  | note | Acceptance Criteria - Form timber shutters or Earth form to edge of levelling pad
label | c4959613-2db5-537b-a353-2e094824a1a5 |  | note | – Levelling pad is a 500mm wide by 150mm thick unreinforced concrete footing
label | 7d047857-c78b-5c3f-b099-125178a94bff |  | note | Method - Measure, Visual
label | 134a063a-980f-5413-8757-0db9978bcb18 |  | note | Frequency - Each Lot
label | 94bcc02c-c411-549e-b83f-f38699457814 |  | note | Category - IP
label | 1f406090-a8cd-5847-b5f9-1aa7b1b67787 |  | note | Responsibility - SE/Site Supervisor
label | 31a40388-c323-5690-b252-91bee2312bf0 |  | note | Verifying Documents - This ITP Signed off
date | e373f9ce-3f80-5ba7-86f4-68ceb9af0417 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Leveling Pad Concrete Pour
label | 614a3988-40ff-50a2-8837-41af317b29ce |  | note | Reference - IFC Drawings VR610
label | b381b487-d2d8-5ffd-928d-f167d1902711 |  | note | Acceptance Criteria - Concrete to be placed in accordance with VR610.
label | bbd86c96-f9fa-5cce-9e5b-270d28bcbeac |  | note | Attach: Concrete Delivery Docket
label | 707ba3ee-ccd9-5165-b617-6df234a784bf |  | note | Method - Visual
label | 8445b6d8-410e-5635-afe1-3816b547657d |  | note | Frequency - Each Lot
label | 12fb176c-5197-5b28-a9ed-21d03578f449 |  | note | Category - IP
label | 8eecf2cb-80b5-5228-ad57-feec9a670d28 |  | note | Responsibility - SE/Site Supervisor
label | 7aa20989-f933-5850-8491-a92ba3bb5936 |  | note | Verifying Documents - Concrete Pour record, Concrete Delivery Docket
date | b4b42449-a834-507a-bb44-1acc0c6f83b6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Leveling Pad Concrete Testing
label | 65d049fb-0d74-5ef3-a5f3-a4e054d35a1e |  | note | Reference - IFC Drawings VR Section 610.16 (b)
label | 5341df0d-2628-5b15-81ab-db9e2504bc5b |  | note | Acceptance Criteria - Concrete testing for compressive strength shall be undertaken at the testing frequency specified in VicRoads Section 610.16 (b)
label | 8fa3486a-d4dc-5c25-b52d-888458145384 |  | note | ○ Concrete strength (Min): N25 Mpa
label | 80589885-c02c-55de-81fe-77c51f95238d |  | note | Attach: Concrete test report
label | 76d74232-9178-5dc4-b30a-512265299d2e |  | note | Method - Document Review
label | 2b79629b-e428-5b84-8bb8-7935d9bb4904 |  | note | Frequency - Each Lot
label | dadb7b20-1925-5bad-aa1a-c38a92a3f07f |  | note | Category - IP
label | 3589530b-f0eb-54e1-ac83-24adcdc02337 |  | note | Responsibility - PE
label | 73a32238-3b4f-5dea-b908-157a41f0c595 |  | note | Verifying Documents - Attach Concrete Test Report
date | 7c0cb9be-1d43-5708-a704-00fd1cb8a888 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Levelling Pad-Post Pour Survey-Levelling Course
label | 1788d0e9-ecaf-57e0-878c-ca07ba956970 |  | note | Reference - IFC Drawings MRP-080-C-RFL-DRG-33-CPV-CSW-1202 to 1205
label | 745b8f3e-ecdb-5fe6-853a-d284702d524f |  | note | Acceptance Criteria - Levelling course level shall not deviate from the specified level by more than ±3mm
label | 5a403c9d-3e34-5af8-a801-62275639a190 |  | note | – 20mm Nominal gap between levelling pad and adjacent ground beam is to be maintained
label | 4e1cb190-e451-5fc9-8b71-51a0d04cf5c4 |  | note | – Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
label | 7b3eb44c-c639-5017-a72d-adca738576f8 |  | note | Method - Measure, Visual
label | 41ea2075-c45d-5558-b605-f3fceb0aeeaa |  | note | Frequency - Each retaining Wall
label | 85d85d78-46df-5b73-a75f-036581d42c94 |  | note | Category - IP
label | a4d42980-bb8d-5947-b387-c24672e1b603 |  | note | Responsibility - PE/Surveyor
label | 5a86b060-ccab-5524-b247-60e6f1e79256 |  | note | Verifying Documents - Attach Survey Report
date | 699c987b-831f-5ffd-a87c-b897fa9ef9c1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Wall Panels Installation
label | e38ace6c-a84b-57a9-b1bb-c077b5644c3f |  | note | Reference - VR682.17
label | a843f47f-00ae-5b4a-ad3a-1962a2427e78 |  | note | Acceptance Criteria - The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The
label | d9b80e58-ff32-5a86-a8ba-badc9cdc3b27 |  | note | ○ Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions.
label | 745b30ae-298b-5944-8923-f4caa19833c4 |  | note | ○ Refer to checklist for each course of panels
label | 2c838cb1-197c-5abd-abbf-e094f6d2025d |  | note | Attach: Lot map
label | 1d1f42e0-712d-506d-9d0a-ae42f2490af4 |  | note | Method - Visual Measure
label | 5f228282-3a72-5d42-bf58-6dd884022eb3 |  | note | Frequency - Each course of facing panel
label | 464ac046-3212-5f2d-b385-afd9070230d1 |  | note | Category - HP*
label | 82eadf45-12db-52f7-a291-4fd1d7eb7048 |  | note | Responsibility - SE/PE
label | fdbacf2e-e41a-5aee-9960-b81ab75420ab |  | note | Verifying Documents - Inspection record checklist: CHK-008-STR-CPD-RSS Walls-Precast Panel installation
date | 1e05f5c6-a080-5a28-8839-b3612fc63849 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Drainage-base of the Wall
label | 8fffbeaa-6797-5b5b-a607-2e2edb045734 |  | note | Reference - IFC Drawings MRP-080-C-SME-DRG-34-CPV-CSF-3031
label | f2bb8b91-d785-5994-ace9-96c3846cf3c9 |  | note | Acceptance Criteria - to install 300mmx300mmGranular backfill in Geotextile BIDIM A24 around 100mm Dia. Perforted plastic pipewith 0.5% min fall to weepholes in RSS panels.
label | 1c83db86-93c7-5a8a-9f14-b0f4837c470b |  | note | – Geotextile BIDIM A24
label | 06e95dfb-8d58-56dd-b8b4-b2f1934f9f18 |  | note | – 300mmx300mm Granular backfill
label | 60a52c94-e505-57df-bf40-ac2d8d13e6c5 |  | note | – 100mm Dia. Perforted plastic pipe
label | 7be5ba29-6063-5db7-80dd-f7e984116884 |  | note | – Perforated pipe to have 0.5% minimum fall
label | a42da700-ce33-5aa3-aa70-d0736181bcae |  | note | Method - Visual
label | 94e8dc71-671f-5c85-83a7-511947d0e5a6 |  | note | Frequency - Each wall
label | 13c82418-6a34-531e-815d-613e2179f6ed |  | note | Category - IP
label | 405e8a44-5ba4-5de2-9256-8c17c66ee5b5 |  | note | Responsibility - SE/PE
label | 1fa42912-8311-5ca8-ac53-8f9964482d8b |  | note | Verifying Documents - This ITP Signed off
date | 3a65987a-f6aa-5838-a7b6-18184004f725 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Fill
label | 4c39f14f-83ad-5668-a3ad-66287f7719c0 |  | note | Reference - VR682.16
label | be39dc12-7412-5de3-babb-50b0ab12902b |  | note | Acceptance Criteria - The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed.
label | 79b871de-242e-5ac8-916e-6bba4093f658 |  | note | ○ Refer to checklist for each fill layer
label | d606adfe-54ac-5fd4-ae58-66ddda053020 |  | note | Attach: Lot map
label | e462a55f-1357-5fa5-94fe-ff2c1b6c2b2b |  | note | Method - Visual, Test, Measure
label | 4b17adb7-27a3-5fde-9f2f-13509428243d |  | note | Frequency - Each layer of fill
label | 99e6e588-29d5-59f9-b15e-0c463da4792b |  | note | Category - HP*
label | 8e627a26-5e17-5aa0-a0f8-f8c286d5829d |  | note | Responsibility - SE/PE
label | 02cd0653-492e-527e-9f58-1a4980453a02 |  | note | Verifying Documents - Inspection record checklist: CHK-009-STR-CPD-RSS Walls-Fill Placement
date | 00a06841-3c52-572f-a060-faa15d91f6df |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Settlement Monitoring horizontal inclinometer
label | 2e1ea935-df0e-5482-b3bb-ba66d809c6a2 |  | note | Reference - IFC drawings MRP-080-C-SME-DRG-34-CPV-CSF-3007 VR 682.15
label | 10d0a8c3-50d5-5658-92ee-faac1bdb4e93 |  | note | Acceptance Criteria - Survey Pin and Inclinometer survey procedure us as follows:
label | c66e2329-8af2-5008-b1a6-f72adbbed9dc |  | note | ○ Inclinometers shall be installed prior ro placement of any fill
label | 70b2dc8d-b2dc-583d-bfd0-6d7b8e8bbaaf |  | note | ○ RSS Wall and abutment wall survey pins shall be installed immediately following construction of the first level of RSS wall/Abutment wall and prior to any fill placement
label | 6c7c99f3-d0fd-55dc-8185-736451c22ee8 |  | note | ○ Traffic barrier survey pins shall be installed following construction of pavement and barriers
label | 770c0a8c-40f2-5fc5-b38f-fe524f6a1780 |  | note | ○ All survey pins shall have appopriate stick-up from finished surface level for continous settlement throughout construction/post construction
label | b9261bcd-c401-5f39-8cb1-05591767e950 |  | note | ○ Pavement construction shall not commence until monitoring from inclinometers and RSS wall/abutment wall survey pins indicate ground movements have reached at least 90% of construction settlements and confirmed by the geoechnical engineer
label | d498b2eb-f201-512f-accb-34e60c7c9789 |  | note | ○ Settlment Monitoring readings shall be taken at maximum one week intervals or for every one metre of fill placement (whichever is more frequent) unitl settlement stablisers or advised by the geotechnical engineer
label | 84b6f22c-e774-5057-8f67-0f276d0e46b6 |  | note | ○ If at any stage prior ro the to the completion of the RSS placement, the total settlement exceeds 50mm, fill placement must be suspendedm and direction sought from the design engineer.
label | df77d2f8-a62c-5913-8aee-515960910b4a |  | note | ○ Survey pins and horizontal inclinometer shall be installed to monitor ground movement throughout and after the RSS wall construction.
label | dc90afc2-be1b-532a-a70d-b92ddbadb55e |  | note | ○ Only hand operated equipment shall be used within 1m distance from inclinometers
label | 40d4c93a-cecb-5ab0-a312-cea03855000b |  | note | ○ Geotechnical instruments shall be preserved and protected for monitoring until the conclusion of post construction. Damaged or malfuctioning inclinometers shall be reported and replaced where possible.
label | 81de2609-af80-5b7e-8537-3538b1f4d06e |  | note | Method - Document Review
label | 9f8e254e-2ebf-52a9-891b-ca4ac48e37ae |  | note | Frequency - Each Inclinometer
label | 4ac076d1-5749-5953-9b38-a90207cf5867 |  | note | Category - HP
label | f46ea647-3411-5f3b-95e5-366faf076d7c |  | note | Responsibility - SE/PE
label | 24f82a38-0912-5de9-bd63-57b12d674b0f |  | note | Verifying Documents - Teambinder approval
date | e9f659a3-da02-58bc-aa96-e7e5985e210e |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - As-built Survey
label | 7c362dfa-70c2-5ac5-a36f-2ba48388d0ff |  | note | Reference - MRPA Quality Management Plan, IFC Drawings
label | 1bbad82a-2b7b-5f7a-8ccb-47a568286dcf |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances as per IFC drawings.
label | 7bc5895d-b2bb-5c12-bb1a-2d25b206863c |  | note | (a) Plan position shown on the drawings, at base of wall shall not exceed ±15 mm;
label | abb45417-91b0-5c54-962e-8e41616c7bb9 |  | note | (b) Relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall;
label | acf4ac3b-f471-55be-9f8c-f47f85b9529e |  | note | (c) Local deviation of the wall face measured at any location with a 3m straight edge shall not exceed 15mm;
label | ece30a9f-b0c6-5118-b3de-30ad532d3525 |  | note | (d) The tolerance on position measured at the top of the wall face shall not exceed 5mm per 1m of wall height;
label | e8d40f04-a621-5bf4-9f1e-7ffebac933d6 |  | note | (e) The wall level shall not deviate from the specified level by more than ±20mm;
label | f22f81c2-774d-5f4a-b38f-86e6c4a91bde |  | note | (f) Variation in gap width between facing panels shall not exceed 5mm per metre length and 10mm over the full length of the gap.
label | b1739066-a03f-511e-98da-c32608acbe86 |  | note | (g) The levelling course level shall not deviate from the specified level by more than ±3 mm;
label | 564abc57-5b98-5257-9e7c-e22ffe14cd33 |  | note | (h) The vertical deviation of the soil reinforcement shall be within +1% (upwards) & -0.3% (downwards) of the soil reinforcement length, relative to the connection height unless noted otherwise
label | c7f2456c-37ad-5fb6-81b4-ef26a711f2f4 |  | note | Attach: Survey As-built / Survey Report
label | efe76cb0-840a-503c-bcc2-e4abe62a16cf |  | note | Method - Document Review
label | 0c2447b0-2769-5cae-8600-34afc07e3622 |  | note | Frequency - Each element
label | 10a980df-843f-5f61-897e-e7d571d38cea |  | note | Category - IP
label | b449445d-4188-537f-b2aa-d8b6654ac822 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 1320a2b1-68e4-5765-958d-33203e7a624f |  | note | Verifying Documents - Survey Report
date | d9d4a5df-7485-5bda-8c7e-c210931c5cec |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Wall Post construction monitoring
label | 539b174b-0ee7-5424-bf2c-e16b65b7695e |  | note | Reference - IFC Drawings VR 682.20, VR 682.151
label | ad6917af-f2b1-5a52-b7ea-8f10ee46203d |  | note | Acceptance Criteria - The Contractor shall take measurements of the position of the RSS at the points defined in clause 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period.
label | e3bae21a-3934-5b79-a376-109bc7f9e526 |  | note | Method - Measure, Survey
label | c7e5be72-f95e-57dd-a497-986efc80bcb7 |  | note | Frequency - Each wall
label | 62a8c277-0b9e-5570-bf73-d7773ee6ade9 |  | note | Category - IP
label | aea8bc91-8ec6-557d-8b8c-8f10bd2e0ecd |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 03231913-6223-52bf-a8d4-0de8ac6c3441 |  | note | Verifying Documents - Survey Report
date | 74515ab0-9fae-5189-9bca-d94a9449cf9b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Settlement Monitoring
label | b8911b72-8218-5036-a046-f37017f8c2f7 |  | note | Reference - IFC Drawings VR 682.15, VR 682.20
label | 4c952ec2-9cca-527d-a67a-1829c565fc36 |  | note | Acceptance Criteria - RSS wall base level:
label | 3b4d0f97-5d83-5236-8866-55ce82ae2385 |  | note | – Start of wall construction to completion of wall construction (before pavement placement) Approx vertical settlement < 20mm
label | 09a63d85-11fa-5f2d-af86-30aa7002160c |  | note | – Completion of pavement construction to end of defects liability period (2 years after practical completion) Approx vertical settlement < 15mm
label | fc5312aa-bffd-551f-adfb-250cd6ab95a6 |  | note | Pavement level (Top of RSS wall):
label | 8224fda1-fc31-5b06-8a1a-31a2c9d24430 |  | note | – Start of Pavement construction to completion of pavement construction Approx vertical settlement < 20mm
label | aef4a9f2-ddef-5caf-92e2-fe3b6ba8887e |  | note | – 10 years following practical completion of payment < 50mm
label | 7abd0441-1349-5a2b-b24b-691eaf351019 |  | note | ○ Settlement monitoring readings shall be taken at maximum one week intervals or for every one metre of fill placement (whichever is more frequent) until settlement stabilised or advised by the geotechnical engineer
label | 8574507f-c4bc-5590-ad32-51749c9edcae |  | note | ○ If RSS fill placement total settlement >50mm, fill placement must be suspended, and the mitigation method reviewed by the superintendent and DTP before recommencing fill placement.
label | 9310ee61-7d95-5171-9f2f-d826fa51a3ca |  | note | Method - Measure, Survey, Document Review
label | a2c24ba1-e220-586d-ac92-8e56e8099e29 |  | note | Frequency - 1m of fill
label | 474a2c8c-da59-5df6-bb6c-d8fdd9eadb7d |  | note | Category - HP
label | ebaa1a6c-1d66-54a7-8084-62eae5990b33 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 24cde826-7549-5027-b984-afa260e7d2d8 |  | note | Verifying Documents - Settlement monitoring results
date | e77032d4-d88f-5d10-8311-baa5dccca5d4 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | 3a8f8f5d-729a-5aed-968b-56507b806587 |  | note | Reference - MRPA Quality Management Plan
label | 7903c01c-5d82-59ba-abab-33179c83496a |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 3854ebdf-58e8-526d-a0a6-cfae7034e29a |  | note | Method - Document Review
label | 595004da-bcc1-52da-943e-6ed4f8c709ec |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 156538f3-d68a-589d-a720-d7431c60c4e9 |  | note | Category - HP*
label | 77a91613-98d0-58e9-bdd1-23ae1c1eb819 |  | note | Responsibility - SE/PE/SPE
label | de66aa23-4612-5f14-9325-926a683bfb8c |  | note | Verifying Documents - This ITP Signed off
date | b0517ef2-cbf0-5ad9-8725-ce6088e141c8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 8c6ba7ec-3387-50e0-84fb-70b09713a11d |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 91c58319-dc15-5f4a-82b7-1f211ffcdcfe |  | textbox | Name:
text | a00407d3-93b5-568e-9869-046dd1289c5c |  | textbox | Position:
date | 28ce3d48-6c98-50b1-a920-2ce4477ded28 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation | itp |  |  |  | Yes | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | dcbcfbeb-c210-4449-9a89-a119dcf5f8e1
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | f6383529-49d8-56eb-ba06-5a01383d031b |  | note | Document Title: ITP-122-STR-CPD -Precast Barriers and Kerbs Installation
label | 5c9abf57-444c-504f-aeae-cdd52928671e |  | note | ITP Description: CPD -Precast Barriers and Kerbs Installation
label | a7c6cc13-9e0f-50cc-9188-0fa997489897 |  | note | ITP Number: 122
label | e5135bd5-42ec-52a5-ae31-6770f70488f6 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 54136beb-d494-5e74-8917-1440cb91e7ee |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 7bb2518c-f0f3-5695-bb7e-4be3bd26541d |  | note | Revision Number: 0
label | d546f5a8-0ea2-507b-9f1b-4b18b69fe2ae |  | note | Revision Date: 19/01/2024
label | 7694ff07-8845-5046-8ca1-a22ff65407f0 |  | note | ITP created by: Andrew Carlini
label | 97b9c826-d04a-5955-9101-113af18911cc |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 039fe781-83dd-5276-ba09-09a136e06c59 |  | note | Reference - VicRoads Section 610 Feb 2020
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 044524f2-02b0-5c30-843e-64d2a39ad16b |  | note | Reference - VicRoads Section 620 May 2009
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | c83d3581-d20f-5258-8021-9a95aa8a8f2c |  | note | Reference - VicRoads Section 630 October 2013
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | ba43cb52-c44e-51f1-9704-8f590cb759f4 |  | note | Reference - VicRoads Section 670 October 2013
checkpoint-status |  |  | checkpoint | 1.5 - Non Dependent
label | 6399ae26-b717-542f-8a6d-ef9843b35fa0 |  | note | Reference - VicRoads Section 671 October 2013
checkpoint-group |  |  | section | 2. Preliminaries Materials
checkpoint-status |  |  | checkpoint | 2.1 - Grout
label | c8d381c3-5677-5694-83c1-b21c57b0eabd |  | note | Reference - MRPA Quality Management Plan
label | 619dd369-9d62-53f5-88d0-e1420f0960da |  | note | Acceptance Criteria - Details of the grout to be placed between the precast elements to be submitted for review to the Nominated Authority.
text | 90526186-0ee6-588d-ba6c-0007754829d3 |  | textbox | Enter: Teambinder Material Approval number
label | dfa0979a-2190-52aa-9ce3-5f87f5abeb6a |  | note | Method - Document Review
label | d06cdcb6-ccae-52a0-89d6-699a8dc39aee |  | note | Frequency - Once, for each product
label | 1323e4f6-1c4c-5ef4-a735-2be1cd1f104b |  | note | Category - HP
label | df4bc97b-9954-5a15-988f-f2e4cec31d16 |  | note | Responsibility - Nominated Authority
label | 05ebd81f-6c46-5c69-a561-2a06515b588f |  | note | Verifying Documents - This ITP
date | 0907ca29-effc-5d86-8b6d-c64d880a3740 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Shims
label | f178c70b-fed4-5cc4-a0a2-3e2137bee850 |  | note | Reference - MRPA Quality Management Plan
label | c4ea7f71-a1ee-53bb-afb0-e50e1dce4cf5 |  | note | Acceptance Criteria - Details of the Shims to be placed beneath the precast elements to be submitted for review to the Nominated Authority.
text | c242a327-be07-5dad-ba67-4e13331b8095 |  | textbox | Enter: Teambinder Material Approval number
label | aedc183a-2216-5eda-b168-84839943b329 |  | note | Method - Document Review
label | 05fa81f7-214c-5b7b-aff4-d772bffd09fe |  | note | Frequency - Once, for each product
label | 979fc28f-e88d-58e4-b1c7-bbc502e8ba74 |  | note | Category - HP
label | 7d1f7e66-aba7-50c1-a2a2-55ed5b8a413c |  | note | Responsibility - Nominated Authority
label | 18a6c869-def1-5870-8fda-a37578262ae9 |  | note | Verifying Documents - This ITP
date | 09e06f68-e9c5-5a34-9f9d-3b68240d0bf6 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Bitumen Board
label | 21e3e88d-5dd8-5761-8a8a-22660cd9c9db |  | note | Reference - MRPA Quality Management Plan
label | b9b58b7e-8769-57c3-a7a7-30afba18ac24 |  | note | Acceptance Criteria - Details of the Bitumen Board to be placed between the precast elements to be submitted for review to the Nominated Authority.
text | 55fbce2c-7990-5b24-b747-767a57ac6283 |  | textbox | Enter: Teambinder Material Approval number
label | 8cf47468-cb1a-5172-b455-30f29c81c098 |  | note | Method - Document Review
label | 292a0c1a-452c-5f3f-b60c-e827f56a2aee |  | note | Frequency - Once, for each product
label | 5a8cbdd1-a047-5898-a3cd-f218f0fa3ce2 |  | note | Category - HP
label | e8c4ff70-db77-5732-8db3-bdbf1b52d0f3 |  | note | Responsibility - Nominated Authority
label | b5932c3b-4311-5414-b81e-271818fd0486 |  | note | Verifying Documents - This ITP
date | c80d5ac7-3530-59ea-9a33-9c5117101c58 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Abelflex
label | 38b4ff9f-7160-56dd-9aea-a46a597c1cfb |  | note | Reference - MRPA Quality Management Plan
label | b8a5d2d1-0b46-5da2-ba5d-d457e8279a76 |  | note | Acceptance Criteria - Details of the Abelflex to be placed between the precast elements to be submitted for review to the Nominated Authority.
text | 14214c45-b509-5c3a-a7ea-5824990a09bc |  | textbox | Enter: Teambinder Material Approval number
label | cf4e16b1-dd4d-5d29-8db1-37d1300d3815 |  | note | Method - Document Review
label | 3d07a681-fafa-5c2e-b3e3-080a59141c43 |  | note | Frequency - Once, for each product
label | 77e79fe5-1c75-5b46-9c30-df5c0bf432ff |  | note | Category - HP
label | 717c139c-efa1-5abc-9897-155bc48b3985 |  | note | Responsibility - Nominated Authority
label | 9b4644ca-415f-588b-818a-9b1e2a7bc3b4 |  | note | Verifying Documents - This ITP
date | c37000ad-1ba4-5812-96e7-6224f438228d |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Documents
checkpoint-status |  |  | checkpoint | 3.1 - Precast Elements
label | d07805be-8880-518c-9200-5f32dfec4bfa |  | note | Reference - IFC Drawings VR 610
label | c508fe9c-299e-554d-a15b-e2ede3136b2a |  | note | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | c0e409a3-f1de-5ec3-9f5a-57372e0a384b |  | note | i. Certificate of Compliance / Birth Certificate
label | ddf3f85c-7cc6-5e1b-a617-08d402d1c9ae |  | note | ii. Compressive strength test results
label | 9aee2bfb-46c9-5b15-89fc-029b8b06a4b4 |  | note | iii. Precast Lifting Design
label | 251debd4-fa4f-5938-9269-c1911bd8ee53 |  | note | iv. Pre-pour check sheet / ITP
label | f2ae5362-ce4b-51b6-a125-2c1b3238125f |  | note | v. Post-pour check sheet / ITP
label | f05d37b4-e45f-59dc-93f6-e71f8623530b |  | note | vi. Covermeter check record
label | d79f9f1b-7e19-5077-b4b3-1b62579830e0 |  | note | vii. Record of dimensional measurements
label | 2f3d0aef-f3fe-564e-b971-81dc98730b05 |  | note | These documents are typically stored in a MDR Lot in Team Binder.
text | 071b1615-fdff-5820-9c75-3005b50f9a47 |  | textbox | Enter: Teambinder Material Approval number
label | ebc6ac92-729c-52e2-8393-0040347ad3ee |  | note | Method - Document Review
label | d16b979d-0c9b-5b91-9bac-219203687690 |  | note | Frequency - Each element
label | 22895b96-2e7c-5c97-a4db-bd8e18203be7 |  | note | Category - IP
label | 74dbed88-f264-5368-88ef-5acc5bd36b2c |  | note | Responsibility - PE/SE/SPE
label | 4a96ab7d-5971-5761-98a3-9add1573f8ea |  | note | Verifying Documents - This ITP
date | a46a7a70-0fe9-5d2b-9793-a0e03a89f5dd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Bridge Deck / Foundation Compressive Strength
label | 25ebcb7d-591d-5c9e-8268-e606c81bbcfa |  | note | Reference - 671.03
label | 2c597354-f156-5dd2-aa68-fcccfa118b8e |  | note | Acceptance Criteria - For Preccast elements installed on bridge deck, check that the 7 day compressive strength as shown on the IFC Drawings has been achieved.
label | f2143ff4-039f-5686-87b2-58a7faf36b76 |  | note | Method - Document Review
label | c6ca7946-d0ac-5728-88e2-814f45415aec |  | note | Frequency - Each installation location
label | c5e08dd0-9eb1-5007-8f1e-c5e369841dbd |  | note | Category - HP*
label | 52f8c2f7-6118-5fd8-b2c8-91cab75aa73f |  | note | Responsibility - SE/PE/SPE
label | 0ec87aa1-f127-53ce-a24b-3d49a0b11344 |  | note | Verifying Documents - This ITP
date | aba0e334-dd71-55b9-a52c-1ce9b134b14f |  | date | Date Completed:
checkpoint-group |  |  | section | 4. Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - IFC Drawings
label | e37db948-2665-50bd-9128-6abb70702539 |  | note | Reference - MRPA Quality Management Plan
label | 6a0ec849-08af-56a7-b0e2-113d4adf6e37 |  | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | b745af10-29a3-544c-aea8-152efbc1959e |  | note | Method - Document Review
label | ac430811-9391-54c0-b4a8-0f8594e6b6a1 |  | note | Frequency - Prior to starting Works and at regular intervals
label | ba528a03-ab05-5f2c-93eb-f6ea0d3deec5 |  | note | Category - HP*
label | ac5b1d0a-b9d5-5709-adb6-e33abe6180a5 |  | note | Responsibility - All
label | b78e7b1c-b70b-53b9-bc80-9ba6fc1a74b5 |  | note | Verifying Documents - This ITP Signed Off
date | 0f8c14ca-4075-51d5-b2b1-33eef2018f3e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Survey Set-out of Precast Elements
label | a48747ab-b45c-59f4-92a4-ccca276aaba4 |  | note | Reference - IFC Drawings
label | ff5772f8-9349-5c04-9c87-ace9263472b8 |  | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances.
label | 9b63a396-4ac0-5a47-a2c1-b2e8fc445d1d |  | note | ○ Where anchor bolts are cast in to the concrete, ensure that these are within tolerance.
label | 4d0dad05-753a-57d6-aee4-f6725dc943ed |  | note | ○ If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
label | e890f311-3439-54a7-93bc-35105d3b396c |  | note | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
label | 90c3e77b-0bf4-5a69-a2d0-a76dd04a881d |  | note | Method - Measure, Visual
label | b7618d06-41b0-5cea-87fc-b9b9e99b93db |  | note | Frequency - Each element
label | 4fa6ddb7-a2a9-52ea-86ba-856efd6326af |  | note | Category - IP
label | 3210137a-6d46-5ea0-93ab-0b5261ff2495 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 13ce24e6-13c9-5e2d-b0fc-87a9ad5b742f |  | note | Verifying Documents - This ITP
date | 037eea51-3acd-5c0e-a38a-ed61e3f1adb9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Bearing Shims or Bearing Strip Placement or Mortar Pads
label | 2bb11bef-286e-55a8-924a-04f6175d69a8 |  | note | Reference - IFC Drawings
label | 560f2b28-fac3-589f-80a5-b9a8cdc4b642 |  | note | Acceptance Criteria - Place the bearing shims, strip or variety of shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
label | d502ee49-70ce-54a1-ac18-1e0046d98074 |  | note | Note: If the precast elements are to be grouted, the minimum and maximum thicknesses of the bearing will determine the product for the grouting activities (usually 10mm min.)
label | 5535a376-c680-5067-b1bc-38f367cc546b |  | note | Method - Measure, Visual
label | eca329f5-e9f3-5357-a4ee-51a21572255f |  | note | Frequency - Where applicable, each installation location
label | a9fe7921-956d-58fd-888e-e12e1f672b4b |  | note | Category - IP
label | 57b3b62c-d9fd-5c1f-ba5b-f3b7d6a90538 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | e5b3fdef-65d7-5eea-a8b0-5eef3a1d34ec |  | note | Verifying Documents - This ITP
date | 45d8d7ea-6a23-5b8e-880e-a84c05f22bcd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Bitumen Board and Ableflex placement
label | cede9589-61c7-5871-abfb-cc552eab3b5a |  | note | Reference - IFC Drawings
label | 32e2dda7-3552-58b5-96ea-d20111c42931 |  | note | Acceptance Criteria - Adhere any bitumen impregnated fibre-board and ableflex into the positions shown on the IFC Drawings and where grout or concrete ingress will affect the end use (such as around conduits).
label | 39b9c2d0-b2e6-56ab-9036-a39154ade0ea |  | note | Method - Measure, Visual
label | 6312929f-2d1a-5756-a116-5e2f74fbb9cb |  | note | Frequency - Where applicable, each installation location
label | 1920d53a-c5ff-58e2-bc49-4b811abbb173 |  | note | Category - IP
label | 8d6f5d5c-dfff-5dcb-86b2-a71269f9e0d5 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 009af049-21b5-572f-b2bb-540954eb21cb |  | note | Verifying Documents - This ITP
date | db836cb4-8e42-5ac2-ab8a-8ccd529377aa |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 - Precast kerbs roughened surface
label | 604639ae-b4dd-5ffe-8a79-eb385a0f1ecc |  | note | Reference - IFC Drawings Section 610.20
label | 7fca641c-2afe-5e4f-bd85-61f63a318825 |  | note | Acceptance Criteria - Roughened surface means concrete surface shall be roughned as construction joint in accordance with IFC drawings and VR Section 610.20
label | 2c93be35-48a3-5bf4-994a-c965d472bec3 |  | note | Method - Visual
label | d350928f-2a9f-5ff6-aae8-93cfb9dbc541 |  | note | Frequency - Each element
label | 7271d59c-ff5e-579e-8472-d8e5e809be25 |  | note | Category - IP
label | cb29ff7e-ce3b-5f78-a22a-9c294cfea18d |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 4a3b3760-2a2c-54fc-bb78-8de2fcb3202f |  | note | Verifying Documents - This ITP Signed Off
date | ac8928c1-429e-55ec-9782-f1cc6c0a6d42 |  | date | Date Completed:
checkpoint-group |  |  | section | 5. Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Precast Handling
label | 1b05d33c-5e30-5d5b-b9d3-cb7aea2f68c8 |  | note | Reference - 620.07 Crane Lift Study
label | 8b5235d5-ff31-55b2-a3a4-6a04f0a2e4ad |  | note | Acceptance Criteria - Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | 2ffdb81b-fee6-5a86-aa0d-db6a098000d6 |  | note | Method - Visual
label | c57a54d9-1b01-586b-a6fc-ef33eb0c52df |  | note | Frequency - Each element
label | 535d1f66-43a5-58ad-8005-a2dbb480f07a |  | note | Category - IP
label | 9b33ff38-2182-5bb1-ae84-20f04a738d9a |  | note | Responsibility - SE/PE/SPE
label | 5795b6d1-bb15-567e-96c0-d7e69da033d5 |  | note | Verifying Documents - This ITP
date | 815d4b7d-c0e1-5fcc-b72e-ffce79be8880 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Precast Placement
label | 09287f00-8b53-5976-9337-41143fbc46f1 |  | note | Reference - IFC Drawings VR 670.05
label | 5e0df7b1-5013-5998-8919-c8cdb417513f |  | note | Acceptance Criteria - Precast elements shall be placed onto the bearing shims and not released from the crane until sufficiently braced or restrained by bolted connection, in accordance with the approved temporary works design and/or IFC drawings.
label | 6a735383-c07e-5004-b306-cfe0f3c8ddf4 |  | note | Adjustments to be made to achieve following tolerances:
label | 4fbfaec4-dc2e-5cf6-a245-f522a807d909 |  | note | (a) Departure from plan position .... 25mm
label | a53e3333-00a6-57cb-bec2-a73dc738a7e8 |  | note | (b) Departure from alignment ........ 5mm
label | abb86bb6-383b-5a47-a940-2c7b1f1a12fa |  | note | (c) Irregularities in alignment ......... 3mm in 3m
label | 56d59de2-f16d-59dc-9e35-5a386a877379 |  | note | (d) Variation in joint gap width ....... 3mm
label | 019b0ed9-1e36-57f3-8dd6-f4e336f0d342 |  | note | (e) Vertically of posts, panels, balusters and openings ... 2mm
label | cbd38737-91a2-5213-baa1-e6ee812fbcd1 |  | note | ○ The nominal gap between elements is as per the IFC Drawings.
label | 08d2951a-0fa7-5881-81b7-10df7c63b578 |  | note | Method - Measure, Visual
label | f0778c63-c904-5455-a04b-f7e153be66d5 |  | note | Frequency - Each element
label | ea1ebd64-c37d-50f1-9f3b-0c6bef2e6424 |  | note | Category - IP
label | 3ce0406c-f01b-5969-8d85-f6dda85847cd |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 62cca861-2810-5909-883d-007f3fdfa3a4 |  | note | Verifying Documents - This ITP
date | d991d9c3-cf97-5b7a-98b2-ac1a407feadc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Hold-down Bracket Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
label | 1819b323-7a0b-5794-8379-a43e5ca2c7ab |  | note | Reference - IFC Drawings 630.20 (a) & (c) AS5131 Clause 8.3
label | 067993dc-7c87-5cae-b4f2-efdbfcbe8e3c |  | note | Acceptance Criteria - Place washers and nuts onto the embedded thread as detailed on the IFC Drawings.
label | cac3936e-049c-5b18-b35e-2c75bb294153 |  | note | ○ Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
label | db5a2d51-c086-5d3d-b1fd-e98402ed3ace |  | note | ○ Tighten with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
label | d0e8018c-887b-546b-9a8f-b2c8cb11b3d4 |  | note | ○ Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | 77539608-2b04-53d6-a288-62ef5f645722 |  | note | Method - Visual
label | f619ad8e-9b34-560f-8d86-56d868970f3d |  | note | Frequency - Where applicable, each bolted connection
label | 38eaa1e8-5485-54d7-ba1a-77d92ecdab4a |  | note | Category - IP
label | aaa4dc79-66da-55ed-9820-3c6a5303c6e9 |  | note | Responsibility - SE/PE/SPE
label | 75d0b9ac-9ac5-58e4-afa3-1c284bf97715 |  | note | Verifying Documents - This ITP
date | f86bc712-e3b0-51d4-a0ce-6331e9e21161 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Precast Traceability
label | f57ab36e-fa41-533c-af8e-2aca81cb706d |  | note | Reference - 620.09
label | 855415d0-324e-56da-bb43-24f196d348dd |  | note | Acceptance Criteria - All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
label | 018c7c76-1693-560b-8dc7-0d8308351e61 |  | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
label | cf6b1ecb-fc6c-5c78-9125-acf056b1e7fc |  | note | Method - Visual
label | 63584100-4f9b-5094-92f5-aa34de8df9b5 |  | note | Frequency - Each element
label | c5bd0559-8955-5c80-8942-610181b4210f |  | note | Category - IP
label | d2dc337c-25e5-53c1-8e36-d09558e21c21 |  | note | Responsibility - SE/PE/SPE
label | c63867e8-b7d9-54c1-a8c1-1bd784eb995b |  | note | Verifying Documents - This ITP
date | bfde12e4-6966-5408-90e6-eab6ef5b525b |  | date | Date Completed:
checkpoint-group |  |  | section | 6. Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - As-built Survey
label | 6391522d-8675-5de3-9ef9-455f4752ee2b |  | note | Reference - IFC Drawings VR 670.05
label | 40f36976-ae58-56ce-9b23-cc3cacdc3966 |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per VR 670.05
label | 9ead845a-4420-514c-b706-6ee5feef7412 |  | note | (a) Departure from plan position: 25 mm
label | 53bd0c4d-c12e-5111-86d1-74937de01e1a |  | note | (b) Departure from alignment: 5 mm
label | 98a83268-a7a2-5183-9f6f-e227811eab67 |  | note | (c) Irregularities in alignment 3 mm in 3 m
label | ac36c247-edca-53e8-86a4-aa58dd3a15f9 |  | note | (d) Variation in joint gap width 3 mm
label | a99f9905-8064-5e3c-a030-54f929687048 |  | note | (e) Verticality of posts, panels, balusters and openings ±2 mm
label | 7d6a32ba-4059-574f-8b3e-7f872aa7cd20 |  | note | Attach: Survey As-builts / Survey Report
label | ea8ed7cb-4dea-58d2-8e7b-fe5ea5a32e2f |  | note | Method - Document Review
label | 783a39e2-b346-5f38-8490-9a9569294984 |  | note | Frequency - Each element
label | 0d5354f8-1c12-5c32-9733-7dfa866010a3 |  | note | Category - IP
label | 1bace8ee-fd6b-5618-8faa-c06420d6b3f6 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 8a55d85b-b889-58ca-bbc4-800a7e38f7d5 |  | note | Verifying Documents - This ITP
date | de0445fe-e505-5dcf-bd39-d74acae4851c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Non-conformance Report (NCR) Closure
label | d94c852a-a02e-54f5-bf3c-dc1d6191c2e8 |  | note | Reference - MRPA Quality Management Plan
label | a75337cb-98b0-5ff1-92e5-39db13135af2 |  | note | Method - Document Review
label | 62c989ec-cdb1-515b-ab5f-58567acf4e85 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 6a9c1117-dc1c-5dae-9e4a-83973aed63bd |  | note | Category - HP*
label | a14fc6db-799e-5881-aa03-68ae06d92059 |  | note | Responsibility - SE/PE/SPE
label | 25acb7a9-c4a7-580b-9590-e3fe85648549 |  | note | Verifying Documents - This ITP
date | c7808271-5247-568c-a6d2-4250fd9cf123 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | f12f50b2-c77d-5a98-b848-4989b4be79f3 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 40a2eb17-650f-5c71-bf39-8e87ef3d6538 |  | textbox | Name:
text | fd402052-0efe-5e9f-a365-10cc009651ee |  | textbox | Position:
date | 9597eef7-0f27-542a-a396-490dd82acaf2 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-112-STR Precast L-shape Wall Rev1 | itp |  |  |  | Yes | ITP-112-STR Precast L-shape Wall Rev1 | e5994219-ee26-4a50-8c5d-8685118d3ed1
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 5c2f115a-3b6b-5bd9-a9dc-def0dbda79df |  | note | Document Title: ITP-STR-Precast L-Shape Wall (Supply & Installation)
label | 778d05de-8b0a-513b-bd6b-2ea23bd87281 |  | note | ITP Description: Precast L-Shape Wall (Supply & Installation)
label | 551997e1-1215-51b0-a503-90be43e01791 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | f4e2d6d5-8767-5ca5-8cf5-4fb44537169a |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 11c40e23-eb08-5b21-a76a-261ccc5d3421 |  | note | Revision Number: 1
label | c108933d-9345-5cb8-b280-a68d70975981 |  | note | Revision Date: 4/12/2023
label | d2d918ec-faf0-5bee-86b7-c18a7b018338 |  | note | ITP created by: Matthew Dib/Jason Quan
label | 5aa195f2-d45c-53af-a7c4-c67af7b20c94 |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 2b6ed922-1c00-5a64-8e2e-7dfe068b852c |  | note | Reference - VicRoads Section 610
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 29518ce6-45cc-5f98-bfa8-1d2d59e5a6d4 |  | note | Reference - VicRoads Section 620
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | 971e2381-6bc5-5f3a-9b17-801af1328f4b |  | note | Reference - IFC Drawings
checkpoint-group |  |  | section | 2. Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 - Precast Elements
label | 7e43c90f-fffe-5e01-ba0c-189d860631a0 |  | note | Reference - IFC Drawings 610.47 (a) Table 610.474
label | 4513d817-6537-537b-a50b-9db5cd9015ef |  | note | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | cb430eb8-5103-57a0-9e11-822555044b82 |  | note | i. Certificate of Compliance / Birth Certificate
label | f217dfde-308e-573d-a170-d0959185e3a2 |  | note | ii. Compressive strength test results
label | 59968e3c-1a56-530c-b65f-559f297d0f3b |  | note | iii. Precast Lifting Design
label | 58a5be56-c275-58f6-b3e1-8179e537e44b |  | note | iv. Pre-pour check sheet / ITP
label | 33cce3fc-8ae1-5bec-9278-f0dc529915e4 |  | note | v. Post-pour check sheet / ITP
label | e8a90ae5-abc8-5156-875e-10b58b1ac25c |  | note | vi. Covermeter check record
label | eb67e935-787e-526e-aaf0-8056dc9b2481 |  | note | vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown on table 610.463 (November 2018) / 610.473 (March/June 2019).
label | 219beefe-f283-567c-b4c8-f25d6ac9f416 |  | note | Note: Different revisions of 610 have different clause numbers
label | c15c11ec-30ca-5aeb-bae3-f87b18c64080 |  | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
label | 1b059c1b-30ad-5eed-bd77-d3924495f2b3 |  | note | Method - Document Review
label | fa812c37-0be1-5fcf-a210-acc2b62a9e86 |  | note | Frequency - Each element
label | 4af7a4b4-6152-52dc-b8db-7eb73ccd9163 |  | note | Category - IP
label | 0146191e-f88c-5551-ae7e-9f145e8e90e2 |  | note | Responsibility - PE/SE/SPE
label | 1ce28ac0-563f-5c5d-a3b2-695b639b4fff |  | note | Verifying Documents - This ITP
date | 9d23dcb2-9802-502b-9be2-2e075ed68f21 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Joint Sealant
label | 76baec38-64ae-5835-b76e-b22b252fbefa |  | note | Reference - MRPA Quality Management Plan
label | b3e4b4aa-e0b9-50f5-b62e-a32ee4868aeb |  | note | Acceptance Criteria - Details of the joint sealant used to seal around the precast element to be submitted for review to the Nominated Authority.
text | 267e650c-8119-5b73-96a5-da3b795691cf |  | textbox | Enter: Teambinder Material Approval number
label | d8f7fbff-6846-58d7-b0bd-c33736ade3d0 |  | note | Method - Document Review
label | 40a0c0ea-5332-54bf-b4ca-bea7165b9ebe |  | note | Frequency - Once, for each product
label | 46924b02-c733-5b98-88be-7857076b5bc9 |  | note | Category - IP
label | 2ffcf096-08ff-5a53-8b7c-0c87254d58a0 |  | note | Responsibility - Nominated Authority
label | 383fc283-f1e1-5709-b1bf-e5b57a310963 |  | note | Verifying Documents - This ITP
date | 47df4a6b-2835-5e2f-b5f1-741ca2c18156 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Foundation
label | 73ba0b36-9d5a-5601-8fd4-49f1e494c2b7 |  | note | Reference - IFC Drawings
label | a008bb9e-025b-5e23-bac8-cbb74ab2a397 |  | note | Acceptance Criteria - Foundation material under L-shape wall base slab shall adhere with minimum design bearing capacity of 200kPa and shall exhibit a minimum unndrained shear strength of 80 kPa. L-Shape wall shall be founded on 0.5m of Type B Structural fill
label | d6edf79c-47d2-50a9-8289-a611330a9a76 |  | note | Method - Document Review
label | d1d02242-5e05-5a71-90cd-a6caccf471d2 |  | note | Category - IP
label | b606a5b4-6bcc-5f17-ac39-7635fab9d300 |  | note | Responsibility - Nominated Authority
label | 3aacb8a4-924e-5aaa-a4d8-c8a166813cbc |  | note | Verifying Documents - This ITP
date | 78b9d5cf-e599-5aee-87b5-dadc75546f55 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Architectural Finish
label | 02a1ccf8-9852-5760-9dba-bce492c20fa9 |  | note | Reference - IFC Drawings
label | d77e2c39-e89d-5eb9-8c57-63464ee58126 |  | note | Acceptance Criteria - 50mm Thick Architectural finish. 20mm Thick Dummy Joint in Architectural finish.
label | 41b0c114-5841-5129-ac2c-a7d622430d34 |  | note | Method - Visual
label | 0df6e7a3-e0b1-5662-8fb1-8576e507d94f |  | note | Frequency - Each element
label | 118246c2-5fc5-5fc9-9bc3-ff6db19eaa1b |  | note | Category - IP
label | 9121ebb7-5bfb-5535-ae59-43f1c7371d6e |  | note | Responsibility - SE/PE/SPE
label | 499a6aa4-6bfd-542b-a971-74feda7286b3 |  | note | Verifying Documents - This ITP
date | e243bbc8-0a7b-5df6-bda9-5738bc47bfed |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Precast Traceability
label | cb14e508-c62b-5483-8efb-0190eb388972 |  | note | Reference - 620.09
label | e1610e8f-f9a3-59c6-adda-d4a5b0f101e0 |  | note | Acceptance Criteria - All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
label | 1a194a12-b971-523c-ac6f-350591ba1ed2 |  | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
label | d83a12bb-09a9-5342-ac51-85ea7d01e56b |  | note | Method - Visual
label | d5718f86-c9be-5e74-830a-50cbb1d3d853 |  | note | Frequency - Each element
label | 63aa8fc4-81a5-511a-9579-e181aff7ce3c |  | note | Category - IP
label | 55a372fa-cd4e-5e4a-9f36-de16672031eb |  | note | Responsibility - SE/PE/SPE
label | ab57a5c1-cb66-556c-be86-248ee3f9d7fa |  | note | Verifying Documents - This ITP
date | 0bb98fe4-763e-5fa7-b1c9-e64a9377a61b |  | date | Date Completed:
checkpoint-group |  |  | section | 3. Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 - Survey Set-out of Precast Elements
label | 9581c9c6-4409-539c-af2d-6a99f65a4afb |  | note | Reference - IFC Drawings 610.47 (a) Table 610.474
label | e8a9ccfc-a1eb-53cf-8236-4015caa73f1f |  | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.474 as applicable to the element.
label | 1e9a8d03-6cb3-5da3-9aa3-6ad04587256a |  | note | Method - Measure, Visual
label | 72334d6a-bc35-5b82-93be-560b6c763253 |  | note | Frequency - Each element
label | 5e5aebf4-7bd3-55d2-9c99-3659c190df12 |  | note | Category - IP
label | a060f8e8-4e6d-5e56-8de2-8bed733af010 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | fbaac7b4-fc88-596c-9c38-2ebe6ed047a3 |  | note | Verifying Documents - This ITP
date | f0c13d93-9e89-53f2-9a81-9b53ec5a87a1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Blinding Concrete
label | ffba990e-59c9-5190-a16d-4ffaa1a7c24c |  | note | Reference - IFC Drawings
label | f73d8c13-4aaf-5e32-b234-07e425ae35dd |  | note | Acceptance Criteria - Blinding concrete shall be placed, leveled and surveyed. Provide stiff broom finish or rougher, Minimum N15 Concrete 50mm thick
label | 72b1296b-9c60-5ea1-8f16-0482203e3a33 |  | note | Method - Measure, Visual
label | 4bffd5b2-47ed-5a0f-96c9-8bcb4c7e915a |  | note | Frequency - Each element
label | c13ca6f0-a8f9-5705-b04f-e221faef8324 |  | note | Category - IP
label | 90703554-5836-57d2-81c9-30edbd99303d |  | note | Responsibility - SE/PE/SPE
label | d194ad2b-5a4c-54ce-b10f-4f6e61dd9304 |  | note | Verifying Documents - This ITP
date | 312724c1-cc02-55f5-8d4c-9110c73d6215 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Packers
label | ec844503-5b8a-544b-bab2-fbce5303ea03 |  | note | Reference - IFC Drawings
label | dc99223f-a52d-51e6-a4c8-d9e3deff479a |  | note | Acceptance Criteria - 100x100 min non metallic packers shall be placed on blinding concrete
label | 840765bd-53ce-5282-a9a6-756842d30ca1 |  | note | Method - Measure, Visual
label | 7c86bb0a-4bd7-539f-9315-175b0e3edeac |  | note | Frequency - Each element
label | bd5d402d-4612-545e-9ef1-ce160b09f20d |  | note | Category - IP
label | 3072606f-50a7-555a-a74e-e0101cb3621a |  | note | Responsibility - SE/PE/SPE
label | 351c2feb-a6fd-5061-9794-9e867dea907c |  | note | Verifying Documents - This ITP
date | 2957d0bc-e2ef-5675-aeab-141a61d55bd1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Ferrules
label | e8d9d5b2-bbd8-55b8-b82d-10304b76aa6b |  | note | Reference - IFC Drawings
label | 57f87267-79ba-58e6-9c90-a924f92ccd5d |  | note | Acceptance Criteria - Ferrules are installed as per IFC drawings
label | ef998869-579f-59fa-845c-019379c1d3b7 |  | note | Method - Visual
label | fe3edc8f-0b41-57ee-810d-c468ae249842 |  | note | Frequency - Each element
label | bb84192f-8150-55b6-8310-d6894402f166 |  | note | Category - IP
label | d1176d02-4505-553e-ac7f-85bd7cac6251 |  | note | Responsibility - SE/PE/SPE
label | d49f9e2b-1487-57c8-b1b4-99762ebf0401 |  | note | Verifying Documents - This ITP
date | 55add579-81a4-5342-89a3-c193d6c69940 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 - Materials Inspection Checklist
label | 5f515491-321e-555e-b937-a3ad83c3a9ce |  | note | Reference - 620.06, 620.07 MRPA Quality Management Plan
label | 29274d99-0ef2-5866-b189-2b5eb36d567b |  | note | Acceptance Criteria - General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings.
label | e0904ab5-e14b-56c9-bace-3e4bcfb9df27 |  | note | ○ Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to).
label | 307ada0d-d6bf-5670-bec6-0f8bc2c586ec |  | note | ○ Elements shall have unique identification and orientation marked (if applicable).
label | 8b1f9cd3-5e37-52e0-a741-cf14615ecbc6 |  | note | Complete: Materials Inspection Checklist in ConQA
label | f8a43ae2-2be5-52da-a84f-d525401309ad |  | note | Method - Measure, Visual
label | 0b692649-b48d-5ac1-8d1f-6e1cbbfde581 |  | note | Frequency - Each element
label | bfb4dc1a-bb16-5ef5-bb0e-f5b9352df542 |  | note | Category - IP
label | ea0d9616-5990-5c2d-bebc-b16aa7861fb2 |  | note | Responsibility - SE/PE/SPE
label | 4d5e08e5-ec46-551f-81eb-ab25d9c89864 |  | note | Verifying Documents - Material Inspection Checklist
date | 839a233c-3a64-5a6e-a43d-19a2e70d6a10 |  | date | Date Completed:
checkpoint-group |  |  | section | 4. Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Precast Handling
label | e21777cf-abd5-5971-add6-c2c0f9c5d4a4 |  | note | Reference - 620.07 Crane Lift Study
label | 556181e1-ac3b-512f-a1dd-1ea0595c1fe8 |  | note | Acceptance Criteria - Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | 6c9bf39f-74ce-5345-be65-cb858de0d518 |  | note | Method - Visual
label | 07119e75-51f3-56ed-ab3b-8e0079493c17 |  | note | Frequency - Each element
label | d06e09cd-89ef-5ca2-9a60-e7f15b7cb3e9 |  | note | Category - IP
label | cc49a420-52a9-5566-b283-300421d337c7 |  | note | Responsibility - SE/PE/SPE
label | 42cb4e10-4f6b-5a83-83d4-b0ee2694ac12 |  | note | Verifying Documents - This ITP
date | 628d0df6-551b-58f4-a4f9-a867fb46967e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Precast Placement
label | af5a7017-3c8e-5f4b-b540-206121c86a02 |  | note | Reference - IFC Drawings 610.27
label | df23c2be-6d86-56b0-8684-afcea014def9 |  | note | Acceptance Criteria - Make any adjustments necessary by lifting the unit and adding/removing shims or adjusting the levelling bolts so that alignment between units, overall height and position remains in tolerance.
label | 868cfbc1-54e0-52c9-80be-5e5f3bfdb3cc |  | note | ○ The nominal gap between elements is as per the IFC Drawings.
label | 0d29c38c-c437-5d99-b2ef-c865b7576eae |  | note | Method - Visual
label | 0c2d1071-dbff-52c2-b3c3-edd827a0db0e |  | note | Frequency - Each element
label | 0f701b51-0f15-5760-b34d-e383dfca97cc |  | note | Category - IP
label | f9418b5a-2c4a-5427-8c85-f60a07b1bd31 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 46d014ef-591f-5b2c-95f0-457ae133c4a8 |  | note | Verifying Documents - This ITP
date | 827de890-4a9c-5019-a32f-16b639ef0264 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Flowable Grout
label | 626b975f-fd36-500a-b346-181621f35a1f |  | note | Reference - IFC Drawings
label | 23f40d6c-d9ba-5b41-8311-500996cabd16 |  | note | Acceptance Criteria - U.N.O All cementitous grout shall be a flowable type C class dual shrinkage compensated grout with a minimum compressive strength of 40 Mpa
label | 46c5521a-5a3f-5252-83f7-d8b227a65f61 |  | note | ○ 50 NOM gap between precast wall base and blinding shall be flood grouted.
label | 8c287916-8ef9-528f-857d-e47e75a3dfa7 |  | note | ○ Backfill and compaction may commence after Grout has achieved 10 MPa Min Strength
label | aa449747-d38e-5798-977f-3e67928e90aa |  | note | Method - Visual
label | 23dca991-59fa-530c-9649-d36c5ffa0266 |  | note | Frequency - Where applicable, Attach Concrete Test Result
label | b5015452-d657-5fc3-9031-7ae56bbe9c66 |  | note | Category - IP
label | 0d2de902-37d8-551c-89e4-efc2fe657ef5 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | bda1a941-f839-5eaf-8dbd-6a75c10147ba |  | note | Verifying Documents - This ITP
date | 36c0e3be-076c-5086-87d3-6a05137806a0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Panel Joint - RSS and L-shape wall
label | 828ea906-4d8a-57a3-8553-c77e5142c5e1 |  | note | Reference - IFC Drawings
label | 54abe26c-d41b-528a-928d-1286f227fe3b |  | note | Acceptance Criteria - The gap between each precast element or at interfaces with other structures should be sealed with an the approved filler. Install compressible filler with backing rod both faces.
label | 09e227ee-02f9-587a-abb7-07c4f73be0e9 |  | note | ○ 300 Wide Bitac Multi-laminate tape centrally over joint between RSS wall and L-Shape panel.
label | 50a257dc-ff05-5c3d-805d-1719637f3488 |  | note | Method - Visual
label | 9d040eb9-d5c7-53ba-95e6-bd56aa3d642f |  | note | Frequency - Each element
label | e555ed88-f2b5-5094-925d-a8a0a7243b2b |  | note | Category - IP
label | 74cee11b-217a-527d-8bb6-5cbe908e2a40 |  | note | Responsibility - SE/PE/SPE
label | 796ac34a-024d-5fba-a668-76973a4f755f |  | note | Verifying Documents - This ITP
date | 449595f2-b9e0-5771-a225-e3a75c2fd6e2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 - Drainage
label | 2506ba36-6aa5-5c4a-bef1-339f7de76743 |  | note | Reference - IFC Drawings
label | eab2be06-9d05-5a5b-b883-165969b7b945 |  | note | Acceptance Criteria - Drainage Weepholes to be installed as per IFC Drawings
label | afffdd62-5fbc-57ea-8180-8ac4c42f32f4 |  | note | ○ Install 50 Diameter uPVC Pipe with 0.5% min fall.
label | 54c36984-3d33-5bb9-833e-c8b0df82ad6d |  | note | ○ 300 Wide Strip vertical strip drain (Prodrain PD40) positioned centrally on back face of panel
label | dce3681a-2ac0-516d-8d60-87026d5ffa2d |  | note | Method - Measure, Visual
label | b415b154-58dc-5ae7-8266-ccf9b20f880a |  | note | Frequency - Each element
label | 64f487fa-e8f8-51d4-9b12-91abc238501e |  | note | Category - IP
label | 8e9f244d-edbc-5fcc-9fb9-1512f0ecc4b8 |  | note | Responsibility - SE/PE/SPE
label | 01cbddfb-f7ed-5c8c-84cd-91cabf613c16 |  | note | Verifying Documents - This ITP
date | 79dcc89c-d37e-5847-83cf-68888981d97b |  | date | Date Completed:
checkpoint-group |  |  | section | 5. Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - As-built Survey
label | 1dd54b46-2021-52ba-812d-fef9dc829b16 |  | note | Reference - IFC Drawings 610.47 (a) Table 610.474 (Feb 2020)
label | 4cbbb080-b1a1-5357-82a3-d48ff9f6672b |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.47
label | cab54a28-1a05-52b1-8b47-610fa4856af5 |  | note | Attach: Survey As-builts / Survey Report
label | bcd156b5-7499-551d-bf25-837bb61a6ff1 |  | note | Method - Document Review
label | b2b9329f-c2e3-58e2-afd6-7566ebbb8986 |  | note | Frequency - Each element
label | c72e4186-a76c-549d-96b4-af9715878e7c |  | note | Category - IP
label | 8484fb0f-b358-5a1c-8a85-804cd468c972 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 3540b731-5f8e-5678-b901-15563051ef21 |  | note | Verifying Documents - This ITP
date | bb46a365-2941-564a-8f72-5a833baedcf8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Non-conformance Report (NCR) Closure
label | 970e375f-621a-5ec9-a630-327a3f7406f8 |  | note | Reference - MRPA Quality Management Plan
label | db839d34-6ef5-5708-a8b9-ac2ce75639da |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 3371a286-5dc1-5131-9fd9-1cc20a6d0508 |  | note | Method - Document Review
label | 2255eff1-a65b-506c-ab72-078ed26d926d |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 5208162c-9c58-526b-bca2-978c7747733e |  | note | Category - HP*
label | fcc1f980-6b98-5561-a0d2-371ff362c607 |  | note | Responsibility - SE/PE/SPE
label | 9c32d3c3-b4b9-5a88-89f5-253b575ac562 |  | note | Verifying Documents - This ITP
date | b65ca038-7f91-5deb-988a-f6c2357b3052 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | b4aa91e2-aa05-54ad-bb8e-ff2972eee94e |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | fd7acf0f-cfcf-5b58-a4ab-ebc30da69b44 |  | textbox | Name:
text | 0d29112d-75a0-5ee0-bea9-a5001ebcefd9 |  | textbox | Position:
date | eaaa6851-f6d4-54e7-b2c4-637c39a2baf3 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-114-CIV-CPD -Jemena Conduit Bore Rev 1 | itp |  |  |  | Yes | ITP-114-CIV-CPD -Jemena Conduit Bore Rev 1 | ed0e2f56-d2df-4917-be48-3e6b6c25ffee
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | e99cf2d2-30c6-58c1-bef4-3c43b10a229c |  | note | Document Title: ITP-114-CIV-CPD-Inspection & Test Plan - Horizontal Directional Drilling
label | 67f5be0f-97bd-5c3f-ad24-1ba14bb81308 |  | note | ITP Description: Jemena Conduit Bore
label | df085331-598c-5a61-b7c7-e5f42c8e2aaa |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 61d7e18d-1a16-555a-acaa-f8bca90748a1 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 6736d612-d6d4-512f-9b18-bce960cd9cd4 |  | note | Revision Number: 1
label | 71f2a565-3225-5d1e-96a1-a3d4386618bd |  | note | Revision Date: 12/12/2023
label | 4581dbf0-fbd3-5a7f-a61e-ff3cdbcfbc2a |  | note | ITP created by: Lachlan Morris/Pat Sabaruddin
label | fc634587-72f9-59d0-9330-b6102770b4a3 |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - IFC Drawings
label | 68903ee5-f6a1-5d06-bc44-f9789ad400f5 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
checkpoint-status |  |  | checkpoint | 1.2 - VESI D&C Standard
label | 8a4b3509-54ab-5326-9219-ce75c4d5bd31 |  | note | Reference - VESI_URD_003
checkpoint-status |  |  | checkpoint | 1.3 - Plastic Industry Pipe Association - Industry Guidelines
label | db364956-70e0-5004-be28-0686111ecc57 |  | note | Reference - PIPA POP 003
checkpoint-status |  |  | checkpoint | 1.4 - Australian Standards
label | 6eae4cf9-ef8d-527a-a8ab-6ea25b5c422c |  | note | Reference - AS 2033, AS4142
checkpoint-group |  |  | section | 2. Preliminary Works/ Materials
checkpoint-status |  |  | checkpoint | 2.1 - Electrical Conduits
label | 906afc69-f8a7-5d48-9682-ca57689aefa3 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003
label | 2acc479c-d45d-5ae1-b7fb-ba0002b47a2a |  | note | Acceptance Criteria - Conduit Grade PE100, SDR 13.6
label | 44340154-40fd-5c51-b72f-ca905cedd0ed |  | note | Reference:TeamBinder Material Approval Number:
label | 5474e9cc-baa9-54c6-9e6c-7d597e657ca8 |  | note | Method - Document Review
label | ae5d14dd-8324-582c-8138-0965a60bc2f1 |  | note | Frequency - Prior to commencement
label | 17a59224-6ac1-5fac-8feb-dea03fc502f7 |  | note | Category - HP
label | b95ccf83-7f13-5428-bf7a-0ba32ead4b2f |  | note | Responsibility - PE/SE
label | 59b47f2e-de72-5619-8f58-48788a16f282 |  | note | Verifying Documents - Teambinder approval number
date | 0a0ae259-f9cb-5e48-86af-5535c2be972f |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Grout
label | 3e4ea3c6-b320-579c-a4e1-4196c854fd8d |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | d619d962-48a5-56d3-bedc-4360e8054d13 |  | note | Acceptance Criteria - N/A
label | c3911137-8046-5455-94a8-edd3b8f01b2a |  | note | Method - Document Review
label | 7bbb0c3d-46dc-5408-8861-2dfb20a464d2 |  | note | Frequency - Prior to commencement
label | ea69a55c-bc20-52f3-8847-cb2307b629a2 |  | note | Category - HP
date | c5048fb7-fb20-5b64-bb1e-4992b098ab27 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminary Works/ Procedures
checkpoint-status |  |  | checkpoint | 3.1 - Check that current revision drawings are being used
label | 526500e9-582a-5230-95de-b785cd788e8a |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | e4ebf4ad-4cfc-5870-b506-351a62ba2edf |  | note | Acceptance Criteria - Drawing revison must be confirmed with the design manager
label | e86b54b6-cdf1-5b75-885a-b0a6980ac541 |  | note | Method - Document review
label | f372b4fb-5d00-5aeb-b963-b8d3e5e5a1e5 |  | note | Frequency - Prior to commencement
label | eb7ec909-bb18-5041-92ec-ff1f26285317 |  | note | Category - HP*
label | 0753249b-30d8-5804-826a-2a5ebbfd5a5a |  | note | Responsibility - SE/PE/SPE
label | 42d3bf9e-6746-5385-80c0-588b1f3b3bcc |  | note | Verifying Documents - Design drawings.
date | 0b56e4b2-7795-5e60-9059-1e006a52341e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Auditor accreditation
label | f70c3f3b-f32c-538f-aa06-130d1e94a4d8 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003
label | 67d5d173-4e3b-5a00-97ec-de029562f4ef |  | note | Acceptance Criteria - Auditors are to be VESI accredited
label | 32f74ca1-f4e5-5737-872f-2dbc0300abb8 |  | note | Method - Document review
label | dfc63961-d09d-5b6d-ba9b-d9e45bb53de2 |  | note | Frequency - Prior to commencement
label | 8f593e91-1c95-5c89-854b-be595541b445 |  | note | Category - HP*
label | 7887a15e-e703-561a-a3cb-a240c3fa6a02 |  | note | Responsibility - PE/SE
label | c6ebc7a7-93cd-58f8-a36b-f99c95b3f1fb |  | note | Verifying Documents - Teambinder approval number
date | 3ade642d-e974-5804-99f2-ccc2a5cf4e3c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - PE Welders Qualifications
label | c0a93a96-2802-5cb8-a972-4ae45a9b8633 |  | note | Reference - AS 2033, PIPA-POP-003
label | 22f6b648-c64a-5595-b19a-dbda4934c334 |  | note | Acceptance Criteria - PE welders are to be qualified and regularly certified by a suitable RTO to PMBWELD301E
label | e1cb521a-8483-5c97-af1c-3fd97f786596 |  | note | Reference:Teambinder Hold point release number:
label | e55c3390-6106-58a9-9ee6-d2ede7b54777 |  | note | Method - Document review
label | 849804fd-592b-57f5-adef-7b0d0b417fa4 |  | note | Frequency - Prior to commencement
label | c2e1f59d-cf47-5fc7-80f4-aa693d4e0ffe |  | note | Category - HP
label | faae7862-6e63-5ebb-b742-ef6e45ef70fc |  | note | Responsibility - SE/PE
label | 9a1329ed-c99a-54d3-8c9a-07e5ef5cbe16 |  | note | Verifying Documents - Teambinder approval number
date | b076ef38-c4aa-508e-9a44-ea1528978473 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-out
label | ccd02d0b-1e2c-5c2a-92be-53729d1aff40 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003; cl5.10.13
label | 7db81439-1769-52c5-a9d8-d489eebba60d |  | note | Acceptance Criteria - Set out line and level of drilling works.
label | 86b562ab-6bff-575b-886d-4e9ca544cbe5 |  | note | Method - Set out line and level of drilling works.
label | 2308aab4-2554-5e0d-89c4-5e734a9ab3dc |  | note | ○ Survey to mark out existing services.
label | c9381ae5-1ead-5cc1-8d54-4612bc78bbbc |  | note | ○ Must maintain a min. clearance as per VESI D&C 5.10.13.
label | c30b0bed-f157-5e2b-b870-03ed29d6710c |  | note | Frequency - Measure, Visual
label | cd392fe7-fcab-5fe6-bde1-d3db69026d25 |  | note | Category - Each element
label | fdc4b033-bc1a-5e59-b13b-fe64c84d0da6 |  | note | Responsibility - IP
label | 709469a6-645a-5e34-9b16-022cbddd26ab |  | note | Verifying Documents - Surveyor, SE/PE/SPE
date | c05e1525-6646-5646-a268-7e0dd1ed902e |  | date | Date Completed:This ITP
checkpoint-status |  |  | checkpoint | 4.2 - Draw ropes
label | afcf164e-21dd-58bf-a9a5-7dd620b1c908 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, AS4142
label | cd36b161-9117-5e59-a005-e8f512337bda |  | note | Acceptance Criteria - All conduits must have minimum of one 6mm polypropylene draw rope to AS4142.
label | 4bc42dab-37cb-5fd9-a54c-e6b8c2922b28 |  | note | Method - Document review/ Visual
label | 21eefa28-cf19-5b12-80b5-9662131c8488 |  | note | Frequency - Prior to commencement
label | dbbc3444-5e63-5d68-aff3-59696ab7ce1f |  | note | Category - IP
label | 21bcbc76-ff5e-5e2b-bdd5-884d2de57d53 |  | note | Responsibility - PE/SE
label | b23a1352-ee0a-515e-98a2-df24ca9c89e1 |  | note | Verifying Documents - Material compliance certificate
date | 020410c0-cb55-5250-8822-aca504691d3e |  | date | Date Completed:
checkpoint-group |  |  | section | 5. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Conduit welding
label | 4ce25c27-e154-5773-948c-0d1bf38ec272 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, PIPA-POP-003
label | fed80b2c-4994-5693-983f-73199e4cae9e |  | note | Acceptance Criteria - Joints are to be butt welded.
label | 9faf490c-7455-5ff8-aa67-34cee2dd0a84 |  | note | ○ Weld map to be supplied and identify unique joint numbers.
label | 0d4e6933-a8ca-561e-9569-73ac61afb929 |  | note | ○ Butt Welding records to be supplied.
label | 647da021-29cd-5ea4-8767-0b0b02464fe1 |  | note | Method - Document review
label | 78db6a44-7cbf-5797-aa10-6eb4fefffde0 |  | note | Frequency - All Joints
label | aa66a2c7-1164-5017-af0e-80f635d37cfe |  | note | Category - IP
label | 15883d1f-31c5-5f8c-ba69-6b09c0a3fe51 |  | note | Responsibility - SE/Site Supervisor/Survey
label | 3e88b158-b927-5a42-b397-d88956086e95 |  | note | Verifying Documents - Sign ITP, Butt Welding Records
date | 775f27f6-8c93-5f70-840b-5211e1cee124 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Drill rig setout
label | 4b2ef03f-f0ea-524b-8640-fce7489fd8c4 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | 6d6b56c7-3cc2-57b7-bd40-cc044adc5ed6 |  | note | Acceptance Criteria - Location as per current Drill shot plans
label | e9045223-c39a-553c-9f64-39514c8ea575 |  | note | Method - Measure, Visual
label | 5d73ba72-0da0-55bd-a8a7-9e37df5dfb49 |  | note | Frequency - Prior to commencement
label | ad654842-dc67-5d23-8983-d38048d5f163 |  | note | Category - IP
label | a5fdf361-b6e0-5520-b0a3-6437708215b7 |  | note | Responsibility - SE
label | 68402971-158d-5935-a44a-30b23b7b0a17 |  | note | Verifying Documents - This ITP
date | 98ff112b-abeb-56e9-8766-44fc9e02f5a9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Installation of Pipeline (Trenchless method)
label | 598f9a73-6093-5e34-9f87-84b7ebec0577 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003
label | 6ba82f20-47e6-5626-8556-6e92733c6dc8 |  | note | Acceptance Criteria - Drill to be installed as per the survey setout.
label | bf9b96fc-aaa4-5bfa-a43c-1ee6c0ed7e3d |  | note | ○ Bore logs to be supplied.
label | c02e1055-440f-56d0-a948-f817ed34fee1 |  | note | ○ When multiple conduits are installed into one bore hole care shall be taken to ensurethe conduits do not rotate during installation. Accurate detailing of conduit positions must be undertaken.
label | 129d6e15-558b-55b9-9fec-981052286476 |  | note | Method - Document review, Visual inspection
label | cd66787c-3854-5411-ada5-824535138845 |  | note | Frequency - During pilot bore and conduit installation
label | efb091ef-011a-5ee9-8e08-0a3fe5d55beb |  | note | Category - WP
label | 41c4ce52-10c0-5467-8cad-d2395c0569a8 |  | note | Responsibility - SE/Site Supervisor
label | 241e41fb-5c13-5df4-9c23-b3c2aa672b14 |  | note | Verifying Documents - Bore logs
date | d0b33ab9-ce98-5760-ac2e-612b81f28532 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Plug pulling
label | e766b8fd-9cdd-5df0-916a-10e5a1219b00 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | 6911bd1a-844e-58ce-ba01-40fe351993d0 |  | note | Acceptance Criteria - Mandrel with 90% of the pipe diameter to be pulled thrugh each conduit to ensure the conduit hasent been compressed.
label | 7313b3c8-f1ff-5923-8fd5-48bbf81d3e41 |  | note | Method - Record and Review
label | 602a9987-a96c-53a2-ae76-83734432dc97 |  | note | Frequency - All Pipe
label | e7430db4-d77f-502e-866f-294e67d94cbb |  | note | Category - HP*
label | 33916ad1-c74c-560e-9c46-065b924f5c9f |  | note | Responsibility - SE/SPE
label | bbcf6bfd-c0eb-5ba0-b977-091785d0e99b |  | note | Verifying Documents - Sign ITP, Visual of pipe pull pictures. Subcontractor Test Record
date | d19a3f4b-7aa5-5a7c-a54b-e0d04614a75f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Draw rope
label | 4bc12696-75cc-565e-b454-eeaecdad5a3b |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | b7288165-5256-563d-afc8-c74e37de3f94 |  | note | Acceptance Criteria - All draw ropes must be continious between shafts and have 2m slack in the shaft.
label | 7c4bb466-d403-583d-8748-33d833b55330 |  | note | Method - Visual
label | 9c113881-67fc-55c1-bb2f-85be3ccb3ac2 |  | note | Frequency - All Pipe
label | f35c0d98-ff94-576e-b4ee-a288374ca474 |  | note | Category - IP
label | 3d68ca35-2809-50c3-868b-743cbd463586 |  | note | Responsibility - SE
label | 6b413113-84f5-5a8f-8e7d-4b933fb4e39b |  | note | Verifying Documents - Sign ITP.
date | 2e46d822-ea6f-544f-b984-d9482bc52afa |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Auditing
label | 77bca45c-0a78-57b7-9687-2fdc9255a922 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | 116635f6-a946-5c86-a3f0-bfde470cc344 |  | note | Acceptance Criteria - Auditing to be completed on conduit ends prior to backfilling of entry and exit shafts.
label | 12939338-8c93-5eb7-940e-114d8d44abce |  | note | Method - Record and Review
label | ca234e3a-2a96-514b-8154-cd6a0b7a545e |  | note | Frequency - All Pipe
label | 3bcf3ccd-47b7-513f-b65a-2529596a2db9 |  | note | Category - HP*
label | 65739fc3-b013-582f-b31d-18447b0471e2 |  | note | Responsibility - SE
label | bc90cb0f-2e8a-5aa6-8110-9f76b460b055 |  | note | Verifying Documents - Sign ITP, Auditing Report
date | 0eb2f303-b9d8-5e1a-b171-ade3cc815773 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Reinstatement
label | 0675fd44-dd19-5c4a-bfcc-e80958bfaaa9 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | 9d5542c7-7113-5bb8-8a21-5ca5fc071739 |  | note | Acceptance Criteria - Entry pits, exit pits and trenches to be backfilled with Type A or crushed rock. Backfill material shall be compacted to the same density as adjacent material or as specified.
label | 8855e73b-7018-5fd7-8c25-f27a6aa61611 |  | note | Method - Visual
label | 2c790064-5080-52e7-b002-0c43dbeb2400 |  | note | Frequency - Each shaft
label | 23775305-ceb4-5ff1-bd7e-0096ab87c339 |  | note | Category - IP
label | 7ec05128-ca93-5b37-98f3-297af6416371 |  | note | Responsibility - SE/Site Supervisor
label | 0c99032b-d013-57df-8d36-10fe985bc752 |  | note | Verifying Documents - Sign ITP
date | 9230cb13-abf9-59df-a5f9-d8de0e34a047 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Subcontractor ITP
label | f7054897-a74a-56be-a846-27a8ae6211e5 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | 842e69c6-03c9-5b45-b074-3b11c6881beb |  | note | Acceptance Criteria - Acceptance and closeout of subcontractor ITP
label | 7558f78d-225e-527e-af76-cd07e13ade3f |  | note | Method - Document review
label | 881fd6d2-322d-5db7-a9eb-23dd10b7c2b5 |  | note | Frequency - Each element
label | d27fe65b-124b-5bf8-afab-c4352ec44802 |  | note | Category - IP
label | 907385f4-ad58-5274-a3d7-371b03ead775 |  | note | Responsibility - SE/SPE
label | 8bdd7c51-ec65-541e-825b-fbea17fb609b |  | note | Verifying Documents - Sign ITP Completed
date | ef6773d3-2daf-5887-9770-99ad9effc581 |  | date | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - As-built Survey
label | 4c3f0d0a-b7e1-5045-be52-e4ab917074f3 |  | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | 168d00d2-5b51-5367-a274-b3539ededfff |  | note | Acceptance Criteria - Survey as built report to be compiled.
label | 01603476-25a5-53a4-8089-0463446a60e7 |  | note | ○ Borelog obtained from subcontractor
label | 8c6ed733-f5db-5c30-aba4-f2e5842047ce |  | note | ○ Autocad and PDF reports are to be supplied to:
label | d094d9ee-1068-524d-99b7-c45a55ff33d4 |  | note | Method - Document Review
label | fb1cfc7f-ab58-5e48-909a-739e3cab9baa |  | note | Frequency - Each element
label | c14af921-b599-5fda-a8d4-a54866a9400d |  | note | Category - IP
label | ffb53cfd-2c9f-5a9e-bd70-2e149bae0f9c |  | note | Responsibility - Surveyor, SE/PE/SPE
label | a422a380-4dac-545d-b38d-45da0dd7e7f0 |  | note | Verifying Documents - Survey As Report
date | b9a5d7bf-ad64-5314-9ed6-b25261b877a9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Red-line / As-constructed IFC Drawings
label | d621ffbf-f4e6-562b-a177-504d31a12802 |  | note | Reference - MRPA Quality Management Plan
label | e676c5db-5014-547d-9e42-5a48eb0d27b8 |  | note | Acceptance Criteria - All RFIs, NCRs and changes to the IFC drawings are captured on a controlled drawing set marked "Red-line", "As-built" or similar.
label | ea13b683-d49d-56c8-a72a-2ad6072fe852 |  | note | Method - Document Review
label | c0f5d327-c7da-59c8-82c9-57cc94f17e97 |  | note | Frequency - Once, after construction of the design package
label | 6299a18a-0c4f-574b-b3dc-52b8bd742917 |  | note | Category - WP
label | 488dff39-365d-5f11-8245-36a2b92fe1ca |  | note | Responsibility - SE/PE/SPE
label | f868facd-b069-542e-955b-163fed5845bd |  | note | Verifying Documents - This ITP
date | 33fd4b8b-7e38-54d8-b7a0-e068194b1bea |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 40ad701d-75f0-5791-bde1-1dca940a14a6 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 8ba6ec3b-7260-56cf-82bc-baedff33b8db |  | textbox | Name:
text | bfdd0459-cfe1-5068-8c40-27106bb3800f |  | textbox | Position:
date | 59d384c8-4839-598c-8f17-e433b2600813 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-055-CIV-CPD-Conduit & Pits-Rail (Supply & Install) | itp |  |  |  | Yes | ITP-055-CIV-CPD-Conduit & Pits-Rail (Supply & Install) - Rev 0 | ee98f55a-f499-409c-a25c-ac3c6a9d17f9
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | d574efd4-ae65-577c-8f36-b253727c2e98 |  | note | Document Title: ITP-055-CIV-CPD-Conduit & Pits-Rail (Supply & Install)
label | 0e346702-12a7-5fff-b8e1-8446c0b3b1c5 |  | note | ITP Description: Conduit & Pits - Rail (Supply and Install)
label | d215155f-81ff-52e8-b169-f142c50ba78a |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 3939086a-5226-54e2-95bb-ce728f55cc4f |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 3ce57144-ec29-57e5-ad0d-b28455374f10 |  | note | Revision Number: 0
label | 15de89f3-76c2-5184-87af-10d6a7b23638 |  | note | Revision Date: 4/08/2023
label | db21fc11-ca47-5c1f-8eb3-963ae41db11b |  | note | ITP created by: Andrew Carlini
label | 17e349c7-4521-52a7-a0cf-ec6a4974126e |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 700c534b-d66c-5720-b337-23bd8e85c2ee |  | note | Reference - IFC Drawings L1-CHE-STD-043 (VRIOGS 012.2.1) L1-CHE-SPE-070 Australian Standards MRPA Standards
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Conduits
label | adda807a-ac2c-5131-95df-260c5add916c |  | note | Reference - HV Conduit: AS 2053, HV Conduit (boring): AS 4130, Comms Conduit: AS/ACIF S008:2006, LV Conduit: AS/NZS 3000 - 2000. L1-CHE-STD-043, L1-CHE-SPE-070
label | 641e28d3-a4a6-5fa1-b3de-129b42980852 |  | note | Acceptance Criteria - LV & Signalling: 100Ø (114mm OD), orange electrical heavy duty 5.9mm wall thickness
label | 2ad198a9-daf3-57a3-b6e7-94848db131f2 |  | note | ○ LV & COMMS CONDUITS TO HAVE A MIN 600mm BENDING RADIUS
label | fd55a62f-8c2b-5cc6-9f61-e59c79bf4925 |  | note | ○ Inspect materials upon delivery and attached delivery dockets.
label | a414aed1-ee27-5902-8fe3-c955e274455d |  | note | Method - Visual, Document Review
label | 2dc4ce3b-6496-5123-a6cf-528a1feafce2 |  | note | Frequency - Each Material Type, Each Delivery
label | b1e6392e-0a69-5f54-911d-d68df12eec36 |  | note | Category - IP
label | f9fbfead-bc3e-50b2-8248-b531e1569ffb |  | note | Responsibility - SE/PE
label | ac4286c5-11cb-5c11-97dc-a3e2ff9c8035 |  | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
text | 8ae9671f-ecfb-52d6-936e-6c6629e382f1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Pits and Pit Lids
label | 5a2b71e2-aeb4-5842-836d-e5c22f3db003 |  | note | Reference - IFC Drawings VRIOGS 012.2.1 Section 6.15-16, VRIOGS 012.2.1 Section 6.9, VRIOGS 012.2.1 Cl.6.7 (c) L1-CHE-SPE-070 Cl.10 AS1289
label | 8e0c8c84-808e-521d-b47b-20baa8abb5d8 |  | note | Acceptance Criteria - Pits:
label | 2ba34af4-eae6-5e7f-8564-fc1360054418 |  | note | ○ Pits located within 1.5m of nearest rail, pit to be 300LA Railway loading
label | 00d89f1f-ff61-5d12-a523-dcf5c908bee1 |  | note | ○ Pits 900x900mm or greater, multipart pits lids to be used.
label | 397b2ab5-52ac-52d0-a02a-99f1091d4004 |  | note | Pit Lids:
label | 6a7cb99d-b793-5063-8d62-b9fa3a16bbc5 |  | note | ○ Pit Covers shall comply with AS3996-2006
label | 5dfe8848-8465-5782-bf1b-9a17f5bd312e |  | note | ○ Pit lids in trafficable areas to be Class D, non-trafficable areas to be Class C.
label | 01ea0439-4a0c-5f4e-90de-51a1d95c6d9d |  | note | ○ LV, Comms Cover: pit covers shall be labelled with the words “RAILWAYS SIGNALS & COMMUNICATIONS” (L1-CHE-STD-043 14.6)
label | 228eb118-fe5b-5679-ab30-dfb17a518fa1 |  | note | ○ Inspect materials upon delivery and attached delivery dockets.
label | 3e1cdd0f-f6ba-51bf-b195-5730b4e1b780 |  | note | Method - Visual, Document Review
label | 22003fba-5c13-5142-8fd2-e2d56322f224 |  | note | Frequency - Each Material Type, Each Delivery
label | 0ea1de73-44ad-5115-bf3c-e1463d998309 |  | note | Category - IP
label | f9b48deb-5708-593b-841e-471a76a1a888 |  | note | Responsibility - SE/PE
label | 9e49cac3-6eb9-52d6-9933-8c04b786a9c2 |  | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
text | 23d54b23-4ef6-50e0-a002-63795f327098 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Warning/Marker Tape
label | 81322cb4-fb9b-566d-a1a5-23b2cc751a0d |  | note | Reference - IFC Drawings AS/NZ 2648.1 TS-SP-013 L1-CHE-STD-043 6.4
label | 177bcef4-9d12-5df8-ac98-952330e76d8c |  | note | Acceptance Criteria - Warning/Marker Tape:
label | e7a554ba-76fa-58b6-af2d-9fb5ceff60af |  | note | Above LV:
label | 068f767f-0fc1-5e8d-9e52-154ca2294b5d |  | note | ○ 150mm minimum wide orange coloured PVC
label | e5423953-b56c-538e-8cda-30cc2f27b69b |  | note | ○ ‘DANGER RAILWAY SIGNALLING CONDUITS’
label | 62c87c4d-caea-5e44-97a6-e2cc8696b950 |  | note | Above Comms:
label | 1aaa33f0-1ddb-50c8-ba9e-0cd1dc43a833 |  | note | ○ 75mm minimum wide white coloured PVC
label | 90bb46ae-0a50-537b-b900-481bf0a0e297 |  | note | ○ ‘WARNING COMMUNICATIONS CABLES’ with an embedded stainless steel trace wire to be laid directly above trenched VicTrack assets
label | e18c2a58-1b69-5405-bc5b-e02400443ea6 |  | note | Above HV:
label | 667b80b6-2b57-5bae-8d69-43d1a4a5f5d1 |  | note | ○ 300mm minium width orange coloured PVC 'Danger - Electrical Cable Below'
label | a13d5dad-11ed-5423-8d90-523db7729ffb |  | note | ○ Inspect materials upon delivery and attached delivery dockets.
label | 8246514c-c6c3-5dc9-a6c1-1247a06e69f5 |  | note | Method - Visual, Document Review
label | 92e2f927-3749-52f8-b351-3e46f711ed51 |  | note | Frequency - Each Material Type, Each Delivery
label | 0b44d18b-032e-534c-991e-73089137eccf |  | note | Category - IP
label | 51b3c154-84a3-5557-98b4-1b5c2ef8185c |  | note | Responsibility - SE/PE
label | e3b7bf58-1770-5e93-ac66-73fe45488051 |  | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
text | dbc7ad92-4ef6-5dbf-9fa7-b0bda4d41cb2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Protection Barriers
label | f3168ab3-1588-585c-b331-cca86a14873a |  | note | Reference - IFC Drawings L1-CHE-STD-070 10.3.3 AS4702
label | 088bdbf5-25fe-5f73-b445-3f9d03c21013 |  | note | Acceptance Criteria - Protection barriers shall be polymeric cable protection covers complying with AS4702 OR a min. 40mm thick concrete barriers (pavers) not less than 15MPa at 28 days
label | 95c43c6d-d061-53ea-99f6-97138cc812bd |  | note | ○ Inspect materials upon delivery and attached delivery dockets.
label | f3b9df6e-5228-501c-8e4c-5e52f7cf1cc3 |  | note | Method - Visual, Document Review
label | 3f526150-ac73-5840-b772-2a10433adc3e |  | note | Frequency - Each Material Type, Each Delivery
label | 5800ab40-e139-503c-8eba-7ce86b1ecae3 |  | note | Category - IP
label | bbbfbaba-abc0-5063-b81f-f96d843d495d |  | note | Responsibility - SE/PE
label | f0db990e-5907-5adb-8395-916e0f2fbeaf |  | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
text | 17516c59-4539-58b5-81f8-3c16e72e22b4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Backfill Material (stabilised sand)
label | a4095bee-1b38-5faa-8d65-3bab95828070 |  | note | Reference - IFC Drawings, L1-CHE-STD-043 Section 2 Table 1
label | 3d88d363-a112-5329-8d68-c20519686407 |  | note | Acceptance Criteria - Material free of rocks that will not pass a 30mm sieve. The material shall be free or organic matter or anything that could dmanage the conduits.
label | d40f9be1-1cb4-5efb-a5ed-b39e07a2410e |  | note | ○ Inspect backfill material.
label | 8990036b-a781-5223-b5f4-36e607b82d94 |  | note | ○ Attached delivery dockets (if applicable).
label | 288a02cd-f330-5062-b692-0088c2786dd6 |  | note | Method - Visual, Document Review
label | d567bd72-ac03-55ad-b563-90de126f2fc6 |  | note | Frequency - Each Material Type, Each Delivery
label | 436df35b-a50b-51d8-8944-0e4b9ea1660a |  | note | Category - IP
label | 4d8576a0-3d27-59a6-a8c6-23192ebee22a |  | note | Responsibility - SE/PE
label | ad07a356-62cf-5142-9db0-40e1be211b10 |  | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
text | 62919031-e79c-5d11-a056-7a28a0a50896 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - Bedding Sand
label | 5d2d8ad6-0283-5e6b-bf72-fe94f760e0c7 |  | note | Reference - IFC Drawings AS2758.1
label | 2b1dd650-d6e2-5e6a-829d-96eb9cdea7f8 |  | note | Acceptance Criteria - Bedding Sand shall be a clean sand that is an uncrushed fine aggregate to AS2758.1 and shall have a thermal resistivity ≤ 1.2 °Cm/W at 5% moisture content.
label | 1dcd8f0f-d9be-5339-88cc-8457094006dc |  | note | Method - Visual, Document Review
label | dad097f9-26a7-5c45-a254-30c811dab74e |  | note | Frequency - Each Material Type, Each Delivery
label | facdc3db-7b75-55a7-9fc1-c0ab9f341c92 |  | note | Category - IP
label | fb3f4156-cb40-5483-bc4d-729c3bde7653 |  | note | Responsibility - SE/PE
label | 2f252b55-8443-5185-99dd-9d1bbab1fb23 |  | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
text | 8cdae23a-759f-5eec-b077-d5be044d8a65 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Draw Wires
label | 0f61742f-2d8a-5ff6-acd3-13d9feadf38c |  | note | Reference - TS-SP-013 AS 4142
label | 1732fa4e-2f8d-5120-8527-23dad8a2018f |  | note | Acceptance Criteria - 6 mm diameter polypropylene blue/yellow
label | d11d5b4a-e8a8-5727-b13c-141fbf112420 |  | note | Method - Document Review
label | 9985d47c-af0a-5ac1-aa94-ab13f61536e2 |  | note | Frequency - Each Material Type, Each Delivery
label | a2b44d4a-b56d-555e-9e76-f3b32e1010f2 |  | note | Category - IP
label | 309035bd-6091-5495-9a26-2a9988b9a287 |  | note | Responsibility - SE/PE
label | e4fd4868-6b84-5fb5-b632-bafbe11e82c9 |  | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
text | ae06fbdd-2580-5ce9-8ab9-4edf2a99c372 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 - Concrete Mix - Trench
label | f09cb20e-9e0c-5d09-a71c-8f616caac142 |  | note | Reference - L1-CHE-STD-043
label | c1758b37-f8f5-5579-bd5b-3f266fd70f48 |  | note | Acceptance Criteria - N/A
label | 352fc044-65f9-52c7-bd44-5e54040a3f4a |  | note | Method - N/A
label | b2e9fd7a-7a4d-5a01-8f62-32826ba23586 |  | note | Frequency - N/A
label | 249e00d4-2d5c-56b9-8518-8d9ee519afda |  | note | Category - N/A
label | 3939c5ea-1736-5823-9346-d7f9693172b9 |  | note | Responsibility - N/A
label | 120ece0a-ecf5-5d6a-ba78-1f28512e149c |  | note | Verifying Documents - N/A
text | cdd8c11f-2684-52b7-a3fe-8b8abbab728e |  | textbox | Date Completed:
checkpoint-group |  |  | section | 3. Prelimnaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Services
label | 10592b48-0888-51f1-a807-1bfed85b1143 |  | note | Reference - Services CAD file
label | f04260c8-f036-5644-8316-05a0bcaa61d6 |  | note | Acceptance Criteria - All services within 5m of Excavation location have been identified and appropriate control in place (refer to MRPA Excavation Permit).
label | 1f91c915-cc1a-5226-932b-d2b31a10364d |  | note | ○ Survey to mark out existing services.
label | cbfb6c8b-a507-596c-bdc3-be7e784474f2 |  | note | Method - Visual
label | d4decad2-ca0d-54ea-a5f9-86b56725c039 |  | note | Frequency - Prior to commencement of works
label | 474aa9e9-30a6-5af3-aeb9-2e1eb12b9107 |  | note | Category - IP
label | 7160db47-3e2d-560c-a8e8-de0d193dd936 |  | note | Responsibility - SE/Site Supervisor
label | cc293ac5-9031-5254-bc62-36d93bce4e40 |  | note | Verifying Documents - This ITP
text | 6c4dff34-fc15-5b53-a688-5c461423c08c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - CSR Works Procedure
label | 3f780eb8-3bad-5bff-ac91-94761f1afc29 |  | note | Reference - WAP_CPD_254
label | 18db5f7f-3efe-5bd7-9713-fa52735f82f0 |  | note | Acceptance Criteria - WAP to be reviewed and signed by all relevant stakeholders along with Rail Safety highlighting works proedure with in the Rail Corridor
label | e145eee5-a827-5eac-8d1b-61c81743a18e |  | note | Method - Document Review
label | ef997b0c-9663-5265-957f-1855c48a13bf |  | note | Frequency - Prior to commencement of works
label | 8861eb41-a5b3-5bb1-aba8-2305181d43e7 |  | note | Category - HP*
label | cf353dbf-e1f6-53c8-a293-5356b683923e |  | note | Responsibility - SE/Site Supervisor
label | 08937bdd-eb45-50aa-a3e8-d9f9a6c94a81 |  | note | Verifying Documents - This ITP
text | 7bdef42d-8851-595d-a36b-edeaff63d926 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 4. Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-out
label | 280f7842-2107-557a-9099-3c8f7688f5b8 |  | note | Reference - IFC Drawings
label | 1ab1d630-2ff1-5297-8965-6c018fbeddc5 |  | note | Acceptance Criteria - Survey to set out trench alignment and pits, and establish construction control (alignment and level).
label | 97420f9c-eac0-53e4-b078-4a02e0c551fc |  | note | Method - Measure, Visual
label | c8fba9b8-1004-5af3-b25f-76131d46159d |  | note | Frequency - Each element
label | c9c95446-196f-5396-b79e-38461fe7afe8 |  | note | Category - IP
label | af43c15d-4ce3-583d-b328-9e8388647c93 |  | note | Responsibility - Surveyor, SE/Site Supervisor
label | d5ac35ad-87e6-5192-bb2b-62a74cb22731 |  | note | Verifying Documents - This ITP
text | 1aa5020d-3efb-5ccf-afef-dd10f3a19f24 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - IFC Drawings
label | c4f6c505-b815-57d1-8a80-e185aa0b0754 |  | note | Reference - IFC Drawings
label | d1263639-8a8c-56d9-a54b-302fa6a40597 |  | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 24835c94-aa10-5192-9caf-4cc4aef3770b |  | note | Method - Document Review
label | 9d29eb8d-5e17-5760-8d8b-b0da9ebf1610 |  | note | Frequency - Prior to commencement of works and at regualr intervals
label | a4dfc6d9-6b14-513d-bcb8-fcdcf2889d45 |  | note | Category - IP
label | f461ecaf-c155-50a9-bdcd-d6cac30a22c0 |  | note | Responsibility - SE/Site Supervisor
label | c8ed7922-a6ff-5152-918d-6c33c3e4de27 |  | note | Verifying Documents - This ITP
text | 6456aa3a-ec76-57e5-9ca8-54757e1e8a10 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Trench Excavation
label | eafe2cec-edd8-5851-baaa-65984714dd1f |  | note | Reference - IFC Drawings L1-CHE-SPE-070 7.3 Table 2 L1-CHE-STD-043 L1-CHE-STD-070 7.1c
label | 49da775b-5a2c-54da-93e9-f5fe9e473888 |  | note | Acceptance Criteria - Trench profile and depth as per IFC drawings.
label | 26b6a76b-ce11-5280-b227-4172134cb1ef |  | note | ○ Edge of trenching to be a min. 2m from strucutres/pile foundation (unless it is mounting the structure) and a min. 4m from the rail for HV and 3m from the rail for LV & Comms
label | a0d4c894-6777-5133-90c5-d2d13161acb9 |  | note | ○ The bottom of the cable trench shall be level across its width and free from any protrusions and rubble that could cause damage to the conduits.
label | e6acfa55-b7ec-5408-97b6-938162db8efc |  | note | ○ The width of the trench shall be not less than 200 mm (chain or bucket excavation) or 300 mm (backhoe and other).
label | 1d4e5e63-53be-5e06-b29c-c427696e1c85 |  | note | Method - Measure, Visual
label | 70443a86-d9ca-5db1-ac8f-c88e8fa21e34 |  | note | Frequency - Each lot
label | 02f91683-dcea-588f-a18a-c693fd031530 |  | note | Category - IP
label | 6f553e96-fdbc-521e-b453-7fb0e7bc4919 |  | note | Responsibility - SE/Site Supervisor
label | f426a83e-7956-5c83-b990-7b15e1cb3998 |  | note | Verifying Documents - This ITP
text | 707266e4-30d8-59ab-b6c1-0ed87694b3a2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Trench Stability
label | 7af6e120-bf32-5a2d-86dd-dc524cc3e33b |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings MRPA Standards
label | 3ed4fb2b-7dea-578f-aac2-e86d84841634 |  | note | Acceptance Criteria - Trench stability check:
label | 64119b42-f251-5901-8c1e-72c25702b036 |  | note | – Shoring,
label | 973cb3e1-5f45-5c93-916f-e22f04f6ac1a |  | note | – benching
label | 2f45c57b-32e4-5bee-96a7-07d6afc08643 |  | note | – geotech signoff
label | 5e019d02-7665-5a1e-ab68-68fd6cab0276 |  | note | ○ Attached Geotech Report
label | 0cad6040-798f-589e-8838-1a402002776b |  | note | Method - Visual, Document Review
label | ccbe28d7-2884-55ee-b5ea-ce2b92010380 |  | note | Frequency - Each lot
label | ab0fbaf2-e89a-5d5b-9995-dbe823b51196 |  | note | Category - IP
label | 6b7d5873-8b4b-549b-8aff-95670b773cf9 |  | note | Responsibility - SE/Site Supervisor
label | be4bd7df-2cf8-5fea-9d77-247259a15f60 |  | note | Verifying Documents - This ITP
text | c46005aa-52c8-5052-9409-e076baebd2a6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Placement of Bedding Sand for Conduits
label | 58215e33-3c32-5291-a656-975b486d8139 |  | note | Reference - IFC Drawings L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070
label | 3303d0ca-532c-5f38-96dc-1bd669541f42 |  | note | Acceptance Criteria - 100mm of bedding sand/crusher dust to be places at the base of trench.
label | de3b34a7-0c7d-56fb-bfb2-773517287700 |  | note | Method - Measure, Visual
label | c21dab29-fb23-559d-83b1-3c497b8f81e0 |  | note | Frequency - Each lot
label | e8249845-e3c1-5c6e-947b-0762469a6e22 |  | note | Category - IP
label | 3f65e296-0bfa-5261-8679-f5d44764cd29 |  | note | Responsibility - SE/Site Supervisor
label | 2a3cb03e-ea87-5798-87ff-19b15aa016c1 |  | note | Verifying Documents - This ITP
text | 8e674989-908a-5d29-8bc4-baeb9831bbb5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Conduit Placement & Configuration
label | 12f01c77-9dd5-5b2b-8d0a-e9e5c47b8b60 |  | note | Reference - IFC Drawings L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070, L1-CHE-STD-077
label | 7d5bb706-effe-5738-bee8-3a6d399bfa5d |  | note | Acceptance Criteria - Conduits are configured in accordance with IFC drawings and meet cable separation requirements.
label | 6eaf6216-fbbb-53f2-99af-b88244e2f5df |  | note | Min Cover
label | c30331cc-26fd-509c-a1cb-70fbe221c371 |  | note | – HV: 1000mm
label | 694951ad-c1a0-5f74-a6f8-28db36e53f24 |  | note | – VicTrack: 650mm
label | 645642a8-f0f8-5b63-a991-8a3918f01464 |  | note | – Signalling: 800mm
label | 75429d5d-c8fc-5a75-a370-13540c127f0e |  | note | – LV: 800mm
label | c344a6bc-47ef-5f98-9639-d2f3805d6122 |  | note | – Electrolysis: 800mm
label | c34c4e1a-d20f-5054-a38e-8c3db6f2503e |  | note | – SCADA: 800mm
label | d3f76d18-d174-5a20-9bd6-0df0538854ba |  | note | – MTM Comms: 600mm
label | 28d37a54-6f77-5481-9d47-acec5f1492a3 |  | note | – 800mm below water coarses (stab sand encasement)
label | 52a236c1-6022-537f-a81d-d965c6ad98fe |  | note | – 1200mm Under VicRoads Roads & top of Rail
label | 354b1e05-9ecc-593f-bf73-5b0fdcb367c3 |  | note | – 900mm below council roads
label | e6076fdb-e220-567f-ac03-1abd806be704 |  | note | Method - Measure, Visual
label | 11370d73-1af8-5b8b-9510-8f6c0a0eb185 |  | note | Frequency - Each lot
label | 38681cc7-f1b1-5a70-966f-1030c61c16b2 |  | note | Category - IP
label | f9daada6-2b74-5cf8-b562-5ed416a9eec3 |  | note | Responsibility - SE/Site Supervisor
label | 8f377df5-6e8b-5008-b2aa-03b258c0063f |  | note | Verifying Documents - This ITP
text | cdce26f5-31aa-58e9-8ca1-c3b2b6b302a9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Separation of Services
label | 074698bf-7bca-54dd-82c2-5f8e735081a0 |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070, L1-CHE-STD-077 IFC Drawings
label | 9c630784-ff45-5859-8d9d-a661d1df465f |  | note | Acceptance Criteria - Separation of services
label | 7a350678-4383-5844-8498-27ea4448964d |  | note | – HV: Min. seperation distance between HV conduits at least 50mm
label | 0a5c0bbf-4844-5247-8205-c25f8d57b397 |  | note | – VicTrack: fiber 300mm from HV
label | f155bdc6-dc87-5ccf-a29a-b3d739a9e47d |  | note | – Utility: 300mm to utilities
label | b91f18e7-77a4-56df-8037-16cf4f034a8f |  | note | – Rail: When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | 8bb70b9a-71cd-5411-93b2-382c4a3d5eef |  | note | Method - Measure, Visual
label | c9ea7a7e-5892-59a2-888b-bd389eec7989 |  | note | Frequency - Each lot
label | c3716912-4c25-56cf-8258-16e8b1b504aa |  | note | Category - IP
label | a0a4d3c9-eb34-5104-be42-b0236146890d |  | note | Responsibility - SE/Site Supervisor
label | 898f7551-f6b5-5ef6-878d-f2ace6eadce4 |  | note | Verifying Documents - This ITP
text | fc57cdbe-62ee-56c8-b0b9-eee946127b24 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Joints
label | 3db65550-8b92-5c38-8cdf-068f02046324 |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | db7abc2e-2f5c-5463-96a4-b8265ad52c6c |  | note | Acceptance Criteria - All conduit joints shall be made by utilising the spigot and socket ends.
label | 2fa5f6eb-df66-5d14-8eca-bbcf04875a26 |  | note | ○ Ends to be joined shall be thoroughly cleaned using a solvent approved by the conduit manufacturer.
label | 076de0a0-d42e-54de-a842-2147d22fed78 |  | note | ○ The joint shall be impervious to water and shall be glued with an adhesive approved by the conduit manufacturer.
label | 3b3ff1a3-0c07-598a-b338-3fbd09fb722c |  | note | ○ Socket ends to be placed firmly into the spigots then hit with a mallet to ensure a sound connection
label | 3a6dcc2a-de49-503b-a855-dcc587b4fe32 |  | note | Method - Visual
label | f74c4c14-e29f-5621-ab09-6165e3d001f9 |  | note | Frequency - Each Joint in each trench
label | c670e2d4-9e7e-583e-aecd-35b462a9c783 |  | note | Category - IP
label | 96a5a622-7fba-586f-bed7-c20a37f53cfc |  | note | Responsibility - SE/Site Supervisor
label | b7d64d44-2120-5744-aeac-ea1693042f60 |  | note | Verifying Documents - This ITP
text | 420e5be8-0f38-56f2-9ded-8d22f9a43850 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Conduit Inspection
label | 58a8c196-2d73-5ff6-8911-4c142cd69418 |  | note | Reference - L1-CHE-STD-070 16
label | 3c6837d8-c79c-58ff-b652-f1489a88348f |  | note | Acceptance Criteria - Provision shall be made for inspection of cable routes by NA, MTM/VicTrack representatives prior to backfilling.
label | 39c9a83d-05dd-5c80-b502-cee0596e7fec |  | note | Method - Visual
label | 0cf29286-ad39-513d-bfbc-905329a628cc |  | note | Frequency - Each lot
label | 29b22df1-8f70-5c70-9bc5-540085ce9469 |  | note | Category - HP*
label | aaa8ec4f-5d95-54af-b904-cc67a8374a43 |  | note | Responsibility - SE/PE MTM / VicTrack Rep.
label | 1e896922-7d20-532f-9ad0-447705ead382 |  | note | Verifying Documents - This Itp
text | 32f728f1-699a-5828-9135-fa7d7cd37e8d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Bedding Sand Installation
label | ef9e6720-6fc3-5332-8862-41f1e4895814 |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 CL13.1 IFC Drawings
label | 9076c4f9-845e-5ead-8887-fabc81fe88b2 |  | note | Acceptance Criteria - Bedding sand/crusher dust extends 50mm past edge of conduits.
label | c4d2992f-115d-507b-a1e4-c9014f805f25 |  | note | ○ Bedding sand/crusher dust extends 100mm above conduits.
label | cf0df211-2f73-524f-8667-b7c1a8073e55 |  | note | ○ Attach Delivery Dockets
label | 84a51892-c323-5cef-83e8-f056e128ef9c |  | note | Method - Visual
label | bca1b862-bf5a-5dbe-887b-46ccbf70b24c |  | note | Frequency - Each lot
label | 63804100-df35-5244-a25a-06f3df7bd53f |  | note | Category - IP
label | 1f41e38e-038f-5569-baab-6f720ca0eefe |  | note | Responsibility - SE/Site Supervisor
label | cf561779-1a21-52c5-8417-80c8c4c667ed |  | note | Verifying Documents - This ITP
text | 44f53d78-5ea3-5d15-aea2-87a864af9a6a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 - Marker Tape
label | cd41623d-2523-588e-a4fe-b90c9213011f |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-SPE-070 Cl10.3.3
label | 5cd38453-ca09-59bf-9fc7-cf1b21117ac9 |  | note | Acceptance Criteria - Warning Tape installed a min. 300mm above top conduit or a min. 300mm above HV protection barrers.
label | 09f494b4-a20b-587b-913f-36540c08526d |  | note | ○ Tape to be one continuous length.
label | 8a285ce1-fbea-55f1-8ce1-b200855b781c |  | note | ○ VicTrack to inspect the Marker Tape placement..
label | 85b211cd-0ef6-5449-861c-500aed2dbce0 |  | note | Method - Visual
label | 7c78e7fb-eed2-5280-92af-8d6bd1797b57 |  | note | Frequency - Each lot
label | e4a8e826-4f5b-52c3-bce3-7dabf858dd95 |  | note | Category - HP*
label | 4a9ef731-ac03-55f5-bac9-a0ddf2f39f8c |  | note | Responsibility - SE/PE, MTM / VicTrack Rep
label | 5120c505-f768-5844-ade4-ff7531728474 |  | note | Verifying Documents - This ITP
text | e17ee366-ce0f-54bb-b6be-117cab6ddf43 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 - Backfill Installation for Conduits
label | 309229fb-1770-511d-9d02-d1e4fe30c714 |  | note | Reference - IFC Drawings L1-CHE-STD-043 clauses 6.15 and 6.16
label | fa39071b-07aa-52bf-b872-154f9b0bb4e3 |  | note | Acceptance Criteria - Backfill per trench profile
label | 9b6e5712-8d68-52c5-bf7f-bcf65a7558b4 |  | note | – 150mm layers of 3% stabe sand
label | 38885896-f690-5a06-9198-ae87018dbc2f |  | note | – conduits under water ways to have 800mm cover from base of water way and backfilled with 3% stab sand
label | 4535510d-1ad1-5c6c-b1f4-7169bdfac958 |  | note | ○ The trench shall be finished with a slight mound, height equal to approximately 25% of trench width, to provide for further settlement.
label | 9948f318-7ebe-5092-a08b-07690e522eae |  | note | ○ Trenches under road pavement - backfill to be same material as the road formation material.
label | 42a9ea04-373b-5aa6-baba-d9257c33676c |  | note | ○ Trenches immediately adjacent to footing shall be 3% stab sand. To be thoroughly placed to fill all voids without placing undue strain on or cause displacement of conduits.
label | ac8e80a6-1d6a-52ca-9e4d-aa1046b29db5 |  | note | ○ When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | 21f0ae9e-1b44-5347-9a58-fefbd261fda3 |  | note | ○ VicTrack to be notified and witness the first layer of backfilling.
label | 2650814c-a180-5ae0-98cf-4dcec2d79619 |  | note | ○ Attached Delivery Dockets
label | 85bb2de2-e23a-5781-90b9-94df0ac25668 |  | note | Method - Visual
label | d8812673-1803-5f52-9e15-c1020001d7b2 |  | note | Frequency - Each lot
label | 4c6f81a3-3039-513c-9343-143e79c91960 |  | note | Category - HP*
label | 321d3578-d78c-5754-ad69-9c98e2d2ca52 |  | note | Responsibility - SE/PE, MTM / VicTrack Rep
label | 5e158dca-a361-5545-b04f-7585263be18a |  | note | Verifying Documents - This ITP
text | 29c721d9-d35d-5437-beb3-99c340ab58c0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 - Signalling Pits, LV Pits, Electrolysis Pits, SCADA Pits, MTM Comms Pits
label | e5a8adc3-c03b-5f2b-850a-8251b9fb8bd8 |  | note | Reference - L1-CHE-STD-043 Cl7.14.o, Cl7.14.g
label | 0b84102d-2880-518e-b673-f514e1509d83 |  | note | Acceptance Criteria - intervals no greater than 400m (electrolysis 190m)
label | 9755bc0f-988a-5c61-a508-492bdba1cca4 |  | note | – 3m from rail
label | 702ad092-ff4b-536e-b232-1d65d55e51b1 |  | note | – Access Roads, Class D lids
label | b1f33314-a101-5636-bfb2-41de0398d1fc |  | note | – Footpaths and non traffiacl areas, Class C Lids
label | 7ac5c2a1-c0e1-570c-b3e8-ef1b5d83c0ce |  | note | Method - Visual, Measure
label | 2b4e2c64-4b51-5257-9a47-5985ff87efde |  | note | Frequency - Each Pit
label | 99417a6c-a826-58e1-a193-055512ba4037 |  | note | Category - IP
label | 0f25147b-6957-57da-ac57-fee24b77d4c4 |  | note | Responsibility - SE/Site Supervisor
label | 927b5fb9-22ac-5527-b140-9a67c343157e |  | note | Verifying Documents - This ITP
text | c07001d1-40a3-5781-879a-d452edfd60be |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 - Additional Considerations
label | f6aaaa5f-309a-5d3f-8e6d-709ff5b0eb9c |  | note | Reference - IFC Drawings
label | af47d0a8-79c1-5689-bf5b-cebba95fb597 |  | note | Acceptance Criteria - Access tracks to pits
label | fd5888b6-4114-56a9-ac01-4e044623674c |  | note | ○ Safe access and egress (i.e. lid doesn't open up with workers back to the rail)
label | 917c4c9a-fe1d-555d-99da-01cc3636a20e |  | note | ○ Hand rail & retaining wall installed as required
label | abd696f1-43b3-575d-96f5-cb201c2d6737 |  | note | Method - Visual
label | 7eba5134-a139-5c4e-9c49-28714126a6e5 |  | note | Frequency - Each Pit
label | a932b828-c904-549e-9c6f-859a9cf0e852 |  | note | Category - IP
label | e426eb48-4028-5a26-b0bd-482b701c223a |  | note | Responsibility - SE/Site Supervisor
label | 21e28740-15c5-5e53-9ded-77f3b811d434 |  | note | Verifying Documents - This ITP
text | 4a89f8d3-e9f0-5084-8cc6-04cf1d51c348 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 - Bedding for Pit Installation
label | e6c529e8-c553-550f-ae53-317a76a425f8 |  | note | Reference - L1-CHE-STD-070 Cl 7.21.u L1-CHE-STD-043
label | 38a14659-045d-5455-b1f2-0ee310c02bd4 |  | note | Acceptance Criteria - 150mm of crushed rock under pit extending 500mm past the pit
label | 2d84c477-ede4-5b53-84d1-dd088d15bdd6 |  | note | ○ Drainage arrangements shall be provided at the base of each pit.
label | 83c6375c-11f3-56ce-865f-e931179c37ad |  | note | ○ Attach Delivery Dockets
label | 02a0ea38-aeeb-5fb6-a7bf-17d1888eed82 |  | note | Method - Visual, Measure
label | 76f70624-88ba-56f7-b201-8eabd84f7d94 |  | note | Frequency - Each Pit
label | 871556c0-dce9-5950-af1d-97d8153e5acb |  | note | Category - IP
label | d6a1118d-e36f-5f8a-a9cd-0a0d10906f14 |  | note | Responsibility - SE/Site Supervisor
label | 1f3e0a81-00ca-5b32-b7ea-fa173f58ce63 |  | note | Verifying Documents - This ITP
text | 45687674-a8c0-5d6e-abc3-ab731c923cea |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 - Pit Orientation
label | 4095909a-a01d-5d75-a411-0dd9c1bc4143 |  | note | Reference - IFC Drawings
label | 0e800dc5-6ccd-5dc8-88ec-296957475509 |  | note | Acceptance Criteria - Pit to be parallel to track and parallel to conduit route.
label | 6e6295a5-cabc-5df2-be14-7b01d6156613 |  | note | Method - Visual
label | 255d3569-1447-5776-a29f-0732352aa9f6 |  | note | Frequency - Each Pit
label | 1a32b1d5-bca4-5760-9b73-79907ee0cbd7 |  | note | Category - IP
label | 26af59a4-1fe8-5c72-8c4d-648a7d21482d |  | note | Responsibility - SE/Site Supervisor
label | f1521a62-99c2-5c0a-8379-ec62b37d2cb8 |  | note | Verifying Documents - This ITP
text | fbd14b9f-58bf-5693-b72a-69c91f163126 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 - Pit Installation
label | 767baceb-d5f4-5c84-a7a6-665fa6353fb9 |  | note | Reference - IFC Drawings
label | 2fea99fa-570d-528d-946f-14963f7808bf |  | note | Acceptance Criteria - Pit installed to design specifications. Pit chamber floor to be 100mm lower than the underside of the lowest conduit.
label | 40b6d2b6-1dbd-53da-b432-a5e65a433505 |  | note | Method - Visual
label | 7aae198c-7f3b-5043-aa17-894d9e8089dd |  | note | Frequency - Each Pit
label | 743825cb-bd78-5b9a-ae5e-44e2e4dd6bd2 |  | note | Category - IP
label | 716681d5-38eb-5699-ab54-cf3804c90a91 |  | note | Responsibility - SE/Site Supervisor
label | bc2acf09-1d65-511e-a4dd-b85110ab4ec1 |  | note | Verifying Documents - This ITP
text | 088089ab-ac40-5a91-a9e5-fc96f9cdca90 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 - Conduit Entry onto Pits
label | ea4af1eb-01c7-5c1d-84c0-146b23bf77e2 |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | b717a97f-4229-59ac-9e88-ffed48553ec5 |  | note | Acceptance Criteria - Lowest conduit 100mm from the pit chamber floor.
label | bc8d57c4-b2c7-5ade-8b50-b9aeaa31eb0d |  | note | Method - Visual, Measure
label | f612fe6c-ad8f-5ef8-bf42-ad08e7166ca2 |  | note | Frequency - Each Pit
label | 1e3126be-4798-5253-9bdb-1dad82a58be8 |  | note | Category - IP
label | c18330d4-0a04-5086-8df4-f0cad540a016 |  | note | Responsibility - SE/Site Supervisor
label | 679d6c1e-6767-5c35-9f6e-1e12dbeed974 |  | note | Verifying Documents - This ITP
text | b75ba114-400d-5cb1-8f10-0411b6e7b1a5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 - Tracer Wire
label | fa991a31-8af9-5351-b2f6-342b564d3ce8 |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | f279d04f-fc97-56d2-8494-e282a6339468 |  | note | Acceptance Criteria - Warrning tracer wire for Vic Track routes to be drilled into pits and crimped off. If tracer wire broken needs to Crimped
label | bb4729e0-a0d3-5038-b9fb-7311e37177d1 |  | note | Method - Visual
label | 3e1b70cc-450b-51fb-9b5c-02c0938f86b6 |  | note | Frequency - Each VicTrack Pit
label | 3dd1a31a-4882-56c4-aabf-7f76f5c16cc3 |  | note | Category - HP*
label | 767cf503-623c-5c2c-afa8-ad41d9c37731 |  | note | Responsibility - SE/PE, MTM / Vic Track Rep
label | 5ba3acab-e38c-5549-8894-3aab6f5e6d36 |  | note | Verifying Documents - This ITP
text | 84567fe8-f43e-5462-9925-059c6a7d4200 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 - Spigots and Bell Mouths
label | 6c9ba6b0-40bd-5f4f-9863-8c9b8550b09c |  | note | Reference - L1-CHE-SPE-070_9.3.4
label | c40254c0-8726-5f68-a59a-6a8c86a26f1c |  | note | Acceptance Criteria - All conduit ends in pits are to be correctly fitted with spigots to ensure that there are no sharp edges on the conduit; they are to be mounted flush with the pit wall and not touching any other spigots.
label | 047871a9-496d-5bf2-832c-a0c3d3e0a5c1 |  | note | ○ HV Conduit entering the pit shall extend a minimum of 150mm beyond the edge of the excavation and be fitted with Bell Mouths.
label | 5631a1f9-24a1-575d-9e07-f8ef4e417384 |  | note | Method - Visual, Measure
label | 0812f447-08c4-582f-b275-445e2cd3e71a |  | note | Frequency - Each Pit
label | ad7a28c6-d64d-5e5a-9b63-36cd1adca824 |  | note | Category - IP
label | 7565d39b-fdde-588a-984f-8e229a176803 |  | note | Responsibility - SE/Site Supervisor
label | 1b804370-3a92-553c-a790-a0a3a3cec32d |  | note | Verifying Documents - This ITP
text | 49211a3f-4b6a-53e3-90b9-623874e0daaf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.19 - Draw Ropes
label | fbdca9ef-7c41-59ab-af02-b06b4fe182bc |  | note | Reference - VRIOGS 012.2.1
label | 0096efee-b8b9-5474-ba62-bce62a249561 |  | note | Acceptance Criteria - The draw wire shall be continuous for the complete length of the conduit run.
label | d3afb3d3-05f9-59d0-8c6e-99bf73ae7490 |  | note | ○ The draw wire shall have a minimum of 2 metres of slack within every pit.
label | 24a72e33-0a42-5e4e-a125-1dbdb5b4c2fe |  | note | Method - Visual
label | 647079a6-7a33-59a6-a9cd-4caca6f63731 |  | note | Frequency - Each Pit
label | 3ddb0e2e-d185-55e6-9383-ea9aa5c3d23f |  | note | Category - IP
label | 5f059c2f-024f-5473-94bb-0ce5ae8f7da1 |  | note | Responsibility - SE/Site Supervisor
label | 10bfb173-f04f-5f5b-bd1b-75751d2e2f22 |  | note | Verifying Documents - This ITP
text | d883517e-2efc-5fc6-8d0a-6346372b79b1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.20 - Backfill and Compaction Testing (if applicable) arouns Pits
label | d3dc11e4-fb0f-5b39-9c60-b3e43b4f8cb6 |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | c10eecfb-8f64-5872-9009-67f96676270f |  | note | Acceptance Criteria - Backfill used around pit & pit lid to achieve 95% standard compaction in layers no more than 150mm layers
label | c0b42b7d-43d3-5d6e-96bc-41979ac8f9fb |  | note | ○ Sand within sand pits to be compacted in layers no more than 250mm layers
label | e3fd918a-8917-5ba0-aca0-6f2626e53be0 |  | note | ○ Backfill shall be compacted and level with the collar and surrounds for Trafficable Pits.
label | 6c5da9c4-0f32-5938-a3aa-ebc3f9b44301 |  | note | ○ Attach Test Report
label | 27af2d9b-f078-5ade-9066-a2610c3732d1 |  | note | Method - Document Review, Visual
label | 99fcb32d-c3a2-5564-bb26-405bc5fbb413 |  | note | Frequency - Each Pit
label | d3bfb12e-96c7-5f3d-8383-ae37b607bc9a |  | note | Category - IP
label | 31d880ab-318e-5f93-8324-5948b6ead153 |  | note | Responsibility - SE/Site Supervisor
label | 00678977-c135-5e41-87c4-4127b3f3d9ef |  | note | Verifying Documents - This ITP
text | 461944d6-dbb3-5917-aaab-04cfe24b14a5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.21 - Spare Conduits
label | 7198f4db-5b7b-570b-a1f1-3fb56104cb02 |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | f9e07ac0-4542-55b4-a8a4-b34267630601 |  | note | Acceptance Criteria - Spare conduits to be sealed and to be included on survey report.
label | 17ac863b-f4e8-5e2a-938c-ee715ea69d9b |  | note | Method - Visual
label | ab8ff0b7-e019-5192-a5bd-0d3837f0da91 |  | note | Frequency - Each Pit
label | e9383298-dd2f-5452-86e3-2fbf54e2011b |  | note | Category - IP
label | d38579e2-5c7a-5ec4-901f-9374d988bdbc |  | note | Responsibility - SE/Site Supervisor
label | 70ab70a9-793d-5329-91b7-0fe8684388f0 |  | note | Verifying Documents - This ITP
text | 84d3e9cf-635e-5c8b-863b-25b610b60306 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.22 - Pit Lables
label | 8b2469d8-609e-5f00-b0fa-5088ab86608b |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | 5b15e083-257f-50fa-b595-758ec9ab2eb2 |  | note | Acceptance Criteria - Pit labels Brass Label (30mm x 150mm)
label | ff2c4770-d874-5461-83bc-fdce2cc6e4c4 |  | note | – HV: DANGER - Railway High Voltage
label | ce7bdc95-7fd3-53b3-8d54-0bc8db360a0a |  | note | – VicTrack: Victrack Comms
label | 65763f92-69f7-58bc-9fec-38b76ccfeb60 |  | note | – Signalling: Rail Sign Comms
label | 5e2edce3-a88d-53d0-bf62-01d6910270ab |  | note | – LV Pits: Electrical
label | 06ec0057-9e77-55c6-8d5d-d82c652a1f33 |  | note | – Electrolysis: Electrolysis
label | 98363d14-5df3-5bbb-80c3-5789a0de2289 |  | note | – SCADA: Rail Sign Comms
label | 199a783b-d4a3-55b2-9163-c50c0162fe51 |  | note | – MTM Comms: Rail Sign Comms
label | 38085be2-d7e4-57fa-9e1c-60c4dfa68df6 |  | note | Method - Visual
label | aff0a11d-f6e2-5892-bd78-6c8ffb652972 |  | note | Frequency - Each Pit Lid
label | 823c27cc-93e7-5eb5-a615-bd098be7eecc |  | note | Category - IP
label | 19b42533-ee3b-5017-9b8b-cdb9de7e191d |  | note | Responsibility - SE/Site Supervisor
label | 00882f4f-1703-51e3-a2e1-33c47b43665f |  | note | Verifying Documents - This ITP
text | 6f66be85-0084-5e78-9ee8-76d26f5b1a98 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.23 - Pit Numbers
label | 57ef8401-2bef-58e4-95f8-e546a9032d3a |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | 2a33ed09-48aa-54e5-a160-57cbc29eb625 |  | note | Acceptance Criteria - Pit Number Brass Label (30mm x 150mm)
label | 63690212-9fad-5d38-87c1-f4707d2a35ef |  | note | – HV (22kVV Feeders): ###HV
label | c0f2a534-82a8-598e-a35d-88814d5eea8e |  | note | – DC (HV Feeders for OHLE): ###DC
label | 218ea3fd-3708-5225-a2c4-291ff3d93fe3 |  | note | – VicTrack: ###C
label | 538569ad-7b93-5cf6-9279-e3dd5c06d950 |  | note | – MTM Comms: ###M
label | cbe824e2-7099-53dd-9dd1-92c9c050defc |  | note | – Signalling LV: ###SL
label | 07be26a5-329a-5bb8-a4cb-3bda1612cdcd |  | note | – Signalling HV (2.2 or 3.3kv): ###SH
label | 528dee8d-a4e1-5a24-bc20-5316099c9679 |  | note | – LV Pits: ###L
label | 8a24c374-843e-522b-a204-313fa5bf95bf |  | note | – Electrolysis: ###E
label | 0b5c6c83-c7ac-5b6f-9f64-fc18611bad71 |  | note | – SCADA: ###MS
label | 6a31ff1a-cf87-5e1c-a51e-c0562438c5e1 |  | note | Method - Visual
label | 6aaa054c-563f-56c4-b8a9-027445a94742 |  | note | Frequency - Each Pit Lid
label | 25ac117d-b851-5d0f-b96d-b5662fa889b4 |  | note | Category - IP
label | 33a8480d-b169-5976-bda0-46a55412dc09 |  | note | Responsibility - SE/Site Supervisor
label | 38099c11-dc29-5088-8f09-f33d88d5da5a |  | note | Verifying Documents - This ITP
text | 8f8a93b9-56f1-58f3-96fc-09154eeedf1e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.24 - Cable Route Markers
label | 1c316756-406a-576d-a4ef-fa15cdd852d7 |  | note | Reference - L1-CHE-SPE-070_13.2, STD_E0169 and STD_E0170, AS 4799, STD G0003 and STD G0004
label | ef3cc1bc-cfc0-502a-aa8a-8fd4f7b2dd32 |  | note | Acceptance Criteria - Cable Route Markers
label | 3a02f06b-1422-5cb0-b0ee-db8042e2badd |  | note | – points entering & leaving the rail corridor
label | edca459c-117b-5ca5-b23b-ab70b9e441ce |  | note | – no greater than 100m spacing
label | f80540f6-b852-581e-b636-eff54eb60409 |  | note | – Change of direction (more than 5 degrees)
label | 06fa92c2-025a-5e50-ae37-facacc42e258 |  | note | – White posts with marker plates for conduit runs
label | b7d09e33-fda0-56e7-8e49-584662f57331 |  | note | Method - Visual
label | 38b3656d-8e2f-515e-9d01-58337029eb14 |  | note | Frequency - Per Cable Route
label | 00bd0f77-8335-5221-8ab7-3403377ab11c |  | note | Category - IP
label | ad2815d8-db44-5225-be92-184b82028378 |  | note | Responsibility - SE/Site Supervisor
label | 2f94395e-c145-5fe8-9ed3-6ffa6f8e3aa7 |  | note | Verifying Documents - This ITP
text | 415afb5e-0fac-5ed3-8e8e-7f988ea60088 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.25 - Cable Pulling
label | e0740c34-d166-58e8-ab4c-b0c4292a3158 |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | f12da0cf-59a4-5134-be7b-54a48bf69d93 |  | note | Acceptance Criteria - Cable pulling to be witnessed by MTM/Vic Track and to be signed off.
label | 8732c8b5-fa53-53f3-84ec-8cebed44ab64 |  | note | Method - Visual
label | 87c219c2-6112-5985-b033-ebbb52dc7630 |  | note | Frequency - Per Cable
label | b4e85ddd-b085-5915-a90d-c9df148007cf |  | note | Category - HP*
label | 1119c78b-fbae-5ca4-8ea9-6ced38748868 |  | note | Responsibility - PE, MTM/VicTrack Rep
label | f45a34d3-f75f-51c9-80d7-43f4ed019697 |  | note | Verifying Documents - This ITP
text | d3827269-fe2d-5dd5-b2c4-d29cfff946ae |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.26 - Cable Labels
label | bd18e5a6-f38f-57c6-b402-7c25863f6a36 |  | note | Reference - L1-CHE-SPE-070 Section 13.3
label | 2c09ddcd-9084-55bb-8bb9-e99937d4a8d9 |  | note | Acceptance Criteria - All installed High Voltage Cables shall be legibly and indelibly marked with an appropriate identifying label at each end of the cable, and at any cable joints.
label | 93e2e7e8-682d-5fc1-807b-b8c8c6f1184e |  | note | ○ The label shall state the destination points of the cable and the name of the cable relevant to appropriate drawings
label | 4314af9b-6159-53e7-ba7b-590e8072d39c |  | note | Method - Visual
label | bef2445f-605f-5913-8bc5-f48db783ec5a |  | note | Frequency - Per Cable
label | 897034a6-3750-518e-821b-b8226f3951a4 |  | note | Category - HP*
label | e107edca-571b-5f46-97b9-c7b74793cfc9 |  | note | Responsibility - PE, MTM/VicTrack Rep
label | f200d832-f329-53f8-80b4-a720f6da7a12 |  | note | Verifying Documents - This ITP
text | 1ef0e06a-a75f-5be5-b2ad-859e4607142a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.27 - Cable Joints
label | 27358873-bc05-5137-9d81-7f04d3d273b6 |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | 6d3afe82-ce73-579e-be9b-84f22854d7c6 |  | note | Acceptance Criteria - Cable joints are installed correctly, with sufficient fault loops lengths & supported correctly in pits.
label | 61587ece-4611-5c14-8ed7-cd33e7c769f2 |  | note | Method - Visual
label | 00810287-ae5f-501f-b19e-3e849ac3f6d1 |  | note | Frequency - Per Joint / Termination
label | f7280edd-2119-5d72-8337-8ad007fecd77 |  | note | Category - HP*
label | e4488101-8738-5daa-b94e-9702177a8668 |  | note | Responsibility - PE, MTM/VicTrack Rep
label | e93aa4f1-4c92-58b9-af3e-41828e2bc68f |  | note | Verifying Documents - This ITP
text | 16e2445a-77e6-5156-ac41-9e9a80ebbe98 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - As-built Survey
label | 5010c438-01ea-5916-a091-e7cff0c23133 |  | note | Reference - IFC Drawings L1-CHE-SPE-070 Section 13.1
label | 8f70877c-a2e2-5ad1-9479-baf43f33fb89 |  | note | Acceptance Criteria - Survey report to include but not limited to:
label | 07581f97-bc09-5cf6-8009-85695454ac8f |  | note | – Cable joint locations.
label | 5e6eee6c-b335-52b3-a148-59e98b4330a1 |  | note | – Cable pit locations (Corners)
label | 574d1ccf-2992-563f-977c-dc2797c1fe26 |  | note | – Pit dimensions & pit lid type
label | 41802733-43a4-5950-b8ce-e0d3684c58c9 |  | note | – Under line crossings
label | 8bbbf653-2927-5476-93f6-0325a8fbcc49 |  | note | – Under road crossings
label | 17b441e3-f462-5a00-8401-af5258c8841a |  | note | – Changes of direction
label | c86c2ca3-576c-55ea-be4a-6af3ce98ec5e |  | note | – Spare Conduits
label | 5fb45484-975b-59bb-a1a0-6bcac21ccd1a |  | note | – Conduits labelled as per trench profile
label | 69d1f8ec-011f-5c2a-b3da-b073813b89c9 |  | note | – every 10m
label | fda627e0-f0c9-5a6a-93e0-b20391b251b9 |  | note | – Other significant points of the cable route
label | d6d03b8e-a0ed-55cf-9c52-8a13506b53ad |  | note | ○ Attached Survey Report
label | 20e9cb1c-b5f9-5b0c-888e-a4ebe4eb4140 |  | note | Method - Document Review
label | ff1245a2-1acb-52ae-8081-6dea999155a1 |  | note | Frequency - Each Lot
label | 8ef73a25-2dee-5a63-805a-4564f330f04b |  | note | Category - IP
label | 1932aaf6-2a6c-5f47-9d93-38b7b4ba8a8a |  | note | Responsibility - SE/PE
label | c7a7d7f1-517c-585b-88d0-567837b51bbc |  | note | Verifying Documents - This ITP
text | b6b38845-7056-54b6-9209-c99adc186c46 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Handover Check
label | 1d488719-bd0f-5139-b906-c79d2b181adf |  | note | Reference - IFC Drawings
label | 09883a1f-dfb8-5107-b3e5-a64b0140d14d |  | note | Acceptance Criteria - Handover check completed for Testing and Commisioning.
label | a81d3e37-c1a1-535e-ba67-3189a2355801 |  | note | ○ Attach MTM/Vic Track Check Sheet (Signed-off)
label | e4ba4984-868f-5a65-83e4-1f84bb96d5bd |  | note | Method - Document Review
label | 5e2ca7fe-cd7e-5584-8708-b112b132c65a |  | note | Frequency - Each Lot
label | dd429740-1468-5cdf-ad56-629ba69a00f1 |  | note | Category - HP*
label | 4a4b687b-0975-5e4c-b6d0-e33ea794463e |  | note | Responsibility - PE, MTM/VicTrack Rep
label | 6ccd5f93-d08c-598a-9cd1-44a869b7c514 |  | note | Verifying Documents - This ITP
text | 5a9b9141-e1e4-582e-9ac3-80d4a3cb71b6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Testing and Commissioning
label | af019a27-52af-5329-85fd-6e4b55746cd9 |  | note | Reference - IFC Drawings
label | de0abc0e-f493-561a-a05b-faa3f82092f9 |  | note | Acceptance Criteria - Testing and Comminsiong to be completed
label | af79657f-efb8-5799-8224-c99300cab46d |  | note | ○ Attach Testing and Comminsiong Report
label | c41cc4e9-0c9d-5898-ac6a-3296182059a2 |  | note | Method - Document Review
label | 0997c5c0-19b3-5fa2-999d-53754efd1875 |  | note | Frequency - Each Lot
label | cab6c9b5-d8df-5c42-90a1-3057d19def65 |  | note | Category - HP*
label | 73783d45-9e70-5d68-adaa-68467df20161 |  | note | Responsibility - PE, MTM/VicTrack Rep
label | 4b591755-52d2-5db2-8e4f-eb54b233c200 |  | note | Verifying Documents - This ITP
text | eefa444b-c58e-5a09-a6f4-5713e806bd9a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | f5319cb6-11f7-5b30-ab23-af85159a1eb2 |  | note | Reference - MRPA Quality Management Plan
label | 3c4084dc-0e77-515f-a2f0-5e4e4f76efc6 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 1ce62661-6684-58f1-99ff-d42b77acd1a0 |  | note | Method - Document Review
label | 28db623d-fe29-5557-aa70-2855e4f3c3a0 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | e25f0eaf-e438-5072-9525-39ebecab4401 |  | note | Category - HP*
label | a54ae390-f890-536b-8023-ebe7c9ba4a1f |  | note | Responsibility - SE/PE/SPE
label | 3cd77f36-2b38-573b-8121-83de76430ec7 |  | note | Verifying Documents - This ITP
text | 27213cda-753a-5f6e-9846-bf2c68ba8972 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | ac07e7f9-467b-5be0-9d99-69a508a34d63 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 691b314f-2aa8-5cab-af7e-908f31fc9297 |  | textbox | Name:
text | 745b76df-e074-5503-bb42-33bff019e066 |  | textbox | Position:
text | 362b811d-0e4f-5d48-9a08-842ed50ade40 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-009-STR-Bored Piling |  |  |  |  | Yes | ITP-009-STR-Bored Piling - Rev 0 | f3d066a9-d57e-4e39-94c6-6e609efce0b3
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 70deff00-e4c2-5484-ae92-ce89f855f706 |  | note | Document Title: ITP-009-STR-Bored Piling
label | 6ef3d51e-9fe2-556a-8294-ab785c5c5ef3 |  | note | ITP Description: Bored Piling
label | bef5ddca-cda4-5034-803c-f21f973ef84f |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 639ee6a9-c63f-59c1-952b-9d135eea4666 |  | note | Discipline (e.g. CIV/STR/RAIL): 009-STR
label | 860a3bb4-6b87-5525-8dc7-bf3d68f15b2b |  | note | Revision Number: 0
label | 4f49a0fb-0218-59fd-afc2-d3df71a80909 |  | note | Revision Date: 11/10/2022
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 641b35d4-14be-5196-9ff2-697557431081 |  | note | Reference - VicRoads Section 606 July 2017
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 688df7bb-a8eb-5248-b79c-433c1ac166e0 |  | note | Reference - VicRoads Section 610 Feb 2020
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | d844f97e-6b2e-50a4-953b-79581650df4b |  | note | Reference - VicRoads Section 611 November 2018
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | 6d361911-ccfb-5caf-b282-9738c4ec2344 |  | note | Reference - AS2159-2009
checkpoint-status |  |  | checkpoint | 1.5 - Non Dependent
label | 7e8c2ef8-8d3b-537e-a808-9adb584b8ff2 |  | note | Reference - AS3810.1 2018
checkpoint-status |  |  | checkpoint | 1.6 - Non Dependent
label | 2825e1fd-2eda-5103-8318-b27132c0dddf |  | note | Reference - AS5100.3-2017
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Concrete Mix
label | c46bd9d7-05b0-508e-96b1-9ca3e995e7fe |  | note | Reference - 610.07 Table 610.071
label | 185f114c-5b6b-5bec-a0c6-061dd78339c6 |  | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
label | 164ddf8d-41d1-5961-a707-c3fab2c53837 |  | note | • Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
label | afb43345-92dc-580d-a184-6db0f897bbc2 |  | note | Enter: Teambinder Material Approval number
label | 933742c4-77c8-5fef-bd7e-90a47db67028 |  | note | Method - Document Review
label | 9db5dc46-e510-5161-b166-23ce1253f146 |  | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
label | c3f17396-fa57-5f6f-b603-aaf766e16b57 |  | note | Category - HP
label | c96a2fc7-df6c-56e8-959f-144173db2238 |  | note | Responsibility - Nominated Authority
label | 9695e915-0047-5bb2-9a8a-7c18f9f9e0d5 |  | note | Verifying Documents - ConQA Hold Point Release
text | a89b79c4-9756-5dda-9a87-cdef5f74787e |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - ACRS Certification (for Reinforcement)
label | 4cc5f199-c03a-5e72-a8ef-352c00bd512d |  | note | Reference - 611.05 (a)
label | 94a8981b-4bf9-50e2-bae6-ff07e803187d |  | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
label | 011d8146-4fb6-51cc-bad2-d2ff81f2e864 |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | 0fb27cfd-0607-51b7-a607-b0ef4e127d85 |  | textbox | Enter: Teambinder Material Approval number
label | 938994a9-054f-5094-8726-6bbe98201695 |  | note | Method - Document Review
label | 1c31a660-6966-5344-9c4f-cba319bb014c |  | note | Frequency - Once for each supplier, 14 days of award of contract
label | 0e570fdd-4672-52d3-b407-3cb16acd2439 |  | note | Category - HP
label | a738ab58-d089-542d-b6fe-7fa8022305d8 |  | note | Responsibility - Nominated Authority
label | 61990dc4-580e-5172-b067-b1caf9b21a39 |  | note | Verifying Documents - This ITP
text | 7e53f986-a668-5c08-8c75-3939f230d273 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Bar Chairs/Aspros/wheels Certification
label | 4b4e101f-dd88-57f3-bf25-ba9a0a8b81b7 |  | note | Reference - 610.26 (a)
label | a9dab2f2-d03f-5aa4-9b65-29a5c206ca08 |  | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demostrate suitablity to prevent excessive deformation under loads.
label | 6f95c768-3e5b-5478-aa66-85c452a3f9a4 |  | note | • Concrete aspros require annual compressive strength and soluble salt testing is required.
label | 015cc1d4-2424-5230-80b5-430111a6f273 |  | note | • Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | a8c2ac94-488c-5531-9527-da44b2d85ca0 |  | textbox | Enter: Teambinder Material Approval number
label | 5204e8ac-9d63-5dbb-bdf1-0fcb4a741237 |  | note | Method - Document Review
label | 4c038cca-5d51-595c-ab2e-78f821ee5ae2 |  | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
label | 5a1ae7af-5cad-5a6e-96cd-cd827393de5d |  | note | Category - HP
label | 6ce6ae7f-b307-5cf3-a6d7-8303a3d595ae |  | note | Responsibility - Nominated Authority
label | ac2a7554-1ed5-5e09-98f1-94e293d0cc98 |  | note | Verifying Documents - This ITP
text | 2108ce6f-1d9f-50e1-93ce-7d78dba01652 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Working Platform certification
label | 5e9eb1b0-511b-5d80-8e64-0ec00e5e4658 |  | note | Acceptance Criteria - Satisfies minimum plant bearing pressures requirement
label | 494d1fa2-fa0b-5ca1-88f0-9c935222cedf |  | note | Method - Document Review
label | 4f5c9553-289e-57a1-b8b7-3706ec7110bc |  | note | Frequency - Prior to works commencing & after rain event which there is >10mm in a 24hr period.
label | 22895676-31fe-5d9f-bf96-ec9c72c87330 |  | note | Category - HP
label | 33372c2a-3842-5baf-95a2-11de3bc87e1f |  | note | Responsibility - Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
label | 5a0f0ff1-d1c5-5510-ace5-94e24fc6ffcd |  | note | Verifying Documents - This ITP
text | a6b9ef00-968d-5a0f-8e19-43b7423f9eaf |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Piling Operations Work Procedure
label | 19a55fbc-dd2b-5e43-aad5-cb8286214c24 |  | note | Reference - 606.03 (a)
label | 5d33d674-711f-5b46-9fca-cdb73ff2f722 |  | note | Acceptance Criteria - Piling operations work procedure to be submitted for review to the Nominated Authority.
text | 4a84677a-2aeb-53a5-a9c4-fdc51470e70b |  | textbox | Enter: Teambinder Approval number
label | 866b9f2e-c337-5de2-857f-7dd9705b6c9f |  | note | Method - Document Review
label | a08d7c62-0f9c-5982-95f9-b7a5ceffd854 |  | note | Frequency - Once, 4 weeks prior to the commencement of piling
label | f2861df1-b38a-55f2-bc3e-d3e3128ae5fe |  | note | Category - HP
label | fdbbcb31-8dc9-521a-9eb8-3261bbbfdf2e |  | note | Responsibility - Nominated Authority
label | ceecfde2-b5c4-5f57-8128-74741d275694 |  | note | Verifying Documents - ConQA Hold Point Release
text | baf340be-13c1-50e6-b49b-fb6eddf4f679 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Temporary Steel Casings
label | 77d2711e-9d3e-5192-af59-d6179c19e73a |  | note | Reference - 606.03 (b)
label | 6440ac1a-e921-534d-abdc-a2146d66fc61 |  | note | Acceptance Criteria - Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
label | dbdfafff-e0dd-5d58-939e-01d242b467b3 |  | note | • Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
label | 22a2dc1d-4ddb-5a6f-9ae9-a137410c89d8 |  | note | • The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
text | 5fb88094-f5f8-5c32-a09d-5fa5167aed40 |  | textbox | Enter: Teambinder Approval number
label | 577d364d-c460-5819-94f2-8910f8732b25 |  | note | Method - Document Review
label | e299dbae-04ee-5664-9bf9-2c5b887ed961 |  | note | Frequency - Where applicable, once, prior to use
label | 5d0ac6da-bc19-512b-9089-c92ed9e09e89 |  | note | Category - HP
label | f9edf96a-0573-5651-8270-ee8513307f77 |  | note | Responsibility - Nominated Authority
label | ab9dc98c-4c75-5a4e-b937-606cede89cbe |  | note | Verifying Documents - This ITP
text | cfc155bc-89f9-54db-8532-9f758223ce3d |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Casting Under Water Procedure
label | 852e7a91-dea2-5743-9462-418af568d3e8 |  | note | Reference - 606.06 (a)
label | 29bbb10c-7542-5463-9cea-0407c6bfcc54 |  | note | Acceptance Criteria - Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
text | 050db3af-735e-55f5-be20-908bf53978cf |  | textbox | Enter: Teambinder Approval number
label | 4edc7f83-d45d-55f1-a78c-3265d6768512 |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | 2c872037-2fe0-5ffb-b145-182ee38a55b4 |  | note | Method - Document Review
label | bc553972-ecfa-55d0-8ae9-0ff524eb9605 |  | note | Frequency - Where applicable, once, prior to placement of concrete
label | 5161391c-98fb-5ed3-bac7-8c5103153287 |  | note | Category - HP
label | d80a3d1d-c769-5a30-bdac-84b2651b044a |  | note | Responsibility - Nominated Authority
label | 0094db76-fda0-56a6-877d-be25ec9fd212 |  | note | Verifying Documents - This ITP
text | a08ad46a-8b0e-553d-9edf-bda6a50edae7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Boring With Bentonite or Polymer Fluids
label | 5393e021-cd75-583e-a782-6b15e121a60f |  | note | Reference - 606.03 (c)
label | fc93b65d-002b-574d-93fa-3136837fdb7e |  | note | Acceptance Criteria - Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
text | bff898b9-ed74-5381-843f-8159e1fe39a1 |  | textbox | Enter: Teambinder Approval number
label | 82b07a35-6b70-5477-9b5f-358a870b4edb |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | 78dd738f-5ef3-5da5-9d27-0e6878ec613b |  | note | Method - Document Review
label | 55eaf5ad-5db1-5bbe-8f1a-3b44437a67e9 |  | note | Frequency - Where applicable, once, prior to commencement of boring
label | 6467ca66-604d-58f8-bbcc-7496147a68b3 |  | note | Category - HP
label | b4a7ffdb-062a-50b3-a365-5f8aaec24f8f |  | note | Responsibility - Nominated Authority
label | 8bad09d6-6992-5793-a403-f6a01179f00e |  | note | Verifying Documents - This ITP
text | 1ee2689d-c5b2-53e9-8eea-287ecc10a9c2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Dynamic Pile Testing Procedure
label | 47d0d2dd-f141-50e9-893a-486d315f573e |  | note | Reference - 606.07 (c)
label | 86c4e241-a19d-5754-a1bc-8b727c439f1b |  | note | Acceptance Criteria - Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
text | 2e9891f3-0500-5ccc-94c3-77ff34e4ea2e |  | textbox | Enter: Teambinder Approval number
label | e5c65b1b-c547-5fe1-8dd8-c0cbb9e9a8ae |  | note | Method - Document Review
label | d48a7568-8dd1-51d0-9091-eadc43c55bff |  | note | Frequency - Once, prior to testing
label | 206b1981-f9f1-5a8b-b255-36de0579ecd9 |  | note | Category - HP
label | d41faa86-651c-5914-8d47-4a90819b78c1 |  | note | Responsibility - Nominated Authority
label | 634a2276-807a-5e49-972b-1d9aa9d59853 |  | note | Verifying Documents - This ITP
text | c9e65f2f-caee-59df-b466-d261f8c584d0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Pre-qualified Pile Testing Consultant
label | 41e19f97-beb6-56cf-8439-02cfa696181e |  | note | Reference - 606.07
label | 50586dc0-a8c8-5aae-8351-6ee554fc903a |  | note | Acceptance Criteria - All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
label | f30dee24-1fc1-55a6-960e-298b00715a59 |  | note | • Details of the consultant to be submitted for review to the Nominated Authority.
text | d3365d35-913c-572b-82ac-ee3f0b0c1696 |  | textbox | Enter: Teambinder Approval number
label | 3d253a86-0f84-53bb-9f2f-379e4c212136 |  | note | Method - Document Review
label | 41e0f3d7-f5f9-5824-85f3-c7dd51e1e355 |  | note | Frequency - Once, two weeks prior to testing
label | 5c1e1f2e-6674-5bb4-90b9-a67124d3149c |  | note | Category - HP
label | 394fa4c9-64c5-5880-a11f-cb15eaa8f22c |  | note | Responsibility - Nominated Authority
label | 895ba038-c9aa-575a-912e-6feebeebc3c4 |  | note | Verifying Documents - ConQA Hold Point Release
text | 29565947-b1d9-5ab1-a932-52f289942255 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Reinforcement Welding Specifications & Qualifications
label | cb2c9e3b-1700-58be-a0f8-ceda08077c88 |  | note | Reference - 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3 611.14 (b)
label | 94182149-cf10-5286-a001-a167a2871ae2 |  | note | Acceptance Criteria - Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding specification & qualifications (including macro inspection) have been approved by Nominated Authority.
text | ee91287b-88ea-5930-80d8-6eb5b764913f |  | textbox | Enter: Teambinder Approval number
label | c2ea2cc6-15f9-5c16-8ba7-5f204921e47e |  | note | Method - Document Review
label | 5979b1b9-0f14-5ffe-b3fb-507b72c2d038 |  | note | Frequency - Where applicable, once, prior to welding
label | 65b844cc-1d90-59e3-a6b6-1e1aefdf02a9 |  | note | Category - HP
label | 6c593126-2fd9-537b-ac35-0ce3bc981105 |  | note | Responsibility - Nominated Authority
label | 3154af69-03c7-5e1e-af72-d4cf823a8fd2 |  | note | Verifying Documents - ConQA Hold Point Release
text | 6674978b-4b73-5efb-96d6-bec603d11782 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - IFC Drawings
label | 5bddffc5-0d1f-5633-935f-483d48084536 |  | note | Reference - MRPA Quality Management Plan
label | e57f53bb-dba1-5cb9-a8fd-94cb03369afe |  | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 183688c3-b5e2-51b5-a1b1-9848113ceb91 |  | note | Method - Document Review
label | 29a7dbbc-0394-509b-b062-c10ab9b8f751 |  | note | Frequency - Prior to starting Works and at regular intervals
label | 1a8d4338-2622-5605-a6ec-b22b41159907 |  | note | Category - HP*
label | 679f47db-c605-599b-8063-7160b387eaa9 |  | note | Responsibility - All
label | c1f7601f-22d5-5f99-9427-6dfed845c4a7 |  | note | Verifying Documents - This ITP
text | 7dd0fa56-209a-5b32-972a-74dfc35403ae |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Survey Set-out
label | dd1b7f7f-26fc-5034-b4db-cef8fc49d576 |  | note | Reference - IFC Drawings 606.08 (a - c)
label | b4a06923-68a5-5301-adbd-04ed86486c0c |  | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
label | ab482f12-f23a-5e36-9701-cfe4ea38fdbe |  | note | Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
label | 90842512-57ca-5ee2-a8e5-506301e115a1 |  | note | Method - Measure, Visual
label | 7822bc61-0ca1-5efc-9f1a-1ac0daec2a91 |  | note | Frequency - Each pile
label | 0815d47a-3087-585e-9ed6-c4fcebced536 |  | note | Category - IP
label | 83edb9a1-d6c3-5744-993f-5593f684c40f |  | note | Responsibility - Surveyor, SE
label | 68aec104-2401-5567-af27-6fd7bac18ec6 |  | note | Verifying Documents - This ITP
text | 665d69ce-ba28-5078-82cc-c3a0a0ae7798 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Protection of Adjacent Piles
label | 787cfeaf-2ba3-5868-af07-83837ca91f1e |  | note | Reference - 606.04
label | 168813c7-0d42-51e5-af7c-a9530cd5b6df |  | note | Acceptance Criteria - Pile construction shall not:
label | e814fc41-5f5c-50ad-ab08-ce60988e6e8e |  | note | i. result in damage to adjacent newly cast piles due to ground vibration.
label | 09e24af0-9a2d-510b-92ef-82f8fc3c93bf |  | note | ii. commence within 2.5m clear distace from newly cast piles if that pile concrete strength <15MPa
label | 702f700d-8128-59a6-81be-070636581710 |  | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
label | 4c777e02-8960-5f31-a13b-407c4a89ec01 |  | note | Method - Measure, Visual
label | 6d96d74f-777d-503e-960f-178e94bcbe8a |  | note | Frequency - Each pile
label | 7d6589a7-1981-5f76-ae41-99e2700b7230 |  | note | Category - HP*
label | e35a8016-ea0f-5b6b-83c8-08df39f3cbab |  | note | Responsibility - SPE/PE
label | 24bcb744-d085-5b84-aae6-38c61a371d77 |  | note | Verifying Documents - This ITP
text | 4e2e5597-d0b3-5506-b107-5c1efb7a0f8c |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Boring Operations
label | 2e0e66ae-c32c-50a2-9260-637225c508f1 |  | note | Reference - IFC Drawings 606.03 (a)
label | 19e7bed7-f446-5330-8abb-c97c6e810bd1 |  | note | Acceptance Criteria - Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
label | b52cd620-5e74-5166-b404-cd3297d5d3de |  | note | • Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
label | 3999ddb6-e160-5ed2-ac55-0fdee1019f58 |  | note | • Excavation clean and de-watered (where applicable) for inspection.
label | 869cc012-f33f-57b2-ba30-ad6b0b9792bc |  | note | • Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
label | 2e2646fe-8a7d-52e7-a31a-eb3089acf99c |  | note | • Excavated material to be disposed of as appropriate to maintain a clean site.
label | ff74b51f-39bf-52dc-b89c-ff990d2bd686 |  | note | Method - Measure, Visual
label | f4e9d4c3-6bfb-5f0d-83ca-5a4cdee92bc3 |  | note | Frequency - Each pile
label | ecd4d15f-a7ce-5d6b-8905-60951373b4b6 |  | note | Category - IP
label | ad9ce876-6f2c-5960-a267-f3edcdc416f8 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 4ecc093a-56a1-51e0-9911-5208d694b2a7 |  | note | Verifying Documents - This ITP
text | 4ccce1e1-f277-57d3-9f68-042ba7140e83 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Formwork Extension
label | 8bc3c99f-a4be-58bc-825a-d30f52db1633 |  | note | Reference - IFC Drawings
label | 5a2444e8-9cff-50c8-8e13-e9d2f94b43a1 |  | note | Acceptance Criteria - Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
label | 56843e52-2052-58eb-807f-3a3a2e546788 |  | note | Method - Measure, Visual
label | 671aa1a0-9623-5ee6-b3e5-a882f5e63a3c |  | note | Frequency - Where applicable, each pile
label | 6923fc64-35a9-5109-9a64-8f1aa261e634 |  | note | Category - IP
label | 995e5b4d-09e8-5410-9972-87d31c5719ac |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 27027c48-f2b0-5454-965a-1dcfef2e3b1e |  | note | Verifying Documents - This ITP
text | c1724e1c-1ee9-55bc-9809-fec4a5ebbfb4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Inspection of Pile Excavation
label | 6c86c6e8-85a8-5a5a-95b3-982af1ff16e5 |  | note | Reference - 606.05
label | 92bc4419-fef2-5e48-a1ef-5b7fffd3524c |  | note | Acceptance Criteria - Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | 50beec26-9707-5195-b9d7-918807941c84 |  | note | Attach: Geotechnical Field Sheet or Report
label | dc445c7c-26bb-53a0-aff0-549cd7a08960 |  | note | Method - Measure, Visual
label | 5e4d8257-be18-5544-ac47-4a6af400b582 |  | note | Frequency - Each pile
label | ee751d8b-4777-52df-b2dd-01b7436fc707 |  | note | Category - HP
label | 6b17c0a0-2bb0-53e4-84d9-3acbc92c9687 |  | note | Responsibility - Geotechnical Engineer
label | a7f1be9f-b758-5fa3-bdf0-1579c5ed739d |  | note | Verifying Documents - ConQA Hold Point Release
text | fddf5e1f-50dd-5dee-a133-2ec2d4fe7992 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Reinforcement - Placement
label | c0d5509f-4c0e-531a-a927-98dbb33d5f89 |  | note | Reference - IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12, 606.06 (a)
label | 2b6f02f2-d59d-5539-9783-b265089ed39a |  | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | 0c77b42d-05a8-51d4-a265-bc7b3883b143 |  | note | • Projecting reinforcement is the correct length and location.
label | 383015dc-0157-5ded-bfdd-39307502e1e1 |  | note | • Splice lengths achieve the minimum length and are in contact for this length.
label | cb8f452b-8007-5249-9ee6-caa3d548a142 |  | note | • The reinforcement surface condition is free from dirt, debris and damage.
label | 8f0409b7-c1b2-5840-92e1-e305cc640c5c |  | note | • The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | a637e21a-5b15-5414-aad3-ae9fcc1ea38a |  | note | • Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
label | 4a1ce2f2-a6f5-5f51-9ea0-bfa1f238cc49 |  | note | Method - Measure, Visual
label | b9d48af2-cde8-58b0-90b8-949778b26041 |  | note | Frequency - Each pile
label | edc011a1-da90-5f57-9fda-4152e220188c |  | note | Category - IP
label | d7686d48-67b7-54eb-8b92-fa70c8999f15 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 7ab39a4c-15e9-510c-b9ce-5e2f3e01ce09 |  | note | Verifying Documents - This ITP
text | 23814118-bfbc-5b8d-937f-58ad6e70f9b8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Reinforcement - Electrical Continuity
label | 8f5e0c62-f8f8-5f5a-8ae8-6e023530a64d |  | note | Reference - IFC Drawings 610.29 (d), 610.43
label | b8773b64-bab6-5f8e-a7fa-2539cc80e44c |  | note | Acceptance Criteria - Pile reinforcement cage to be made electrically continuous by:
label | ce190e68-f8c7-5648-bc21-64be9ede9d75 |  | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
label | 45cde450-090f-5728-885b-c36a56742954 |  | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
label | d18e43c8-dceb-5512-8dd1-d5d9f70160f7 |  | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
label | 4d6d29e3-aa8e-57c4-8d40-5bb2cac575c6 |  | note | • Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
label | 56ef2b2d-13dc-57ff-9827-96b3bd1c06e5 |  | note | • Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
label | 11652ba8-4ccc-5fd7-a877-520b19693dfc |  | note | Method - Measure, Visual
label | 14167044-8b7c-59df-9635-a3041ceeff18 |  | note | Frequency - Where applicable, each pile
label | e76a2cf0-6667-54df-bcaa-460875c24d3a |  | note | Category - IP
label | 1ec6c1fa-5f1f-505a-af05-7bb51d3c509d |  | note | Responsibility - Earthing Engineer, SE/PE/SPE
label | 989b82f4-eae5-5a1a-9dfe-a93e01b6f259 |  | note | Verifying Documents - This ITP
text | 5f41aa10-3720-5cfb-94d2-8a69676507a0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Cast-in Items
label | 19f8fcde-a882-5eaf-b154-5a430baac213 |  | note | Reference - IFC Drawings 610.46 (a), Table 610.462 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2
label | 5b735a64-8d4e-5786-af63-168b596f6655 |  | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | 21f9ca48-9872-5124-a6fb-2d368a4c856b |  | note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | dcd7de38-1ba1-5b65-8ffc-da15a16d1b66 |  | note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | f67d5f75-a150-5602-8fb1-3eb71cd54e37 |  | note | • Grout tubes shall be fastened at regular intervals to prevent kinking.
label | 7d264d81-7d6d-5157-b6be-7ea9f59952bc |  | note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | 2d205eaa-e326-51e5-b6c8-2a65aebf73d6 |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | fb88f485-72c6-5f5c-9f8a-8904948b9f15 |  | note | ii. Running dimensions of a group of the above = ±6mm
label | 8e26a7f8-8e77-5389-94f3-06cb41fae72c |  | note | iii. Ducts and conduit location = ±12mm
label | e472e455-b7f2-54ef-a3ec-504f10280c21 |  | note | iv. Diameter of ducts and conduits = ±3mm
label | 8efb410c-2531-5ec6-a9b8-2c988fc93014 |  | note | Method - Measure, Visual
label | 403cda94-2204-5db9-b482-94f481400f40 |  | note | Frequency - Where applicable, each pile
label | 513dbd4a-fef4-5d4f-8c58-931b67fbff50 |  | note | Category - IP
label | a1dcdd77-54f4-5636-8987-d7b37b89eef9 |  | note | Responsibility - Foreman, SE/PE/SPE
label | f8d710ed-8097-516d-9a21-7f3bdc51bd62 |  | note | Verifying Documents - This ITP
text | d26079d0-d158-5b26-b1eb-7e50c346cbf9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Pre-pour Inspection
label | 26a05ffb-c0d1-59a5-8234-ec521a909376 |  | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
label | b31d5516-867e-57f1-9e0e-a0619547e9ee |  | note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | 154049df-8f96-5e80-b398-68576561b0b8 |  | note | • All foreign material has been completely removed from the excavation.
label | ad23c896-9c1a-5c4b-a984-897e77d4d922 |  | note | Method - Measure, Visual
label | d13d6261-fcfc-5954-b4ae-e6f6781fcbaa |  | note | Frequency - Each pile
label | b2a6f744-3450-5403-9a2e-e969a9247d84 |  | note | Category - HP
label | ac8fd46f-5541-583d-ac63-46d9f7013710 |  | note | Responsibility - Nominated Authority
label | 7afe085d-1a52-56ff-9fef-5f6c40e3fd52 |  | note | Verifying Documents - ConQA Hold Point Release
text | 64d68c03-43eb-50f2-87cf-81af218a0c68 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.8 - Weather Conditions & Evaporation Limits
label | 01c37bf8-1a5a-5ac1-8b77-0bd744e0e3c4 |  | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
label | d455a339-9141-579b-95ba-029c5a5a11cc |  | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 7df65bd9-783a-5200-9181-2cacc8b19310 |  | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 841b0326-ba53-5167-a1ca-8489ac2871e6 |  | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 0d8c9813-1b1a-5f21-a70c-147aae31ac32 |  | note | • When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | 57eabf29-3c98-5d7a-9bc8-4b3a2665db69 |  | note | Record: Required information on the Concrete Pour Record.
label | b0182d67-8a7e-5b27-aa05-49c40d409a3e |  | note | Method - Measure, Visual
label | 3af144a4-d2b7-5d75-8941-0ca826dfbe19 |  | note | Frequency - Each pile
label | addb3a1f-970b-5a4e-8801-cec383bf9347 |  | note | Category - IP
label | 2a572dfb-41f1-53be-b5c5-14e8fe2ad5d7 |  | note | Responsibility - Foreman, SE/PE/SPE
label | be616ec0-b313-5b9e-82f1-7e021247037b |  | note | Verifying Documents - This ITP
text | 5736ff18-b456-5dd8-a998-cf60bf5f83e0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 - Concrete Testing - Sampling Frequency
label | a8ac749e-48eb-5176-b330-80d8cfbaba0f |  | note | Reference - Site Sampling & Testing Procedure 610.16 (b) Table 610.161
label | a428b53c-a748-56ab-97da-8e710c088066 |  | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 01f9ecb5-16cd-57d9-bbbe-3652617482e3 |  | note | • 0m³ to 10m³ = 1 sample
label | 97489ab9-c01a-5629-8517-f1b6c27fc659 |  | note | • 10m³ to 25m³ = 2 samples
label | 40293a3c-ec10-52b1-8137-080e66348e8f |  | note | • 25m³ to 50m³ = 3 samples
label | 0c797d15-bb8b-5650-95ae-7898de01b38c |  | note | • 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | ae5a7495-ac36-5427-bd47-ae625bca663d |  | note | ○ For each additional 50m³ and additional sample shall be taken.
label | 41c629b4-658b-5ebd-a19e-95d208d178bd |  | note | ○ where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
label | 3186641b-5786-5247-9f88-ec278a0eb7b3 |  | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | 0d507ecc-5efb-5682-8c5e-de25d351f8c1 |  | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | 5ab32254-0f39-5a55-b936-924da5a63a4b |  | note | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
label | 224d93ee-e6a8-5d6f-84eb-8f5186430cb7 |  | note | Record: Required information on the Concrete Pour Record.
label | 1cc8f27b-8ce2-59f5-8e6d-80f15969bd59 |  | note | Method - Test
label | 564d1b74-88b4-5104-8105-4b00708d7727 |  | note | Frequency - Each pile
label | a0de3e8c-6078-5cf5-bb5d-221adf0f7899 |  | note | Category - IP
label | dc7ddb89-6456-56c9-bb4f-2729533af90a |  | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
label | 259aec42-9d3b-5f9e-9783-8a08079be40f |  | note | Verifying Documents - This ITP
text | e61c9fb5-3de0-5af6-bfe2-3d78396f4c37 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 - Concrete Testing - Spread, Passability & Viscosity
label | c50304c0-a508-58ea-8ae1-3e9bbc15a952 |  | note | Reference - 610.13 (b)
label | cea33701-f9cc-5a83-a318-f6b6319fbad5 |  | note | Acceptance Criteria - Spread range = 550mm to 750mm
label | 2395d27f-fdf2-59aa-b7f0-268cdc489bdc |  | note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | a010b04c-6d28-53a8-aedd-732d9456fee7 |  | note | • Passability = ≤10mm (aggregate height differential)
label | d1d80c52-2a39-5002-adf6-b1b8552f7d21 |  | note | Record: Required information on the Concrete Pour Record.
label | 95f31521-72d0-5dfc-8642-746ede2eece3 |  | note | Method - Test
label | 72ce3045-7603-5aff-9d67-994c50c72e14 |  | note | Frequency - Each sample of Self-compacting Concrete
label | cd7d726c-512e-595a-aa99-397dadcadce5 |  | note | Category - IP
label | e8961b09-00ce-595c-b138-5b43aea05c27 |  | note | Responsibility - Concrete Tester
label | 19d7f9a1-792b-5736-b438-6349f70ca4d6 |  | note | Verifying Documents - This ITP
text | 91262c33-ef3c-5369-a36e-011909452a57 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 - Concrete Testing - Compressive Strength Cylinders
label | 498bf912-5031-56db-9f30-84b3e8aa9159 |  | note | Reference - Site Sampling & Testing Procedure 610.16
label | 77f92e38-7eb0-5f43-827c-8a64fe154fa4 |  | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
label | e8329f3c-2bdd-5df0-bd19-abe22904d7f4 |  | note | Record: Required information on the Concrete Pour Record.
label | 0c161da9-e06f-5820-ab19-58bb496af78f |  | note | Method - Test
label | 82114fe6-f2a6-52af-be59-246ff5f6bdd5 |  | note | Frequency - Each sample
label | a015c77e-120d-564e-8e69-6681ad252438 |  | note | Category - IP
label | beb8dbad-5c5e-5627-a0ca-39204eff4827 |  | note | Responsibility - Concrete Tester
label | 01f8c5e5-1441-5901-a779-a136b6a9fa90 |  | note | Verifying Documents - This ITP
text | 7d61cedb-3b32-5327-bce9-fc1c839fc7ea |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 - Placement & Compaction (Dry or Wet Excavation Conditions)
label | 50f5461d-d33b-5b71-a034-93ddc144cf84 |  | note | Reference - Piling Quality Procedure 610.18 (a) & (b), 610.18 (d) (i), 606.06 (a & b)
label | 3495ec75-4557-5fff-899e-ae6c6b9975e5 |  | note | Acceptance Criteria - Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
label | 077d25b6-87f8-59eb-9795-0307f81f603c |  | note | • All concrete batches are traceable.
label | 392ca1c8-34d8-5133-9bbc-11fcadfbcf28 |  | note | • Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
label | 65a996e5-de5d-5ad6-b57e-c8c6d402d304 |  | note | • The initial discharge is pumped to waste until a consistent workable mix is discharged.
label | 58906133-50e4-5599-9105-57012729efee |  | note | • the ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
label | 0f2e4f18-7f1b-535f-9e99-2bc59fbe65b5 |  | note | • Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
label | 789e32d2-2d4c-543b-802e-7981f162bf40 |  | note | • Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
label | 74f80b59-d3c0-5628-99ec-9cd4409060b0 |  | note | Record: Required information on the Concrete Pour Record.
label | 7f7bcfc0-5bca-5a70-80be-04bc3359df98 |  | note | Attach: Concrete Pour Record
label | 94cb4a78-3ef7-5875-804b-223b5738c198 |  | note | Attach: Concrete Dockets
label | 6856b66b-72c6-5a5f-8711-102abef51f5d |  | note | Method - Visual
label | 3467b85d-0218-54b8-bb71-c75933af15eb |  | note | Frequency - Each load
label | 7b632bab-0c58-517d-9900-b84c79e379a1 |  | note | Category - SP
label | 10e86cc3-6161-5a18-aa25-8b06ef280317 |  | note | Responsibility - Foreman, SE/PE/SPE
text | 65b00a6d-3526-5536-b70e-d0ed6d55825b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 - Surface Finishes
label | 8ab540c6-0549-5637-b0f7-5682b00e5430 |  | note | Reference - IFC Drawings 610.31, 610.20
label | 2a0fbe2e-f68f-5dfe-a548-9c915c1c9544 |  | note | Acceptance Criteria - Surface finish as per IFC drawings.
label | 34a068a4-827e-52c6-929f-b56877992595 |  | note | Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | c5b3d4ce-f8fb-5652-b688-5632839514ed |  | note | Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | 524c2986-849e-5168-9399-edbc4f36399e |  | note | Method - Visual
label | 6dd14904-d372-50f7-8873-d7a51e762e3f |  | note | Frequency - Each pile
label | 2653eeaa-84e9-506a-96c5-2d6779fe4404 |  | note | Category - IP
label | d19c9d3a-4a35-5ced-9493-c4fc72011c96 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 65370567-7b84-50ba-8951-eb08e6b9cb79 |  | note | Verifying Documents - This ITP
text | 82112d01-7b66-565d-a3c4-e3c8f780e2c5 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Pile Trimming
label | 4af8e301-96f4-5c22-a06a-3597c3db0871 |  | note | Reference - IFC Drawings AS2159 Clause 7.2.2 - 3, 606.06 (a & b)
label | 57462bbf-fffd-548a-9080-e98f36b8f046 |  | note | Acceptance Criteria - Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
label | 513230ec-c76a-56f9-81c4-b9c6ab93800a |  | note | • Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
label | 6b35115c-5a41-5f63-9515-531a28e130fe |  | note | • Any weak or damaged concrete shall be removed back to sound concrete.
label | 8ad4fbd8-1819-5493-8bcb-ebaffaf5d8f6 |  | note | Method - Measure, Visual
label | 94a38309-3711-5b5a-a12f-d8b6e25eab1b |  | note | Frequency - Where applicable, each pile
label | 9eb4f118-a4a1-5146-845d-36d88458ab69 |  | note | Category - IP
label | 40b67f49-0dd2-54e8-aaee-2613484e895d |  | note | Responsibility - SE/PE/SPE
label | 21e3755c-36e4-5258-8565-78b009b927a2 |  | note | Verifying Documents - This ITP
text | ed0ed1b7-34c0-5bd3-a9cb-058ca5dfe7d9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Compressive Strength Test Results
label | 00800f81-04d1-5b0e-a49c-f2fcb758883b |  | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
label | d9671c21-3380-5453-9498-d443acb6ae02 |  | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | e67d52e4-c612-5724-9af8-84b9fa246105 |  | note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 1fd1bcb1-d2d8-504c-8044-b426f3364ee8 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | a4197524-ccd9-5064-8984-3bc408c19eb6 |  | note | Attach: Compressive Strength Test Results
label | 05802d91-48c8-5c04-9f8a-e0f05aa3ed7c |  | note | Method - Document Review
label | 131061ef-7b2e-5daf-b124-556df8f9cc89 |  | note | Frequency - Each cylinder
label | ef05b7f2-fe31-5745-b417-572f3a373606 |  | note | Category - IP
label | 89aea3b0-671e-5748-bc4e-76ca2381886f |  | note | Responsibility - SE/PE/SPE
label | 5b3700f9-cd24-52be-b3f3-bcb5585ef23f |  | note | Verifying Documents - This ITP
text | 27019cad-7c8d-5ab8-850b-72b9905f445b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Pile Integrity Testing
label | d08293cb-c9f7-5e84-8ca9-176a7c3037cd |  | note | Reference - 606.07 (a, d & e) AS2159 Clause 8.8
label | 2502d88e-6e25-5f40-b2ff-3a3594b95fef |  | note | Acceptance Criteria - Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
label | eed571e4-dc37-5ca4-a3b5-661746583a0d |  | note | • Cross-sectional area = ≥95%
label | e7b5bf39-1546-56b7-b662-386351fe4949 |  | note | • If any test fails, all piles shall be tested.
label | b32bf22b-8cb7-5389-94f3-d820ec4e6d2e |  | note | Attach: Pile Integrity Test Report
label | 481224b3-970b-5205-8cc6-54b151088e74 |  | note | Method - Document Review
label | ebc1ef1a-39b3-50fc-adb7-ec835c4e00f9 |  | note | Frequency - Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass
label | bd57d94f-25ab-5bbb-b98e-6f412261de56 |  | note | Category - IP
label | 43c5efe2-6a68-525e-a8b7-fbe061f111bb |  | note | Responsibility - Testing Consultant, SE/PE/SPE
label | 51b75e46-79dd-5184-80e9-1cd5b9cc8c65 |  | note | Verifying Documents - This ITP
text | 0b5e482d-a0dc-5582-b750-caf8c25bc14d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 - Static Load Testing
label | bb3e1383-3fc9-5bf2-801a-8e8e8273f23f |  | note | Reference - IFC Drawings 606.07 (b, d & e) AS2159 Clause 8.4
label | c7ebcbc3-949d-50d7-a1b4-b7d58fd43b81 |  | note | Acceptance Criteria - Static load testing to be conducted on the designated piles as shown on the IFC drawings after the concrete strength has reached the 28 day compressive strength.
label | eb1655fe-e3b9-543a-8e87-c0422fad802d |  | note | i. Displacement vs Time Graph = linear or decreasing rate of creep
label | 57dffeb7-c639-5b57-9603-5143dd28a2fb |  | note | ii. Creep rate = <2mm / log cycle of time at the test load
label | 6e615506-14e1-58f7-99d5-23d996442b2c |  | note | iii. Maximum pile settlement and lateral displacement at the design load = < values on IFC drawings
label | 2a02f7b3-2393-5efa-bf5f-6579a2179907 |  | note | Attach: Static Load Test Report
label | 582f95eb-89f6-52ed-a42c-359ee650c629 |  | note | Method - Document Review
label | 5bc9f1a0-de25-5ec5-8f2d-1499a692278a |  | note | Frequency - Where applicable, as shown on the IFC Drawings
label | 6131c4c6-6d58-5b75-ae28-caf3b8a90d3b |  | note | Category - IP
label | 53fcf8ee-5a0b-5a3e-af6a-2f62ad575f31 |  | note | Responsibility - Testing Consultant, SE/PE/SPE
label | 0955070d-08ab-5025-b845-25e3fc6d4175 |  | note | Verifying Documents - This ITP
text | 81883927-3da1-5755-aa7c-2ad8faf168b1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 - Dynamic Pile Testing
label | 6e7800f9-ec5d-518b-afc4-e51dceb1b554 |  | note | Reference - 606.07 (c, d & e), AS2159 Clause 8.7
label | e7ee23fe-366b-58af-bc60-3c5054b05dd8 |  | note | Acceptance Criteria - Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
label | f2a32143-d929-5f9a-9eee-64619d12624f |  | note | • Measured Ultimate capacity = ≥ values on IFC drawings
label | f993cc28-a30a-52c6-ba17-83dfcf5068bd |  | note | Attach: Dynamic Pile Test Report
label | 4ca71fe8-6361-5cf0-9782-02f6a3a34c8a |  | note | Method - Document Review
label | 26c93876-4132-5aac-97ea-81474c292fe0 |  | note | Frequency - Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile. At least 1 test per 10 piles
label | 75cf3c85-4cbc-5a1b-9e26-c8e779e4316f |  | note | Category - IP
label | 1c5e918c-b0fd-58b4-a3cf-47f58edf26d6 |  | note | Responsibility - Testing Consultant, SE/PE/SPE
label | ad7a6b35-e228-5d59-981b-de9c4b4e90f3 |  | note | Verifying Documents - This ITP
text | 0bf1011f-b840-5f23-b9f9-3a9bfe9a1b37 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 - As-built Survey
label | e210b520-0d29-5adb-9bba-ed0ff3ffe4b6 |  | note | Reference - IFC Drawings 606.08 (a - c), AS2159 Clause 7.2.2
label | d9cc5fa4-2e41-5d59-ad78-59a2af6f192f |  | note | Acceptance Criteria - The following tolerances apply to piles:
label | 11b9fcf9-ddaf-5e07-a95c-40edfe180db3 |  | note | i. Pile head plan location = ±75mm
label | 13c164b7-9184-5afc-a4f2-796ef4186f11 |  | note | ii. Variance from vertical or rake = 1:100
label | 927d25e5-7fa6-5f41-ad37-37c8c5172536 |  | note | iii. Irregularities in straightness = 1:100
label | 881c4620-ba37-5b61-aa82-1b7735a81455 |  | note | iv. RL = ±25mm
label | 5c0ae95e-dda1-543e-94ac-f930da1e58c8 |  | note | Attach: Survey As-builts / Survey Report
label | fb9bd508-5768-5edd-ae9a-2de3bd11c7cc |  | note | Method - Document Review
label | 2025aadb-9b87-5af1-b424-f9a720d97c2d |  | note | Frequency - Each pile
label | 25839e40-57b8-5b79-9192-fd744cbdf541 |  | note | Category - IP
label | e4e0712d-66b9-5234-830e-d4eb3b55a3d8 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 5234d5b7-0bdf-52dd-af6e-bb5d7d0fe9b2 |  | note | Verifying Documents - This ITP
text | bb115e70-f532-5135-aaf4-2212c5170e81 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 - Non-conformance Report (NCR) Closure
label | 15bb5809-c770-53ae-a21d-6d42d1ec0132 |  | note | Reference - MRPA Quality Management Plan
label | 3634dacd-dee7-5df4-bccb-9b857df9b3c5 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 3748ef3c-af8d-5033-925f-7fe9fca118ee |  | note | Method - Document Review
label | 66a34beb-791f-5600-96e0-7a27cebe2f1f |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 0cd02d17-19bf-5562-bb81-efc65d17b789 |  | note | Category - HP*
label | d9039f95-6d2f-5ea5-9fd7-adea2711689d |  | note | Responsibility - SE/PE/SPE
label | abadb37b-ae2a-5d72-be92-561b79eb911c |  | note | Verifying Documents - This ITP
text | 4edb2188-9c84-5248-bfa5-ef7ec6ee42fd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 4b9eb61b-e649-5927-a92b-6f76a54f79cc |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 9501bf7f-0768-5dec-8503-7e148a57b4c2 |  | textbox | Name:
text | a1806edd-8307-58fa-bf09-403bfef965dc |  | textbox | Position:
text | aed64315-ebdd-59b6-b933-4e4a7140e9fe |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP