## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection | itp |  |  |  |  | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection Rev 1
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
label | ITP Description: Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 1
label | Revision Date: 09/02/2024
label | ITP created by: Pradeep Talasila
label | ITP approved for use by: Aldrin Guinchoma
checkpoint | 1 - Materials - Fabrication
label | Reference / ITP Reference - IFC Drawings Section 620, Section 701
label | Acceptance Criteria - (1) Precast items manufactured in accordnace with IFC Drawings
textbox | Drawing Ref No.
label | Method - Visual Inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - Material Delivery Docket
date | Date Completed:
checkpoint | 2 - Materials - Delivery
label | Reference / ITP Reference - IFC Drawings Section 620, Section 701
label | Acceptance Criteria - (1) Purchase Order and Material Description and Qtys matches
label | (2) Ensure precast concrete elements are as per IFC Drawings upon delivery and no damage evident.
label | (3) Lifting and Manufacture compliance certification provided
textbox | Purchase Order No.
label | Method - Visual Inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - Material Delivery Docket, Purchase Order
date | Date Completed:
checkpoint | 3 - Materials - Manufacture's Certificate of Compliance
label | Reference / ITP Reference - IFC Drawings Section 620, Section 701
label | Acceptance Criteria - (1) Ensure Manufacturer’s certificates of compliance are received for precast RCP during delivery on site and min required strength is achieved prior to transporting.
label | Method - Visual Inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - Material Delivery Docket, Compliance Certificate
date | Date Completed:
checkpoint | 4 - Materials - Delivery to site
label | Reference / ITP Reference - IFC Drawings Section 620, Section 701
label | Acceptance Criteria - (1) Identification of product is legible (Stamp, Label, Etc) and should be marked on every precast element.
label | Method - Visual Inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - Material Delivery Docket
date | Date Completed:
checkpoint | 5 - Materials - Others
label | Reference / ITP Reference - IFC Drawings Section 620, Section 701
label | Acceptance Criteria -
textbox | (For Additional Comments)
label | Method - Visual Inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - Material Delivery Docket
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
holdpoint | Sign ITP