## Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | 0. HB AWPT ITP - Material testing |  | 0. HB AWPT ITP - Material testing | 6f0eff6d-fb94-4996-883c-3e6cf7dfade8
| section | Basecourse Material Testing
| checkpoint | Approved Aggregate
c017c45e-8ae3-5af5-ae1e-0ba4fe6c4834 | note | Specification Reference - TNZ M/4 Table 4
3cf95b2d-a775-538f-894a-e3ad1c3a29de | note | Test Required - Grading
0b9a8f3d-a9fb-5e76-a67f-411bcc12e27f | note | Task Timing / Minimum Task Frequency - 1 independent test per 500m3, prior to basecourse placement
b2dab19f-01f1-5f43-a7c0-a7cc1a45d702 | note | Task Assigned To - IANZ accredited laboratory
9150971a-6824-5833-9051-f1e70cd69df8 | note | Measuring Devices or Method - NZS 4407:2015, Test 3.8
f5ee4eed-1783-50cf-b656-592431211b12 | note | Criteria - Napier River Gravel
654a2ea8-5799-5f66-8b5b-e336ece54d02 | note | ○ 78-100% 26.5mm
ae9a531c-b73b-5437-9f04-721b42a602ef | note | ○ 13-25% passing 1.18mm
9c3e6dd2-c614-5207-af63-2db46e1a4e33 | note | ○ 10-19% passing 600µm
14fd0390-c81e-5426-b543-321b503d4ed1 | note | ○ 7-14% passing 300µm
32347d23-dcec-565f-b0d7-4076567cd0e4 | note | ○ 5-11% passing 150µm
824581e9-8ffc-52d1-ad73-1b5a5a613739 | note | ○ 3-8% passing 75µm
6f1f7e98-3e0e-58a3-8645-225987bfe26e | note | QA Form - QA Measurement Sheet
| section | Bitumen Manufacture
| checkpoint-no-value | Note: These tests are reproduced from NZTA M/1 for information only. A copy of current approval letter will be required for each grade and source of binder used on the project to verify the binder is approved.
| checkpoint | Penetration
6179c817-5d35-5341-aaff-ead72d577e1f | note | Specification Reference - NZTA M/1 Table 1
346928ac-ff67-5c8d-9775-f3bd34bb8ab2 | note | Test Required - Penetration at 25°C, 100g, five seconds
25d5ac43-893f-5e92-928a-ae106beb2e43 | note | Task Assigned To - IANZ accredited laboratory
9c3508e2-35c2-52de-b1da-f342a54b9022 | note | Measuring Devices or Method - ASTM D5
| checkpoint | Viscosity (1)
360b0a5b-72e2-5b50-af96-360bb42e5d2a | note | Specification Reference - NZTA M/1 Table 1
522e6d56-3f25-581d-aa36-1c3e31b17190 | note | Test Required - Viscosity PaS at 60°C
f3df050f-d6f4-54e0-8405-f48d4d5e0013 | note | Task Assigned To - IANZ accredited laboratory
ef06f4b8-a792-5a10-b392-602648c4040e | note | Measuring Devices or Method - AS 2341.2 or ASM D2171
6d614ecc-0d5e-5dc2-8384-3d8117e058a1 | note | Criteria - Complies with requirements for penetration grade as per TNZ M/01 Table 1.
| checkpoint | Viscosity (2)
7c625f0f-2628-5a45-848a-bab9d875ae16 | note | Specification Reference - NZTA M/1 Table 1
b5811269-afaa-541f-b3de-3d942a9ff1bc | note | Test Required - Viscosity mm2/s at 135°C
5a95aede-b5c1-54a2-9654-5a759b5aefda | note | Task Assigned To - IANZ accredited laboratory
0eaefcf1-efef-5161-b609-64f2b9bf4c75 | note | Measuring Devices or Method - AS 2341.3 or ASM D2170
b749a0f5-1b28-5d9f-b275-f2fc86690cf9 | note | Criteria - Complies with requirements for penetration grade as per TNZ M/01 Table 1.
| checkpoint | Flash Point
31fcb9d1-7eea-54d5-8d6a-6d24ef18c644 | note | Specification Reference - NZTA M/1 Table 1
530fe060-2820-51b1-a009-aa105b443b7b | note | Test Required - Flash point (Cleveland open cup), °C
90186177-0247-5b24-b563-f5da709ec26e | note | Task Assigned To - IANZ accredited laboratory
9a65d397-2f20-5bd0-a943-571839ade8d2 | note | Measuring Devices or Method - ASTM D92
8f44496e-ba26-5edf-bdcf-00c1a4f78f08 | note | Criteria - Complies with requirements for penetration grade as per TNZ M/01 Table 1.
| checkpoint | Solubility
c4505d32-4a0d-5a47-9e43-83891bfb4abe | note | Specification Reference - NZTA M/1 Table 1
e571232a-6f95-51d0-8668-fb3dbbfaceed | note | Test Required - Solubility in Trichloroethlyene, % or Solubility in Toluene, %
fde38550-1b9c-5bad-a265-e29bdc597786 | note | Task Assigned To - IANZ accredited laboratory
ea69d6c9-d14a-5b0e-9e3e-5cf4e895ff49 | note | Measuring Devices or Method - ASTM D2042, AS 2341.8
44913f61-54fa-5b1b-859b-ec9fecaaa363 | note | Criteria - Complies with requirements for penetration grade as per TNZ M/01 Table 1.
| checkpoint | Penetration
d549c673-aefd-5b44-95b9-a9a90276f114 | note | Specification Reference - NZTA M/1 Table 1
994fa4b5-506e-5e04-9526-2d2840b75e77 | note | Test Required - Penetration of residue, at 25°C, 100g, five seconds, % of original.
b1a62323-5111-52e3-8336-0e0e3a8695de | note | Task Assigned To - IANZ accredited laboratory
425e7f7e-c965-54c0-b38f-4d7d499c1def | note | Measuring Devices or Method - ASTM D5
52de6447-eda0-5b0c-99b6-c30abcbd4e60 | note | Criteria - Complies with requirements for penetration grade as per TNZ M/01 Table 1.
| checkpoint | NZTA Approved
1f589101-c5d2-53de-8269-e1d50e5ded41 | note | Specification Reference - NZTA M/1 5
ec289500-b296-5ced-9de8-77fd7c09fa6e | note | Test Required - Letter from NZTA
135576f0-197d-5981-ac17-6edd1031bac1 | note | Task Timing / Minimum Task Frequency - 1 per source and grade of binder used
4f80bb70-152f-50ea-bddb-b614e5a1ee9c | note | Task Assigned To - NZTA
973f7b92-83cc-5dbd-934d-b8c58b356a5d | note | Criteria - Complies with requirements for penetration grade as per TNZ M/01 Table 1.
| section | Sealing Chip Material Testing
| checkpoint | Crushing Strength
4f71f51f-e5d0-54e2-92c6-c819adb96843 | note | Specification Reference - NZTA M/6 3.2
b0a57ef5-b46a-5262-a4af-18442a8c26e7 | note | Test Required - Crushing Resistance Test
a934d8fa-1873-55c3-a041-dab8b3cdeb68 | note | Task Timing / Minimum Task Frequency - Once per year - 1 test
f4c62ad8-b3be-5ad6-8400-27aee43c6329 | note | Task Assigned To - IANZ accredited laboratory
10200ec6-aee5-5029-a411-8950cbfd654d | note | Measuring Devices or Method - NZS 4407:2015, Test 3.10
36cc1bcc-c0c8-5a44-8206-459b397a3106 | note | Criteria - <10% fines passing 2.36mm under 230kN load
| checkpoint | Weathering Quality
60532d02-2e0a-5a50-af48-6c8025311518 | note | Specification Reference - NZTA M/6 3.3
c4fe07af-440a-5c7d-998e-47b45c127ca8 | note | Test Required - Weathering Quality Index Test
5e915326-569e-525c-8845-795039e55933 | note | Task Timing / Minimum Task Frequency - Once per year - 1 test
f1d3f483-db53-596a-9e8c-cff8da332d15 | note | Task Assigned To - IANZ accredited laboratory
c37de08c-1a07-5fdb-a730-9ccd74ff57f3 | note | Measuring Devices or Method - NZS 4407:2015, Test 3.11
02a94bc5-4584-5bd7-8fcd-04ad00e8fdc4 | note | Criteria - AA or BA
| checkpoint | Weak Particles Test
af28feb1-b9fd-5d80-be2a-2b8b6d442533 | note | Specification Reference - NZTA M/6 3.4
9db43972-2677-5d5c-a7b4-91d032dae678 | note | Test Required - Australian Weak Particles Test
b9a0bab2-91f7-595d-a3ef-53cc30f3ad06 | note | Task Timing / Minimum Task Frequency - Only undertaken in case of dispute.
69711a32-2ec4-5a40-b27c-1d7d5545c93c | note | Task Assigned To - IANZ accredited laboratory
ff50e7ce-7dd6-5246-b24e-e33d0e810ccd | note | Measuring Devices or Method - AS 1141.32-1995
1829a69c-77f6-5ea3-b5e0-1dc4dc4a912a | note | Criteria - Maximum of 1%
| checkpoint | Polished Stone Value
d3e4b7d1-c2f8-5f08-bd66-67fcff080de4 | note | Specification Reference - NZTA M/6 3.5
3a83d399-ab91-5a24-ba4e-e8d1d31210d9 | note | Test Required - Polished Stone Value Test
8ee42d69-43b4-5f19-b9c1-d4099000fe8d | note | Task Timing / Minimum Task Frequency - Once per year - 1 test
f8fcc0ca-cf13-5139-8db8-d9aba33d4226 | note | Task Assigned To - Accredited PSV Testing Agency
abc34548-a397-5ae6-8c86-2f8a160647ee | note | Measuring Devices or Method - BS 812 : Part 114
ff3f84b8-f6ff-51ad-99b3-61c4dfb8e54e | note | Criteria - PSV Required = 53
| checkpoint | Cleanliness
c5c4da20-4665-577b-864e-69de67a09f7d | note | Specification Reference - NZTA M/6 4.1.1.
09612193-458a-54e4-be93-9ef4921326b2 | note | Test Required - Cleanliness Test
ef2b9ef3-1596-5cbd-8f86-2e61996d788b | note | Task Timing / Minimum Task Frequency - 1 test per 500m3
8706c9b2-8b10-5465-822c-4076b34bdfc8 | note | Task Assigned To - IANZ accredited laboratory
2f65b834-f1b9-5c29-b2ea-005955d72060 | note | Measuring Devices or Method - NZS 4407:2015, Test 3.9
8328f7e4-678c-53f3-98dd-ab012624fd36 | note | Criteria - Grade 3 - 87 min, Grade 5 - clean & free of soft, weathered, disintegrated or deleterious material
| checkpoint | Size & Shape
0e83be57-01a1-51fc-a3c8-0e356e2dc6ed | note | Specification Reference - NZTA M/6 4.1.2.
c4424ee7-128e-5b65-9ce1-987c8237a252 | note | Test Required - Size & Shape
6aaf5de2-2868-5f15-af86-a9ec1ddde554 | note | Task Timing / Minimum Task Frequency - 1 test per 500m3
bed06d01-3201-5e7c-acea-7e7905698bf6 | note | Task Assigned To - IANZ accredited laboratory
d370c5ce-86f6-5024-8f95-d44a4600b00e | note | Measuring Devices or Method - NZS 4407:2015, Test 3.13
aeb7f533-fcf6-5800-8154-bf8fed924ec1 | note | Criteria - Grade 3 - ALD 7.5 - 10.0, 70%Min within 2.5% ALD
| checkpoint | Broken Faces
bb4753e0-13a2-5929-a0dc-61496f4f9778 | note | Specification Reference - NZTA M/6 4.1.2.
b325156b-430a-50fc-95a5-4bf292cd78bf | note | Test Required - Broken Faces Test
b1f2d179-7537-57c6-b2b5-d7347c9f833a | note | Task Timing / Minimum Task Frequency - 1 test per 500m3
928b259d-29f5-5871-91df-3ddb1ff43e3b | note | Task Assigned To - IANZ accredited laboratory
9f8afcb3-aed5-5027-b42b-e78df0852083 | note | Measuring Devices or Method - NZS 4407:2015, Test 3.14
27188844-b216-5a01-85f1-db3beb158c9e | note | Criteria - 98% with minimum two broken faces
| checkpoint | Grading
76e2708d-ed78-592e-91b4-0080c1da5a3c | note | Specification Reference - NZTA M/6 4.2.2.
d59a2369-8015-5537-88f3-1d1a1dedfaf5 | note | Test Required - Grading
cbf3bb47-9933-5b22-9f64-545cbe5e6c55 | note | Task Timing / Minimum Task Frequency - 1 test per 500m3
dddccb3d-5835-50c1-be6e-6ea2aa27174b | note | Task Assigned To - IANZ accredited laboratory
18978e38-c1f8-5cdf-92df-9fa28e961540 | note | Measuring Devices or Method - NZS 4407:2015, Test 3.8
e6f92b91-b0d0-5164-b094-232186d7a3c1 | note | Criteria - Grade 5: 95-100% passing 9.5mm, 0-8% passing 4.75mm, 0-2% passing 2.36mm
| checklist | 1. HB AWPT ITP - Nth Rakaipaka |  | 1. HB AWPT ITP - Nth Rakaipaka | 5229d904-5dd5-414a-940f-1ceeb7f613d6
| section | Preliminary / Establishment
| checkpoint | Establish TTM
2346e8e4-c7fb-5b41-afb3-de1f177ed1e4 | note | Test Required - Visual Inspection
f9a34cc8-c9ba-5681-a603-e15c7c5155ca | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
07e3ffa5-c8cf-5127-bcfc-63ec4e00f690 | note | Task Assigned To - STMS/Site Foreman
04209cc9-5caa-59ee-b666-92f2bf7fdf2a | note | Measuring Devices or Method - Visual
4dec6e74-ebeb-50b7-bca2-dea1483513ee | note | Criteria - As per TMP and ensure TMC advised in advance of works.
e4a44636-9b69-5c5e-8c93-e20d144379df | note | QA Form - Daily Diary
| checkpoint | Permits
509533f9-3b95-58b6-b4eb-d1fa8bcdf108 | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
6100b311-96ca-5347-8af2-5e0874cc1c6b | note | Test Required - Document Review
8c5ab6e3-cb0c-5312-bbb8-fbcbc6e6c1ad | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
e9589a34-2639-519e-90ea-00243c515515 | note | Task Assigned To - Site Foreman
80e1c81a-78b1-5fa8-a80e-40ff6c0e947b | note | Measuring Devices or Method - Visual
9a0138bd-fcc2-58d9-8708-c26635d641b7 | note | Criteria - Obtain permits and mark outs prior to construction
1597436b-2d87-59af-b416-d94dcef3b74f | note | QA Form - Copy of Permit on site
| checkpoint | Clear-Shoulder and Side drain
c185533d-fe02-58cd-a94d-1c1d927f04e1 | note | Test Required - Visual Inspection
adab292e-d0d9-547d-911e-663da7cb4a7e | note | Task Assigned To - Project Engineers/Site Foreman
1d93f184-5cd0-5876-bf27-4e219c6b4363 | note | Measuring Devices or Method - Visual
8fdc9879-3a5d-5bc9-abc9-397a93012c78 | note | QA Form - Daily Diary
| checkpoint | Digout Failed Areas
542c5bf1-af60-5a0f-89c4-80341ec7fff6 | note | Test Required - Visual Inspection
eb8e03f7-c1de-59b2-ba83-a4aff1d458eb | note | Task Timing / Minimum Task Frequency - As Requested
cfa993b8-56f5-5892-91d3-f529435f083b | note | Task Assigned To - Project Engineers/Site Foreman
0029a368-4ffc-5af1-bcaa-d61790420b4c | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
62245261-9e82-548d-adcf-028af1f68616 | note | Criteria - Backfill with Basecourse
b0cb6e09-acd8-56c6-ab5d-a969f223a2c1 | note | QA Form - Daily Diary
| section | Inspection Test Plan - In Situ Cement Stabilisation
| checkpoint | Cement for stabilisation
2d3c0755-008f-58a2-9bb4-f4f9ca5547da | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
d05ae5b7-0350-5579-b20b-ac8fa1560a11 | note | Test Required - Certified in accordance with NZS 3122
a9cf6809-6da5-5861-8144-9b5af8f503a1 | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
| checkpoint | Production plan
3859bc1f-e976-5f94-8dd7-5bf8f6d16c6f | note | Specification Reference - NZTA B/5:2008, 7.2.2
bd00eeba-6c7f-59c8-8456-5470471fe6fa | note | Task Timing / Minimum Task Frequency - 1 per site
| checkpoint | Stabilisation mix properties (including cement):
932b13e7-c0af-5457-81e8-c5ae834749b6 | note | – Maximum dry density (MDD)
f16b471a-86ae-5ab9-98b1-962cb2b0701d | note | – Optimum water conent (OWC)
8a94ae39-86d0-5f40-9052-e0a2c6b2616c | note | – Solid density (SD)
333716e0-dc14-5610-b118-22f8ae7ad7f3 | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
43dae03b-b69e-5011-81a1-58dfdf2ca1b4 | note | Test Required - Material properties for compaction verification
5e5d5d19-bbb7-5f08-8582-81957852db6e | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
743feb28-8864-50ba-85b3-3c8e73a91513 | note | Task Assigned To - Hold Point - Approval required by site engineer
407d4ee8-3e8f-5c95-b7ee-67a59104574a | note | QA Form - QA Measurement Sheet
| signoff | HOLD POINT
| checkpoint | In-situ moisture content of existing pavement aggregate
33678cc3-f3b8-50b2-a1c3-5c708710d585 | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
1807703f-1866-5660-8a5f-eaf977f1e191 | note | Test Required - In-situ moisture content Between 90% to 100% of OWC
7f71072f-581a-5682-97ed-a15241f3be90 | note | Task Timing / Minimum Task Frequency - As required
df47c37d-d585-56ee-a7ee-33241209d343 | note | Task Assigned To - Inspection - Lab
d4252f1f-39aa-575e-9cb1-45f080d8f0f2 | note | QA Form - QA Measurement Sheet
| checkpoint | Top-up metal
e8c9707b-89e7-5ad6-8280-8636e3dce2d9 | note | Specification Reference - TNZ M/4 Table 4
1426a3a0-d141-593d-852d-1b5e53a408f0 | note | Test Required - Placed to required depth and design levels
82c97a50-690d-50b0-9f5e-bcbb8ed4940c | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
db47c239-9591-5f96-9a34-88d7f1c17c2b | note | Task Assigned To - Site Foreman
db3114ed-6acb-505f-9444-f0c45c45f63a | note | QA Form - QA Measurement Sheet
| checkpoint | Cement spreading
3b13c9f5-2af0-5c1e-be38-b41b9a4383c9 | note | Specification Reference - NZTA B/5:2008, 7.3
605f4392-2a1e-5a5d-96e7-fffb389ca39f | note | – Mat test (1m2 canvas mat)
c7695b9a-dc64-59c4-aed9-52bf2d60d3ef | note | – Average usage test
04aef123-aaab-5164-b65e-392646551efc | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
1e167dff-44ea-585b-86b5-b1c95bc2d46b | note | Task Timing / Minimum Task Frequency - Inspection & sign off by Site Supervisor
b62e5c1b-b233-5851-be6c-776632478cdd | note | Task Assigned To - Inspection & sign off by Site Supervisor
2662eafd-e94e-5c11-8547-b6010766428c | note | QA Form - QA Measurement Sheet
| checkpoint | In-situ mixing - Cut depth
d806b182-88cb-51a7-a807-da5ce03bd164 | note | Specification Reference - NZTA B/5:2008, 7.6.1
50bc4b34-dd24-598b-8958-63d6cea4e225 | note | Test Required - Maximum variation -5mm and +15mm
7f1b3697-1778-5d6e-b3d2-85fca075131c | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
bd591b59-1f93-5163-bbff-df869bc3ca9f | note | Task Assigned To - Inspection & sign off by Site Supervisor
f2661985-3f6b-5b29-ae64-523b8b4c8b77 | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
0963015f-c6c8-5e2c-9d47-fe16fbedc568 | note | Specification Reference - NZTA B/5:2008, 7.7.1 NZS 4402 Test 41.3
264eccbd-bbe2-5c73-9e5c-60a378c7299f | note | Test Required - Plateau testing
a200c8fa-bb86-5919-944c-68b58bf793ec | note | ○ Mean value ≥ 98% of MDD
fd1173c5-492f-5b28-b49f-71aa27bb6d51 | note | ○ Minimum value ≥ 95% of MDD
8e28baf1-0cab-55ff-8635-7eee6cf5e3a3 | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
e40d9ce9-b575-55dc-90a4-b1749351ef5d | note | Task Assigned To - Hold Point - Approval required by site engineer
b29fd211-211a-55a9-86da-a53f189fad03 | note | Measuring Devices or Method - Nuclear Densometer
532ff4da-7519-5d73-9ab7-ec93d7c9c5de | note | Criteria - Minimum value 95% of MDD
90f99efe-8590-5307-bcc7-66bbfa12e340 | note | QA Form - Test Reports
| signoff | HOLD POINT
| checkpoint | Surface shape
cbef2b1a-3a06-5102-9ded-0809a638a7c2 | note | Specification Reference - NZTA B/5:2008, 7.8
a30a3ce0-677f-537f-bda1-7fda4160df2b | note | Test Required - ≤10mm from 3-metre straight edge, No depression, Vertical variations -5 + 15mm
88e919b1-f8ba-54fd-a888-274293d4e6e9 | note | Task Timing / Minimum Task Frequency - 20m intervals
644c7dfc-9195-5f85-a6ff-7a5e1bb09a75 | note | Task Assigned To - Inspection & sign off by Site Supervisor
b54f7e08-4ea3-557f-bd03-eac8610fef71 | note | Measuring Devices or Method - Stringing, Tape measure
ffe779a9-99cd-5bf8-8472-f0249a46cad7 | note | QA Form - QA Measurement Sheet
| checkpoint | Crossfall
56d3a123-4161-5321-ae4d-1b0722f0df1d | note | Specification Reference - NZTA B/5:2008, 7.9
5c16cecf-20e4-57e8-8a97-d2ad01f98496 | note | Test Required - Not less than exisitng crossfall at the start of construction
b5cfe9fe-dae2-5865-97a7-33c1b9b94e57 | note | Task Timing / Minimum Task Frequency - 20m intervals
864b1392-84a9-5295-9be9-6a6819350b7b | note | Task Assigned To - Inspection & sign off by Site Supervisor
7e5dd190-566c-5c05-a0d7-019959ae9be6 | note | Measuring Devices or Method - Stringing, Tape measure
8159318d-6ba1-5315-9088-7a37f023a107 | note | QA Form - QA Measurement Sheet
| checkpoint | Surface finish
38de163d-1adf-5aeb-9601-62e4c045a1d1 | note | Specification Reference - NZTA B/5:2008, 7.10
bebc45cc-f73d-5107-8442-c5d617de3ba3 | note | Test Required - See clause
a548da74-2fe1-5fd2-87ea-4e8f18a3d9fc | note | Task Timing / Minimum Task Frequency - 20m intervals
19ad890b-bf15-52bb-87b1-bd2a9040111e | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
a505d190-1e43-55a9-be24-a481eed833a5 | note | Measuring Devices or Method - Visual
| signoff | HOLD POINT
| checkpoint-no-value | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
| checkpoint-no-value | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
| section | Chipseal Construction (NZTA P29)
| checkpoint | Ensure appropriate TMP used
b5df889d-6ce7-591a-aefa-a3e8fe3973cd | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
| checkpoint | Seal design
932f78d5-11dd-58cb-a65f-5e14597bee16 | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
aec675aa-e450-56bc-bab2-5a1b4d34ebb9 | note | Task Assigned To - Project Engineer
023c01b3-ffcb-5770-ab2b-a9aaa3925bed | note | Criteria - Seal design to be reviewed prior to surfacing
1ef0ddc2-320a-56a8-9cbb-b5f49e6bbc88 | note | QA Form - Seal design template
| signoff | HOLD POINT
| checkpoint | Location/Size Confirmation
d815ab07-9ee0-57ac-b2c8-a4f1e3b8c151 | note | Test Required - Mark up extent of chipseal
4cf920f9-921b-54f1-a481-78a2ae40a1b1 | note | Task Timing / Minimum Task Frequency - Prior to surfacing
35a49727-7162-5d88-a243-1d49f005e998 | note | Task Assigned To - Project Engineer
f5b201e2-2644-57aa-8d6f-cb5507ac7ff1 | note | QA Form - Daily Diary
| checkpoint | Surface Cleanliness
eb53f897-d775-5f8c-b95d-40029d97f96f | note | Test Required - Visual Inspection
a852a750-81b1-5a2f-9b36-9c6de2487139 | note | Task Timing / Minimum Task Frequency - Prior to application of binder
8d226232-5668-50bd-a8ac-d7d8f45f8fe0 | note | Task Assigned To - Site Foreman
21a2187a-1740-58fe-8e17-bb780e4640f6 | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
7df651f5-6a55-5ca5-a9b4-29abaaa8bcae | note | QA Form - QA Measurement Sheet
| checkpoint | Plant Resource
36a1f0d3-39c9-58c2-88bf-656a3454280b | note | Test Required - Visual Inspection
7fcc09ff-cb36-5db2-b95d-0df375a1c799 | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
25b9b0d9-16be-5d66-8aee-c2920a3c8a55 | note | Task Assigned To - Site Foreman
23913796-c0ea-5bc5-aeb0-26e656a04c3a | note | Measuring Devices or Method - Visual
0d405182-a9cb-57b7-a008-ac19e0ba68e6 | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
0683dd3f-7464-5ca8-8edd-f7eae01955f9 | note | QA Form - Daily Diary
| checkpoint | Binder Application
0bd41cc1-45c3-5396-9663-4a48d9037b4b | note | Test Required - Binder type, Cutback, Temp, Application rates
3392ddaa-0b9e-53e5-8149-c15b6b398139 | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
bd24ee15-4c32-5fde-8e2f-f894d5722994 | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
ffd31dcb-4912-5924-a1c8-0df92da3cacb | note | Measuring Devices or Method - Visual
8692977a-4c6b-5d04-abaa-460168dd7876 | note | Criteria - Binder Type = 180/200. Cutback to suit 1st coat seal 4pph kero max. Temp = 150deg celcius min, Application = Design l/m2, +/- 0.1 l/m2.
16d2a7b7-8e33-5c13-9d9a-c32528cf4d43 | note | QA Form - Bitumen Spray Sheets
| checkpoint | Chip Application
82d0a6ea-e3b3-5da3-954b-82abfc2522f0 | note | Test Required - Chip type, Chip Application
69cdf642-1788-50bf-ac68-8a40ce8b2c8b | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
79ab55ac-3b00-532d-9314-5215bfa964df | note | Task Assigned To - Site Foreman
8b3a75d0-c2fb-56cf-bc8e-304ad7e499b5 | note | Measuring Devices or Method - Visual
96354846-e730-55cd-b35f-906cb3f1c3ad | note | Criteria - Trucks loaded with correct chip.
98cc0c9b-7ae5-5501-9bc7-231749971228 | note | ○ Chip clean. (G4/6 Racked example)
89e5234d-1ea3-5882-8859-abe4e6b6fbe7 | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
763345c1-c5f9-5dd9-ae90-e05929715cdc | note | ○ G6 application = Enough to just fill the voids around the G4.
09ec7806-0258-5de2-8a6e-e7e9ae5c8cbb | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
d88dfdab-b3ed-5541-b141-3d86d767ac58 | note | Test Required - Visual
1a591eca-fd2e-5c83-9149-53497430cb3c | note | Task Timing / Minimum Task Frequency - At completion of rolling
7bb589fb-095f-55ad-8393-b45258e0324e | note | Task Assigned To - Site Foreman
4dd35467-3e80-5343-b2d8-4bacce5c2fef | note | Measuring Devices or Method - Visual
84fb1976-59e4-582a-9a77-6d1dcda63b88 | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
28ab5d1f-ce52-56c8-aa81-b66130d2fb8a | note | QA Form - QA Measurement Sheet
| checkpoint | Site Measure
2521a57a-066e-5e33-969f-a6e5001b2537 | note | Test Required - Record final site measure
e8ce2965-dc27-5ffb-8592-c8ff649dcb7e | note | Task Timing / Minimum Task Frequency - Completion of works
3244e567-6cb1-5dd7-ada6-54adbe6e2326 | note | Task Assigned To - Site Foreman
bd32e130-b935-51ef-a226-9e7e47911732 | note | Measuring Devices or Method - Measuring Wheel or Tape
d863103d-da95-5365-85b6-a18b80f13f72 | note | Criteria - Sketch and record seal area and QA detail
16d0b647-9476-58e8-b788-f76385b1f6e0 | note | QA Form - QA Measurement Sheet
| checkpoint | Post Seal Care
a63f63eb-ec6c-5ade-93b4-5b3e6bf7bf58 | note | Test Required - Visual inspection
de203a03-4f85-56f3-925f-45e40a72d315 | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
ee5c2a90-ea46-58b4-af05-2863fbd33f8a | note | Task Assigned To - Site Foreman
33d4803a-ebb4-5e6b-bf8a-2ad08135573c | note | Measuring Devices or Method - Visual
5368a926-78e2-5167-88b4-74fada5fd994 | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
cd4e02cc-2c48-5f42-a9ac-d5ce5523570a | note | QA Form - Daily Diary
| section | Chip Removal, Pavement Marking, Traffic Services
| checkpoint | Removal of excess chip
72b3381f-1a06-5a86-ae48-207cddff1906 | note | Test Required - Visual Inspection
08c61188-cb2d-5351-bdca-61137efa4bdc | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
4b98b978-1df2-5d77-ac5d-6af3b7723222 | note | Task Assigned To - Project Engineers/Site Foreman
650563e2-d19c-5c1c-87dc-48520a10c474 | note | Measuring Devices or Method - Visual
be0399f1-514b-50f2-bfe4-fce800aab142 | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
4d449fbb-f0bd-5506-9146-9ab81755b85a | note | QA Form - Daily Diary
| checkpoint | Pavement Marking
e916876f-24f9-5c73-a6ea-19f238d117fb | note | Test Required - Visual Inspection
7916175f-93b6-5b99-beb3-8185f5e9dedc | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
fa1e8f6d-2638-50ea-bfab-49655da2cd04 | note | Task Assigned To - Project Engineers/Site Foreman
6c497c2d-0772-5af7-8e50-0654b7a60472 | note | Measuring Devices or Method - Visual
a696641e-9ce4-5f74-a8d7-61ee0992c715 | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
00afd4a4-f0d8-5b7e-93af-de89d9e57f9a | note | QA Form - Daily Diary
| checkpoint | Removal of TTM
dabee641-5b3c-5133-be2a-6e62601a55f3 | note | Test Required - Visual Inspection
36ebfc46-e74e-533f-896e-badec09d4f3b | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
2814bb41-d20e-5753-a29b-ee808efb0214 | note | Task Assigned To - Project Engineers/Site Foreman
3bb7b767-1710-5c67-9744-27d9a10e9c9c | note | Measuring Devices or Method - Visual
f2ae9bb6-2811-54ff-890c-be5cff4704c8 | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
13842ba9-e3e2-5868-9a87-05bf259d6820 | note | QA Form - Daily Diary
| checkpoint | Traffic Services
e2784b90-dd4b-5be3-8e61-da315cadb3d0 | note | Test Required - Visual Inspection
f706ad98-3802-5b2b-a510-c180c43675c5 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
f9f87f9f-9006-555f-8edb-c7b42acc8ef8 | note | Task Assigned To - Project Engineers/Site Foreman
cc2cb8dc-66ac-50cb-9b30-05399192bfe9 | note | Measuring Devices or Method - Visual
be518738-34e4-58d9-b66a-819507f2b14b | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
28066207-6c35-5856-8759-825ad8bfa8a1 | note | QA Form - Daily Diary
| checklist | 2. HB AWPT ITP - Rakaipaka A |  | 2. HB AWPT ITP - Rakaipaka A | aa096b80-fe82-4153-bc7c-c4727be03e3f
| section | Preliminary / Estabilishment
| checkpoint | Establish TTM
9b29814d-eea4-5755-bd3d-77575baec9d1 | note | Test Required - Visual Inspection
c37b4ade-8c1a-5ea7-a101-02575dd0bb86 | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
22b21397-497a-5a2e-91ea-0423d1ee44e3 | note | Task Assigned To - STMS/Site Foreman
2272177a-01bc-5452-a943-916620e49585 | note | Measuring Devices or Method - Visual
380a4dbc-edd3-5267-8e03-152ee37b0715 | note | Criteria - As per TMP and ensure TMC advised in advance of works.
4b264fa6-1136-53c1-96d5-c63960dbfdd5 | note | QA Form - Daily Diary
| checkpoint | Permits
ae063b22-3163-57bf-864c-ae7ad215d0b5 | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
b611847f-0de1-508a-8659-f134c6c2b5ea | note | Test Required - Document Review
95c1cb24-a130-59d5-9a6c-4f397b7445b1 | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
46b2e041-0e60-50b8-8b09-f2f5b9e5ea5d | note | Task Assigned To - Site Foreman
816b1d3e-e339-5e17-baae-4e8def770f3d | note | Measuring Devices or Method - Visual
c5ce0072-f99e-50df-895a-b71ba4944390 | note | Criteria - Obtain permits and mark outs prior to construction
02286de0-2d96-5081-80f6-dec9ca41ad30 | note | QA Form - Copy of Permit on site
| checkpoint | Clear-Shoulder and Side drain
a0981b62-271d-5df0-961c-725a14747d4d | note | Test Required - Visual Inspection
8c6dcd87-42b8-5378-94d2-579949f4dec9 | note | Task Assigned To - Project Engineers/Site Foreman
97990be2-9e53-5263-94bb-f192c5c4d45f | note | Measuring Devices or Method - Visual
6e39ea0a-8ae5-559e-87f0-bf5a276cf76c | note | QA Form - Daily Diary
| checkpoint | Digout Failed Areas
8c3bdde8-7abc-53e5-acb0-c2d6b0607f27 | note | Test Required - Visual Inspection
d1bd66ce-48ae-5e65-8ebf-1c467410f7a5 | note | Task Timing / Minimum Task Frequency - As Requested
6e41ee67-1c68-5033-8fd5-7d6975c887f5 | note | Task Assigned To - Project Engineers/Site Foreman
b68c274d-8308-5015-816c-eb001bb29272 | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
0668f97c-0e5f-5b82-987a-ae0b8ec7baca | note | Criteria - Backfill with Basecourse
aa271a66-92c1-51bc-8b8d-101a6f601588 | note | QA Form - Daily Diary
| section | Inspection Test Plan - In Situ Cement Stabilisation
| checkpoint | Cement for stabilisation
5503e582-f4dd-52e5-b161-9ce191f32e51 | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
77a1c411-f9dc-5f5c-84d3-827efd33dea7 | note | Test Required - Certified in accordance with NZS 3122
24ea3da4-f5e2-5986-8151-c62fbea963ef | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
| checkpoint | Production plan
5727d58d-766e-51a8-a545-b3a64a2078b8 | note | Specification Reference - NZTA B/5:2008, 7.2.2
c54a9b7a-b7d0-5728-a893-95b2112d8fb7 | note | Task Timing / Minimum Task Frequency - 1 per site
| checkpoint | Stabilisation mix properties (including cement):
7984f5f1-060d-5cf9-8ae3-12bde3de896c | note | – Maximum dry density (MDD)
d555f958-91bf-5ffd-98ff-7084de334b31 | note | – Optimum water conent (OWC)
a503c2e8-7969-5e3a-abd4-6f10b988cbb8 | note | – Solid density (SD)
547c0b89-5d48-5249-b922-5676bce65145 | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
b4e50806-881a-5816-b270-fb01e5a3d66a | note | Test Required - Material properties for compaction verification
0b8e90cd-824f-5e76-bea2-f2269026f783 | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
db6b5f35-d23e-50f6-b893-3dcc51d5bfc1 | note | Task Assigned To - Hold Point - Approval required by site engineer
051f5a78-2b95-58b9-903a-e025df652a5f | note | QA Form - QA Measurement Sheet
| signoff | HOLD POINT
| checkpoint | In-situ moisture content of existing pavement aggregate
1522ad8a-f6e9-5824-8998-6e19f28d1ca3 | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
00ab3038-c841-5fee-adf5-8145774dd0a1 | note | Test Required - In-situ moisture content, Between 90% to 100% of OWC
75352996-b104-5c46-8d95-9463b65d68f2 | note | Task Timing / Minimum Task Frequency - As required
7d70aa49-2fd8-54fa-8fe3-6dd0d4dbae7a | note | Task Assigned To - Inspection - Lab
4dd2578f-308f-5fc6-b5bc-a719f8dc0469 | note | QA Form - QA Measurement Sheet
| checkpoint | Top-up metal
963989e4-2c50-55d0-b5c7-863c7227571f | note | Specification Reference - TNZ M/4 Table 4
770395d7-ab20-5868-abb7-dbd1ce5b7b4d | note | Test Required - Placed to required depth and design levels
bd97ef3d-6760-55c2-ba35-e86651379c6c | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
83ba94da-ca12-5f1b-8ad0-f4d02d4d0aa0 | note | Task Assigned To - Site Foreman
870722ed-61c2-5083-b9fc-6acd795ae897 | note | QA Form - QA Measurement Sheet
| checkpoint | Cement spreading
ffdde42c-ade4-5f4b-9d72-3a4d631e1aab | note | Specification Reference - NZTA B/5:2008, 7.3
b58c834d-ffbc-5bb3-ab18-95a0b7f825b6 | note | – Mat test (1m2 canvas mat)
9e0cacfb-9f33-5a60-861d-f36272e751b6 | note | – Average usage test
082eff31-4006-5e33-89de-280a57de6784 | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
a8974720-59f1-58d1-a0b6-03065be1d0a9 | note | Task Timing / Minimum Task Frequency - Every 400 m2, Upon emptying spreader and bulk tanker
e9532ce2-a1e7-5d39-bc43-4ecb545388e4 | note | Task Assigned To - Inspection & sign off by Site Supervisor
c383a181-15fe-527b-96aa-66d4992ce5d9 | note | QA Form - QA Measurement Sheet
| checkpoint | In-situ mixing - Cut depth
2f4ab3cb-2f79-5d8c-8dfc-c62f6cd48f4d | note | Specification Reference - NZTA B/5:2008, 7.6.1
368587bc-f100-5ad1-aa3b-3e9c09fe5872 | note | Test Required - Maximum variation -5mm and +15mm
40edcddf-ce98-5281-a256-f326b313c258 | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
cc10dab1-c06b-50f3-8fec-dadb276be392 | note | Task Assigned To - Inspection & sign off by Site Supervisor
c9fa802d-3d1d-5a4c-ad59-aaf5a01d2443 | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
0cfc082c-5e2b-5072-80a4-cf2537c88082 | note | Specification Reference - NZTA B/5:2008, 7.7.1, NZS 4402 Test 41.3
d67c36fe-6fe3-5023-aae9-383f73cb1bbd | note | Test Required - Plateau testing
cfee74a4-8b7a-5c4e-b2fc-9c1d71898b8a | note | ○ Mean value ≥ 98% of MDD
10e83193-0254-5012-8577-aa8f4c7f6974 | note | ○ Minimum value ≥ 95% of MDD
bf3f4cac-caa9-5410-bf78-635b5c0c7197 | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
6da686a1-f4e4-5ef6-9db7-01b0caa3fcf5 | note | Task Assigned To - Hold Point - Approval required by site engineer
5db21a97-716c-5126-ab7a-041dc85978cf | note | Measuring Devices or Method - Nuclear Densometer
8b92993a-c848-5b4c-aa95-727e50649007 | note | Criteria - Minimum value 95% of MDD
0ca9c05c-976f-5959-bccd-005251c27523 | note | QA Form - Test Reports
| signoff | HOLD POINT
| checkpoint | Surface shape
e41e36ef-6c63-5b95-be15-a66ca0110077 | note | Specification Reference - NZTA B/5:2008, 7.8
315e489f-4332-5443-b33e-f8574c0dd971 | note | Test Required - ≤10mm from 3-metre straight edge
b32673b0-b328-56b4-a714-8b6f6cbee311 | note | – No depression
1267a8fc-5841-5bf5-a281-26eb3328790a | note | – Vertical variations -5 + 15mm
19d0bb44-3862-54e2-a803-c1d684b6d2f8 | note | Task Timing / Minimum Task Frequency - 20m intervals
a12fdbca-cd26-558e-996a-719b0f80a3da | note | Task Assigned To - Inspection & sign off by Site Supervisor
08b5ca5e-3e13-585a-a35d-a4286d0ab932 | note | Measuring Devices or Method - Stringing, Tape measure
8554a205-e948-5d01-be2b-b1a2db4665bd | note | QA Form - QA Measurement Sheet
| checkpoint | Crossfall
205937a5-ba29-5511-8a88-da808f778161 | note | Specification Reference - NZTA B/5:2008, 7.9
431221cb-d024-5613-bf04-37eb6ceeec51 | note | Test Required - Not less than exisitng crossfall at the start of construction
62b11677-885c-550f-bf8c-39a1306f5417 | note | Task Timing / Minimum Task Frequency - 20m intervals
668230ae-f930-5843-9f03-2152f4e16b3e | note | Task Assigned To - Inspection & sign off by Site Supervisor
8090cd24-52f1-5952-9c2f-d710e5ca8b61 | note | Measuring Devices or Method - Stringing, Tape measure
d503e1e8-9001-5007-8d5c-3424ee65c436 | note | QA Form - QA Measurement Sheet
| checkpoint | Surface finish
e892f6d2-f836-57eb-ad52-acbfc576011b | note | Specification Reference - NZTA B/5:2008, 7.10
d219305b-18e0-5ccb-bfdc-e9a180817672 | note | Test Required - See clause
a0731827-f3ca-5254-a7f4-2ccdc9ce2c67 | note | Task Timing / Minimum Task Frequency - 20m intervals
46f24b38-e0d6-5590-9c63-643d04cc4f97 | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
c19b4438-1129-5035-85f3-1f7e86f938c9 | note | Measuring Devices or Method - Visual
| signoff | HOLD POINT
| checkpoint-no-value | * Normal Risk = < 5 x 106 ESA's (or< 500 HCV per lane per day)
| checkpoint-no-value | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
| section | Chipseal Construction (NZTA P29)
| checkpoint | Ensure appropriate TMP used
3870fc3c-8e36-5f2d-baea-8a045bac1c49 | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
| checkpoint | Seal design
c7095aef-a50e-5ee5-9da0-353261e6f6a5 | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
fef122c2-d11f-5be7-99cd-a0390749a80d | note | Task Assigned To - Project Engineer
5cb28bf8-f8ec-563f-8aa9-01f45e3c55ff | note | Criteria - Seal design to be reviewed prior to surfacing
4aa97448-aea1-5dcd-951e-47b91504505a | note | QA Form - Seal design template
| signoff | HOLD POINT
| checkpoint | Location/Size Confirmation
d884b402-2f34-54c3-a419-827ab9a08a1f | note | Test Required - Mark up extent of chipseal
6004e878-ad5f-567e-9e4d-0046ccc0427f | note | Task Timing / Minimum Task Frequency - Prior to surfacing
150cf92b-0884-5dda-badb-4d91b6040c1c | note | Task Assigned To - Project Engineer
f420f6cd-6cde-5cfd-bcae-2c036069f4f6 | note | QA Form - Daily Diary
| checkpoint | Surface Cleanliness
dc9dfa49-8e43-5512-894d-bcbd3bea2d9f | note | Test Required - Visual Inspection
31a5eea1-c373-5463-9fa9-1641e99c4686 | note | Task Timing / Minimum Task Frequency - Prior to application of binder
e9f13e5c-2e9d-57bf-a7b2-409a120220ba | note | Task Assigned To - Site Foreman
b51a35b7-3069-5d7b-ab1f-008ce87cbba0 | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
1dd18a88-3023-5f37-89ec-4a927c79c930 | note | QA Form - QA Measurement Sheet
| checkpoint | Plant Resource
d71212a8-1216-5ce7-82fa-1e812070c472 | note | Test Required - Visual Inspection
e98ed4e8-d937-505b-b61b-1e46956a7cc9 | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
85f18ef1-cac0-5671-8511-11ff6f8f240c | note | Task Assigned To - Site Foreman
60facac9-e4b9-5adc-b271-33c41f2fbc2c | note | Measuring Devices or Method - Visual
a897a391-e553-522f-b236-30460c297675 | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
70c96c94-98ae-5905-b691-7e18a6cbf3b0 | note | QA Form - Daily Diary
| checkpoint | Binder Application
2594a6c6-3122-5329-9379-e1b349f75320 | note | Test Required - Binder type, Cutback, Temp, Application rates
8227d69e-7cd9-57ef-a3ec-c032b3d38d00 | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
3c1a70bb-3754-5c55-8899-8e6800ce8bf2 | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
7e323a8d-f8aa-5c14-aada-91a0be1a2eb1 | note | Measuring Devices or Method - Visual
7ee25feb-57b5-5b39-a2a1-b175e78fa5eb | note | Criteria - Binder Type = 180/200.
412eef46-d94c-5165-8138-a9cbe0f6afdc | note | ○ Cutback to suit 1st coat seal 4pph kero max.
8b0826b0-b41f-516c-b2e2-fd56dadf9bf3 | note | ○ Temp = 150deg celcius min
7394a312-b8c3-5da7-b4c0-06f46fe2e6ae | note | ○ Application = Design l/m2, +/- 0.1 l/m2.
cc290c1b-916b-555c-bd30-846018d0b364 | note | QA Form - Bitumen Spray Sheets
| checkpoint | Chip Application
e7d3f3b3-0718-5341-8ca8-ae52c08481c1 | note | Test Required - Chip type, Chip Application
4ef5fe66-b1cf-52bc-8b69-697d46c257ad | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
8a143c4a-6fe4-5e26-8624-de7ad304534d | note | Task Assigned To - Site Foreman
c58496b6-2166-5368-a09f-f091bc864d5b | note | Measuring Devices or Method - Visual
a7e7604d-94c1-5e73-b96e-a498fccb9a43 | note | Criteria - Trucks loaded with correct chip.
33ac837e-e941-53bf-b18f-3da6ce967f37 | note | ○ Chip clean. (G4/6 Racked example)
07ef5ba8-4f18-5a8d-8fa8-2d5a710a7a66 | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
3540168b-b184-5f92-9787-7c2328e36cdc | note | ○ G6 application = Enough to just fill the voids around the G4.
b0572ccf-48d7-5c4f-83d4-ae55746f8d6e | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
81c339b0-1e56-52af-ae0c-eedd6de3eb6d | note | Test Required - Visual
6d0e7bdb-fa1d-543e-b757-bead4571823b | note | Task Timing / Minimum Task Frequency - At completion of rolling
b7858b7e-f2cb-5d3d-af03-9bdbec8cae74 | note | Task Assigned To - Site Foreman
6f2e0a97-8cc6-5254-b7f8-ce0ecab6646c | note | Measuring Devices or Method - Visual
4be6c2a5-4992-5487-b143-6c97a1b949c3 | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
96c64ba2-c1a5-5feb-92a7-78b99e2fccc5 | note | QA Form - QA Measurement Sheet
| checkpoint | Site Measure
5d9f9070-b700-567e-88aa-a6328c8ed9e4 | note | Test Required - Record final site measure
22527a1a-dbdc-5e66-8b4f-fe501b92d35e | note | Task Timing / Minimum Task Frequency - Completion of works
0c8ccbc6-1f5e-59eb-a038-970e653112f0 | note | Task Assigned To - Site Foreman
12fcff64-99de-5705-88a5-800b7ca994d0 | note | Measuring Devices or Method - Measuring Wheel or Tape
68c7fa76-a2a5-5772-8826-cdc4c7e76a25 | note | Criteria - Sketch and record seal area and QA detail
d11824dc-1e81-574b-b32d-cc3c3ffb1648 | note | QA Form - QA Measurement Sheet
| checkpoint | Post Seal Care
0eedc156-78f1-5fc6-b0a1-86abe2a8886a | note | Test Required - Visual inspection
da91b0e8-1d9b-5036-b158-889785b2bc6c | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
4d87d9b5-1f04-5dce-9a85-3fc597725a96 | note | Task Assigned To - Site Foreman
c82f2e10-3221-548f-8dd9-3eab1be9ca80 | note | Measuring Devices or Method - Visual
b825313b-de79-509f-aa12-108034f9290f | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
4ff0e745-438b-5947-853a-f963f0e359b0 | note | QA Form - Daily Diary
| section | Chip Removal, Pavement Marking, Traffic Services
| checkpoint | Removal of excess chip
f27bf570-65b6-573d-b2cf-cdf6443e77fa | note | Test Required - Visual Inspection
5797326c-ecda-513a-a4d3-52a8a3a58802 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
fccae71b-75d7-5151-8ab7-c44a59c9ff3d | note | Task Assigned To - Project Engineers/Site Foreman
f64a4753-eb6c-51e2-8186-dc673571ec1a | note | Measuring Devices or Method - Visual
8c7a193c-dcad-52e4-b54e-59e6c150203f | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
9f869e73-4a03-579f-8de9-4462ff3b6e4e | note | QA Form - Daily Diary
| checkpoint | Pavement Marking
f1cf5a27-80a9-5f5f-a221-f16d05d7de32 | note | Test Required - Visual Inspection
b86c6901-cca4-5a10-b6cf-c9674b39d2f6 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
ffa12e01-1d98-5de9-8007-6aff58cbe9e0 | note | Task Assigned To - Project Engineers/Site Foreman
fce1bab9-9e91-500a-9f9c-87a4e505666e | note | Measuring Devices or Method - Visual
c28c1e68-d676-5cde-837a-134448ee0b17 | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
09411e26-61b5-5d8a-8dc7-50a8cbea9e58 | note | QA Form - Daily Diary
| checkpoint | Removal of TTM
319d963f-2c0e-5879-be82-85a70f931aa0 | note | Test Required - Visual Inspection
d31e5c7f-321e-52e2-989f-638392c56849 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
71617c45-675e-59de-8cca-88aa94e60123 | note | Task Assigned To - Project Engineers/Site Foreman
638153f9-cce7-51f6-862e-793cc6c1556b | note | Measuring Devices or Method - Visual
5ab9b013-c02a-5d07-b363-c519a275a62c | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
f9b4617c-14b1-53cc-9438-5ce315a14953 | note | QA Form - Daily Diary
| checkpoint | Traffic Services
0f573298-85fc-5747-9a6f-ad66f9d99016 | note | Test Required - Visual Inspection
66d53b87-019d-581b-aaf3-cf375446a882 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
7ecc9676-5dcb-5d3a-85be-d7648775e396 | note | Task Assigned To - Project Engineers/Site Foreman
4ac4068e-4209-5dfd-8a74-bfdc1a436653 | note | Measuring Devices or Method - Visual
e3d13d33-a0db-52d9-b495-6c0bc8a6a6a2 | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
35f1db88-e8de-5ee8-894d-9b3fcca8e006 | note | QA Form - Daily Diary
| checklist | 3. HB AWPT ITP - McKenzies |  | 3. HB AWPT ITP - McKenzies | 075f4a39-0f25-41c9-8310-dc747431bb18
| section | Preliminary / Estabilishment
| checkpoint | Establish TTM
af850ef5-71f8-5e03-ae49-e28dfceb8f86 | note | Test Required - Visual Inspection
3f33bba9-2d5f-5ff9-a684-bf6fdaccdf8f | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
1efced5c-40ff-56ed-abb5-bc1a11ccb6bf | note | Task Assigned To - STMS/Site Foreman
4a93c0f8-5cd4-558e-b7e5-ce59e59ba513 | note | Measuring Devices or Method - Visual
ea208df8-9f50-5662-b7ab-565150acb570 | note | Criteria - As per TMP and ensure TMC advised in advance of works.
8afeb445-6451-5ee4-8fa5-4baa31a0894e | note | QA Form - Daily Diary
| checkpoint | Permits
9fe94df4-08cd-5661-9e51-79c90303034a | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
33f81939-c267-5126-b91f-efa221a2c4e1 | note | Test Required - Document Review
5614bc98-17f0-53d5-8ad9-141122358840 | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
c1bcc6f8-9d73-5727-ad2e-5c2c8793b7bd | note | Task Assigned To - Site Foreman
d53f8a9a-eeb9-56ae-83e6-fc503ab043e1 | note | Measuring Devices or Method - Visual
06d69ccf-800c-5b5e-800a-a8adbe43b7c3 | note | Criteria - Obtain permits and mark outs prior to construction
f11573b0-f6bd-5b1b-abba-b1a25fb0202a | note | QA Form - Copy of Permit on site
| checkpoint | Clear-Shoulder and Side drain
f4e28b61-ec31-5247-bd21-429f09e04fc9 | note | Test Required - Visual Inspection
fc6ab4cc-bedf-5eff-8da3-2e3232251c03 | note | Task Assigned To - Project Engineers/Site Foreman
6ffa6631-5df8-526b-b9c8-88c6e6ca9bed | note | Measuring Devices or Method - Visual
3d886d97-4707-56ee-8396-ee89393ac9d9 | note | QA Form - Daily Diary
| checkpoint | Digout Failed Areas
a4b695e0-0729-5f6d-ad64-1b1b0a34ab6b | note | Specification Reference - Refer to Design Report for required depth based on Scala results
fb02f0d6-269e-55e6-b69a-eab11d9f7d37 | note | Test Required - Visual Inspection
226a8373-d9a1-5bac-9d62-677f1924073a | note | Task Timing / Minimum Task Frequency - Prior to Pavement Rehabilitation Construction
7aed6ab6-0919-5c0c-9744-fa67469fa263 | note | Task Assigned To - Project Engineers/Site Foreman
3e7b08fb-3c10-5f52-a45e-124b2f78ca70 | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
2fa44150-9af8-5b41-8a4a-e9d67cd0015c | note | Criteria - Backfill with Pavement Aggregate
1e283d0a-9811-5aea-8290-160e692c0c37 | note | QA Form - Daily Diary
| section | Inspection Test Plan - In Situ Cement Stabilisation
| checkpoint | Cement for stabilisation
08decc68-69e1-5034-b586-cd6609d5b03c | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
5f514f79-2497-5c59-8af9-f798ce7b99d0 | note | Test Required - Certified in accordance with NZS 3122
d58e6344-b8be-5fda-a40f-f461d05e54b1 | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
| checkpoint | Production plan
a1ee1ad8-2132-52b8-8d37-2fb2bba0e6ac | note | Specification Reference - NZTA B/5:2008, 7.2.2
55254d6f-df3c-548d-b394-db195dc23c00 | note | Task Timing / Minimum Task Frequency - 1 per site
| checkpoint | Stabilisation mix properties (including cement):
d386e0c4-3085-57c9-b15b-2480204abb1b | note | – Maximum dry density (MDD)
1be1b594-3edf-5b6f-8e9e-7e272f02984d | note | – Optimum water conent (OWC)
33e55ac0-03e9-52af-9ebb-635a93af0123 | note | – Solid density (SD)
47d8813f-5e7f-52c6-84ac-c10ad55a9e3b | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
ac83b3b6-73ca-5a25-9e8d-8ca957db7cb1 | note | Test Required - Material properties for compaction verification
705fa293-41b7-5ab2-a90a-5335805e1d51 | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
4ee7ed93-edd0-5466-9514-99774fba91ab | note | Task Assigned To - Hold Point - Approval required by site engineer
d391cf4d-d43c-5a1c-a5e6-4814d4acd1e4 | note | QA Form - QA Measurement Sheet
| signoff | HOLD POINT
| checkpoint | In-situ moisture content of existing pavement aggregate
3aaac256-503b-5feb-96fa-926d36b37a53 | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
e7af630b-742a-564e-865f-867692c37b38 | note | Test Required - In-situ moisture content Between 90% to 100% of OWC
384c0c34-a0b8-55c4-a4ee-bb42a398c29e | note | Task Timing / Minimum Task Frequency - As required
69564ecc-ad0c-5dc3-b5b9-9f536fc42a01 | note | Task Assigned To - Inspection - Lab
5ad645fe-1468-50fe-b40e-953eab53a1d4 | note | QA Form - QA Measurement Sheet
| checkpoint | Top-up metal
939a5f60-55e7-50b7-8d18-43e92e6f4bf2 | note | Specification Reference - TNZ M/4 Table 4
18632f55-231f-5bea-9c3a-d6551013290b | note | Test Required - Placed to required depth and design levels
263a91cf-d801-5c0a-9f32-11a1b4fe0e72 | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
cb4f7626-274e-519b-ae8c-a4a802845a77 | note | Task Assigned To - Site Foreman
c194cee0-dfa5-557c-a808-3b06d03474f0 | note | Measuring Devices or Method - Stringing, Tape measure and or survey
5024f357-eec5-5860-8d62-5d4ed3d6bc36 | note | QA Form - QA Measurement Sheet
| checkpoint | Cement spreading
e865f898-960c-5d42-9669-52cac2b17a37 | note | Specification Reference - NZTA B/5:2008, 7.3
d2c400e8-35c9-592a-9415-b3ddf698285b | note | – Mat test (1m2 canvas mat)
8aba7ac8-f5e0-5bb2-b58f-8ebd31fec825 | note | – Average usage test
1f64b22f-0b97-52cb-8b8e-c5c83feff079 | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
d5ece7ae-af58-5d5a-891e-7edca6bfd4aa | note | Task Timing / Minimum Task Frequency - Every 400 m2, Upon emptying spreader and bulk tanker
0a50671b-b91e-5e95-b597-d1c980cfe26a | note | Task Assigned To - Inspection & sign off by Site Supervisor
0ff82b5a-54cc-521c-8ab1-80c582f51456 | note | QA Form - QA Measurement Sheet
| checkpoint | In-situ mixing - Cut depth
ace093aa-5c19-5da7-96e2-94c781e19b8c | note | Specification Reference - NZTA B/5:2008, 7.6.1
77d6d018-daec-518f-9324-14d8bd9be08d | note | Test Required - Maximum variation -5mm and +15mm
99c0b945-999d-5662-b3c5-81bab74c8258 | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
aa6ccd86-45f0-5752-b547-5f85b26445d1 | note | Task Assigned To - Inspection & sign off by Site Supervisor
44f02253-7330-5198-b0e2-dfdafb6e939c | note | Measuring Devices or Method - 250mm Depth
2fed62e1-0c51-515f-bd9b-1847e2bad73d | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
5c0eedcc-c594-590c-85c3-374e66345818 | note | Specification Reference - NZTA B/5:2008, 7.7.1 NZS 4402 Test 41.3
f69eb0b6-e4af-5481-914b-5660cfe623d5 | note | Test Required - Plateau testing
5809ad45-13c4-5457-b780-3b66855a1c71 | note | ○ Mean value ≥ 98% of MDD
5357c9ac-696b-5d00-b435-5700810d27c0 | note | ○ Minimum value ≥ 95% of MDD
358d9aad-3b96-5aff-bd03-4505d5b72db6 | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
c876f753-efee-5da5-ae63-b8314ee385e3 | note | Task Assigned To - Hold Point - Approval required by site engineer
89fac70e-d089-594a-af3d-49a769a88d66 | note | Measuring Devices or Method - Nuclear Densometer
10809696-9ae5-541b-8d30-af318352cf74 | note | Criteria - Minimum value 95% of MDD
d386147d-de86-5282-87bd-d8ad5265b2b5 | note | QA Form - Test Reports
| signoff | HOLD POINT
| checkpoint | Surface shape
97fefc29-7a3c-51e5-8357-f6d915623504 | note | Specification Reference - NZTA B/5:2008, 7.8
32e6542d-6455-55e4-9fb2-e4a9b6057878 | note | Test Required - ≤10mm from 3-metre straight edge
edbed1a6-a8c9-55b5-b3c1-fee7a45a8eb7 | note | – No depression
e293933d-cc8c-56a1-9efd-f07f5897a89b | note | – Vertical variations -5 + 15mm
99b8d382-3e4e-5269-809a-786985789240 | note | Task Timing / Minimum Task Frequency - 20m intervals
93f5dcde-d4ce-5dac-b615-a2c6ec67abbf | note | Task Assigned To - Inspection & sign off by Site Supervisor
645515fb-3923-5157-89c1-fd26f4fe2c09 | note | Measuring Devices or Method - Stringing, Tape measure and or survey
8b4ec6e9-fc9b-52a7-a70d-65a7a2200ad9 | note | QA Form - QA Measurement Sheet
| checkpoint | Crossfall
a7b3d6c4-06a4-5d79-afb4-1d3a2f25824c | note | Specification Reference - NZTA B/5:2008, 7.9
bbf35a9f-1db3-51fb-9b6f-13e03deccc57 | note | Test Required - Not less than exisitng crossfall at the start of construction
e9fbcd6e-2940-5481-b57c-3e67422ccaf9 | note | Task Timing / Minimum Task Frequency - 20m intervals
355cd3d3-a6ab-5c01-8a46-c9b7ed64660e | note | Task Assigned To - Inspection & sign off by Site Supervisor
3ef9730f-e3c4-5525-86f4-45280dd37ecc | note | Measuring Devices or Method - Stringing, Tape measure and or survey
39f4440b-d2bc-5f45-95f6-08975ce3a8f9 | note | QA Form - QA Measurement Sheet
| checkpoint | Surface finish
90a0f73f-e0d1-5a84-9fa4-445af336062e | note | Specification Reference - NZTA B/5:2008, 7.10
5845613c-c752-556b-9d10-a93978a4c226 | note | Test Required - See clause
0f1d96e4-2bf4-5512-89cc-53a0952b0bb9 | note | Task Timing / Minimum Task Frequency - 20m intervals
4d86d6c3-47ab-5691-824a-940f9759c10f | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
bbbdaf3a-d52a-5911-ba9b-318de62cb638 | note | Measuring Devices or Method - Visual
| checkpoint-no-value | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
| checkpoint-no-value | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
| section | Chipseal Construction (NZTA P29)
| checkpoint | Ensure appropriate TMP used
e731b267-e1b2-5b8b-b606-a9c36a4e1555 | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
| checkpoint | Seal design
5df487f7-cc46-57ec-947e-962d803acd0f | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
b5157884-f8d9-5acf-bdd5-9be9ec805c19 | note | Task Assigned To - Project Engineer
f198e064-b636-5e1e-a8d4-2ec2c9502791 | note | Criteria - Seal design to be reviewed prior to surfacing
2e0e5360-10f7-5613-a477-77b482f95172 | note | QA Form - Seal design template
| signoff | HOLD POINT
| checkpoint | Location/Size Confirmation
5ca3117b-c84a-5a36-b32f-fbefdde540e4 | note | Test Required - Mark up extent of chipseal
ea1975cb-dc3d-5fa3-9b36-dcc71b634f3c | note | Task Timing / Minimum Task Frequency - Prior to surfacing
b413b96f-0de1-53a0-94de-4f5f627f3731 | note | Task Assigned To - Project Engineer
9e094f44-5bce-58f4-92b6-66380ca61a2d | note | QA Form - Daily Diary
| checkpoint | Surface Cleanliness
a6c489a9-22f2-5145-a319-ef4e2669248f | note | Test Required - Visual Inspection
090c7f25-eda3-5549-b582-ec81f0e8cb37 | note | Task Timing / Minimum Task Frequency - Prior to application of binder
c01ef9f2-f5eb-5b04-bf40-04a50c6995e3 | note | Task Assigned To - Site Foreman
d1e269ca-8154-5cc4-8e56-4f3580984e5e | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
7fc09843-0816-5fc4-a105-ac36f1be19b3 | note | QA Form - QA Measurement Sheet
| checkpoint | Plant Resource
8ae15dca-a91e-5e1a-a066-21e5e188dbb3 | note | Test Required - Visual Inspection
a54c1408-936e-5982-81bf-d8110e2fe4c4 | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
5bb74e72-e582-50ee-ac9c-192f1b583dc0 | note | Task Assigned To - Site Foreman
8f8bac14-b4e5-50e7-bf12-b3ffbfe41994 | note | Measuring Devices or Method - Visual
d51b766e-3f6d-5b10-a90e-31911a3ef9eb | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
2d1a4f04-9309-581e-af24-6ed610e1e68b | note | QA Form - Daily Diary
| checkpoint | Binder Application
61dc46de-484e-5498-b0cf-ccfc1d4b50a7 | note | Test Required - Binder type, Cutback, Temp, Application rates
0cd2023e-3187-5b4d-938b-6407f331fecb | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
600ccf86-a002-50ee-8709-96760de57202 | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
9e60668b-2c80-578f-b3cf-e2f583604309 | note | Measuring Devices or Method - Visual
85594e38-4a9b-5630-a9cb-7d3eed85579e | note | Criteria - Binder Type = 180/200.
a5aadf71-8bd3-5383-8b4a-3656478b1a8d | note | ○ Cutback to suit 1st coat seal 4pph kero max.
3f5cb0ad-817c-559f-a528-8ed4d0f49ecb | note | ○ Temp = 150deg celcius min
5059775d-a529-558b-a851-47b4d4726381 | note | ○ Application = Design l/m2, +/- 0.1 l/m2.
aaf29903-8016-54d4-a8f9-c4efb80295cb | note | QA Form - Bitumen Spray Sheets
| checkpoint | Chip Application
c0bbbb20-ad5b-5b4b-81a8-ee6887977f42 | note | Test Required - Chip type, Chip Application
4cf7593f-5d73-5e3c-904f-8b82f6124c3f | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
8f5f5122-0178-5496-9c5f-70c3440da440 | note | Task Assigned To - Site Foreman
ea6e3f77-d3d5-5a53-90d1-b6fa8b021fe0 | note | Measuring Devices or Method - Visual
2f6df7f0-649b-505e-ba73-cf4e3536bf06 | note | Criteria - Trucks loaded with correct chip.
76159247-55f3-580d-836d-aa12f822855e | note | ○ Chip clean. (G4/6 Racked example)
8e5d4975-7e8e-5c8d-8d05-d25ec6abfb31 | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
0e7ab8d2-fd14-5430-aef6-9f19b6150599 | note | ○ G6 application = Enough to just fill the voids around the G4.
f4aa000d-d9da-50ee-a1fe-0e53071130c1 | note | QA Form - 'QA Measurement Sheet
| checkpoint | Compaction
e0de6630-93f0-5975-b2d9-d45375034b76 | note | Test Required - Visual
1c3bfae1-f07b-5162-a6ff-4a77da73656e | note | Task Timing / Minimum Task Frequency - At completion of rolling
8dc3286a-c27b-55e5-8b1f-c3fbdf6108cb | note | Task Assigned To - Site Foreman
fca54f7d-ae26-5814-8291-ae9b84e6ba74 | note | Measuring Devices or Method - Visual
1415af99-78e2-5c7a-9109-55cf08d3f346 | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
675d02a5-193a-541e-b96c-c75f8686de9f | note | QA Form - QA Measurement Sheet
| checkpoint | Site Measure
a695fdb2-1b82-5acc-b16c-300edf5b9fb8 | note | Test Required - Record final site measure
5d49a707-e6c1-5af7-8fdb-f48b5d14f38a | note | Task Timing / Minimum Task Frequency - Completion of works
5e2188c7-f367-51ff-af40-3ad4bd917fbf | note | Task Assigned To - Site Foreman
824c2535-31fe-5a6a-ab56-924aa4616bf2 | note | Measuring Devices or Method - Measuring Wheel or Tape
5eef4fae-ce19-57ad-a6b5-6342086ce818 | note | Criteria - Sketch and record seal area and QA detail
e339b1ac-ffa2-5430-8c56-2874a7da14b0 | note | QA Form - QA Measurement Sheet
| checkpoint | Post Seal Care
d4eff21f-3fa6-5acc-85c5-f0a9a6e654f2 | note | Test Required - Visual inspection
b29d08a5-ce41-543e-a057-c49fa962ea25 | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
d2d87c04-d8e0-5998-b683-4fa887326653 | note | Task Assigned To - Site Foreman
69431531-c812-5403-b2d6-b469235d69d9 | note | Measuring Devices or Method - Visual
d02dde0f-e000-5565-97cb-e7f05c5e7ea4 | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
1a336b44-0ab0-5abc-baef-ce313fb0514b | note | QA Form - Daily Diary
| section | Chip Removal, Pavement Marking, Traffic Services
| checkpoint | Removal of excess chip
43bf1fbc-dfbe-5a7e-ba1f-de33d1d2deaf | note | Test Required - Visual Inspection
bfc8f627-8b47-5f21-b544-5e57566a2342 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
51b2d957-c7a2-5c68-98a6-efa46155b2bf | note | Task Assigned To - Project Engineers/Site Foreman
b3c8fb70-582e-5465-8ff4-8bc4c36678ab | note | Measuring Devices or Method - Visual
1fd8b6cd-933e-58e9-b894-46ed329fba14 | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
2a2be0f7-9497-59f5-a2e4-daa61e972f50 | note | QA Form - Daily Diary
| checkpoint | Pavement Marking
11d30969-9e7e-5443-9d97-9cf65d668f40 | note | Test Required - Visual Inspection
56741978-e3a0-5abc-92a5-d6d37496e847 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
f1216e3d-95c4-548c-8732-22db5a6b5507 | note | Task Assigned To - Project Engineers/Site Foreman
8c462110-3af0-55e7-9778-60afe6da6fd8 | note | Measuring Devices or Method - Visual
ce178b24-ebc3-5041-994e-8a39ab70c705 | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
1573c25f-0612-5589-b183-7e3b1fd82a52 | note | QA Form - Daily Diary
| checkpoint | Removal of TTM
d2acd26e-7b93-5ac1-baa3-af6b4518cc52 | note | Test Required - Visual Inspection
81ce1205-e6d2-5209-a684-ee88f30dedcd | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
fbb7fffb-d56e-5a76-8cd4-a8fd13c95a91 | note | Task Assigned To - Project Engineers/Site Foreman
dcaf27a4-2318-577f-a16e-2287f8a2f927 | note | Measuring Devices or Method - Visual
175ca669-7543-5d88-9baf-394f47e8a27b | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
3d095f05-bc9c-5e47-ae76-c79ac2923365 | note | QA Form - Daily Diary
| checkpoint | Traffic Services
e75d0643-65f8-52b2-883f-310fa3e83ec1 | note | Test Required - Visual Inspection
6d340f4a-9c9b-554d-bd29-ee2f73c9823e | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
55adf4c1-d7c7-5438-ba04-6e65c55950f8 | note | Task Assigned To - Project Engineers/Site Foreman
4a68e499-f45c-5657-9974-21f20d950c41 | note | Measuring Devices or Method - Visual
9f2e2102-06a6-5e77-9b39-ab31e3688095 | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
6cf5ce19-8783-532f-a602-ecfcfb5235ae | note | QA Form - Daily Diary
| checklist | 4. HB AWPT ITP - Mahiaruhe Stream Bridge Sth |  | 4. HB AWPT ITP - Mahiaruhe Stream Bridge Sth | b73a77f7-b84e-48ff-94fc-8c708c7b6437
| section | Preliminary / Establishment
| checkpoint | Establish TTM
0b4cc237-b98e-5277-bc81-da4dd4ee11fe | note | Test Required - Visual Inspection
a8ebb2ff-0388-54b6-8774-21e32617a84c | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
5b9543cc-1ba4-5a1c-bfc4-08bbc4397e3b | note | Task Assigned To - STMS/Site Foreman
d12c11e3-6100-546d-8f34-34571c8695fc | note | Measuring Devices or Method - Visual
5b5609ee-a920-512a-96c8-7bb6838dd1f3 | note | Criteria - As per TMP and ensure TMC advised in advance of works.
dea48328-8f60-5e7f-a05e-fdc81be724e5 | note | QA Form - Daily Diary
| checkpoint | Permits
8faa57d2-513e-5079-a290-2b9195ed7b6f | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
87d71875-a82d-502c-b4f5-c47958cd38ec | note | Test Required - Document Review
cbf39d8e-634c-5f03-b2f8-2bf83531594b | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
5ce8eabe-744e-5aaf-b31d-505eadcf6735 | note | Task Assigned To - Site Foreman
c43f47ee-ac8c-5e0d-87db-a9823d984695 | note | Measuring Devices or Method - Visual
bfebf68d-c653-5c8e-be5e-0cb3da85b2af | note | Criteria - Obtain permits and mark outs prior to construction
40b560ec-fb78-57b0-bd9c-db4416063f20 | note | QA Form - Copy of Permit on site
| checkpoint | Clear-Shoulder and Side drain
bf365de5-a801-591d-b7cd-ecf6740af5f4 | note | Test Required - Visual Inspection
71ff8223-6c29-5c22-b090-032269f0ce03 | note | Task Assigned To - Project Engineers/Site Foreman
3f86778d-2f0a-5a15-aa55-9e4bc5c63660 | note | Measuring Devices or Method - Visual
d0ec3e12-71d7-5509-97fe-3eff889f4849 | note | QA Form - Daily Diary
| checkpoint | Digout Failed Areas
8a126da5-b38a-57a1-9793-a16ab7c12329 | note | Test Required - Visual Inspection
795c8f57-7305-5a4c-8d3a-db98c0fd792f | note | Task Timing / Minimum Task Frequency - As Requested
d91ffad3-815a-52f0-95e0-fe7c2da336af | note | Task Assigned To - Project Engineers/Site Foreman
fce77690-7179-51e0-9844-40c670e22795 | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
b732cb3a-5907-535b-89e7-c8d52b38ab32 | note | Criteria - Backfill with Basecourse
293f4e96-4062-5c4c-9150-914bc261ba2d | note | QA Form - Daily Diary
| section | Kerb Construction
| checkpoint | Basecourse layer construction (1)
e5d826d6-77d0-54ff-9b2e-2cf65d3acd92 | note | Specification Reference - TNZ B/2
8eda5303-1a89-5df0-bf73-979982068389 | note | Test Required - Level and alignment
d0f41214-c464-597a-8301-503e9fe6c23a | note | Task Timing / Minimum Task Frequency - Every 20m
da24f7a6-763e-5168-af3d-fbfd1be38600 | note | Task Assigned To - Project Engineer
| checkpoint | Basecourse layer construction (2)
2ac07518-0703-52c8-9073-c73d10072de8 | note | Specification Reference - TNZ B/2
deac1dd2-186b-5a2f-8436-8b74e6d29753 | note | Test Required - Compaction
73d234f1-7e1c-5d38-b274-58b54193390a | note | Task Timing / Minimum Task Frequency - Every 20m
2d2c42cd-a07e-5182-9f5c-7ecc24e8e3c3 | note | Task Assigned To - Project Engineer
149734ce-3553-5e98-9488-3235f1ee8a27 | note | Criteria - 25min on the 4th drop
7d92ea31-f7f1-5351-a53f-d33ab45106d1 | note | QA Form - QA Measurement Sheet
| checkpoint | Kerbing
102984e6-031f-5e38-b19f-289699c23f70 | note | Test Required - Set-out level and alignment
d9393e99-1134-5196-9e1a-cc70e17656f7 | note | Task Timing / Minimum Task Frequency - after base construction and prior to placement of concrete
1f14a9f7-8090-56a5-8468-7e442ed22065 | note | Measuring Devices or Method - survey check
ee54125c-18b0-555d-aa31-fd090224c17e | note | Criteria - Horizontal: ± 20mm, Vertical: ± 5mm
| checkpoint | Concrete Works
2b327f9e-c5d5-5655-917b-81b233d5b4d0 | note | Test Required - 20MPa
8ef0ff6c-7e2e-5f55-999f-1ce371ac37ed | note | Measuring Devices or Method - Copy of delivery docket
93a6a3d2-4eec-5932-8eef-b02d07ddb8ac | note | Criteria - 20MPa, 28days
| section | Inspection Test Plan - In Situ Cement Stabilisation
| checkpoint | Cement for stabilisation
7763619c-1907-5390-b99b-70d68336d3e4 | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
fa150408-9032-57d2-8ec3-681845fc83e1 | note | Test Required - Certified in accordance with NZS 3122
174d64c6-60c6-5c6a-9265-52e8169576fe | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
| checkpoint | Production plan
7d4f72ae-8a70-5284-bbb1-262441642461 | note | Specification Reference - NZTA B/5:2008, 7.2.2
bf2193d0-5ed5-52d0-b45d-0185c3d2c1bc | note | Task Timing / Minimum Task Frequency - 1 per site
| checkpoint | Stabilisation mix properties (including cement):
9b665b30-30c8-5423-81d8-851ee02ab705 | note | – Maximum dry density (MDD)
9c4e80bb-c8fd-5032-9d94-055d8e52d4e0 | note | – Optimum water conent (OWC)
d2cdb56e-59ff-549c-afb1-f1fb83280603 | note | – Solid density (SD)
0096c04f-01e6-5ec9-8d94-f800bc9c5faf | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
fc3b62f4-c61a-59b1-95ee-2eb898fc28bd | note | Test Required - Material properties for compaction verification
65f4e514-26bb-5068-85a5-48b76b59b514 | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
08039f2a-e1c3-54ce-bc78-f3d8b39e4c07 | note | Task Assigned To - Hold Point - Approval required by site engineer
523d5820-25b1-5da6-a19d-c92b13cb5240 | note | QA Form - QA Measurement Sheet
| signoff | HOLD POINT
| checkpoint | In-situ moisture content of existing pavement aggregate
51d2664d-18fa-5466-990a-ea14d8b6269a | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
1a8a1f78-f940-5853-83e8-e2e18c988baa | note | Test Required - In-situ moisture content, Between 90% to 100% of OWC
edc8e114-eac3-5671-aa4b-88d3d031a0e9 | note | Task Timing / Minimum Task Frequency - As required
8cd671dc-452f-5473-aa1f-c2da1d23fdd1 | note | Task Assigned To - Inspection - Lab
0fbe4119-a3f9-5c6f-8171-d6c802311c11 | note | QA Form - QA Measurement Sheet
| checkpoint | Top-up metal
174f2b91-1dc3-581d-b6ca-70e7bc5ceb1a | note | Specification Reference - TNZ M/4 Table 4
10beb72a-7e8c-51ee-af40-451e045ff925 | note | Test Required - Placed to required depth and design levels
efa0aabf-ae7b-5cc6-8fc8-79af45ca200c | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
93d21e60-d42b-5e16-89d2-f739723d318f | note | Task Assigned To - Site Foreman
04563c5a-55f5-5c9f-84fb-5d170d70f8f6 | note | QA Form - QA Measurement Sheet
| checkpoint | Cement spreading
1479603d-2580-5b4d-89a5-366dffc262af | note | Specification Reference - NZTA B/5:2008, 7.3
8361a513-9afa-599f-822f-e782d623cb9a | note | – Mat test (1m2 canvas mat)
45139730-5aa2-55db-8f30-16f810da4b29 | note | – Average usage test
4a404ea3-6043-59dc-8002-ac8fa65baa48 | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
52a595b5-9824-5bef-8475-e1b14d9ced7a | note | Task Timing / Minimum Task Frequency - Every 400 m2, Upon emptying spreader and bulk tanker
7a4df1fa-7ba9-54e8-959c-b51679aa2537 | note | Task Assigned To - Inspection & sign off by Site Supervisor
fa33b642-65e8-5ed1-b9a4-48d9b979f2a1 | note | QA Form - QA Measurement Sheet
| checkpoint | In-situ mixing - Cut depth
f218f0ec-329d-554c-9c3a-541c9a33032c | note | Specification Reference - NZTA B/5:2008, 7.6.1
ee9f5831-6c7a-5cbd-a7f1-53dabc174353 | note | Test Required - Maximum variation -5mm and +15mm
82b1b4e4-fb6d-5363-9d3e-b444f04cc518 | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
b585cd2c-776a-59ca-9270-76d4a34c4b9d | note | Task Assigned To - Inspection & sign off by Site Supervisor
1bae00d3-ece8-5249-b9bf-34410bc358b1 | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
8536bb9d-a255-5ced-a187-894b3c652485 | note | Specification Reference - NZTA B/5:2008, 7.7.1, NZS 4402 Test 41.3
d1741ffd-c4af-5dc4-be0a-854c0be8f03f | note | Test Required - Plateau testing
990361ed-43cd-5ffc-a8ec-e13d779f89a8 | note | ○ Mean value ≥ 98% of MDD
04a7e2f1-3c28-5aba-8eee-4d45847f8e21 | note | ○ Minimum value ≥ 95% of MDD
8f0a77a5-0072-5f60-83d0-a2e8867e383f | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
39c1bd92-b780-51c6-9d63-9c061ec15f81 | note | Task Assigned To - Hold Point - Approval required by site engineer
ae5d8459-0d68-5f65-a74f-9b17d5422bd8 | note | Measuring Devices or Method - Nuclear Densometer
399058f7-8278-5433-83e3-817b5b01290f | note | Criteria - Minimum value 95% of MDD
e690ca06-3f44-52ee-b413-4575ba530d4a | note | QA Form - Test Reports
| signoff | HOLD POINT
| checkpoint | Surface shape
9e00678a-a90d-5693-8935-e17555f8c071 | note | Specification Reference - NZTA B/5:2008, 7.8
d955642f-2b9f-5a69-9873-e22cd43a285b | note | Test Required - ≤10mm from 3-metre straight edge, No depression, Vertical variations -5 + 15mm
e4d697e4-7e19-5a84-936d-c98e5024666b | note | Task Timing / Minimum Task Frequency - 20m intervals
03aa30cb-91ef-5d3f-a3b1-3fb161b8e01d | note | Task Assigned To - Inspection & sign off by Site Supervisor
ac9e1228-9cfd-5014-9814-72786e941d2e | note | Measuring Devices or Method - Stringing, Tape measure
74ec2921-7206-5b66-a754-170770d1a3c2 | note | QA Form - QA Measurement Sheet
| checkpoint | Crossfall
f74a34f4-6a8d-5440-9c00-3c8f5420d5d5 | note | Specification Reference - NZTA B/5:2008, 7.9
4eb6a65e-3d64-5474-b566-3c5438116171 | note | Test Required - Not less than exisitng crossfall at the start of construction
c4f037da-947c-561d-b1d4-40c7cc90b991 | note | Task Timing / Minimum Task Frequency - 20m intervals
a9a1b184-0011-5d00-aa08-f0ea9422c4cc | note | Task Assigned To - Inspection & sign off by Site Supervisor
5a075343-e45f-515e-8416-9f961e55301b | note | Measuring Devices or Method - Stringing, Tape measure
6da06598-935f-5602-be3a-6162517608d3 | note | QA Form - QA Measurement Sheet
| checkpoint | Surface finish
f50d118d-bd8b-526e-a4b0-c76aa69ff811 | note | Specification Reference - NZTA B/5:2008, 7.10
7e8ad013-9845-5763-b7b3-31d1f2967a65 | note | Test Required - See clause
50878e14-bc25-587c-b441-4571104dc4be | note | Task Timing / Minimum Task Frequency - 20m intervals
284359a9-3fb5-51cf-a012-bdce94b51074 | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
be95931a-c334-5f56-a70b-1ea51928a141 | note | Measuring Devices or Method - Visual
| signoff | HOLD POINT
| checkpoint-no-value | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
| checkpoint-no-value | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
| section | Chipseal Construction (NZTA P29)
| checkpoint | Ensure appropriate TMP used
f9409b1d-71b8-5e37-b96f-9c0c072f5c45 | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
| checkpoint | Seal design
96f9334d-a157-5e3d-9923-766819236bb6 | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
27bb3a0a-ea9b-5c19-a14c-9daa9445da35 | note | Task Assigned To - Project Engineer
f82f867f-67ff-54a7-bf74-09ee950528dd | note | Criteria - Seal design to be reviewed prior to surfacing
052871cc-7171-5c86-a4bf-eda87ec89940 | note | QA Form - Seal design template
| signoff | HOLD POINT
| checkpoint | Location/Size Confirmation
36feab03-f525-5dea-b057-8d35f0e05bbb | note | Specification Reference - Mark up extent of chipseal
b156c35d-d2ec-5cf1-8eb4-121662254af7 | note | Test Required - Prior to surfacing
f6081ef0-3c2a-5434-a2ac-e0b83dbe9759 | note | Task Timing / Minimum Task Frequency - Project Engineer
140ee0b1-42c9-5559-912f-5243828c8b30 | note | QA Form - Daily Diary
| checkpoint | Surface Cleanliness
6749f55c-bbdd-5875-a863-7187e66bc084 | note | Test Required - Visual Inspection
88f08790-8261-5961-8a41-2f9ea341b1b7 | note | Task Timing / Minimum Task Frequency - Prior to application of binder
d522e056-1581-55de-96db-546d95fae89f | note | Task Assigned To - Site Foreman
2c009dd0-f32e-5963-8e07-3cb121da5012 | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
411ead23-c3b0-5b1e-bf0e-3ce844755cec | note | QA Form - QA Measurement Sheet
| checkpoint | Plant Resource
ba520792-45a0-5876-8fe8-5cfa8c8b6bd6 | note | Test Required - Visual Inspection
71ad4ba9-e930-5100-ae79-1d68ebcf5ad2 | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
3038cbc0-dbfa-5b15-a920-83b26bcb5ffd | note | Task Assigned To - Site Foreman
04b24b27-6be4-52a3-a802-a94acfe29663 | note | Measuring Devices or Method - Visual
c4da6684-1d6c-5005-b3dc-b454dc35a8bb | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
7b477481-b38a-576e-a11f-593b2e54f9e9 | note | QA Form - Daily Diary
| checkpoint | Binder Application
47e36f20-2dd2-5284-89bc-9e5ead67a530 | note | Test Required - Binder type, Cutback, Temp, Application rates
014ef88c-05ca-550c-b7f8-27bef178cea5 | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
61193acc-5ab5-5e08-8f4a-e6df36213047 | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
d1399273-5142-5824-b091-18af2644a834 | note | Measuring Devices or Method - Visual
de0e30e8-cacb-571f-beba-ca9cb8d106d4 | note | Criteria - Binder Type = 180/200.
465d4c23-d201-5b11-b00d-e88f73a0a5a6 | note | ○ Cutback to suit 1st coat seal 4pph kero max.
b8524b2b-dc7b-5183-8e02-664a1dd510eb | note | ○ Temp = 150deg celcius min
944026e2-5d95-5990-9c91-f0f8304f3b49 | note | ○ Application = Design l/m2, +/- 0.1 l/m2.
bd496121-0f85-5849-bfb2-3069b635e78e | note | QA Form - Bitumen Spray Sheets
| checkpoint | Chip Application
585c4913-110e-5dfb-abbc-369b002f23a0 | note | Test Required - Chip type, Chip Application
18621cec-fc03-5b7c-a209-e4e6aa0f45a8 | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
68977e62-c495-5cc9-b26e-389089697399 | note | Task Assigned To - Site Foreman
1c3d4a1a-4e23-5a75-a51a-9034ca3bcbfd | note | Measuring Devices or Method - Visual
2a4de28e-c146-51c1-8592-048dfd206af3 | note | Criteria - Trucks loaded with correct chip.
85263994-3e52-5777-ace5-dd9f293d3c57 | note | ○ Chip clean. (G4/6 Racked example)
ab6275d4-3d65-593b-bf5b-c02fde632ce3 | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
5f6352e0-2bad-5a03-9149-c6d5c661eb78 | note | ○ G6 application = Enough to just fill the voids around the G4.
1cc63e38-dc49-5b79-a0d1-20455b12ee01 | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
d8929323-454f-5157-b5f7-dd1fb8b5f569 | note | Test Required - Visual
18c82faf-5e82-5e33-b1fc-32cd2decced6 | note | Task Timing / Minimum Task Frequency - At completion of rolling
21281eac-5d3d-5ced-bc0b-8b35f06915ec | note | Task Assigned To - Site Foreman
89bb0789-09c9-5291-a96e-ad180a8ae962 | note | Measuring Devices or Method - Visual
d86f96e3-8b10-5210-936a-155d5cf63978 | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
997c8a7d-77b7-5900-a4bc-4e13cd489485 | note | QA Form - 'QA Measurement Sheet
| checkpoint | Site Measure
9694d6a5-3412-5258-8e2d-6c9d40409370 | note | Test Required - Record final site measure
0b5577bf-7e97-522a-989e-b65bcfe2fdb0 | note | Task Timing / Minimum Task Frequency - Completion of works
337978e1-4082-5de0-9ab4-6b4ab5986116 | note | Task Assigned To - Site Foreman
701999a4-54cd-5b5c-a48c-6712456953f5 | note | Measuring Devices or Method - Measuring Wheel or Tape
b81e3173-6fc6-59e0-a095-b0777c20a790 | note | Criteria - Sketch and record seal area and QA detail
e3e0c10a-0281-572f-9d45-c1d2c7f22775 | note | QA Form - QA Measurement Sheet
| checkpoint | Post Seal Care
ebd74920-e012-59e1-a602-ee410cddbc78 | note | Test Required - Visual inspection
d95f1382-04b3-50bf-87f8-a311653dfcfc | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
44492a7d-cc40-5b8d-96b5-d77de9f22a6d | note | Task Assigned To - Site Foreman
12eff720-709d-5d88-8f18-c4bb3862b75a | note | Measuring Devices or Method - Visual
cbcd7991-b7fd-5e68-a713-dd60cd153718 | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
5db6fe23-4612-5d24-ace0-10779251acd6 | note | QA Form - Daily Diary
| section | Chip Removal, Pavement Marking, Traffic Services
| checkpoint | Removal of excess chip
1e42311d-5f1f-5dca-9a10-a50f45c89033 | note | Test Required - Visual Inspection
25de1c67-2dff-50a4-b1ba-e90aff841421 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
bc504528-389c-5b6c-a919-3601480b1aff | note | Task Assigned To - Project Engineers/Site Foreman
6f5fd346-5be0-520e-a424-65770d204a1f | note | Measuring Devices or Method - Visual
3ff2f5d6-7b59-553c-a6ce-9d5026dd962a | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
ec54d021-e1e3-59d4-ac7f-2283f489139d | note | QA Form - Daily Diary
| checkpoint | Pavement Marking
acd0b334-c8c3-59d3-bbe3-491987d433df | note | Test Required - Visual Inspection
770fe5d4-130c-521d-b856-58818c3f8185 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
32174133-3bb4-55fd-b832-a6449eb12aa6 | note | Task Assigned To - Project Engineers/Site Foreman
ade8e1be-e4e1-53d3-ab07-9ff77f24da73 | note | Measuring Devices or Method - Visual
d4f45d1f-becb-5c7d-aa1c-14198bc1e389 | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
653296cc-9113-5e39-8bf7-f8377d66af27 | note | QA Form - Daily Diary
| checkpoint | Removal of TTM
58796da2-39b0-57cd-9783-d6f7695c5028 | note | Test Required - Visual Inspection
a0a35e40-613c-58e0-9620-c6c1d1b8d639 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
d2081b7f-91b4-5686-80ec-150c6e0896e6 | note | Task Assigned To - Project Engineers/Site Foreman
6e250860-6b94-519c-aced-356579d5f3a3 | note | Measuring Devices or Method - Visual
adfc2e9f-88f0-572c-851a-5f171887b991 | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
741ddc98-5834-5800-9e38-b76bb619172a | note | QA Form - Daily Diary
| checkpoint | Traffic Services
94b1db30-4180-5246-ac46-c159ceb4e1f9 | note | Test Required - Visual Inspection
51e1d611-2e20-5c5b-846c-dca5c3c68d77 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
c216540e-c3bd-5b6c-ab7e-44c5f9e69780 | note | Task Assigned To - Project Engineers/Site Foreman
45b3eb70-b641-5f55-b9e4-953e3f6d72a5 | note | Measuring Devices or Method - Visual
b3e0c72c-5b25-5db3-8ab5-ac79265586c6 | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
1f563038-1803-5bd6-8648-5cde48442d33 | note | QA Form - Daily Diary
| checklist | 5. HB AWPT ITP - Snee Rd II |  | 5. HB AWPT ITP - Snee Rd II | 1035b024-fbf6-4740-a368-468169a8d46f
| section | Preliminary / Establishment
| checkpoint | Establish TTM
5fb862be-9ce3-54a8-bad0-d7f8990c8d93 | note | Test Required - Visual Inspection
4bebd3d5-0878-5652-a879-0ecf932c28f9 | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
262420ab-a12c-5c78-9ea7-65bfe9e16a1b | note | Task Assigned To - STMS/Site Foreman
349d9718-39d7-58d1-8e9e-70fda974490b | note | Measuring Devices or Method - Visual
5b1b0ac1-fe26-5e9b-a2d8-70c71de8f3b2 | note | Criteria - As per TMP and ensure TMC advised in advance of works.
f9ed209f-e50f-5d59-bac0-c5b8b23b93f8 | note | QA Form - Daily Diary
| checkpoint | Permits
bf6fadf2-98a6-51e6-86d0-406c2b00db43 | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
f0b3bd95-732a-5fb8-a04a-771b1772ba6d | note | Test Required - Document Review
2a42d632-e47c-5146-a6e2-7ac1999f7310 | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
e017bff7-62b0-54de-b94a-8137ad89b72d | note | Task Assigned To - Site Foreman
03442ec9-5ef6-52ee-b4d0-bdc9ab4bebd0 | note | Measuring Devices or Method - Visual
c5e4b60e-892d-52e7-ad8a-755258ef1a9d | note | Criteria - Obtain permits and mark outs prior to construction
9d8a93d1-31e9-50f6-aa15-0491b7ecc4ef | note | QA Form - Copy of Permit on site
| checkpoint | Clear-Shoulder and Side drain
82ebda7f-436c-56bd-8b71-ed6ebb672dbf | note | Test Required - Visual Inspection
3b84ebac-cdcc-588b-988f-c5dbc8693523 | note | Task Assigned To - Project Engineers/Site Foreman
44dc7e4c-2069-58b9-a789-b180b98b90b7 | note | Measuring Devices or Method - Visual
23aa44b3-ed84-5954-8af0-fafbbfdf561e | note | QA Form - Daily Diary
| checkpoint | Digout Failed Areas
44a6d330-b0f1-5093-acb4-069b837dd72d | note | Test Required - Visual Inspection
e237dab7-9fb9-598f-9fd3-9582afa2774c | note | Task Timing / Minimum Task Frequency - As Requested
55bd27a7-6bfa-5b22-8024-a75dbe721705 | note | Task Assigned To - Project Engineers/Site Foreman
e8fe65de-1646-53c7-b8da-c37ddcf99d97 | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
5a8ce62d-89a9-516e-82bc-e46c2cea62d6 | note | Criteria - Backfill with Basecourse
a4b22c29-8bd2-52d4-9d97-04a25836ba38 | note | QA Form - Daily Diary
| section | Inspection Test Plan - In Situ Cement Stabilisation
| checkpoint | Cement for stabilisation
aebb764f-bff9-5b0b-8493-5a802b6b5dec | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
9e805c77-c118-51a8-a205-467286734232 | note | Test Required - Certified in accordance with NZS 3122
51a89581-afc3-5bd9-bc35-69299ac6ff2f | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
| checkpoint | Production plan
53e7cf42-c4c7-5ef5-b5ce-ba1f208a2cf5 | note | Specification Reference - NZTA B/5:2008, 7.2.2
478397b9-120e-5931-8338-f99c9557f0fd | note | Task Timing / Minimum Task Frequency - 1 per site
| checkpoint | Stabilisation mix properties (including cement):
41c8810b-ce97-5216-9bee-71d8081ebd09 | note | – Maximum dry density (MDD)
51d32042-8558-5948-9fea-4b1ebd40f6ba | note | – Optimum water conent (OWC)
3603ceb9-daaa-5044-bb0f-59a41cfdedad | note | – Solid density (SD)
f7fbfeda-eceb-545b-8e70-42590746f37c | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
f2d070fe-8c51-5c25-9237-1e6b51275027 | note | Test Required - Material properties for compaction verification
fe44a267-71c9-52fe-a1af-4c9cf404d8ca | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
b08db3d6-708f-56df-8a3e-116fdedb3430 | note | Task Assigned To - Hold Point - Approval required by site engineer
e00fef26-53fd-5351-ba28-437ce37e929c | note | QA Form - QA Measurement Sheet
| signoff | HOLD POINT
| checkpoint | In-situ moisture content of existing pavement aggregate
93c9e9ee-808f-5b03-9d0a-09d6f2deedf3 | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
4cd77759-4281-55a4-802c-6bccfda9e274 | note | Test Required - In-situ moisture content, Between 90% to 100% of OWC
ffbafcc8-bbdc-50e2-9b58-d132992f23f5 | note | Task Timing / Minimum Task Frequency - As required
ebdc325d-e1b6-5a76-aa72-69ef993caec1 | note | Task Assigned To - Inspection - Lab
317d2896-7b38-5665-9180-3834ba6b76fd | note | QA Form - QA Measurement Sheet
| checkpoint | Top-up metal
4ff31d20-9bc2-5c1f-b8a1-1d4f76790554 | note | Specification Reference - TNZ M/4 Table 4
d6ddd36a-1a28-5d75-8487-3d872e7a26a8 | note | Test Required - Placed to required depth and design levels
851a90b1-817f-5fa8-a749-fe1b91eecc52 | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
874aee0c-9699-565b-9de5-ae7a61169a84 | note | Task Assigned To - Site Foreman
17b8a7ae-1ba4-5456-ac6e-8b71ab63ff83 | note | QA Form - QA Measurement Sheet
| checkpoint | Cement spreading
f48953f3-7037-5ed8-8eee-7aa91bfdf7ba | note | Specification Reference - NZTA B/5:2008, 7.3
9951362b-c4ef-54db-bbfc-27c5bb3a607d | note | – Mat test (1m2 canvas mat)
3cf6f084-6e05-547e-9a4d-c4d1de4c30d6 | note | – Average usage test
4a71d46b-f42d-592f-bd88-c90211139970 | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
e69c5dc0-4bb6-52ee-98e0-8e4126ec5b0b | note | Task Timing / Minimum Task Frequency - Every 400 m2, Upon emptying spreader and bulk tanker
1c8712e8-f8dc-5524-b4a5-ef6cd815e640 | note | Task Assigned To - Inspection & sign off by Site Supervisor
1be1197b-7870-527b-8fef-dfbdda2709ba | note | QA Form - QA Measurement Sheet
| checkpoint | In-situ mixing - Cut depth
92dd9b9e-e5a0-5787-acd1-b01e3975454c | note | Specification Reference - NZTA B/5:2008, 7.6.1
9e720c70-0b9d-5d23-9e85-9c9601cc8d81 | note | Test Required - Maximum variation -5mm and +15mm
481e4ffb-7c33-5e74-be14-69c2d1e862ce | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
f164cc6f-f56a-56f4-8cd2-ca60b68a2418 | note | Task Assigned To - Inspection & sign off by Site Supervisor
550d228c-3ba6-51d6-a31d-8f2ec4a4da32 | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
1d47be70-6bb3-5de3-a6da-451652f17239 | note | Specification Reference - NZTA B/5:2008, 7.7.1, NZS 4402 Test 41.3
bf09f076-b687-59c9-ae1f-7c4de6e3d7c3 | note | Test Required - Plateau testing
b7c8b8d1-481f-5589-95a9-7b900eeb96ed | note | ○ Mean value ≥ 98% of MDD
3c9055fd-a2a8-5469-820b-e0e5d01987bd | note | ○ Minimum value ≥ 95% of MDD
df917caa-d608-5328-9341-7507672e0eb6 | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
130cbcda-ef40-5d9a-b1aa-8aec64b50a8a | note | Task Assigned To - Hold Point - Approval required by site engineer
d0c33c84-936c-5469-b018-66fc77533e5c | note | Measuring Devices or Method - Nuclear Densometer
260c1b34-0333-5080-8193-61edb22f3781 | note | Criteria - Minimum value 95% of MDD
b6a932df-f2c1-5ccb-9a60-3268cc67a981 | note | QA Form - Test Reports
| signoff | HOLD POINT
| checkpoint | Surface shape
d9f9bc18-f3ee-5b6b-934f-37c18fe882a0 | note | Specification Reference - NZTA B/5:2008, 7.8
6895f197-27e0-5d12-ac3c-fef5435d0910 | note | Test Required - ≤10mm from 3-metre straight edge, No depression, Vertical variations -5 + 15mm
4ce13567-a48c-5cc1-b8d6-aae891dd33f7 | note | Task Timing / Minimum Task Frequency - 20m intervals
4c77cc91-5bb6-53b3-8298-308d257e4791 | note | Task Assigned To - Inspection & sign off by Site Supervisor
7f62a0a3-b55f-5a1a-8592-20d3c2e8b779 | note | Measuring Devices or Method - Stringing, Tape measure
9d5801e3-7ce3-5525-a528-28386f2b363e | note | QA Form - QA Measurement Sheet
| checkpoint | Crossfall
6eb025a0-7003-59b5-8ade-89b527b199dd | note | Specification Reference - NZTA B/5:2008, 7.9
e73563a3-02f5-50ea-ac89-2334372b0771 | note | Test Required - Not less than exisitng crossfall at the start of construction
7e9d671d-1b2a-574c-9c81-a7fa5962c6a1 | note | Task Timing / Minimum Task Frequency - 20m intervals
e5ec48a5-ca6b-577c-959c-a09f628372aa | note | Task Assigned To - Inspection & sign off by Site Supervisor
602851d9-c4a5-5a41-a7e1-188ffd5ea5a3 | note | Measuring Devices or Method - Stringing, Tape measure
9b87c1ea-ca24-5723-9a08-8a26c3351b9a | note | QA Form - QA Measurement Sheet
| checkpoint | Surface finish
36fb6d18-fdf7-5f90-b30b-5299a94da29b | note | Specification Reference - NZTA B/5:2008, 7.10
095debb0-51b6-5535-9264-172864361177 | note | Test Required - See clause
08f25850-b878-50d8-92dd-3393d1d0a6af | note | Task Timing / Minimum Task Frequency - 20m intervals
a158e552-2eba-56a7-9b78-5d25930d76a4 | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
25ebef81-c28e-593a-831c-0b8223c335e6 | note | Measuring Devices or Method - Visual
| signoff | HOLD POINT
| checkpoint-no-value | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
| checkpoint-no-value | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
| section | Chipseal Construction (NZTA P29)
| checkpoint | Ensure appropriate TMP used
275769cf-a68b-5c69-a788-fa9bf07729cf | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
| checkpoint | Seal design
833ec145-eb43-58ba-82ba-f40e6a1e2bce | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
d9b8011f-daa6-5d43-8fd7-f1b98a52f505 | note | Task Assigned To - Project Engineer
bd831281-09b7-5a85-a7ba-f8636fffea2b | note | Criteria - Seal design to be reviewed prior to surfacing
97d3aab9-133e-5b90-a44f-36409076455a | note | QA Form - Seal design template
| signoff | HOLD POINT
| checkpoint | Location/Size Confirmation
02a1b64c-8be5-5a54-ae5f-49cba0c401ec | note | Specification Reference - Mark up extent of chipseal
9e8c2dfe-67e6-5480-9666-c0485faa1c1a | note | Test Required - Prior to surfacing
a41743b9-ec2f-5dfb-8304-723b06d7df6e | note | Task Timing / Minimum Task Frequency - Project Engineer
f5f0ad31-49f5-5389-a162-04bb1dd5a019 | note | QA Form - Daily Diary
| checkpoint | Surface Cleanliness
a449b7b0-4cb4-5d1d-97d3-8471f3ab5b7f | note | Test Required - Visual Inspection
a47b508e-4972-5be9-848b-64a5c94bf079 | note | Task Timing / Minimum Task Frequency - Prior to application of binder
450814d1-05d1-566e-a7e4-9d22f096cdde | note | Task Assigned To - Site Foreman
658cd04e-78b9-5d9f-a3db-af17129952e8 | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
835fa6e1-463e-5b0f-9ac7-c83d6a702d15 | note | QA Form - QA Measurement Sheet
| checkpoint | Plant Resource
80910abb-ac87-5301-a282-c4682cb3e21c | note | Test Required - Visual Inspection
e8ad88f3-fc48-572e-af37-be0e5066b1d2 | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
de996be6-6ca8-59c6-99cc-d11fd8060adb | note | Task Assigned To - Site Foreman
88b12ae1-3f6f-5580-bdfd-801b6179ae10 | note | Measuring Devices or Method - Visual
9da2428b-5ab1-532f-b969-14f854dbf7ee | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
9ffa929b-e37d-5a74-8842-f0078ccff996 | note | QA Form - Daily Diary
| checkpoint | Binder Application
588ea8e5-34f8-5c31-a211-e72529b4dd93 | note | Test Required - Binder type, Cutback, Temp, Application rates
ff2fc897-1282-5206-bc02-9178e34a8768 | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
731da5b5-149b-5f05-b721-9dd1c07625a1 | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
14c2f34b-bd51-54fe-96c2-56ce0463d720 | note | Measuring Devices or Method - Visual
dd4270eb-1016-5fd0-9167-ccce2a67f5b9 | note | Criteria - Binder Type = 180/200.
b89b45bf-0f69-5ea7-a4ac-0624d7a02427 | note | ○ Cutback to suit 1st coat seal 4pph kero max.
d2a74fcd-3c3b-549f-b4e3-b67c2a21f98b | note | ○ Temp = 150deg celcius min
d5f0552e-20c1-5066-a597-045c65739ff4 | note | ○ Application = Design l/m2, +/- 0.1 l/m2.
2315168a-9f38-59c3-aeee-9f1cd5e11ffc | note | QA Form - Bitumen Spray Sheets
| checkpoint | Chip Application
d1528ab9-f370-577b-b8a1-b25e13d8c57d | note | Test Required - Chip type, Chip Application
913316af-aa30-5ae1-a97e-ec29645b3590 | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
ced241d1-966f-545b-adee-c11ae5ec53bb | note | Task Assigned To - Site Foreman
8cc0bcec-3c15-5047-9c26-b29aa131e28a | note | Measuring Devices or Method - Visual
d5481c18-2d50-5e4a-84be-5d54d8a766ad | note | Criteria - Trucks loaded with correct chip.
5c3ccfa5-bed8-5a31-929a-941a075a7291 | note | ○ Chip clean. (G4/6 Racked example)
70124bce-03a2-5b47-8ce6-e131f9829ac3 | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
83c7c9d4-2158-5061-81ef-1f07f289578d | note | ○ G6 application = Enough to just fill the voids around the G4.
897a8fe7-ebb0-5760-ac56-c310cace84c7 | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
3c631c03-73a2-56bc-8b47-db3a3cd2a117 | note | Test Required - Visual
17664467-c75c-549f-a8f6-0e2fab89047f | note | Task Timing / Minimum Task Frequency - At completion of rolling
b7ab78dd-5c14-52bf-9903-670fea2fb22b | note | Task Assigned To - Site Foreman
91f88405-32ed-5370-b181-b9f828667a74 | note | Measuring Devices or Method - Visual
fb22ab97-560e-59bf-b64b-a7910b2a3ff4 | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
ae7384f7-60c7-5f5e-922d-ddb5ce33da52 | note | QA Form - 'QA Measurement Sheet
| checkpoint | Site Measure
b0b5a0d6-8a09-58f6-9357-cc8cff5fca62 | note | Test Required - Record final site measure
78d69b08-4771-5e22-94cc-944a8a21a057 | note | Task Timing / Minimum Task Frequency - Completion of works
77a036f7-ea0f-5170-bb84-7a7682c74aa1 | note | Task Assigned To - Site Foreman
1dc4d556-49c7-52bb-88da-debaecee95b2 | note | Measuring Devices or Method - Measuring Wheel or Tape
4c95b3a2-4d52-5eb0-8994-20636cd574e1 | note | Criteria - Sketch and record seal area and QA detail
98bceb82-33c8-5e29-a1d3-e200d67b824f | note | QA Form - QA Measurement Sheet
| checkpoint | Post Seal Care
c6ed3776-2d22-5b01-8f4f-a52897951eaf | note | Test Required - Visual inspection
ba2d6d7b-6b36-5aff-b5db-a57ca34558f0 | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
14019db0-3088-5312-8da8-d78d51b85a9c | note | Task Assigned To - Site Foreman
564248e7-ed7a-5f15-8392-3f9ee53a1157 | note | Measuring Devices or Method - Visual
d7676ef1-a9be-5af8-84e8-a0dca3f80519 | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
67119314-415a-5a38-897d-da4310ec6e61 | note | QA Form - Daily Diary
| section | Chip Removal, Pavement Marking, Traffic Services
| checkpoint | Removal of excess chip
3cf120cf-791a-5f72-97b2-8024c2c55571 | note | Test Required - Visual Inspection
328b6a72-3e50-59cd-8f8e-59a222e8023d | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
9d73e507-3617-5d65-98a1-d4f966e9e68f | note | Task Assigned To - Project Engineers/Site Foreman
782445b9-9c47-520f-986e-b1f10eef0fce | note | Measuring Devices or Method - Visual
60e06e5b-d7ba-54de-b61d-f4842146e0f4 | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
c4f3ff7a-cd4b-5063-b4cc-80dfff1d083a | note | QA Form - Daily Diary
| checkpoint | Pavement Marking
3bb830e2-953e-54bb-b7de-ac8b08fd5e12 | note | Test Required - Visual Inspection
16920172-9eac-5c8a-a297-5c1f4f57bc22 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
352cd3a6-8f77-5ea3-96fa-20a5e3005592 | note | Task Assigned To - Project Engineers/Site Foreman
64344400-d63a-56fc-8091-a3c1b3c5fede | note | Measuring Devices or Method - Visual
f75a6688-deaa-568c-bf64-e66f934cc2f6 | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
4febb4d8-cb23-572e-9c1c-cf2df71c6d2b | note | QA Form - Daily Diary
| checkpoint | Removal of TTM
01f43b0b-3305-586d-bff9-3cb82910aa6a | note | Test Required - Visual Inspection
2bd5e1cb-1438-5638-85d3-dab742295b06 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
f457cf51-fcb3-5ef8-978c-6c1ccba99097 | note | Task Assigned To - Project Engineers/Site Foreman
6eb9ceab-cf85-5ba4-83b9-6cc7370fa54d | note | Measuring Devices or Method - Visual
803d126a-38b0-5b95-b106-21c292776318 | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
df8b71fa-3b9d-5bf4-9eff-c1308d33e271 | note | QA Form - Daily Diary
| checkpoint | Traffic Services
150d2d54-682f-51ea-99ce-94c31ac44ba6 | note | Test Required - Visual Inspection
b5bdec19-05ed-5409-bb36-63d2b61f86a0 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
7b8f908e-b1e9-5877-9c05-88c10708e659 | note | Task Assigned To - Project Engineers/Site Foreman
4587dde2-5108-59ae-b1cb-91bee594b060 | note | Measuring Devices or Method - Visual
cfe0c9bd-a78c-542b-920e-1bd2fe961838 | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
1ca12b25-9c65-545e-97bb-6658bc8e1bf8 | note | QA Form - Daily Diary
| checklist | 6. HB AWPT ITP - Nth of Waione Bridge |  | 6. HB AWPT ITP - Nth of Waione Bridge | 54adc08f-bf54-4de4-8154-ae208e12713d
| section | Preliminary / Establishment
| checkpoint | Establish TTM
38d9a751-bb54-534e-b8d5-c63aeb68ee3a | note | Test Required - Visual Inspection
ed8fe355-b711-5b30-8fcb-df3ba0df4033 | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
eeea2cb5-6a24-5000-8f5a-c88d1f0e23b6 | note | Task Assigned To - STMS/Site Foreman
3c7b36c2-9cce-5564-8bdd-ba439606a2a1 | note | Measuring Devices or Method - Visual
ef04f272-1fd0-51a6-8bbb-b9e2409da624 | note | Criteria - As per TMP and ensure TMC advised in advance of works.
3c46f11a-68ac-5a06-affc-ff826fe932ac | note | QA Form - Daily Diary
| checkpoint | Permits
6d20d895-3d12-5283-97ea-23802ef7d9dd | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
62d65d6e-ab09-5688-8c85-588968de595d | note | Test Required - Document Review
e844dc36-6786-5102-91bd-ff5e3a13cbe5 | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
21786bd6-6b5c-5203-b606-7e55c6041472 | note | Task Assigned To - Site Foreman
31e0de35-0a91-5e55-9b29-265f9b77a079 | note | Measuring Devices or Method - Visual
d8d52c64-79d5-5567-9f8f-3a16694a6a11 | note | Criteria - Obtain permits and mark outs prior to construction
4c28e2e7-2deb-5e5b-a40b-9690846e0eaa | note | QA Form - Copy of Permit on site
| checkpoint | Clear-Shoulder and Side drain
5778fbe3-c6ac-5552-942b-54a92ae00b9c | note | Test Required - Visual Inspection
1d31aff9-3b90-5d99-80ea-3a91d242e443 | note | Task Assigned To - Project Engineers/Site Foreman
eb2be1ea-d2c9-5e3f-aeea-eb2fd56adb00 | note | Measuring Devices or Method - Visual
6a29dd35-9901-5fb1-acf4-9abdbb8a8486 | note | QA Form - Daily Diary
| checkpoint | Digout Failed Areas
ce29fc28-570c-5f04-9871-93e152d9b129 | note | Test Required - Visual Inspection
fee47c67-b1e3-5931-b055-4f5290613ab0 | note | Task Timing / Minimum Task Frequency - As Requested
83ea561a-a11e-56be-9eff-fbfd0930f239 | note | Task Assigned To - Project Engineers/Site Foreman
25bd2da9-656f-538f-8c78-623354f67665 | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
830ff297-abf6-5c62-9093-c60d92b3cab6 | note | Criteria - Backfill with Basecourse
c89e998f-e980-5c7a-a99e-683cce6b0c56 | note | QA Form - Daily Diary
| section | Inspection Test Plan - In Situ Cement Stabilisation
| checkpoint | Cement for stabilisation
53430fa4-7f77-50f8-85c7-0d37fb39e9c5 | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
0dcd4ed0-c426-5e33-bd79-366820f3dd2d | note | Test Required - Certified in accordance with NZS 3122
a678e196-abc9-52f0-9ee3-1bbe425f86cc | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
| checkpoint | Production plan
26140ea8-7985-5fd4-8114-a32d98ffbf5c | note | Specification Reference - NZTA B/5:2008, 7.2.2
adc08a4f-95ca-5c01-a58d-8d124fc8edc1 | note | Task Timing / Minimum Task Frequency - 1 per site
| checkpoint | Stabilisation mix properties (including cement):
35c9d167-448b-5979-b548-0c32c52c1d81 | note | – Maximum dry density (MDD)
cf3783b6-ab21-5bf5-a783-d1d6ef370607 | note | – Optimum water conent (OWC)
eefd2679-41de-5823-8cfe-82cc645a803d | note | – Solid density (SD)
aa2ff381-eed7-50a4-a5d7-06c6a9840be1 | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
9ac6296f-53b8-513e-87b2-9f4086569b69 | note | Test Required - Material properties for compaction verification
ea8e9578-4433-5b7e-b737-dce0bd3687bc | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
f28f717a-d1d9-5817-8583-7d1d40a6019d | note | Task Assigned To - Hold Point - Approval required by site engineer
e4ce7070-8e67-543e-88ba-dadec32270e5 | note | QA Form - QA Measurement Sheet
| signoff | HOLD POINT
| checkpoint | In-situ moisture content of existing pavement aggregate
7247f360-89ee-5655-8cbe-39b225ce226c | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
8cc10f80-948a-5734-9cb0-b14fe3b27141 | note | Test Required - In-situ moisture content, Between 90% to 100% of OWC
bc10c98a-95e5-5688-aad9-cda64322aaf7 | note | Task Timing / Minimum Task Frequency - As required
91f58eb3-409a-5a82-a636-03f48160b967 | note | Task Assigned To - Inspection - Lab
77614e93-241e-5c36-a822-7c663ebada4d | note | QA Form - QA Measurement Sheet
| checkpoint | Top-up metal
0ccbed2b-c0e1-51c5-b5d1-18f80c210d97 | note | Specification Reference - TNZ M/4 Table 4
f89beff0-624f-5894-b365-7706e43eeacd | note | Test Required - Placed to required depth and design levels
9a7dde5f-d167-518d-9c21-69b8096fb8cd | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
07f89223-29df-5d6e-9f91-757af2498567 | note | Task Assigned To - Site Foreman
74e67f79-7d75-51c5-8ced-5a8c9357ed7e | note | QA Form - QA Measurement Sheet
| checkpoint | Cement spreading
7d34751e-d72b-5fb8-8238-6c54b0a28688 | note | Specification Reference - NZTA B/5:2008, 7.3
3208117e-9bf7-584c-9a76-2cbf2f89ac43 | note | – Mat test (1m2 canvas mat)
1fbac610-74ac-5b47-9501-9b511b30c5a2 | note | – Average usage test
1946b65b-0160-5580-b215-a7a28620c92e | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
37478768-39ac-5c71-ad35-099fe76f1849 | note | Task Timing / Minimum Task Frequency - Every 400 m2, Upon emptying spreader and bulk tanker
6d17fb88-edf8-5c1b-8d53-6393536c04de | note | Task Assigned To - Inspection & sign off by Site Supervisor
e19e75db-d5c2-57f5-93bb-e7610d2556c1 | note | QA Form - QA Measurement Sheet
| checkpoint | In-situ mixing - Cut depth
65f11e5c-0e8c-5fb3-953f-d7d51d7098ac | note | Specification Reference - NZTA B/5:2008, 7.6.1
ad0a933a-0e1f-5bcc-ba1d-05b37a097fa7 | note | Test Required - Maximum variation -5mm and +15mm
ceae56f6-7df0-57e3-8059-5447b68073b1 | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
a6231344-03d5-5ee3-b0dc-1725bf824367 | note | Task Assigned To - Inspection & sign off by Site Supervisor
e3afb3db-292e-5060-9e5b-8d92bc989e83 | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
5a301811-7790-59f5-a5a3-526dd24eedd9 | note | Specification Reference - NZTA B/5:2008, 7.7.1, NZS 4402 Test 41.3
eeb6323b-8d45-5dc7-9af2-16648679fdc2 | note | Test Required - Plateau testing
dc26cc31-ddaa-5045-a70c-8a7341d2245b | note | ○ Mean value ≥ 98% of MDD
edb485cf-78c7-5b37-9912-08756d50d3a4 | note | ○ Minimum value ≥ 95% of MDD
b49d5b1c-540d-52bc-aa9e-195569022eeb | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
1360da9c-aa8a-51b1-9466-4a3f6bd4def5 | note | Task Assigned To - Hold Point - Approval required by site engineer
bbf325ae-515e-5d3b-990b-e6ec1ddc737e | note | Measuring Devices or Method - Nuclear Densometer
3fcd3648-5278-5a2e-a773-c3634126eaaa | note | Criteria - Minimum value 95% of MDD
dcfab9b8-b540-5f2e-b6b4-540053b14e82 | note | QA Form - Test Reports
| signoff | HOLD POINT
| checkpoint | Surface shape
1c5f9c0d-680c-5c62-ace6-392d948ae546 | note | Specification Reference - NZTA B/5:2008, 7.8
ec4238b5-02e8-596e-9a76-271b087b4a08 | note | Test Required - ≤10mm from 3-metre straight edge, No depression, Vertical variations -5 + 15mm
0afd0d70-cdd4-5b41-bf0e-89c85fa51ab9 | note | Task Timing / Minimum Task Frequency - 20m intervals
3a3ba271-c201-52ca-a5be-64e651878b83 | note | Task Assigned To - Inspection & sign off by Site Supervisor
fe47eb8d-9f35-57cd-9023-6493f260a712 | note | Measuring Devices or Method - Stringing, Tape measure
ff0d3795-6a0b-514b-b164-688af956af27 | note | QA Form - QA Measurement Sheet
| checkpoint | Crossfall
3b9de9e4-50c8-5549-b1d4-40b9148ed0f1 | note | Specification Reference - NZTA B/5:2008, 7.9
a9bdfb51-028b-58b2-bfb9-8f5ecf163652 | note | Test Required - Not less than exisitng crossfall at the start of construction
297ee8a1-c393-5993-b2d6-e3920126cd50 | note | Task Timing / Minimum Task Frequency - 20m intervals
4aa45d2e-05ce-5346-9823-328c8cc26d8a | note | Task Assigned To - Inspection & sign off by Site Supervisor
011b0f29-4b57-596d-bb70-5187fad27266 | note | Measuring Devices or Method - Stringing, Tape measure
4890b899-572f-5571-83c4-67710206f13f | note | QA Form - QA Measurement Sheet
| checkpoint | Surface finish
9ea988dc-4c01-5be3-b035-36235fb5f07a | note | Specification Reference - NZTA B/5:2008, 7.10
36c2a529-5f61-5d1a-8e74-26b86eb2f97b | note | Test Required - See clause
5baaeff9-fb66-5018-9052-9465caca2331 | note | Task Timing / Minimum Task Frequency - 20m intervals
d34d2fd3-3ff5-5d2b-9450-ddddbd4c34b7 | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
d9e2db30-4bb9-5488-a084-c521460b2b42 | note | Measuring Devices or Method - Visual
| signoff | HOLD POINT
| checkpoint-no-value | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
| checkpoint-no-value | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
| section | Chipseal Construction (NZTA P29)
| checkpoint | Ensure appropriate TMP used
84f51587-3292-5a95-b118-f432d4fad642 | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
| checkpoint | Seal design
57b89ce8-4957-53a5-a05d-286ce3b9cc79 | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
46e37d65-67e2-5888-839c-ef766cd7b03d | note | Task Assigned To - Project Engineer
2fb7259e-0012-5d1e-9014-ca3ade8d2b88 | note | Criteria - Seal design to be reviewed prior to surfacing
60084855-19d1-57dc-acb6-443acc1d2d06 | note | QA Form - Seal design template
| signoff | HOLD POINT
| checkpoint | Location/Size Confirmation
3247cd18-5d89-5512-803e-0cae8649db73 | note | Specification Reference - Mark up extent of chipseal
a5cc1917-8312-5901-8f19-d998bd80ffe7 | note | Test Required - Prior to surfacing
ce3f9973-00c9-5a39-878d-9c3151215421 | note | Task Timing / Minimum Task Frequency - Project Engineer
1278892d-9274-5d29-8ac2-59ec026767f3 | note | QA Form - Daily Diary
| checkpoint | Surface Cleanliness
5bfe132b-14b7-50f4-a8eb-540dc80dddd7 | note | Test Required - Visual Inspection
9443a80f-30f3-58dc-97a6-218de27646a8 | note | Task Timing / Minimum Task Frequency - Prior to application of binder
7ac9813a-7c00-5fd7-95cf-c8cb65ecfdbe | note | Task Assigned To - Site Foreman
0569fcb4-9410-5d6a-9bc8-72218593f7ba | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
f79cf4f5-7c7d-5956-a09c-758f77da6ec8 | note | QA Form - QA Measurement Sheet
| checkpoint | Plant Resource
320ceb20-ab7a-538c-9956-bd39f28cdc0e | note | Test Required - Visual Inspection
0d7a1c3a-bac3-5058-9b61-de7098a1bb6e | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
e2de6435-cea9-5ceb-b0d6-32b29f99e779 | note | Task Assigned To - Site Foreman
4a24acd1-82a4-5e32-b7bc-591c4c302f9c | note | Measuring Devices or Method - Visual
9fb33ce8-8f5c-5502-b8e7-d80303883100 | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
67577120-da7c-5413-9539-d2fd7ff4d5a7 | note | QA Form - Daily Diary
| checkpoint | Binder Application
bdcce479-ab53-5253-bf3e-ccea91f82f8f | note | Test Required - Binder type, Cutback, Temp, Application rates
7a31b4a6-a7dc-51c5-ae6b-1bcf2f8e7806 | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
9202987b-e12c-5cfb-8111-412dd065c181 | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
b17c3ff7-2575-530b-a9d9-fa1854522952 | note | Measuring Devices or Method - Visual
fa96ba39-78a9-52dd-9460-f68c519507bd | note | Criteria - Binder Type = 180/200.
0b8f03a0-c84d-5003-bb8d-0ad76f45a8ca | note | ○ Cutback to suit 1st coat seal 4pph kero max.
e0dd6147-e262-5954-9a94-89b24e8cb66c | note | ○ Temp = 150deg celcius min
9311d1c2-3734-5516-9adc-94f81a0039c6 | note | ○ Application = Design l/m2, +/- 0.1 l/m2.
6381c34e-fd59-5574-968a-5a1c95d7f894 | note | QA Form - Bitumen Spray Sheets
| checkpoint | Chip Application
1d942dcc-5a48-5255-90fc-7c9828b1b169 | note | Test Required - Chip type, Chip Application
75563529-6155-5143-9b25-e91f9a929c80 | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
897a98b4-5e47-59ae-941e-2c702d1e7b66 | note | Task Assigned To - Site Foreman
f721e793-5d54-56f7-96c8-fef5e789e518 | note | Measuring Devices or Method - Visual
bb79996f-8a9c-5a84-8617-bf1edb56335c | note | Criteria - Trucks loaded with correct chip.
cffa1cc1-48f2-511d-b522-9cdd44589276 | note | ○ Chip clean. (G4/6 Racked example)
0a063d3c-0a91-5283-bb9d-6c6451ffde0a | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
7bde1a68-6473-5d3b-af2f-d2c5802aa8e3 | note | ○ G6 application = Enough to just fill the voids around the G4.
96595aa6-5062-55ff-a6ac-1ce4e9aa6eec | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
14a66912-dda8-54f8-a023-40e09cba41e7 | note | Test Required - Visual
288d6889-2dd1-5973-a0af-e19d1954b51d | note | Task Timing / Minimum Task Frequency - At completion of rolling
1138f4a4-21f3-5893-a82b-b009cb13bbe8 | note | Task Assigned To - Site Foreman
11c1df9e-bdf0-59bc-b912-31a5ce2663a0 | note | Measuring Devices or Method - Visual
91d1b185-aa2a-5519-91b7-ee2760226f19 | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
85a1a6fa-80e4-50a9-8cdc-65031f8fb053 | note | QA Form - 'QA Measurement Sheet
| checkpoint | Site Measure
9e9089d4-8939-5076-b268-b015f84013b2 | note | Test Required - Record final site measure
c711cb7a-5da6-5003-9cee-a32f1c942263 | note | Task Timing / Minimum Task Frequency - Completion of works
0b23aa7a-6a18-546e-882d-b25aa55536a9 | note | Task Assigned To - Site Foreman
a006b963-0bfd-5c7c-9c45-fd90a2451d9d | note | Measuring Devices or Method - Measuring Wheel or Tape
fba6e9ab-fa37-595a-8b2c-df46fdd16cf4 | note | Criteria - Sketch and record seal area and QA detail
8a597c6b-001c-5d0c-a09a-c7e3017036ce | note | QA Form - QA Measurement Sheet
| checkpoint | Post Seal Care
ec5bddbc-ea9f-5588-bdc1-807b99d0c3ee | note | Test Required - Visual inspection
4405e873-0f03-5dbe-91c8-db6900ff6098 | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
25da6529-5275-5fe8-bf3b-e80ecedce2f7 | note | Task Assigned To - Site Foreman
702c69e1-b0c6-5fd0-813e-9556a8a0ece2 | note | Measuring Devices or Method - Visual
c515a892-da8d-5f03-b1c3-d9d941bdd260 | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
4c35fa18-4771-554d-944c-2243d60ba1af | note | QA Form - Daily Diary
| section | Chip Removal, Pavement Marking, Traffic Services
| checkpoint | Removal of excess chip
e5c51db8-7dbc-51f1-ae9d-bc53cc6e44c3 | note | Test Required - Visual Inspection
c2cdad7f-155b-5622-89af-fbc6c5c845d5 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
05ec0b81-812e-5caf-a04e-230e415a3b12 | note | Task Assigned To - Project Engineers/Site Foreman
7727649b-628a-5512-b75e-c82c56ffcb5a | note | Measuring Devices or Method - Visual
05b27c11-6499-566e-9919-41c8091608c4 | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
a4366244-d03a-500b-a104-6213ef3c0189 | note | QA Form - Daily Diary
| checkpoint | Pavement Marking
39417e24-e4d2-538d-9e66-2514c242794a | note | Test Required - Visual Inspection
a3a620b0-c2ed-53af-b7aa-904da73f2b5b | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
c7581edd-37ea-5d2e-bc14-04875ac7826a | note | Task Assigned To - Project Engineers/Site Foreman
7e0da1b2-6f50-5837-8298-d83464cc594e | note | Measuring Devices or Method - Visual
b1c46ad4-6df0-5dda-ad69-0f2ad9c01fe0 | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
25f9b1c3-b46a-5385-8fb6-fe71190dada7 | note | QA Form - Daily Diary
| checkpoint | Removal of TTM
4d6ec002-ea5c-51ed-9792-17c972f8ef69 | note | Test Required - Visual Inspection
58697d87-c5f9-58fb-8459-a842a1545416 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
23a1c201-cdf3-5f1f-b363-68a84aa0e819 | note | Task Assigned To - Project Engineers/Site Foreman
20de402a-12f2-51c3-abd1-006bc83af8be | note | Measuring Devices or Method - Visual
cc5a3294-7c46-51a7-bba5-ab4a54ab3776 | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
6e71cb8e-bdff-544f-b506-42635565853e | note | QA Form - Daily Diary
| checkpoint | Traffic Services
000fe201-64e4-546a-a804-c4ca2f95aae8 | note | Test Required - Visual Inspection
ffde1824-f216-5100-9387-1bf1ff960c75 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
98a1f0ba-d851-5afb-bd6b-daec4b80eab1 | note | Task Assigned To - Project Engineers/Site Foreman
1e281de1-3c70-5891-bd00-93d7d019637f | note | Measuring Devices or Method - Visual
a0726351-caa2-5590-ae0d-e26d4b11a75a | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
931cef85-90ea-5014-9929-4f023ced4b19 | note | QA Form - Daily Diary
| checklist | 7. HB AWPT ITP - Maori Gully II |  | 7. HB AWPT ITP - Maori Gully II | 73315b14-924f-4dab-8cf6-f73620b4e06d
| section | Preliminary / Establishment
| checkpoint | Establish TTM
9e727d69-e6d0-5c15-b5fd-32fcc6e88d29 | note | Test Required - Visual Inspection
452927ff-e8eb-5e11-a1d0-70b1bfaded73 | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
9bb146c0-d2af-5eea-b19e-e79b7ee5516f | note | Task Assigned To - STMS/Site Foreman
8a97edbb-0d75-5f94-aa75-4de275df4514 | note | Measuring Devices or Method - Visual
1f53a997-cf46-523d-9437-7cde01b6ca99 | note | Criteria - As per TMP and ensure TMC advised in advance of works.
a0a1915d-6a1e-5b1e-be6c-3f521f5cb894 | note | QA Form - Daily Diary
| checkpoint | Permits
214e6942-2a7d-5f71-ab32-c2845937d59a | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
c49ea305-78eb-50a1-a761-40ff3874554f | note | Test Required - Document Review
c98e7472-20ce-55ed-b78c-2a26ae11074d | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
5f2665ee-89c4-53af-b7be-178c0bfee858 | note | Task Assigned To - Site Foreman
b76679a4-4be6-57ea-a258-ca93fa370a6a | note | Measuring Devices or Method - Visual
f3c7b250-ca60-5b21-a484-15507719d077 | note | Criteria - Obtain permits and mark outs prior to construction
63375072-db9d-523e-ab86-3bdda92b775e | note | QA Form - Copy of Permit on site
| checkpoint | Clear-Shoulder and Side drain
495d8504-de5f-5153-9f3d-9dcd19b85617 | note | Test Required - Visual Inspection
cce986d6-8585-5307-aa70-3ad7e33ea4ea | note | Task Assigned To - Project Engineers/Site Foreman
ccdb8f73-c74e-51cb-95dd-334a095e1853 | note | Measuring Devices or Method - Visual
fdfb7bea-ef97-5ebf-9ed3-f9d7b43fc54d | note | QA Form - Daily Diary
| checkpoint | Digout Failed Areas
2942f81e-a0f1-50bd-a35f-6c872dbf8e19 | note | Test Required - Visual Inspection
198cd783-5947-5c57-96cb-0169fa92c855 | note | Task Timing / Minimum Task Frequency - As Requested
a3bbd18b-5d75-5ebc-9aaf-7f3a8eab56a9 | note | Task Assigned To - Project Engineers/Site Foreman
3049eb92-a325-5be7-b3fc-940a8797a536 | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
53592d48-d13f-5a64-a83f-8d6d3941cb23 | note | Criteria - Backfill with Basecourse
7024b36d-ec57-5ee8-80f1-cf428e46dbc2 | note | QA Form - Daily Diary
| section | Inspection Test Plan - In Situ Cement Stabilisation
| checkpoint | Cement for stabilisation
d6d75fef-8d13-555e-9c4c-aedd8790dc4d | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
f736fd03-5735-5e51-93e5-8ac54d245f5c | note | Test Required - Certified in accordance with NZS 3122
657601a3-a596-5415-92eb-cb473a6a9c15 | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
| checkpoint | Production plan
4499221e-d0ec-5e33-8de4-07bcbaff3fec | note | Specification Reference - NZTA B/5:2008, 7.2.2
6fa55405-2b10-5392-93a6-50166813138f | note | Task Timing / Minimum Task Frequency - 1 per site
| checkpoint | Stabilisation mix properties (including cement):
3e6b7318-01b3-5ee5-94c5-285d40514d16 | note | – Maximum dry density (MDD)
4136c32c-1c66-580c-8001-61d16c858b1d | note | – Optimum water conent (OWC)
5cb7d2ff-145c-51a3-92f1-b986cdd8f508 | note | – Solid density (SD)
5e8d775c-da37-574c-88e5-f83f33ab0649 | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
f1cf27d6-dcff-5779-9e2f-4dd28248306d | note | Test Required - Material properties for compaction verification
71e2ec38-36f6-59cb-ad3b-511be806fc17 | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
ac73eaae-fbcb-5794-b0ef-1bb05fc1c8ad | note | Task Assigned To - Hold Point - Approval required by site engineer
9175c801-d476-525a-9a98-4b42e37a26a1 | note | QA Form - QA Measurement Sheet
| signoff | HOLD POINT
| checkpoint | In-situ moisture content of existing pavement aggregate
9e66b795-eb9d-50c3-a83e-881ac67cee09 | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
a3711edf-8cea-53a9-85cf-b99f3f8d5b47 | note | Test Required - In-situ moisture content, Between 90% to 100% of OWC
033c3441-9cb9-5111-8c1c-402ff81dd258 | note | Task Timing / Minimum Task Frequency - As required
9b99a7da-63e4-563c-b884-726e151162a8 | note | Task Assigned To - Inspection - Lab
bd09d86b-148f-5386-b91c-d2b5bcdeee17 | note | QA Form - QA Measurement Sheet
| checkpoint | Top-up metal
9a8a3828-9d10-5048-be36-ae1c0d83bf84 | note | Specification Reference - TNZ M/4 Table 4
cd81896c-1f2b-552f-8316-2a532d7e34ed | note | Test Required - Placed to required depth and design levels
5a12cb64-d970-5c6a-bb6d-1d6c1212cd25 | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
e7e0cfa9-d265-56f7-8dd2-fdd25854652a | note | Task Assigned To - Site Foreman
5fc938e6-22de-5608-ae00-0aff594e5d7f | note | QA Form - QA Measurement Sheet
| checkpoint | Cement spreading
627bf848-56fc-5f2b-9597-37afc94e2a04 | note | Specification Reference - NZTA B/5:2008, 7.3
a36ace53-ddda-52a0-acd2-861dfe9d1cda | note | – Mat test (1m2 canvas mat)
e6d03b99-eab8-5d9e-8944-798041b3ece5 | note | – Average usage test
456bcdb4-6387-53ce-9487-b44722016805 | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
663c2c92-e950-52bc-a8d6-d394a5c51f40 | note | Task Timing / Minimum Task Frequency - Every 400 m2, Upon emptying spreader and bulk tanker
5d9dff98-931b-5ec2-a6ab-0ae4c5660b00 | note | Task Assigned To - Inspection & sign off by Site Supervisor
6b12f254-c937-57aa-a443-37310fe2b7df | note | QA Form - QA Measurement Sheet
| checkpoint | In-situ mixing - Cut depth
a52fafa3-6132-5e1e-82f4-f9a160fdf074 | note | Specification Reference - NZTA B/5:2008, 7.6.1
d04e632d-a535-53f8-a3b8-f36d672dc60d | note | Test Required - Maximum variation -5mm and +15mm
98ece1fb-ec29-5af4-b451-faec88f0d7a5 | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
5c28fb65-8abb-5251-927a-2daec1984e5f | note | Task Assigned To - Inspection & sign off by Site Supervisor
d059b241-4acb-569d-ad63-42b4945f5d6b | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
b5181747-d69f-55b0-bc44-f61c87e002fe | note | Specification Reference - NZTA B/5:2008, 7.7.1, NZS 4402 Test 41.3
01e80b6a-59e6-5fa2-86cc-3caa21e7cf18 | note | Test Required - Plateau testing
a5551f41-8b46-52da-9b28-4ae814d54b75 | note | ○ Mean value ≥ 98% of MDD
f8064a62-b66b-55b2-a2a9-1707c0da7139 | note | ○ Minimum value ≥ 95% of MDD
a026ece9-14b7-583c-91ff-7b34a84ea363 | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
97d287f2-a93f-51a7-9357-3e4fcfd9b2e4 | note | Task Assigned To - Hold Point - Approval required by site engineer
637606ee-9c8f-5041-a476-ac676e1d1bf4 | note | Measuring Devices or Method - Nuclear Densometer
ae5003d5-eb80-5e96-b233-af607447320a | note | Criteria - Minimum value 95% of MDD
e63f2b45-f4cd-58ac-8712-e1613cc8a396 | note | QA Form - Test Reports
| signoff | HOLD POINT
| checkpoint | Surface shape
27f5add4-837b-553b-8018-cc8f7987e957 | note | Specification Reference - NZTA B/5:2008, 7.8
34652781-8c57-5e9b-a5b6-96c9906fd827 | note | Test Required - ≤10mm from 3-metre straight edge, No depression, Vertical variations -5 + 15mm
2ef8eaf6-0bb4-59c5-8d1f-62c563c68272 | note | Task Timing / Minimum Task Frequency - 20m intervals
e0abb821-55df-5f89-a9dd-d2304bd048b5 | note | Task Assigned To - Inspection & sign off by Site Supervisor
485ab4c9-0e8a-5e67-8bbd-88469c24c9f0 | note | Measuring Devices or Method - Stringing, Tape measure
4a6cebdf-49df-52dc-92e9-0814a4853de6 | note | QA Form - QA Measurement Sheet
| checkpoint | Crossfall
36a030f6-0dc8-5256-8cc5-3763fa9d2430 | note | Specification Reference - NZTA B/5:2008, 7.9
fad195eb-8c5e-5da8-a60c-0e6fbd393a15 | note | Test Required - Not less than exisitng crossfall at the start of construction
8e634981-6ef9-5475-89a0-5791c95f2f1f | note | Task Timing / Minimum Task Frequency - 20m intervals
a28a0011-3e7e-5eab-a3af-a72727f7eaa2 | note | Task Assigned To - Inspection & sign off by Site Supervisor
dbee86bf-a2ad-5053-87ad-22d646a5845d | note | Measuring Devices or Method - Stringing, Tape measure
6b61478e-9dd6-565d-b815-1bfbf80aad49 | note | QA Form - QA Measurement Sheet
| checkpoint | Surface finish
cc0b0195-d04d-559e-ba26-205962c78d4c | note | Specification Reference - NZTA B/5:2008, 7.10
4783037a-0de5-503f-ab36-5f1d3f328ca1 | note | Test Required - See clause
75cce73b-8daf-5ef0-821e-4e46668c6872 | note | Task Timing / Minimum Task Frequency - 20m intervals
a5075f49-de10-5f2f-ad11-6f48023a8c2a | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
5017875c-faf7-55bd-b1fd-b65a394aa0f1 | note | Measuring Devices or Method - Visual
| signoff | HOLD POINT
| checkpoint-no-value | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
| checkpoint-no-value | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
| section | Chipseal Construction (NZTA P29)
| checkpoint | Ensure appropriate TMP used
fbbc7485-7643-59f4-b998-d2cebeac3a9f | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
| checkpoint | Seal design
2573347e-06a6-5011-bd4a-1fcfdb9159fb | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
28036359-c695-5611-8074-35379b8b8f14 | note | Task Assigned To - Project Engineer
31f19ff0-e08b-5b6e-9dae-74e4aad625c2 | note | Criteria - Seal design to be reviewed prior to surfacing
966d3014-7d93-5977-a6d2-45c813533173 | note | QA Form - Seal design template
| signoff | HOLD POINT
| checkpoint | Location/Size Confirmation
0d5a0481-1d89-50ef-baab-b2468f3afe8f | note | Specification Reference - Mark up extent of chipseal
8f995ebb-7321-5f3b-9568-e5e37c56af13 | note | Test Required - Prior to surfacing
63e51689-d220-55d2-81bb-9e87babbaa4a | note | Task Timing / Minimum Task Frequency - Project Engineer
cb9a5507-7699-569b-80bf-3ce464de022a | note | QA Form - Daily Diary
| checkpoint | Surface Cleanliness
1c04d82d-4be2-5857-b363-6dd8cd2da193 | note | Test Required - Visual Inspection
7f737f98-2796-5858-b6f5-bd25c106fdc2 | note | Task Timing / Minimum Task Frequency - Prior to application of binder
1363f441-7599-5974-a55b-d6158900a264 | note | Task Assigned To - Site Foreman
2fb9765d-c893-5e94-a460-d8e9b66cc961 | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
adf72013-6fd8-5ffb-a44b-c838cadeb0d8 | note | QA Form - QA Measurement Sheet
| checkpoint | Plant Resource
939237e9-ab87-579e-a9af-dedd46195fb6 | note | Test Required - Visual Inspection
15f9fcf7-7594-5feb-b119-0e5a75196d2a | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
2bb543bc-bbdc-5433-a1c6-7f8113536ae6 | note | Task Assigned To - Site Foreman
3db8641b-502d-5aae-b08d-0bf5a0df88d3 | note | Measuring Devices or Method - Visual
40b037e1-9a02-5d2c-b144-735ac6599e8c | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
15e622ed-d484-5720-87d2-7cf8019b2433 | note | QA Form - Daily Diary
| checkpoint | Binder Application
5c56c43a-fc02-5724-9e30-c7d936fd8c33 | note | Test Required - Binder type, Cutback, Temp, Application rates
0df12f9e-c318-5b86-abea-bf96c2759486 | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
e6ea6ea9-c077-574c-897a-dc2550d58528 | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
86f6f219-6b0c-5a94-85e2-db2971b55ef5 | note | Measuring Devices or Method - Visual
806767c3-e5c6-5d7d-9b7c-2e2a9d691503 | note | Criteria - Binder Type = 180/200.
d9f93319-d9dc-5034-a098-91d522de6dab | note | ○ Cutback to suit 1st coat seal 4pph kero max.
4014c17c-70d5-52cf-ad39-dfac0cac043f | note | ○ Temp = 150deg celcius min
bc426ef9-0e1f-526f-9f7c-abf31430c811 | note | ○ Application = Design l/m2, +/- 0.1 l/m2.
c05868dd-3d0f-5265-bfef-6ad24189d9f0 | note | QA Form - Bitumen Spray Sheets
| checkpoint | Chip Application
1df9dc25-75e6-5613-a2a7-48f3418a9d88 | note | Test Required - Chip type, Chip Application
356b3d1e-4975-54f1-8eed-b5712dbf5285 | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
f06aa4c7-c436-5c2c-a066-624048b90b91 | note | Task Assigned To - Site Foreman
5003c798-298e-5539-97f0-b0e850c71e30 | note | Measuring Devices or Method - Visual
5923bc20-70d6-5372-aeb6-5a03cc85c53e | note | Criteria - Trucks loaded with correct chip.
ce974590-6d4a-5bc6-aa0c-3ced9b8dd640 | note | ○ Chip clean. (G4/6 Racked example)
7a4bf8fc-0cd8-5e42-9ca6-6b35f3993693 | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
52de6216-cc84-59ca-b738-8d62fd01b1bc | note | ○ G6 application = Enough to just fill the voids around the G4.
7344bc79-e1b7-5c6e-a72a-e920f86dc204 | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
593cbbac-829b-5356-9cf9-8e607bfb8ef7 | note | Test Required - Visual
1ab853bf-acf7-51ae-af51-ef61e0a489f2 | note | Task Timing / Minimum Task Frequency - At completion of rolling
922363ca-6595-56f5-b03d-80d493364e9b | note | Task Assigned To - Site Foreman
8e7c05ba-8767-5f6d-9ccc-935ae6ffd30f | note | Measuring Devices or Method - Visual
2ed203e4-75d2-5598-ae78-103cce1cb439 | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
19635c5e-4bec-50e2-b600-1578ea03dba3 | note | QA Form - 'QA Measurement Sheet
| checkpoint | Site Measure
09fd2aeb-b1a2-5a9d-a13e-0117a3b61f3e | note | Test Required - Record final site measure
2ddcab13-cbfe-5bb3-bee5-b0965a161e45 | note | Task Timing / Minimum Task Frequency - Completion of works
f345c4e1-8b18-575f-8add-3083f8921a0d | note | Task Assigned To - Site Foreman
1d1b797c-0d94-5d75-9f85-09a8603c10f3 | note | Measuring Devices or Method - Measuring Wheel or Tape
a009fe3b-18b0-5d9f-a76c-87254ae92f2c | note | Criteria - Sketch and record seal area and QA detail
c78b3a92-f166-5776-a12e-edb4365e5b76 | note | QA Form - QA Measurement Sheet
| checkpoint | Post Seal Care
7c59cf82-c427-5376-9b2f-a8e5e0deffb8 | note | Test Required - Visual inspection
0634009b-283c-5ac8-8f1d-37bc0d9ea2d8 | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
c733ede8-e930-52d8-898e-22855779b1e1 | note | Task Assigned To - Site Foreman
2dde7978-ae49-55c1-8107-c6d8b4b97a02 | note | Measuring Devices or Method - Visual
ef8ab778-a954-5d26-8d71-68aae3c37ecc | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
f4d5bd94-2aaf-53a5-a751-b6008980e4ad | note | QA Form - Daily Diary
| section | Chip Removal, Pavement Marking, Traffic Services
| checkpoint | Removal of excess chip
1fcf4fb8-9360-5755-a0b9-d04d338c2af5 | note | Test Required - Visual Inspection
8bb92c22-31af-5d4d-abc9-7c9fd153c12f | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
484dd708-cee1-5d48-a366-12f3aa47cd74 | note | Task Assigned To - Project Engineers/Site Foreman
a0f69bc6-aa7e-5aff-8cfd-e91abd6f3389 | note | Measuring Devices or Method - Visual
226280d7-0bda-563b-af95-daf1e0e8be83 | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
08da7270-287b-5742-942b-2f95f07f3a29 | note | QA Form - Daily Diary
| checkpoint | Pavement Marking
8d95e559-f323-57cb-bdda-fac204878608 | note | Test Required - Visual Inspection
d00a3088-80e4-564e-a674-c408e8ac7aa8 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
f8f9f20c-6909-5a22-95a9-5e1d1208d396 | note | Task Assigned To - Project Engineers/Site Foreman
8bc79abf-cf78-5f6e-a0a1-5768dfb507f5 | note | Measuring Devices or Method - Visual
67dc97da-84b1-5ef2-9b8e-9da717911419 | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
56003cce-5966-5dda-aff5-e7c173ad72cd | note | QA Form - Daily Diary
| checkpoint | Removal of TTM
2296148e-864c-58ee-8c5e-ed0af3fe2595 | note | Test Required - Visual Inspection
a23c0043-c28f-59c0-994f-c46b419aa57f | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
ae9fcdc8-ec7c-53b7-8760-a02a3e8d0b4d | note | Task Assigned To - Project Engineers/Site Foreman
8bfe5d89-bc95-5c27-b25b-5904cb726d99 | note | Measuring Devices or Method - Visual
f0b38261-f912-5223-8288-49054065ce46 | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
2fa112bd-e9b1-52be-9dbd-e6cdfa05a7e1 | note | QA Form - Daily Diary
| checkpoint | Traffic Services
55fc42b2-585f-50ae-9a59-cee05f7e8b4b | note | Test Required - Visual Inspection
7256f138-bbcb-5f0e-933d-9c552738a577 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
eee0b414-8897-5293-bfdd-f44fa5a40c2c | note | Task Assigned To - Project Engineers/Site Foreman
76f07081-288c-5211-a9c3-0657593f7862 | note | Measuring Devices or Method - Visual
02930075-490d-57ee-9b36-b8f759f3ea5d | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
199f7453-0671-5d5e-9cb8-2260e6143427 | note | QA Form - Daily Diary
| checklist | 8. HB AWPT ITP - Clarkesons Hill A |  | 8. HB AWPT ITP - Clarkesons Hill A | 10b56f46-5432-4199-a4c7-2f4d29bc53ad
| section | Preliminary / Establishment
| checkpoint | Establish TTM
9f9615f6-5fe9-54f1-832c-805bf92b797a | note | Test Required - Visual Inspection
c099eb00-f713-5f18-9774-88b6e6a2f409 | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
35c3b9fe-2ba0-5e60-80f3-841815d4f156 | note | Task Assigned To - STMS/Site Foreman
a8a5d54e-81c5-5328-b4cc-c313ba02074e | note | Measuring Devices or Method - Visual
32b51d6f-802e-5d7d-8bdc-1d7c18b89dbc | note | Criteria - As per TMP and ensure TMC advised in advance of works.
d48832c8-b3bf-587c-bb92-94a0617ae2ef | note | QA Form - Daily Diary
| checkpoint | Permits
789ad237-ac22-5605-b570-377ff7504ff2 | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
f0f47384-7a04-5666-ae21-076ed746cf0b | note | Test Required - Document Review
3f122113-17d7-5ead-a736-cbaf94748893 | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
a7cacdff-c3e8-5d76-9b11-3d02efcf7718 | note | Task Assigned To - Site Foreman
7363c45f-f74c-5790-b494-8262eef0082f | note | Measuring Devices or Method - Visual
b6825292-bc87-55d7-8c75-efcba5a4baa2 | note | Criteria - Obtain permits and mark outs prior to construction
518eda35-edff-509f-8fdc-3626d35a13ed | note | QA Form - Copy of Permit on site
| checkpoint | Clear-Shoulder and Side drain
6b9a14bd-385c-5e95-9a66-8c8cd04792bf | note | Test Required - Visual Inspection
1e3fb442-4458-52e6-8f00-80e5b0aaab8b | note | Task Assigned To - Project Engineers/Site Foreman
878a5f2a-afa3-57c2-83eb-2123a6adc15c | note | Measuring Devices or Method - Visual
b86fd4dc-922a-5697-880d-d8d1d39d7bb1 | note | QA Form - Daily Diary
| checkpoint | Digout Failed Areas
9e8c04da-9938-5fa5-b0b7-3a666691ee38 | note | Test Required - Visual Inspection
73f31b00-f7f5-5fcf-b6c4-bd28fd6ff6e5 | note | Task Timing / Minimum Task Frequency - As Requested
93203692-c8b1-554a-9637-753a9536ebcd | note | Task Assigned To - Project Engineers/Site Foreman
9937a9c9-4c25-559b-bb1e-5dc83f0ac081 | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
4adc9165-71cd-5667-8a1e-c478b6d349d5 | note | Criteria - Backfill with Basecourse
227e378c-21b3-5f0a-957d-974d440ba9b5 | note | QA Form - Daily Diary
| section | Kerb Construction
| checkpoint | Basecourse layer construction (1)
89f89651-c326-5a0f-ab9f-dbe74d748d63 | note | Specification Reference - TNZ B/2
4f11a46a-72e1-5beb-9395-6fcacd2e6ed4 | note | Test Required - Level and alignment
ad070208-ff9e-58c9-8083-614d9c749411 | note | Task Timing / Minimum Task Frequency - Every 20m
3aecab4b-5be2-5e27-b532-b10ec6382b53 | note | Task Assigned To - Project Engineer
| checkpoint | Basecourse layer construction (2)
078c50cf-38c8-5edb-898e-cf4963f0a68c | note | Specification Reference - TNZ B/2
a41bb285-b126-5630-9c0a-f8691894949f | note | Test Required - Compaction
e34aff7b-bda8-55b1-b04f-68675e87a419 | note | Task Timing / Minimum Task Frequency - Every 20m
71152df4-484b-5b77-9c83-fd94e40c5bbb | note | Task Assigned To - Project Engineer
8669bef6-e636-521f-8059-fb962cec9572 | note | Criteria - 25min on the 4th drop
47b85271-43d9-53a5-aa38-4e2822e0c7d7 | note | QA Form - QA Measurement Sheet
| checkpoint | Kerbing
04c1a518-b17f-5b7d-a983-a2b4f65d53b3 | note | Test Required - Set-out level and alignment
c78906b0-a00c-5225-b2d5-c858bf1c6b57 | note | Task Timing / Minimum Task Frequency - after base construction and prior to placement of concrete
cea67277-a8a5-5ac8-86da-f572e6b882e1 | note | Measuring Devices or Method - survey check
b16914ca-5ad7-5e37-bdfc-f277b5373ce0 | note | Criteria - Horizontal: ± 20mm, Vertical: ± 5mm
| checkpoint | Concrete Works
ab256e45-a3b7-5629-b212-5e98397c10a4 | note | Test Required - 20MPa
05d2cfe2-a940-5979-8d0e-849bdc903487 | note | Measuring Devices or Method - Copy of delivery docket
f08b2a70-f25f-59a4-a8f8-c93053c41139 | note | Criteria - 20MPa, 28days
| section | Inspection Test Plan - In Situ Cement Stabilisation
| checkpoint | Cement for stabilisation
52789124-7328-5295-a5fc-307a286ca159 | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
4cc99be6-7498-5d1c-9ac0-a3bab12e2a0a | note | Test Required - Certified in accordance with NZS 3122
0ec41559-40b3-53fe-ac8f-27a8fc4a4b0a | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
| checkpoint | Production plan
e14f0f17-155f-5227-8957-d8d65fc9d62d | note | Specification Reference - NZTA B/5:2008, 7.2.2
59fa78cf-ec86-5ded-bcf0-c76e58af88b0 | note | Task Timing / Minimum Task Frequency - 1 per site
| checkpoint | Stabilisation mix properties (including cement):
6fedc27a-bbd6-59d3-af12-8024e5029fd2 | note | – Maximum dry density (MDD)
c6d41be6-6f37-5543-aec6-ab5e2e80a80a | note | – Optimum water conent (OWC)
b4561958-d7c3-593a-9133-0a04fe104f43 | note | – Solid density (SD)
c0f8f601-4167-5916-9c99-a426c2157036 | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
ff17db8f-4305-558b-9ce9-6b15095e2277 | note | Test Required - Material properties for compaction verification
271a6cea-7681-5f52-a316-46b853a951ed | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
243b771f-1c2f-52ef-8ccf-f983a9902962 | note | Task Assigned To - Hold Point - Approval required by site engineer
6d435f75-8dbb-59e2-9697-29dc35ea68de | note | QA Form - QA Measurement Sheet
| signoff | HOLD POINT
| checkpoint | In-situ moisture content of existing pavement aggregate
09f89974-2cc3-529f-abe8-cb424696d370 | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
ca5a4331-0b26-5d6f-bffb-cbb2f45d2f7a | note | Test Required - In-situ moisture content, Between 90% to 100% of OWC
f4e2edc8-2ca7-55ea-92f4-315faf0f7ea1 | note | Task Timing / Minimum Task Frequency - As required
c8ea393b-4762-5ec2-a9d1-67e3f32095a8 | note | Task Assigned To - Inspection - Lab
a0dbd5f8-e8de-50c7-a74e-5344e4468b45 | note | QA Form - QA Measurement Sheet
| checkpoint | Top-up metal
542b2963-e6fb-5c02-b826-0b73fcd216de | note | Specification Reference - TNZ M/4 Table 4
01b465f4-92c1-5856-a605-1ca14b625daa | note | Test Required - Placed to required depth and design levels
8ec48b85-6482-5b41-ab90-05eecc099248 | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
af45abe8-b734-5f5d-a9db-beffe40aae66 | note | Task Assigned To - Site Foreman
f77051d2-1838-58c8-b6e2-14f5c234a97b | note | QA Form - QA Measurement Sheet
| checkpoint | Cement spreading
d580969a-c604-51de-a639-dc4f7c5ed289 | note | Specification Reference - NZTA B/5:2008, 7.3
2d56eeb4-1084-5acf-bf21-66d7b99fd593 | note | – Mat test (1m2 canvas mat)
00c1f01c-0f8b-5c53-a4ec-ff4a8a23dde9 | note | – Average usage test
40077438-b495-5034-b9f8-b1cced70a464 | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
9ce535a9-1801-5a24-b243-b7fdead3142b | note | Task Timing / Minimum Task Frequency - Every 400 m2, Upon emptying spreader and bulk tanker
3b7af9da-3869-50ff-a966-84adc3627d90 | note | Task Assigned To - Inspection & sign off by Site Supervisor
2a1b5e72-3635-5775-83d2-97729833bd4d | note | QA Form - QA Measurement Sheet
| checkpoint | In-situ mixing - Cut depth
87f7b815-2ee5-56ef-8d89-2ab140f4ccf2 | note | Specification Reference - NZTA B/5:2008, 7.6.1
a0f1c177-8a83-5b80-8bb2-1f6c4f6b522c | note | Test Required - Maximum variation -5mm and +15mm
98341e5e-0340-565b-aa7f-027deb2a1b0a | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
8f46e5e4-f69e-5a9e-a31b-e990cd4ce356 | note | Task Assigned To - Inspection & sign off by Site Supervisor
a8f76f1b-f83d-50cd-9bd4-5b5cf5d76cfd | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
67fdb6ed-02a8-56c1-92e6-39af7880fe78 | note | Specification Reference - NZTA B/5:2008, 7.7.1, NZS 4402 Test 41.3
3bd7be8d-2688-562f-b2dd-48b06d31b0ec | note | Test Required - Plateau testing
579abd4d-4a09-52df-937e-20c1c49452ca | note | ○ Mean value ≥ 98% of MDD
c7ed232b-8b45-538b-ad38-6f816e0174ff | note | ○ Minimum value ≥ 95% of MDD
cf0e48aa-e193-58a8-a0ca-493aa285b5fb | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
d3747ac7-31f0-593b-89cb-603ff001403a | note | Task Assigned To - Hold Point - Approval required by site engineer
d6c45cc7-197a-509e-86be-f44b4158d877 | note | Measuring Devices or Method - Nuclear Densometer
b9b84758-a8ad-5876-82c6-79a7cbd16551 | note | Criteria - Minimum value 95% of MDD
0c15783b-ea85-5e69-9d62-cb58435b120f | note | QA Form - Test Reports
| signoff | HOLD POINT
| checkpoint | Surface shape
5726e7b0-790a-5b70-8b2a-b3025e55e643 | note | Specification Reference - NZTA B/5:2008, 7.8
5588a1d8-6076-59de-9728-3ee3a6202f34 | note | Test Required - ≤10mm from 3-metre straight edge, No depression, Vertical variations -5 + 15mm
67157436-ba52-50c7-8bec-9f2873fe516d | note | Task Timing / Minimum Task Frequency - 20m intervals
c50c2623-ef09-5200-a01d-2b7426cbd35a | note | Task Assigned To - Inspection & sign off by Site Supervisor
33a2e2f9-2881-529c-b45c-24d3a9b967f1 | note | Measuring Devices or Method - Stringing, Tape measure
ed84ffe1-7548-5a95-a1a8-6586955620aa | note | QA Form - QA Measurement Sheet
| checkpoint | Crossfall
51a6fcf1-4a87-5f2e-8a56-b3876265ac79 | note | Specification Reference - NZTA B/5:2008, 7.9
80556c65-371e-5520-bff8-1b7a3713aaa1 | note | Test Required - Not less than exisitng crossfall at the start of construction
1ab420ef-a48f-56b9-81f1-299e322a372a | note | Task Timing / Minimum Task Frequency - 20m intervals
dc906c92-03d8-59a1-b59e-931d35ff99e5 | note | Task Assigned To - Inspection & sign off by Site Supervisor
87495094-110d-5458-9862-8593fd9fa3bb | note | Measuring Devices or Method - Stringing, Tape measure
b2c23006-f25c-5505-8b1e-965b6e9b2bf7 | note | QA Form - QA Measurement Sheet
| checkpoint | Surface finish
de6165fb-4ab2-5c4a-b251-47e8ddc45abf | note | Specification Reference - NZTA B/5:2008, 7.10
d26739eb-e00b-5cb9-a602-4f3f42852e52 | note | Test Required - See clause
ad6879ce-f1a7-5fb4-ab86-88e34ad0712a | note | Task Timing / Minimum Task Frequency - 20m intervals
83b781ba-951c-510c-ae61-3e256041a63c | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
a2b01da0-3af3-5e2c-8f1b-469be3add62e | note | Measuring Devices or Method - Visual
| signoff | HOLD POINT
| checkpoint-no-value | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
| checkpoint-no-value | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
| section | Chipseal Construction (NZTA P29)
| checkpoint | Ensure appropriate TMP used
2146abda-5e3e-5833-8dc0-a60dde1cee00 | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
| checkpoint | Seal design
de864163-0592-595c-9ba1-42e07fc0eb18 | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
dfd1a5a4-c782-5bcf-8a9f-a6ef5256c167 | note | Task Assigned To - Project Engineer
c8cb05dc-fd9f-5eb8-a735-2c09867cc3ca | note | Criteria - Seal design to be reviewed prior to surfacing
81ed2747-6e19-52d8-b34f-209f76934b4d | note | QA Form - Seal design template
| signoff | HOLD POINT
| checkpoint | Location/Size Confirmation
c27aa341-412d-5116-b57d-32ba6be352bf | note | Specification Reference - Mark up extent of chipseal
fdd52201-3dd9-580e-8f1f-964d33f497b7 | note | Test Required - Prior to surfacing
b3451788-d922-587b-8fc0-a409d5dba38a | note | Task Timing / Minimum Task Frequency - Project Engineer
a78d289b-e18a-5417-bef8-18e9d4a34da7 | note | QA Form - Daily Diary
| checkpoint | Surface Cleanliness
1d9d21d3-54ce-5efe-92c0-efd96471f1f1 | note | Test Required - Visual Inspection
e9518a19-e67c-5dd3-9181-4486a869eb79 | note | Task Timing / Minimum Task Frequency - Prior to application of binder
2d03562c-3681-5a7d-9c90-f16e09c4541a | note | Task Assigned To - Site Foreman
ad746014-fdee-5539-81fd-ecac4d4f9631 | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
0ca43e9f-ea99-5639-80bc-9a19c221b560 | note | QA Form - QA Measurement Sheet
| checkpoint | Plant Resource
93a16345-13c0-5a3d-af25-38bba297a2e6 | note | Test Required - Visual Inspection
da556196-4f6e-5943-a9cd-9e539389036b | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
eeb77bc2-d784-5a97-9017-8f6f2e74c128 | note | Task Assigned To - Site Foreman
dd277c7e-7042-513f-a94f-b8b5c23b2694 | note | Measuring Devices or Method - Visual
3e2938e1-216b-5f86-8e8c-46640ed269cb | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
3fd31a18-d5ce-54a7-9c8f-05b76146499f | note | QA Form - Daily Diary
| checkpoint | Binder Application
e003997c-edb4-5353-9c24-6b241d08093f | note | Test Required - Binder type, Cutback, Temp, Application rates
9b5bfa33-37d3-549c-bbad-3b89b39505aa | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
77a431cb-0edd-5af2-9d37-3e22e55a8b37 | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
ae9fa691-1fc1-589b-9bfb-d83a6311d934 | note | Measuring Devices or Method - Visual
34128450-3c8d-51a2-a115-e5db8c72d0be | note | Criteria - Binder Type = 180/200.
5edb08d7-5a38-5e03-96f5-d35aee2cadf2 | note | ○ Cutback to suit 1st coat seal 4pph kero max.
8c67bcbb-1a90-5e68-8995-900e15873f15 | note | ○ Temp = 150deg celcius min
572bbeeb-ca3e-5391-bdf2-4e1a6509d7cb | note | ○ Application = Design l/m2, +/- 0.1 l/m2.
cc6a0100-9e76-506a-bb27-c6d4e6063be5 | note | QA Form - Bitumen Spray Sheets
| checkpoint | Chip Application
36f3c615-452e-5cce-81a1-49cdbf6b516b | note | Test Required - Chip type, Chip Application
3a4f2716-0452-5ce8-aa81-fbe32293aa6e | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
1fe48731-3d48-5b73-bab6-54342dbaea4b | note | Task Assigned To - Site Foreman
324e4d1b-f478-518e-92a7-4fc52bc31711 | note | Measuring Devices or Method - Visual
50490e24-906a-5bcf-bab6-2fcf92ee1e6b | note | Criteria - Trucks loaded with correct chip.
09da1baa-36b0-597c-b822-3960dd28f5b5 | note | ○ Chip clean. (G4/6 Racked example)
ca001fd1-a151-5146-bc34-e6c2b530b3f9 | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
f45225cf-5cd0-502c-a1dd-f40498abbfea | note | ○ G6 application = Enough to just fill the voids around the G4.
ed9ae10e-be48-5cbf-8dc2-f545d1382e66 | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
7ae03ee1-4d24-5d45-add7-d1b17155c513 | note | Test Required - Visual
9f3e2039-717b-5df1-a462-aebc22bbfef3 | note | Task Timing / Minimum Task Frequency - At completion of rolling
f98b3b2d-1af0-52c2-b7ac-3a22461c4a6c | note | Task Assigned To - Site Foreman
2e3ccb98-e74a-55af-ba31-d31b7a1341ba | note | Measuring Devices or Method - Visual
860a0677-66f0-5e99-b92b-38e38fb3803f | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
23b2c3b2-62dc-5f63-9eb7-1068abafb490 | note | QA Form - 'QA Measurement Sheet
| checkpoint | Site Measure
ff7b7667-b59f-5cef-88c3-5fa05bbb9414 | note | Test Required - Record final site measure
ec08eb82-baeb-54c2-9302-2bebabb34918 | note | Task Timing / Minimum Task Frequency - Completion of works
ce21673d-83de-52a7-b467-64a6990b65b5 | note | Task Assigned To - Site Foreman
30cfd6da-961c-563b-b8be-3367177ee57f | note | Measuring Devices or Method - Measuring Wheel or Tape
b53a3264-a650-564c-95bd-aaed90039460 | note | Criteria - Sketch and record seal area and QA detail
f0de65c0-c15f-5b34-b31c-40107aacb82a | note | QA Form - QA Measurement Sheet
| checkpoint | Post Seal Care
77f6d138-a5ce-54e9-8c41-787916c56f1d | note | Test Required - Visual inspection
1c370494-fadc-5c61-8e93-69913acf8e1e | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
3bd7336b-3e26-5ca9-877f-41b532c0ff72 | note | Task Assigned To - Site Foreman
8a937b3d-0b92-51ed-b566-d93f39e10dd1 | note | Measuring Devices or Method - Visual
523e9f5d-ce3f-56a9-9dd6-96941a7cc0ce | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
87e3f05b-2bbb-5532-acf3-2bd74711117f | note | QA Form - Daily Diary
| section | Chip Removal, Pavement Marking, Traffic Services
| checkpoint | Removal of excess chip
6a2c5d23-b527-5474-8591-bbff12384482 | note | Test Required - Visual Inspection
eb889dfd-92d9-5568-bc2c-2267ae032ae5 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
2b0d87a0-5d50-5de1-babe-315d332cb16d | note | Task Assigned To - Project Engineers/Site Foreman
1bc321ad-a13e-5f24-826b-2ea0e648ec8d | note | Measuring Devices or Method - Visual
38aa8270-3fcc-5a2d-9eb2-d8c53ce4c337 | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
486e487b-46b5-5824-88fb-85b764abef23 | note | QA Form - Daily Diary
| checkpoint | Pavement Marking
f35e2458-3c43-512e-97ab-8cd96fd64eac | note | Test Required - Visual Inspection
60e036a4-b110-5eb7-aaa6-5ea06cf3906f | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
b98114fd-0b99-5301-8065-faa092b1e81f | note | Task Assigned To - Project Engineers/Site Foreman
447ef6ce-e718-52a7-8e3e-ea5eaaca830e | note | Measuring Devices or Method - Visual
afe0daaf-597a-555c-9312-11292b6d326b | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
4844ad4b-5549-5e4c-8e49-e4c52b96bdc2 | note | QA Form - Daily Diary
| checkpoint | Removal of TTM
024ed583-2ed8-5ea3-9396-c5d1105c4a78 | note | Test Required - Visual Inspection
eecca2e9-b120-57e8-a9f6-bab96c4eaba8 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
83fb1299-c7b5-5029-90d3-a8938327472a | note | Task Assigned To - Project Engineers/Site Foreman
7ea5adc0-f6c1-5efe-aa58-61be1b487f9f | note | Measuring Devices or Method - Visual
f5f31f81-2176-5d74-9c8f-1b5ce057df12 | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
e11ce5e1-8ae4-571d-852a-18c527317426 | note | QA Form - Daily Diary
| checkpoint | Traffic Services
c6912911-6e0c-5814-b02a-95f4da573499 | note | Test Required - Visual Inspection
72df5ee2-b260-52ca-bcd9-d4f65effdb4a | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
cbd67f70-9bcd-56fb-942e-e4047fbf94e8 | note | Task Assigned To - Project Engineers/Site Foreman
c959752f-d752-5b9d-a683-97ae93dd94c2 | note | Measuring Devices or Method - Visual
2c236bd7-df83-5e19-8b5f-354524cadd9e | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
34fdcc20-6fc6-5ae2-b218-54bd8a50de70 | note | QA Form - Daily Diary
| checklist | 9. HB AWPT ITP - Clarkesons Hill B |  | 9. HB AWPT ITP - Clarkesons Hill B | 1befbfab-ae0f-4f03-97c8-c117516162f3
| section | Preliminary / Establishment
| checkpoint | Establish TTM
b1ee275f-d68c-5a15-8b4f-9eb843baaa97 | note | Test Required - Visual Inspection
cc45ea55-b359-50a5-b25f-c6e3cda87c5c | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
c9b857aa-78c7-5057-9da9-0a30104a1e01 | note | Task Assigned To - STMS/Site Foreman
a19d51b3-7f5d-56e1-b416-7dfe7a04daa0 | note | Measuring Devices or Method - Visual
26c4e8ff-3660-5076-89c6-ffd587d46736 | note | Criteria - As per TMP and ensure TMC advised in advance of works.
a73d15a9-718c-550f-ad1d-90b4fb2774f7 | note | QA Form - Daily Diary
| checkpoint | Permits
797d8d37-ae6a-5d48-a890-d62a4ec628e4 | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
34b45fc5-4a92-589d-a0b2-a92c3f7bc28e | note | Test Required - Document Review
ce9a748b-69d3-5b72-a8b3-e5fa33b0f2e3 | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
06001c79-ad87-5b6f-a0f3-c8c79987924e | note | Task Assigned To - Site Foreman
779601ea-8775-5dd3-a6e6-6d033ec28906 | note | Measuring Devices or Method - Visual
e4fd2055-ba90-5a23-9ae2-fbf19b6ff110 | note | Criteria - Obtain permits and mark outs prior to construction
5615b212-298c-5436-a622-32b2bdf00307 | note | QA Form - Copy of Permit on site
| checkpoint | Clear-Shoulder and Side drain
31f0ba43-8185-5365-8fa5-8c7d6742b90d | note | Test Required - Visual Inspection
1f6baeca-1b21-5dd3-8a69-dc440c92b783 | note | Task Assigned To - Project Engineers/Site Foreman
c3d039a8-6ac7-5a11-9feb-eeea2b4f1bf3 | note | Measuring Devices or Method - Visual
3833a2ae-0b20-573f-979a-9ca4fe23615a | note | QA Form - Daily Diary
| checkpoint | Digout Failed Areas
330b1799-cf26-57c1-89b5-7e5588d21faf | note | Test Required - Visual Inspection
7140b887-51b9-523a-8bfb-0e26b7ae631c | note | Task Timing / Minimum Task Frequency - As Requested
2e36ec08-03f4-5f59-842f-1659c10179a2 | note | Task Assigned To - Project Engineers/Site Foreman
ccca1dcf-5684-5cf8-8d54-831bbbf9b404 | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
fd0e0abb-74b4-514f-ab73-d6eaaf1efe6d | note | Criteria - Backfill with Basecourse
86817d81-4732-58b5-a492-14166a58c6c1 | note | QA Form - Daily Diary
| section | Kerb Construction
| checkpoint | Basecourse layer construction (1)
51786667-4add-5489-a0f9-2b329bada835 | note | Specification Reference - TNZ B/2
bef97d1d-5047-58f0-a827-8ae0d82cece8 | note | Test Required - Level and alignment
0a83f13f-25e7-5e01-bd23-e7041e0a7f9e | note | Task Timing / Minimum Task Frequency - Every 20m
41dbf942-adfb-55ce-8ebc-c9a6eb7fa172 | note | Task Assigned To - Project Engineer
| checkpoint | Basecourse layer construction (2)
730f58fa-c9ef-5520-bc30-8f282dc6ec6b | note | Specification Reference - TNZ B/2
afa09493-08c2-5b12-b9c6-7bb93f387912 | note | Test Required - Compaction
06005127-32af-51d2-b286-bdb402f20e7a | note | Task Timing / Minimum Task Frequency - Every 20m
17596aed-cc4f-5473-ab86-a6c47a0ae320 | note | Task Assigned To - Project Engineer
5a86da7b-0c3c-58df-b021-631b5028e1bc | note | Criteria - 25min on the 4th drop
d1db1b61-eed6-5170-81e6-6122ff0c805c | note | QA Form - QA Measurement Sheet
| checkpoint | Kerbing
54ebaeff-9c0b-57c9-8ee9-c6cd56a1524e | note | Test Required - Set-out level and alignment
2211e0dc-9454-5d86-808f-da74fbe877a9 | note | Task Timing / Minimum Task Frequency - after base construction and prior to placement of concrete
a08633de-a222-5ace-ac0f-dfb516deac6f | note | Measuring Devices or Method - survey check
a614b784-39a2-58f6-9641-3fcdce81faf3 | note | Criteria - Horizontal: ± 20mm, Vertical: ± 5mm
| checkpoint | Concrete Works
433d5c21-7396-58eb-8f80-d491a344a8ea | note | Test Required - 20MPa
e0197a9e-23d2-52f4-8af5-b21bf1fbcce4 | note | Measuring Devices or Method - Copy of delivery docket
fc9bf63a-258c-5ee4-9db7-1d9bb5116e7d | note | Criteria - 20MPa, 28days
| section | Inspection Test Plan - In Situ Cement Stabilisation
| checkpoint | Cement for stabilisation
2ad08ba9-b80b-5024-b7da-fa5ed7aa758b | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
0fd58c7a-9f02-526e-b431-a00cb6dc672c | note | Test Required - Certified in accordance with NZS 3122
15b8e0d8-cddb-592d-8ca0-31a40277bc1c | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
| checkpoint | Production plan
679f0f4a-4f4d-5a03-80b1-c0531698b56c | note | Specification Reference - NZTA B/5:2008, 7.2.2
1d89444e-5f42-502f-9296-417724bcee7a | note | Task Timing / Minimum Task Frequency - 1 per site
| checkpoint | Stabilisation mix properties (including cement):
a3b9bdc9-373f-586c-a3e6-31f3feb547ab | note | – Maximum dry density (MDD)
ee2936d2-ace9-51da-b537-1985402c1c20 | note | – Optimum water conent (OWC)
a3ac339f-c315-50bf-9cc0-2a79d1312fc1 | note | – Solid density (SD)
0f7fe82e-04f0-58b7-bde9-6e39f35ee745 | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
d202e947-3c80-536d-9633-c65dcbb7d0a3 | note | Test Required - Material properties for compaction verification
20c1ab2a-0aef-56af-8565-08598239b9c8 | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
9015b414-c465-5876-9d3b-ff0c21c7f6a0 | note | Task Assigned To - Hold Point - Approval required by site engineer
9b20592f-af19-5b3e-b430-a919f4572f22 | note | QA Form - QA Measurement Sheet
| signoff | HOLD POINT
| checkpoint | In-situ moisture content of existing pavement aggregate
3cf8e55f-7dc0-545e-b358-bbc10ef44b71 | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
e0f27768-9cbc-5304-9154-9902d012742a | note | Test Required - In-situ moisture content, Between 90% to 100% of OWC
8e4e9390-dbe3-5293-856a-4c71f8673a17 | note | Task Timing / Minimum Task Frequency - As required
eaedc41a-8a78-5c73-8880-02c8db7d5579 | note | Task Assigned To - Inspection - Lab
17643378-7b0f-5ce2-a7f0-fc0c2ce2e113 | note | QA Form - QA Measurement Sheet
| checkpoint | Top-up metal
10d31154-a15e-5527-b033-74fbf70df0af | note | Specification Reference - TNZ M/4 Table 4
a117fd17-8687-5f8d-8b82-ec4d5c46f3f9 | note | Test Required - Placed to required depth and design levels
34b0c081-33a5-55cc-a2fc-9365b64202f5 | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
e023d2bd-71b1-51a9-b715-1bdc8f10c3f8 | note | Task Assigned To - Site Foreman
58e0fa60-f098-5741-b034-a50aafd8a62e | note | QA Form - QA Measurement Sheet
| checkpoint | Cement spreading
a82b0bd0-3c92-5351-b7b5-33a3fb0026b0 | note | Specification Reference - NZTA B/5:2008, 7.3
8b6eab63-8584-5676-86a1-6eb8d9721a7b | note | – Mat test (1m2 canvas mat)
4f3516a9-e9c1-50be-bafc-82d4610453ff | note | – Average usage test
20a1cf54-1782-593e-a685-fa5145bc653d | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
a95af12b-2c3e-5df5-b815-81c7ae745bc7 | note | Task Timing / Minimum Task Frequency - Every 400 m2, Upon emptying spreader and bulk tanker
51469bc9-5f52-5948-9597-d4a07ed7b36c | note | Task Assigned To - Inspection & sign off by Site Supervisor
588b3de1-e86a-5e72-8dda-eedf907cf6d7 | note | QA Form - QA Measurement Sheet
| checkpoint | In-situ mixing - Cut depth
ebfbd6f4-0fc8-548f-ab12-4dd6a654e730 | note | Specification Reference - NZTA B/5:2008, 7.6.1
8d6a15d4-aef7-5501-9a77-d0379392f281 | note | Test Required - Maximum variation -5mm and +15mm
47a513d4-05ce-5219-89da-74c7692a5e1d | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
493aef0c-1731-5bda-a079-d760057587d9 | note | Task Assigned To - Inspection & sign off by Site Supervisor
3755a873-ff39-5727-8b30-0693eea84db2 | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
2098663b-00c0-563d-846c-b7857cb11793 | note | Specification Reference - NZTA B/5:2008, 7.7.1, NZS 4402 Test 41.3
e76824cc-334b-51e8-b70a-70001cf6536e | note | Test Required - Plateau testing
21a097fc-5d9f-5a90-a7c7-dcbe80d1fca3 | note | ○ Mean value ≥ 98% of MDD
e222b39c-4cbf-5c79-bbed-d24cd99242a7 | note | ○ Minimum value ≥ 95% of MDD
2eea8749-be22-5bad-b19c-5d761c5b2a6f | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
06e9407c-5a15-56db-a0e0-0d89a28621fd | note | Task Assigned To - Hold Point - Approval required by site engineer
7ec2146e-5b79-5598-bfc9-d78e4d6fecb8 | note | Measuring Devices or Method - Nuclear Densometer
0e6ae2a8-425c-562d-bc7c-735745441370 | note | Criteria - Minimum value 95% of MDD
f61d0771-f266-5b82-b8a7-ebe0b850035b | note | QA Form - Test Reports
| signoff | HOLD POINT
| checkpoint | Surface shape
f0544342-d1ff-58df-b842-0a77bd3d88ef | note | Specification Reference - NZTA B/5:2008, 7.8
92f9b985-2423-5356-bfd6-1ec23b8dc1ab | note | Test Required - ≤10mm from 3-metre straight edge, No depression, Vertical variations -5 + 15mm
49dfa3d5-123e-5d7f-baab-c75c89079c40 | note | Task Timing / Minimum Task Frequency - 20m intervals
48f292f2-f89b-53e0-b3fa-196faa13cd95 | note | Task Assigned To - Inspection & sign off by Site Supervisor
9733c92b-8e73-5a18-8693-3842f2135243 | note | Measuring Devices or Method - Stringing, Tape measure
90581362-fd2f-5e4f-a3ae-c2fb919e7b8c | note | QA Form - QA Measurement Sheet
| checkpoint | Crossfall
f2736107-f4be-58d4-9eba-5bc77fdcf12a | note | Specification Reference - NZTA B/5:2008, 7.9
e60bb7ce-b31b-5190-a7e8-6446b453ba17 | note | Test Required - Not less than exisitng crossfall at the start of construction
2cf47544-4a0b-53fc-ba28-67a76f0c48b3 | note | Task Timing / Minimum Task Frequency - 20m intervals
fdbc0f02-d785-5a6d-9476-a76a79dc256f | note | Task Assigned To - Inspection & sign off by Site Supervisor
1229e09f-c197-52f3-8e4b-725315bfc538 | note | Measuring Devices or Method - Stringing, Tape measure
58376b49-4a1f-5dcb-a190-14db3fef263d | note | QA Form - QA Measurement Sheet
| checkpoint | Surface finish
fba67fa2-7f68-5a74-9846-142d37bacf40 | note | Specification Reference - NZTA B/5:2008, 7.10
d2fc8324-4850-530e-9053-2c87f0eea876 | note | Test Required - See clause
3578229c-1b1e-528a-bc52-422eb824eb7b | note | Task Timing / Minimum Task Frequency - 20m intervals
60c62e4c-b913-52d0-86ae-71f36c896613 | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
fe13580b-e6cb-5e21-ab43-b62f2312327f | note | Measuring Devices or Method - Visual
| signoff | HOLD POINT
| checkpoint-no-value | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
| checkpoint-no-value | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
| section | Chipseal Construction (NZTA P29)
| checkpoint | Ensure appropriate TMP used
fe34aa32-7fe0-5c3f-9bab-814b73aacb22 | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
| checkpoint | Seal design
dc4d656f-0d64-539d-bd53-856923aae1ef | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
8b7917e3-9bdd-59f5-a345-c8a0b2ead699 | note | Task Assigned To - Project Engineer
05d80574-2915-538b-a05b-eb543df0e497 | note | Criteria - Seal design to be reviewed prior to surfacing
adcce0a0-bb40-5a5b-8502-3b68b609bb81 | note | QA Form - Seal design template
| signoff | HOLD POINT
| checkpoint | Location/Size Confirmation
d1359f13-8d85-54a2-8033-e5e4632410a6 | note | Specification Reference - Mark up extent of chipseal
cc681d30-14d1-5119-8824-f29edd484898 | note | Test Required - Prior to surfacing
b0f13e91-54dc-5818-9e7f-e180b00c4a71 | note | Task Timing / Minimum Task Frequency - Project Engineer
70480d72-0c4c-53bc-8868-665f55e11b49 | note | QA Form - Daily Diary
| checkpoint | Surface Cleanliness
dab9deb3-ee10-510c-9ef0-5a9fa933f292 | note | Test Required - Visual Inspection
b56bd97c-206a-5448-90b4-ed2f71b5f71e | note | Task Timing / Minimum Task Frequency - Prior to application of binder
25a63ad9-772a-5d1c-bff8-6038971c80b3 | note | Task Assigned To - Site Foreman
91fe74e3-751e-520a-a006-1cd02a79df63 | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
463cca6d-ecb6-5e9a-a624-822e4990cd3d | note | QA Form - QA Measurement Sheet
| checkpoint | Plant Resource
07e4c6fc-ee8e-528e-a3bf-e1661cf2caa5 | note | Test Required - Visual Inspection
986f3681-791b-506c-83e4-1a5d386908f5 | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
2f5ad221-6d72-5d6d-8676-afe0bf6d7e75 | note | Task Assigned To - Site Foreman
51306215-6156-5988-aeca-65e0b0d3a073 | note | Measuring Devices or Method - Visual
03c96a4d-5453-5e15-9919-10f4b2f412fb | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
11e2de61-6acc-5b5f-ae06-14323df95a36 | note | QA Form - Daily Diary
| checkpoint | Binder Application
c3d6a0e5-c5dc-5063-af4a-e70b53e5f46b | note | Test Required - Binder type, Cutback, Temp, Application rates
c88a08b8-393b-518e-bbc5-8c0d755dbdf1 | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
3a0ea77d-fd15-5428-bc94-6e1a49bf1ee6 | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
ee855ee6-0d0d-50f7-9723-7dd15d268952 | note | Measuring Devices or Method - Visual
9e54687b-e4cb-52a9-9feb-a583a7a0bf6d | note | Criteria - Binder Type = 180/200.
40f2a9ed-2c71-524f-a4f7-b0c4d6ad97fc | note | ○ Cutback to suit 1st coat seal 4pph kero max.
4de4c0d0-f31c-5e68-b0f0-5522a99160d7 | note | ○ Temp = 150deg celcius min
6ddecb33-eaf5-5f68-966a-7c76dabde708 | note | ○ Application = Design l/m2, +/- 0.1 l/m2.
8e37cdff-8aca-5223-b328-f3c2f9a409bb | note | QA Form - Bitumen Spray Sheets
| checkpoint | Chip Application
c0daf26c-9d4f-56dd-80da-0093965b6fc3 | note | Test Required - Chip type, Chip Application
12af4c35-9566-50b6-b12a-7b192a09cce8 | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
4ac622c9-0e59-5436-a30b-2a5386f33a19 | note | Task Assigned To - Site Foreman
c304d81a-bc65-5363-9a4b-d819b5298bc6 | note | Measuring Devices or Method - Visual
cc60b74a-f4ad-5ab1-a5c2-8112a61642a7 | note | Criteria - Trucks loaded with correct chip.
2e7755df-9c49-52ee-80ac-23618ad936fa | note | ○ Chip clean. (G4/6 Racked example)
6e4903f7-21b5-5d7f-a364-d92329e86f96 | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
bacda8ee-b51b-535a-98f0-cee412ccf278 | note | ○ G6 application = Enough to just fill the voids around the G4.
a3428f22-8328-5b68-9520-758f83d7fe22 | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
34b83295-6d7a-51a2-94dd-43924dd3068a | note | Test Required - Visual
73d28dd0-4399-579e-bfbb-17d8f633515d | note | Task Timing / Minimum Task Frequency - At completion of rolling
5f00c11c-e8e2-5443-ac40-e03850d5047e | note | Task Assigned To - Site Foreman
5f80a280-9a55-503d-b119-7fd27a7d5092 | note | Measuring Devices or Method - Visual
ad17ebcd-dfc0-5353-aa49-2a83b9a88d9c | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
66b62776-4004-5fd3-92e1-06d4e72a38bf | note | QA Form - 'QA Measurement Sheet
| checkpoint | Site Measure
f45bc688-dde1-539d-a849-e0a7d8a9cf84 | note | Test Required - Record final site measure
8733bfe5-7d4c-5ae2-a79a-011b80a56c81 | note | Task Timing / Minimum Task Frequency - Completion of works
e6119e66-1b70-5e20-851f-f4dc6e66b55b | note | Task Assigned To - Site Foreman
da74d426-6f9d-50ac-a009-54ddec84bb53 | note | Measuring Devices or Method - Measuring Wheel or Tape
3e5333bf-986a-5064-a1f0-4031c0d02fe0 | note | Criteria - Sketch and record seal area and QA detail
f5743024-b44a-532d-b33a-1f714a239894 | note | QA Form - QA Measurement Sheet
| checkpoint | Post Seal Care
3467dda1-e3cc-5e8f-9656-af460d01c1a0 | note | Test Required - Visual inspection
fbb02145-c28e-55cd-bdd2-82a6aac0cd06 | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
2a74346d-7989-56fc-9e71-f627b9c5b6d4 | note | Task Assigned To - Site Foreman
15456b4c-123f-5362-9324-3d0139abbd99 | note | Measuring Devices or Method - Visual
9d250803-2ef4-58e3-b68a-5c5bcbab0eaf | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
a021b707-3530-5243-9f85-33bba6062cf4 | note | QA Form - Daily Diary
| section | Chip Removal, Pavement Marking, Traffic Services
| checkpoint | Removal of excess chip
9eaf77ff-9a8d-5641-a8b6-59559d7ae3a7 | note | Test Required - Visual Inspection
2281c306-59c2-5f52-b2b2-4e266cc73b51 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
0302a3f1-0bf8-50ef-a139-9086088bcf74 | note | Task Assigned To - Project Engineers/Site Foreman
edf6f64d-f442-597a-a177-7e221abdc87d | note | Measuring Devices or Method - Visual
20cb17dd-1061-50b2-aebc-753ba326d4b8 | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
4a47c2d2-0745-59b2-bde3-3ca31b0e1169 | note | QA Form - Daily Diary
| checkpoint | Pavement Marking
72a3dde1-a6c8-5946-8c24-f029a3ded53a | note | Test Required - Visual Inspection
b1c22dd5-66a8-585a-9916-6ca2584bb982 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
3fdc306f-c62a-56f2-8538-418ad570145b | note | Task Assigned To - Project Engineers/Site Foreman
31edeb95-d7d2-5169-895a-6a915baf16dc | note | Measuring Devices or Method - Visual
84b58c17-ab98-516e-a69d-bdf4ca542585 | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
7a434c10-3a22-5ea2-a7ff-78240231150c | note | QA Form - Daily Diary
| checkpoint | Removal of TTM
5db4ba89-93d6-5cfc-aae1-d6698e06d034 | note | Test Required - Visual Inspection
611fe62c-413f-5b38-91f5-30d85dab5656 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
2a31521f-5f9b-556b-a783-81e120ef9e59 | note | Task Assigned To - Project Engineers/Site Foreman
658f1e06-71ca-5149-b4bd-869bb5d52ee9 | note | Measuring Devices or Method - Visual
3edccdf4-748b-5b88-8aca-8860753e91fb | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
5b983245-49c2-51a2-8dcd-328d10dfaff7 | note | QA Form - Daily Diary
| checkpoint | Traffic Services
9d424ffc-5e5d-5f60-9d18-7870edec8a34 | note | Test Required - Visual Inspection
20b11828-4bc3-5e10-a11e-1d57f27ea3b4 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
0e347011-bc30-5905-87fe-1335971216af | note | Task Assigned To - Project Engineers/Site Foreman
daf241bb-bc55-5433-bdf4-9afbda5bc7f7 | note | Measuring Devices or Method - Visual
b31d95b0-794b-5252-ab40-9c3c713d7145 | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
8ee6cd32-acdc-560c-8a41-1a108ecc8f68 | note | QA Form - Daily Diary
| checklist | 10. HB AWPT ITP - Sainsburry Farm |  | 10. HB AWPT ITP - Sainsburry Farm | 7e6aee5c-603b-44a0-81e6-0e78bb712df4
| section | Preliminary / Establishment
| checkpoint | Establish TTM
300426eb-5e25-50dd-b48b-4733d5c709b9 | note | Test Required - Visual Inspection
8d0f2ad1-ea6d-5a96-bd14-ba16a7d9f485 | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
e415993c-eab3-5747-b2e6-8669db508f93 | note | Task Assigned To - STMS/Site Foreman
554bca69-e617-5f7c-bdb4-923634c6e287 | note | Measuring Devices or Method - Visual
dc74e511-264e-59d6-a058-d80e190555f5 | note | Criteria - As per TMP and ensure TMC advised in advance of works.
e18442c5-3db7-5a39-a8dd-f8ca2df5cea8 | note | QA Form - Daily Diary
| checkpoint | Permits
80e065f5-61b8-536f-95b0-def94e69c76a | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
2b50a009-d8ee-562f-946f-59cb85d29955 | note | Test Required - Document Review
38dc289e-f1f4-509e-aea8-e33d52857671 | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
ba7ac953-07f5-5131-94eb-ee839fa16025 | note | Task Assigned To - Site Foreman
d278ae4c-11bd-5e04-8084-7c3f7866cd35 | note | Measuring Devices or Method - Visual
df49c2e5-2843-55ba-b4e5-7f0f80f37dbf | note | Criteria - Obtain permits and mark outs prior to construction
59ef89df-baaf-5e2c-85e8-d187748e3590 | note | QA Form - Copy of Permit on site
| checkpoint | Clear-Shoulder and Side drain
2ff65f6c-f088-51f7-b3ef-3c715925f594 | note | Test Required - Visual Inspection
63615f0b-589d-5487-8840-916263348b9a | note | Task Assigned To - Project Engineers/Site Foreman
0d5521b4-30da-5257-8e32-0cefc2429c06 | note | Measuring Devices or Method - Visual
5c94f07a-be93-54f6-9ba0-49717ef8ae44 | note | QA Form - Daily Diary
| checkpoint | Digout Failed Areas
835ff09e-08ff-557f-9395-5549340e5c02 | note | Specification Reference - Refer to Design Report for required depth based on Scala results
de178b0b-6f51-532b-92f3-9f07b40ef2f4 | note | Test Required - Visual Inspection
efc85846-2134-54bb-ac07-29a7b8d3dd8c | note | Task Timing / Minimum Task Frequency - Prior to Pavement Rehabilitation Construction
bbff3182-bc71-5d12-b14d-e9497d0673c5 | note | Task Assigned To - Project Engineers/Site Foreman
3abe9a1f-bade-5da3-b508-86153785aa9d | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
86f10fef-ece9-5d0a-8113-4fa3bc08caaf | note | Criteria - Backfill with Pavement Aggregate
a86e2faf-99af-5ded-9b2b-f330d0c928e2 | note | QA Form - Daily Diary
| section | Inspection Test Plan - In Situ Cement Stabilisation
| checkpoint | Cement for stabilisation
a48fb759-de1f-5d62-a720-4db9a9b734f2 | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
f6389dd8-7e73-5169-91aa-b8794e95e7a7 | note | Test Required - Certified in accordance with NZS 3122
1a14c3ff-2385-5989-9e08-d6c517519390 | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
| checkpoint | Production plan
24b7eedc-34cd-5e87-a603-b4510724be18 | note | Specification Reference - NZTA B/5:2008, 7.2.2
ff04f72b-f1fd-5663-aa8d-62a47def3cc6 | note | Task Timing / Minimum Task Frequency - 1 per site
| checkpoint | Stabilisation mix properties (including cement):
f1277344-88cf-5fe9-8500-beea1ffe677a | note | – Maximum dry density (MDD)
a5aa581f-4a17-58cb-a36b-4cc123cdd273 | note | – Optimum water conent (OWC)
dfa650ac-aa26-559f-811c-8eebb67d5042 | note | – Solid density (SD)
79d4350a-9e1d-5f77-8f71-bc9ae05acc97 | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
a019ae70-6e41-599c-af3c-212d8a6fc455 | note | Test Required - Material properties for compaction verification
c8aeea6d-2bd4-5f0f-8726-fcffdb8a7d38 | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
85f1a699-f6df-5f22-81a9-051df8fb9953 | note | Task Assigned To - Hold Point - Approval required by site engineer
94deeaa2-e622-5503-bcdc-01f23a78c999 | note | QA Form - QA Measurement Sheet
| signoff | HOLD POINT
| checkpoint | In-situ moisture content of existing pavement aggregate
be660110-2543-5dfd-84e3-8bb9adc3e898 | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
df9ffe67-d9ab-58fc-ab0a-b81ee0711ae5 | note | Test Required - In-situ moisture content, Between 90% to 100% of OWC
e630d5f0-67ae-534d-926e-e1b4d6dc8907 | note | Task Timing / Minimum Task Frequency - As required
678b8550-2c4b-5661-a42f-e877cdede233 | note | Task Assigned To - Inspection - Lab
c61088bf-efc9-5866-b0c1-8838b71b8369 | note | QA Form - QA Measurement Sheet
| checkpoint | Top-up metal
1bc652b9-7051-5e22-8b67-c17dd7f5ba11 | note | Specification Reference - TNZ M/4 Table 4
511c35be-4bc8-5125-9cbc-75ab6da25a3c | note | Test Required - Placed to required depth and design levels
26d7e4e6-0b32-5f5d-bbae-6b546eacf4b4 | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
8fccff67-699d-50d8-b68a-62ab07fec6ee | note | Task Assigned To - Site Foreman
213b7f1d-7837-5424-a227-8b7de2db4788 | note | Measuring Devices or Method - Stringing, Tape measure and or survey
1801c75b-3715-57b3-82d0-808d9898138e | note | QA Form - QA Measurement Sheet
| checkpoint | Cement spreading
e95258dc-f589-55f3-a575-f9fbce86517a | note | Specification Reference - NZTA B/5:2008, 7.3
87686999-20b5-5aab-a176-b954670d7170 | note | – Mat test (1m2 canvas mat)
a10db913-4e0b-5fee-8a61-d80b37dd89aa | note | – Average usage test
dcfa2525-bffc-5013-b9b6-97c0e2af362d | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
cc83e796-b855-53d9-94eb-53b06effd6fc | note | Task Timing / Minimum Task Frequency - Every 400 m2, Upon emptying spreader and bulk tanker
ca8af87e-012e-5670-b69a-3e245711331a | note | Task Assigned To - Inspection & sign off by Site Supervisor
75769740-8b8a-525e-b0ac-cefb528cb6f8 | note | QA Form - QA Measurement Sheet
| checkpoint | In-situ mixing - Cut depth
cffb4f2a-a978-5747-acac-180d22bf73a6 | note | Specification Reference - NZTA B/5:2008, 7.6.1
d0dce1af-38df-5785-861f-f30120fe01f6 | note | Test Required - Maximum variation -5mm and +15mm
db9931a3-dc43-5f9a-b9f6-e0ea40a9057f | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
5e2f4638-cff8-5db2-adc0-b1cf348c65c1 | note | Task Assigned To - Inspection & sign off by Site Supervisor
416e6364-1b28-5f87-9d11-ed19ef5c6d9f | note | Measuring Devices or Method - 250mm Depth
41f0d2d8-a59f-5702-bf33-06d4cf608171 | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
73043dbb-e0e4-5588-afb4-4e7e3fb00d50 | note | Specification Reference - NZTA B/5:2008, 7.7.1, NZS 4402 Test 41.3
a2a4f841-be9b-550b-aa87-825c8ee3adf4 | note | Test Required - Plateau testing
2c2a6e20-ba18-5693-a119-eca45908dfa3 | note | ○ Mean value ≥ 98% of MDD
8c7d5ee5-9b89-5f36-887c-262701305f7c | note | ○ Minimum value ≥ 95% of MDD
31b860aa-85bc-5603-b6a2-1952459c67cf | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
e3c441e8-6da4-52ff-a607-9345c1a85560 | note | Task Assigned To - Hold Point - Approval required by site engineer
4345fd51-1449-542f-982d-99787e68102d | note | Measuring Devices or Method - Nuclear Densometer
585824ce-6977-52f1-873e-93987016164d | note | Criteria - Minimum value 95% of MDD
271fc28e-702c-5d68-b0fa-3bb50099c409 | note | QA Form - Test Reports
| signoff | HOLD POINT
| checkpoint | Surface shape
5d297b21-e787-5291-a5c6-258fea77a9f7 | note | Specification Reference - NZTA B/5:2008, 7.8
f3a1e366-ddd7-5a21-b700-97a47c5b9b8a | note | Test Required - ≤10mm from 3-metre straight edge, No depression, Vertical variations -5 + 15mm
2ad9d198-baac-5127-8703-16692abff198 | note | Task Timing / Minimum Task Frequency - 20m intervals
5b1b6311-05a2-56d1-8996-25847a7bc5c2 | note | Task Assigned To - Inspection & sign off by Site Supervisor
51261395-cdbc-58ef-89cd-5efe4d438960 | note | Measuring Devices or Method - Stringing, Tape measure and or survey
b8008982-8c97-572e-b2b2-474dcb317a42 | note | QA Form - QA Measurement Sheet
| checkpoint | Crossfall
5f48eb59-43a9-5a46-8310-c245a75c57fe | note | Specification Reference - NZTA B/5:2008, 7.9
cb1b5298-7369-52c2-a959-2bf53852c9c6 | note | Test Required - Not less than exisitng crossfall at the start of construction
a6f89f8d-25e2-59e3-b845-b23d6a36ebf5 | note | Task Timing / Minimum Task Frequency - 20m intervals
844476cc-dcbd-5953-b013-8246630b0d2d | note | Task Assigned To - Inspection & sign off by Site Supervisor
4989df29-59cb-5e1f-8ceb-71b62215a78b | note | Measuring Devices or Method - Stringing, Tape measure and or survey
ba1a6f8e-6f7d-519d-b581-826b1120b7c7 | note | QA Form - QA Measurement Sheet
| checkpoint | Surface finish
9f2cb97c-b934-5e39-abcb-227ad74a8232 | note | Specification Reference - NZTA B/5:2008, 7.10
9fd4b5bd-5bbc-53b5-b29f-32a70cf95e40 | note | Test Required - See clause
5eb457a8-5343-5c07-8cc1-3f99b70c6bf4 | note | Task Timing / Minimum Task Frequency - 20m intervals
1327229e-972d-5931-9d5b-8eb1a6a6872a | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
0e87d119-2f24-53d4-befd-82ea698a4c70 | note | Measuring Devices or Method - Visual
| signoff | HOLD POINT
| checkpoint-no-value | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
| checkpoint-no-value | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
| section | Chipseal Construction (NZTA P29)
| checkpoint | Ensure appropriate TMP used
cfe9d4b6-124c-5506-bc8b-1a3a58a2cf41 | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
| checkpoint | Seal design
32849463-8b6a-52a0-8892-3752adc81e42 | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
f91d6d0a-f93d-5478-b3d3-fad0feeefef2 | note | Task Assigned To - Project Engineer
ed08c656-2995-5930-bab7-36ff9bdbd438 | note | Criteria - Seal design to be reviewed prior to surfacing
57c8aaea-415c-5003-b56a-0805d8c65094 | note | QA Form - Seal design template
| signoff | HOLD POINT
| checkpoint | Location/Size Confirmation
9f1b9485-8c38-56b1-9ebc-913ca5ac2a2f | note | Specification Reference - Mark up extent of chipseal
1faeaf78-8e48-5a11-8d50-30f6589d74c3 | note | Test Required - Prior to surfacing
f31cc376-0a7d-5a4b-baf5-0777848a5690 | note | Task Timing / Minimum Task Frequency - Project Engineer
16f5e106-8d14-5e0d-9f82-0ba0cbca2be3 | note | QA Form - Daily Diary
| checkpoint | Surface Cleanliness
0d8370c2-2e9f-5b8b-bff6-d4bb74033449 | note | Test Required - Visual Inspection
fd07f54f-a1f2-538e-9268-cc8a1f3e6db9 | note | Task Timing / Minimum Task Frequency - Prior to application of binder
41b88376-7d61-5537-9cee-3d8bc384d8df | note | Task Assigned To - Site Foreman
08498d5b-5a17-592d-a2c7-b5b8d8976356 | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
a2c81594-61c3-5785-9121-b99bfbfbd03b | note | QA Form - QA Measurement Sheet
| checkpoint | Plant Resource
5c23c945-638a-5b81-bcbb-8046febf20f1 | note | Test Required - Visual Inspection
f60b402a-e4f1-5f5c-9ffa-2c2132bef7a4 | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
6d638dd5-3901-5569-8262-6f48556857bc | note | Task Assigned To - Site Foreman
1aa886dc-7dd3-5c57-9568-ef1376c94bed | note | Measuring Devices or Method - Visual
c0a2d0cd-9845-5306-9577-6424d4104ab3 | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
8cd2726a-bee1-58c5-a91e-1b5f7485a6a4 | note | QA Form - Daily Diary
| checkpoint | Binder Application
8e924d56-2313-5e85-8022-e54e82ea0765 | note | Test Required - Binder type, Cutback, Temp, Application rates
c5b75710-59d4-5421-a6c7-071004658606 | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
bfa15d11-7b3a-5833-845a-bd7155e7a8b8 | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
60d643fc-9251-54c4-91af-1e01fdffa0f2 | note | Measuring Devices or Method - Visual
a94bbe62-d448-5c27-87fe-1e061936bbd3 | note | Criteria - Binder Type = 180/200.
91c8cdf3-c4d8-5cc0-b8d6-595180a1bbbb | note | ○ Cutback to suit 1st coat seal 4pph kero max.
cee66963-aebc-52c7-bdac-10dea2274121 | note | ○ Temp = 150deg celcius min
7474a19e-7e0c-5f90-ba24-5c26e20054b1 | note | ○ Application = Design l/m2, +/- 0.1 l/m2.
b9818c9c-db34-5960-8717-018a7dd2f44f | note | QA Form - Bitumen Spray Sheets
| checkpoint | Chip Application
01f8e7c8-4eff-5cad-9405-c03407a836d0 | note | Test Required - Chip type, Chip Application
1d912813-2f55-553d-9ff6-1d2475048f97 | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
7e7d6360-ed60-562b-ad6d-42ff98f25311 | note | Task Assigned To - Site Foreman
bc13bed2-1424-50bd-8c05-1a019ec1f1fe | note | Measuring Devices or Method - Visual
cbe38da2-1960-5db2-b1d0-d18514f840d7 | note | Criteria - Trucks loaded with correct chip.
674b4092-2cc6-5382-8acf-4a2ff3a54cd4 | note | ○ Chip clean. (G4/6 Racked example)
df6d866c-115b-5735-b07b-c61e8c839e09 | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
a198fe86-3ebe-5632-8513-c6b46d41d430 | note | ○ G6 application = Enough to just fill the voids around the G4.
f4346868-f479-5247-a931-b220c51d4f1c | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
da144088-1782-5db0-af09-c1177c001708 | note | Test Required - Visual
f4001d51-0e2f-5f8b-a01a-0182e0a79628 | note | Task Timing / Minimum Task Frequency - At completion of rolling
c44358e7-97d9-5efb-8fdd-a5d3fc19e950 | note | Task Assigned To - Site Foreman
33b48c1a-7511-54d5-a6a2-184d1210b86a | note | Measuring Devices or Method - Visual
5dc966c3-6fa2-5fe7-975d-16fd122b5e49 | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
b8456458-7580-53e7-92e6-901ddb33e578 | note | QA Form - 'QA Measurement Sheet
| checkpoint | Site Measure
2fbe100c-3199-547b-98af-22fa20cadb2a | note | Test Required - Record final site measure
ccfd4b1b-4972-5b33-9c80-b692b3996c0d | note | Task Timing / Minimum Task Frequency - Completion of works
a5550fde-a19d-5b5f-af45-eab13bf49735 | note | Task Assigned To - Site Foreman
bffeeec8-3f1f-5d3f-b249-7e78472afba2 | note | Measuring Devices or Method - Measuring Wheel or Tape
0674d7ac-3c75-5659-822a-cd49c979f04f | note | Criteria - Sketch and record seal area and QA detail
20e9ef1f-39a9-5b13-923b-c0c347df6e1c | note | QA Form - QA Measurement Sheet
| checkpoint | Post Seal Care
687770d4-6d3f-5704-bd6b-0c4b7121f9bd | note | Test Required - Visual inspection
12ee0c14-3b7b-5544-bbef-515733f6853c | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
353e1ad2-2f24-55c1-9252-d7df5b460121 | note | Task Assigned To - Site Foreman
8e8a68a2-e0fc-529f-a7da-f13d56e2df38 | note | Measuring Devices or Method - Visual
de76292b-57d7-5e78-b100-ffb42e5b3d1a | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
3b886f4e-307b-58c1-80fd-7e14cc77fa51 | note | QA Form - Daily Diary
| section | Chip Removal, Pavement Marking, Traffic Services
| checkpoint | Removal of excess chip
39a5fda4-5688-513e-89a5-3a8f46ea51a7 | note | Test Required - Visual Inspection
35681b99-36b3-5652-aa5a-5abbaf54a5c3 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
d519be18-f337-5d41-949f-9f854cad6db4 | note | Task Assigned To - Project Engineers/Site Foreman
bc71c2c3-19cb-5449-8e84-679e10ca0b33 | note | Measuring Devices or Method - Visual
b4e735c7-8276-5c6d-91f3-6d6db29b4f5e | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
aad85a5b-942d-570c-a8a4-07af0328024c | note | QA Form - Daily Diary
| checkpoint | Pavement Marking
cf9caeaf-0c64-56f9-8d0b-83ab567a7e1d | note | Test Required - Visual Inspection
fd8f0bda-4533-51ef-90be-a84bc6a263e3 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
73c646cf-a413-5fa8-ab2b-58695cac841e | note | Task Assigned To - Project Engineers/Site Foreman
46b6cad3-b5e2-5930-b65c-821a8d6ffb0a | note | Measuring Devices or Method - Visual
f81a7580-ceb0-5e6b-8bf6-fe0658e95739 | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
c2f9cd28-c067-53d9-bbaa-11f75c39038c | note | QA Form - Daily Diary
| checkpoint | Removal of TTM
bda7d959-c7d3-5fbb-96ed-f82bdd9920c5 | note | Test Required - Visual Inspection
3f6feb51-4d6f-57e2-9b6e-c4d9e7018250 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
8f88b475-5652-50e8-abab-59a86a28fd65 | note | Task Assigned To - Project Engineers/Site Foreman
b23f0dd0-8e00-51f4-9f06-123bab365b67 | note | Measuring Devices or Method - Visual
869d946d-6aea-5667-8cb1-2062e9b6f9fc | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
5bf47d7c-6a86-5200-b6cc-2ff1f017ddb5 | note | QA Form - Daily Diary
| checkpoint | Traffic Services
434022e1-5edd-5cfc-8d86-46c701296683 | note | Test Required - Visual Inspection
1d339f4e-0085-5d73-b475-23009238cc00 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
7fea9227-dcc8-549b-91fa-52f6ec9dac56 | note | Task Assigned To - Project Engineers/Site Foreman
880c3c82-eb3d-5bdb-be2f-a4101e9825fa | note | Measuring Devices or Method - Visual
ec45f09a-340a-5e1b-b446-2b4280dc7a5c | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
a33731ad-d4e1-5bf9-85a7-2cc28570bb77 | note | QA Form - Daily Diary
| checklist | 11. HB AWPT ITP - Sth Tikokino Rd |  | 11. HB AWPT ITP - Sth Tikokino Rd | 7929ccbc-0397-45df-8ab4-538fafe9a307
| section | Preliminary / Establishment
| checkpoint | Establish TTM
91538060-9873-51ce-9dfb-9c9de2525f7c | note | Test Required - Visual Inspection
5798a19d-73cd-5dc1-852b-9ae794401101 | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
5afa72c8-e1dc-5019-acee-c4cd2fc34d61 | note | Task Assigned To - STMS/Site Foreman
0df74b12-33d6-5f6f-88ec-b2a45aa01e6a | note | Measuring Devices or Method - Visual
3d38c849-9b27-5f5a-b2f7-324854be76d1 | note | Criteria - As per TMP and ensure TMC advised in advance of works.
ba3b834c-3243-5ad5-9229-101262c0d174 | note | QA Form - Daily Diary
| checkpoint | Permits
ddc0e0ff-ae1f-51b5-aff8-27ed63ffda1c | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
405be179-e028-5a88-9e73-f2e6f33b171b | note | Test Required - Document Review
e0ebc954-f416-5e41-9992-7abffb9fc375 | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
071d5a18-afb6-5e79-b265-00101462f84a | note | Task Assigned To - Site Foreman
dd028f6d-25c2-5d4f-b390-4d675f9452f0 | note | Measuring Devices or Method - Visual
741261fd-893d-501a-aa49-ca1bd2df89ed | note | Criteria - Obtain permits and mark outs prior to construction
62892809-c874-5b44-9bfc-e899484d3b18 | note | QA Form - Copy of Permit on site
| checkpoint | Clear-Shoulder and Side drain
0cb0f75a-fa50-594f-8baf-410c6c41cbcd | note | Test Required - Visual Inspection
111eb40c-0aae-5ce2-a281-de8e16a26025 | note | Task Assigned To - Project Engineers/Site Foreman
aa940636-a7c4-524f-bbca-3eaea59019c9 | note | Measuring Devices or Method - Visual
14808c72-5018-5707-ab34-8f12607801b8 | note | QA Form - Daily Diary
| checkpoint | Digout Failed Areas
2aa37540-a08a-52b3-8a08-0fbf294bda40 | note | Test Required - Visual Inspection
d5fabe2b-96cf-563b-9d9e-1b6c4897cda3 | note | Task Timing / Minimum Task Frequency - As Requested
5804d450-bd44-596d-9d79-9a491b3ffaca | note | Task Assigned To - Project Engineers/Site Foreman
6c6b2da0-1ea7-5618-a561-f424b3609ee2 | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
a0aa6791-3a2d-54bb-8e95-1eccabd85851 | note | Criteria - Backfill with Basecourse
6f5b1150-abaf-50a2-854b-83ac3abe0a39 | note | QA Form - Daily Diary
| section | Inspection Test Plan - In Situ Cement Stabilisation
| checkpoint | Cement for stabilisation
e505fca6-aa87-5d8e-8334-984fafb4dc7b | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
01afbe2a-5110-57ea-ba76-2e281c986789 | note | Test Required - Certified in accordance with NZS 3122
dbc7d379-1d91-5603-a2cf-440a5d2a0979 | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
| checkpoint | Production plan
17149eda-a01d-5d4d-b400-09a14d0de478 | note | Specification Reference - NZTA B/5:2008, 7.2.2
e1a4ee0e-1bee-5b1e-845f-0f0edda7706d | note | Task Timing / Minimum Task Frequency - 1 per site
| checkpoint | Stabilisation mix properties (including cement):
bdeca950-d630-5fd4-8656-0e7d40da6940 | note | – Maximum dry density (MDD)
de1e53db-d690-524c-bfd1-e94044ca024d | note | – Optimum water conent (OWC)
76f10a16-1977-5638-9103-14202c42b748 | note | – Solid density (SD)
d7b6e2e1-0be0-5558-a50d-a0eb757e8f85 | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
0746165d-a493-5821-8643-64a99ab5187e | note | Test Required - Material properties for compaction verification
08a1441a-a8fa-5cba-8e4c-1954da2dc906 | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
35cd3f68-14ee-5088-83c7-574d40adac42 | note | Task Assigned To - Hold Point - Approval required by site engineer
cdaa17e3-8336-5b91-9bd8-a49f58bcf899 | note | QA Form - QA Measurement Sheet
| signoff | HOLD POINT
| checkpoint | In-situ moisture content of existing pavement aggregate
697bf1ea-be28-5d3a-94f8-f63d891f1c89 | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
5a3f6503-0bf2-52b9-be53-5215516ce5aa | note | Test Required - In-situ moisture content, Between 90% to 100% of OWC
d9c60a67-938c-5865-934a-b60d134ae8a7 | note | Task Timing / Minimum Task Frequency - As required
a3393fca-ce4d-5cf3-9ec9-7f5d855e29da | note | Task Assigned To - Inspection - Lab
b768d9d9-98b4-57fc-80fe-2cd4a87e1653 | note | QA Form - QA Measurement Sheet
| checkpoint | Top-up metal
64c3aab4-d2a8-5ddf-8cf3-611ef6019d79 | note | Specification Reference - TNZ M/4 Table 4
ceb7e4df-03fb-54ce-8970-21c43ff71248 | note | Test Required - Placed to required depth and design levels
9cf81f28-a394-5e28-b562-31d44cf00952 | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
5217ed14-ffff-5ece-be71-d4310e34369b | note | Task Assigned To - Site Foreman
afa32026-ab03-5fd4-bdab-b8d0b93c62c8 | note | QA Form - QA Measurement Sheet
| checkpoint | Cement spreading
b7b303a3-6daa-5c6b-b43b-d3487b2175dd | note | Specification Reference - NZTA B/5:2008, 7.3
9107eb25-b71d-53cd-9782-0d8bb4eb30d7 | note | – Mat test (1m2 canvas mat)
2f9a7e3d-d5ce-54ce-aa94-7cb60505ef8b | note | – Average usage test
87d04961-227a-5c28-b85e-383e4ff1dc0d | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
dbf1c84d-7a86-52bb-90d7-873fa7d3408c | note | Task Timing / Minimum Task Frequency - Every 400 m2, Upon emptying spreader and bulk tanker
57653590-9c6b-516c-a279-6932558a64e3 | note | Task Assigned To - Inspection & sign off by Site Supervisor
536bec45-b73b-5f21-9596-a8a5cf0e6e3b | note | QA Form - QA Measurement Sheet
| checkpoint | In-situ mixing - Cut depth
32650744-ad2c-5479-b6e7-dd217db910d1 | note | Specification Reference - NZTA B/5:2008, 7.6.1
bae74d56-dd4c-5614-8e5b-974abc3e9280 | note | Test Required - Maximum variation -5mm and +15mm
588136ca-18d5-5cd7-98e7-07e9e994a91b | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
1656f027-1673-5d51-a228-c79129d7f46f | note | Task Assigned To - Inspection & sign off by Site Supervisor
dfa45f7d-bbaf-5194-9313-ed46dff3a8a6 | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
42246533-de61-5d4c-bec6-73aed991c33a | note | Specification Reference - NZTA B/5:2008, 7.7.1, NZS 4402 Test 41.3
4a58d37f-564d-5f23-9537-04dc09f50c20 | note | Test Required - Plateau testing
87242c11-8616-5956-981e-32e35bbf18a9 | note | ○ Mean value ≥ 98% of MDD
a3dbb30e-1052-5dbc-9b6b-92b1e2d14f0c | note | ○ Minimum value ≥ 95% of MDD
ad44e4ef-cfe6-56a4-bf1e-0d581bbd3407 | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
c6188b2a-889f-5486-8dbe-67ab5fe0b6ed | note | Task Assigned To - Hold Point - Approval required by site engineer
2eef69f2-738c-5dd6-947f-6b9052ca7bf1 | note | Measuring Devices or Method - Nuclear Densometer
77f6f1cc-0d6e-536b-a29d-7d1906bd3912 | note | Criteria - Minimum value 95% of MDD
c53231a0-4f60-5db9-995c-4c3ca7a32764 | note | QA Form - Test Reports
| signoff | HOLD POINT
| checkpoint | Surface shape
d18580f7-7c6e-55ea-aa91-ec58605e096c | note | Specification Reference - NZTA B/5:2008, 7.8
6c5147bb-96c5-52bf-b016-d0e881a1603b | note | Test Required - ≤10mm from 3-metre straight edge, No depression, Vertical variations -5 + 15mm
87649053-14da-5267-9fd2-981427ea1d76 | note | Task Timing / Minimum Task Frequency - 20m intervals
38e49fbf-7333-5a73-9d03-5203d1e4fa86 | note | Task Assigned To - Inspection & sign off by Site Supervisor
64521cf9-3b2b-5730-a46d-ddc0ff8a227c | note | Measuring Devices or Method - Stringing, Tape measure
f60edbaa-ceb8-5cd6-a5d0-a660595197ca | note | QA Form - QA Measurement Sheet
| checkpoint | Crossfall
127c39f4-6ce3-5d97-a762-734fff9a4ff1 | note | Specification Reference - NZTA B/5:2008, 7.9
6bfb7652-fcac-5bce-a833-efb1e83229e3 | note | Test Required - Not less than exisitng crossfall at the start of construction
a3e4a174-69c4-5f1c-8d74-7ca543b55ddb | note | Task Timing / Minimum Task Frequency - 20m intervals
cc9511f3-282a-5433-8fd5-6fb61240ebc3 | note | Task Assigned To - Inspection & sign off by Site Supervisor
21e6eb1c-7102-583d-9f7f-5b99a7e350fb | note | Measuring Devices or Method - Stringing, Tape measure
c6cd7f96-cb38-5165-82cf-3fbf1018a0c8 | note | QA Form - QA Measurement Sheet
| checkpoint | Surface finish
08c43f96-04ad-5a56-8d8f-d63ae0ae982a | note | Specification Reference - NZTA B/5:2008, 7.10
d2e43b59-296f-5afb-a731-e84965de65d7 | note | Test Required - See clause
55657528-67b3-5b13-ac41-3d4675cd0d38 | note | Task Timing / Minimum Task Frequency - 20m intervals
1f64fabb-5f3c-5126-9cd0-075ea444cf80 | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
a459d50a-9692-53bf-b172-4fffb1cae76f | note | Measuring Devices or Method - Visual
| signoff | HOLD POINT
| checkpoint-no-value | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
| checkpoint-no-value | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
| section | Chipseal Construction (NZTA P29)
| checkpoint | Ensure appropriate TMP used
93b153d5-a53c-5616-bf1d-85c80e700797 | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
| checkpoint | Seal design
c277b8d3-b3f1-51ac-b3da-c502b2ca6bd5 | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
1a4cd2f8-e817-5429-91d9-eb463667847c | note | Task Assigned To - Project Engineer
c36efb57-e365-5437-933a-60950bd68020 | note | Criteria - Seal design to be reviewed prior to surfacing
6e7bb9de-19a6-5afe-882f-dae404c38d5a | note | QA Form - Seal design template
| signoff | HOLD POINT
| checkpoint | Location/Size Confirmation
6dbfdfd3-ae8e-5d47-ac5a-49a4df252ca7 | note | Specification Reference - Mark up extent of chipseal
fb98a765-c728-55be-8df5-079d02736116 | note | Test Required - Prior to surfacing
0424f916-1b27-5cfa-a4ef-b14e5cc0da1c | note | Task Timing / Minimum Task Frequency - Project Engineer
f5dec31b-eed2-513a-bbc9-d3aa5dcf8848 | note | QA Form - Daily Diary
| checkpoint | Surface Cleanliness
e99c5e8d-8dcc-5f24-ac37-354a766bfb25 | note | Test Required - Visual Inspection
ab97d5d0-3789-513b-bc4d-221663b18be6 | note | Task Timing / Minimum Task Frequency - Prior to application of binder
0f7d2ec1-5547-5c04-aebf-97fc40d3a251 | note | Task Assigned To - Site Foreman
af61cbd3-efa8-5a7a-b355-9c3d69fb60ae | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
aa46706b-bc29-570c-a12d-a760a69caa33 | note | QA Form - QA Measurement Sheet
| checkpoint | Plant Resource
fbfc4b7f-363c-5229-9015-ac7ad938364a | note | Test Required - Visual Inspection
9010a24e-6ba2-55b0-934f-0202dffa4554 | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
db09224c-f8fd-56a7-bc64-8c714cfeee1b | note | Task Assigned To - Site Foreman
a572a93e-6208-5b8f-84c7-7f3996d8014c | note | Measuring Devices or Method - Visual
1880d797-622a-51f3-943b-a3b7e35a306c | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
cb8f2187-390f-535c-a3db-15961dbdfd32 | note | QA Form - Daily Diary
| checkpoint | Binder Application
57341a15-50b4-527a-882d-30431dabe391 | note | Test Required - Binder type, Cutback, Temp, Application rates
527272b9-7546-567d-b083-c2fc2a70585d | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
858588d8-6f12-541f-96a7-117dc4a1fe2d | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
ce89601e-01a1-5756-af52-0e42d95ae38b | note | Measuring Devices or Method - Visual
ebe1d09d-245e-58c1-94df-5c091450ff60 | note | Criteria - Binder Type = 180/200.
dc8ef95d-821e-5baf-84d6-b16944517868 | note | ○ Cutback to suit 1st coat seal 4pph kero max.
07576941-5822-57ac-b8c6-96f4f8e980d2 | note | ○ Temp = 150deg celcius min
d0a4f1ea-bd57-5541-9833-87aa3ba73a3e | note | ○ Application = Design l/m2, +/- 0.1 l/m2.
d256dfa4-dadb-51af-a465-edb721ebf363 | note | QA Form - Bitumen Spray Sheets
| checkpoint | Chip Application
9d8a909f-aee1-5fcb-9474-5007ecaeb105 | note | Test Required - Chip type, Chip Application
b7dad6b4-9534-5cef-8898-739bdfa70b16 | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
ef575e0d-11c3-5b03-a25f-87c8b6547c88 | note | Task Assigned To - Site Foreman
f8856054-65aa-503e-a710-ad43327fadf5 | note | Measuring Devices or Method - Visual
10ba5ae0-5900-55e3-b099-c915eaa7f1bd | note | Criteria - Trucks loaded with correct chip.
55d1c1b0-a9c5-59f5-b074-4a5ecaa44e0e | note | ○ Chip clean. (G4/6 Racked example)
732a3a39-c287-5ed0-abb3-6b2d5f67c99a | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
949c2edd-6753-59b4-91a1-e51d47b383de | note | ○ G6 application = Enough to just fill the voids around the G4.
34cc6d1b-2f40-5365-9e20-e1734aa8e14c | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
7922cbe5-31b7-5319-afc4-bda4e9f0a75a | note | Test Required - Visual
c359c581-60bd-5eba-ae00-2defc2efe4f7 | note | Task Timing / Minimum Task Frequency - At completion of rolling
d148da6f-d73d-5547-9412-5ddfbf7f0e58 | note | Task Assigned To - Site Foreman
7daabc3f-df5c-5a0d-bfb3-86d25933b0a0 | note | Measuring Devices or Method - Visual
187f5593-81d2-5422-bac4-fd13dd67aa73 | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
b751b84c-d5bb-5471-8db1-a068bedb19ce | note | QA Form - 'QA Measurement Sheet
| checkpoint | Site Measure
0c953b5e-688b-524a-bb6f-330e3eee8c6e | note | Test Required - Record final site measure
f0dd5f80-8d8f-520f-9891-c11a704f439c | note | Task Timing / Minimum Task Frequency - Completion of works
76bdac05-ef5e-5077-826a-4ef861f1cbbf | note | Task Assigned To - Site Foreman
0ec2b717-4363-5277-91eb-f503ab6dd457 | note | Measuring Devices or Method - Measuring Wheel or Tape
a19974bd-45b9-583f-b653-9dcb8ba40e57 | note | Criteria - Sketch and record seal area and QA detail
f06f7b0b-ea31-5a69-89d7-9101fd20fa24 | note | QA Form - QA Measurement Sheet
| checkpoint | Post Seal Care
3c79a9ea-6925-5c57-a162-3ebd37544c74 | note | Test Required - Visual inspection
b4e0d90f-81c8-5038-8c23-1c39fc0f2791 | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
f796e4c4-8ac7-55ec-95e7-a08ba51a9ac0 | note | Task Assigned To - Site Foreman
24133333-0b68-56e8-9882-a3610940293a | note | Measuring Devices or Method - Visual
31d85c78-d166-5db6-b0b8-43510db6c8d6 | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
05e5b859-1987-568b-9920-208affcf5d6d | note | QA Form - Daily Diary
| section | Chip Removal, Pavement Marking, Traffic Services
| checkpoint | Removal of excess chip
b4653fe4-0a49-51df-bf7f-f2cd21cf3a75 | note | Test Required - Visual Inspection
f2ca2c76-7a30-5e05-b504-6e538af7fd11 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
fdd81dd8-33f9-54f9-ba75-2a2542843480 | note | Task Assigned To - Project Engineers/Site Foreman
4daeece6-a061-54ae-8991-2f90f77d05c4 | note | Measuring Devices or Method - Visual
c1bac996-2623-54b6-9d9e-a750566703e6 | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
4f4f08cd-4134-514d-82eb-bd00f61a8060 | note | QA Form - Daily Diary
| checkpoint | Pavement Marking
72998183-70b0-51c5-b172-1491a7cb35ca | note | Test Required - Visual Inspection
3cb495d1-6260-566f-9da1-49e4d3904d87 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
75372e74-aafe-5533-a2e0-2cf14b17b8dd | note | Task Assigned To - Project Engineers/Site Foreman
56191d13-57c6-57d7-b994-565175665a18 | note | Measuring Devices or Method - Visual
41c730e3-c693-526d-8863-ed90083e6679 | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
2fc807f7-0eda-5ed1-b259-49969d10c6f4 | note | QA Form - Daily Diary
| checkpoint | Removal of TTM
7fb19597-34db-5b4c-8eda-b879a42fce63 | note | Test Required - Visual Inspection
b7cba2f3-364c-53d3-8cbd-8cad1181c20a | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
09d8cbf6-3efe-5de3-8582-00132305c0c1 | note | Task Assigned To - Project Engineers/Site Foreman
ca8732ae-377e-589d-b33b-b2fc508c4fe7 | note | Measuring Devices or Method - Visual
78f44d45-cbe2-59bd-9924-4afc1b5c1454 | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
54923fc6-51aa-51af-a62f-0480009a2ea8 | note | QA Form - Daily Diary
| checkpoint | Traffic Services
e0836c92-a716-5fd0-9d2b-94ae0035e995 | note | Test Required - Visual Inspection
a267ccca-a2a5-5ba8-a79e-3c2d34d7c31f | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
60dc4f5b-3b1d-599d-892e-682e4f106467 | note | Task Assigned To - Project Engineers/Site Foreman
17459b7e-6826-5e51-b546-efa462bb24df | note | Measuring Devices or Method - Visual
5a91be88-4ee0-5810-bf71-4c2c1d34e411 | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
fd0bdc54-3749-5b4e-ad3d-d471b5dd9a41 | note | QA Form - Daily Diary
| checklist | Approved JMF |  | Approved JMF | 0f230045-6516-4dd6-932c-88e32a125c5d
| checkpoint | Approved JMF
| checklist | ITP - Asphalt Resurfacing - HAWKES BAY NOC CONTRACT | itp | ITP - Asphalt Resurfacing - HAWKES BAY NOC CONTRACT | 788e0d0a-38fa-432e-ab3a-99cde7bde07b
| section | 1. Procurement
| checkpoint | Binder - Penetration Grade (1)
3317062f-c238-55bc-815b-a8f9ac569d40 | note | Controlling Documents - NZTA M01: 2020
72bfb1ed-bcf9-5e75-a269-ff6d067356b7 | note | Acceptance Criteria - Table 6.1
37353d5f-f902-581e-9ccf-488952f2a10c | note | Method - Property Test
529b992a-5a42-5d69-906f-c5b536a30af6 | note | Frequency - Approvals are for a period of five years
5944664a-c3e6-5e66-87ab-39205f53aeb3 | note | Responsible Person - Bitumen Supplier/Project Manager
f8487853-b24b-5cf4-bed9-08bbd931e556 | note | Verifying Document - IANZ Report
dac37be0-4ba1-53ad-ae42-a41ad7dc42e5 | note | Conduct - S
ecd80fa8-7ce6-59bc-bcba-c1751dc3414a | note | Produce Record - S
| checkpoint | Binder - Penetration Grade (2)
d89587f3-a585-50bb-b91c-e5cefd15cd5f | note | Controlling Documents - TNZ P11: 2007
db5d6f48-46e4-5e6e-a350-195ee748b2d4 | note | Acceptance Criteria - Table 5.2 Lab Mix Design Volumetric and Physical requirements
dba1262d-88e3-5d6b-a137-406750abee0c | note | Responsible Person - Aggregate Supplier / Project Manager
e57782b2-f05e-5c28-93d5-342ab67a156c | note | Verifying Document - IANZ Report
791088f8-2e07-54ae-9f3f-ad1e14324649 | note | Conduct - S
ce5f42d5-cd54-5334-9be0-7f6ce18ecbf5 | note | Produce Record - S
| checkpoint | Source Property -Coarse Aggregate (1)
f67b17e9-f044-5536-9e13-f4234c138f2a | note | Controlling Documents - TNZ P11: 2007
96156703-2c61-51f0-b8c9-51c84aa5f80e | note | Acceptance Criteria - 230kN minimum
6c167a43-5f9b-513c-8ae6-4e9019801cd9 | note | Method - Crushing Resistance
f436fba7-6aa9-5701-a183-1af3740d094e | note | Frequency - 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
6d4465f8-c9a5-5f85-b8bf-b89e6c3f00ce | note | Responsible Person - Aggregate Supplier / Project Manager
c8146629-e31d-536f-bfae-3139d2160d97 | note | Verifying Document - IANZ Report
f5052a35-4434-51ca-a3c5-40e036490cbe | note | Conduct - S
ee9619d7-34ce-5d0e-abbb-9f4be8791b95 | note | Produce Record - S
| checkpoint | Source Property -Coarse Aggregate (2)
17b41657-9caf-5d0e-bac6-7e612b353c5a | note | Controlling Documents - TNZ P11: 2007
e4727ab0-c31a-5c03-b63a-bc9ec7e0c209 | note | Acceptance Criteria - AA or BA
4d7e28d5-6c9a-5134-9ea4-40eeffdc2fc8 | note | Method - Weathering Quality Index
4161bb2a-7145-5c3b-948d-bb4c8e348ebe | note | Frequency - 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
25ea233f-f5ca-5134-8027-d79422639216 | note | Responsible Person - Aggregate Supplier / Project Manager
3184229a-87c1-5b5a-99ea-be8ece840b52 | note | Verifying Document - IANZ Report
8278a567-0bd7-5842-b600-6dda3c42fd1b | note | Conduct - S
1db8391c-45f1-5a95-9aa7-234dd6e5f6d8 | note | Produce Record - S
| checkpoint | Production Property -Coarse Aggregate (1)
d37ee15d-f464-5c98-907d-7ec74847dd6f | note | Controlling Documents - SPC-21711902a-PVT-PV3006-H-01 + TNZ P11:2007
21cee825-ec64-5d04-96b0-445b37056098 | note | Acceptance Criteria - ≥ 58. (At least 85% by mass of minimum PSV)
e75374b9-287f-548a-bb30-26c617c50bf0 | note | Method - PSV
ea5a8441-ec98-5993-a38f-9ed1e7bdb631 | note | Responsible Person - Aggregate Supplier / Project Manager
557f4d32-f308-5841-ace5-95d76a832887 | note | Verifying Document - IANZ Report
0da30d93-4df9-5dc4-86ec-741dc5daf840 | note | Conduct - S
3e641ff3-da7f-5c2d-9c6e-0eaf9b91f3e6 | note | Produce Record - S
| checkpoint | Production Property -Coarse Aggregate (2)
83f4379c-01ae-5657-a5ea-76e057e0fd75 | note | Controlling Documents - RPT-21711902a-PVT-PV310-H01
9dbab2ef-1f76-5931-82e1-528e2b7ad58d | note | Acceptance Criteria - Table 3.13 for various sites
21231d4a-58b9-5d75-9a42-5c05f9c5affc | note | Method - PSV
8b6902d5-c9b9-597d-b701-e851816ad8b5 | note | Responsible Person - Aggregate Supplier / Project Manager
bc6f5b01-cce7-54e8-bb4f-272ceff21ffb | note | Verifying Document - IANZ Report
6cbaec29-6a36-5d19-a377-e58889d24c1a | note | Conduct - S
9559edaa-091e-5f3f-a642-90765f678e65 | note | Produce Record - S
| checkpoint | Source Property -Fine Aggregate
54e98c6a-ea7d-54b6-8692-86a0ca9682a5 | note | Controlling Documents - TNZ P11: 2007
13e5b84e-50c9-573d-9cac-c3079a2fb10d | note | Acceptance Criteria - 130kN minimum
fbdde7b1-d0c6-53e7-ace3-e5affd35281b | note | Method - Crushing Resistance
f1331e14-6b6c-56bc-b564-77d5fc8e2d9e | note | Frequency - 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
9ce68cd6-689f-5b95-96c9-aa8b65fdfc5c | note | Responsible Person - Aggregate Supplier / Project Manager
3388c773-48a1-5aa5-a0b6-93371a3f422d | note | Verifying Document - IANZ Report
e700fdd5-9d18-5d40-9a38-0b91bddd6a7c | note | Conduct - S
b995e34a-1bbc-5a93-8200-f4ea016bb4a9 | note | Produce Record - S
| checkpoint | Production Property- Blended Coarse Agregateate (1)
8132b98c-e387-5dfb-ad9d-812befaf209a | note | Controlling Documents - TNZ P11: 2007
5904d030-1094-56c4-bd15-b512299a620d | note | Acceptance Criteria - 2.25 max
ec1e3c58-ae13-58ee-84be-30a8d8561de7 | note | Method - Particle Shape
2beac0fd-ebca-5e35-b888-e44a2f108fe2 | note | Frequency - 1/500m³ (Section6 of RNZ 9805:2009)
27d52f71-4af3-5ab6-b786-1192c3d47ec0 | note | Responsible Person - Aggregate Supplier / Project Manager
a1be3b87-2418-5dbf-93b4-38c42ff8926f | note | Verifying Document - IANZ Report
381526b2-60f3-52a0-933e-9c2172caf418 | note | Conduct - S
69188dd1-2ed5-50a7-874d-472dc21aba61 | note | Produce Record - S
| checkpoint | Production Property- Blended Coarse Agregateate (2)
2dce0d1a-82af-579e-8751-0b90df590cc4 | note | Controlling Documents - TNZ P11: 2007
12dccb68-5de4-5805-ae0c-2833136ae16a | note | Acceptance Criteria - 98%
1aeeaad9-79ec-5c26-8b22-ffe40620791a | note | Method - Broken Faces
6cd72228-187e-56dc-9026-18db270a93c3 | note | Frequency - 1/500m³ (Section6 of RNZ 9805:2009)
5cebd6d6-3401-5021-83ac-a2d224fbad3e | note | Responsible Person - Aggregate Supplier / Project Manager
fc5393c3-4616-501b-9edf-80966f4b4c5d | note | Verifying Document - IANZ Report
e3b21656-73f4-56be-9c35-67ea7fd0c355 | note | Conduct - S
3394c22a-b242-5241-884f-0237fc902aae | note | Produce Record - S
| checkpoint | Production Property- Blended Coarse Agregateate (3)
be8a3135-fbbf-5c1d-b8d6-b94aa410c172 | note | Controlling Documents - TNZ P11: 2007
c40ae226-a0b5-5d10-9802-2ba69a819997 | note | Acceptance Criteria - Report Value-5 minimum
0f8331c1-acfd-5c1b-b5dc-42eb5f091566 | note | Method - Cleaness Value
7c2dfd69-66e3-5b80-b604-62b8a70a8003 | note | Frequency - 1/500m³ (Section6 of RNZ 9805:2009)
e7dd90ff-3bf3-5c4e-a45d-3ad1bba8c4a8 | note | Responsible Person - Aggregate Supplier / Project Manager
8d317e86-473c-5e16-9d01-be6f3dbdd365 | note | Verifying Document - IANZ Report
465e21b9-0ccf-5f24-81f9-433fdb396012 | note | Conduct - S
6d5c3060-30e2-53ae-b49a-9d3aa7f22276 | note | Produce Record - S
| checkpoint | Design Mix
6a21fa1e-c4da-5107-a1f3-733e38a0d808 | note | Controlling Documents - TNZ P11: 2007
575d9bee-357a-5ec0-b0af-2831c8bbe7fe | note | Acceptance Criteria - Table 5.1 Mix Envelop & 5.2 Lab Mix Design Volumetric and Physical requirements
a006bc32-590c-55a4-ada9-fe125cf135c9 | note | Frequency - 10 days minimum prior to paving
62f0065f-43c8-5594-a00b-7805f1d3b357 | note | Responsible Person - Project Manager
e99fda86-988b-5959-8e48-5027ec1c8ef4 | note | Verifying Document - IANZ Report
af9c871a-d5c7-59ce-9166-16d9bf775a2a | note | Conduct - S
864506b3-6419-5a73-902d-d1281f897e10 | note | Produce Record - S
c52ff2d6-0cab-5bc0-9e1e-370e4425bed9 | note | Approval - E
b1fb8fc2-4d28-522c-978e-92837a17b6b3 | note | Note: Verify the type of mix specified in the contract and confirm with the laboratory-David Jones. Allow 6weeks for new desig mix.
| signoff | HOLD POINT
| section | 3. Construction
| checkpoint | Production Property Test (1)
5a31c78e-7c8f-5d3a-86e8-5b1ef4e2678b | note | Controlling Documents - SPC-2171902a-PVT-PV3006-H-01
9cface2b-af93-542e-8352-d714c2e8eb00 | note | Acceptance Criteria - Approved JMF + Table 7.1 - Mix Control Tolerance Note: ±0.4% rolling ave of four
c031874f-c58c-56aa-b375-38067f575e6c | note | Method - Grading
7f93f794-35fb-5e9e-8a4b-46d026f2f45b | note | Frequency - 1/>30mimutes production run and 2/>5 hours production run
18d59cc9-66c4-5af6-b154-a9809367e026 | note | Responsible Person - Project Manager
0abc92de-6cc7-55c5-b89c-f85fa0859712 | note | Verifying Document - IANZ Report
379e0976-06b0-50be-8c70-4308984462fc | note | Conduct - S
63ec4b2f-7302-5444-aeca-e7b8778e3549 | note | Produce Record - S
| checkpoint | Production Property Test (2)
5d686aed-41cc-5a60-8727-66b8cd0338b8 | note | Controlling Documents - SPC-2171902a-PVT-PV3006-H-01
1f5576e8-24e2-5da7-953a-ebff0364669d | note | Acceptance Criteria - Approved JMF + Table 7.1 - Mix Control Tolerance Note: ±0.4% rolling ave of four
206475e9-9172-561d-8eb2-892882ef8d8f | note | Method - Binder Content
fc1fd217-6d44-52d3-8fae-80967921f6b4 | note | Frequency - 1/>30mimutes production run and 2/>5 hours production run
3ba59fd5-1ac3-5922-8eee-1bd80fcfe6dd | note | Responsible Person - Project Manager
342e31f3-453a-5ac0-9162-d26a8b99b080 | note | Verifying Document - IANZ Report
9cc01249-6323-511c-88ad-315d9eae1845 | note | Conduct - S
19f37c8b-1c79-5dad-9305-e0dba9bcf31a | note | Produce Record - S
| checkpoint | Production Property Test (3)
8cfd8425-34b3-5be8-9f00-f39861371052 | note | Controlling Documents - TNZ TM6002:2006
49019cbc-706a-54e2-9ed4-1c3166de2242 | note | Acceptance Criteria - Report Value
77e53f18-0445-5489-9e22-96871aad6c84 | note | Method - Maximum Specific Gravity
c4fd6393-ff89-5a10-98f2-a523d556cff4 | note | Frequency - 1/>30mimutes production run and 2/>5 hours production run
49547f1c-3add-589c-bbf4-097e79c9b4a8 | note | Responsible Person - Project Manager
b45a299f-4480-54bb-9f67-57a7a81e938d | note | Verifying Document - IANZ Report
7e8344bc-2c8d-5551-b361-2bc68d7ecf42 | note | Conduct - S
b224f5e2-0983-5da7-8df5-406021911b2f | note | Produce Record - S
| checkpoint | Production Property Test (4)
200b5d5e-10b8-5099-ad17-7ef323dec447 | note | Controlling Documents - TNZ P11: 2007
d13b4a60-6542-5a3a-a1fa-480df1e4dd00 | note | Acceptance Criteria - ±10 oC from recommended mixing temperature
2c75ddde-b0a2-560f-9ae4-6ba4fd1aeb02 | note | Method - Ave temperature
9ca5d79e-ac7d-5791-84ad-53995f40fd1f | note | Frequency - Any truck load
1528a80b-e7a3-5c0b-afd9-b9f307c5afb4 | note | Responsible Person - Project Manager
19f75d8e-27c7-52d2-951f-b0af0e660f94 | note | Verifying Document - IANZ Report
e6d6c9ba-f03d-5c50-9ada-08a56d61574d | note | Conduct - S
d6e4bf2c-6a27-5c90-8ec1-b1a9e4516d16 | note | Produce Record - S
| checkpoint | Ensure accurate survey setting out is in place.
c03841cf-914b-58de-b895-da277dbdba7f | note | Controlling Documents - For Construction Drawing
65497562-874e-52c9-9208-c0e8849faf87 | note | Acceptance Criteria - Visual Inspection
411f205f-b367-5932-97de-246204c53481 | note | Method - Survey set out
49861404-b12e-59b5-b5a7-42d4e3769974 | note | Frequency - Prior to start paving
4fbb1d07-23e0-583a-aafc-08e00ff2c8da | note | Responsible Person - Project Manager
16e40dbb-afde-557d-b9b5-5d2706dd4ce9 | note | Verifying Document - Survey Record
50c53194-35b1-5ac5-83d9-7e6959154537 | note | Conduct - S
1bdeb4c4-ac02-5984-8e8f-b4d7820770b3 | note | Witness - C
ad1d8006-0f5b-5b8a-858e-791ac6349fbc | note | Produce Record - S
f3db1e88-96ea-57e4-9709-d3bc17d41757 | note | Witness Point - Y
| checkpoint | Check weather
faf34823-42cf-5f5b-80ff-4fcef5656d52 | note | Acceptance Criteria - Not foggy or raining or wet surface. Base Temp ≥ 7ºC (25 – 75mm layers)
0b824ca3-6504-5cb6-8cb2-6c05eae55b03 | note | Method - Weather Forecast
64de52eb-e748-56f4-a22c-5848426be004 | note | Frequency - Prior to starting
aae05374-5983-5af8-a2d9-c2a9923cdeb7 | note | Responsible Person - Project Manager
0846ece7-c90b-549d-b2e6-6fe0be6a2678 | note | Conduct - S
becdb7ac-6cd1-53f9-ac8e-cec3c4cb3fec | note | Approval - S
| checkpoint | Ensure previous layer is broomed clean.
4de76b1a-d7ed-5714-8743-bb01ab472e6b | note | Acceptance Criteria - Visual Inspection
13798f77-4a7a-5c9f-a1c8-0378054000b3 | note | Method - truck broom
3be859f1-0a34-5557-9a18-0e5f14f79faa | note | Frequency - Prior to start paving
28da6755-49e1-503e-8b48-ce6d446cc87d | note | Responsible Person - Supervisor-Paving
05586fb6-23f6-5dd5-b540-25e823fb61e0 | note | Conduct - S
57168ce6-176b-58ac-8d15-7bf2516be030 | note | Witness - C
23d894dd-d052-598f-a5a8-e2faf063f62f | note | Produce Record - S
04de79b8-331b-527e-80f0-992465e00e8c | note | Witness Point - Y
| checkpoint | Layer Thickness
bb366c99-a946-5667-95b1-314f64b20e0b | note | Controlling Documents - SPC-2171902a-PVT-PV3006-H-01
e5a2280b-14e2-5d72-be5d-2e9567d3a3ed | note | Acceptance Criteria - ±5mm nominal thickness as shown in the Drawings, Plans and/or Specifications
066654d9-9234-5ab3-82a5-d48ef547a368 | note | Method - As-built survey
8d41e23a-e46f-58b1-a3de-7ac398730a11 | note | Responsible Person - Supervisor-Paving
0e21f300-7939-5a3b-8a22-a7e5ac512a22 | note | Verifying Document - IANZ Report
1fdd5767-bcc7-5fe4-8ce7-41c76adcde92 | note | Conduct - S
5825412b-ecff-5868-8a10-dda628a15944 | note | Produce Record - S
| checkpoint | Surface Shape
a426409a-f769-5867-b163-e02ab93735a1 | note | Controlling Documents - SPC-2171902a-PVT-PV3006-H-01
04aeff1d-7689-5e53-a13e-5865af104709 | note | Acceptance Criteria - ≤5mm
d2733170-610b-5358-890c-1b90f01fa0ee | note | Method - 5m straight edge
24632550-b198-5fc5-bed6-8082e8d88ccd | note | Frequency - During paving operation
9c30fb84-213f-5caf-9578-3d5e671927dc | note | Responsible Person - Supervisor-Paving
1be5fc3b-de2b-5c6f-aedf-d57a8389ac7d | note | Verifying Document - Recod Sheet
1de6d055-74b5-5164-87c9-99516ae2c969 | note | Conduct - S
e30a50fb-9424-5701-9ec5-1b509196b80d | note | Produce Record - S
| checkpoint | Surface Texture
db4aa7f2-08fc-5fd7-8301-416790441dc7 | note | Controlling Documents - NZTA M10: 2023
75515241-7869-5cea-a988-6e36d92d7160 | note | Acceptance Criteria - Table 3
632e2f23-01db-5833-82a1-7e2d40b1dfc0 | note | Method - Laser Profilometer
36d25c88-fa29-5f77-b8f7-28206a8e1875 | note | Frequency - every 10m
504e1b5f-4bcd-577f-b1c4-3299985d925d | note | Responsible Person - Project Manager
759e2c45-c433-5f7b-85ef-e81c792316b9 | note | Verifying Document - IANZ Report
c8ee3edb-75d1-5dee-a419-11a9a5293dee | note | Conduct - S
687f80a8-3499-519f-a943-53fc17b40dc3 | note | Produce Record - S
| checkpoint | Ride quality
68114c6b-ed5b-5a87-abd1-d8854b85c06d | note | Controlling Documents - 10. Appendices to Principal's Requirement
c10d2354-fdc4-5b38-8f83-5f31a558fa76 | note | Acceptance Criteria - 50 NAASRA count as a 95%tile for every 100m rolling section
b7eecb89-edde-5643-b0c1-43e6e078eac2 | note | Method - NAASRA
d495e506-92e5-5e6f-8471-1ee7047dc41b | note | Frequency - Upon 100% completion of OGPA layer and at expiry of defects liabilty period
c91cccc3-048a-5f86-b809-0dca4535c373 | note | Responsible Person - Project Manager
c4eda79b-d97a-5ce6-b1d1-92450ecb8dbd | note | Verifying Document - IANZ Report
8337cd0c-5be9-5e51-bb92-782acffd0105 | note | Conduct - S
a69e1636-87d7-54ac-80d9-36dfec7354e6 | note | Produce Record - S
| checkpoint | As-Built
ec6d7fd7-449a-58c6-8356-fe81ee074a00 | note | Acceptance Criteria - Visual Inspection
ea7a2e39-ea6e-5914-83a8-178b6e41b556 | note | Method - Survey
1ac0818d-8135-5856-a683-c330b7e98309 | note | Frequency - Upon completion
eab5efd4-982a-5683-ad71-f5c45ede4c3f | note | Responsible Person - Project Manager
a6f0409c-29c4-5c64-a68f-b7b157ada930 | note | Verifying Document - As-Built
4346aea9-aeda-5fe8-b8b5-0a0a50b3eeea | note | Conduct - S
66918854-7cb8-5e71-b856-2deaf63922fd | note | Produce Record - S
| checklist | ITP - Chip Resealing - HAWKES BAY NOC CONTRACT | itp | ITP - Chip Resealing - HAWKES BAY NOC CONTRACT | 180e55ac-edd8-4b05-8a3a-cebe2514dadd
| section | 1. Procurement
| checkpoint | Binder - Penetration Grade
22c900ba-3cec-5f01-8da3-25bc5f53dea5 | note | Controlling Documents - NZTA M01: 2020
812cb4c6-2238-505b-b691-c6692d0375e3 | note | Acceptance Criteria - Table 6.1
8fdaaf2f-f9d5-5305-aa3d-20b5e8da8e0d | note | Method - Property Test
5dfd0306-cdf2-525f-bfcf-d53eca223033 | note | Frequency - per Bulk shipment/grade
ffad7d49-d615-5792-83ee-3a6a43511a57 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
ab5faf5a-e567-51b4-af09-f703b86e055a | note | Verifying Document - IANZ Report's
2ddd3a25-28db-51ca-991c-96447b2c3776 | note | Conduct - C
b5032a27-9487-5cf6-a40a-1694f47d4cad | note | Produce Record - C
b3d76be8-123b-5c9f-82f9-b22e4634893d | note | Approval - N
80070bb9-e789-5d33-a7d8-c0f9f6264dbb | note | Inspection Point - Y
| checkpoint | Binder - Polymer Modified Emulsion
c8390382-80a0-5ef3-bd3a-b066ef0ee3fc | note | Controlling Documents - Higgins Internal Specification
5f734bfd-acc7-5924-9ec8-e794d73c9308 | note | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
2b2b36e0-3226-5e8d-835b-b285801238df | note | Method - Property Test
b02e32e7-6710-5350-98cb-7745470ed199 | note | Frequency - 1/100,000 litres supplied
ee6bf142-4998-518d-8e00-be868f10bfe0 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
789130ad-bd6e-5cf6-853a-46a3ba9760e8 | note | Verifying Document - IANZ Report's
191d7a83-5ac0-57f1-bebd-e1c053f367ad | note | Conduct - C
9e85c660-1daa-51a8-a420-a7fa4d48e7db | note | Produce Record - C
aaa59840-24da-55a4-9ec6-6bf1fb3555ad | note | Approval - N
e4873397-4a98-5ec0-9ae3-8855963b20b5 | note | Inspection Point - Y
| checkpoint | Source Property -Coarse Aggregate - Crushing Resistance
83ead2b4-459f-5ec1-9d6b-9396c3b64c3f | note | Controlling Documents - NZTA M06: 2019
3af22c8e-0f62-576b-9704-62904d55a7b3 | note | Acceptance Criteria - <10% fines under 230kN minimum
7ca1edc1-4908-5b49-83ea-f103e9dba21a | note | Method - Crushing Resistance
79bab32a-b99c-5e0c-9094-37ed26b38af0 | note | Frequency - 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
4e8dbcd5-4583-5844-810e-65b156023395 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
ca067579-d2e7-50fb-8558-9b05e2dc4ae7 | note | Verifying Document - IANZ Report's
4c20ac66-4b79-5243-8687-73fa15abbbc4 | note | Conduct - C
92bd1ee0-cd99-59eb-85eb-f0d521ecd330 | note | Produce Record - C
203d4501-4585-56de-8452-3ac203d7e202 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Source Property -Coarse Aggregate - Weathering Resistance
3149a553-2fd5-515d-94ca-840a797eab44 | note | Controlling Documents - NZTA M06: 2019
c56a4435-a18b-50a7-a955-8ddda1db6f6d | note | Acceptance Criteria - AA or BA
4ec6a4a2-098f-5a3c-99fd-b0bec1f25d80 | note | Method - Weathering Quality Index
1ff61114-720c-5b45-b81d-3405fe5d0405 | note | Frequency - 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
dffa48e6-1711-5b77-b1bb-9600944f7bc2 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
a96dff67-8a16-5e27-a913-7d1cfd1f7714 | note | Verifying Document - IANZ Report's
952b7274-c030-5ae4-bbc6-6471b0c4d66f | note | Conduct - C
47491785-fe11-5b19-b715-af73233e8450 | note | Produce Record - C
daea09da-676f-56b7-bbf6-efa3adaa3539 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Skid Resistance
43f97133-3a69-572a-ab2f-d2d4a91301ec | note | Controlling Documents - NZTA T/10
8ae3f5b0-f567-5945-a714-4398c9747726 | note | Acceptance Criteria - Meet Skid performance Requirement
81f482e4-49cf-5663-9dd0-2cee1787802d | note | Method - PSV
dc5f3e34-5ef3-5db8-9808-5171399b3f93 | note | Frequency - Each Site
e298dbd0-7435-54ea-b410-977bf9c64d79 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
39866c5b-2eaa-5646-83b2-629bb0c7f03c | note | Verifying Document - IANZ Report's
c448188d-ddac-51d5-889e-c0a3520550e3 | note | Conduct - C
2d4de794-6acf-516d-aa23-a14b7c3dc9a8 | note | Produce Record - C
65fa7faa-ff30-5635-b703-c94e1bfc4ad5 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Cleaness Value
5b9360b1-34ce-53ff-b6ad-d07f4ad20d04 | note | Controlling Documents - NZTA M06: 2019
e2bddf48-252d-5b89-aa46-c9bec19a10ec | note | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
99e6c92a-17c8-52e0-9dfd-418e455dc564 | note | Method - Cleaness Value
bef88f93-5389-580b-aff1-6119e744ed9b | note | Frequency - Per Stockpile
0fe2937d-c494-5a66-8413-e5c99d0043b0 | note | ○ <100m3 - 1 Sample
b133cf2c-75b9-5c77-9ab6-328f10ad5aa4 | note | ○ 100-500m3 - 2 Samples
44484778-0690-59c8-87b6-70b73e058ca4 | note | ○ >500m3 - 3 Samples
98ddd79a-b9f3-503a-837d-463899782358 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
1a1381b0-089e-5f20-ba2d-ff56c80e18de | note | Verifying Document - IANZ Report's
bb4a8073-a2bd-522c-9214-4e4f1c5617e9 | note | Conduct - C
2375572a-b86e-5fa2-950d-2dd7d7992112 | note | Produce Record - C
24022ebb-3ed9-5a76-8db8-1dea117d7dd5 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Particle Size/Shape
99d95264-63c9-5b0f-8abb-3a591672e281 | note | Controlling Documents - NZTA M06: 2019
c02bd6e1-82af-55ea-820e-93f2773aa809 | note | Acceptance Criteria - As per Table 2 and 3
9c894b83-3d69-5ac3-b7a1-ba98fd41771a | note | Method - Particle Size/Shape
11aac630-6d58-5394-8708-efd1aedc9f32 | note | Frequency - Per Stockpile
32d0df34-20e9-5984-99c9-11464ea9ca54 | note | ○ <100m3 - 1 Sample
b275147a-13ad-5d9d-adea-62bd5b1dd295 | note | ○ 100-500m3 - 2 Samples
2a1768a9-83ea-5d85-8a88-f69bb648afd3 | note | ○ >500m3 - 3 Samples
04134edf-ec91-587b-b963-ff40c584d14b | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
e5cf9c63-5c1c-5cf7-9ec2-aea8834495dc | note | Verifying Document - IANZ Report's
4c24264d-7051-5737-9110-d4ff3874313f | note | Conduct - C
2ad05f74-7bfe-5e5f-a388-aa7eab9d57f3 | note | Produce Record - C
af79bfef-3491-5c45-9bbd-7c9bf9804523 | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Production Property - Broken Faces
60a91ff6-f07a-5efd-8775-d0d3a593699f | note | Controlling Documents - NZTA M06: 2019
ffccd4c3-45ca-5f80-b1a1-a17219e58ef2 | note | Acceptance Criteria - 98%
b0fc4d26-5f38-52c4-bda0-cec1e76ec83d | note | Method - Broken Faces
d072995c-e324-5d78-be97-dd25ae61ec68 | note | Frequency - Per Stockpile
8cdbb2b3-4a97-5182-a563-ec7b085c6c2f | note | ○ <100m3 - 1 Sample
acf36422-556a-5a75-b2ac-54e7489dcbb0 | note | ○ 100-500m3 - 2 Samples
b4a33232-cc16-58ba-a46e-2214dce7c31e | note | ○ >500m3 - 3 Samples
affe6cbd-52b4-525c-9a86-62f048672226 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
64a9f10e-06dc-5857-9167-f75281dd13b5 | note | Verifying Document - IANZ Report's
23c61bb7-edde-5d59-abd1-057ed1e0289a | note | Conduct - C
b3276391-9ff6-52c9-95a5-d96fe586db11 | note | Produce Record - C
1245c5a4-b2be-593e-a079-6d9e97b9dfb5 | note | Approval - N
| signoff | HOLD POINT
| section | 2. Construction
| checkpoint | Chipseal Designs
8c648d60-2a70-5f2a-924e-bdf543e301ad | note | Controlling Documents - HB NOC Design Report, Chipsealing in NZ, NZTA P/17
bf14d0f9-1ee7-5b20-85e5-0f428f42ffa3 | note | Acceptance Criteria - Client Approval
61626e69-c65a-52bc-9e7c-b677273fc733 | note | Method - Review
d54af904-2a07-5ad5-9339-5110c3291cd8 | note | Frequency - Annual
6c8695b6-1949-5879-8a2f-3d84068ab20f | note | Responsible Person - Surfacing Project Manager
4a837e0e-3b95-5e0b-a87b-e940c30e6f54 | note | Verifying Document - HB NOC Design Report Acceptance
50e07ebd-fbbf-56fe-add0-a944aca6b9f0 | note | Conduct - C
a7ddcdcf-1371-54d2-84bb-2a41d18da9ca | note | Produce Record - C
54bdf7d8-1455-5d2f-8a31-7b5d399a16bd | note | Approval - N
| signoff | HOLD POINT
| checkpoint | Finalise Sprayrate
1b2b3f58-e846-5cf8-baf9-33399f471e8f | note | Controlling Documents - HB NOC Design Report, Chipsealing in NZ, NZTA P/17
12c36d17-2223-53b1-8e47-5157fcbb4df9 | note | Acceptance Criteria - N/A
0fe21b5d-03da-5add-b5c3-67f1771dbb16 | note | Method - Review
22f34153-84fc-5a44-b900-1743d2253e61 | note | Frequency - Per Site
f727fab5-27bc-58fb-9e29-ea025d7b2540 | note | Responsible Person - Surfacing Project Manager
b7f0f5f6-d3a6-5c5b-ab56-a09e6cdc7c13 | note | Verifying Document - Site/Spray Instruction
c4ed21f1-6d2d-57a5-9fc2-648039ddd495 | note | Conduct - C
2a953d26-a6ed-51ab-9ee7-0dce1b712df8 | note | Produce Record - C
c93d7bbc-bdfb-54ad-8133-492fb9b12ad6 | note | Approval - C
de70c372-40a3-572d-8eda-c27d04e4f24e | note | Inspection Point - Y
| checkpoint | Check weather
ebb66426-fd35-5af3-a492-10a6c092d4c0 | note | Controlling Documents - N/A
308d6469-32cb-550b-b8ba-b811dbf67c13 | note | Acceptance Criteria - Not foggy or raining or wet surface. Base Temp ≥ 10ºC and rising. No rain forecast in next 24 hours
83c3e115-b434-5a0b-95bb-1bfd42df7be4 | note | Method - Weather Forecast
d645f42e-d212-5b29-97a2-31149e6c66e2 | note | Frequency - Prior to starting
1c2117d2-65f0-5d82-8f05-0c2c6a64df79 | note | Responsible Person - Surfacing Project Manager
4e8594af-48eb-5642-b058-5997dbed0923 | note | Verifying Document - Daily Report, Chip Sealing Quality and Site Record
9cb31cbc-bc21-53d7-83cf-8e8c0b040adf | note | Conduct - S
0f9e5876-104b-5f0e-8bc2-b7d9a7ab662d | note | Produce Record - S
4c186fbb-d94a-5303-b560-7d20a7f9d675 | note | Approval - C
b172030f-c06e-5df5-8aea-0c11edc2bde8 | note | Inspection Point - Y
| checkpoint | Ensure Limits of site are marked
4a780bfb-bf69-512f-9e35-3fd21ac78aee | note | Controlling Documents - HB NOC Design Report
e72b7422-cddf-5e55-9c07-252708bb2438 | note | Acceptance Criteria - Visual Inspection
fea20393-99ee-5b8c-b2a9-f92d7b1d6dec | note | Method - Visual
02a97881-d48a-58f1-9bef-eb6f4e42d0fc | note | Frequency - Prior to start Sealing
32ad21a8-b67a-59b9-96cd-c10d2b4bcb3f | note | Responsible Person - Surfacing Supervisor
35df1ffb-373d-563c-9eba-584c58f8b46f | note | Verifying Document - Chip Sealing Quality and Site Record
af37607a-cb72-5ce6-8f01-134a631cb7f0 | note | Conduct - C
440a8c50-8fb9-587c-9f1b-7b357fc3afd7 | note | Produce Record - C
63dd4c9b-2761-5eb7-acc7-a6653ae0db40 | note | Approval - C
9267963e-361b-5e4c-91ff-1c7f99ffb5e9 | note | Inspection Point - Y
| checkpoint | Establish TTM
542023a0-af4d-5ada-8358-63e71b517eec | note | Controlling Documents - TMP
b53327ca-ac52-5e7d-865d-3f6c0d4b7582 | note | Acceptance Criteria - Comply with TMP
970719a5-8a92-5bde-b207-a0cabab57dfb | note | Method - Visual
09c1ac0f-f923-51a0-aa52-a715b4ca12c8 | note | Frequency - Per Site
77090fd5-0e9b-55c8-aa47-529687a1613f | note | Responsible Person - Surfacing Supervisor / STMS
a7dba451-e015-5f60-aa61-8fbb38d98445 | note | Verifying Document - Daily Diary / STMS Record
77736fc9-47ea-5796-9c96-fd3725ba94bf | note | Conduct - C
05b1c871-f73b-515b-99dc-7197e310f1b8 | note | Produce Record - C
4917af1b-1201-5f34-a191-59eeefe3920a | note | Approval - C
def037db-b12a-58dd-afc0-3cf0c5dbbc51 | note | Inspection Point - Y
| checkpoint | Sweep surface clean of deleterious material
09a4ee37-85ec-50a2-94cb-a8354f29522e | note | Controlling Documents - P/17
774ea01e-3839-5776-93b3-0b7f2477d7f9 | note | Acceptance Criteria - Visual Inspection
6436741f-1504-5d6e-a91b-9dd93f3dce48 | note | Method - Tractor Broom
9a7cf622-7850-5a00-b65b-980a1f2c071c | note | Frequency - Each site, prior to start of sealing
08c423e3-1003-5830-baea-1787cb94a877 | note | Responsible Person - Surfacing Supervisor
c299aad2-fce4-522f-aadc-754eb7a197b6 | note | Verifying Document - Chip Sealing Quality and Site Record
2f60165b-4ffb-5b2c-8d6a-063da3dc83a5 | note | Conduct - C
cc0b2bc9-cf5a-538a-97b0-860d0fecd1b0 | note | Produce Record - C
92a266f0-578e-5226-a6f9-ed1b712a5585 | note | Approval - C
639c15de-8a32-5354-bf36-33749dbf38f2 | note | Inspection Point - Y
| checkpoint | Confirm correct treatment(s) and chip
2828cbab-a1fd-5d19-be06-b5e80a5ca18e | note | Controlling Documents - HB NOC Design Report
f4275c2e-ef80-54c9-96c9-829d31e1a059 | note | Acceptance Criteria - Details/chip correct
d84e4db9-22a6-5fd0-8b72-269e0be8956b | note | Method - Visual
6653e118-10f5-57e7-8509-24f324372f88 | note | Frequency - Per Site
c679efad-8b49-5f35-881c-1ff274d1405d | note | Responsible Person - Surfacing Supervisor
76fa3ebc-a6aa-5122-b719-762af85d57e8 | note | Verifying Document - Chip Sealing Quality and Site Record
b5959392-1e2c-55b0-862d-3263e93c38a4 | note | Conduct - C
c020d445-fecb-5831-9ed2-f7850603edb1 | note | Produce Record - C
44bd34f8-ecda-5956-9db9-9f8a3ee94ee2 | note | Approval - C
465933d2-d237-5197-a654-ecceb638b2fd | note | Inspection Point - Y
| checkpoint | Cutback Bitumen Blend
b08a8ee1-7f11-5317-aaa2-62fb2c8e7302 | note | Controlling Documents - RNZ 9803_0513
bc1516b2-a817-5788-8f3d-9d5176040cf8 | note | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
e9d4da72-ee37-5040-a9de-2e8441ea2f29 | note | Method - Sample and test
86a8ba7c-8321-5f69-b810-a47bb1e94671 | note | Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
3135261d-628f-5a94-b0ab-9a9227cf84ba | note | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
0868846f-728e-551e-bfd2-be40c4bf0a1a | note | Verifying Document - IANZ Report's
a5b1d14b-5447-5dcc-baba-c7a5a49901df | note | Conduct - C
ab119211-206a-55bd-8c6f-8fdb5da96047 | note | Produce Record - C
83f4142d-3704-5910-b9ab-9af85f1f60ed | note | Approval - C
7fb28d04-128d-5d8a-86ca-7e134d1051e3 | note | Inspection Point - Y
| checkpoint | Bitumen Application Rate
c8a5224a-445c-534b-8455-7c2c7e5286c5 | note | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
1539d4dd-6e1f-5c4e-9bef-84e898badd83 | note | Acceptance Criteria - Current E/2 Certificate, +/- 4% per Spray Run
8b75a248-059f-59be-b39b-992a3aeac6b2 | note | Method - Test, Review
354d7a7a-2744-5b28-8793-74c52b5816ca | note | Frequency - Per Sprayer, per Site
80c5ef9f-165c-5039-a418-2f8509d686db | note | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
df929051-268f-552b-89b1-a0faf84f449d | note | Verifying Document - E/2 Certificate. Spray Sheets
ebb87c14-6d56-5e8d-afb9-8b1d9d5c4027 | note | Conduct - C
62429abe-6102-55e5-a46e-daa4961c9dfc | note | Produce Record - C
0ceabe36-6d0d-58dc-976d-445281def09b | note | Approval - C
e87f70ab-e682-54fc-a2c1-798593027785 | note | Inspection Point - Y
| checkpoint | Chip Application Rates
8dbd7294-e27e-5c41-b803-2250acc19b74 | note | Controlling Documents - Chipsealing in NewZealand
b69c08c5-031b-5623-bc97-af8cbac67b16 | note | Acceptance Criteria - As per Chipping Guide
9c266ecd-d0d5-57ba-accd-4d664242b8b3 | note | Method - Record
098ca101-27fe-505f-9b53-136af639e401 | note | Frequency - Daily
abfc36db-dd2b-5bfc-ba0c-36228e5d74c5 | note | Responsible Person - Surfacing Supervisor
4d0e4b7d-4250-58f8-b0d4-4076acb3f816 | note | Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record
f4a33b29-374e-5300-9b4f-66b5d0056381 | note | Conduct - C
09687337-031b-586c-b511-1ec4448291d8 | note | Produce Record - C
e159137c-60c8-579a-a103-c3c548719234 | note | Approval - C
68ada6ea-c409-5b29-8d9a-7b35c045a4c0 | note | Inspection Point - Y
| checkpoint | Rolling
33f6e3b2-16ae-5765-879e-6e30c342a452 | note | Controlling Documents - Chipsealing in NewZealand
2a63052b-f8a3-534c-be66-3cd770233076 | note | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
d9b2d90c-2d2b-5e1d-98b7-e55b3b6f1759 | note | Method - Record
8355e729-6043-55f7-af3e-8af2900ec25b | note | Frequency - Per Site
842ffae2-cdb8-5eb1-a019-5046ba42b88d | note | Responsible Person - Surfacing Supervisor
c96729bf-1fa6-5a1e-95f6-1e081631d71e | note | Verifying Document - Chip Sealing Quality and Site Record
eae43be1-8bbb-524e-83a2-62f962ec9f63 | note | Conduct - C
7bda5f00-cf1f-5138-aa32-5c8a93241d0e | note | Produce Record - C
cf5ada43-8340-5543-a84e-1992b64a1850 | note | Approval - C
cf6116f5-2a52-56f2-a89b-bc459cc73b2b | note | Inspection Point - Y
| checkpoint | Cleanup
c477407a-2310-52c3-aa66-066127144e4e | note | Controlling Documents - Chipsealing in NewZealand
f68af6f1-1687-587a-8125-c90a7d18ad9b | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
081f40a5-f225-5fcb-a261-5be80f2e95ce | note | Method - Visual
51108bba-3e8d-578c-b1d2-88d474cfb54a | note | Frequency - Per Site
b6801172-9570-55a8-8467-c1c78c051e16 | note | Responsible Person - Surfacing Supervisor
64a18d98-bbd1-5b22-8d70-afffc74e5613 | note | Verifying Document - Chip Sealing Quality and Site Record
41b20a17-b83c-5573-b786-3a104e27ac98 | note | Conduct - C
d5b01be0-ac72-518d-b4b9-75090614347e | note | Produce Record - C
79de001a-6fd0-54ad-a535-684797d4d245 | note | Approval - C
4553033c-0bc1-5806-8a3f-b84682ab7f10 | note | Inspection Point - Y
| checkpoint | Removal of TTM
e45c417f-cea6-5861-a00e-b41d01718984 | note | Controlling Documents - TMP
d04b6c1c-ae97-5229-952c-ed931d184b85 | note | Acceptance Criteria - Comply with TMP
7918faf4-94c9-514c-85e1-587c81b934dd | note | Method - Record
cb6c1a7a-b56c-5e41-b17c-fefdf3dcced9 | note | Frequency - Per Site
b6534888-cd02-5bf2-a91c-27e0b42a86be | note | Responsible Person - STMS
a55bc835-63a0-5077-8e54-34d9327f7426 | note | Verifying Document - STMS Record
a50f5597-676e-510a-b6f5-a0a41f382b38 | note | Conduct - C
8b51e9ed-251c-5a5a-bb02-8f753a421eb2 | note | Produce Record - C
392f8363-22f0-5627-b7a9-06bd5a9c86fd | note | Approval - C
06a124d3-acf0-5a3e-a220-3762ac288d6c | note | Inspection Point - Y
| checkpoint | RAMM Data
4cb55e6a-558a-53b7-89ca-8d939da81b0b | note | Controlling Documents - RAMM Xcel
44f7535e-8780-5234-8db9-8bd3c2a11ed4 | note | Acceptance Criteria - Comply with NZTA format, contractor paid on completion of RAMM data
6493418e-e18b-5cb7-9f8b-117859c5e4cf | note | Method - Record
6f0077fe-c352-5635-8f1c-7d64c9d074ec | note | Frequency - Per Site
9fce32da-1d45-543e-b627-7e8ebedc6957 | note | Responsible Person - Project Manager
92762315-e2ec-5821-9d22-1bca6f08efc6 | note | Verifying Document - RAMM Xcel spreadsheet
7adad245-59b9-583c-867c-0750503cf0b6 | note | Conduct - C
a9a4ca36-07b4-59a2-9fdd-e8feaea83369 | note | Produce Record - C
ef84ae3f-6837-5773-ad4d-0966c7b78312 | note | Approval - C
f7a3f47f-304b-54e6-af47-87cc8f0ef6cc | note | Inspection Point - Y
| signoff | HOLD POINT
| checkpoint | Resurfacing Construction Completion report
cd6e0d65-7b76-5ab8-8c89-dc12a87a5c3b | note | Controlling Documents - NOC; MS 6.1.3
c4a1ae83-b040-597c-9a21-5e3c00fbabca | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
d31695b3-7b50-5294-9e1f-a5706ac2bbcc | note | Method - Record
ddb02557-73d9-545b-951c-1c2e7e534a32 | note | Frequency - Per Site
142cea19-eded-55ff-acfe-3b4409b39f5b | note | Responsible Person - Resurfacing Construction Completion report
846195cb-1e66-5e3f-bd5b-acbf2bca5da6 | note | Verifying Document - STMS Record
c990bb95-0381-58f5-baf6-229d88986e1b | note | Conduct - C
1ba724fc-d6b2-558b-a0ea-f22bae30c093 | note | Produce Record - C
a4e5a720-e936-50ac-ab55-8e3197ba7e9c | note | Approval - C
b8c311fe-14cd-5a28-87fa-52608bdcbb94 | note | Inspection Point - Y
| checkpoint | Chipseal Post-Verification Testing and Report
133ebc90-ac69-5ee6-b8c1-0bb92792bc37 | note | Controlling Documents - NOC; MS 6.1.3
d4308443-22d2-5e10-bfba-98d66726f62e | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
d395b461-c1f6-58a3-b89a-ae704903437a | note | Method - Record
11cd7c96-5822-55f3-a442-c7891debea95 | note | Frequency - Per Site
b2ada8f9-dd53-5443-a4c1-f77c676dc128 | note | Responsible Person - Surfacing Manager
e58f9b67-5745-535b-b669-ef5dfa14ec6e | note | Verifying Document - Chipseal Post-Verification Testing and Report
d3b2d7d4-1bed-5295-a5bb-c400d24de154 | note | Conduct - C
6378a66d-b221-5dfb-813d-af044a582f65 | note | Produce Record - C
4b47329b-7c80-57e5-a159-83cca4c3e62f | note | Approval - C
4533fce3-4a8a-5d8c-b93b-b127dc8ca762 | note | Inspection Point - Y
| checklist | Production and Testing ITPs |  | Production and Testing ITPs | 03ba6713-33d2-4f0e-8fee-0e534bf8e297
| checkpoint | Production and Testing ITPs
| checklist | QMP |  | QMP | d11d2615-699c-4242-a2e7-fdf176a2a6c6
| checkpoint | QMP
| checklist | Sign-off |  | Sign-off | 6a8e47a8-e2bf-4801-b1c0-cdc452c0496c
| checkpoint | Send sing-off below
| signoff | Sign-off
| checklist | Verified Program |  | Verified Program | 4031e91b-ef8c-473e-8e03-e3b98a769670
| checkpoint | Verified Program