## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | 5. TREC AWPT - Kaihiwi IV |  | 5. TREC AWPT - Kaihiwi IV
| section | Preliminary / Establishment
| checkpoint | Establish TTM
| note | Test Required - Visual Inspection
| note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
| note | Task Assigned To - STMS/Site Foreman
| note | Measuring Devices or Method - Visual
| note | Criteria - As per TMP and ensure TMC advised in advance of works.
| note | QA Form - Daily Diary
| checkpoint | Permits
| note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
| note | Test Required - Document Review
| note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
| note | Task Assigned To - Site Foreman
| note | Measuring Devices or Method - Visual
| note | Criteria - Obtain permits and mark outs prior to construction
| note | QA Form - Copy of Permit on site
| checkpoint | Clear-Shoulder and Side drain
| note | Test Required - Visual Inspection
| note | Task Assigned To - Project Engineers/Site Foreman
| note | Measuring Devices or Method - Visual
| note | QA Form - Daily Diary
| checkpoint | Digout Failed Areas
| note | Test Required - Visual Inspection
| note | Task Timing / Minimum Task Frequency - As Requested
| note | Task Assigned To - Project Engineers/Site Foreman
| note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
| note | Criteria - Backfill with Basecourse
| note | QA Form - Daily Diary
| section | Kerb Construction
| checkpoint | Basecourse layer construction (1)
| note | Specification Reference - TNZ B/2
| note | Test Required - Level and alignment
| note | Task Timing / Minimum Task Frequency - Every 20m
| note | Task Assigned To - Project Engineer
| checkpoint | Basecourse layer construction (2)
| note | Specification Reference - TNZ B/2
| note | Test Required - Compaction
| note | Task Timing / Minimum Task Frequency - Every 20m
| note | Task Assigned To - Project Engineer
| note | Criteria - 25min on the 4th drop
| note | QA Form - QA Measurement Sheet
| checkpoint | Kerbing
| note | Test Required - Set-out level and alignment
| note | Task Timing / Minimum Task Frequency - after base construction and prior to placement of concrete
| note | Measuring Devices or Method - survey check
| note | Criteria - Horizontal: ± 20mm, Vertical: ± 5mm
| checkpoint | Concrete Works
| note | Test Required - 20MPa
| note | Measuring Devices or Method - Copy of delivery docket
| note | Criteria - 20MPa, 28days
| section | Inspection Test Plan - In Situ Cement Stabilisation
| checkpoint | Cement for stabilisation
| note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
| note | Test Required - Certified in accordance with NZS 3122
| note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
| checkpoint | Production plan
| note | Specification Reference - NZTA B/5:2008, 7.2.2
| note | Task Timing / Minimum Task Frequency - 1 per site
| checkpoint | Stabilisation mix properties (including cement):
| note | – Maximum dry density (MDD)
| note | – Optimum water conent (OWC)
| note | – Solid density (SD)
| note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
| note | Test Required - Material properties for compaction verification
| note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
| note | Task Assigned To - Hold Point - Approval required by site engineer
| note | QA Form - QA Measurement Sheet
| signoff | HOLD POINT
| checkpoint | In-situ moisture content of existing pavement aggregate
| note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
| note | Test Required - In-situ moisture content Between 90% to 100% of OWC
| note | Task Timing / Minimum Task Frequency - As required
| note | Task Assigned To - Inspection - Lab
| note | QA Form - QA Measurement Sheet
| checkpoint | Top-up metal
| note | Specification Reference - TNZ M/4 Table 4
| note | Test Required - Placed to required depth and design levels
| note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
| note | Task Assigned To - Site Foreman
| note | QA Form - QA Measurement Sheet
| checkpoint | Cement spreading
| note | Specification Reference - NZTA B/5:2008, 7.3
| note | – Mat test (1m2 canvas mat)
| note | – Average usage test
| note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
| note | Task Timing / Minimum Task Frequency - Inspection & sign off by Site Supervisor
| note | Task Assigned To - Inspection & sign off by Site Supervisor
| note | QA Form - QA Measurement Sheet
| checkpoint | In-situ mixing - Cut depth
| note | Specification Reference - NZTA B/5:2008, 7.6.1
| note | Test Required - Maximum variation -5mm and +15mm
| note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
| note | Task Assigned To - Inspection & sign off by Site Supervisor
| note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
| note | Specification Reference - NZTA B/5:2008, 7.7.1 NZS 4402 Test 41.3
| note | Test Required - Plateau testing
| note | ○ Mean value ≥ 98% of MDD
| note | ○ Minimum value ≥ 95% of MDD
| note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
| note | Task Assigned To - Hold Point - Approval required by site engineer
| note | Measuring Devices or Method - Nuclear Densometer
| note | Criteria - Minimum value 95% of MDD
| note | QA Form - Test Reports
| signoff | HOLD POINT
| checkpoint | Surface shape
| note | Specification Reference - NZTA B/5:2008, 7.8
| note | Test Required - ≤10mm from 3-metre straight edge, No depression, Vertical variations -5 + 15mm
| note | Task Timing / Minimum Task Frequency - 20m intervals
| note | Task Assigned To - Inspection & sign off by Site Supervisor
| note | Measuring Devices or Method - Stringing, Tape measure
| note | QA Form - QA Measurement Sheet
| checkpoint | Crossfall
| note | Specification Reference - NZTA B/5:2008, 7.9
| note | Test Required - Not less than exisitng crossfall at the start of construction
| note | Task Timing / Minimum Task Frequency - 20m intervals
| note | Task Assigned To - Inspection & sign off by Site Supervisor
| note | Measuring Devices or Method - Stringing, Tape measure
| note | QA Form - QA Measurement Sheet
| checkpoint | Surface finish
| note | Specification Reference - NZTA B/5:2008, 7.10
| note | Test Required - See clause
| note | Task Timing / Minimum Task Frequency - 20m intervals
| note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
| note | Measuring Devices or Method - Visual
| signoff | HOLD POINT
| checkpoint-no-value | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
| checkpoint-no-value | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
| section | Chipseal Construction (NZTA P29)
| checkpoint | Ensure appropriate TMP used
| note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
| checkpoint | Seal design
| note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
| note | Task Assigned To - Project Engineer
| note | Criteria - Seal design to be reviewed prior to surfacing
| note | QA Form - Seal design template
| signoff | HOLD POINT
| checkpoint | Location/Size Confirmation
| note | Test Required - Mark up extent of chipseal
| note | Task Timing / Minimum Task Frequency - Prior to surfacing
| note | Task Assigned To - Project Engineer
| note | QA Form - Daily Diary
| checkpoint | Surface Cleanliness
| note | Test Required - Visual Inspection
| note | Task Timing / Minimum Task Frequency - Prior to application of binder
| note | Task Assigned To - Site Foreman
| note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
| note | QA Form - QA Measurement Sheet
| checkpoint | Plant Resource
| note | Test Required - Visual Inspection
| note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
| note | Task Assigned To - Site Foreman
| note | Measuring Devices or Method - Visual
| note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
| note | QA Form - Daily Diary
| checkpoint | Binder Application
| note | Test Required - Binder type, Cutback, Temp, Application rates
| note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
| note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
| note | Measuring Devices or Method - Visual
| note | Criteria - Binder Type = 180/200. Cutback to suit 1st coat seal 4pph kero max. Temp = 150deg celcius min, Application = Design l/m2, +/- 0.1 l/m2.
| note | QA Form - Bitumen Spray Sheets
| checkpoint | Chip Application
| note | Test Required - Chip type, Chip Application
| note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
| note | Task Assigned To - Site Foreman
| note | Measuring Devices or Method - Visual
| note | Criteria - Trucks loaded with correct chip.
| note | ○ Chip clean. (G4/6 Racked example)
| note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
| note | ○ G6 application = Enough to just fill the voids around the G4.
| note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
| note | Test Required - Visual
| note | Task Timing / Minimum Task Frequency - At completion of rolling
| note | Task Assigned To - Site Foreman
| note | Measuring Devices or Method - Visual
| note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
| note | QA Form - QA Measurement Sheet
| checkpoint | Site Measure
| note | Test Required - Record final site measure
| note | Task Timing / Minimum Task Frequency - Completion of works
| note | Task Assigned To - Site Foreman
| note | Measuring Devices or Method - Measuring Wheel or Tape
| note | Criteria - Sketch and record seal area and QA detail
| note | QA Form - QA Measurement Sheet
| checkpoint | Post Seal Care
| note | Test Required - Visual inspection
| note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
| note | Task Assigned To - Site Foreman
| note | Measuring Devices or Method - Visual
| note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
| note | QA Form - Daily Diary
| section | Chip Removal, Pavement Marking, Traffic Services
| checkpoint | Removal of excess chip
| note | Test Required - Visual Inspection
| note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
| note | Task Assigned To - Project Engineers/Site Foreman
| note | Measuring Devices or Method - Visual
| note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
| note | QA Form - Daily Diary
| checkpoint | Pavement Marking
| note | Test Required - Visual Inspection
| note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
| note | Task Assigned To - Project Engineers/Site Foreman
| note | Measuring Devices or Method - Visual
| note | Criteria - Linemarking must be completed within 48 hours of surfacing.
| note | QA Form - Daily Diary
| checkpoint | Removal of TTM
| note | Test Required - Visual Inspection
| note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
| note | Task Assigned To - Project Engineers/Site Foreman
| note | Measuring Devices or Method - Visual
| note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
| note | QA Form - Daily Diary
| checkpoint | Traffic Services
| note | Test Required - Visual Inspection
| note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
| note | Task Assigned To - Project Engineers/Site Foreman
| note | Measuring Devices or Method - Visual
| note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
| note | QA Form - Daily Diary