## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Usage Count | Resource Id
| checklist | 5. TREC AWPT - Kaihiwi IV |  | 5. TREC AWPT - Kaihiwi IV | 2
| section | Preliminary / Establishment
| checkpoint | Establish TTM
2346e8e4-c7fb-5b41-afb3-de1f177ed1e4 | note | Test Required - Visual Inspection
f9a34cc8-c9ba-5681-a603-e15c7c5155ca | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
07e3ffa5-c8cf-5127-bcfc-63ec4e00f690 | note | Task Assigned To - STMS/Site Foreman
04209cc9-5caa-59ee-b666-92f2bf7fdf2a | note | Measuring Devices or Method - Visual
4dec6e74-ebeb-50b7-bca2-dea1483513ee | note | Criteria - As per TMP and ensure TMC advised in advance of works.
e4a44636-9b69-5c5e-8c93-e20d144379df | note | QA Form - Daily Diary
| checkpoint | Permits
509533f9-3b95-58b6-b4eb-d1fa8bcdf108 | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
6100b311-96ca-5347-8af2-5e0874cc1c6b | note | Test Required - Document Review
8c5ab6e3-cb0c-5312-bbb8-fbcbc6e6c1ad | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
e9589a34-2639-519e-90ea-00243c515515 | note | Task Assigned To - Site Foreman
80e1c81a-78b1-5fa8-a80e-40ff6c0e947b | note | Measuring Devices or Method - Visual
9a0138bd-fcc2-58d9-8708-c26635d641b7 | note | Criteria - Obtain permits and mark outs prior to construction
1597436b-2d87-59af-b416-d94dcef3b74f | note | QA Form - Copy of Permit on site
| checkpoint | Clear-Shoulder and Side drain
c185533d-fe02-58cd-a94d-1c1d927f04e1 | note | Test Required - Visual Inspection
adab292e-d0d9-547d-911e-663da7cb4a7e | note | Task Assigned To - Project Engineers/Site Foreman
1d93f184-5cd0-5876-bf27-4e219c6b4363 | note | Measuring Devices or Method - Visual
8fdc9879-3a5d-5bc9-abc9-397a93012c78 | note | QA Form - Daily Diary
| checkpoint | Digout Failed Areas
542c5bf1-af60-5a0f-89c4-80341ec7fff6 | note | Test Required - Visual Inspection
eb8e03f7-c1de-59b2-ba83-a4aff1d458eb | note | Task Timing / Minimum Task Frequency - As Requested
cfa993b8-56f5-5892-91d3-f529435f083b | note | Task Assigned To - Project Engineers/Site Foreman
0029a368-4ffc-5af1-bcaa-d61790420b4c | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
62245261-9e82-548d-adcf-028af1f68616 | note | Criteria - Backfill with Basecourse
b0cb6e09-acd8-56c6-ab5d-a969f223a2c1 | note | QA Form - Daily Diary
| section | Kerb Construction
| checkpoint | Basecourse layer construction (1)
cbd2ae9b-cf39-5fbc-b12a-572dcd62e13d | note | Specification Reference - TNZ B/2
ec56ac65-d383-5114-bf16-bf8e84f16f34 | note | Test Required - Level and alignment
03e9df46-d636-5002-9146-3d94129a574d | note | Task Timing / Minimum Task Frequency - Every 20m
9f860395-61bc-5741-a9e9-9bbb1755fd56 | note | Task Assigned To - Project Engineer
| checkpoint | Basecourse layer construction (2)
90bed3eb-a7a8-5d11-b8bc-1d866efcfc1d | note | Specification Reference - TNZ B/2
f7f4e98a-e8a4-55d4-a319-5ec1fd84e00f | note | Test Required - Compaction
8b642a9c-6bbc-5571-876d-3f06e1de1d5a | note | Task Timing / Minimum Task Frequency - Every 20m
49cf0e39-5832-5064-8805-552293cf13ab | note | Task Assigned To - Project Engineer
4a538086-6376-5e1f-b304-f82ad24349ed | note | Criteria - 25min on the 4th drop
7a8305b8-1a33-5f8a-b93f-b06bf74eb759 | note | QA Form - QA Measurement Sheet
| checkpoint | Kerbing
34ec7e49-c2b6-5b22-a8b8-a03bf9c2c765 | note | Test Required - Set-out level and alignment
d7a18ae1-848c-5c04-8ecc-a945680dfafb | note | Task Timing / Minimum Task Frequency - after base construction and prior to placement of concrete
fca6f132-bd45-5fda-8e9c-d4e5968ee9d6 | note | Measuring Devices or Method - survey check
be0be355-1e13-5a55-bd0b-322f03a8d264 | note | Criteria - Horizontal: ± 20mm, Vertical: ± 5mm
| checkpoint | Concrete Works
40e92a8c-e40e-5e0f-9534-52c4cdba3fb8 | note | Test Required - 20MPa
1d9458b6-e634-5542-b965-66fb8c83adcc | note | Measuring Devices or Method - Copy of delivery docket
161cc415-cc80-52ab-8db6-3ad93b49631f | note | Criteria - 20MPa, 28days
| section | Inspection Test Plan - In Situ Cement Stabilisation
| checkpoint | Cement for stabilisation
2d3c0755-008f-58a2-9bb4-f4f9ca5547da | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
d05ae5b7-0350-5579-b20b-ac8fa1560a11 | note | Test Required - Certified in accordance with NZS 3122
a9cf6809-6da5-5861-8144-9b5af8f503a1 | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
| checkpoint | Production plan
3859bc1f-e976-5f94-8dd7-5bf8f6d16c6f | note | Specification Reference - NZTA B/5:2008, 7.2.2
bd00eeba-6c7f-59c8-8456-5470471fe6fa | note | Task Timing / Minimum Task Frequency - 1 per site
| checkpoint | Stabilisation mix properties (including cement):
932b13e7-c0af-5457-81e8-c5ae834749b6 | note | – Maximum dry density (MDD)
f16b471a-86ae-5ab9-98b1-962cb2b0701d | note | – Optimum water conent (OWC)
8a94ae39-86d0-5f40-9052-e0a2c6b2616c | note | – Solid density (SD)
333716e0-dc14-5610-b118-22f8ae7ad7f3 | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
43dae03b-b69e-5011-81a1-58dfdf2ca1b4 | note | Test Required - Material properties for compaction verification
5e5d5d19-bbb7-5f08-8582-81957852db6e | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
743feb28-8864-50ba-85b3-3c8e73a91513 | note | Task Assigned To - Hold Point - Approval required by site engineer
407d4ee8-3e8f-5c95-b7ee-67a59104574a | note | QA Form - QA Measurement Sheet
| signoff | HOLD POINT
| checkpoint | In-situ moisture content of existing pavement aggregate
33678cc3-f3b8-50b2-a1c3-5c708710d585 | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
1807703f-1866-5660-8a5f-eaf977f1e191 | note | Test Required - In-situ moisture content Between 90% to 100% of OWC
7f71072f-581a-5682-97ed-a15241f3be90 | note | Task Timing / Minimum Task Frequency - As required
df47c37d-d585-56ee-a7ee-33241209d343 | note | Task Assigned To - Inspection - Lab
d4252f1f-39aa-575e-9cb1-45f080d8f0f2 | note | QA Form - QA Measurement Sheet
| checkpoint | Top-up metal
e8c9707b-89e7-5ad6-8280-8636e3dce2d9 | note | Specification Reference - TNZ M/4 Table 4
1426a3a0-d141-593d-852d-1b5e53a408f0 | note | Test Required - Placed to required depth and design levels
82c97a50-690d-50b0-9f5e-bcbb8ed4940c | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
db47c239-9591-5f96-9a34-88d7f1c17c2b | note | Task Assigned To - Site Foreman
db3114ed-6acb-505f-9444-f0c45c45f63a | note | QA Form - QA Measurement Sheet
| checkpoint | Cement spreading
3b13c9f5-2af0-5c1e-be38-b41b9a4383c9 | note | Specification Reference - NZTA B/5:2008, 7.3
605f4392-2a1e-5a5d-96e7-fffb389ca39f | note | – Mat test (1m2 canvas mat)
c7695b9a-dc64-59c4-aed9-52bf2d60d3ef | note | – Average usage test
04aef123-aaab-5164-b65e-392646551efc | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
1e167dff-44ea-585b-86b5-b1c95bc2d46b | note | Task Timing / Minimum Task Frequency - Inspection & sign off by Site Supervisor
b62e5c1b-b233-5851-be6c-776632478cdd | note | Task Assigned To - Inspection & sign off by Site Supervisor
2662eafd-e94e-5c11-8547-b6010766428c | note | QA Form - QA Measurement Sheet
| checkpoint | In-situ mixing - Cut depth
d806b182-88cb-51a7-a807-da5ce03bd164 | note | Specification Reference - NZTA B/5:2008, 7.6.1
50bc4b34-dd24-598b-8958-63d6cea4e225 | note | Test Required - Maximum variation -5mm and +15mm
7f1b3697-1778-5d6e-b3d2-85fca075131c | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
bd591b59-1f93-5163-bbff-df869bc3ca9f | note | Task Assigned To - Inspection & sign off by Site Supervisor
f2661985-3f6b-5b29-ae64-523b8b4c8b77 | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
0963015f-c6c8-5e2c-9d47-fe16fbedc568 | note | Specification Reference - NZTA B/5:2008, 7.7.1 NZS 4402 Test 41.3
264eccbd-bbe2-5c73-9e5c-60a378c7299f | note | Test Required - Plateau testing
a200c8fa-bb86-5919-944c-68b58bf793ec | note | ○ Mean value ≥ 98% of MDD
fd1173c5-492f-5b28-b49f-71aa27bb6d51 | note | ○ Minimum value ≥ 95% of MDD
8e28baf1-0cab-55ff-8635-7eee6cf5e3a3 | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
e40d9ce9-b575-55dc-90a4-b1749351ef5d | note | Task Assigned To - Hold Point - Approval required by site engineer
b29fd211-211a-55a9-86da-a53f189fad03 | note | Measuring Devices or Method - Nuclear Densometer
532ff4da-7519-5d73-9ab7-ec93d7c9c5de | note | Criteria - Minimum value 95% of MDD
90f99efe-8590-5307-bcc7-66bbfa12e340 | note | QA Form - Test Reports
| signoff | HOLD POINT
| checkpoint | Surface shape
cbef2b1a-3a06-5102-9ded-0809a638a7c2 | note | Specification Reference - NZTA B/5:2008, 7.8
a30a3ce0-677f-537f-bda1-7fda4160df2b | note | Test Required - ≤10mm from 3-metre straight edge, No depression, Vertical variations -5 + 15mm
88e919b1-f8ba-54fd-a888-274293d4e6e9 | note | Task Timing / Minimum Task Frequency - 20m intervals
644c7dfc-9195-5f85-a6ff-7a5e1bb09a75 | note | Task Assigned To - Inspection & sign off by Site Supervisor
b54f7e08-4ea3-557f-bd03-eac8610fef71 | note | Measuring Devices or Method - Stringing, Tape measure
ffe779a9-99cd-5bf8-8472-f0249a46cad7 | note | QA Form - QA Measurement Sheet
| checkpoint | Crossfall
56d3a123-4161-5321-ae4d-1b0722f0df1d | note | Specification Reference - NZTA B/5:2008, 7.9
5c16cecf-20e4-57e8-8a97-d2ad01f98496 | note | Test Required - Not less than exisitng crossfall at the start of construction
b5cfe9fe-dae2-5865-97a7-33c1b9b94e57 | note | Task Timing / Minimum Task Frequency - 20m intervals
864b1392-84a9-5295-9be9-6a6819350b7b | note | Task Assigned To - Inspection & sign off by Site Supervisor
7e5dd190-566c-5c05-a0d7-019959ae9be6 | note | Measuring Devices or Method - Stringing, Tape measure
8159318d-6ba1-5315-9088-7a37f023a107 | note | QA Form - QA Measurement Sheet
| checkpoint | Surface finish
38de163d-1adf-5aeb-9601-62e4c045a1d1 | note | Specification Reference - NZTA B/5:2008, 7.10
bebc45cc-f73d-5107-8442-c5d617de3ba3 | note | Test Required - See clause
a548da74-2fe1-5fd2-87ea-4e8f18a3d9fc | note | Task Timing / Minimum Task Frequency - 20m intervals
19ad890b-bf15-52bb-87b1-bd2a9040111e | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
a505d190-1e43-55a9-be24-a481eed833a5 | note | Measuring Devices or Method - Visual
| signoff | HOLD POINT
| checkpoint-no-value | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
| checkpoint-no-value | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
| section | Chipseal Construction (NZTA P29)
| checkpoint | Ensure appropriate TMP used
b5df889d-6ce7-591a-aefa-a3e8fe3973cd | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
| checkpoint | Seal design
932f78d5-11dd-58cb-a65f-5e14597bee16 | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
aec675aa-e450-56bc-bab2-5a1b4d34ebb9 | note | Task Assigned To - Project Engineer
023c01b3-ffcb-5770-ab2b-a9aaa3925bed | note | Criteria - Seal design to be reviewed prior to surfacing
1ef0ddc2-320a-56a8-9cbb-b5f49e6bbc88 | note | QA Form - Seal design template
| signoff | HOLD POINT
| checkpoint | Location/Size Confirmation
d815ab07-9ee0-57ac-b2c8-a4f1e3b8c151 | note | Test Required - Mark up extent of chipseal
4cf920f9-921b-54f1-a481-78a2ae40a1b1 | note | Task Timing / Minimum Task Frequency - Prior to surfacing
35a49727-7162-5d88-a243-1d49f005e998 | note | Task Assigned To - Project Engineer
f5b201e2-2644-57aa-8d6f-cb5507ac7ff1 | note | QA Form - Daily Diary
| checkpoint | Surface Cleanliness
eb53f897-d775-5f8c-b95d-40029d97f96f | note | Test Required - Visual Inspection
a852a750-81b1-5a2f-9b36-9c6de2487139 | note | Task Timing / Minimum Task Frequency - Prior to application of binder
8d226232-5668-50bd-a8ac-d7d8f45f8fe0 | note | Task Assigned To - Site Foreman
21a2187a-1740-58fe-8e17-bb780e4640f6 | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
7df651f5-6a55-5ca5-a9b4-29abaaa8bcae | note | QA Form - QA Measurement Sheet
| checkpoint | Plant Resource
36a1f0d3-39c9-58c2-88bf-656a3454280b | note | Test Required - Visual Inspection
7fcc09ff-cb36-5db2-b95d-0df375a1c799 | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
25b9b0d9-16be-5d66-8aee-c2920a3c8a55 | note | Task Assigned To - Site Foreman
23913796-c0ea-5bc5-aeb0-26e656a04c3a | note | Measuring Devices or Method - Visual
0d405182-a9cb-57b7-a008-ac19e0ba68e6 | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
0683dd3f-7464-5ca8-8edd-f7eae01955f9 | note | QA Form - Daily Diary
| checkpoint | Binder Application
0bd41cc1-45c3-5396-9663-4a48d9037b4b | note | Test Required - Binder type, Cutback, Temp, Application rates
3392ddaa-0b9e-53e5-8149-c15b6b398139 | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
bd24ee15-4c32-5fde-8e2f-f894d5722994 | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
ffd31dcb-4912-5924-a1c8-0df92da3cacb | note | Measuring Devices or Method - Visual
8692977a-4c6b-5d04-abaa-460168dd7876 | note | Criteria - Binder Type = 180/200. Cutback to suit 1st coat seal 4pph kero max. Temp = 150deg celcius min, Application = Design l/m2, +/- 0.1 l/m2.
16d2a7b7-8e33-5c13-9d9a-c32528cf4d43 | note | QA Form - Bitumen Spray Sheets
| checkpoint | Chip Application
82d0a6ea-e3b3-5da3-954b-82abfc2522f0 | note | Test Required - Chip type, Chip Application
69cdf642-1788-50bf-ac68-8a40ce8b2c8b | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
79ab55ac-3b00-532d-9314-5215bfa964df | note | Task Assigned To - Site Foreman
8b3a75d0-c2fb-56cf-bc8e-304ad7e499b5 | note | Measuring Devices or Method - Visual
96354846-e730-55cd-b35f-906cb3f1c3ad | note | Criteria - Trucks loaded with correct chip.
98cc0c9b-7ae5-5501-9bc7-231749971228 | note | ○ Chip clean. (G4/6 Racked example)
89e5234d-1ea3-5882-8859-abe4e6b6fbe7 | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
763345c1-c5f9-5dd9-ae90-e05929715cdc | note | ○ G6 application = Enough to just fill the voids around the G4.
09ec7806-0258-5de2-8a6e-e7e9ae5c8cbb | note | QA Form - QA Measurement Sheet
| checkpoint | Compaction
d88dfdab-b3ed-5541-b141-3d86d767ac58 | note | Test Required - Visual
1a591eca-fd2e-5c83-9149-53497430cb3c | note | Task Timing / Minimum Task Frequency - At completion of rolling
7bb589fb-095f-55ad-8393-b45258e0324e | note | Task Assigned To - Site Foreman
4dd35467-3e80-5343-b2d8-4bacce5c2fef | note | Measuring Devices or Method - Visual
84fb1976-59e4-582a-9a77-6d1dcda63b88 | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
28ab5d1f-ce52-56c8-aa81-b66130d2fb8a | note | QA Form - QA Measurement Sheet
| checkpoint | Site Measure
2521a57a-066e-5e33-969f-a6e5001b2537 | note | Test Required - Record final site measure
e8ce2965-dc27-5ffb-8592-c8ff649dcb7e | note | Task Timing / Minimum Task Frequency - Completion of works
3244e567-6cb1-5dd7-ada6-54adbe6e2326 | note | Task Assigned To - Site Foreman
bd32e130-b935-51ef-a226-9e7e47911732 | note | Measuring Devices or Method - Measuring Wheel or Tape
d863103d-da95-5365-85b6-a18b80f13f72 | note | Criteria - Sketch and record seal area and QA detail
16d0b647-9476-58e8-b788-f76385b1f6e0 | note | QA Form - QA Measurement Sheet
| checkpoint | Post Seal Care
a63f63eb-ec6c-5ade-93b4-5b3e6bf7bf58 | note | Test Required - Visual inspection
de203a03-4f85-56f3-925f-45e40a72d315 | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
ee5c2a90-ea46-58b4-af05-2863fbd33f8a | note | Task Assigned To - Site Foreman
33d4803a-ebb4-5e6b-bf8a-2ad08135573c | note | Measuring Devices or Method - Visual
5368a926-78e2-5167-88b4-74fada5fd994 | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
cd4e02cc-2c48-5f42-a9ac-d5ce5523570a | note | QA Form - Daily Diary
| section | Chip Removal, Pavement Marking, Traffic Services
| checkpoint | Removal of excess chip
72b3381f-1a06-5a86-ae48-207cddff1906 | note | Test Required - Visual Inspection
08c61188-cb2d-5351-bdca-61137efa4bdc | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
4b98b978-1df2-5d77-ac5d-6af3b7723222 | note | Task Assigned To - Project Engineers/Site Foreman
650563e2-d19c-5c1c-87dc-48520a10c474 | note | Measuring Devices or Method - Visual
be0399f1-514b-50f2-bfe4-fce800aab142 | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
4d449fbb-f0bd-5506-9146-9ab81755b85a | note | QA Form - Daily Diary
| checkpoint | Pavement Marking
e916876f-24f9-5c73-a6ea-19f238d117fb | note | Test Required - Visual Inspection
7916175f-93b6-5b99-beb3-8185f5e9dedc | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
fa1e8f6d-2638-50ea-bfab-49655da2cd04 | note | Task Assigned To - Project Engineers/Site Foreman
6c497c2d-0772-5af7-8e50-0654b7a60472 | note | Measuring Devices or Method - Visual
a696641e-9ce4-5f74-a8d7-61ee0992c715 | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
00afd4a4-f0d8-5b7e-93af-de89d9e57f9a | note | QA Form - Daily Diary
| checkpoint | Removal of TTM
dabee641-5b3c-5133-be2a-6e62601a55f3 | note | Test Required - Visual Inspection
36ebfc46-e74e-533f-896e-badec09d4f3b | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
2814bb41-d20e-5753-a29b-ee808efb0214 | note | Task Assigned To - Project Engineers/Site Foreman
3bb7b767-1710-5c67-9744-27d9a10e9c9c | note | Measuring Devices or Method - Visual
f2ae9bb6-2811-54ff-890c-be5cff4704c8 | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
13842ba9-e3e2-5868-9a87-05bf259d6820 | note | QA Form - Daily Diary
| checkpoint | Traffic Services
e2784b90-dd4b-5be3-8e61-da315cadb3d0 | note | Test Required - Visual Inspection
f706ad98-3802-5b2b-a510-c180c43675c5 | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
f9f87f9f-9006-555f-8edb-c7b42acc8ef8 | note | Task Assigned To - Project Engineers/Site Foreman
cc2cb8dc-66ac-50cb-9b30-05399192bfe9 | note | Measuring Devices or Method - Visual
be518738-34e4-58d9-b66a-819507f2b14b | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
28066207-6c35-5856-8759-825ad8bfa8a1 | note | QA Form - Daily Diary