## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | INF-HSEQ CC0398-ITP-003 Base Pavement Construction Rev 1 | itp | INF-HSEQ CC0398-ITP-003 Base Pavement Construction Rev 1 |  | c2d50d7f-6b8c-4b90-9a2a-f936795b5260
| section | 1.0 Preliminaries
| checkpoint | 1.1 - Determine lot size
6501d8b1-cb43-5bdf-9dd5-67d2dba00fa2 | note | Ref docs - 235929-000-CV-SP-002
8f839c3d-0f6f-57fd-ba40-2524e8f064c0 | note | Acceptance criteria - Lot sizes is determined by the lesser of: One day’s production or 4000m2
5b2bd2ef-3e75-540d-8649-4edd104a0c67 | textbox | Acceptance |  |  | m2
cca7cbfa-c2a2-5d83-aafb-5efa18c67deb | note | Maximum lot size = 4000m2
54c4c5c8-e11c-59fa-87eb-3fd3e9d0f909 | note | Key - S
43d09c37-555c-5265-aaf5-711e3df335c7 | note | VIVA - S
26acb492-9acd-5d06-9f7a-caaa1143b6cb | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
5f18f051-a676-5e3f-ba60-44534e570e48 | tickbox | Lot Mark-Up
| checkpoint | 1.2 - Survey set-out
e8633a6d-758b-59ef-888f-cfbd143e64c6 | note | Ref docs - IFC Drawings
8aa7e653-16c3-56d5-a513-2a0363d44dbf | note | Acceptance criteria - Is the work area clearly pegged out for line and level?
0cf98971-5246-5cfd-bb65-0aeee80bd42a | button | Acceptance | Yes,No,N/A
f05c6e9a-36fd-54f4-9394-97ae24b54482 | note | Key - W
80487666-1cd6-59d5-9be7-ddf3c4831cbf | note | VIVA - S
| checkpoint | 1.3 - Material classification and source
c8bdf585-db77-5229-bb64-061071d89421 | note | Ref docs - 235929-000-CV-SP-002
e7cdf885-173b-58de-9df0-d8f3b7831e41 | note | Acceptance criteria - Has the nominated materials been approved for use on the project?
de56d295-db70-5412-bccf-81f55a7a0d9e | button | Acceptance | Yes,No,N/A
09c71a68-3758-568f-9a6d-6c9c77bb59ac | note | Key - H
da0fb1c6-15c0-5f0d-b6cd-10bfcd11bd24 | note | VIVA - H
50b1f835-aba7-5703-b6c1-ad3b1bee2549 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
0b95c8ae-2a21-58f2-83fd-e8a8b36dcac9 | tickbox | iDocs Approval Document
a0b6986c-2be2-535f-9125-dee4d5976015 | textbox | iDocs Number
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 Conformance of previous layer
| checkpoint | 2.1 - Conformance of previous layer
81e0e4e3-8ddc-5612-87a0-8bea0288a50d | note | Acceptance criteria - Has the previous layer passed acceptance criteria?
b612900e-50a7-53c2-9c3e-25418ac21c1e | button | Acceptance | Yes,No,N/A
20018853-84de-5729-a379-0079ffd0af5d | note | Key - H
7189376a-d627-5626-ac23-398505e4b612 | note | VIVA - H
69de0e78-36f8-56fa-8320-0efe083ebfcc | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
1dfb806b-055f-532e-a775-2f5f663def65 | tickbox | ITP Number
| signoff | AUTHORITY HOLDPOINT
| checkpoint-no-value | Type of Pavement:
92c74975-23d8-5dba-ac9b-cfbc0807f4fd | note | ○ For Crushed Rock Placement Below Concrete Pavement Refer to Section 3.0
bb8147f6-6b95-58d6-9639-45561ac2fbe2 | note | ○ For Crushed Rock Placement for Gravel Pavement Refer to Section 4.0
6f7016fe-c9ef-5f8e-96f6-14ac56a767c4 | note | ○ If multiple pavement types exist please complete as applicable
fa1f7190-e811-5ac9-aa81-8394c776142d | note | ○ Please strikeout not applicable sections
| section | 3.0 Crushed Rock Placement Below Concrete Paving
| checkpoint | 3.1 - Placement
01389caa-4b1a-5fa6-bc77-a97e7bfdaf7c | note | Ref docs - IFC Drawings 235929-000-CV-SP-002
eedb55a1-590d-5c8e-bd12-a9b3399987a2 | note | Acceptance criteria - Has Class 2 Crushed Rock been placed to be a minimum of 250mm Thick as per IFC Drawings?
49a7d8d8-0a74-59b1-a156-b8b99f0eca12 | note | ○ Crushed Rock Layers must not exceed 250mm thick lifts if additional Crushed Rock is required.
aa11b76c-a823-5d46-b72f-3ab49ffe384d | button | Acceptance | Yes,No,N/A
13d22732-d375-567f-ae22-91ec50f1151b | note | Key - S
d33cfb8c-8769-50e6-b2c3-6b5e9d1a63ec | note | VIVA - S
| checkpoint | 3.2 - Moisture
35ca5b69-0a83-52dd-90db-9a5dd46b3dcf | note | Ref docs - IFC Drawings 235929-000-CV-SP-002
d36c6c8c-68d5-5902-a3df-69c08681e1ac | note | Acceptance criteria - Has the material maintained at optimum moisture content (>85%), with additional water being added if required during compaction?
56384fb5-6c00-5e73-9829-9bc53e2d806e | button | Acceptance | Yes,No,N/A
d9a60ee9-b6a9-5faf-94b2-132f3ffa344e | note | Key - S
dfbb937b-ae3c-5a8e-b34e-c057068ebd28 | note | VIVA - S
| checkpoint | 3.3 - Compaction
6f254900-fcbe-5d4b-8fd3-ef732cce8350 | note | Ref docs - IFC Drawings 235929-000-CV-SP-002
| note | ○ DoT 304.09
| note | ○ DoT 304.11
| note | ○ DoT 304.121
b13d3546-2115-5f3d-a10f-5ad32e2d15eb | note | Acceptance criteria - Compaction Testing is to be completed at 3 tests per lot to the below requirements:
9e51b6f7-df24-5291-853d-8e637d5708dd | note | ○ 98% MDD
777dfafa-dd95-5ab7-84cf-43a2ea10dcb4 | note | ○ +-3% of Modified Moisture Content
d4759b59-4e66-559e-8bf6-e84562d8c480 | note | – If testing of the first 3 consecutive lots have achieved the above requirements testing is to be reduced to testing per 2 lots until such time that a lot fails to meet the specified requirements.
fc38b74e-a939-5072-bb4d-f2930e7803e7 | button | Acceptance | Yes,No,N/A
3caeb15a-4034-5a12-9768-059f494dea8f | note | Key - H
cc0b4ae2-f2cb-50c8-9a1f-3885365cab1b | note | VIVA - S
15b9e5e0-0d48-574a-8e61-7d86ed4b494d | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
ced06147-f3a9-5f5e-8a88-a800e350c339 | tickbox | Compaction test reports
| checkpoint | 3.5 - Test rolling
8417ed8f-2d33-52ef-a780-bd97adf43f18 | note | Ref docs - IFC Drawings 235929-000-CV-SP-002
a8f60c05-766d-5571-addc-cbcb1fc24664 | note | Acceptance criteria - Does the layer withstand test rolling without visible deformation?
e3bad8fa-53d1-560a-af29-9e43dcc80a08 | textbox | List attendees:
96a4c8b6-a202-5e3e-a455-8cf8a1489620 | button | Acceptance | Yes,No,N/A
9121f4ae-077d-5192-9de9-8264c6fc4043 | note | If ‘no’ please see below
60e4dcc6-7e37-5a9a-8641-39b5671cd033 | note | If ‘yes’ please proceed
dd985b01-e537-5220-bc7c-0a7c3b8bebe5 | note | Key - H
f612c7e6-fcca-5810-a8f0-6ec9ace8f618 | note | VIVA - W
3d64c171-4402-579f-80a6-972f4c57472a | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
823e135f-1efe-55b0-add1-ccb87dbe91b1 | tickbox | Proof Roll Sheet
| checkpoint | 3.6 - Identification of soft wet or unstable material
97ec0340-9dee-5e5e-b847-719c46b8fabb | note | Ref docs - IFC Drawings 235929-000-CV-SP-002
bb6b736c-dcf1-52ac-8f40-6f3784b729f9 | note | Acceptance criteria - What quantity of soft, wet or unstable material is present?
9d156093-5a40-585f-813e-1c1b080e35b6 | button | Acceptance | Yes,No,N/A
e576fcb6-bb54-5c0f-8724-31107bfd1a20 | textbox
4cde47f5-e32c-561b-b519-d786462843ab | note | Key - H
711c6f8c-97d8-5f7f-aed0-21b69f7e8ea8 | note | VIVA - W
| checkpoint | 3.7 - Treatment of unsuitable material
7cee4b29-d1cb-58e1-8c35-56348ddcbb6c | note | Ref docs - IFC Drawings 235929-000-CV-SP-002
99bdd0a0-8ccf-522e-94f1-0e32eeec3810 | note | Acceptance criteria - Has the nominated soft/wet spot been rectified by a remove and replace method?
64a62daa-c37e-54dd-b280-2dd59e017376 | button | Acceptance | Yes,No,N/A
45041a27-b536-5253-abd1-fa5e6a8ccc1e | note | Key - H
ac86a90b-0949-513b-8285-c65a5a3f4e25 | note | VIVA - W
| checkpoint | 3.8 - Placement of Polythene Membrane
d828a38b-e40c-5ade-94aa-c9a127b199e4 | note | Ref docs - IFC Drawings
c5623489-4e10-5d5e-abbc-4fd16d806e60 | note | Acceptance criteria - Has the Polythene Membrane been installed above the completed Crushed Rock layer?
cf22dba4-bc72-5cf7-b78c-84e43e394556 | button | Acceptance | Yes,No,N/A
7ba0d442-51ce-5efd-8ef4-30b7ca7ed19d | note | Key - S
e4125fc3-a679-5ef3-aa19-0754b7f8a6c9 | note | VIVA - S
| section | 4.0 Crushed Rock Paving
| checkpoint | 4.1 - Placement of Geogrid
0dfc6fcf-b3d8-54cb-be50-3a61746a69f7 | note | Ref docs - IFC Drawings
6f887263-f3e7-51de-b4bc-4c53f829ef5d | note | Acceptance criteria - Has Geogrid been installed where non-paved areas have been excavated?
6add77c9-adf0-5e59-8097-b90ed6bf983e | button | Acceptance | Yes,No,N/A
e9c174ad-573b-5fa3-84ff-93dea5f41103 | note | Key - W
b1571a35-8fd3-55ca-8946-26ccf49e833f | note | VIVA - S
0de21b6f-e82a-575c-aefb-940a38bbfcfa | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
f3ff3c71-43a1-54e0-8bdb-05d75404f2e3 | tickbox | Material Approval
| checkpoint | 4.2 - Placement of Crushed Rock
a903b078-bc18-51df-b13c-98e9eaabc123 | note | Ref docs - IFC Drawings 235929-000-CV-SP-002
d72fa877-9882-5c97-bf6e-e26e10174d14 | note | Acceptance criteria - Has 20mm Class 3 Crushed Rock been placed to be 400mm thick?
853dda95-b172-5def-a1dc-8a3763e8c205 | note | ○ Crushed Rock Layers must not exceed 250mm thick
5a401019-1e96-5ec9-af57-9ee3a4591000 | button | Acceptance | Yes,No,N/A
cd392d81-4008-5da9-9916-cc3bdabb4f79 | note | Key - S
fa358042-4cbf-5c10-91c1-e7292a11b583 | note | VIVA - S
| checkpoint | 4.3 - Moisture
2331b14f-f1d0-57ed-870e-6dbaa9f9ee1a | note | Ref docs - IFC Drawings 235929-000-CV-SP-002
43495157-14fb-57dd-940e-3c1945e4c980 | note | Acceptance criteria - Has the material maintained at optimum moisture content (>85%), with additional water being added if required during compaction?
6ec08d96-7bff-5e62-9518-0224f15059c6 | button | Acceptance | Yes,No,N/A
6c99e8bd-c06d-578b-be29-711ddc8e0327 | note | Key - S
156e0296-e4be-5c66-b962-6dbc51d53533 | note | VIVA - S
| checkpoint | 4.4 - Compaction
429d6bce-33c6-59a5-8d64-2ad478c6f108 | note | Ref docs - IFC Drawings 235929-000-CV-SP-002
| note | ○ DoT 304.09
| note | ○ DoT 304.11
| note | ○ DoT 304.121
d3209243-9c30-5573-a1c7-30fafcce5b85 | note | Acceptance criteria - Compaction Testing is to be completed at 3 tests per lot to the below requirements:
89d3e070-4413-528d-a4ab-06f872de98b9 | note | ○ 100% Standard Compaction
7d6e1f91-a934-5645-955d-5a669e035a9e | note | ○ +-3% of Modified Moisture Content
cae85642-5db5-5937-8890-cff42144a5c2 | note | If testing of the first 3 consecutive lots have achieved the above requirements testing is to be reduced to testing per 2 lots until such time that a lot fails to meet the specified requirements.
077a6c37-c1ca-518a-a2fe-3f5d83345928 | button | Acceptance | Yes,No,N/A
bbc07bbe-5011-5668-b581-002833c721dc | note | Key - H
5e43bae2-a18c-5b73-802c-99b64fe06a10 | note | VIVA - S
31de37d4-20c8-5b82-ac43-255a2389f771 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
2ab9353d-83ac-5c89-8b8b-fff09aebef9c | tickbox | Compaction test reports
| checkpoint | 4.5 - Test rolling
97553362-56f8-5ff2-96e9-adceb75265b9 | note | Ref docs - IFC Drawings 235929-000-CV-SP-002
e2b50d78-d3a3-5c10-8da2-5bbaef359853 | note | Acceptance criteria - Does the layer withstand test rolling without visible deformation?
73e1ee2b-08c7-59b8-8150-983da127d3d2 | textbox | List attendees:
9ed16321-b204-5483-84c0-64512d1e5bb4 | button | Acceptance | Yes,No,N/A
d94bbfa0-63bf-5cb6-84b5-b96884759f4e | note | If ‘no’ please see below
99f6596e-bfaa-57ed-976b-bf8607a2d7da | note | If ‘yes’ please proceed
b404bfbf-5950-599a-85c1-593556c3903a | note | Key - H
92ec5bda-49ea-54a3-997a-d6a6a08fec5c | note | VIVA - W
b44fcef6-f2ee-5175-8a9e-11575b2a3639 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
88894f45-536d-5d61-9345-5e915faf41f9 | tickbox | Proof Roll Sheet
| checkpoint | 4.6 - Identification of soft wet or unstable material
d9af96d1-8e5a-5322-b353-453a3f02f9b6 | note | Ref docs - IFC Drawings 235929-000-CV-SP-002
49f6f314-8b5e-5f7f-a09d-2ea51e17b811 | note | Acceptance criteria - What quantity of soft, wet or unstable material is present?
57d94117-c5d9-5bab-9a31-aedeb125c5ff | textbox | Acceptance |  |  | m2
2dc07789-628d-5968-8330-be11e9005f8e | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
14f24b55-a5a3-5dec-bcae-aeeaa06a36b3 | tickbox | Photos
| checkpoint | 4.7 - Treatment of unsuitable material
7e103013-e4ba-5867-b406-eb6bdcf54080 | note | Ref docs - IFC Drawings 235929-000-CV-SP-002
8b850234-8a5d-5309-94cb-d3464137601c | note | Acceptance criteria - Has the nominated soft/wet spot been rectified by a remove and replace method?
cd5e9e8a-b263-5276-817a-74fadbaa2bd3 | button | Acceptance | Yes,No,N/A
e0c726a2-a991-5162-a318-691e492d7a7e | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
e99da963-0e22-5ffe-b518-56c61c6bc0b1 | tickbox | Proof Roll Sheet
| section | 5.0 Conformance check
| checkpoint | 5.1 - Pavement finish
e3602dc3-74e4-5984-a2d1-dc831e4cf811 | note | Ref docs - IFC Drawings 235929-000-CV-SP-002
5ae04c9c-9fe2-5dab-9a1f-ccbd33dd9cbf | note | Acceptance criteria - Has the crushed rock layer been finished to a smooth and uniform surface?
cc0f4e16-2509-583f-9afe-298f60b0c4e7 | button | Acceptance | Yes,No,N/A
2717a8ab-24fb-5764-8c65-53db17151273 | note | Key - W
| checkpoint | 5.2 - Surface level of pavement courses
053d23a8-26a5-5bff-87cd-6177a5936e8f | note | Ref docs - IFC Drawings 235929-000-CV-SP-002
52c172d6-67d7-5bb0-95e7-f4602e1d0206 | note | Acceptance criteria - Has the prepared layer been surveyed in accordance with and verifying specified requirements?
b56f3ef5-c7f8-51f5-8117-6ae41b140ee4 | note | ○ Tolerance: +-15mm
fbe17cc5-0a4e-58f6-8614-779e62dcaadb | button | Acceptance | Yes,No,N/A
6ecc219a-e6f4-5a30-bc48-062c3d1071c0 | note | Key - H
563af117-9dcf-54aa-b1e7-1c84bd60befc | note | VIVA - H
26c1a71c-e3c7-54f6-8619-3035514505c5 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
8128f3ee-2a3d-56f1-9e6a-fb0a34a30417 | tickbox | As built reports
| signoff | AUTHORITY HOLDPOINT