## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Box Gutter Installation | [5 empty] | Roof - Zone 1 / Roof 3 - Box Gutter Installation Checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | Syphonic Outlet
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Fix only Syphonic Outlet
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Roof - Zone 1 / Roof 3 - Insulation Checklist
section | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof - Zone 1 / Roof 3 - Roof Installation Checklist
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Roof - Zone 1 / Roof 3 - Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Parapet Wall Cladding | [5 empty] | Roof - Zone 1 / Roof 3 - Parapet Wall Cladding Checklist
section | Material Inspection
checkpoint | Wall Cladding - 50mm ASKIN panel Parapet lining
checkpoint | Top hat support: 0.75mm Top Hat
checkpoint | Flashing Material: 0.61mm Colorbond Ultra Matt
section | Installation
checkpoint | Insulated Panel Wall Cladding - Butyl Tape to Side, Top, and Bottom
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
checklist | Roof Penetrations | [5 empty] | Roof - Zone 1 / Roof 3 - Roof Penetrations Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
text | Client Representative:
checklist | Box Gutter Installation | [5 empty] | Roof - Zone 2 / Roof 4 - Box Gutter Installation Checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | Syphonic Outlet
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Deletion of Valley Gutter replace with Apron & Soaker
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Roof - Zone 2 / Roof 4 - Insulation Checklist
section | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof - Zone 2 / Roof 4 - Roof Installation Checklist
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Roof - Zone 2 / Roof 4 - Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Parapet Wall Cladding | [5 empty] | Roof - Zone 2 / Roof 4 - Parapet Wall Cladding Checklist
section | Material Inspection
checkpoint | Wall Cladding - 50mm ASKIN panel Parapet lining
checkpoint | Top hat support: 0.75mm Top Hat
checkpoint | Flashing Material: 0.61mm Colorbond Ultra Matt
section | Installation
checkpoint | Insulated Panel Wall Cladding - Butyl Tape to Side, Top, and Bottom
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations | [5 empty] | Roof - Zone 2 / Roof 4 - Roof Penetrations Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
text | Client Representative:
checklist | Box Gutter Installation | [5 empty] | Roof - Zone 3 / Roof 1 - Box Gutter Installation Checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | Syphonic Outlet
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Deletion of Valley Gutter replace with Apron & Soaker
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Roof - Zone 3 / Roof 1 - Insulation Checklist
section | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof - Zone 3 / Roof 1 - Roof Installation Checklist
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Roof - Zone 3 / Roof 1 - Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Parapet Wall Cladding | [5 empty] | Roof - Zone 3 / Roof 1 - Parapet Wall Cladding Checklist
section | Material Inspection
checkpoint | Wall Cladding - 50mm ASKIN panel Parapet lining
checkpoint | Top hat support: 0.75mm Top Hat
checkpoint | Flashing Material: 0.61mm Colorbond Ultra Matt
section | Installation
checkpoint | Insulated Panel Wall Cladding - Butyl Tape to Side, Top, and Bottom
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations | [5 empty] | Roof - Zone 3 / Roof 1 - Roof Penetrations Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
text | Client Representative:
checklist | Box Gutter Installation | [5 empty] | Roof - Zone 3 / Roof 2 - Box Gutter Installation Checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | Syphonic Outlet
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Deletion of Valley Gutter replace with Apron & Soaker
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Roof - Zone 3 / Roof 2 - Insulation Checklist
section | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof - Zone 3 / Roof 2 - Roof Installation Checklist
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Roof - Zone 3 / Roof 2 - Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Parapet Wall Cladding | [5 empty] | Roof - Zone 3 / Roof 2 - Parapet Wall Cladding Checklist
section | Material Inspection
checkpoint | Wall Cladding - 50mm ASKIN panel Parapet lining
checkpoint | Top hat support: 0.75mm Top Hat
checkpoint | Flashing Material: 0.61mm Colorbond Ultra Matt
section | Installation
checkpoint | Insulated Panel Wall Cladding - Butyl Tape to Side, Top, and Bottom
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations | [5 empty] | Roof - Zone 3 / Roof 2 - Roof Penetrations Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
text | Client Representative:
checklist | Box Gutter Installation | [5 empty] | Roof - Zone 4 / Roof 5 - Box Gutter Installation Checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | Syphonic Outlet
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
checkpoint | Soaker Gutter
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Deletion of Valley Gutter replace with Apron & Soaker
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Roof - Zone 4 / Roof 5 - Insulation Checklist
section | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof - Zone 4 / Roof 5 - Roof Installation Checklist
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Roof - Zone 4 / Roof 5 - Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations | [5 empty] | Roof - Zone 4 / Roof 5 - Roof Penetrations Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation | [5 empty] | Roof - Zone 4 / Roof 6 - Box Gutter Installation Checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | Syphonic Outlet
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
checkpoint | Soaker Gutter
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Deletion of Valley Gutter replace with Apron & Soaker
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Roof - Zone 4 / Roof 6 - Insulation Checklist
section | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof - Zone 4 / Roof 6 - Roof Installation Checklist
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Roof - Zone 4 / Roof 6 - Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations | [5 empty] | Roof - Zone 4 / Roof 6 - Roof Penetrations Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation | [5 empty] | Roof - Zone 4 / Roof 7 - Box Gutter Installation Checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | Syphonic Outlet
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
checkpoint | Soaker Gutter
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Deletion of Valley Gutter replace with Apron & Soaker
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Roof - Zone 4 / Roof 7 - Insulation Checklist
section | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof - Zone 4 / Roof 7 - Roof Installation Checklist
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Roof - Zone 4 / Roof 7 - Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation | [5 empty] | Roof - Zone 4 / Roof 8 - Box Gutter Installation Checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | Syphonic Outlet
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
checkpoint | Soaker Gutter
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Deletion of Valley Gutter replace with Apron & Soaker
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Roof - Zone 4 / Roof 8 - Insulation Checklist
section | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof - Zone 4 / Roof 8 - Roof Installation Checklist
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Roof - Zone 4 / Roof 8 - Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation | [5 empty] | Roof - Zone 4 / Roof 9 - Box Gutter Installation Checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | Syphonic Outlet
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
checkpoint | Soaker Gutter
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Deletion of Valley Gutter replace with Apron & Soaker
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Roof - Zone 4 / Roof 9 - Insulation Checklist
section | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof - Zone 4 / Roof 9 - Roof Installation Checklist
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Roof - Zone 4 / Roof 9 - Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation | [5 empty] | Roof - Zone 4 / Roof 10 - Box Gutter Installation Checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | Syphonic Outlet
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
checkpoint | Soaker Gutter
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Deletion of Valley Gutter replace with Apron & Soaker
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Roof - Zone 4 / Roof 10 - Insulation Checklist
section | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof - Zone 4 / Roof 10 - Roof Installation Checklist
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Roof - Zone 4 / Roof 10 - Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation | [5 empty] | Roof - Zone 5 / Level 3 Roof - Box Gutter Installation Checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | High Capacity Overflow
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Fix only Syphonic Outlet
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Roof - Zone 5 / Level 3 Roof - Insulation Checklist
section | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof - Zone 5 / Level 3 Roof - Roof Installation Checklist
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Roof - Zone 5 / Level 3 Roof - Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Compression Flashing
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate Fixings for Compression Flashings (Max 100mm Nylon Anchors)
checkpoint | Adequate sealants applied with minimal dust in between wall and flashing
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
date | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative: