## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | MataCryl Trafficable |  | MataCryl Trafficable |  | 4d01149f-08f1-4e83-93c3-e2e59a4694a9
| section | Details
| checkpoint | Scope Description (from Bravada SOW) and item numbers
38cab569-f797-59d2-a049-f646b6e97043 | textbox | Enter SOW description
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Preliminary Substrate Assessment for Potential Rectification
f41d6911-96e6-577d-a0a7-3bc6758a5b91 | button | Adequate fall in substrate? | Yes,No,N/A
2fb105ca-3ae1-5199-8670-340d33612898 | textbox | Provide description, photos and plan identifying any areas where the client is required to repair/remediate the substrate
| checkpoint | Substrate Assessment for Acceptance, and Adhesion Testing
6f113128-51af-5511-afe9-b111a1405d48 | button | Substrate deemed acceptable for membrane application as per VicRoads specification 691 | Yes,No
| checkpoint | Substrate Preparation
c8000910-8c67-5b7b-8c2a-a032b00cc875 | button | Substrate to be washed/cleaned | Yes,No
9057495b-9b53-5c2c-ba18-2cad305afcf9 | textbox | If any damage has occurred since initial assessment and/or rectification please identify and alert builder.
44d93ac6-2650-5282-858a-ada13a24f8de | button | Substrate ready for membrane application. | Yes,No
| checkpoint | Matacryl Primer H Application
b2e763ad-ba95-5878-9ceb-d191ec72b4d9 | button | Substrate free from surface water | Yes,No
c4407f4d-94f2-5785-90e4-6c9c1fafe4e7 | button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
2e23fcae-2653-52a0-9b3b-b20cf00e106a | button | Moisture content > 7% | Yes,No
dfb596f3-5d9a-5cdc-a8d6-ed6591ff52ae | textbox | Record (Photo) batch number and date of manufacture of primer
09b6bf38-9d29-5890-8c21-128961194399 | textbox | Record date/time, temperature and % catalyst at time of mixing primer
dd1c3c2f-d81d-5557-8f40-c94e88b66aab | button | Substrate free from surface water - record moisture reading | Yes,No
78849dc7-9782-5f12-8217-7915df27cfee | button | Primer installed before pot life expiry? | Yes,No
dafb7bc2-5c48-585f-9c09-6238793b147a | textbox | Record date and time of primer installation
0047e4db-c33f-50cc-a488-27d2d58cd341 | button | Quartz aggregate broadcast into primer | Yes,No
2b996476-a1fd-528d-8c26-d21078ddf33e | textbox | Record date and time of quartz broadcast
| checkpoint | Matacryl Manual Base Coat Application
368ed5cd-c4a2-5018-bda3-6b671be97c16 | button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
2e758321-1bdd-514b-95d9-202a9e3702f9 | textbox | Record (Photo) batch number and date of manufacture of MataCryl Manual
2f0ba8f8-7f37-58c8-ba58-3e124f427971 | textbox | Record date/time, temperature and % catalyst at time of mixing MataCryl Manual
729a8143-5e4a-5026-a183-f590e573f797 | button | MataCryl Manual installed before pot life expiry? | Yes,No
c47a9f01-191c-5a16-8384-4ca01a01d005 | button | MataCryl Thix installed to upturns before pot life expiry? | Yes,No
9c80f2c8-47e3-58ff-bea7-93c26122775d | textbox | Record date and time of MataCryl Manual installation
| checkpoint | Matacryl WL (Wearing Layer) First Top Coat Application
1cf936e9-0f91-590f-bdd9-fc996ce92fe5 | button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
e5b60403-f58a-5aa5-8667-982b9c9f69cc | textbox | Record (Photo) batch number and date of manufacture of MataCryl WL
efbb8808-ae77-5500-a1ba-f93dab1eefc9 | textbox | Record date/time, temperature and % catalyst at time of mixing MataCryl WL
9d2a4f39-2829-5fb2-a71a-9a7dc7e6f4e0 | button | MataCryl WL installed before pot life expiry? | Yes,No
e8b9541a-975f-5a87-ab76-a8fe6fe4eec1 | textbox | Record date and time of MataCryl WL installation
6d5ae0fd-b8c2-5833-be4b-b89312d071dd | button | Quartz aggregate broadcast into primer | Yes,No
d6105bab-218a-515f-849d-db54237fc03b | textbox | Record date and time of quartz broadcast
| checkpoint | Matacryl WL (Wearing Layer) Second Top Coat Application
dde7f578-1156-5dcc-b3f2-a431c0e4af3e | button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
1fa3c3c4-f5ce-5867-97a6-7b2de1276155 | textbox | Record (Photo) batch number and date of manufacture of MataCryl WL
b1943c27-30de-5334-b646-cb3b2c7a11e0 | textbox | Record date/time, temperature and % catalyst at time of mixing MataCryl WL
80604813-719d-5f55-a9d6-41532438344e | button | MataCryl WL installed before pot life expiry? | Yes,No
961a91c7-443d-5cbb-b2d9-6dbb76882ba8 | textbox | Record date and time of MataCryl WL installation
c0c55c1a-ad57-569d-8d12-725b9f986e1d | note | Attach Client Signature Below