## Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | ITP - R011 - Stormwater Drainage | itp | ITP - R11 - Stormwater Drainage | 10922d77-9415-479d-b9e4-319a84f20b42
| section | Manufacture Drainage Products
| checkpoint | 1. Precast concrete drainage pipes
0f718691-a94f-50c8-ae65-b81264163a78 | note | Reference documents - R11.2.1 R11.2.6
ff870432-3510-57b6-bbf5-95117e15f79d | note | Criteria/Test Method/Spec - The manufacturer must implement and maintain a Quality Management System in accordance with AS/NZS ISO 9001 as a means of ensuring that the manufactured precast concrete pipes conform to the requirements of the Specification.
415ba4f8-d3c2-5e42-bfa2-5ada347a3d25 | note | ○ Precast reinforced concrete pipes must comply with AS 4058 and the requirements in R11.2.1 (I to 11)
7fdcc121-1ebf-5877-8823-d0826660500e | note | Record for conformity/Inspected by - Submit Certificate of conformity at least 7-day prior works commencement to PV
1c1155c5-c4fc-57b5-b742-023d262b9838 | note | Type of Record - HP
699ddc56-b6e9-55d3-ba44-4ca2e30887bd | note | Responsible Position - Project Engineer (PE)/PV
| signoff | HOLD POINT
| checkpoint | 2. Design of “Other Drainage Products
183dd5e9-8512-5a16-a246-f84d0c79d656 | note | Reference documents - R11.2.4.1 R11.4.7
f3cdc9fa-9417-579e-83d9-d30a7ee0dc0a | note | Criteria/Test Method/Spec - The design must be in accordance with the Standards shown in Table R11.1 for the structure or component
bc8c54fc-b578-51b8-9600-ec278f9f4485 | note | ○ Design and development must also comply with TfNSW Q.
2738f188-8571-5245-9cad-72451465ab70 | note | ○ Supply of precast concrete members subject to traffic and/or earth pressure loading, and water retaining structures with capacity greater than 25,000 litres.
9990b108-85da-503a-afa2-2b39b6ad7d31 | note | ○ For all pits, such as junction box, gully pit, drop structure, etc, which are deeper than 600 mm, install an individual-rung ladder (step irons) in accordance with AS 1657 on one internal wall for the full depth of the structure.
e0673ae2-dd52-5f6b-9c5d-59a1ca75a069 | note | Record for conformity/Inspected by - At least 7 days prior to the date of delivery, submit the documents specified in Clause 2.4.1 to the PV.
21286b31-59ea-5684-87b9-14ae6fdc0813 | note | Type of Record - HP
aef58f1f-81e9-5b5b-b605-3fa468e91875 | note | Responsible Position - PV/PE
| signoff | HOLD POINT
| checkpoint | 3. Precast Concrete Pits, Access Covers and Grates, Ladders,
efc814eb-45c0-54e2-968f-4c13b1b365c5 | note | Reference documents - R11.2.4.3, R11.2.4.4, R11.2.4.5
a770ab92-cc16-5755-bdf9-53629c7a39ff | note | Criteria/Test Method/Spec - If precast units are proposed for use to construct drainage pits, the base units (or any other riser units to which incoming drainage pipes will be joined) must be manufactured specifically to suit the design configuration of the particular pit with pre-formed knockouts only in the walls that require them.
a8ac92f8-ec90-5cd8-9658-ddbbb9c7776a | note | ○ Metal access covers, grates and frames must comply with AS 3996.
89c6e0cd-c111-5600-99b3-03aa2714a49e | note | ○ Ladders, including individual-rung (step-iron) ladders, must comply with AS 1657
91c8fd73-450e-5cac-a71b-6169790234ff | note | Record for conformity/Inspected by - Submit Certificate of conformity at least 7-day prior works commencement to PV
3fd89095-ad3b-5ba2-9a7a-cc42e4ef7677 | note | Type of Record -
7d6328e0-b91c-539b-851e-4b909f743d7e | note | Responsible Position - PV/PE
| checkpoint | 4. Marking on precast units
7f215ec7-92ff-58f2-91ce-b5d633628c56 | note | Reference documents - R11.2.5
9a1255c5-bfcc-56ab-84e3-2df6d0929570 | note | Criteria/Test Method/Spec - Markings on the inside of pipes must, as a minimum, include the following:
1882dfde-2971-52ed-afc1-f0a9fc466657 | note | (a) manufacturer’s name or registered mark.
9f15f322-54e0-5bb2-aaf7-54d7c0d7e1c8 | note | (b) date of manufacture.
2a15a6d7-9913-56d7-95ac-e401ec052460 | note | (c) pipe load class.
8571308c-8800-5701-8c40-35c8e70368c2 | note | and may be painted on if located on the obvert of the pipe.
407ea0c6-c1a4-5887-ac59-a6866dc225ec | note | Markings for other precast units must include, in addition to items (a) and
9aa5f3cb-2d8a-5769-a3f3-575ffd1064c7 | note | (b) above, the following:
e2fa8885-31fa-5fe4-addc-62f5694c10cc | note | (i) location of manufacture.
242ceb38-e531-5251-946a-cdb6d078515f | note | (ii) maximum mass of unit in kilograms
7d1f4ca7-c820-5d9f-a519-5a628a938e8b | note | (iii) any other identification necessary to directly relate the unit to tested samples, e.g. batch number;
7abf1dd4-7660-5cbf-8e23-cbec7f2511c2 | note | (iv) inspection status
24230de2-54c1-5480-83e9-da068411bfff | note | Record for conformity/Inspected by - Visual inspection
c686de58-ec1b-5f9c-92e1-fdb94f6ad3b9 | note | Type of Record - IP
3a721400-6a62-507c-b5dd-1f02aaeeeac5 | note | Responsible Position - PE
| section | Bedding and Support Fill Materials
| checkpoint | 5. Type BH Select Fill
d44e4fd0-6739-5224-b5be-76137982e2a3 | note | Reference documents - R11.3.1.1
c5bdeec5-aced-5b6c-94c3-118e2aeb8fb2 | note | Criteria/Test Method/Spec - a particle size distribution, determined by Test Method TfNSW T201, within the limits set out in Table 6 in AS 3725 (or Table 5.1 in AS 1597.2); and
38a7654d-96f1-5aab-9e05-878ec78dc661 | note | ○ a Plasticity Index, determined by Test Method TfNSW T109, of not more than 6.
b0ecfa02-3f5d-5132-8ef3-17a346d98b6a | note | Record for conformity/Inspected by - Test report (NATA)
8fbce4d7-22e0-5e33-8de7-a6489310f462 | note | Type of Record - AP
8c7e947f-4d7f-51eb-acf7-b818a76c3315 | note | Responsible Position - PE
| checkpoint | 6. Type SO Select Fill
a4df8e2f-98b1-5946-a4cb-84a3cfed76d3 | note | Reference documents - R11.3.1.2
e4e1f251-1614-527d-81ca-3ce1d2168e76 | note | Criteria/Test Method/Spec - a maximum particle dimension of 53 mm; and
b75ca151-1414-5c00-b630-d84646fa8e98 | note | ○ a Plasticity Index, as determined by Test Method TfNSW T109, of between 2 and 12.
ad889d4a-ccb4-5112-92a2-8a2c3bb71fd0 | note | Record for conformity/Inspected by - Test report (NATA)
0080e398-cfcb-5b26-acf4-e6134c5c3dc7 | note | Type of Record - AP
4d453026-18c4-5624-8aad-17d443e57e9d | note | Responsible Position - PE
| checkpoint | 7. FILL MATERIAL FOR EMBANKMENTS IN OPEN DRAINS
bff6b2b4-a392-58ed-8c42-3760a3be1c24 | note | Reference documents - R11.3.3
4a55d096-0489-5902-b530-977fd41aa3c5 | note | Criteria/Test Method/Spec - a particle size distribution, determined by Test Method TfNSW T107, such that between 20% and 60% inclusive by mass of material passes the 425- micron sieve; and
d097a4f2-1af9-5fb5-b4d0-699d60ae7365 | note | ○ a Plasticity Index, as determined by Test Method TfNSW T109, of between 15 and 30
e671f648-6ca9-52ac-bdaf-09f7e4cb4940 | note | Record for conformity/Inspected by - Test report (NATA)
145ab494-2305-56b0-a7f0-94e809c33216 | note | Type of Record - AP
4a73d5ff-5aca-5de9-b1c1-c08a703acd67 | note | Responsible Position - PE
| section | Construction
| checkpoint | 8. Setting Out
232f2499-e8f9-50a9-ad39-b51dba613694 | note | Reference documents - R11.4.1.1
a690da06-e653-5eae-b3e4-4889d97fd2a8 | note | Criteria/Test Method/Spec - Set out of drainage system.
0fbabec0-2191-5de7-b428-a15ac4c62108 | note | Record for conformity/Inspected by - PV to Visually inspect set out for drainage system and propose changes if necessary
7012352d-368c-59d2-8911-df7396c63f02 | note | Type of Record - HP
a8b4cb7e-44c2-51a2-bf84-4b98c462733b | note | Responsible Position - PV/PE
| signoff | HOLD POINT
| checkpoint | 9. Excavation of Open Drains
b6d3eae2-ea97-5be6-a9a4-9a72ded01fbe | note | Reference documents - R11.4.2.1
c664e83b-afe6-56a8-b1f2-d94257a481bf | note | Criteria/Test Method/Spec - Construction of open drains with grade less than 0.5%.
1f60f253-0a63-5944-ba47-0ac7852ce649 | note | Record for conformity/Inspected by - PV to consider the matter and direct contractor further before release HP
a3323027-5761-510e-b423-9076c42c233e | note | Type of Record - HP
dd7159c6-d424-5839-a00f-8930b1b83336 | note | Responsible Position - PV/PE
| signoff | HOLD POINT
| checkpoint | 10. EXCAVATION FOR DRAINAGE STRUCTURES
11e8ae06-1492-5e18-b0f8-e3cef4d4d087 | note | Reference documents - R11.4.3
85b4947f-4d04-503d-8e9e-d27db39ff9a5 | note | Criteria/Test Method/Spec - Excavation for pipe installation and other drainage structures (Pits)
e32b110d-e387-5aa3-9931-5cd46196d03d | note | Record for conformity/Inspected by - Notify PV not later than 24 hours but not earlier than 5 working days,
9087756d-f9a2-5256-8f81-38ba2a32b43e | note | Type of Record - WP
848c8c61-34c7-5333-86e0-dfbb970355d4 | note | Responsible Position - PE
| checkpoint | 11. Inadequate Foundation Material
7d36f9cf-7eb3-541f-9380-b73ec00b523b | note | Reference documents - R11.4.3.3
f3a1e14d-579b-5aee-8967-acd09b454150 | note | Criteria/Test Method/Spec - Replacement of inadequate foundation material
7339593b-8fda-58a4-8042-8a781aa30e6a | note | ○ Notification that inadequate foundation material has been excavated to the extent directed.
c967b1ba-a70b-5931-92c0-3647777edd5c | note | Record for conformity/Inspected by - Notify PV to inspect the excavation and may direct further excavation
a5e632d0-70b7-518d-a38d-fa7d84dc20cd | note | Type of Record - HP
e432d123-aefd-5e75-8df8-de2e85564be6 | note | Responsible Position - PE
| signoff | HOLD POINT
| checkpoint | 12. Install Pipe Support Type and concrete pipes
818ccb0b-1f3a-56fd-a7fb-e86ed36a82bc | note | Reference documents - R11.4.4.1, R11.4.4.2
f4d23ab3-0a1c-5e51-80fc-64d38c4e7012 | note | Criteria/Test Method/Spec - Provide pipe support of Type HS3 complying with AS 3725 and Standard Drawing R0240 - 01.
bd17d93d-512d-5452-939d-c204427401fe | note | ○ Handle, store and install the concrete pipes in accordance with the manufacturer’s recommended practice.
9e09fd74-d1ed-5907-8814-4eca54c38314 | note | Record for conformity/Inspected by - Visual inspection
db562519-61b6-5f28-ac3e-cf8c51a097a4 | note | Type of Record - IP
7faa78a3-38c4-5099-b3bb-68947b5c650b | note | Responsible Position - PE
| checkpoint | 13. Anchor Blocks, Sealing of Lifting Holes, Joints,
32af1955-a419-5d82-a08c-28ccad0f8ed1 | note | Reference documents - R11.4.4.3, R11.4.4.4
8ae81a7e-81f0-55ea-88cc-228d746e8369 | note | Criteria/Test Method/Spec - Provide anchor blocks at a maximum spacing of 3 m and at bends or junctions for all stormwater pipes laid on a grade exceeding 20% and where shown on the Drawings.
99c21105-3229-5482-9b22-31b81dacff96 | note | ○ Seal all lifting holes in the pipes, and all flush or butt joints used to extend existing pipes, to prevent the ingress of materials.
6564719b-5890-558f-841d-c37872277683 | note | Record for conformity/Inspected by - Visual inspection
b4103940-06f4-5c24-9b1f-703d3210cc8a | note | Type of Record - IP
281170b9-ce18-56e6-b66a-80c57e196b08 | note | Responsible Position - PE
| checkpoint | 14. Subsurface Drainage Pipe at Discharge End of Pipes
cb0c0dbb-8254-52d5-ae76-17ef49194c22 | note | Reference documents - R11.4.4.5
83972e2f-0959-5e7c-8a4a-01c2658e84c2 | note | Criteria/Test Method/Spec - Install a subsurface drainage pipe, complying with Specification TfNSW 3552, at the discharge end of pipes at gully pits, junction boxes and headwalls unless the Drawings specifically direct the subsurface drainage be omitted.
319dae4d-8494-56e2-a78a-3eadd4beae5b | note | ○ Unless shown otherwise on the Drawings, the subsurface drainage pipe must be a 3 m length of 100 mm diameter subsoil pipe laid beside, and 100 mm above the invert level of the drainage pipe discharging through the wall of the pit or headwall.
08372cd2-2351-58aa-92be-21128e956e1e | note | Record for conformity/Inspected by - Visual inspection
87fe736d-7704-58d8-912c-f8e9948103c8 | note | Type of Record - IP
05cd7066-666b-50b0-b631-8927b11f1f00 | note | Responsible Position - PE
| section | Construction of "OTHER DRAINAGE STRUCTURES" include gully pits, junction boxes, drop structures, inlet and outlet structures, and energy dissipators
| checkpoint | 15. Foundations for “Other Drainage Structures
ecfe8000-cf0b-5e3f-94c2-1725cf09372b | note | Reference documents - R11.4.7.2
a66b0b5c-de99-5ee8-a6a7-cba1612cd957 | note | Criteria/Test Method/Spec - For precast pits, install the precast pit on top of a minimum 50 mm thick Class 2 DGB bedding material, complying with Specification TfNSW 3051, or controlled low strength flowable fill material complying with Appendix A in AS 3725, to support the precast pit uniformly
70c38043-ef64-5a93-8f9e-630c4d8adb53 | note | Record for conformity/Inspected by - Notify PV for inspection
9431c757-ac13-5952-9ffd-fa9fa8bfc1ae | note | Type of Record - WP
725a6d4d-4e6d-512c-b2dc-2f5b4a629d71 | note | Responsible Position - PV/PE
| checkpoint | 16. Precast Headwalls
081f6b9c-62d0-5b36-828b-1554daf08ed6 | note | Reference documents - R11.4.7.3
7de5e218-0e71-557c-8ffc-d1eaf4465b93 | note | Criteria/Test Method/Spec - For precast headwalls for pipes of 300 mm to 1200 mm diameter, provide a curtain wall at the outer edge of the apron in accordance with the TfNSW (RMS) Standard Drawings. Do not use precast headwalls for pipes greater than 1200 mm diameter unless approved otherwise by the Principal
15f3c27f-1d23-53ac-99a0-fd7a9c60f841 | note | Record for conformity/Inspected by - Visual inspection
e57fc199-5ccb-59b9-8f04-f7fdcdad2d51 | note | Type of Record - IP
a9e456ca-4650-55f0-94da-5385ce162f0a | note | Responsible Position - PE
| section | Backfilling, Compaction and Disposal of Surplus Excavated Material
| checkpoint | 17. Backfilling
69ec9c05-f208-57f6-aebb-2416a38d582d | note | Reference documents - R11.4.9.1
58090d7b-8aa6-57d9-9419-a63a73dfdb06 | note | Criteria/Test Method/Spec - Backfill the Side and Overlay zones of box culverts with Type SO Select Fill. Refer to Figure 1.1 of AS 1597.2 for schematic details of these zones.
47954c3a-49f3-5257-9e9e-7ca27160af06 | note | ○ For pipes and box culverts located within a rock fill embankment, provide a minimum thickness of 1000 mm of Type SO Select Fill within the Side and Overlay zones, separated from the surrounding rock fill by a geotextile complying with Specification TfNSW R63.
b938dca2-2d6d-54e4-a3d6-ce3cb5ec2b0b | note | ○ Unless otherwise specified or directed by the Principal, place fill material for the foundations, bedding, support and general backfill in layers not exceeding 150 mm compacted thickness. Compact the fill material to the requirements of Clause 4.9.2 of this Specification.
998f8509-32a2-598b-ae66-817d82333eb3 | note | ○ Do not carry out backfilling against cast-in-place box culverts until the compressive strength of the concrete has reached at least 75% of the specified 28 day strength, and against other concrete drainage structures until at least 7 days has elapsed after placing the last concrete in the structure, unless authorised otherwise by the Principal.
55be628b-fad4-56d3-bbdc-1c73dbe2b9b1 | note | ○ When backfilling against box culverts, the difference in level of the backfill on opposing sides of the culvert must not exceed 500 mm
d3bead62-ca26-570f-9085-429c7a7714e9 | note | Record for conformity/Inspected by - Visual inspection
f4539439-0bea-53dc-b1b1-c10ca776e27e | note | Type of Record - IP
f1984c59-fe51-5153-bc25-00e5c1b176f9 | note | Responsible Position - PE
| checkpoint | 18. Compaction
f7260499-0dd7-5ccf-af30-b913688c4772 | note | Reference documents - R11.4.9.2
d3e2d931-9a6e-598e-9a78-e6a5e47505eb | note | Criteria/Test Method/Spec - Compact the foundations and fill material placed to achieve the minimum characteristic value of relative compaction for the particular type of material, as shown in Table R11.2.
7f00c091-52e6-5e69-a2d3-4d2ad10569ea | note | ○ Select Fill in the Side and Overlay zones of box culverts (compaction 98%)
149eea7e-db0b-5fef-9a4c-e21f489aa390 | note | ○ Backfill material within the Selected Material Zone of the adjoining earthworks (refer Specification TfNSW R44) (102%)
04d601c9-936b-5558-b694-6383f7b75fe1 | note | ○ All other embankment (compaction is 95%)
2a79c811-d47c-5389-a3c2-78e04196b00b | note | Record for conformity/Inspected by - NATA report
d352998e-fa3e-59cb-8cae-598e38bd4165 | note | Type of Record - AP
1db7302f-0baa-5de1-a4d1-998f2d508847 | note | Responsible Position - PE
| checkpoint | 19. Construction traffic
188a3c8c-defd-51b4-8a2f-1ef66c45ce69 | note | Reference documents - R11.4.10
41b77f39-03c8-5b72-9338-dd2e39d8f056 | note | Criteria/Test Method/Spec - Moving heavy construction plant or vehicles over pipe or box culvert structures.
44cb89d0-0077-5b4d-81c9-c92478282bcb | note | ○ Where you propose to move heavy construction plant and vehicles over pipe or box culvert structures, design and provide protective measures for each crossing in accordance with Specification TfNSW G2.
ccdd1956-f92f-53d4-b52b-22a18f231911 | note | Record for conformity/Inspected by - Notify PV
a409fdfb-a99f-5a73-b85e-d3ef956ee4e1 | note | Type of Record - HP
ec3109fc-6131-5d9d-9776-0589239f1d2c | note | Responsible Position - PV/PE
| signoff | HOLD POINT
| checkpoint | 20. Survey check and tolerances
7b9098c1-1e49-5c5b-bc1b-5a05b1eb1195 | note | Reference documents - R11.5.1
b6751694-5a3b-56bf-b9f1-a0bf221b0fd7 | note | Criteria/Test Method/Spec - Concrete pipes, box culverts, headwalls and wingwalls, energy dissipators, inlet and outlet structures (location within 200 mm of the plan position shown on the Drawings) (invert level within 20 mm of the design level at any point)
5dce7af7-6a6a-5380-9cef-ede80658fac5 | note | ○ Gully pits and junction boxes (location Within 200 mm longitudinally and 20 mm laterally of the plan position, with reference to the control line for the road shown on the Drawings) (invert level Within 20 mm of the invert level shown on the Drawings)
a392a606-1699-5db4-8e74-c98006b2b99e | note | ○ Precast concrete box culvert units (On the internal faces of the walls and roof, no step between adjacent units must exceed 20 mm. Steps between 10 mm and 20 mm must be smoothed to a standard of durability equal to the rest of the culvert)
ed335560-f6a9-5c24-8e24-0b634793a917 | note | ○ Open drains (location as per R44) (level Within 50 mm of the design level at any point provided that there is a continuous downgrade in the direction of flow not less than 0.5% at any point) (Waterway area Not less than 95% of the design cross sectional area at any point)
ba6cf086-72c8-57f5-ba04-b0dde07ce441 | note | Record for conformity/Inspected by -
f3db9574-509a-5ded-affc-0f1cbd9bcd80 | note | Type of Record -
ecbeb23b-88a2-567c-993e-e75fb473a116 | note | Responsible Position -
| checkpoint | 21. Inspection and CCTV test
e41741b0-d971-50cb-b868-29374ba11a67 | note | Reference documents - R11.5.2
245c46e8-8b4b-5cca-a4c3-cb5c5088ba07 | note | Criteria/Test Method/Spec - Carry out closed-circuit television (CCTV) inspections of all pipe and box culverts with dimensions that restrict human access, to verify that the works have been constructed within the specified tolerances
b9e8c4cf-9b47-5376-8c69-e3b093e6b77c | note | ○ for visible signs of defects, at the following times:(a) on completion of the subject drainage structure and prior to commencement of the overlying pavement, and (b) no more than 14 days prior to Completion
1ba01dd3-9890-5d4c-a70e-fb42bfb4dd6f | note | Record for conformity/Inspected by - Submit report results to PV
586ac5c0-0966-5afb-a6fb-25b4c7ea5ef5 | note | Type of Record - AP
8bc0f78d-5c10-54df-8978-b7978f963e25 | note | Responsible Position - PE
| checklist | ITP - R015 - Kerb and Gutter | itp | ITP - R15 - Kerb and Gutter | af253987-5aa6-4227-908e-2f5a36451ec0
| section | Kerb and Gutter
| checkpoint | 1. REMOVAL OF EXISTING ELEMENTS
a458f330-0d82-5885-977e-7e417373cf60 | note | Reference documents - R15.3.2
3de49c1c-a65c-51d9-af5c-a4a75a295cdb | note | Criteria/Test Method/Spec - Remove existing kerbs, channels, profile transitions, vehicular crossings and kerb ramps where specified or shown on the Drawings. Sawcut where necessary to provide a neat surface at the joint.
a243d1ce-5762-555f-b3b6-a4773315a9e5 | note | ○ When removing these elements, do not cause damage to adjacent elements which are to be left intact.
244d02cb-ed05-52f5-ac04-a8ddfc415241 | note | ○ Re-use the removed elements in the Works, recycle or dispose of them off Site in accordance with Specification TfNSW G36.Backfill the void remaining after removal of existing elements with sound material to prevent the infiltration and ponding of water, unless specified otherwise.
95b06787-7991-5263-985a-916ffc0e5b33 | note | ○ Compact the backfill material to at least the relative compaction of the existing material in the adjacent ground.
c2efea18-b7a3-5424-a298-5c0788e3c03d | note | Record for conformity/Inspected by - Visual check
f933f383-ac8b-5950-8250-b9e5b772c3c1 | note | Type of Record - IP
141ce698-a82f-56fb-a583-deef046ae417 | note | Responsible Position - PE
457e0e55-4882-53ba-aa1a-0b28c47a7efe | textbox | Initials:
| checkpoint | 2. Support layer preparation and no-fine concrete
03bb9e27-9451-57af-bcab-f61e7815422e | note | Reference documents - R15.3.3.1, R15.3.3.2
3e7504d8-986b-5d41-941a-4989fa1d260a | note | Criteria/Test Method/Spec - Compact subgrade, unbound granular subbase and base layers supporting the K&C to the standard specified for these layers
e6e79042-1d4a-5bc0-8de2-78e8962a9810 | note | ○ Construct the no fines concrete pad (beneath the K&C), including installing a geotextile around the pad, where shown on the Drawings.
e920166e-e53d-5ba2-ac7e-b1ead9fb1bd9 | note | ○ Implement measures during placing to prevent segregation and formation of a slurry layer at the surface of the concrete.
cd4f13b4-39fd-5f60-bddf-868f013e4cf8 | note | Record for conformity/Inspected by - Visual check and survey report
2eb6a7ce-4034-5cc5-bf80-1a385382a9c5 | note | Type of Record - IP
734935cc-933a-5b1e-95f2-2c5184677462 | note | Responsible Position - PE
59708ee6-b39a-5e10-bbf5-f72c59edf2fe | textbox | Initials:
ba54553a-32ad-5e0e-9d61-c58c57e7ba45 | date | Date:
| signoff | Sign:
| checkpoint | 3. Steel reinforcement
e1fed1be-1d01-5d8a-ba88-86a4e7a55b65 | note | Reference documents - R15.3.5
3a64fd2e-95a8-5ff3-942c-a2f8ba01dfdf | note | Criteria/Test Method/Spec - Provide steel reinforcement such as tiebars, to the K&C as shown on the Drawings.
1da53f68-8d5d-5082-96f8-90e347559522 | note | ○ Provide a minimum cover for the steel reinforcement in accordance with TfNSW R53, unless shown otherwise on the Drawings.
f438f618-f0b5-5b68-b24d-57c9ded30963 | note | ○ Provide kerbs which are placed on top of a concrete base with ties as shown on the Drawings
5a2d4310-2426-5a72-9c4a-38fc3a553114 | note | Record for conformity/Inspected by - Visual check
503874b2-6b0b-540a-bdb1-79bb1d0f1171 | note | Type of Record - IP
a8c78fbc-6a0e-5a22-a6c1-2607108d444b | note | Responsible Position - PE
f482eeff-170b-5848-ad9d-5c538dde5be3 | textbox | Initials:
| checkpoint | 4. Concrete placement
0073fabb-7a4c-5b4b-ada4-c3d32f211bd5 | note | Reference documents - R15.3.7
536a9eaa-b888-5bc3-b401-38135ebe13ed | note | Criteria/Test Method/Spec - Unless otherwise specified, supply, place, compact, finish and cure concrete K&C in conformity with TfNSW R53. The Hold Point in TfNSW R53 for placing of concrete applies.
f50b6d06-087d-5517-b3e9-3d15fb648fef | note | ○ You may construct K&C either by manual placing using fixed forms, or by machine- placing either by extrusion (dry mix and ramming) or slipforming (wet mix and vibration), unless otherwise specified.
22a0e3db-9ced-5c47-bcd0-08a036e7ce39 | note | ○ Do not place by extrusion K&C which are located alongside, and tied to, a concrete base.
c83064b9-a21b-5b91-9373-22e94e46062b | note | ○ Where the K&C is to be constructed integrally with a concrete base, construct the K&C to the same requirements as that specified for the base.
4d91236b-3805-5c50-ae26-f5ca1379f79e | note | Record for conformity/Inspected by - Visual check
0078dabf-4d19-5613-8f6b-cf5385bcb88b | note | Type of Record - IP
3240de6f-e35d-5d56-9e43-4b711448ba7d | note | Responsible Position - PE
9b882573-dc04-514a-b256-223536fe4b05 | textbox | Initials:
| section | Joints
| checkpoint | 5. Inspection prior to placing concrete, mortar and grout and where washout of vehicles will occur
3f549fcc-0911-581d-98c4-d1d4b1233767 | note | Reference documents - Visual inspection R53.3.3
c658c2c9-af27-5f4a-99cd-1c3d0c16688c | note | Criteria/Test Method/Spec - Each pour
480f19d7-8a4d-521a-a5da-66f5833b64fb | note | Record for conformity/Inspected by - PV, Hold Point
75fc9ebf-4de6-5b33-8e9a-8dc94947b4ea | note | Type of Record - PE/PV
a8db32d7-beaf-5283-b803-5ffaabba155c | note | Responsible Position - Customer Notification
14c28e0c-ff53-5746-b748-ff453679cae9 | textbox | Initials:
ac481721-eec6-5ecc-9161-d72e9f5a2cc4 | date | Date:
| signoff | Sign:
| checkpoint | 6. Longitudinal Joint with Base
7025112f-3861-5147-a16b-f57d1d8d00db | note | Reference documents - R15.3.8.2
74dcb996-e90c-5ea6-8345-2bdcdf465cf8 | note | Criteria/Test Method/Spec - (a) With Flexible Pavement Base Where K&C is to be constructed alongside an existing flexible pavement, conform to the requirements shown on the Drawings or specified in Annexure R15/A1.
943c342b-d1d9-5c75-92da-aae8ceae6960 | note | (b) With Rigid Pavement Base Where the K&C is not placed integrally with the concrete base, the longitudinal joint between K&C and the concrete base must be continuous over the full length without steps or offsets and must not deviate from a 3 m straightedge by more than 20 mm after due allowance for planned curvature.
39bb601f-f2b1-5823-8eff-3626eb766ff0 | note | ○ The longitudinal joint must be tied, and corrugated only where shown as such on the Drawings
094dcdd6-2f08-5eac-a087-f2f062768eba | note | Record for conformity/Inspected by - Visual check
bb9d520a-99ba-5c70-afff-f6d1f7e2f38e | note | Type of Record - IP
42a04972-0b77-5025-a26f-c3f516c738ac | note | Responsible Position - PE
0493cf34-268a-501f-8708-c9da97f28ec5 | textbox | Initials:
| checkpoint | 7. Sealing of Transverse Joints in Concrete Base
73cbdf4b-98d7-5348-ac49-da263b0bedb6 | note | Reference documents - R15.3.8.3
1995f311-35e2-5264-b493-b55d50d9d126 | note | Criteria/Test Method/Spec - Where the K&C is constructed after the concrete base (whether constructed on top of or alongside the base), complete the sealing of transverse joints in the base prior to placing the K&C, to prevent the ingress of mortar into joints.
a3697a4f-c951-542a-afaf-7b0dd5d9028d | note | ○ In the latter case, where the K&C is constructed alongside the base, when sealing the transverse joint in the base, extend the sealant all the way down the joint at the exposed vertical face of longitudinal joint (between the K&C and base), including the crack beneath the sawcut groove if the crack width exceeds 1 mm.
666cd4f6-0eb9-5ca7-a945-fa05f93898f8 | note | Record for conformity/Inspected by - Visual check
3eab39f5-fef4-54f2-9288-5836c4d9d195 | note | Type of Record - IP
a4a875f8-8198-5a73-9d69-58d92b113910 | note | Responsible Position - PE
25ef6110-4140-5dc6-a9cb-0288a4a9babf | textbox | Initials:
| checkpoint | 8. Location and Alignment of Transverse Joints in Kerb and Channel
7cf3637a-207d-5688-8d8a-d5db6f8673c3 | note | Reference documents - R15.3.8.4
c91b442a-178a-5342-bbea-736d0e0be00a | note | Criteria/Test Method/Spec - (a) Kerb on Top of Concrete Base Where the kerb is placed on top of a concrete base, align each transverse joint in the K&C exactly (i.e. coincident) with the joint in the underlying base.
26fa03cc-c647-50b1-bada-b5394b5d9213 | note | (b) Kerb and Channel Alongside Concrete Base
5c1ae8b4-1961-5b52-bfff-e23643dc3a83 | note | ○ Where the K&C is placed alongside a concrete base, locate the transverse joint in the K&C such that it meets the transverse joint in the base at the common longitudinal joint.
f44faf5f-79ef-5a7d-997b-5251b57edeee | note | ○ Align the transverse joints in the K&C at right angles to the longitudinal alignment of the K&C, as shown on Standard Drawing DS2012/001191 Sheet No 14.
95d52160-cb81-5812-a95f-3616b7abbea5 | note | Record for conformity/Inspected by - Visual check
bb6ee1a6-052b-5c9d-9733-33be9ec3720c | note | Type of Record - IP
5903b3ca-a3a7-5831-8c6a-b01b99312b31 | note | Responsible Position - PE
| checkpoint | 9. Expansion Joints
965ab9ba-4cf6-50c5-aad6-4b62b58874d8 | note | Reference documents - R15.3.8.5
b00d5414-a607-5a98-865b-beeff392fec6 | note | Criteria/Test Method/Spec - Provide expansion joints in K&C at all locations where the K&C abuts structures such as drainage pits, retaining walls and bridges, and where shown on the Drawings or specified in Annexure R15/A2.
19e8e4c7-f1fe-575a-80aa-126b15cc7cd3 | note | ○ Provide expansion joints at the locations where vehicular crossings and kerb ramps adjoin kerbs, channels and concrete paving to the full depth of vehicular crossings and kerb ramps, unless otherwise approved by the Principal.
30b9b97b-a05a-5319-bb25-d741452c8f3b | note | ○ Install a preformed joint filler conforming to Clause 2.6 within the expansion joint.
5eb9758c-d841-57c5-b236-0cf066e11150 | note | Record for conformity/Inspected by - Visual check
33e5c305-d880-5181-a272-5938b8dc9c38 | note | Type of Record - IP
5da25980-41af-5f45-a959-763280a6199f | note | Responsible Position - PE
| checkpoint | 10. SURFACE FINISH
e6a0ecb8-1c3b-5026-8206-16c8c855e56f | note | Reference documents - R15.3.9
09b87053-84b3-5550-9395-ddbb55cfd77f | note | Criteria/Test Method/Spec - Unless shown otherwise on the Drawings, provide a steel float finish to channel inverts and faces of kerbs and a broomed finish to vehicular crossings and kerb ramps. Where directed by the Principal, provide a broomed finish to the tops of kerbs.
4f82a9e1-7173-5d57-b1e1-3002485ca983 | note | ○ Direction of brooming must be transverse to the direction of travel on these elements.
8ddda4e8-556a-576f-8972-4ba7613ebc0c | note | ○ Protect the concrete surface from rain during and after surface finishing and until final set.
6e14e91f-03fd-5248-89e4-9361da7561ae | note | Record for conformity/Inspected by - Visual check
d3365751-3c2b-513c-a466-f68fc2e2068a | note | Type of Record - IP
6ccc05e0-bc2a-5323-9d82-3929ded85856 | note | Responsible Position - PE
| checkpoint | 11. Modular drainage product type drains
2f5ed2ca-4a8e-570e-aaf9-e565a56c9866 | note | Reference documents - R15.3.10
f8c3cb08-275d-5cbd-9cd9-9472628276ed | note | Criteria/Test Method/Spec - Install MDP type drains at the locations shown on the Drawings.
d874e374-e045-5228-9034-e0a31c5893bb | note | ○ You may submit for approval by the Principal the use of MDP where they are not shown on the Drawings, but the Principal is not bound to accept your proposal.
ddafab8a-620f-5b77-b0fb-4a1b9d464beb | note | ○ Include in your proposal evidence that all other options for drainage have been considered, implications on flow if grated drains are not to be installed and verification that the proposed system is fit for purpose.
68513c04-3788-5923-833d-eaf87d645be2 | note | Record for conformity/Inspected by - Visual check
a3f9e4e8-dbe4-56b9-b385-9b9cd46df1f7 | note | Type of Record - IP
e1fe0cce-ae19-511f-8694-160546ad9011 | note | Responsible Position - PE
| checkpoint | 12. Survey check and tolerances
2b9fa00d-12b1-541b-9797-1808d2d060a8 | note | Reference documents - R15.4.1
f166708a-35d1-5d9e-abca-cd56a6d66d7a | note | Criteria/Test Method/Spec - All finished surfaces must conform to the lines, levels, grades, thicknesses and cross sections shown on the Drawings within the specified tolerances.
8b24512b-4a13-5ebc-b22c-85cef41e5e19 | note | ○ The tolerances stated in AS 2876 for irregularities in the bedding layer, level of the bedding layer, horizontal alignment, level, deviation from a 3 m straightedge, deviation on vertical curves, and profile dimensions also apply, except that the level of the constructed channel lip must not vary by more than
e7fdb54b-3e69-5ba5-b100-a9920886e726 | note | ○ 0 mm above or 10 mm below the adjoining pavement surface at any point.
9b656ed8-5e94-508c-91de-8e60e4262bd9 | note | Record for conformity/Inspected by - Survey report
2cf25d3b-e5cb-5d80-8ba6-42f9e16dd866 | note | Type of Record - AP
dc80c1ae-3ac0-51d1-a490-ff6020f621ba | note | Responsible Position - PE
| checklist | ITP - R033 - Trench Drains | itp | ITP - R33 - Trench Drains | bf4f12a3-a51d-4304-9c67-cc8020979c78
| section | Trench Drains
| checkpoint | 1. Submit material compliance/test certificates for approval.
2a0bc3b2-e68c-5451-ae03-3c6c414761db | note | ○ Corrugated plastic slotted pipe
6fe37613-32e7-534f-869e-2b91636eabdd | note | ○ Seamless tubular filter fabric
e5a16cad-6626-5d91-887d-4cab04ee1765 | note | ○ Geotextile
e6558c78-f440-5a8c-93d8-11074cfcd040 | note | ○ Filter Material – Aggregate
16d3c817-3625-5ca0-9bc2-9f0c3d3ef0fa | note | Reference documents - R33.2.1, R33.2.2, R33.2.3, R33.2.4
eb82c655-e96c-5bd1-8f3e-0834990d7ad6 | note | Criteria/Test Method/Spec - RMS 3552, RMS 3553, RMS R63, RMS 3580 MD.R33.A06
e25279b5-270a-515f-a95c-342b6278ca99 | note | ○ Release of Hold Point
48a2c0ee-1e57-568b-9d47-f7b9144e95b6 | note | Inspection/Test Frequency - In accordance with Annexure R33/L
e4900202-8336-51c2-b278-a985478fdaee | note | Inspection/Test by - PV
08f83013-ddf7-519e-a606-1fa580bfb48c | note | Responsible Position - PV/PE, PV
f15dc0dd-a64c-56e3-80f9-c347f2c24d69 | note | Type of Record - HPR Form
d8787b35-3e6b-5a0f-b83a-38ad4fc02f6a | textbox | Initials:
| checkpoint | 2. Excavate trench to line, grade, width & depth shown on drawings.
7c573a78-7615-549f-91a3-5cee73f2865f | note | Reference documents - R33.3.2
b0e47bb4-e9b7-5a50-8499-92c272da769c | note | Criteria/Test Method/Spec - Minimum grade 0.5%
3bc58681-2286-58b6-82c5-52eb121c7bf3 | note | Inspection/Test Frequency - After excavation
ad01ba4c-0f6c-527c-9f20-67e4434c9687 | note | Inspection/Test by - SS/Surveyor
cb6c95df-68b3-5731-8499-92d4104967cc | note | Responsible Position - PE/SS
7611ef6f-28e5-5ba3-b3ee-24ccd50402bb | note | Type of Record - As-builts
0fd0021f-0d9d-507e-9400-a01225cf3498 | textbox | Initials:
| checkpoint | 5. Place geotextile in trench.
5aea2ada-60b1-5a29-ba10-172cea7f3c1a | note | Reference documents - R33.3.3
686339da-ec07-5b86-a8d2-fdeee6b7b6a4 | note | Criteria/Test Method/Spec - Visual inspection
4ed5c0e6-5dbc-5f9c-8789-25536139f0ab | note | Inspection/Test Frequency - After geotextile placement
309ab109-30e6-5aca-8555-87bb08384ade | note | Inspection/Test by - SS
574c58f3-0995-5e96-abb7-953ec9984a9c | note | Responsible Position - PE/SS
5d3d7e50-1831-5241-929d-a2d2bd37c67a | textbox | Initials:
| checkpoint | 6. Lay pipe on 50mm bed of filter material.
9467a247-3a25-523a-9277-437069abd11b | note | Reference documents - R33.3.4
ed4ea4e8-67ef-5671-9d82-8de53fd01416 | note | Criteria/Test Method/Spec - Visual inspection
6593e4af-1e7f-5b5d-9d89-3848a9985d81 | note | Inspection/Test Frequency - After bedding placement
65cc4fc8-9c4d-54ab-b786-4dfca9172618 | note | Inspection/Test by - SS/PV
c408946e-8399-5938-a2ca-2e284db182ed | note | Responsible Position - PE/SS
d9c831c9-37f6-5468-8d0b-afb656c79c41 | textbox | Initials:
| checkpoint | 7. Verify that pipe laying, jointing & bedding are complete & conforming
7e5d82e2-80f7-5f8e-b2b1-a7acac776a4c | note | Reference documents - R33.3.5
0241aca2-2ed0-5c35-80ba-ade268393dfc | note | Criteria/Test Method/Spec - R33 Cl 3.5
0bb38d4a-a755-57d4-9266-5d4d92982120 | note | ○ Release of Hold Point
cbe2d432-662d-58d0-958f-e880e46a87fb | note | Inspection/Test Frequency - At completion laying, jointing & bedding
9305eb03-5ab1-5a19-a3ec-e377e84c0f2a | note | Inspection/Test by - PV
71ab0359-468e-5116-8fbe-5c39ea467e36 | note | Responsible Position - PV/PE
e14ece86-dd50-5289-b13b-ed1279c5af2b | note | Responsible Position - HPR Form
75dac98c-27c1-5d43-a37d-6c978ebc9fd5 | textbox | Initials:
| checkpoint | 8. Backfill pipe with filter material, compact to avoid consolidation & lap geotextile.
da376165-44d9-5dcd-80b8-e6de782dbff5 | note | Reference documents - R33.3.5
d2cf8b9c-d887-5901-a3ca-363c89202eb3 | note | Criteria/Test Method/Spec - Visual inspection
748b0467-95c9-5890-a9a6-ba03e05e739e | note | Inspection/Test Frequency - After HP release
35289494-1517-502b-8384-e2eb769625b1 | note | Inspection/Test by - SS
25585a55-3314-5897-a7a6-29d259cf94a6 | note | Responsible Position - PE/SS
256245ee-7817-55e4-88cb-6303b566ff37 | textbox | Initials:
| checkpoint | 9. Install flush point covers and outlet in batter, structure including connections to pits.
e0c5a942-1ae9-5b0c-aa48-28bbd2c4ab54 | note | Reference documents - R33.4.2, R33.4.3, R33.5.2.1, R33.5.2.2
0647252b-38ba-568a-950c-885976ae09ab | note | Criteria/Test Method/Spec - Visual inspection
17160939-01b9-5f80-a046-ca5cd7e277fd | note | Inspection/Test by - SS
9a087139-bae8-5997-8171-0fda78c26186 | note | Responsible Position - PE/SS
937a7d81-e50b-5fb4-bba4-c5c97c4b5fe6 | textbox | Initials:
| checkpoint | 10. Marking trench drain and submit WAE drawings to Principal <28 days of completion
8ebadb81-869b-5d6f-894c-bfb0bb2c560d | note | Reference documents - R33.6
93546324-52b0-5da4-9f50-dc18c975766e | note | Criteria/Test Method/Spec - R33 Cl 6
3f14ee72-24a0-5a89-b11d-32fb768875a8 | note | Inspection/Test Frequency - <28days of completion
324f8f0a-53ae-5dd8-a760-08a4f962cdc5 | note | Inspection/Test by - SS
f4c216ca-d0d2-5da0-9f74-d5639cab2c15 | note | Responsible Position - PE/SS
b3803f47-4ff4-540e-91ac-1563f494e43b | note | Type of Record - WAE dwgs
80fa8c37-5c97-53ec-b8df-b454510dca0c | textbox | Initials:
| checklist | ITP - R054 - General Concrete Paving | itp | ITP - R54 - General Concrete Paving | b0d60f50-9dfa-4c85-9add-15c9d6a0c01a
| section | General Concrete Paving
| checkpoint | 1. Obtain conformance of granular foundation materials
6dd934fc-1404-5ffa-836e-0b8967067639 | note | Reference documents - R54.2.1, Annexure R54/L
848bba48-fd54-58a1-9d05-a0884005208f | note | Criteria/Test Method/Spec - Select Fill Type U must consist of a granular material with a particle size grading of 100% passing the 26.5 mm sieve and a Plasticity Index, determined by Test Method RMS T109, of between 2 and 12 (testing frequency 1 per 200m3 prior to placement)
00050514-1a9a-50fc-8ae8-5aa94deefdfe | note | ○ Class 2 DGB must comply with Specification RMS 3051.
adaa351d-ed2e-5191-bfb6-a70525077109 | note | Record for conformity - Test report
35814db5-fe3e-551b-bdb8-4efcd9111383 | note | Responsible Position - Project engineer
91b292a0-8c98-5e34-b15c-a483d3bd6200 | note | Type of Record - TP
| checkpoint | 2. Use approved concrete mix:
d24b4689-fe56-5d61-8147-d9295c9efd58 | textbox | Hold Point No.:
4f71299b-9edd-546a-a190-9efd603c4772 | textbox | Mix ID:
ddd18a7a-9f2d-5c0a-9fb0-0f76a81c4ade | textbox | Strength:
ca228c2a-4d4d-5749-97e7-8d1cbeb92b5a | note | Reference documents - R54.2.1.2 & R53.1.4
c5884b11-6ba6-5c7b-80a8-adbfb1f2fa48 | note | Criteria/Test Method/Spec - Refer to R53-MIX-lots for Concrete mix approvals (Hold Points)
200cb146-b522-560c-9eb6-10c07b47cd4c | note | Record for conformity - Mix report
6f589d8e-c876-5817-9b9b-7e1f74e30429 | note | Responsible Position - PV/PE
2ed27c9b-02b6-5e7b-937e-3e0bd965ed8a | note | Type of Record - HP
| signoff | HOLD POINT
| checkpoint | 3. Obtain Certificate of conformity for reinforcement supply
9dbb2614-b86b-5b63-a563-52123e56b6db | note | Reference documents - R54.2.2 & R53.4
74d63dab-887c-55bd-9d9e-6825a5dcc4af | note | Criteria/Test Method/Spec - Must comply with either AS/NZS 4671, AS1311 or the supplier is accredited with ACRS
d77d3d31-26f1-5fd4-9857-6c6f9f3b884f | note | ○ Galvanizing must comply with AS/NZS 4680
6cac8a72-686c-5726-8d28-093a056b1115 | note | ○ Welding must comply with AS 1554.3
83831a64-2a8e-53b1-a302-9e2160c14d7d | note | Record for conformity - Compliance certificate
c26ac846-f70c-5823-bc82-5389825d306c | note | Responsible Position - PV/Project engineer
e230a02a-bc7a-5f26-829a-200a5b8a95d5 | note | Type of Record - AP
| checkpoint | 4. Tactile Indicator Tiles
2ab7a743-17a6-5f6b-98d2-d4d3ca8cb1bc | note | Reference documents - R54.2.3
14d2f523-28be-512a-9a00-a8a127215505 | note | Criteria/Test Method/Spec - Tactile indicators must conform to AS/NZS 1428.4.1 and must be stain, slip, impact and UV resistant.
f821d44e-8cc8-599f-a207-70f9d8ac1788 | note | ○ Tactile indicators must have a colour contrast to surrounding surfaces and provide a luminance contrast to the surrounding surfaces of ≥ 0.3 (30%) as per Appendix E of AS/NZS 1428.4.1.
af770a42-8919-52d9-9adc-9820fdf7eef0 | note | ○ Adhesive (proprietary bedding material, as per AS 3958.1) for bedding tactile indicator tiles must be either cement-based adhesive or modified mortar (refer R54 Cl 6.1) which is not susceptible to deterioration from water infiltration and can withstand pedestrian and maintenance vehicle traffic loads.
a928bdc3-73ca-5ee1-ae9f-39eb76c7de90 | note | Record for conformity - Compliance Certificate
a900dc0a-c535-5e97-871e-97b158855ac6 | note | Responsible Position - Project engineer
9e480b88-c21a-52db-9c98-d6a7c1cd828e | note | Type of Record - AP
| checkpoint | 5. Obtain Certificate of Compliance for Preformed Joint Fillers
d4dfddc6-b12a-5b1e-b5c2-9fcbb6b3e9ce | note | Reference documents - R54.4.4.3
03f5212e-8a3c-5c57-87a0-352a5542d701 | note | Criteria/Test Method/Spec - Provide a certificate of compliance verifying that proposed product complies with the requirements of 3204 and NATA endorsed test documents. Certification must relate only to the composition on which the tests were made and valid for ≤ three years. New certification will be required whenever changes in product composition are made.
aa2ca34d-7892-52df-a23b-766e4b283326 | note | Record for conformity - Compliance Certificate
ffe22456-e471-50a9-8244-fde7ec98d03d | note | Responsible Position - Project engineer
91655141-7c07-54e7-b7a3-6dd76a7a0fda | note | Type of Record - AP
| checkpoint | 6. Designate concrete truck washout area (s)
f14620fb-5cd8-5640-8cc2-212cd5480b09 | note | Reference documents - R53.5
25138741-c4be-58a1-9c41-6aa043270daa | note | Criteria/Test Method/Spec - Impermeable plastic lined or approved equivalent bunded area
c0330677-bf9d-53ca-bbd4-02fdde0c2984 | note | Record for conformity - Verification Checklist
c9b8a42a-c33c-5a00-99b2-67f0a84c2f9f | note | Responsible Position - Project engineer
4fa4f30e-cfe6-5329-8ba1-cf80b85d7380 | note | Type of Record - IP
| checkpoint | 7. Excavation and Filling
b0ba3818-c43f-5014-99a4-2d3927f8f1c1 | note | Reference documents - R54.3.1
394baa9c-57ad-5370-9cc9-d7f066dc5cd9 | note | Criteria/Test Method/Spec - Verify area is excavated or filled to the levels shown on the design drawings or as directed by the Project Verifier in accordance with R44.
141d48d3-a44a-5ae3-9fda-7fce9542bb33 | note | ○ Surplus excavated material to go into general earthworks activities in accordance with R44.
06acad3a-e84f-52c5-92e8-1cfc81a57f49 | note | ○ Top up low areas to required levels using Select Fill Type U complying with R54 Cl.2.1.1.
adaa4785-ddfc-52cb-9f2f-57e88963e039 | note | ○ Where filling at the sides of Paving or behind kerbs unless shown otherwise on the Design drawings or directed by the Project Verifier, fill these areas with Select Fill Type U complying with R54 Cl. 2.1.1.
b3a45682-8aca-5092-8656-4c7006c78455 | note | Record for conformity - Verification Checklist
7cfe19d1-e0f3-59b1-bf45-22aace560999 | note | Responsible Position - Project engineer
a4904fcd-0fd5-5f1b-923f-d2a8b6ad4c66 | note | Type of Record - IP
| checkpoint | 8. Unsuitable material
4950f176-6211-5844-ad6f-b6a2e97d5693 | note | Reference documents - R54.3.2 & R44
85174046-1b42-52a2-8e6f-4fef6c8b35c3 | note | Criteria/Test Method/Spec - If any area of the foundation contains material that is unsuitable to support the proposed pavement, remove and replace this unsuitable material or use some other foundation treatment in accordance with RMS R44.
0b9ca9d9-af66-5dc3-b13d-3a8f7dcab4fd | note | ○ The Hold Point in RMS R44 regarding unsuitable material applies.
c183226b-a6a7-57ab-af69-60e16d751e11 | note | ○ Principal to be notified if found unsuitable materials
2b94f566-3e05-5822-9f79-b2d17381e21c | note | Record for conformity - Verification Checklist
2b529b39-0865-51a5-b3a3-9b97ce947ccf | note | Responsible Position - PV/Project engineer
134489ce-ee8b-55a3-8546-3fad57b51bae | note | Type of Record - HP
| signoff | HOLD POINT
| checkpoint | 9. Notify the GDR that unsuitable materials has been removed as directed
955ddd93-7c80-5e59-b7a3-4392152fe68d | note | Reference documents - R54.3.2 & R44.2.4.1
74805046-524a-52ff-81cc-b74bb5503a0d | note | Criteria/Test Method/Spec - Notification to the GDR is done after the removal of unsuitable material. The Geotechnical Design Representative will inspect the excavation and may require removal of further material as unsuitable material prior to authorising the release of the Hold Point.
22ce0940-c269-548a-ae59-eca599af3c3a | note | Record for conformity - Hold point
ff8a1d51-4252-5398-9acd-dd013598f456 | note | Responsible Position - PV/ Project engineer
41f026b5-b6c2-521a-8704-4c93686f1d76 | note | Type of Record - HP
| signoff | HOLD POINT
| checkpoint | 10. Granular Subbase
3e5ba998-bf03-5fde-929e-a50ec2285878 | note | Reference documents - R54.3.3
13379d76-ece8-5b72-aee3-0d6f0fc982f6 | note | Criteria/Test Method/Spec - Unless shown otherwise on the Design drawings, construct a subbase layer comprising Class 2 DGB20 beneath the concrete paving as follows:
2206df68-6397-59c4-b344-4d8bce83e0db | note | ○ Footpath: 75mm thick;
04b2abd4-9327-51db-9103-ec221b0ec349 | note | ○ Bicycle path/shared path: 150 mm thick.
48661e9b-6700-5a46-9ca2-0f35288dd442 | note | Record for conformity - Verification Checklist
12a28861-f955-593a-a278-3368d28d8d0c | note | Responsible Position - Project engineer
2c148eb8-6b10-59bf-8546-e86a7ee05a1a | note | Type of Record - IP
| checkpoint | 11. Compaction
9ef893df-e411-5fd1-9c71-2a21dd76c283 | note | Reference documents - R54.3.4
52fd0990-5ca0-50f8-b209-f3d7bf26b18d | note | Criteria/Test Method/Spec - Compact the subbase, foundation, etc to achieve the minimum characteristic value of relative compaction specified Table R54.1 hence:
c306dad0-f0fd-5cff-a251-b95e1c6d91d1 | note | ○ Under footpath, bicycle path or shared path & median
e4c7f1f3-387f-515d-bb91-aab85dcb207e | note | – Subbase layer (where required) ≥100%
f9e07fdd-8957-59f1-9daa-92f8f2dda7d9 | note | – Top 150 mm of foundation ≥ 98%
bf83e928-cd48-5534-a083-24dded00ace7 | note | – Filling below a depth of 150 mm from top of foundation ≥ 95%
82d95e69-60e2-586c-9386-3d2d87a2f58c | note | ○ Fill outside of footpath, bicycle path/shared path and fill at edge of paving and behind kerbs ≥ 95%
1df621ba-f578-5ac2-a192-c35dba6f291a | note | ○ Driveways to comply with the relevant Council’s requirements, unless specified otherwise in the Deed documents.
70a8bc87-7af9-5b06-b8e9-646555053098 | note | ○ Testing in accordance with Q6
cbd9f089-d46b-50b0-9c6e-e63c83850050 | note | Record for conformity - NATA Test Reports
e5983f58-8445-50e9-ae1f-cc38a7ebabc0 | note | Responsible Position - Project engineer
7f043f27-6fac-5802-b934-632de70b071a | note | Type of Record - TP
| checkpoint | 12. Check finished surface levels
75eb26dd-863b-5d86-a6d2-f282b809dc51 | note | Reference documents - R54.3.5
f454f43e-25b5-537d-a2dd-143555a17c6e | note | Criteria/Test Method/Spec - Construct top of foundation to the design surface levels, with a tolerance of +5 mm and -10 mm.
2d63c184-202b-5a6c-85cb-7f1e2e901aba | note | ○ The finish surface must not deviate from the bottom of a 3 m straight edge laid in any direction, by more than 10 mm, except at grade changes.
747ac126-cebb-5706-99b8-aee309566be9 | note | Record for conformity - Survey Report
548386b9-16b5-5204-9c26-f136188814d1 | note | Responsible Position - Project engineer
87016361-2300-5cf6-bc0e-424f2c825dc4 | note | Type of Record - Surveyor
| checkpoint | 13. Install steel reinforcement
8e82c29c-4231-5f81-bf2a-f1ef94e4bfe5 | note | Reference documents - R54.4.2, R53.4
b1bc98e8-8858-527a-8556-95ee1d32b10b | note | Criteria/Test Method/Spec - Provide steel reinforcement for concrete paving
1ea4225d-7f60-5391-84e2-2fb0d2c9c302 | note | ○ Where the steel reinforcement is not shown on the Design drawings, provide the reinforcement as specified in Table R54.2. shown on the relevant Council’s STD dwgs, unless specified otherwise deed documents. Reinforcement lap splices as per design drawings or R53 Cl4.
1db8a678-ddea-5f40-8124-3446620f66c6 | note | ○ Provide a minimum cover for the steel reinforcement in accordance with R53 Cl.4 hence 50 mm, unless shown otherwise in the Design drawings.
89317374-478c-5fb0-bae0-b46bccda22f5 | note | ○ For slab of thickness 120 mm and greater, fix the steel mesh within the top half of the slab.
fcd9c08a-331e-5828-a912-2c370fca5660 | note | ○ For slabs of thickness less than 120 mm, fix the steel mesh at the mid- depth of the slab. In this case, the minimum cover specified in R53 does not apply.
064fc785-64ce-5235-a027-2005bc14c544 | note | Record for conformity - Verification Checklist
40067b7e-baf4-5f8d-b922-9b90940f36e2 | note | Responsible Position - PV/Project engineer
3d5ceb72-e0d1-5638-bd38-36d190b8570d | note | Type of Record - HP
| signoff | HOLD POINT
| checkpoint | 14. Commence with pre pour planning activities
38f34142-1ea6-5da2-ae28-3a0562ead74f | note | Reference documents - R54.4.3, R53.6.3 & Annexure R53/E
f59d3fa8-348f-5d32-adb2-5af31d30b5e8 | note | Criteria/Test Method/Spec - Verify formed areas free of water, dirt, construction debris and any other foreign matter removed.
911848f5-0d36-5675-94b2-9f13c074a427 | note | ○ Rain not imminent, air temperature between 5- 38oC
3cc95643-afd2-5279-8646-51a3a385aed3 | note | ○ Concrete tester arranged as required
47c66bad-33fe-5aa9-aa2b-9a2855f68761 | note | ○ Bunded concrete washout area provided
2c0574f1-30df-5c43-a3d3-3db8dcee4798 | note | Record for conformity - Verification Checklist
5cbbd80e-670c-5b62-abe1-943bd6fda4d3 | note | Responsible Position - Project engineer
7b57c822-4d74-5205-8903-e80423316952 | note | Type of Record - IP
| checkpoint | 15. Notification for Placement of Concrete
a8f96b8f-4c58-5e3b-9bdc-bb971c0ea448 | note | Reference documents - R54.4.3 & R53.6.1
8bf652c4-4b57-5f96-bd0a-bfac4921a564 | note | Criteria/Test Method/Spec - As required for the preceding Witness Point hence:
6db6b3c8-615b-5f81-98c1-472f56ba62fa | note | ○ Notify the Project Verifier Representative, not less than 24 hours and not more than 3 clear working days prior to the intended time of commencing to place concrete, mortar or grout, when fixing of the formwork and reinforcement in position (if applicable) will be completed and when concrete, mortar or grout will be placed.
85df3ede-6423-5a4b-9d84-bf061d69641e | note | Record for conformity - Hold point
4152fa72-56e9-5734-92bd-5ced0799041a | note | Responsible Position - PV/Project engineer
d274b769-d776-5c92-8cfa-7e14a0d3e4df | note | Type of Record - HP
| signoff | HOLD POINT
| checkpoint | 16. Carry out the concrete pour
df2af9eb-e1ad-5e4a-8518-3393c4bd22ae | note | Reference documents - R53.6.2, R53.6.4 & Annexure R53/EL
cfde8d1b-5307-52e4-9b12-5891994bdc4b | note | Criteria/Test Method/Spec - Concrete docket checked for correct mix
aca563bb-dcae-5e97-97a3-4a2acc4b743d | note | – Unreinforced paving
3f7d45d7-e643-5ef1-bb91-4b63ccd3cfc4 | note | ○ N20, 80mm slump & 20mm aggregate
e42c5579-875a-571a-a7f9-9da1ad929e8e | note | – Reinforced paving N25, 80mm slump & 20mm aggregate
21657ba4-15e8-5850-ad8f-cd3eb11dd199 | note | ○ Ensure concrete is placed & finished to:
76cf47b2-98a5-5c26-9fad-8cdc5ad3c5a0 | note | (a) limit segregation or loss of materials;
935896ce-cda0-54b9-a725-cfffd757ca93 | note | (b) limit premature stiffening;
cb9b382d-2e0d-56d9-a2c8-9f6f64e9d8a9 | note | (c) produce a dense homogeneous product which is monolithic between joints and edges;
6ff3c298-6af8-5c3f-a21f-35f67554c7a9 | note | (d) expel entrapped air and closely surround all reinforcement and embedments; and
af111714-5981-5180-8e1f-9c34f098c9ba | note | (e) provide the specified thickness and surface finish.
2dbe1226-da7c-542d-9cfc-557998ad1576 | note | ○ Ensure the finishing unformed concrete surface
6a3d6509-f79d-5957-9332-d57d9854a8a3 | note | (a) has achieved the specified:
748a027b-b012-519a-ac30-5fe54bf1197e | note | (i) dimensions and grade;
9e237920-6fee-5657-83b8-87c9fa84a21c | note | (ii) cover from the surface to reinforcement
eea22b37-63c2-54a6-aa50-39b3fdf3d602 | note | (iii) texture of the surface; and
6a8ca188-0605-5984-9ff5-293a1e0db01a | note | (b) has avoided plastic or drying shrinkage cracks.
49de4acc-468a-5709-b96f-489dfb5b6aa3 | note | Record for conformity - NATA test report
f35898db-8c06-51b3-a871-173d5e0c6fe8 | note | Responsible Position - PV/ Project engineer
d094144c-8e79-5a70-b171-f860a67ca7dc | note | Type of Record - HP
| signoff | HOLD POINT
| checkpoint | 17. Transverse joints in pavement
5de625ce-9906-5937-9756-06abcb62e7f5 | note | Reference documents - R54.4.4.1
f0adeb98-5baf-513a-8963-65af4b2b1035 | note | Criteria/Test Method/Spec - Transverse joints must be constructed at right angles ±6° to the longitudinal edge of the paving slab, otherwise the slab will be treated as odd shaped slabs.
9a1ed840-4df1-52a7-a4ac-f0f25693114a | note | ○ Avoid where possible creating odd shaped and mismatched slabs.
5c6dd6f2-8613-5837-af27-29b4402efb44 | note | Record for conformity - Verification Checklist
4068cb20-5349-5d38-8dcf-dc214d0439c9 | note | Responsible Position - Project engineer
323450f0-09f7-5acd-979a-acba58101356 | note | Type of Record - IP
| checkpoint | 18. Movement joints in pavement
e45376a4-abfc-5091-81fd-ab3bee88290f | note | Reference documents - R54.4.4.3
3c2f2364-f396-5a81-8157-48f6a39472aa | note | Criteria/Test Method/Spec - a) Footpaths and Medians
50db16d2-5ab6-5932-92ae-b3b818579277 | note | ○ Provide contraction joints 3 mm wide and 25 mm deep at every 1.5 m length of footpath or median paving.
4f29f80b-94f2-59c1-9301-7af80cdd5c94 | note | ○ Provide expansion joints at intervals not exceeding 6 m and at the location of expansion joints in adjacent kerbs.
2abf0711-2fa7-58f2-9e6a-66022d8991dd | note | ○ Provide isolation joints along median paving where the paving abuts against kerbs, gully pits, retaining walls and bridges.
7445e4dc-2f4a-53d2-8efd-94a9cf130e29 | note | ○ Expansion and isolation joints must be 10 mm in width for the full depth of the paving and filled with a preformed joint filler in accordance with Specification 3204
22a89d23-7c93-5685-b87c-e5eef7b59f66 | note | (b) Bicycle Paths/Shared Path
b986eb35-701e-594d-887b-491285d70694 | note | – Provide movement joints as shown on the Standard Drawings.
535c302e-eb4f-5d16-a247-12dd4540da89 | note | (c) Driveways
0a41db22-4a1c-55fe-9d29-f110e365b959 | note | – Provide movement joints in driveways at the locations shown on the relevant Council’s
77062309-fec6-5309-9b66-afe19bfed127 | note | Record for conformity - Verification Checklist
2f5ac407-be89-515f-b6ea-bad02787ca64 | note | Responsible Position - Project engineer
1bb98af1-bc97-5bb7-a186-1b3684d1ded1 | note | Type of Record - IP
| checkpoint | 19. Finished paving surface
428306ed-22f4-5435-934b-aa7ecfb87c70 | note | Reference documents - R54.5.1
42f6cdd8-6ff9-5e95-87e7-12799674f2b2 | note | Criteria/Test Method/Spec - ○ Provide on the top surface of concrete paving (except patterned concrete paving) the surface finish specified in Table R54.3
e608276a-dce1-5586-bd99-dd595596c1de | note | ○ The finished paving surface must be uniform in colour and appearance.
712f048e-f1e3-5f73-be6a-dd17b6486a45 | note | ○ All edges, except for those abutting other paving or structures, must be neatly rounded to a radius of 10 mm. Edges abutting other paving or structures must be neatly rounded to 5 mm radius.
f5956e1b-fc80-53a8-b7e3-15558d97e07c | note | Record for conformity - Verification Checklist
00d35491-dcf5-5bfb-baba-9539667e0b9a | note | Responsible Position - Project engineer
d735da10-264e-58e0-8117-b97df4499d13 | note | Type of Record - IP
| checkpoint | 20. Curing & protection of concrete paving
7d7aa3ed-0f38-548f-991d-a1186df4035c | note | Reference documents - R53.7.1, R53.7.2 & R53.7.3
6c0d0ca1-c382-5751-9918-cb29ada3e98f | note | Criteria/Test Method/Spec - Only approved curing compound to be used (refer to R53.7.3 for details)
3917f3f7-76a2-56aa-a0cc-f1260ec6d532 | note | ○ After initial set of concrete; surface is firm and free of bleed water, apply curing and cure for at least 7 days
4f50b1f2-3e86-5583-bac1-df3fb75d7080 | note | ○ If Moist Curing, immediately after concrete has taken its initial set, spray all exposed surfaces with water and keep the concrete continually wet for at least seven (7) days. The water used must be free from ingredients harmful to concrete.
b26d5c32-2961-5852-ac6e-1825838ddc41 | note | ○ For Curing Compounds apply in accordance with manufacturer’s recommendations or at a spray rate min. 0.2L/m2 whichever is the greater
9a28c0ac-e2ec-571c-84b6-4b526174609c | note | ○ Ensure all exposed surfaces receive a uniform cover of the curing compound.
ab141006-4ccc-501e-ae86-8a84786dd659 | note | Record for conformity - Verification Checklist
11237612-80e0-5f2b-a07c-b3154a954c32 | note | Responsible Position - Project engineer
23e3010a-8018-5dd2-befe-cf8421cbd649 | note | Type of Record - IP
| checkpoint | 21. Submission of patterned concrete paving details
9e9307fb-54a9-5b46-bd54-de15cb08dff5 | note | Reference documents - R54.5.2.1
120a2a29-f0c9-57db-a1ef-051989cd4d40 | note | Criteria/Test Method/Spec - Provide details of pattern, colour, class of finish and experience of personnel in producing patterns on concrete paving, at least 5 working days prior. The Project Verifier may require a sample panel to be prepared and submitted.
0c2997aa-7e81-5d7d-b8be-64019ac3c927 | note | Record for conformity - Hold point
4a52b679-ef64-5976-bf20-1e4af885bd97 | note | Responsible Position - PV/Project engineer
cc2216ee-4aeb-5618-8104-ac3151a686e8 | note | Type of Record - HP
| signoff | HOLD POINT
| checkpoint | 22. Procedure for constructing concrete paving
1ff3e6a9-69a0-5bbc-8b56-4f178ecb1887 | note | Reference documents - R54.5.2.2
c8f1ba6d-6f34-5cea-b7b0-9383271628f8 | note | Criteria/Test Method/Spec - Apply the stencil only after the bleed water has evaporated from the concrete surface.
cf6d2a91-5f64-5a3a-923d-3fe1f4444c92 | note | ○ Apply each coat of colour hardener at a consistent rate achieve a total thickness of between 3 mm and 4 mm.
e4282ce3-f58a-5844-8fbb-cb9f9cb8ed73 | note | ○ On removal of the stencil, the surface must exhibit a well defined pattern with no edge ravelling.
6f8a5349-5aac-5589-9808-215dda4b8144 | note | ○ Apply a suitable sealer to the finished surface within 24 hours of forming the pattern, followed by a second coat of sealer 3 days later
daad56aa-36b9-5bd0-b357-d629c6d19bb6 | note | Record for conformity - Verification Checklist
a5e56bbf-3441-5acf-b5cb-3965626e18df | note | Responsible Position - Project engineer
a82bfbc7-ee52-5a17-b2c6-0f6ad75f6a24 | note | Type of Record - IP
| checkpoint | 23. Finished surface levels
81a3f1fa-dd5e-55ee-91aa-141b68ef9bae | note | Reference documents - R54.5.3
85dfeff0-df51-5cd0-84f1-43eba7a635b7 | note | Criteria/Test Method/Spec - Verify finished surface of the concrete paving conforms to the design surface levels, with a tolerance of +10 mm, –5 mm.
a372999d-3349-5a7d-b063-cb996d23867b | note | ○ Verify the finish surface does not deviate from the bottom of a 3 m straight edge laid in any direction, by more than 5 mm, except at grade changes.
603ec8c6-8802-5a96-b06d-c72c5dc5b5a4 | note | ○ Where the concrete paving abuts an adjacent structure, any vertical step across the joint must not exceed 5 mm unless shown otherwise on the Design drawings
f686b729-bfbb-51ce-8e08-99ee1f2dd086 | note | Record for conformity - Survey Report & Straight Edge Test Results Summary
6d8e5d40-ea3a-5286-ac38-19b167d7becc | note | Responsible Position - Project engineer
e6a4d69c-ce33-5ecf-be1d-3927ad8c22a5 | note | Type of Record - Surveyor
| checkpoint | 24. Submission of details of proposed tactile indicator tiles
45238034-4801-52ac-8008-1dde04de07be | note | Reference documents - R54.6.1
338836b6-bf1c-5a2d-950b-c5eda923ce34 | note | Criteria/Test Method/Spec - Provide details of proposed tactile indicator tiles, associated materials (such as adhesive), and installation method to the Project Verifier
02870dc3-d9cb-5c73-97d7-20b0764998a7 | note | Record for conformity - Hold Point
9facc13d-72c0-502f-a777-51c909cd8401 | note | Responsible Position - PV/Project engineer
f3d59b0a-6ad9-5a0d-9427-26bcf615952e | note | Type of Record - HP
| signoff | HOLD POINT
| checkpoint | 25. Installation of Tactile Indicators
db8b8c24-ad08-5ebd-af94-2037801e91f2 | note | Reference documents - R54.6 & AS 3958.1
5691bd0f-46b5-569a-b8f1-2d8af4116d54 | note | Criteria/Test Method/Spec - Ensure tactile indicators will be installed at locations as shown on the Design drawings.
da51482e-2eed-5986-b51b-f2e87d1967f9 | note | ○ Performance level of Tactile indicators is “Commercial” and follow installation guidelines as detailed in AS 3958.1Cl.3.3.1.2 (Exterior floors – General applications, using cement-based adhesive or modified mortar)
2abe8562-3831-5e7b-86ff-c9145980764e | note | ○ Prior to installing the tiles, allow the concrete to cure for 7 days (as per R53), or a duration recommended by the tile adhesive manufacturer to suit the adhesive used.
0dd3a6ab-926b-5a94-95eb-6974fa355c2e | note | ○ Prior to placing tiles, clean concrete slab of dust using water jets, and any contamination using where necessary high pressure hydro-blasting, sand/grit blasting or mechanical scabbling.
6a0b95fa-d059-58d7-b487-38f363bc7fb2 | note | ○ Install tiles so they are fully bedded, without any voids beneath them.
7b674090-9057-5b98-b7d5-b56670feb681 | note | ○ Install tiles at the tile manufacturer’s recommended spacing. Pack the spaces between tiles with grout, and free of all voids and
a47194ca-a4f2-5fab-ae23-7e37e7fc46e0 | note | ○ Do not allow traffic over freshly grouted joints for at least 7 days, unless recommended otherwise by the manufacturer.
86965978-9cb9-5959-978e-c8506881a09e | note | ○ Install movement joints at locations where:
c084c356-83ff-5fa4-8419-9c60bd4af1ce | note | – tiles abut restraining surfaces;
040d468b-2504-5ce0-9aee-4b0cb78c64bb | note | – joints exist in the concrete below the tiles;
05edc3c5-c3f6-5d93-af8b-a6eaf44a88f9 | note | – a change of plane exists in the tiled surface
89452588-e328-57b5-9225-505ff3d19e29 | note | ○ Install the tactile indicator tiles such that the base surface is sitting flush with adjacent concrete surfaces.
009cecea-0163-55db-a60a-23e5ef43667f | note | ○ The finished surface level of the tiled surface must comply with the requirements of R54 Cl. 5.3 pits. Remove any excess grout or grout film.
59b691f8-06d2-5863-b303-d56c27a02bf6 | note | Record for conformity - Verification Checklist
43e65178-fa22-5671-84dd-290e2837601b | note | Responsible Position - Project engineer
6933a4b9-3c17-5d23-b285-7c4a6686cdc8 | note | Type of Record - IP
| checkpoint | 24. Submission of details of proposed tactile indicator tiles
d80e6310-2818-5f4f-8a06-078a5c19e4b9 | note | Reference documents - R54.6.1
e5b66ece-f947-5d52-ae69-374e8d1e55af | note | Criteria/Test Method/Spec - Provide details of proposed tactile indicator tiles, associated materials (such as adhesive), and installation method to the Project Verifier
3c5515a9-5479-5c7d-b61c-f2c69ea8c96f | note | Record for conformity - Hold Point
473ba04c-f6d5-5225-a9fd-b030554e55df | note | Responsible Position - PV/Project engineer
711bf47f-fb16-5821-b9c1-8e591c82dfbe | note | Type of Record - HP
| signoff | HOLD POINT
| checkpoint | 25. Installation of Tactile Indicators
a64ed327-29bf-5cf2-b6f8-bbefc5d16f1a | note | Reference documents - R54.6 & AS 3958.1
6471ab59-ea3f-526e-9bea-fe05f35dd395 | note | Criteria/Test Method/Spec - Ensure tactile indicators will be installed at locations as shown on the Design drawings.
5209172b-1291-5426-8384-a9734c532b60 | note | ○ Performance level of Tactile indicators is “Commercial” and follow installation guidelines as detailed in AS 3958.1Cl.3.3.1.2 (Exterior floors – General applications, using cement-based adhesive or modified mortar)
2952cf7d-6a3f-51cf-b286-f60046e541f7 | note | ○ Prior to installing the tiles, allow the concrete to cure for 7 days (as per R53), or a duration recommended by the tile adhesive manufacturer to suit the adhesive used.
78398011-7017-516e-a862-880a94d6583e | note | ○ Prior to placing tiles, clean concrete slab of dust using water jets, and any contamination using where necessary high pressure hydro-blasting, sand/grit blasting or mechanical scabbling.
5a1df0fd-1a7a-5a1c-b3a3-df762a990c7f | note | ○ Install tiles so they are fully bedded, without any voids beneath them.
30f4e333-2c3c-53e6-9135-9ab268d9cf94 | note | ○ Install tiles at the tile manufacturer’s recommended spacing. Pack the spaces between tiles with grout, and free of all voids and
3044790e-b762-5b42-8434-d9dfe554b885 | note | ○ Do not allow traffic over freshly grouted joints for at least 7 days, unless recommended otherwise by the manufacturer.
4f766536-cc27-5464-897a-4ce7eb96da70 | note | ○ Install movement joints at locations where:
6a5e014e-0288-5341-b365-0bb917b4f7c4 | note | – tiles abut restraining surfaces;
903c5ee5-6974-5a3b-a8da-9a686b5b0a5d | note | – joints exist in the concrete below the tiles;
ee44e0ed-fbf2-59bf-bc8c-3aa6f28e19a1 | note | – a change of plane exists in the tiled surface
6a6228fc-1d5e-5dc0-86b3-67fc1d84de89 | note | ○ Install the tactile indicator tiles such that the base surface is sitting flush with adjacent concrete surfaces.
41e966db-c677-5530-8b72-d8aaa6e5ad8a | note | ○ The finished surface level of the tiled surface must comply with the requirements of R54 Cl. 5.3 pits. Remove any excess grout or grout film.
dc445d20-6e4e-55f1-8791-b088a959321a | note | Record for conformity - Verification Checklist
38823edc-5458-5298-a91d-56b0947b1769 | note | Responsible Position - Project engineer
66b7cec4-ff4b-526a-9061-43c923af0512 | note | Type of Record - IP
| checklist | ITP - R101 - Cold Milling of Road Pavement Materials | itp | ITP - R101 - Cold Milling of Road Pavement Materials | c454a5bb-04b8-4ba2-b1a0-56c37f49b5b5
| section | Cold Milling of Road Pavement Materials
| checkpoint | 1. Cold milling of work area.
d3472b3a-49a0-5588-8b58-6723c0871538 | note | Reference documents - R101.3
8f8ef21d-c339-5031-afe2-b3af23363895 | note | Criteria/Test Method/Spec - Submission of verification documentation, the marking of milling depths and locations of all Hidden Objects on site, records and calculations of the areas to be measured under Pay Item R101P6
7c2e10a2-35a5-5f58-baf3-706a74041360 | note | Record for conformity/Inspected by - The PV will consider the submitted documents prior to authorizing the release of the Hold Point.
2a40eb2b-ecc3-5be7-a770-b7a5ff695530 | note | Type of Record - HP
df919fa6-0271-599f-ad21-6b8b708e41fe | note | Responsible Position - PE/PV
a8acb1cb-4b98-599a-ab66-c68cc8d41ff1 | textbox | Initials:
| signoff | HOLD POINT
| checkpoint | 2. Milling to achieve depth of cut and PV inspection
0b01ef2d-1415-58ce-8216-859a4dae4d52 | note | Reference documents - R101.4.2
b19c1b36-0991-5278-b72c-d160f294c2cf | note | Criteria/Test Method/Spec - Depth of cut and other associated terminology is shown in Figure R101.1
12a27d21-a353-58a0-80ed-8711971c35b7 | note | ○ Covering of milled work area and the removal of the cold milling machine and cleaning plant from the site (after milling to specified depth of cut).
8731b1b8-fa5c-5a78-bb59-7d83102c0058 | note | ○ Written notice to the Principal at least 24 hours in advance of the time when the floor of the milled area will be available for inspection.
b03c9868-4a5a-5c9b-af44-73721d5afd44 | note | Record for conformity/Inspected by - The PV will inspect the completed work prior to authorising the release of the Hold Point.
99cf7093-2315-54a6-9f53-91896e2863aa | note | Type of Record - HP
c074330e-5e16-5acb-9e51-28b2552e2134 | note | Responsible Position - PE/PV
d97b1e6d-c836-5781-8066-e9d05edd7583 | textbox | Initials:
| signoff | HOLD POINT
| checkpoint | 3. Survey check level of cutting
3049713b-b4d5-5e2b-893c-d8f8be9ec78f | note | Reference documents - R101.4.1 R101.4.3
b3a95d2b-2601-5ec5-a588-84ef2f2f1d3b | note | Criteria/Test Method/Spec - Depth of cut and other dimensions must comply with the tolerances specified in Table R101.1. Report levels to the nearest 5 mm
abbdc079-68b6-5e29-9741-c2601b053c54 | note | Record for conformity/Inspected by - will inspect the completed work and view the Survey Report (if required by Annexure R101/A) prior to authorising the release of the Hold Point.
4e8fd32f-5b2c-50ff-910f-81bfe0b71e6a | note | Type of Record - HP
47543f4a-8f48-5168-bb1c-54472ab7230d | note | Responsible Position - PE/PV
bf73e146-9117-5506-803d-fb4913b5242c | textbox | Initials:
5e032300-ebd5-57da-9317-608742c79d42 | date | Date:
| signoff | HOLD POINT
| section | MILLING OF ASPHALT OVER CONCRETE STRUCTURES
| checkpoint | 4. Investigation of thickness of asphalt over concrete structure
b1ec70fe-ffd8-5f16-81d7-8457fe29e7d8 | note | Reference documents - R101.4.6.1
82f29543-2abc-5022-ac09-8035238b9fad | note | Criteria/Test Method/Spec - Carry out the investigation as follows:
3f735684-b3f2-5d28-a9da-595612376441 | note | (a) Determine the proposed pattern of milling works and mark on the pavement the lines of movement of the depth sensing foot on each side of the milling machine.
ad751639-c0de-5afc-8f4f-87ca5f29430a | note | (b) Investigate the thickness of asphalt by taking small diameter cores (e.g. 25 mm), at 3 m intervals (over concrete bridge elements) or 20 m intervals (over other concrete structures) along each line of movement of a depth sensing foot, at least 24 hours prior to the commencement of milling.
d5d1d99b-3219-5346-a75d-d974238e4f12 | note | Record for conformity/Inspected by - Submit the findings of the investigation to the PV at least 24 hours before commencemen t of milling.
8f1a0dfc-19e3-5453-867e-dcc8bfc10bae | note | Type of Record - IP
c45e5bdd-d5a4-5203-bcbe-23883cfef7ee | note | Responsible Position - PE
8a1cc7cf-214a-5246-88c9-609104a451c6 | textbox | Initials:
4512f01b-1528-5403-aa0d-c193f6183327 | textbox | Date:
| signoff | Sign:
| checkpoint | 5. Revised scope of work based on investigation
35473606-2e91-5e7f-ba53-aadf00a00491 | note | Reference documents - R101.4.6.2
56cdac9a-0609-57ca-bbc2-42aa057be105 | note | Criteria/Test Method/Spec - Milling of asphalt, including trials, over each Concrete Structure or where the planned base of cut is within 40 mm of the top surface of a Concrete Structure and/or waterproof membrane that is to be retained.
7b6584a6-e895-5ae2-83b1-1dcde2f31c54 | note | Record for conformity/Inspected by - Notify the PV not less than 24 hours prior to milling of the time and date of commencemen t of milling and the time and date the proposed depths of cut will be marked on the surface.
21a9487d-18ef-5a4d-b91b-ac7778d61145 | note | Type of Record - HP
b7c3a01a-4e9b-5415-8086-1c13b8593e74 | note | Responsible Position - PE/PV
50d7b625-e40d-51f7-9d4f-409b42860595 | textbox | Initials:
23a81f21-2dce-5210-8c14-27c7a5574549 | date | Date:
| signoff | HOLD POINT
| checkpoint | 6. Milling operators
6b9bbd7a-1e2b-5378-951e-8cf4b085dc16 | note | Reference documents - R101.4.6.3
7c96fb38-640f-58f2-a429-4116363fdbfb | note | Criteria/Test Method/Spec - Milling operators must have adequate training and experience in the operation of the cold milling machine (including automatic sensing equipment). Provide three suitably trained and skilled milling machine operators at the cold milling machine at all times as follows:
f1ff0f13-4117-512e-b96e-a4ff5f3f9d32 | note | (i) one on the driving platform;
8b3aa704-6d52-5871-87dc-4713889480e0 | note | (ii) one on each side of the machine generally in the vicinity of the sensor/cutting mandrel.
40ed96b9-f4fd-585e-8ebf-e4f78206ceec | note | Record for conformity/Inspected by - VOC or tickets
ed10b641-0202-567c-b5bf-77af8be035ba | note | Type of Record - AP
9e693743-8757-5ec9-925f-f8dcb0e5e7f5 | note | Responsible Position - PE
| checkpoint | 7. Equipment requirements
7fd92907-8e40-5979-abe7-50139c65b6a9 | note | Reference documents - R101.4.6.4
f820dcb5-4449-5c82-a9f7-096070cb2145 | note | Criteria/Test Method/Spec - Equipment should Comply with the following:
b7ab1259-92d2-5a79-8df7-fae5bb9ac209 | note | (a) Maintain the milling machine in “as new” condition and, unless approved otherwise by the Principal, fit the milling machine with a “fine” cutting drum which provides for tooth cut spacing not exceeding 10 mm;
728be481-dba6-5aed-ae8b-df7c5b67c8da | note | (b) Conduct a cutting trial using the same machine at the commencement of each working shift and after any repair or adjustment to the machine during the works. The trial must include the operation of depth sensing feet and depth adjustment equipment;
e8201a1d-bb74-51df-808c-c64c6f209f72 | note | (c) Equip each operator with a gauge to measure the depth of cut in millimetres.
4016bb34-5ef3-509f-b3d9-570d155c7023 | note | Record for conformity/Inspected by - Visual check
51642124-829b-5642-8c55-0826aa66ec15 | note | Type of Record - IP
1879f4f8-c11a-51af-bc8e-b9ad5825a656 | note | Responsible Position - PE/Forman
| checkpoint | 8. Milling procedure
d6f16c86-e053-584f-a990-0944bdd2d436 | note | Reference documents - R101.4.6.5
42cd082c-07fe-5db8-bc75-832cc9474066 | note | Criteria/Test Method/Spec - Written notice to the PV together with proposed procedures for the work at least 7 days (except for Clauses 4.6.1 and 4.6.2 where it is 24 hours) prior to the commencement of milling work.
f5b2cebe-b0cc-5246-95b1-09ea8656957e | note | Record for conformity/Inspected by - The PV will assess the submission, and may require submission of further details on the effects of milling on the bridge structure, prior to authorising the release of the Hold Point.
3106ef0e-fcd4-53d3-b9bf-510294afe47a | note | Type of Record - HP
58786de0-89d9-563b-ad68-6d27463fd06e | note | Responsible Position - PE/PV
| signoff | HOLD POINT
| checkpoint | 9. Non-conformity due to contact between the cutting teeth of machine and concrete structure
13013cfc-4883-5304-8b26-f544bf73a5c6 | note | Reference documents - R101.4.6.6
5287e550-a2aa-59b1-983d-c470fd7ee6c6 | note | Criteria/Test Method/Spec - After the cutting teeth have contacted the concrete, notify the PV immediately of the incident and submit details of the cause and the proposed course of action.
0fb8542e-0411-5855-ab0d-2f5cf03dd528 | note | Record for conformity/Inspected by - The PV will assess the submission prior to authorising the release of the Hold Point
06ddb558-9941-5856-9d55-a91233c5646f | note | Type of Record - HP
630fb124-5c32-596d-89e3-7921bfe5d50a | note | Responsible Position - PE/PV
| signoff | HOLD POINT
| checkpoint | 10. Further Milling of Pavement
05ecf091-cf64-5650-95c2-26a3abc356af | note | Reference documents - R101.4.6.6.
685b74b8-8cc8-5654-8377-e2f45d16acf8 | note | Criteria/Test Method/Spec - After any change to the pattern of the cut surface due to broken or worn cutting teeth, notify the Principal immediately of the incident and submit details of the cause and the proposed course of action.
09c3203f-b055-54b9-a131-35c97bd84ded | note | Record for conformity/Inspected by - The PV will assess the submission prior to authorising the release of the Hold Point
3f71e07d-2b1a-5316-a6e7-529e7767042d | note | Type of Record - HP
581f5df5-63ae-556f-a622-975fb1783c3c | note | Responsible Position - PE/PV
| signoff | HOLD POINT
| checkpoint | 11. Unsuitable materials
ec0e82e3-8ec2-5dd1-85c0-549dcb7c4313 | note | Reference documents - R101.4.8
29ab6176-4ecf-52c4-a94c-e33e0de1ca40 | note | Criteria/Test Method/Spec - Written notice to the PV of the time that the removal of the unsuitable material will be completed and be available for inspection.
560b9c0b-c8ad-503f-bcd1-3750d2fa6be5 | note | Record for conformity/Inspected by - PV will inspect and consider the depth of excavation of unsuitable material, to determine whether a sufficient depth of unsuitable material has been removed, prior to authorising the release of the Hold Point.
d3ce8426-1421-54f7-9471-d7a57cc31195 | note | Type of Record - HP
a3c0b27f-1f15-5c95-96d6-a2c2c875929e | note | Responsible Position - PE/PV
| signoff | HOLD POINT
| section | TEMPORARY TREATMENT AT EDGES OF MILLING
| checkpoint | 12. Transverse Joints
dc3a7702-1af2-5b0e-9da3-a12359c09ddb | note | Reference documents - R101.4.9.i
6469d93e-d024-55ee-871b-ccd9cd844bbf | note | Criteria/Test Method/Spec - A minimum taper length of 2.5 m for each 50 mm variation in levels or part thereof for areas where the speed limit exceeds 60 km/h and a minimum taper length of 1.5 m for each 50 mm variation in levels or part thereof for areas where the speed limit is less than or equal to 60 km/h
70d7e4f8-e631-52d9-acdc-d6437195501c | note | Record for conformity/Inspected by - Visual inspection
8686cfc6-898d-542b-9695-3523960bf9de | note | Type of Record - IP
04d45059-a4f4-5987-ba77-31812a377e0a | note | Responsible Position - PE
| checkpoint | 13. Longitudinal Joints
a4e2fddd-5824-5a8c-9581-13ac8f89cdad | note | Reference documents - R101.4.9.ii
4cfac0b0-62a7-5a8e-b8f4-77117c085d6c | note | Criteria/Test Method/Spec - Where traffic is required to travel on a longitudinal edge, provide a ramp of minimum 1.0 m length for each 50 mm variation in levels (or part thereof)
1f3d9d78-bda4-582f-9af5-c7f8cf7790fa | note | Record for conformity/Inspected by - Visual inspection
d7f234d4-ca91-56b5-80df-65bdb68b2121 | note | Type of Record - IP
435c81ac-0542-5a97-9bb1-e5754e6d5e40 | note | Responsible Position - PE
| checkpoint | 14. Interface with Structures
e6a9f2fb-86ca-516e-af1a-5b9420d7bbed | note | Reference documents - R101.4.9.iii
c65203e1-de27-57d4-9e38-2b395221aa50 | note | Criteria/Test Method/Spec - Form and compact asphalt ramps around manholes, gully grates, utility covers or other similar structures unless otherwise directed by the PV. The ramps must have a minimum taper length of 1.5 m for each 50 mm depth of cut (or part thereof).
1159f03c-461e-5885-b8e3-0c6a87742425 | note | Record for conformity/Inspected by - Visual inspection
a61ca4b6-2bdc-5cdd-9386-1bb2e5850fdf | note | Type of Record - IP
55d478eb-b730-5098-918f-440ce7b109c1 | note | Responsible Position - PE
| checkpoint | 15. Clean up and dispose foreign items
2571fff0-a38d-57c9-aa8b-e811c43e8af4 | note | Reference documents - R101.4.10
56333bed-36e1-5b1d-8465-de277285fe36 | note | Criteria/Test Method/Spec - After the completion of cold milling, remove all loose milled material. The material removed will become your property unless otherwise specified in Annexure R101/A.
a54481b0-185b-533a-9117-1f26496542ca | note | ○ If the milled material remains the property of the Principal, deliver the milled material to the stockpile site(s) nominated in Annexure R101/A. Shape the milled material in uniform stockpiles with regular sides and, where appropriate, slope the top to promote water runoff. Clearly identify the milled material by signposting.
53340eae-7a96-5fcf-b043-a825623b54b6 | note | ○ If the milled material becomes your property, remove it from the site in accordance with the Waste Management Plan
5ecdb8ee-6f47-50a7-8373-797ec73d77d8 | note | Record for conformity/Inspected by - Visual inspection
d58f9518-a501-5830-bca3-d7add95a0dbe | note | Type of Record - IP
be443b97-28f2-59c3-8a75-9d55daa3fb8a | note | Responsible Position - PE
| checklist | ITP - R106 - Sprayed Bituminous Surfacing | itp | ITP - R106 - Sprayed Bituminous Surfacing | 30deca7d-4a0a-470b-b6fd-41807c3d67dd
| section | Sprayed Bituminous Surfacing
| checkpoint | 1. Prepare Safe Work Method Statement.
4e53d222-a5bc-5a94-a8b6-b4bef4d25fd1 | note | Criteria/Test Method/Spec - WHS Act 2011, WHS Regs 2017
4d6dab2a-ac40-5225-817f-68fd02d11e01 | note | Inspection/Test Frequency - Prior to commencing
3b2d6860-9fc6-5d64-8c5a-b1244fc0def6 | note | Inspection/ Test by - PV
dfd4fa1c-8e4f-5027-b51f-ab5d42d2385c | note | Responsible Position - Site Supervisor (SS)
ea6af761-f587-5fe5-82ad-a21e3f0fbecb | note | Type of Record - SWMS, HPR Form
2a86eae6-ebbf-5ec3-8f3a-0e6bbb2d2223 | textbox | Initials:
| checkpoint | 2. Submit nominated design including supplier certificates for bituminous surfacing
f3b418b3-e8da-5af0-a81f-f92c92c2aa90 | note | Criteria/Test Method/Spec - Table R106.1 RMS Form 395A & 395K R106.3.3.3, Release of Hold Point
666b0b45-760d-568c-ba15-0dafa5a270f6 | note | Inspection/Test Frequency - Annexure R106/L
7b75d98f-708f-53c0-ab1d-603403a351c5 | note | Inspection/ Test by - PV
aedcb974-2028-5add-be71-4f7a240647d8 | note | Responsible Position - PE/PV
5e184ec3-d8ee-573d-85ca-9004a54e8350 | note | Type of Record - Supplier comp certificate Form 395A Form 395K, HPR Form
ce840e11-12ec-51db-936e-dbdf3e6c719b | textbox | Initials:
| checkpoint | 3. Submit Aggregate lot details and reviewed target application rates
d29f0c0f-02eb-5b1a-a830-fbe42fffb024 | note | Criteria/Test Method/Spec - RMS 395K form. R106.3.4, Release of Hold Point
8df24203-c866-5ec9-ac6a-4b5a8d143ecb | note | Inspection/Test Frequency - Each lot
1fea1960-b308-513e-a98d-a0575bfd9df5 | note | Inspection/ Test by - PV
aa17b98c-94cd-53f6-a036-4c622c3e0a35 | note | Responsible Position - PE/PV
a9801f81-7824-59b2-aba2-02d75a8db69c | note | Type of Record - ALD test rep Form 395K HPR Form
fc6e110e-f70e-5016-b29b-ebd1dd2ba4e0 | textbox | Initials:
| checkpoint | 4. Prepare pavement surface by sweeping and removal of any foreign material. Surface slightly damp for spraying of primer
eb88aca6-dbaa-594f-a9d4-b57101e52974 | note | Criteria/Test Method/Spec - Visual Inspection
2678c17e-e643-554e-98ee-d93c4b6a7466 | note | Inspection/Test Frequency - Each lot
bc24fabe-b681-525a-a016-507d6bee74b9 | note | Inspection/ Test by - SS
677f9903-e3b0-5654-9a06-08729dff6ba9 | note | Responsible Position - SS / PE
9a540eac-7d01-50b8-835f-f1cf60d79c32 | textbox | Initials:
| checkpoint | 5. Commencement conditions
6079b302-b1c8-54dc-a7e8-fb2c78b97eed | note | ○ Measure pavement temperature
19cad1bd-4e0d-57ab-83ed-df17ae248486 | note | ○ Don’t commence if wet pavement or when rain appears imminent/ during strong winds/dust storms.
209f5db4-2873-55fc-852c-948c7142dba3 | note | ○ Sprayer has current RMS Form 354
7746db90-fca3-5657-b23f-f3703e4f595b | note | Criteria/Test Method/Spec - Pavement temp >10°C
b014c484-d6a2-51cb-90f7-8992ce7bdde1 | note | Inspection/Test Frequency - Each lot
60d73e74-1263-52a5-b20b-ac13070ec6b3 | note | Inspection/ Test by - SS
f11c15f8-781a-50d8-abc8-aad85d4edfc9 | note | Responsible Position - SS / PE
41d19b71-675d-52ba-9125-b3417078918c | note | Type of Record - Form 354
ff57f3ea-2404-55e4-990f-14664edeba6e | textbox | Initials:
| checkpoint | 6. Apply Primer: Spray commences & ends on paper Actual application rate determined after each run using dipstick. Binder temp at application recorded Overlap btwn adj long’l runs 50mm.
d8a5c126-30da-5a69-9fd9-695660949aef | note | Criteria/Test Method/Spec - Note: Target hot application rate = 0.91/m2 Temperature: 10-30°C
26f2c66b-ade9-5f40-83ce-9550298ee190 | note | Inspection/Test Frequency - Each lot
dd2d2c36-8f53-5e58-b2b7-0ca76c51ff71 | note | Inspection/ Test by - SS
3d3564c5-02cf-547e-8a63-3e1294f179fd | note | Responsible Position - SS / PE
4f126320-fe22-5e9b-9578-ab126c8152bf | note | Type of Record - Form 500A
1a7e515a-e9b3-53b0-8e6b-24c451eb088c | textbox | Initials:
| checkpoint | 7. Primer cured for at least 48hrs prior to application of seal
d70725aa-c8ef-5ee9-86ff-a62f2e9bd752 | note | Inspection/Test Frequency - Each lot
a37acaf6-8624-5280-b1d9-a9ff545bac4f | note | Inspection/ Test by - SS
a1c0d24d-3943-5cc5-b110-12edc7949efd | note | Responsible Position - SS/PE
93e6ecf6-07de-5972-b3ed-28eaabd2e67e | textbox | Initials:
| checkpoint | 8. Apply Seal Binder: Spray commences & ends on paper Cutter oil added per RMS form 382 Actual application rate determined after each run using dipstick. Binder temp at application recorded Overlap btwn adj long’l runs 50mm.
25811cbe-a8b4-5e80-9546-3711251ff075 | note | Criteria/Test Method/Spec - Note:
9ce91d8f-ef4a-5924-ab74-0067dcef8e81 | note | ○ Target 1st layer hot application rate = 1.55/m2
541ae9a7-9416-5eed-9a3c-d5215eecb44b | note | ○ Target 1st layer hot application rate = 1.09/m2
acb79702-c675-5c6c-9793-5d97d12fc446 | note | ○ Temperature: 160-190°C
83deac12-1a24-5399-9d47-44c6c50027c2 | note | Inspection/ Test by - Spray Seal Subcontractor
f571f06b-9dad-57ff-bc61-e1dd0dc87a4e | note | Responsible Position - SS / PE
5679e044-2f1a-5967-a3e3-62a97ecb1d24 | note | Type of Record - Form 500C
6d29d90e-0fca-5d3e-91c7-6b87cc6f13ef | textbox | Initials:
| checkpoint | 9. Application of Aggregate: Aggregate precoated Actual aggregate spread rate measured at Roadworx (per RFI 76) Application complete <15min spray Rolling: 1 (per RFI 76) dual axle pneumatic multi-tyre rollers, >7t, tyre pressure >550KPa, ≥8 passes in <1hr
c4980398-c800-5069-8f47-d10ec89231a7 | note | Criteria/Test Method/Spec - Note: Target agg appl’n rate 1st layer = 98m2/m3
f9671e6b-af3e-5021-8d9a-b4c7907d003d | note | ○ Note: Target agg appl’n rate 2nd layer = 171m2/m3
2bc06f92-a3db-57f3-82e3-a73974bc7a9b | note | Inspection/ Test by - Spray Seal Subcontractor
a2a4d737-2782-55c2-b91b-4e45909c88d8 | note | Responsible Position - SS / PE
3a1c1f7a-ac09-577e-a8ba-9bdff9bff1c2 | note | Type of Record - Form 500C Aggregate Spread rate record
24468221-dd35-511d-903e-1e4dc84dea69 | textbox | Initials:
| checklist | ITP - R116 - Asphalt Laying | itp | ITP - R116 - Asphalt Laying | 170ccea0-d8e1-40aa-916c-88da92f58ecd
| section | 1. Nominated mix design
| checkpoint | 1. Constituent Materials
de51fe9c-8a83-50fa-b0a6-902149e41fb1 | note | Reference documents - R116.2.3.3 (a)
293277c6-4065-59da-9e7a-c438d4892b7c | note | Criteria/Test Method/Spec - Aggregate of a different type or quality, even if from the same quarry face or from within the same quarry, will be regarded as from a different source
53b5d12a-6414-5d88-aaa6-53aab3cb4562 | note | ○ Added filler: type, grade and source
ee57bc07-3b58-56a0-a265-f7ae1aad703b | note | ○ Binder: source, class or grade
9e3ad91a-16f0-56e9-a139-9da50f983c1b | note | ○ RAP material to be comply with R116 Clause 2.2.1 (c)
85faeeea-5ede-5a27-9f68-a84d18c0e9a4 | note | ○ granulated glass aggregate: source to be comply with R116 Clause 2.2.1 (d)
ba7b4a79-b522-53da-8b8f-7359027d5200 | note | ○ Additives: type, source, trade name and manufacturer’s recommendations.
6a034838-655b-57e6-acb5-60e1a8273181 | note | ○ Bitumen emulsion tack coat: source, class of bitumen, any bitumen modification
febecc8b-b4dc-5243-a335-9966d0845b29 | note | Record for conformity/Inspected by - NATA report
76d277e8-3020-591c-bc44-f4e469881567 | note | Type of Record - AP
fb3e5caa-2c68-5b22-b5ba-ed4f1c1d9f24 | note | Responsible Position - Project Engineer (PE)
| checkpoint | 2. Mix Design
183f4a1b-ddc7-5c8d-9981-6d6600fb46ea | note | Reference documents - R116.2.3.3 (b)
930c4f2c-752f-5630-9faf-1b06749112c6 | note | Criteria/Test Method/Spec - For each nominated mix design:
af55913e-6e88-5816-96c7-cbd961b0f18b | note | ○ Proportion of each constituent by percentage of mass of total mix.
5bf961fc-0cd4-5acd-b7d1-6452faf3966b | note | ○ Nominated values and allowable tolerances for each requirement specified in Clause 2.2, where applicable
fae6da42-5653-5fbe-b546-8baa796bc96c | note | ○ Combined aggregate density, including calculations showing how this is determined
2292ec38-77f1-50e5-b7dd-a9728d2032e8 | note | ○ If using RAP material, the RAP Approval Level for which you are approved to use
668b5535-951e-59db-95c6-d04b5339a6ae | note | ○ Type and identification number of the asphalt manufacturing plant and mix identification.
e617c297-3b3b-5f43-9290-d1d31f9d618a | note | ○ Temperature at which the asphalt is manufactured
a7404af5-67dc-5be7-8ac7-db7aa2fe971e | note | Record for conformity/Inspected by - Mix design submission sheet
6efb14dd-17c0-5cc7-b82a-b947c140bfba | note | Type of Record - AP
205675b3-9b55-5e3b-a148-a2d4a9c0bf52 | note | Responsible Position - PE
| checkpoint | 3. Production Trial
d8316dc9-8165-543a-93ac-116d56f71a70 | note | Reference documents - R116.2.3.3 (c)
d8a75eb0-9ced-5d94-a9aa-4ca24f8e43f0 | note | Criteria/Test Method/Spec - Test results from the production trial in accordance with Clause 2.3.2
b7715f7c-5963-5e67-9628-e52502d2f218 | note | Record for conformity/Inspected by - Conformity sheet for the nominated mix
857eb0d0-0c7f-56ea-ab9c-c984231b9fad | note | Type of Record - IP
8e56ca64-a35f-544f-b601-b8276c63f38a | note | Responsible Position - PE
| checkpoint | 4. Warm Mix Asphalt Additives
4bbbf4c3-e5e8-5c86-b9a5-14dfe834cca9 | note | Reference documents - R116.2.3.3 (d)
b5d9a46a-f4cd-5afc-b1a8-363d17758da6 | note | Criteria/Test Method/Spec - provide details of the additive(s) in your nominated mix design submission
b9aea306-40ec-5cfd-95fb-0d10bc679e2f | note | ○ any proposed amendments to the mix design procedure, operational processes and/or test methods as a result of the inclusion of a warm mix asphalt additive
6ae42ed0-4c5c-5790-a509-6ff4a27f9760 | note | ○ classification of the warm mix asphalt additive
cf39d9a2-e697-5027-b0a8-178219c60647 | note | Record for conformity/Inspected by - Additive data sheet
484ce030-3606-58b6-b53a-64770677af94 | note | Type of Record - AP
22fc6bae-8a09-5ef3-92f9-a7a75a08fe17 | note | Responsible Position - PE
| checkpoint | 5. Signed Statement
688541c7-bd76-550f-8eb7-bb3ec9a76aa9 | note | Reference documents - R116.2.3.3 (d)
fa9aeeeb-9abe-5ae0-a284-d3c52e25bf05 | note | Criteria/Test Method/Spec - A signed statement certifying that each nominated mix, the associated production trial mix, and all constituents meet the requirements of Clauses 2.1 and 2.2. The statement must include NATA endorsed test results for all specified tests. Attach a copy of your completed verification checklist.
90774765-2970-59d0-b884-1c48657d4a63 | note | Record for conformity/Inspected by - Statement for test results of trial mix
b585f047-f58f-59d8-8878-bc56ba1455b2 | note | Type of Record - AP
aa5c84fb-1f38-5da5-a30c-3b5448d8652d | note | Responsible Position - PE
| checkpoint | 6. Test Report Validity Periods
ac526d6a-f2f4-5590-9b3b-03b9f15acd6a | note | Reference documents - R116.2.3.4
9520d19a-bdff-57cc-b06a-0a5397c995e8 | note | Criteria/Test Method/Spec - ○ All asphalt and binder tests relating to the nominated mix design submission must not be older than one month prior to the date of submission to the principal.
5e02d5a3-f06b-5ce5-a1d7-ee9c3f507ea0 | note | ○ For high RAP content asphalt mixes, wheel tracking and beam fatigue tests relating to the submission must not be older than three months prior to the date of submission to the principal.
eba26b7e-9065-5bd3-b0a6-f90db723bae7 | note | ○ All other tests relating to the submission must not be older than 6 months prior to the date of submission to the principal.
0ba198a6-00b0-513a-9f1e-ad5ff41f7511 | note | ○ All phases of any particular test must be performed at the same laboratory
b3d901c7-bdd4-577e-91bb-27525b0d5701 | note | Record for conformity/Inspected by - Report of conformity
3d7c3dbd-6be9-523b-b0d5-3f8351b4a123 | note | Type of Record - AP
36748d94-f35e-5e6f-92d9-244f3dae2596 | note | Responsible Position - PE
| checkpoint | 7. Mix design approval
4cc77e4e-3317-5daa-908a-cefb53f607b8 | note | Reference documents - R116.2.3.5
6cfe38f9-0c19-568a-bd69-41637ed6fdd1 | note | Criteria/Test Method/Spec - Documents as detailed in R116 Clause 2.3.3 at least 7 working days before the nominated mix(es) is (are) proposed to be placed.
c483d9ea-60ef-54d3-9720-8afd0fd46a8f | note | Record for conformity/Inspected by - The PV will consider the submitted documents prior to authorizing the release of the Hold Point. This Hold Point release is valid for a maximum period of 24 months.
4ce289d8-e275-558a-9ac9-0c25ad6b349b | note | Type of Record - HP
ab258e1a-2419-540f-845e-a22aab77b69b | note | Responsible Position - PE/PV
| signoff | HOLD POINT
| section | 2. Production of Asphalt
| checkpoint | 8. Method of Production and tolerances
9ce9d738-c5ba-569f-915f-84dbfb2f07d4 | note | Reference documents - R116.2.4.1 R116.2.4.2
4fde51ba-1f71-5658-bfd4-d5b175f8e453 | note | Criteria/Test Method/Spec - (a) control the process and target the nominated mix design;
d6be67c7-2c2d-58ce-a8aa-2cc0573af0cc | note | (b) supply a homogeneous and consistent product at the nominated manufacturing temperature.
158ab649-40c4-5120-9d4a-b8a2901d1faf | note | ○ You may vary the proportion of each constituent for the purpose of process control, provided that:
6b8123c3-5f6a-5575-b764-b09471dfea0d | note | (i) the asphalt produced remains uniform and of consistent quality, and subject to the production tolerances specified in Clause 2.4.2;
d63992c1-63b6-51ea-aa80-079683673b80 | note | (ii) the proportion of RAP does not exceed the RAP Approval Level in Table R116.4 for which you have been approved.
373dd905-3fdc-5906-82f9-2a8caff4298b | note | ○ The actual combined particle size distribution and actual binder content may vary from their nominated values within the limits shown in Table R116.8, provided that the actual values also remain within the limits of Tables R116.2 and R116.3 respectively.
fe351f7b-b248-5d5b-aaaf-4ed488e97b9a | note | Record for conformity/Inspected by - Visual inspection
e2e2a50f-2f49-5892-beca-bb6b56c67fb3 | note | Type of Record - IP
78adb520-1da8-56db-ab5d-7893ed902d62 | note | Responsible Position - PE
| checkpoint | 9. Asphalt Manufacturing Temperatures
e583ece3-8781-5969-91ec-9e279e5bc3cd | note | Reference documents - R116.2.4.5
2b14a79b-9f8e-5e3a-b1d6-c957b835d6d7 | note | Criteria/Test Method/Spec - Control the temperatures of constituent materials in response to suitable thermometer elements placed in the flow of materials from the drier, and in the binder storage system or binder supply line. Thermometer must be readable and accurate to within ± 2°C.
87a8c7bb-329e-5a7c-9614-93b7f9cc5d20 | note | Measure and record the temperature of the asphalt when:
ec1d8eda-ea4f-5465-a255-f880820b3911 | note | (a) asphalt leaves the pugmill or mixing drum; or
1b764e06-26b1-5d7c-ad47-12098a85ddb5 | note | (b) asphalt is being discharged from the hot storage bin(s); or
012dc875-4e0c-585c-b2ca-5e992241db53 | note | (c) in the delivery vehicles, prior to them leaving the plant.
4e248678-8210-5db4-aec1-e1ccd54b3e09 | note | ○ The temperature of asphalt must not at any time in the process exceed 175°C.
4e8870cd-f0db-5f98-86d9-fa081808236c | note | Record for conformity/Inspected by - PE to check temperature using suitable thermometer elements
36efe568-b9fc-57e7-9dd2-fb48d5fc1158 | note | Type of Record - IP
5d3fa444-060c-537e-87cd-7cbaf4dbef25 | note | Responsible Position - PE
| checkpoint | 10. Sampling, Testing During Production and transport of asphalt
59bbfb91-5709-5bb4-b7b9-95fce0986d4d | note | Reference documents - R116.2.4.7, R116.2.5
16389858-59d6-5a5b-9283-4aecaad71e0a | note | Criteria/Test Method/Spec - Verify conformity with the Specification by sampling and testing, and maintain records of your process control during asphalt production.
cc2e45a6-5e36-5f3f-8409-cd5314f958de | note | ○ The frequency of sampling and testing must be in accordance with Annexure R116/L.
ce1c2abd-5755-5e5d-b928-63498d755fd5 | note | ○ Take asphalt samples in accordance with AS/NZS 2891.1.1
09661bee-7f08-5649-9572-8e91a7675666 | note | ○ Transport of asphalt must be in accordance with AS 2150.
1175ac3a-2f58-50b9-b747-c0bb72360b7a | note | Record for conformity/Inspected by - Visual inspection
7d5fd972-78db-5c7a-b4a3-5a29930b53e7 | note | Type of Record - IP
4a4a8ae0-6ec2-5709-8847-a58dc69e8caf | note | Responsible Position - PE
| section | 3. Placing Asphalt
| checkpoint | 11. Provision for Traffic
009b63c1-ca6c-5482-ba8c-4b8ef49b5038 | note | Reference documents - R116.3.1.1
de0de490-94e2-5538-b9a1-23994d01dc42 | note | Criteria/Test Method/Spec - Provide for traffic in accordance with the requirements of Specification TfNSW G10 when carrying out asphalt paving.
0547a7be-2c59-5385-8c01-ce13d2cbc529 | note | Record for conformity/Inspected by - Visual inspection
12d52af3-9b25-5264-a913-59d26c503712 | note | Type of Record - IP
cc27e544-f142-5f98-b87f-ae585f36d230 | note | Responsible Position - PE
| checkpoint | 12. Surface Preparation, Protection of Road and Services Fixtures
f8f72394-3bd6-543e-97cf-b0d2d667affc | note | Reference documents - R116.3.1.2, R116.3.1.3
264ce2fb-e145-53b4-b089-7790bb5a99d6 | note | Criteria/Test Method/Spec - Prepare the surface to be paved in accordance with AS 2150, including removal of raised extruded thermoplastic road markings and raised pavement markers.
ab5d7c7b-47b3-5f13-9f67-5427fecf35e6 | note | ○ Implement measures to prevent asphalt or other material used on the work from entering or adhering to grates, hydrants or valve boxes, service covers, bridge joints and other road fixtures.
9dee27cc-31e0-57ef-b116-c0e8a10c81d3 | note | ○ Immediately after the asphalt has been placed, clean and remove all waste asphalt adhering to road and services fixtures
8d1dc2d2-b7bb-5e64-9cc9-867e9deb1ec6 | note | Record for conformity/Inspected by - Visual inspection
5baaf07c-1339-5ff3-8a11-1b822261c949 | note | Type of Record - IP
33e0f7ce-40e3-57b8-84e0-6498a2271811 | note | Responsible Position - PE
| checkpoint | 13. Tackcoat for existing surface, application rate and reduced application
f1cc9e97-16fc-5b70-a939-a60b2cdfa52e | note | Reference documents - R116.3.2.1, R116.3.2.2, R116.3.2.3
7a4b8144-1b4f-5ecd-aa95-b571b724ac5a | note | Criteria/Test Method/Spec - The existing surface must be clean, dry and free from loose material, prior to application of the tackcoat.
b0edf2d2-cff4-52a8-8612-2e222721ab2b | note | ○ Apply the tackcoat evenly at a rate of between 0.15 and 0.30 litres of residual bitumen per square metre, ensuring that it is effectively bonded to the surface. For joints and chases, double the application rate.
25dbb202-8bf6-5c81-b280-3a2300733cb5 | note | ○ Nominate in writing to the principal your proposed tackcoat application rate prior to applying the tackcoat.
fc81abbd-bc76-56d6-8bac-6524c34aaec6 | note | ○ Determine the required volume by multiplying the nominated application rate of residual bitumen by the specified area of the surface to be tackcoated, including the faces of joints, kerbs and other structures.
3abb8d78-c347-5cee-b539-ca0aa3e6ee3d | note | ○ You may propose in writing to the principal a reduced application rate for the tackcoat, for reasons arising from the existing underlying surface material.
acdba5b8-7fc0-5a56-b567-d167f72e2191 | note | ○ Support your proposal by examples of previous cases where this has been done,
fa714691-5133-51c0-8864-7021f4d41491 | note | Record for conformity/Inspected by - Visual inspection
47e24bc2-0b6a-5d18-bc7a-10f520b08448 | note | Type of Record - IP
0409b60e-8ebe-5547-ba72-2cfb2de08476 | note | Responsible Position - PE
| checkpoint | 14. Temperature and Wind Velocity Measurement
a54d8929-b1c5-5ce5-9ee2-f72c028fa7f3 | note | Reference documents - R116.3.3.1
48960ff6-fc5f-5959-b185-8b7b8226dfe9 | note | Criteria/Test Method/Spec - Measure and record the temperature of the surface to be paved, and wind velocity at the point of asphalt placing.
7c18294f-16be-57b9-9ecb-168ed2395f0c | note | ○ Do not commence or continue placing asphalt containing binder complying with TfNSW 3253 if the temperature of the surface to be paved over, measured at existing surface level, is less than 8°C where the nominal size of asphalt is less than 20 mm, or less than 5°C where the nominal size of asphalt is 20 mm or greater, for a zero-wind speed.
78dd8d38-ed57-5338-87d2-7fe10e68fc08 | note | ○ These minimum temperatures are increased by 5°C for asphalt containing binder complying with TfNSW 3252.
3fb1ffe9-b270-5602-a888-9401542a09b6 | note | ○ These minimum temperatures are increased by a further 5°C for each 5 kph of wind speed above zero; however, the minimum temperatures must not exceed 30°C.
ca76747e-f181-55ab-8396-98604e53e519 | note | ○ Do not place tackcoat and/or asphalt when the surface is wet, and/or when wet weather appears imminent.
1dff566c-3afa-524f-9c9e-1ad71fff9dd1 | note | Record for conformity/Inspected by - PE to check temperature with thermometer
83edab11-2f57-5290-b848-2305c53bb321 | note | Type of Record - IP
741c0eae-1b0e-5aa2-8530-fa18757d23bb | note | Responsible Position - PE
| checkpoint | 15. Method of placement, equipment, and materials transfer
c5b698b7-6b9a-572a-94bf-6dff12e0878e | note | Reference documents - R116.3.4.1 R116.3.4.2 R116.3.4.4
9380be4c-5f6e-51e1-8dd7-c4eda2830ecc | note | Criteria/Test Method/Spec - Your method of placing and finishing the asphalt must:
7c98eadf-3dfa-50b2-9bbf-2e432b622b11 | note | (a) produce a homogeneous product with a tightly bound surface;
ad720de3-c78c-5e59-a30d-08862a7eec2d | note | (b) achieve a uniform bond to the surface below;
968355ff-6f04-5dbd-931e-41449d873818 | note | (c) achieve the finished pavement properties, specified in Clause 5, within the specified tolerances. Compact uniformly each layer of asphalt to achieve insitu air voids requirements before placing the next layer.
953d2b47-5d52-5932-bb09-b3cbbd50f516 | note | (a) a receiving hopper compatible with delivery vehicles;
004530a9-0751-5f55-95dd-4f67c56419fe | note | (b) conveying mechanisms capable of delivering asphalt to the paver at a minimum rate to suit the paving output;
41c12c85-c356-5190-aa35-377032f45503 | note | (c) sufficient power output from the motor to operate with full load on grades up to 6% and travel in tandem with the paver, either directly in front or in an offset position;
14669d93-7e5b-5c71-b685-336f7aed475b | note | (d) capacity to store and remix asphalt if the time between loading the delivery vehicles at the asphalt plant and unloading at the Site is equal to or greater than 1.5 hours, or when the temperature of the surface to be paved is below the minimum specified in Clause 3.3.
2594a77f-6300-5107-bba2-e51bb1a22e5b | note | ○ If so specified in Annexure R116/A, place the asphalt by echelon paving using a minimum of two pavers operating continuously in tandem.
63259320-0713-5628-a708-9ddde753d25c | note | ○ Place the asphalt using a self- propelled paver with the ability to be operated with automatic grade control and automatic joint matching facility.
c7ce9562-2787-5f21-b8b0-e4149d50912a | note | ○ Hand placement of asphalt is only permitted for minor corrections of the existing surface and in areas where placement with a paver is impractical.
e9ad9179-8616-5c45-8a27-95d09374d704 | note | The MTV must be a self- propelled machine with independent controls and demonstrated capability to minimise temperature variation and material segregation. It must be equipped with:
a48ec638-f379-5edb-82cf-5d766407d33b | note | (a) a receiving hopper compatible with delivery vehicles;
e079f6ee-9d40-5349-ac49-8b2866d8e714 | note | (b) conveying mechanisms capable of delivering asphalt to the paver at a minimum rate to suit the paving output;
ca216a8e-ffb9-528a-8a17-1eba7a501fe1 | note | (c) sufficient power output from the motor to operate with full load on grades up to 6% and travel in tandem with the paver, either directly in front or in an offset position;
afebc01b-9be2-57d0-bed8-905b93d5cd5d | note | (d) capacity to store and remix asphalt if the time between loading the delivery vehicles at the asphalt plant and unloading at the Site is equal to or greater than 1.5 hours, or when the temperature of the surface to be paved is below the minimum specified in Clause 3.3.
00048382-c638-5aa5-acdf-2d977b12dffd | note | ○ If so specified in Annexure R116/A, place the asphalt by echelon paving using a minimum of two pavers operating continuously in tandem.
| checkpoint | 16. Paving and compaction temperature
059300ed-f979-5363-b734-314dd2df06fe | note | Reference documents - R116.3.5.1
32bd0a80-7d18-5a65-9765-7a91577d5232 | note | Criteria/Test Method/Spec - Commencement of paving using the nominated mix(es), including trial section (refer Clause 3.8).
3786c717-0c56-536c-a8aa-307d8765f881 | note | If not previously submitted, details of the following:
7ba1093b-b5a1-56a5-8c27-e9e371bd8ec1 | note | (a) minimum temperature at which asphalt will be delivered to the paver;
f0aa0775-26c2-5f8a-829d-47ffdc1febd9 | note | (b) minimum temperature at which initial compaction of the asphalt can still commence;
29a94ba8-c0d2-589f-b7fc-b924ad262300 | note | (c) method of temperature measurement
3ab4b49f-9317-53a4-9317-735d3ef81ef1 | note | Record for conformity/Inspected by - The PV will consider the submitted documents prior to authorising the release of the Hold Point
01a9f2bc-802d-5897-850f-ffa335cfd5ee | note | Type of Record - HP
595767e1-46df-5bac-b0c4-2d0d378edab9 | note | Responsible Position - PV/PE
| signoff | HOLD POINT
| checkpoint | 17. Course and layer thickness
81f88f66-ea45-5571-907a-e1f359de61cf | note | Reference documents - R116.3.6.1 R116.3.6.2
53caf8b0-75a2-5e18-8df8-c55453952581 | note | Criteria/Test Method/Spec - The nominated thickness of a layer of asphalt must be between 3.0 to 5.0 times the nominal mix size.
61d9c636-fd1c-5e26-9eef-8a86d80b40a1 | note | ○ The specified course thickness is detailed in Annexure R116/A, or shown on the Drawings
1ade082a-cae1-5398-b772-dfe00a4ffd6f | note | Record for conformity/Inspected by - Survey to submit report to PE
84459834-3fbf-5d1e-8583-4bd53a4f82bb | note | Type of Record - AP
f8157ddd-6164-521d-8326-8f15b6e93ec4 | note | Responsible Position - PE
| checkpoint | 18. Nonconforming Layer Thicknesses
675b1e2e-950f-5dbf-81b1-f4f8b80464e3 | note | Reference documents - R116.3.6.3
df42c59e-d7d4-545c-9ef5-a2581b9600c8 | note | Criteria/Test Method/Spec - Placing of asphalt in layer thicknesses that does not conform to specified layer thicknesses.
970db05e-16b1-57dc-b15c-fd8af8eb55c4 | note | Details of the following:
9c0f92a8-1ef7-5dc5-ba39-a5e87ec77ca3 | note | (a) nominated layer thicknesses which does not conform to specified thicknesses;
78e9a873-4303-506a-884e-6c4a45fde968 | note | (b) work methods capable of producing a dense homogeneous layer at these thicknesses;
ce84cc01-cbc4-56bf-80e6-c397e7656597 | note | (c) areas affected, and evidence that these areas are the absolute minimum necessary.
2d21c19e-6409-5ad7-b859-1ca3f245bd6f | note | Record for conformity/Inspected by - PV will consider the submitted documents prior to authorizing the release of the Hold Point
8fba14c3-0183-5157-ba23-3aaa8efeb6e7 | note | Type of Record - HP
6bf721b7-ad73-5fe2-9281-104daefe9883 | note | Responsible Position - PV/PE
| signoff | HOLD POINT
| checkpoint | 19. JOINTS, temporary ramp and tie ins to existing pavement
2efa3ca3-ff2d-5582-aec4-a358034b35d0 | note | Reference documents - R116.3.7.1 R116.3.7.3 R116.3.7.4
37750291-da75-581e-aca1-1d53e15c5222 | note | Criteria/Test Method/Spec - Longitudinal joints must be:
051688bf-8cad-5fef-a6a5-b6a7266cbb6a | note | (a) offset by 150 mm from the joint in the underlying layers;
bb8168b5-fd02-5ea9-bacd-80c5221177bc | note | (b) located within 150 mm of the line of change in crossfall;
91d43715-ee7e-5685-b287-798ca0bcd536 | note | (c) coincident with final traffic markings, unless otherwise approved by the Principal. Transverse joints must be:
ba14524a-05f8-5985-a0b3-ee870c87c69e | note | (i) located at a minimum of 25 m apart;
0785f56f-015a-5c00-a038-9369a839fe89 | note | (ii) offset by a minimum of 1 m from the joint in the underlying layer;
1221bc18-173a-51f1-be58-15f85c7ed87f | note | (iii) formed at the commencement of each paving run;
ab1607e9-7986-5fc1-b9da-82df4d569cdf | note | (iv) formed when a delay in paving causes asphalt temperature to fall below the initial compaction temperature nominated in Clause 3.5. Construct temporary ramps at joints for safe trafficking of the work either by placement of asphalt complying with this Specification, or by cold milling the existing or new asphalt layer to form the ramp, as appropriate for the application.
1f9c8bc6-c277-54a5-80cc-1a87502fb365 | note | ○ Construct permanent tie-ins to existing pavement by placement of asphalt complying with this Specification
3d96f45d-f48f-5b6b-9cbb-b51f65926f77 | note | Record for conformity/Inspected by - Visual inspection
98b63fd8-3693-54cd-af0b-6a641d0b04b7 | note | Type of Record - IP
25003c7b-9089-554f-9048-8c29febea72d | note | Responsible Position - PE
| checkpoint | 20. Trial section and commencement of paving at locations other than trials section
ae210821-9d2c-5505-9d6f-0a689fccae0e | note | Reference documents - R116.3.8.2 R116.3.8.3 R116.3.8.6
fe6e946f-881d-5606-8436-f422ab207c05 | note | Criteria/Test Method/Spec - Design the trial to implement all the procedures described in your PROJECT QUALITY PLAN and demonstrate conformity with the Specification in respect of:
d735465d-5f4b-5cb0-a9ea-b4f1b61aa37e | note | (a) homogeneity.
7bdb7e9e-079d-5ae4-8198-aed368dd6ec1 | note | (b) insitu air voids.
7a3ac7ee-3f33-560c-9100-2a2c7a995595 | note | (c) course thickness.
cb1de0bc-bb5b-5df7-860a-19b8a16ce024 | note | (d) course position.
2788723a-9b32-5834-bcd8-e39222dbcec1 | note | (e) surface shape.
611c9ab6-a889-5b10-baa6-8bb63fe9d331 | note | (f) joint quality.
61c121c4-a9b4-54f0-a0ed-285d5767800f | note | (g) ride quality, where specified
b9fab280-e0b4-56f6-8a56-6b75440a1eda | note | ○ Verification checklist and all relevant test results from the trial section demonstrating conformity to the specified requirements, at least 3 working days prior
9f44c092-e7a6-5252-a66e-04c8dd4890d4 | note | Record for conformity/Inspected by - Submit report to PV
2bbe1dc5-b616-5fb7-a20c-ea607d81d630 | note | Type of Record - HP
1822a9a9-11bc-5189-8f42-8dad68153334 | note | Responsible Position - PE
| signoff | HOLD POINT
| section | 5. Conformity
| checkpoint | 21. HOMOGENEITY
90c661ab-16d5-5700-9e9d-dad15066ebb2 | note | Reference documents - R116.5.1 R116.5.2
9cc9933e-fd94-5538-bfd0-a71a59e9551c | note | Criteria/Test Method/Spec - During the first 24 months after the Actual Completion Date:
df1f6b57-2f36-5363-a6fa-1d8b625ea1b2 | note | (a) the placed asphalt must not ravel, rut, shove, strip or bleed; and
1f84df24-d39c-5fb8-9017-eb0a9bb5c6d4 | note | (b) the wearing course for the first 12 months must comply with the surface shape requirements specified in Table R116.12.
9f936c2b-5650-5c38-b173-420e29e7d6bc | note | ○ Placed asphalt must be homogeneous in appearance, and must not exhibit segregation, cracking, ravelling, bony or fatty material, or have been damaged during construction.
7466893a-a8d6-5d58-a209-7892e31bb059 | note | Record for conformity/Inspected by - Visual inspection
da437482-57b7-5da7-8ab2-d02781d98d2d | note | Type of Record - IP
cc25f7b6-9e47-51d3-9bc4-c48c3c1174e9 | note | Responsible Position - PE
| checkpoint | 22. Rectification and Replacement
7a7fde29-93d3-5211-be65-5808e4fd7042 | note | Reference documents - R116.5.8.5
41692231-3649-5d23-b255-77802d47e071 | note | Criteria/Test Method/Spec - Nonconformity Report and details of your proposal to rectify or replace the Lot.
c689c4ea-e0c6-58a0-bb26-e5d667f6a8e3 | note | Record for conformity/Inspected by - PV will consider the submitted documents prior to authorising the release of the Hold Point.
429d1827-117f-5064-bb1f-534e7672c78f | note | Type of Record - HP
c4a96476-141f-5409-a53a-f829120d4245 | note | Responsible Position - PV/PE
| signoff | HOLD POINT
| checkpoint | 23. In situ air voids and Course thickness tolerances
8db0a174-fe5b-5692-8760-2a64f945fba0 | note | Reference documents - R116.5.3 R116.5.4
0f2f5da8-ed94-57fd-a606-a902e904e246 | note | Criteria/Test Method/Spec - The characteristic values of insitu air voids for a Lot must be within the limits shown in Table R116.9.
ef245156-3d11-5f66-b219-89a5bbe45e28 | note | ○ For layer thickness between 30- 50mm, air voids must be between 3% to 8%.
88b6c006-48f2-591b-97a7-0b8de5397391 | note | ○ For layer thickness more than 50mm, air voids must be between 3% to 7%.
70063524-5382-5d83-9e30-624ceed011dd | note | Record for conformity/Inspected by - NATA report
cad00d1a-1378-5c76-a31f-e593a5949dd4 | note | Type of Record - HP
2511ca46-e6e9-52b5-82b1-fea0e6ce2f66 | note | Responsible Position - PE/PV
| signoff | HOLD POINT
| checkpoint | 24. Progression to higher RAP level
1c373d00-c7dd-542b-9407-f1441af2d432 | note | Reference documents - Annex. B2.3
caa37e77-bac0-5277-afed-bee9b8bbc06b | note | Criteria/Test Method/Spec - (a) Proposed corrective action to achieve conformity.
a00e5f04-61a0-5b12-93f7-893de96ee9c8 | note | (b) Test results for insitu air voids and all properties specified in Clause 2.2 of the nonconforming Lot
df27edce-28dc-5605-8d7a-85b3f7de68d4 | note | Record for conformity/Inspected by - PV will consider the submitted documents prior to authorising the release of the Hold Point, and will advise whether the nonconforming Lot can be accepted.
b68ee2b4-0f79-50b0-8df3-d925ea746c65 | note | Type of Record - HP
13d95060-23e5-5315-a0db-439ab47158c2 | note | Responsible Position - PE/PV
| signoff | HOLD POINT
| checkpoint | 25. Finished Surface Levels Specified
cba95919-3fd3-5c69-96d7-148729316227 | note | Reference documents - R116.5.4.2 R116.5.5.1
24bf3a78-0726-5a25-a5fc-818e9c790ade | note | Criteria/Test Method/Spec - The actual surface levels of the placed asphalt course as determined by survey must not deviate from the design levels by more than the tolerances shown in Table R116.11.
188c09ed-ea27-5349-8910-bd98030bf274 | note | – – – – – – – – – – – – – – –
c76f2cb3-a756-5ee0-b3f0-c971597bc6c4 | note | Table R116.11 - Course Surface Level Tolerances
308d4825-d07c-5a43-b4b8-74598f414cd1 | note | – – – – – – – – – – – – – – –
2b3ceddf-bbe1-5265-bf8a-037d49fc34b0 | note | Course ¦¦ Tolerances (mm)
a0e1b130-56be-5d4b-9b11-7bf422c83bb3 | note | – – – – – – – – – – – – – – –
b60d1834-e767-5778-bf47-e06a924f3b64 | note | Wearing course ¦¦ -0 / +10
145e2476-ab7f-579e-8b99-df29dccc2933 | note | Top Intermediate course ¦¦ -5 / +10
717cdfb6-261a-539d-9451-2852b40ab4e1 | note | Other Intermediate Courses ¦¦ -10 / +10
1fc0a8b0-f609-5207-a509-21d96f21281b | note | Corrective course ¦¦ -15 / +10
d36cdc36-3bc4-5555-a573-7a29e0751cf4 | note | – – – – – – – – – – – – – – –
b553a2d6-92f9-5be4-87c0-74c442ae7e14 | note | Record for conformity/Inspected by - Survey report
5fb65e0e-242a-5634-8096-ac35cb81fe08 | note | Type of Record - IP
34836daf-5f5c-547e-a062-0464f037dbbb | note | Responsible Position - PE
| checkpoint | 26. Surface shape
0843208c-05ae-53e3-a20e-e1150a3d8f27 | note | Reference documents - R116.5.6
f06de17e-8289-56e8-963f-3cfda28a471d | note | Criteria/Test Method/Spec - The surface of the course including longitudinal and transverse joints must not pond water.
7d3bae2e-256c-5139-b788-a69364097232 | note | ○ The surface shape of the course within and across traffic lanes must not deviate from the bottom of the straightedge (refer Clause 4.5) laid in any direction by more than the tolerances shown in Table R116.12
8d4da2b3-12c4-56d7-9e59-f384695a93ef | note | – – – – – – – – – – – – – – –
4af96908-a3f5-56ab-95ea-9fdc3c5b86cd | note | Table R116.12 - Maximum Deviation From Straightedge (mm)
94082c2e-eef1-51b0-8c92-70b8431a0bed | note | – – – – – – – – – – – – – – –
1120db14-0441-5245-bdd1-1481fd8615f5 | note | Course ¦¦ Through Carriageway < 70 kph Traffic Speed, Ramps and Roundabouts ¦¦ Through Carriageway ≥ 70 kph Traffic Speed
74ee4313-8010-57fb-8c3e-b5369631ff23 | note | – – – – – – – – – – – – – – –
24f55230-e0a1-519f-af2c-7062095ecf16 | note | – Immediately after placing: –
1631e529-b25d-5f39-81e0-0a87fae5c223 | note | Corrective course ¦¦ 15 ¦¦ 10
396e967b-5e42-5241-9764-89f0854754cb | note | Intermediate course ¦¦ 10 ¦¦ 5
4f54270b-dae5-5c3c-8291-653015e7ce7b | note | Wearing course ¦¦ 5 ¦¦ 3
93b17773-ed65-5813-acf3-68c5a956caa8 | note | – Prior to placing overlying layer: (1) –
0b168a63-8cb5-5cef-a676-112fdd466563 | note | Corrective course ¦¦ 18 ¦¦ 13
c718efc2-1bfc-588c-ab38-c59eac324fec | note | Intermediate course ¦¦ 13 ¦¦ 8
2c3a7d65-255c-5d66-bf56-a55cae6aff57 | note | – 12 months after placing: –
3890a62c-f0bc-55a0-8fd6-4721e9c71dd8 | note | Wearing course ¦¦ 8 ¦¦ 6
20157e05-4dd9-57cb-8c9d-a47526ff6d49 | note | – – – – – – – – – – – – – – –
0ca7ea44-2279-5374-adf5-14e2ba92f82b | note | Notes:
71715888-e6c1-5b0c-9314-7cfc1024e9c1 | note | (1) If longer than 1 month after placing.
52890c03-ed31-546c-80c7-43bd564c4962 | note | – – – – – – – – – – – – – – –
916158e1-4a02-54ab-b623-a6fa9685ad86 | note | Record for conformity/Inspected by - Survey report
073236ed-576f-50b0-a61a-48ae5cfb1004 | note | Type of Record - IP
e861b778-1f0c-527c-a397-6aa2b7856a73 | note | Responsible Position - PE
| checkpoint | 27. Ride quality
0cbbff80-8636-5613-a53e-2337d1ee2b13 | note | Reference documents - R116.5.7
8834e81e-3eb0-56f7-82be-45aed360a230 | note | Criteria/Test Method/Spec - The surface of the wearing course must have a smooth longitudinal profile.
c4d41452-12aa-5b8c-b928-c666ede5c943 | note | When:
0116d866-bf40-5e09-8217-ccbbbeb300d2 | note | (a) construction of the underlying pavement forms part of the Contract; or
8e129d65-5088-5787-9237-0b08628bed03 | note | (b) the course comprises more than one layer of asphalt, including any corrective course, placed over a pavement constructed by others; or
0fae5b2d-12cb-5475-a5f9-1c595b3516d5 | note | (c) the aim of the asphalt paving work is to improve the ride quality; the ride quality of each Lot must not exceed an IRIS of 1.56 m/km. Where a single layer of asphalt is placed over pavement constructed by others, the ride quality of each Lot must not exceed the IRISa values determined as follows (refer Clause 4.6):
f2f0bd29-8b82-51c8-aa42-fad984489ae3 | note | ○ IRISa = 0.2 + (0.6 × IRISb), but not less than 1.56 m/km
933635a1-67b0-5a68-be0a-b4994e09847f | note | where: IRISa is the IRIS after placing the asphalt layer (m/km) IRISb is the IRIS before placing the asphalt layer (m/km)
a9de579b-024c-5a48-8ad3-6c68ed3f7609 | note | Record for conformity/Inspected by - Equation check
f2fc29b7-72ea-5ec1-b3dc-d4ed86c1cbd9 | note | Type of Record - AP
fbe92bd8-ed65-5ebd-b345-cedc6c65b37b | note | Responsible Position - PE
| checklist | ITP - R132 - Guard Rail Safety Barriers | itp | ITP - R132 - Guard Rail Safety Barriers | 1bc9a346-7806-4a4f-aab0-eb9534ab90e4
| section | Guard Rail Safety Barriers
| checkpoint | 1. Confirm safety barrier type & end treatment
3fbef810-ee26-5d0c-96c8-a9b4d27965f7 | tickbox | W-Beam
4329aee2-1e42-5d7c-be45-f1df6c39cafc | tickbox | Thrie Beam
2905d5c1-0339-5a3a-8163-2ebf8efd2f0d | tickbox | Thrie Beam Transition
a37ce7f4-17a8-5846-93a3-a37b216f4544 | tickbox | End Terminal
43643d4f-2ef8-50f7-acbf-51048da57ab0 | textbox | Barrier Label:
f3ec0831-8ba7-5d9b-937f-a70e51e59f8f | note | Criteria/Test Method/Spec - Check design drawing, correct type of barrier, transitions and/or end connection and any additional material component requirements
b1aec081-5685-5013-be69-de088d60bd69 | note | Reference document - RF series Design dwgs, R132.2.1
2dbb3465-ea98-5b60-98e3-c3656a62fe2c | note | Record of conformity - Verification Checklist
4b471d48-346a-5d59-a038-6548c847447a | note | Type of Record - IP
a30f06c4-a291-5472-9713-a13919ef413a | note | Responsible Position - Project engineer
| checkpoint | 3. Verify conformance of proposed safety barrier materials
740b90bf-7497-5bd5-a6cf-1cfad4c2f058 | note | Criteria/Test Method/Spec - Verify safety barrier system components are in accordance with R132, design drawings and manufacturer’s recommendations:
184442e8-08ee-5c6d-aa31-bcc966ce252f | note | ○ Steel components
6793be85-d450-5b52-897e-a333c100c069 | note | ○ Bolts, Nuts & Washers
7ed66a4a-64a6-5ca1-83d1-519a253a41c3 | note | ○ Protective treatment
822d6085-4b21-59fe-991c-4be99e42e0c8 | note | ○ Curving steel rails
12e54042-d5ed-5203-8e54-3a3b3fb06590 | note | ○ Plastic members as per manufactures details
d6843fc9-276f-53e1-81bf-34af8abf0964 | note | ○ Powder coating complies with AS 4506
8403c41a-65b6-5fe1-ab29-b76c2127da22 | note | Reference document - R132.2.4, R132.2.6, R132.2.7, R132.2.9, TfNSW Requirements & Design dwgs
ad2931a4-9a0b-5ccc-9daf-ae1c68567d09 | note | Record of conformity - Verification Checklist
a821ab0d-79e0-59d3-9002-8a8f3ffea0d1 | note | Type of Record - IP
33eb3c25-f182-5fea-8c71-50c1a7c9348a | note | Responsible Position - Project engineer
| checkpoint | 4. Verify conformance of delineators & Retro-reflectors materials
254f75ce-4b2b-5878-b942-48132082ac36 | note | Criteria/Test Method/Spec - ○ Delineation unit in accordance with TfNSW STD dwg R0710-18 details
ffb8bddd-69b2-5bfd-bd9c-4372d0b9290e | note | ○ Retroreflective materials must comply with AS 1906.1 or AS 1906.2 as appropriate
cf67bc00-9ee0-5ef7-bcfb-147dcdbb2017 | note | Reference document - R132.2.8, R132.4.6 & TfNSW dwg R0710- 18
fcdb1fb0-03c3-5cf7-9b35-b09b97ed2a52 | note | Record of conformity - Certificate of Compliance
6aa13dec-57b2-56a7-b98f-01ebb537df69 | note | Type of Record - AP
cd7cad78-28ec-538b-9cae-b3c8d13beb4b | note | Responsible Position - Project engineer
| checkpoint | 5. Inspect guard rail safety barrier items upon delivery
6a6a0714-bfdc-5d76-bbf0-b031a1b5efcb | note | Criteria/Test Method/Spec - Inspect supplied safety barrier system components are in accordance with R132, design drawings and manufacturer’s recommendations and they are not damaged or defective.
b98d3728-f21e-55f9-a63d-04e9dbd4ca0a | note | ○ Components shall be marked in text ≤ 20mm high, the following Information:
9811ac2a-87f6-5261-b75d-5362ac5d4ae1 | note | – Manufacture’s name
19631163-20f1-54e1-984f-c225aa2899be | note | – Batch number, or date of manufacture
1eb7fa07-d720-5b0b-a267-78fab75b0115 | note | – Strength grade and base metal thickness of the steel rails
f6f4b2ad-44dc-57b4-84f5-40815b76e964 | note | ○ Verify galvanizing is undamaged on curved components.
978765ec-70f3-539c-9748-a6b6d58cec7b | note | Reference document - R132.4.1.1 & R132.2.2
334c9816-0132-56e0-a517-83603c71708a | note | Record of conformity - Receival Inspection Checklist
37747d55-8659-5dca-8f78-643731975796 | note | Type of Record - IP
ff64bb94-7761-5a89-9fe8-789ff6c66739 | note | Responsible Position - Project engineer
| checkpoint | 6. Verify underground & overhead services have been identified
380c8309-8196-5c0a-828c-32c5dd04fc9a | note | Criteria/Test Method/Spec - Utilise current Ground Penetration Permit or if new permit is required verify:
bec9c8e4-e440-5596-8300-ec4320741ac6 | note | ○ Dial Before You Dig contacted
b5ed7c68-4ab4-5cb1-88ec-387562b3a7b4 | note | ○ As-built for new services available to add to permit
ac4419c9-8171-584c-adea-29a3f914d827 | note | ○ Working near Overhead Services Permit is obtained
3afe4b02-6022-5404-bd0d-ae1c82185e63 | note | Reference document - WHSMP
490abde9-757b-54c7-bdae-06de969028a0 | note | Record of conformity - Ground Penetration & Overhead Services Permits
0b0c59d3-8df8-5044-a7d6-a069f78f316c | note | Type of Record - IP
69b585fc-4d5e-5afd-a48b-c0760df1263e | note | Responsible Position - Project engineer and site foreman
| checkpoint | 7. Set out
206da8e9-7f3d-598f-b7c6-141a9e9bbb59 | note | Criteria/Test Method/Spec - Verify pegs are in the ground (or paint marks on hard ground) that mark the start and finish points and line of the safety barrier, transition and end treatments inc the line of flare if applicable, prior to commencing construction. Measure offsets for flares from a line parallel to the adjacent lane line.
13fc83f4-9687-5ca8-a134-7b88d936850f | note | Reference document - RF Design dwgs, R132.4.1 & G71
ca84612a-e0a1-5e58-8720-6760873cd90c | note | Record of conformity - Verification Checklist
3fc955a4-a69c-5c28-9a28-facb5ce4d71b | note | Type of Record - IP
8c42bcbb-fa6a-5c42-b380-5eed86a9b7e5 | note | Responsible Position - Surveyor
| checkpoint | 8. Notify PV Representative to inspect set out of safety barrier
3850b0cc-a81a-5e17-971b-49229b06dae3 | note | Criteria/Test Method/Spec - Notification that the set out is in accordance with R132 Specification, the Design drawings and manufacturer’s recommendations, ≥ 2 full working days before the proposed commencement of installation of posts.
7a1b82e1-bd86-5d17-bb3f-591c40eddec7 | note | Reference document - R132.4.1.2
233a85f5-5aac-5c1b-8a7d-2dcac8e8292e | note | Record of conformity - Hold Point
6293cab5-5485-56c3-b144-f1c8d51530cd | note | Type of Record - HP
52250f17-2a8b-54b4-b1ce-199c92adc3ee | note | Responsible Position - PV/Project engineer
| signoff | HOLD POINT
| checkpoint | Constructing a safety barrier on a road open to traffic
b5fadb9e-ea63-5f0a-a2fa-70b8e8b3ed02 | note | Criteria/Test Method/Spec - Commence work at the end closest to approaching traffic, except where the barrier connects at its departure end to a fixed object such as the end of a bridge.
71db5ac6-f849-5e8d-a398-d58ed7cee40f | note | ○ Commission end treatments and transitions at the earliest practicable time. Provide temporary end treatments until the permanent treatment is complete.
18f321ca-197e-5e9e-b981-aac858e6eaaf | note | Reference document - R132.4.1.3
f7027b4b-2729-521c-bb4d-6b51f2c3e07b | note | Record of conformity - Verification Checklist
d8e77a96-8c3f-559f-8550-c70eda29feab | note | Type of Record - IP
1dc53ac9-575f-5661-a533-b98c0bc094da | note | Responsible Position - Project engineer
| checkpoint | Installation of guard rail posts by post driving
60f65721-af4e-5235-823c-8e7baa261709 | note | Criteria/Test Method/Spec - Installation of the posts must comply with the following requirements:
9435ed39-88f5-5eef-ad53-ba760014fd2f | note | ○ Posts must be installed to the depth, line and spacing shown on the Design drawings, and to the tolerances in R132.4.5;
d652d96b-2c09-5a43-929c-a6846a01f3e1 | note | ○ Installation process must not cause any structural damage to the post, including any soil plates attached to the post
b263e756-84c2-5877-8b68-36c51b0d2949 | note | ○ Installation must not cause any damage to the pavement beyond 100 mm from any part of any post, including any soil plate attached to the post;
1c287a89-1db5-55e2-8815-d1fdc37e7009 | note | ○ When a lateral force of 1 kN is applied in any direction within the top 200 mm of an installed post but before the rail is secured, the movement of the post at ground level must be not more than 3 mm;
8f1b5a46-6f52-5748-98b2-880efaab7935 | note | ○ Backfill material around the steel tubes and soil plates of gating leading end treatments, must be compacted to a minimum 95% Relative Compaction, measured in accordance with Test Method TfNSW T166;
9103ce42-0cf1-58c4-bcf1-f9cfc70919b0 | note | ○ Disturbed pavement or ground around a post must be trimmed and compacted to a dense, tight, smooth and sealed condition so that resistance to water penetration is similar to that of the adjacent surface.
090544ba-9e3e-5103-ab78-4a4b8bd5c56a | note | Reference document - R132.4.2 R132.4.5 & Manufactures Docs
42e58480-a301-5393-9383-41c05dfbcc4e | note | Record of conformity - Verification Checklist
6695b600-6e4d-50a0-a6bc-181fc4861e9b | note | Type of Record - IP
8b426737-8b45-5a92-ae84-9dd46f560594 | note | Responsible Position - Foreman
| checkpoint | Excavating holes for post installation where post driving is unsuited
7196a95b-69ad-5c16-8a48-2f76a0cdb239 | note | Criteria/Test Method/Spec - Where post is to be installed through a bound pavement layer carry out excavation or pre-boring to achieve a min. hole dia. of 400 mm. Extend hole dia at least within 300 mm of the level of the bottom of the installed post.
34650870-ed8c-5d15-bc7d-928cb9110f1d | note | ○ Locate each hole so the post will be positioned centrally or towards the nearest traffic lane in the prebored hole.
98afd28f-d7ca-5a8f-bec3-c40b25ea524d | note | ○ Backfill around posts must be clean, well graded, non- cementitious granular material or material obtained from excavating the post holes, provided any different material types from within a hole are placed to match surrounding layers.
19a23625-5bab-5ee4-8460-b3759bc27415 | note | Reference document - R132.4.2.1
a31a7170-c2a1-5978-8c30-e90ec19bfd79 | note | Record of conformity - Verification Checklist
d87186c6-a2e8-513a-8ae0-9e75e4f78084 | note | Type of Record - IP
7bf01793-5967-5e6a-9cf1-80d5172ad48d | note | Responsible Position - Foreman
| checkpoint | Post construction tolerances
d5c5d9df-0ce8-5602-baf8-5e30f8e819af | note | Criteria/Test Method/Spec - Posts installed at correct direction, visually smooth and regular and within tolerance.
f6ab7311-2e8b-5601-834b-802aa237ba78 | note | – height: +/-20mm,
04625226-86ae-5f6c-88ae-77ed656c7d9e | note | – line: +/-20mm in plan view,
ca6de25d-68cd-5d64-8fda-25db39088bcd | note | – verticality (to the ground at the front): +/- 15mm at the top, or to manufacturer’s recommendations.
656f0e10-7a5e-5f22-bf11-1e0525a14426 | note | ○ Tolerance on post spacing must be +/-25 mm. The deviation of the top of any post from a straight line joining the tops of the posts on either side must not exceed 10 mm, after allowing for horizontal and vertical curves.
bb58d6b9-2403-5650-be33-7f6012e5380f | note | Reference document - R132.4.5.1 R132.4.5.2 & Figure R132.1
2416d7af-e576-5bc4-9c62-458bdc175fc6 | note | Record of conformity - Verification Checklist
9704604c-f344-5eac-a7a4-523d5cd82025 | note | Type of Record - IP
a9c9f21e-37a6-577b-a8b7-9a946761f821 | note | Responsible Position - Project engineer
| checkpoint | Installation of rails
d3f7eb93-3a71-5951-b3b3-7a04ed5f15dc | note | Criteria/Test Method/Spec - Guard rails are installed to the posts as per manufactures manual installation information, with correct direction, overlapping, and height as detailed on the manufactures associated technical drawings
94dd7b50-ac33-5250-8822-1abd185a2c86 | note | Reference document - Manufactures Docs
7dbf1912-2d38-534f-9e01-122db5027673 | note | Record of conformity - Verification Checklist
cbbc0655-ddd0-513d-ad90-39b54e9f2db7 | note | Type of Record - IP
7a16480c-f1d8-5fa0-af97-4b159f1f68f8 | note | Responsible Position - Project engineer
| checkpoint | Install end treatments
63944e6c-bbe4-5e76-8f78-3a6d25c58da1 | note | Criteria/Test Method/Spec - Install as per manufactures manual installation information and associated technical drawings
1adb5d61-ca5e-5c3a-8076-12dddce1c751 | note | Reference document - Manufactures Docs
9d8562d9-1f8e-569d-982d-dbcdd8ab0303 | note | Record of conformity - Verification Checklist
cdec3b12-33c0-5482-a3ad-4caa3dea7643 | note | Type of Record - IP
cc9ed143-1a4b-54ee-a7d3-109b8d34e6ff | note | Responsible Position - Project engineer
| checkpoint | Installation of delineators / retro- reflective units
3618a732-4ca0-55da-a19b-88d453032ef1 | note | Criteria/Test Method/Spec - ○ Safety barrier delineators are to be spaced to comply with AS 1742.2 or at 20m centres, whichever gives the closer spacing
fc9d3c94-146c-5a49-a192-2c9744617abd | note | ○ As per TfNSW STD dwg R0710-18 mounting plates shall be attached to the inside of the posts using M6x25 hex bolt with nut and washer, or other approved fastening system.
dcc832b4-36ba-5310-8f7b-bc662b35087e | note | ○ Arrange delineation units so that drivers approaching from either direction will see only:
b0a057e8-c810-5ad0-9b81-afc378fd4f35 | note | (a) red retro-reflectors on their left;
bd162922-7523-5ee7-bf1a-ee4c8258e7f0 | note | (b) white retro-reflectors on their right on two-way carriageways;
33166740-5184-5fb2-b28b-5e2d5ebbbfbc | note | (c) yellow retro- reflectors on their right on one-way carriageways and medians separating traffic in opposing directions
d5cc6899-601e-5dcf-82a1-8dbb37512318 | note | Reference document - R132.4.6 & TfNSW STD dwg R0710 -18
cb47ecde-1f55-558c-aab5-1a9f27dac6b4 | note | Record of conformity - Verification Checklist
34339331-9d93-5b6b-9052-26785450c32c | note | Type of Record - IP
5f073a7c-9e40-5bdd-8210-5a8c54a71e90 | note | Responsible Position - Project engineer
| checkpoint | Obtain approval for opening of traffic (if applicable)
9065cc4a-66a7-5c4b-95cf-33b025f5c395 | note | Criteria/Test Method/Spec - Submit, at least three clear working days before the proposed exposure of the safety barrier system without fully operational end treatments, full details of your proposals together with a risk assessment of your proposals.
99c75e65-ce0b-5d77-82cd-bd45606e2832 | note | Reference document - R132.1.4
9dded780-6892-567d-a95e-0e7d83487c07 | note | Record of conformity - Hold point
4f61d222-fec1-5e06-96a8-d82fc7e4535b | note | Type of Record - HP
b58e3c81-b905-50c3-a0a6-b9be20cbd0dc | note | Responsible Position - PV/Project engineer
| signoff | HOLD POINT
| checklist | ITP - R142 - Retroreflective Raised Pavement Markers | itp | ITP - R142 - Retroreflective Raised Pavement Markers | 38f704fb-4bde-4479-85d9-2466c55cc4f7
| section | Retroreflective Raised Pavement Markers
| checkpoint | 1. Prepare Safe Work Method Statement.
0462e489-51e8-526a-9571-b6d71c901ea0 | note | Criteria/Test Method/Spec - WHS Act 2011, WHS Regs 2017
4387c7cb-91f2-5afd-a01b-af793c73f593 | note | Inspection/Test Frequency - Prior to commencing
776ee3d8-9d10-50f0-b402-d45b2d08393f | note | Inspection/ Test by - PV
d3507f51-b7c0-5f8a-94eb-9c5e838a202e | note | Responsible Position - SS/PE
9b7f2e40-bd87-55c9-b053-cde3e5675e2c | note | Type of Record - SWMS, HPR Form
80eeeafb-65a3-5f0d-bd11-eb404223b79c | textbox | Initials:
| checkpoint | 2. Approval of materials to be used; Retroreflective markers – Adhesive
b8128ab0-e36c-50c0-ba77-1c8a9eb94fea | note | Criteria/Test Method/Spec - AS1906.3 & ATD2015/01 RMS 3354
210c0930-c6e5-50d7-95d1-074b1dcbbbca | note | Inspection/Test Frequency - Prior to commencing
1f060e8b-915d-5f6a-9d72-3108a9b8ed8a | note | Inspection/ Test by - Supplier
7ef9ed82-25e0-5de9-84d3-66319d3a5b9f | note | Responsible Position - SS/PE
69af3fd8-1e71-556b-9414-ffb00ef90f35 | note | Type of Record - Certificate of conformity
0c39c938-97b4-59d5-90be-9d3b410e2663 | textbox | Initials:
| checkpoint | 3. Setting out
f291d16c-a899-5edb-905b-ca52d7b51624 | note | Criteria/Test Method/Spec - RMS R142 Clause 3.1, Release of Hold Point
93743035-c496-592e-a10e-a52ef389ec21 | note | Inspection/Test Frequency - Application of retroreflective raised pavement markers
07f017ec-f926-549e-ae62-fcc6853ed737 | note | Inspection/ Test by - PV
010dcc0f-fcd1-582f-a38b-177a18c8fdd0 | note | Responsible Position - PE
f80d1487-7757-5a00-a476-9c5dfdcc5616 | note | Type of Record - Client notification
29d1b754-c6a9-5f58-8c3a-ffb006b67031 | textbox | Initials:
| checkpoint | 4. Set out for retroreflective raised pavement marker.
d3caa1a4-d820-5e17-939d-a6f57779bc6f | note | Criteria/Test Method/Spec - RMS R142 Appendix 1, Release of Hold Point
327cb6c3-3824-5c46-83e7-17a40fca1649 | note | Inspection/Test Frequency - Completion of setout
32114a47-3d4f-5561-8a34-839659af125c | note | Inspection/ Test by - PV
2fea5c51-3a32-56b6-83cb-af3cbf864ff3 | note | Responsible Position - PE/Surveyor
ba86df5b-7676-55de-9b42-07455e96181f | note | Type of Record - HPR Form
730a330b-f2a6-59c7-b8c0-0a9b90cd6247 | textbox | Initials:
| checkpoint | 5. Install retroreflective raised pavement marker
17c562cc-f0f0-5881-8b22-816940e5df20 | note | Criteria/Test Method/Spec - Visual inspection R142 Cl 3.2.1
d6a9268b-59ad-5bfc-a153-36027733cc4f | note | Inspection/Test Frequency - Completion of Installation
64307a03-c546-5ae5-88ae-02bd1d7fc21c | note | Inspection/ Test by - SS
b6c820c2-b231-56aa-81cb-f6992a7251bb | note | Responsible Position - PE
d1579aec-4035-55bf-b95e-a4c8079ee88c | note | Type of Record - As-built
0f585723-0de8-57e2-8225-a2062c99569a | textbox | Initials:
| checkpoint | 6. Remove redundant markers
ccd233fa-53d7-5976-b3a4-1a5ea817b24a | note | Criteria/Test Method/Spec - Visual inspection
81f096a4-f94e-5c96-ac2b-53cc4c8cca5e | note | Inspection/Test Frequency - Completion of removal
598ebcbc-d2b2-5450-b446-646f3d6405ae | note | Inspection/ Test by - SS
43e75a3b-80c4-5b10-b368-2ff68649731c | note | Responsible Position - SS/PE
e92c39b8-2978-522e-a2f7-d6faf441edaf | note | Type of Record - ITP
6a7d2928-c376-547c-9804-14af6c8eec6c | textbox | Initials:
| checklist | ITP - R143 - Signposting | itp | ITP - R143 - Signposting | c38aa779-f488-42c2-bc99-6e3349dfe287
| section | Signposting
| checkpoint | 1. Prepare Safe Work Method Statement.
96920749-9f4c-517d-a354-5f9cf0c0fc17 | note | Criteria/Test Method/Spec - WHS Act 2011, WHS Regs 2017
5050fd98-6be6-5d64-81c6-6162e3bb2281 | note | Inspection/Test Frequency - Prior to commencing
a6e48abf-8656-51fd-ac7a-da0843c2caeb | note | Inspection/ Test by - PV
4d73c249-5b29-58f6-9575-805d2233bf10 | note | Responsible Position - Site Supervisor (SS)
b102b17e-5d19-531f-b72f-0e83e0551010 | note | Type of Record - HPR Form
9e026b92-3b42-5573-b300-623db556861b | textbox | Initials:
| checkpoint | 2. Approval of signs for use
6119c3e3-bf28-5a98-9f6d-7f6192a4fd3c | note | Criteria/Test Method/Spec - RMS 3400 Contract Drawings
9cdd81d4-41fd-5c3f-a9a7-fa6ba8f555cb | note | Inspection/Test Frequency - Prior to commencing
2b64cbc3-bc80-5217-8f81-f9a61caa5f77 | note | Inspection/ Test by - PV
8769a17b-26b6-5260-b74e-5a65e56d3a36 | note | Responsible Position - SS/PE
49143a83-227c-5e2a-a58f-592dafc6b20e | note | Type of Record - HPR Form
596e5c36-755e-5709-a47e-734fd3a91f59 | textbox | Initials:
| checkpoint | 3. Set out for new signs.
dd989c15-d400-5a7a-b6e2-4f91a404f5fb | note | Criteria/Test Method/Spec - RMS R143 Clause 3.2 Contract Drawings Release of Hold Point
33e075f6-2f55-56a9-8de2-26a7ffb79dfa | note | Inspection/Test Frequency - Completion of setout
10636cd0-d3f8-5f87-89ce-3b91b58f214a | note | Inspection/ Test by - PV
e573c4e1-9bc9-5590-9313-55eaa8b6db39 | note | Responsible Position - PE/Surveyor
31234ff5-e96a-5106-90ca-9425ec7d9fc1 | note | Type of Record - HPR Form
54ee4ac2-5e89-59d5-af82-cd38b07653d0 | textbox | Initials:
| checkpoint | 4. Install Signs as per Contract Drawings
a24f4ba4-c4ea-5988-9700-072cef4ac09d | note | Criteria/Test Method/Spec - Visual inspection
536b3637-88f5-556c-a3c0-35bb7fbd024d | note | Inspection/Test Frequency - Completion of Installation
da4e7090-8a05-5a01-99cb-f2c1842c2752 | note | Inspection/ Test by - SS
fb90ba72-68d9-5a52-9d90-fc2dfe79054b | note | Responsible Position - PE/Surveyor
a585eb13-e676-52c4-9fb0-720af731eff1 | note | Type of Record - As-built
d2d2d45d-320a-597f-aeed-9d2809fdbeae | textbox | Initials:
| checklist | ITP - R145 - Pavement Marking | itp | ITP - R145 - Pavement Marking | 5f954b8d-4638-4c47-9f79-4c1517892d70
| section | Pavement Marking
| checkpoint | 1. Underlying lot conformance (if applicable)
0ca4c08f-1d56-596e-a297-808310eeb962 | textbox | Lot No:
38d22341-334c-58c8-8db5-26b0fb61bd15 | note | Criteria/Test Method/Spec - Underlying lots conform to applicable specifications
58dc9075-8c97-5eb7-be74-9fbb85f9fda8 | note | Reference document - Previous Lot Record
b5c31bdf-2c92-5511-9582-7f8a1cc733c7 | note | Record of conformity - Lot conformance
ce71266d-c581-5ebb-9e3c-de78e4df7c89 | note | Type of Record - Record
693a0afb-98d1-54f0-ad9e-04fe60e5306b | note | Responsible Position - Project engineer
| checkpoint | 2. Check if traffic controls are in place
8ed8f7e5-e3f0-55cc-88d3-003c6e147242 | note | Criteria/Test Method/Spec - Road Occupancy License Obtained if required.
6748322f-3a51-59b4-824f-aaec7526e243 | note | ○ Pedestrian and vehicular public traffic control planning measures established
1c43fe4c-7bfe-556e-8412-4541f4e45050 | note | Reference document - G10.2.4
aadcfc26-1a7e-57b9-a44b-03cc2e322bcd | note | Record of conformity - Approved TCP
3a1e676a-4227-5cbb-9662-fed2b9d2c8df | note | Type of Record - IP
c952ccf0-d10a-501d-81b2-add30dfa7bfa | note | Responsible Position - Project engineer
| checkpoint | 3. Painting Contractor Certification
37cc48ae-fe43-52f5-9c8b-04cfef9d829b | note | Criteria/Test Method/Spec - ○ Works carried out by organization that is accredited to the “Painting Contractors Certification Program
24379975-c730-5323-8fc5-4d16cf7949b3 | note | Reference document - R145.1.4
fb7dffb6-e643-5dc7-acfb-d7773d7bfd99 | note | Record of conformity - Certification
7d6f1744-d923-5f84-af34-6bf5303136ae | note | Type of Record - IP
e82c3b9b-10ad-5443-8416-40a50212c467 | note | Responsible Position - Project engineer
| checkpoint | 4. Verify type of marking material as shown in drawings Waterborne paint thermoplastic paint
6bdb5de9-b28b-5293-8837-49739815c5a3 | note | Criteria/Test Method/Spec - On concrete surfaces in the main carriageway and all local road – waterborne paint
6f506066-1688-5513-8dfe-30c6341261dc | note | ○ Asphalt surface on the main carriageway – thermoplastic paint
2ece341c-a556-5bc7-92a1-f8c4ed46ef92 | note | ○ Type as per relevant design drawings & R145 appendices
b08cdac6-3836-5637-b4a2-b78187feeeb0 | note | ○ provide the RMS representative a list of material proposed for use and limitation to be used
fc4dbb4f-cb5c-5689-a1f2-b77948b442b8 | note | Reference document - R145.1.4, R145.2.1, AS 4049.3, AS 4049.2, 3359, 3360
9ec8e01b-475d-5baf-9634-a217e73c332b | note | Record of conformity - Verification Checklist
d8e99436-ee43-5724-a8a4-111bb29cfea4 | note | Type of Record - IP
a6576b9b-45af-5de1-a7eb-3569351bedf8 | note | Responsible Position - Project engineer
| checkpoint | 5. Verify the reflective glass beads conform to specs requirements
62152bfd-66ee-58ad-80c5-1a53394d674f | note | Criteria/Test Method/Spec - (APAS) Specification APS0042 Clause 6.2 “Heavy metal content”. Obtain evidence of compliance
a386a34e-ac1d-5d72-b0a8-621723e3acf8 | note | Reference document - R145.2.4
501ab432-5722-5c2b-9e7f-60251d89028b | note | Record of conformity - Verification Checklist
98fcb928-a879-5e2b-988c-c30f321c42aa | note | Type of Record - IP
76621f64-8213-5d52-a95f-bd9df83641e9 | note | Responsible Position - Project engineer
| checkpoint | 6. Verify conformance of raised pavement markers & Adhesive
2d8ab91a-8cc5-5fd1-81a7-851cc636c009 | note | Criteria/Test Method/Spec - ○ Use only retroreflective raised pavement markers prequalified by the RMS. Prequalified retroreflective raised pavement markers are listed in ATD 2015/01
243745b7-56de-5e29-b1b1-74bc384c9872 | note | ○ For new installation and complete replacement works, all markers must be identifiable for at least twelve months after the initial installation.
72639078-e165-5289-9f9e-3b4b73b8f9bf | note | ○ For the adhesive and RRPM (retroreflective raised pavement markers) provide a certificate of compliance verifying that the product complies with the specification, together with the results of the relevant tests.
2b698c8f-66c5-589a-8ffd-9cc9c15bb92a | note | Reference document - R142.2.1 3354.7
a5b3205b-7970-5c3a-b726-22dd85654608 | note | Record of conformity - Verification Test Certificate
435d4a77-6073-5984-b365-e21d5fdee471 | note | Type of Record - IP
cee9a8f5-19c2-5ddd-9b97-be8ceb674725 | note | Responsible Position - Project engineer
| checkpoint | 7. Sampling and Testing Plan
29c9e47e-5a98-53a2-a2a8-880eeb864a41 | note | Criteria/Test Method/Spec - Submit to PV contractors proposed sampling plan for assessing the pavement marking
3aff5798-e744-543a-ad06-88ab02bdc9b1 | note | Reference document - R145.5
4c68dbee-fb2f-5b4a-86cb-52cd8c6746b1 | note | Record of conformity - Sampling Plan
4eab24de-16b7-5159-a1a6-184210814428 | note | Type of Record - IP
a580b389-8d8b-5da9-a1fa-33722ec30b62 | note | Responsible Position - Project engineer
| section | Application
| checkpoint | 8. Prepare the Surface for marking
f7fe9e1b-169e-5348-b62a-ac50eadc7050 | note | Criteria/Test Method/Spec - The area to be marked is dry free of dirt, gravel, flaking and other loose foreign material
94175295-46bd-51f7-a856-d6b14214c57f | note | ○ The area around making area is also clean to avoid tracking into the marking area
a15efed5-b27e-5e6b-98dd-10fab8183ecf | note | ○ Curing compound on marking areas of concrete pavements is removed by grinding or blasting.
fd7b9fae-d875-5c02-965c-6ca7639a30bb | note | ○ Surface is compatible to the new line marking materials.
c6ac399f-41dc-552f-b212-5dd463f01b2d | note | Reference document - R145.3.1
9e143eca-98b1-5036-b7f6-68b5b6ca48df | note | Record of conformity - Verification Checklist
58b073b8-3d02-56d0-a5fb-c0ecfb4a3507 | note | Type of Record - IP
87ff2413-23df-5ebb-8784-1bdedefb1e99 | note | Responsible Position - Project engineer
| checkpoint | 9. Set out the works for installation of pavement markings / raised markers
0723a8d9-a6ad-5988-89d3-61b88e55718a | note | Criteria/Test Method/Spec - Notification made to the Project Verifier that the setting out to pavement markings and markers have been done in according with the design drawings
c3a7755f-f4e3-5a33-88d6-4d676daf1080 | note | Reference document - R145.3.2.4 R142.3.1
fb64962b-f5ea-5c42-a96f-fdbe513e5f49 | note | Record of conformity - Hold Point
cc2f57e6-6899-50d0-8118-42940ba6f93e | note | Type of Record - HP
04bd2eee-0d15-5498-8731-c2a911d44574 | note | Responsible Position - PV/Project engineer
| signoff | HOLD POINT
| checkpoint | 10. Supervise the application of pavement marking / markers
20a482dd-6b9f-529b-8a3a-fbc5f74ddb8c | note | Criteria/Test Method/Spec - Paints and markers installed as per manufacturer’s recommendations
c324436b-2b67-5505-a003-21f9bcdf2673 | note | ○ The same materials used with those nominated in the certifications
8c04fb0e-c92f-550f-bd92-b7f18b744083 | note | ○ All longitudinal lines have been applied by the nominated machine unless approved by Independent Verifier
34652b43-ebc6-535b-a7f6-cdfb90934b1c | note | ○ Markings are straight or with smooth, even curves where intended
9641def3-bade-5bd0-bb5f-93965e2a2d0c | note | ○ Edges are clean sharp cut off
34f57830-5cc0-5b66-80a0-38be97209b31 | note | ○ Markings uniform in appearance, texture, width & thickness & free from unbeaded areas
2fbefc12-cc3c-5405-9859-80fef12b76eb | note | ○ Beads uniformly applied onto the material immediately after it has been applied to the pavement & while the material is still molten
9475f5db-1f22-5262-8e12-9e7d3bd7f6c9 | note | ○ Retention of bead material is achieved
45c2511a-cf58-5fd4-a08e-4f85130cf1eb | note | ○ Markings are neat & free from traffic damage or other defects
6523659b-ea2a-53e7-b101-63d5b4a33c72 | note | Reference document - R145.3.2.2, R145.3.4, R145.3.6, R145.4, R142.3, R142.4
305a444f-c1f7-5937-b69c-c1c7079fe115 | note | Record of conformity - Verification Checklist
42c5e6e3-6161-5d35-9caf-ff3626084cc7 | note | Type of Record - IP
af14d0ce-50a9-56cd-b2ce-6d3220afc416 | note | Responsible Position - Project engineer
| checkpoint | 11. Field test of the paint performance. Provide the results of your testing to the Nominated Authority within 10 working days of carrying out the test
ac4d6948-6050-5eec-8f9f-12a7f219e2df | note | Criteria/Test Method/Spec - Thickness of non-profile marking≤6mm
51df7eb1-d65d-5cc3-ab89-f9a7355304f4 | note | ○ Dry Retroreflectivity: min.250 mcd/lux/m2 up to 20 days after opening to traffic.
2673a40d-2985-513a-ba49-5053ab54641c | note | ○ Wet Retroreflectivity: min.80 mcd/lux/m2
a07e5033-64f6-5995-9bd3-13971f1a4186 | note | ○ Skid resistance: min. 40BPN
d8dfd20c-2e4c-50a7-ab67-8f01ec94ac16 | note | ○ Colour change: min.3
013c112f-ab72-5ec3-9299-c47345f1dbb5 | note | ○ Luminance factor: ≥S 2500-N
250153ff-4482-5d06-bdd9-87ed2eae1666 | note | ○ the pavement marking tested must be “70% of area intact” or better
cfb3f97d-d07a-5e38-a1c7-ef26ee19b163 | note | Reference document - R145.4, R145.5 AS 4049.5
b2032115-4bfe-594d-a0e3-26bf11e796ed | note | Record of conformity - Test Report
88984114-814f-560a-b3fa-eb46601644f1 | note | Type of Record - TP
20a958c8-1fa5-59f7-9a27-e96953448556 | note | Responsible Position - Project engineer
| checkpoint | 12. Reinstatement of Pavement Markings After Road Works
54e0eeab-33a8-51b8-a383-4e445d894c69 | note | Criteria/Test Method/Spec - Reinstate the pavement markings as soon as possible after road works where the pavement markings have been removed or damaged, to maintain the delineation for road safety purposes Temporary raised pavement markers can be used for delineation for up to 10 days after opening to traffic, after which the pavement markings must be reinstated.
3fa0bb04-10f7-562b-bf9f-7e8fc3880722 | note | Reference document - R145 CL3.5, R145 Cl 3.5.2
3b58fd2d-ead6-5889-9252-1531f9d9c95b | note | Record of conformity - ITP
96467de0-e27a-51bb-9d3a-558fde85a8d3 | note | Type of Record - IP
09b5ba98-4711-5aba-8880-2217a5b7d0a8 | note | Responsible Position - Project engineer
| checklist | ITP R44 (ed6) - Earthworks QA |  | ITP R44 (ed6) - Earthworks QA | 0d4889ed-ba25-48e2-b73b-18d36cf36b4a
| section | Earthworks QA
| checkpoint | 1 - Implement & monitor ERSED controls
7e32794f-d3e6-5792-8d8a-65b981d45ea8 | note | Spec / Doc Ref. - R44.1.8, G38.3.1, G38.2.2.2
cd4e8c4e-f938-559f-ac00-5374ee468159 | note | Inspection Requirement - Submission of an ESCP(s), Submit written advice that the ESCP controls have been implemented or the date they will be implemented.
ba5b6107-9ccf-547e-974e-456f32c9ba08 | note | Acceptance Criteria - ESCP requirements listed in G38 Cl2.2.2.
9d39707a-a7b6-58fc-b22d-c613905c323b | note | Frequency - ≥10 work days prior earthworks, ≥5 work days prior earthworks, each section
dd97ba97-2c10-583a-8e19-8a869f8c4cbb | note | H / W - H, W
5f15267d-b81f-549e-b738-ee73b316a406 | note | Inspection/ Test Type - Submission, Submission & inspection
777989b7-4169-5ffa-aad2-e4eb35b427dc | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - HPR, ESCPs, WPR
d827efad-4e49-58fd-8efb-ba210e58841c | note | Verified by - Project Mgr (PM) / Project Eng’r (PE)
774fcc17-8b3b-5057-a7f7-4c994c0142f7 | date | Verification Signature - Date:
| signoff | HOLD POINT
| checkpoint | 2 - Existing utility locating & NDD potholing
d1c76032-6138-5b79-98f7-3cd40c892711 | note | Spec / Doc Ref. - R44.1.5.1 (n)
8d249294-1b6f-5da8-a845-d90caf49f816 | note | Inspection Requirement - Check service locating & marking, and NDD potholing of existing utilities is completed
dac78447-1b4d-53a0-8f86-95b758ff4d78 | note | Acceptance Criteria - Controls to protect utilities during earthworks in place
4d63c513-47db-553d-9dce-673a68a9899c | note | Frequency - Prior earthworks, each section
9cd60a36-0fef-5a6b-8ffd-b67e873f9da2 | note | Inspection/ Test Type - Visual
68ed99bf-ca82-59c0-bdd3-18616dd41112 | note | Verified by - PM / PE / Supervisor (S)
1080154f-ffb6-5be3-905c-9a8dc0c8ee54 | date | Verification Signature - Date:
| checkpoint | 3 - Setout earthworks extents
50e68ac3-dbf4-54a4-9f3e-c6703a98e455 | note | Spec / Doc Ref. - R44.1.6.2
1008f8ab-1143-51c0-9c36-d61d50a5a5b1 | note | Inspection Requirement - Setout by marking on the ground the earthworks limits
cbfe62f2-5655-5832-8b3b-2cf9770feffd | note | Frequency - Prior earthworks, each section
b5b7750d-d5e9-5805-9ea7-71c22065bd17 | note | Inspection/ Test Type - Survey
d9392548-dda1-53cb-80f1-a8c1e51faf25 | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - Photo of marking in place
15a76ed9-032d-5322-9dca-9260b1410d4c | note | Verified by - PM / PE / S / Surveyor
b6aebf0b-472f-5f24-83f4-28161ac1475e | date | Verification Signature - Date:
| checkpoint | 4 - Removal of topsoil
fecb5c4e-607e-583e-94fd-db5104555783 | note | Spec / Doc Ref. - R44.2.5.1
411f8b84-5c50-5843-981f-b269bdac22cb | note | Inspection Requirement - Check topsoil removed & stockpiled correctly
fc44c3cc-00b7-5309-86e0-055d71815a27 | note | Acceptance Criteria - Strip full depth of topsoil in earthworks areas. Stockpile for use in revegetation.
b34ed4bf-a249-5d7d-92b9-ff1baaacc951 | note | Frequency - each section
6008c8fe-1d8f-59db-b021-25223d63046e | note | Inspection/ Test Type - Visual
baf20a52-6d58-541c-b341-8948b023fedb | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - Photo
f953faf8-0e43-5b5f-9363-40f7a28192ff | note | Verified by - PM / PE / S
52db033a-118f-5711-b1d9-9385f940dc94 | date | Verification Signature - Date:
| checkpoint | 5 - Test pits to verify CBR10 day & PI of subgrade & insitu SMZ
040b72e8-0328-5d2c-864f-f1fda001ce73 | note | Spec / Doc Ref. - C-0604.00 R1 Table 6 RNB-241, R44/A2.2, R44/L.1
d50b5f8a-b8a3-577b-81be-09cf38d1cd31 | note | Inspection Requirement - Check CBR & PI samples completed from test pits
edc4af9b-ff0c-55e7-95f0-5d5fec5d500d | note | Acceptance Criteria - CBR: Subgrade ≥3%, Insitu SMZlower ≥ 15%,
7de5ba4b-9047-5192-8050-ed3ec9c51cd4 | note | ○ Insitu SMZupper ≥ 30%
639bd5d7-4cc2-5ed4-ba94-4612c39b1c57 | note | ○ PI≤25% (no insitu SMZ)
f49e6781-e8bf-54b6-a131-d03094620353 | note | ○ PI≤15% (insitu SMZ)
1f826d12-6016-5086-88c1-66c9233ff287 | note | ○ SMZ: Max particle dim: 53mm, >50% passing 19mm sieve, >30% passing 2.36mm sieve
44f2e777-df37-59bb-bf69-907d365a4683 | note | Frequency - 1 / 1000m2
3274085b-f1f7-5628-b2c7-090ea927f23b | note | ○ 1 / 1000m2
fca28ef5-5e86-5ead-86b6-1fae5f3c9982 | note | ○ 1 / 1000m2
050262ae-bcf3-552c-87d5-75a4d172977f | note | ○ 1 / 1000m2
56a68af0-b5b7-5200-a0d3-1d2e12bc808b | note | ○ 1 / 1000m2
7701d5e8-8a56-5fd2-8436-6c82d08a9be6 | note | ○ Each Lot
1ccb04f7-395f-5de6-a1da-7a92934d6029 | note | ○ Each Lot
9f6eaa01-59ba-58c8-82d6-52462740d51d | note | ○ Each Lot
26758e8b-45d5-59b3-b1f3-f8ccb1b92547 | note | Inspection/ Test Type - T117, T109, Inspection / T280(if req’ed), T106
55b66211-a001-51b4-91fb-b81e2dd86a06 | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - CBR, PI, max particle, T106 test reports
9bc7907e-e7d1-5f46-8e6c-568367a32bac | note | ○ Note: Report P20009-1 (in D&N Geotechnical report C-0604.00) indicates the ex pvmnt material at BH01 has CBR10 day of 40% per T117)
4cf42276-6e4a-5bbf-88fd-5ec1deea8604 | note | Verified by - PM / PE
1b2db79a-645b-5eef-8916-1fb941f1a369 | date | Verification Signature - Date:
| checkpoint | 6 - Excavate to design levels and profiles
c248b095-4188-52c7-89bc-84877aacb651 | note | Spec / Doc Ref. - R44.3.2, R44/A2.2 C-0604.00 R1 Table 6 RNB-241, Pavement Design Approval - STH18 00222 Tbl R44.8
a32b30fc-b6a5-52fe-a702-be19216edd05 | note | Inspection Requirement - Check excavated to Design Floor Level (DFL). Check CBR & PI tests completed. Present floor for inspection.
a2c9aafb-df12-5e68-ac8b-e51eb57d98d5 | note | Acceptance Criteria - Where at Top of Formation (DSL-330mm), there is ≥300mm existing Sydney Rd pavement, SMZ comprises existing pavement left in-situ, therefore DFL is DSL-330mm.
42d766b7-c307-504f-9f8f-2094bb035465 | note | ○ Where no existing pavement, DFL is DSL-630mm (& a 300mm SMZ to be provided).
c83dcd5a-2787-538c-96cf-57c3d271664f | note | ○ Level tolerance: +10/-40mm (no insitu SMZ), or +0/-20mm (insitu SMZ)
52561b34-cdfd-5f0b-95fe-4d542d04d039 | note | Frequency - each section
19c2d573-e1bd-5ad6-9789-6e96d45ae0f8 | note | H / W - H
1bc4226c-25ea-5c46-ad23-24afdd8aa3f9 | note | Inspection/ Test Type - Survey, Test & Inspection
4329924e-eac5-5ee4-8fec-cd426bbfa9e9 | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - HPR, DFL Level conformance report
b3b4ba52-c627-5e5a-af00-5ecfe02df83a | note | Verified by - PM / PE
7479b377-4a07-5966-8f65-e81b27af968f | date | Verification Signature - Date:
| signoff | HOLD POINT
| checkpoint | 7 - Proof roll DFL
44797871-bad2-591a-a700-8e1f2b604c1d | note | Spec / Doc Ref. - R44.7.5, R44/L.1
c1b78ce6-6cef-59d5-8d63-a65c01ee7a78 | note | Inspection Requirement - Notify Council of proof roll (WP)
2bcf2f1c-486c-5e98-b37e-545a84cc6705 | note | Acceptance Criteria - Not exhibit visible deformation, rutting, yielding or show signs of distress / instability
011cdb1b-a583-51c1-9997-1d74bf6859bb | note | Frequency - ≤1 work day of proof roll
78bec119-cf78-5d4d-b9b8-08931bb602c2 | note | H / W - W
f44d06f7-e266-5cfc-8081-290c14539877 | note | Inspection/ Test Type - T198
016589ad-91b2-5083-bd5b-aef54fc27af1 | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - WPR, proof roll (T198) report
79acdef4-7007-5d84-bb0c-e1db329ae8ba | note | Verified by - PM / PE
1c118335-f815-52f7-903c-f6cc30e43260 | date | Verification Signature - Date:
| checkpoint | 8 - Unsuitable Material (if any)
7c96e5c1-d30b-5dec-b1ea-021382b31acc | note | Spec / Doc Ref. - R44.2.6, R44.5.2.1, R44.7.5, Tbl R44.7 R44/A5, R44/L.1
f885b761-5bef-591b-bc7d-64ebc19d14fa | note | Inspection Requirement - Where unsuitable material indicated by:
cc3b644d-3c3f-5bbf-8be5-6fa35c705faa | note | – inspection in item 5,
847febee-7d6f-5e43-ac54-a06323cdc448 | note | – CBR / PI testing, or
16b68dfa-d9f8-5f17-9302-9a51855ed654 | note | – proof roll, excavate unsuitable to the extent directed by the Principal.
f8494e5f-e54c-50dc-bdaf-4fe376426239 | note | ○ Notify when unsuitable removed to the extent directed (Hold Point).
330cc4bd-ffc0-5cf7-aa7e-68a54bc12a61 | note | ○ Replace w/ compacted Earth Fill or (if directed) Foundation treatments
d3c36707-76bb-5b37-b768-7f1964e55906 | note | Acceptance Criteria - Min Rel Comp: 98%, Moisture: 60-90% of OMC
0fc465dc-3d7b-59e6-8daf-12f789361071 | note | Frequency - each section of unsuitable material
a6357b40-86f4-5b3c-a802-bbe59eb59392 | note | H / W - H
70ca88a6-96c4-5b3e-94f6-d01c12d821f7 | note | Inspection/ Test Type - Inspection, Refer R44/L.1, Refer R44/L.1
30fa86ed-472f-5a26-98ab-941257303b6a | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - HPR, compaction & MC (if replaced by compactible material) report, Survey reports (before & after)
ab5b9980-2934-5a5c-918b-8abf0ba8169f | note | Verified by - PM / PE
8017b09d-646a-5b11-9f71-ee7b13208467 | date | Verification Signature - Date:
| signoff | HOLD POINT
| checkpoint | 9 - Site won SMZ material (for placement where no insitu SMZ)
19ac260f-ba91-57a7-a3eb-f5e1e9bcb579 | note | Spec / Doc Ref. - R44.2.8.5.1, R44.6.1.2, R44/A2.2, R44/L.1 C-0604.00 R1 Table6 RNB-241,
5d501bda-e17e-5ec8-a4ab-b6bdb0266133 | note | Inspection Requirement - Submit test reports verifying conformity of each site won SMZ material stockpile
fc895eda-7350-5c42-b3a2-545e0351686f | note | Acceptance Criteria - CBR10 day (per RNB-241)
e21fe58b-89e3-5be9-b6c9-a90be494a9e3 | note | – Upper layer: ≥30%
f55b8b70-704e-5a1b-819e-a5ec56f092a4 | note | – Lower layer: ≥15%
6a4f3ddd-afd3-5573-864e-b13963330b1b | note | ○ Plasticity Index: ≤15%
bfb58ea7-5944-5c83-8536-d8b957d33c99 | note | ○ Max particle dim: 53mm
0d314c1b-3ccc-5f36-89a0-64519fbd4209 | note | ○ >50% passing 19mm sieve, >30% passing 2.36mm sieve
9442cbf8-a3f5-54f4-ac8d-e726b62b6896 | note | Frequency - Prior SMZ placement,
89214678-936e-5ff1-a2bb-cda69281371a | note | ○ Each Lot
ea20bd1e-662c-58a4-8bc6-15e3a1d5d07b | note | ○ Each Lot
617ef8e8-233d-5296-bea3-ad7c54241cc5 | note | ○ Each Lot
5ebfe7ef-0405-530e-87cb-e2feba4a743d | note | ○ Each Lot
840a481a-53bc-5431-b752-b8e557c99e02 | note | ○ Each Lot
a5360bf3-d9a7-52e0-b3cf-417664bc8bf2 | note | H / W - H
c59e0634-ff83-5ccd-b177-eb3b56155015 | note | Inspection/ Test Type - T117, T109, Inspection / T280(if req’ed), T106
a454f5ee-94f5-56fc-b8ff-5c3f4f690708 | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - HPR, CBR, PI, PSD test reports
2f51a9b6-bcb8-5da4-b775-b13f7112bda6 | note | ○ Note: Report P20009-1 (in D&N Geotechnical report C-0604.00) indicates the ex pvmnt material at BH01 has CBR10 day of 40% per T117)
7c9801e4-7177-524b-9a95-923bc2c4f45c | note | Verified by - PM / PE
e0a163b3-80c0-540b-a4f4-2ded07531b4d | date | Verification Signature - Date:
| signoff | HOLD POINT
| checkpoint | 10 - Placed site won SMZ Layer (for placement where no insitu SMZ)
74917094-3781-5c5f-86f1-90ea65836b4a | note | Spec / Doc Ref. - R44.6.1.2 Tbl R44.7, R44.7.5, R44.7.7.1, R44/A5, R44/L.1 C-0604.00 R1 Table 6 RNB-241, Pavement Design Approval - STH18 00222
93f3e613-308b-5496-8a82-5980e6e53f70 | note | Inspection Requirement - Notify Council of proof roll (WP). Submit verification of conformity of SMZ, with test reports & survey conf reports. Check level, compaction, appearance, proof roll results conform.
075a8ff2-2c2c-593d-8157-06361b52dc0b | note | Acceptance Criteria - Level upper: +0/-20mm
dfaa2807-8dae-543c-98ef-650ab575fac8 | note | ○ Level lower: +10/-40mm
872893b2-0bb5-57bb-9c0b-70cdc21f2135 | note | ○ Thickness upper: 150mm
0dfc9653-9759-5b1f-beab-3a3f2a01aeae | note | ○ Thickness lower: 150mm
029027ed-0f32-5280-ba6e-267f4163e7c3 | note | ○ Compaction: 102%
de83741f-60cf-5c97-8383-535d6bda6fef | note | ○ MC: 60-90% of OMC
9bec27c2-38ab-5a19-8fb1-c323336b4610 | note | ○ Appearance: homogenous & free from segregated stone or excess fines.
86c06c51-08d7-52d0-8b22-f665adc573f6 | note | ○ Proof roll: Not exhibit visible deformation, rutting, yielding or show distress/instability
67d92102-29b9-5c94-befb-9caea366865a | note | Frequency - ≤1 work day of proof roll, Prior covering SMZ, Survey & geotech testing refer R44/L.1
2d083156-ba57-50dd-a568-abcf4590f9ed | note | H / W - W, H
c8e1506f-9888-5eac-ac7a-c47c71a4152a | note | Inspection/ Test Type - Survey
c2ea432d-3983-5b33-ba6f-c256d849ecbb | note | ○ Survey
a1ef733a-5624-51f2-81d6-6dfeb5c2b91a | note | ○ Survey
20231aec-8ceb-5a00-b34f-91a35a5293cc | note | ○ Survey
e44d5262-946c-5387-ad6b-d68f692578ef | note | ○ T166, T173
d18789ba-3d38-5eee-bb2e-70bccdae8c12 | note | ○ T120/T121
c7c8bff9-627a-56f0-b8a7-e837754aa08a | note | ○ Visual
fdf816ee-a434-5662-ae11-882e3c70a1cb | note | ○ T198
6b9d4996-6d13-5875-a7df-2562f0a116aa | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - WPR, HPR, Comp & MC test report, proof roll report, survey thickness & level conformance report
e2623ccb-542c-508e-adb3-8ce858a1eb1b | note | Verified by - PM / PE
619a69ad-0f69-54a9-841f-038fde2add50 | date | Verification Signature - Date:
| signoff | HOLD POINT
| checkpoint | 11 - Submission – Closed ITP w/ material & test reports, survey records
1fa0e94d-debd-5fd5-a05f-909dd78a58bb | note | Inspection Requirement - Submit closed ITP to Council.
aa603460-d778-55dc-b0f5-bc321d9458ee | note | Acceptance Criteria - Complete submission to Council
6c8eab43-cfe0-5b2b-ad3a-a4bf44bb17f0 | note | Frequency - At completion
571f3f8b-bfd8-5dd9-94d4-ea10d685535a | note | Inspection/ Test Type - Submission
1fe312ec-7978-5eac-a037-569c26df10f3 | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - This closed ITP & associated records
d26b3701-2f18-5354-acde-f44cc4003339 | note | Verified by - PM / PE
24a93d62-4ad2-5dff-b9cc-b3dc557ca4de | date | Verification Signature - Date:
| section | The lot verification records are complete and attached with all non-conformances and RFI’s closed out.
| checkpoint | Lot Complete / Records available:
ab4029dc-8de1-532f-91dd-1c881e2569cd | textbox | Name:
f554b39d-0144-5402-8f2e-d5fe0cef4824 | textbox | Title:
33066db0-cde7-55a4-8d98-2dce73feb3cd | date | Date:
| signoff | Signed:
| checkpoint | Lot Approved for Closure:
af2f79d8-0acb-534a-bd96-305770b5134a | textbox | Name:
1422e4f7-2b24-564c-b177-b4b245cb8a68 | textbox | Title:
d94026d2-c6c6-5d3d-bfa3-a79a0bbeb160 | date | Date:
| signoff | Signed: