## ITP-180-Control Cabling
ITP-180 Control Cabling
Project Name: |  |  | Prepared By: |  |  | Builder:
Project No.: |  |  | Approved By (Name & Position): |  | Date issued to Builder: | [5 empty] | ITP-180
Revision Comments: | [7 empty] | Revision No.:
Work Activity / Sequence | Reference (Australian Standards, Spec, Drawings etc.) | Acceptance Criteria (Meets Requirement of Aust. Standards, Contract, Specs, Drawings etc.) |  | Inspection & Verification Procedure Confirmed By: |  |  |  |  | Comments / Records Non- Compliances / Actions
|  |  |  | Name |  | Signature | Date
Safety Risk Assessment / SWMS / Safe work Procedures | Fredon Safety Manual and Procedures. | * Fully compliant, site specific Safety Manual and SWMS have been submitted and accepted by the Principle Contractor. * All Fredon electrical personnel undertaking these works have been trained and inducted in the Safety Manual and the relevant SWMS for these works. * All Fredon electrical personnel undertaking these works are qualified to carry out these works, and are trained, and competent in the use of all equipment and plant required to carry out these works.
Insert project specific requirements here
Scope Of Works | Insert project specific requirements here | * Ensure that the latest revision drawings and specifications are being referred to. * The updated / superseded drawing register, located next to the drawing rack in the site office, has been checked to ensure the latest revision drawings are being referenced.
Fredon shop drawings
Coordination | Fredon shop drawings Service drawings | Ensure that all new installations have been coordinated with other services, both new and existing
Ensure all control curcuits are designed to function under the necessary circumstances that they will be required to function under
Insert project specific requirements here
Cable Installation | Fredon Shop Drawings | * Ensure segregation is maintained pending cable insulation and shielding ratings * Ensure cables can communicate the specific protocols over the distances installed * Ensure the correct amount of cores have been supplied COMPLETE ITC-180.1
Insert project specific requirements here
Termination | Fredon Shop Drawings | * Ensure the requirements of the system and if it requires to be normally open/ normally closed ifor the control/status that is required * Ensure all spares are left in an open state and labelled accordingly * Ensure cable/cores can be easily identified for future works and maintenaince COMPLETE ITC-180.1
Insert project specific requirements here
Testing | Fredon Shop Drawings | Low Level Inputs * Point to Point test individual cores at both the origin and the destination COMPLETE ITC-180.1
High Level Inputs * Confirm the software can be seen on the head end system COMPLETE ITC-180.1
Insert project specific requirements here
Functional Testing |  | Activate functional devices and programming and confirm that the control sytem functions correctly eg. Manually Pressing Emergency Stop - turns off designated equipment
Insert project specific requirements here
Record Changes to Drawings | Working drawing (Ongoing As Built) | Ensure that all changes made to the original drawing have been marked and noted on the Working Drawing located in the Site Office. These drawings MUST be kept updated for use as as built drawings.
Final Inspection |  | Cross check and verify that the as built drawings are complete and correct.
Verify all inspections are complete and collate records.
COMPLETE ITC-180.1
EMPLOYEES INVOLVED IN CONSULTATION, DEVELOPMENT AND ACCEPTANCE OF THIS ITP
Name |  | Signature |  |  | LICENCE NUMBER CPR & SWITCHBOARD RESCUE CURRENT (Y/N) |  |  |  |  | Date
Y / N
Y / N
Y / N
Y / N
Y / N
Y / N
Y / N
Y / N
Y / N
Y / N
Y / N
Y / N
Y / N
Y / N
Y / N
Y / N
Y / N

## ITC-180.1 - Control Cabling
ITC-180.1 Control Cabling
Project Name: | [5 empty] | Name:
Project No: | [5 empty] | Licence No:
Client: | [5 empty] | Signature:
Drawing #: | [5 empty] | Verifier:
Location: | [5 empty] | Verifier Signature:
DB No. / Name: | [5 empty] | Date: |  |  |  |  | ITC-180.1
Origin | Destination | Cable Type | Communication Type | Purpose | Terminated |  | Point to Point Tested | Device Functional | Verifier | Sign Off |  | Date
[5 empty] | ü |  | ü | ü
Comments:
NCR No: