## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITC-180.1 Control Cabling | [5 empty] | ITC-180.1 Control Cabling
section | Details
checkpoint | Control Cabling
textbox | Origin
textbox | Destination
textbox | Cable Type
textbox | Communication Type
textbox | Purpose
bool | Terminated
bool | Point to Point Tested
bool | Device Functional
textbox | Verifier
textbox | Date
holdpoint | Sign Off
checkpoint-no-status | Comments:
textbox | NCR No:
checklist | ITP 180 Control Cabling | [5 empty] | ITP 180 Control Cabling
section | Safety Risk Assessment / SWMS / Safe work Procedures
checkpoint | Fully compliant, site specific Safety Manual and SWMS have been submitted and accepted by the Principle Contractor.
checkpoint | All Fredon electrical personnel undertaking these works have been trained and inducted in the Safety Manual and the relevant SWMS for these works.
checkpoint | All Fredon electrical personnel undertaking these works are qualified to carry out these works, and are trained, and competent in the use of all equipment and plant required to carry out these works.
section | Scope Of Works
checkpoint | Ensure that the latest revision drawings and specifications are being referred to.
checkpoint | The updated / superseded drawing register, located next to the drawing rack in the site office, has been checked to ensure the latest revision drawings are being referenced.
section | Coordination
checkpoint | Ensure that all new installations have been coordinated with other services, both new and existing
checkpoint | Ensure all control curcuits are designed to function under the necessary circumstances that they will be required to function under
section | Cable Installation
checkpoint | Ensure segregation is maintained pending cable insulation and shielding ratings
checkpoint | Ensure cables can communicate the specific protocols over the distances installed
checkpoint | Ensure the correct amount of cores have been supplied
checkpoint | COMPLETE ITC-180.1
section | Termination
checkpoint | Ensure the requirements of the system and if it requires to be normally open/ normally closed ifor the control/status that is required
checkpoint | Ensure all spares are left in an open state and labelled accordingly
checkpoint | Ensure cable/cores can be easily identified for future works and maintenaince
checkpoint | COMPLETE ITC-180.1
section | Testing
checkpoint | Low Level Inputs - Point to Point test individual cores at both the origin and the destination
checkpoint | High Level Inputs - Confirm the software can be seen on the head end system
checkpoint | COMPLETE ITC-180.1
section | Functional Testing
checkpoint | Activate functional devices and programming and confirm that the control sytem functions correctly eg. Manually Pressing Emergency Stop - turns off designated equipment
section | Record Changes to Drawings
checkpoint | Ensure that all changes made to the original drawing have been marked and noted on the Working Drawing located in the Site Office. These drawings MUST be kept updated for use as as built drawings.
section | Final Inspection
checkpoint | Cross check and verify that the as built drawings are complete and correct.
checkpoint | Verify all inspections are complete and collate records.
checkpoint | COMPLETE ITC-180.1