## Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
e87fe57e-080a-4813-9832-6a92c97e1bf4 | checklist | Add Document |  | Document Name: | c3f45c94-96e8-41a6-bd45-29404454d7f0
8f78b608-4661-4b44-89e7-798ffee19815 | checkpoint | Upload all relevant documents and press PASS.
151d73c9-8cf8-47d7-a991-c1a25a570c95 | checklist | Backfill |  | Backfill | 3ffbf215-c4f5-4ef4-ba8b-57ccef7ab87c
673ccb1a-4a13-435e-9a5b-e5980ec28a97 | checkpoint | Backfill methodology and material confirmed
82513925-941e-4d16-bf1f-32652169254d | checkpoint | Any formwork/ debris removed from area
e3f7e615-4cdc-4a9c-bbaa-2ba0ffa683c0 | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
36964e59-6bd7-469b-825b-a5d225066503 | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closed out
2cd72950-340e-413c-b56d-aeca71f8d004 | checkpoint | General photos and observations during backfill
60caf754-d871-49f4-a086-bcfe92928866 | checkpoint | Backfill completed correctly and heights checked/ correct
2fdf6deb-77a9-40e3-a514-d46db5f70391 | checkpoint | Consultant sign off and date or requested to inspect
9f1db91d-f275-4acf-a328-27f5242e2b68 | checklist | Cess Pits Install Checklist |  | Cess Pits Install Checklist | 9ac9c60f-86cc-4635-9ec6-395312a1f648
91a32715-2be8-4a96-b9b2-cf8a324750bd | checkpoint | Drawings referenced and followed
4bd4bcd3-b41c-5c10-931f-fc5f1dd38fa0 | textbox | Drawing & Revision Number
fa86c61f-4537-46c4-b6cd-d007ef1d6d10 | checkpoint | Setout & Excavation completed checked and accurate
4906f351-9328-422c-be52-19b1141d59c0 | checkpoint | Bedding depth and material correct (photo required)
0cc5cea3-c801-4881-a59e-ae49cac80137 | checkpoint | Correct pit size installed to specified Invert Level
285b8af3-33e6-4f44-b1d4-ebb3dc352179 | checkpoint | Grille cover installed and fixed at correct height
6cb7106f-49e3-4f21-a85a-4fc1f24c6f5e | checkpoint | Pit Installation reviewed and approved (photo required)
c1dfb4d0-2ad4-4bdd-b0be-3de52dad692e | checkpoint | Backfill completed & compacted as specified (Photos during backfill required)
a7217499-cc76-477a-a6e5-e2c21b2f44a9 | checkpoint | Received QA from Subcontractor
3c69c6ab-bcb1-4d19-90bc-c31989947262 | checkpoint | Consultant sign off and date or requested to inspect
a5a417a4-be18-4182-b88c-5e16470cf357 | checklist | Channel Drain Install Checklist |  | Channel Drain Install Checklist | a55b7aa4-babe-4fc2-82f6-cdb351349fcd
47587a04-72fc-43fe-b590-f316e5275b06 | checkpoint | Drawings referenced and followed
559559f9-f5cf-5bae-a185-f7c9218689fc | textbox | Drawing & Revision Number
e8413785-fb5c-45f8-832a-5129f8fe86b1 | checkpoint | Location correction
787e7aa5-0e0b-4fee-960e-d2a4500b0433 | checkpoint | Setout & Depth, fall and width
e752539c-7391-4867-bc52-75c18c165c36 | checkpoint | Pararrell, straight
52ac6625-ac1e-4ab1-91d6-962a9aabbbfb | checkpoint | Installed as per manufacturing guidelines
ce53c430-5a15-47aa-81e0-006f8d896376 | checkpoint | Cleaned out
c168e9bd-fb1d-4336-a912-7959fc891288 | checkpoint | QA received
dfd2276f-3ca6-434b-80ca-32144a6290c4 | checkpoint | Consultant sign off and date or requested to inspect
b8a595fe-4508-4afc-97a4-23c22c857b87 | checklist | Comms Pits Install Checklist |  | Comms Pits Install Checklist | d52aad87-f832-4fd7-b273-f2f598a32f93
9b30c47f-5675-4637-a5a4-20050af4e700 | checkpoint | Drawings referenced and followed
2f115660-c713-5891-9c47-0d1b22df2078 | textbox | Drawing & Revision Number
fb3858c6-cd4f-45d1-bb49-92141712cb82 | checkpoint | Setout & Excavation completed checked and accurate
34b9fac4-a7e3-4131-a9d1-d782bb09967d | checkpoint | Bedding depth and material correct (photo required)
f94b97bc-f4cc-4f5e-9b35-0985fdcda208 | checkpoint | Correct pit size installed to specified Invert Level
9d9825b0-0cb4-466c-a604-f53f3429ddfd | checkpoint | Ladders required? Y/N
5a68c932-ad33-423b-9541-5385bdde808c | checkpoint | Ducts installed / Core drilled
fa4d89f4-c0f9-4973-ba17-fd61c5365608 | checkpoint | Cover installed and fixed at correct height
546aed24-f6b1-4f01-92a0-fa37daaa2c48 | checkpoint | Pit Installation reviewed and approved (photo required)
99ce7583-fc1d-42af-a041-baf267f2c81a | checkpoint | Backfill completed & compacted as specified (Photos during backfill required)
3d00cb36-cc95-4b2c-a602-029c9eaaae0f | checkpoint | Received QA from Subcontractor
7d09fcce-1c50-4da7-9fdd-373b8a7f5aed | checkpoint | Consultant sign off and date or requested to inspect
cb25ca80-0407-4a2a-815a-d83b0b3519a3 | checklist | Concrete Pour |  | Concrete Pour | bc1087f2-d710-4c65-9294-6f4c57edf8a4
d37ac939-94b6-471a-82fa-c56bbfc787cb | section | Formwork and Embedded Items
90134705-55ff-48ba-a6d0-244e00100f84 | checkpoint | Latest drawings available, checked and referenced
09ece827-3081-529c-b7ad-f4a2ca985072 | textbox | Grid Line
a8b432fc-7382-482b-bd54-dde0172b42dd | checkpoint | Trades QA received, attached, reviewed and approved
f7959edf-7d45-427c-8aee-ba314a9af59c | checkpoint | Grids and RLs clearly marked for reference
bde36fd3-410d-46a6-9253-25cc454c1ff1 | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
01257ca2-0574-448e-aadc-46efc06b7a50 | checkpoint | Formwork sufficiently fixed and braced (incl any propping)
0f4b5d0e-704f-4bd1-8b72-59767e3b554f | checkpoint | Shear studs installed as-per shop drawings & check ring test
475e6588-7ad0-46ee-bce4-77dd5487b5c0 | checkpoint | Any rebates/ nibs / cast in items are correctly positioned, sized and appropriately fixed in place
5dfe3d0b-e5cd-40b3-a9e5-04e66770322c | checkpoint | Service penetrations formed correctly and locations checked/correct
c280d709-0c27-44c8-9a51-b311156f898c | checkpoint | All surfaces correctly prepared (e.g joints to exisiting concrete, release agent to formwork etc)
1355c1a8-6156-4d19-a2e8-8bfbbb0c83cf | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
938abe7b-db53-43a4-b3b2-b90fc1261ed6 | checkpoint | Any additional formwork photos and observations
0f7a8e14-ea23-41da-8827-dcde52e8e5a6 | checkpoint | All formwork elements completed and ready for concrete pour ( excess debris removed )
291b8399-4f82-4d73-a5d8-29778006e03c | section | Reinforcing
53ff8b55-98f3-44dd-9421-a967d2d0bedb | checkpoint | Trades QA received, attached, reviewed and approved
525d7aad-75a7-4dfb-b99e-0a083f34d9b8 | checkpoint | Size and type correct to specification
39ac2ff9-eb84-4fce-96b9-3d3fdcfe27a0 | checkpoint | Reinforcing spacing and location correct
7b38ac8a-12b6-4ad5-a681-68199d436dfe | checkpoint | Specified covers checked/correct
e691debf-b39d-4cfd-a8e3-32e17c785a3b | checkpoint | Splice laps checked/correct
879cd518-17ff-4e59-85d7-20fd8241b389 | checkpoint | Any starter bars are installed correctly (location, size and spacing )
444d846c-aa07-418f-a6b1-fc608f33512e | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
4a973e21-e29c-481b-a2d5-e3d171ae48eb | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
f4ee19f0-69df-4883-89ee-6f9c2ed14c85 | section | Pre-Pour Completion (Approval to pour)
c13dfe31-d5bd-4444-b8b0-ed0b26d362a4 | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
2d895ac2-84ee-4611-b9e4-0f1b5f648397 | checkpoint | Council inspection completed and attached
1d0ca5ec-e38f-4ab9-95b0-e1c7a5ba6d4a | checkpoint | All relevant inspections completed and attached
06902805-25f7-4c48-9336-34e0985b0061 | checkpoint | Main contractor inspection completed - Approval given to pour concrete
d58a7087-f9d2-43ab-aff1-840f4e636bfc | checkpoint | Heights and falls checked/confirmed before placement
55f43369-b5fe-5d3b-96f7-c0d1488819ef | button | Is the cover correct to specification | YES, NO, N/A
452cbd25-8cd7-4013-a9da-73c12cbd19d9 | checkpoint | General photos and observations of concrete placement attached
ba5f0042-4f38-4ec7-b344-c6a5a3523c0e | section | Pour / Post-Pour Checks/Sign Off
682fada4-3ef2-4fb4-9972-a1fd1c314eb0 | checkpoint | Concrete checked on arrival & correct (slump, MPa etc)
93d37fbb-a6ca-4c10-b14e-ce37971b1684 | checkpoint | Heights and falls checked/ confirmed after placement
6f2ca93b-1fdd-4b90-9b9f-d4a3525bef3e | checkpoint | Any curing compound applied correctly
d512271d-7975-4790-b16d-c3861f6b967a | checkpoint | Concrete surface to specifications
be878130-e8c5-44df-9e34-a2234eae5708 | checkpoint | Area left clean and tidy
cef77fff-94ce-4df2-98a1-06a615a5d7ef | checkpoint | Any remedial work completed
680e7e57-4dc9-4147-8393-b89d3c72de8e | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
cdb2d0c7-a80a-457f-8a0b-83404525d7c0 | checkpoint | Consultant sign off and date or requested to inspect
375e6e52-71da-44ab-8cfb-1bfd9483aa32 | checklist | Detailed Excavation Checklist |  | Detailed Excavation Checklist | cf11d463-500b-44b4-902b-8ff933f0a4f3
98af7d7f-947e-4ef3-9196-2ba14afe5368 | checkpoint | Location accurate
773b4161-fef7-4e9b-b0ae-90f1335b0a28 | checkpoint | Depth correct (allow for site concrete if required)
563c74cd-8b61-4318-81eb-346d4074bb1c | checkpoint | Width correct (allow for boxing if required)
7efafb5a-1f64-45d4-be87-386bc740a968 | checkpoint | Any relevant excavation for services is completed and accurate
91974690-4c20-4086-a1ff-6f57b89e2d36 | checkpoint | Excess Material Cleaned up and removed as required
dd1957ff-a7f2-409d-9adc-33a3d1acec98 | checkpoint | Roadprep completed, reviewed and approved
627332e4-d8da-4f8d-b2e4-79cc6d4edca2 | checkpoint | Consultant sign off and date or requested to inspect
507edf7e-cdb1-4598-9029-269d8fa39382 | checklist | Kerbs Install Checklist |  | Kerbs Install Checklist | fa9b3a28-3fea-44ab-8b83-c0131c365a3d
6b6086b7-3d41-470b-a63e-6b234293085c | checkpoint | Drawings referenced and followed
a59074af-4b37-53ee-a06c-03b456c28856 | textbox | Drawing & Revision Number
092f1678-343f-4a0f-87cb-853de71ecbac | checkpoint | Setout & level completed checked and accurate
b063bbcb-8d7c-4f0d-9d6e-d2ac7a71f80c | checkpoint | Bedding depth and material correct (photo required)
2601857c-68de-4d63-9d7e-011e90663581 | checkpoint | Haunching - concrete delivery note and photos
a5ade5fa-cb22-418d-9b51-e2c193ea170f | checkpoint | Kerbs and drop kerbs laid
3f7523c2-07ea-4754-be57-287c4f40caf5 | checkpoint | Kerbs accepted - no chips, level, in correct location
3975d990-48b1-40c0-afb5-b0efc5cda8f3 | checkpoint | Received QA from Subcontractor
8f9fc038-8eac-4472-8d9d-3fab8c6c84de | checkpoint | Consultant sign off and date or requested to inspect
cd5fb026-10fc-45cd-8bc9-9168742d9ec9 | checklist | Light Pole Foundations |  | Light Pole Foundations | b72a7401-9995-4e86-b821-545e3d77b39e
0d0a4b77-adbd-46b9-94b8-3b394c611aa5 | checkpoint | Trades QA received, attached, reviewed and approved
1c47c34c-f1a1-41b2-b5a5-7cb73af59a56 | checkpoint | Size and type correct to specification
6f67486b-b982-4ff1-a32e-c76c26473199 | checkpoint | Reinforcing spacing and location correct
cca3dc58-2a58-4046-9606-3a3fe42d716e | checkpoint | Specified covers checked/correct
ab30681c-b843-4738-ac8d-81fa3d6ac47b | checkpoint | Splice laps checked/correct
2501b8f9-adea-4b68-8f17-3cf91a798a7d | checkpoint | Any starter bars are installed correctly (location, size and spacing )
437e2c91-4fe4-434f-b345-994075c881c9 | checkpoint | Conduit installed for cable and draw wire
18a58a05-d22a-495a-9235-0c68d84d6d2c | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
6dc817f3-6fe0-402a-9d91-10fbc4938bdf | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
00e0fd0b-af80-45cf-8126-82b38cc60b8d | checkpoint | Received QA from Subcontractor
68b8b9cd-0f9a-4474-b693-fa2c59812554 | checkpoint | Consultant sign off and date or requested to inspect
b982ab2b-312e-4ba9-beac-18145c7c25a3 | checklist | Manhole Install Checklist |  | Manhole Install Checklist | 4a49fb16-034b-4c5c-8440-59c6cb67a26d
cb00494d-68c9-4936-9c8f-f819e19dfa6f | checkpoint-no-value | Manhole Number
550b49a3-2121-4763-b157-5b7f244737a2 | textbox | Manhole Number:
cfe7ce99-8dd9-4129-b8c5-5700b8a64539 | checkpoint | Drawings referenced and followed
422f06ea-00ea-51c1-a13c-6b9d69976e16 | textbox | Drawing & Revision Number
9d68d9ff-2e5c-45b7-9af4-ee552130fc1c | checkpoint | Setout & Excavation completed checked and accurate
a74331b4-3de5-466b-aef6-0aa0388ca1bc | checkpoint | Correct manhole size installed to specified Invert Level
74788682-3810-4e91-9366-8db3eca220d5 | checkpoint | Manhole risers & steps installed and joints sealed as specified (photo required)
900445ad-88ad-4c16-a33a-0a9314038deb | checkpoint | Manhole benching completed and acceptable (photo required)
cc13c907-ccd8-48ef-b35d-e291bb5c57e4 | checkpoint | Concrete manhole cover installed and sitting correctly with hole covered if required (photo required)
e00b1ad8-729f-42fb-8845-0cbfe3b191f8 | checkpoint | Cast Iron Lid installed and fixed at correct height (photo required)
04943de3-1337-4d3d-95d6-19857a4d4d04 | checkpoint | Manhole Installation reviewed and approved (photo required)
f88ce45f-08be-4c10-8598-eb14eaeb44c9 | checkpoint | Backfill completed & compacted as specified (Photos during backfill required)
bd870829-036c-42dd-a835-79770560e520 | checkpoint | Received QA from Subcontractor
a380eb34-676b-433e-9b28-b85a2a995fa4 | checkpoint | Consultant sign off and date or requested to inspect
01e8d9fe-d8fb-4540-9077-772b1d7af5a9 | checklist | Oil Interceptor Install Checklist |  | Oil Interceptor Install Checklist | 515b35e3-a763-4b11-b96b-26a84d6f90e7
9737fd75-e563-48f4-86b0-8991dcfdec68 | checkpoint | Drawings referenced and followed
0cdbb1b7-1921-5cf8-bbd2-8704c5ed56c7 | textbox | Drawing & Revision Number
37946a35-9037-45eb-b6ae-d3606bb869f0 | checkpoint | Technical Submission completed
108725d7-f6d2-49b2-93e5-a35902d6411d | checkpoint | Setout & Excavation completed checked and accurate
9613253d-200b-4884-a910-9c7ed62bc3c6 | checkpoint | Bedding depth and material correct (photo required)
ca8e4875-675f-44ff-b06a-657f601f7ca8 | checkpoint | Correct pit size installed to specified Invert Level
3f479f3f-2b80-49e8-b7c6-6f6ed6e76baa | checkpoint | PVC connector installed
6ff49ab1-1408-408c-955e-fecc1fe152be | checkpoint | Eartenware pipe outlet connectected
9c4c7cd9-dfe7-4da4-b142-1f69ba54c0be | checkpoint | Lid cover installed and fixed at correct height
95543289-457b-47f2-b4cf-343cad1d6005 | checkpoint | Pit Installation reviewed and approved (photo required)
b60b3b25-0322-4b7c-a75c-79f9d62c43f5 | checkpoint | Backfill completed & compacted as specified (Photos during backfill required)
a3a91b75-8865-4fac-9927-e3c2ce6dfecd | checkpoint | Received QA from Subcontractor
cd92ebeb-7f2e-4014-9491-742119c5973c | checkpoint | Consultant sign off and date or requested to inspect
3824ecd3-27d0-4b2b-8266-77268b3df548 | checklist | Pavement Checklist |  | Pavement Checklist | 924330d0-206e-4799-bebf-34d65cdef35a
3990b5d5-e578-4fbb-af13-7918aa9e89d2 | checkpoint | Drawings referenced and followed
43e36119-bec9-57ce-95e9-f6739596e2f1 | textbox | Drawing & Revision Number
63d610a2-750e-4259-a4cd-35179a07e150 | checkpoint | Design Mix Agreed
7efc771f-2781-4225-8e26-8039e7bed34d | checkpoint | Weed spraying completed and substance agreed with engineer
19bd72a4-e6b2-423e-a9df-cf61f4096a1d | checkpoint | Membrane seal or tack coat agreed prior
e4c92a86-b40a-488d-a7c6-ea4260f5aec5 | checkpoint | No ponding level +/- 5mm
100e6be7-17f5-4ca5-a98a-b8374cf0865c | checkpoint | Received QA from Subcontractor
44ca8126-a103-49b4-beae-2d4cafebeeed | checkpoint | Consultant sign off and date or requested to inspect
0423046d-f203-48c3-afb8-e5a1fe1f8fdb | checklist | Retaining Wall Checklist |  | Retaining Wall Checklist | 00e168cf-84f4-4173-8122-ffe94a6342ab
f1824724-f1cc-4725-9336-75370657f70e | checkpoint | Ground test results
38f02cb3-6ec4-4a68-851a-b234711fc81d | checkpoint | Formwork construction checked
77b1542e-dade-460d-97fa-3a6a3ddb459d | checkpoint | Blinding Concrete, DPC Membrane
86340b22-9811-4e22-9211-c7e89881c948 | checkpoint | Formwork
e23d33f7-b93e-5ad5-92a3-5d2d5c27ce9a | button | Design checked | YES, NO, N/A
26aa6874-148d-5bc8-ad7a-2e3594f7249d | button | Position correct | YES, NO, N/A
0112f0c8-348a-5512-9e3c-bbb296b42599 | button | Dimensions | YES, NO, N/A
ea1eea6b-8bf2-5d82-a982-5a182b02a1ac | button | Alignment | YES, NO, N/A
d8c35922-36b9-5a05-a20a-c1a4f3b4fe7b | button | Plumb | YES, NO, N/A
213d7d75-9799-5d4e-8bdf-1065da206c14 | button | Cambers built in | YES, NO, N/A
bacdb935-edab-53a5-bc97-a86323f6c779 | button | Oiled | YES, NO, N/A
0a50e237-4356-5ecd-b377-35eac6951dbb | button | Chamfers | YES, NO, N/A
5a61f004-8ba2-5a8e-859e-1c6853d05627 | button | Bracing | YES, NO, N/A
5a6b4435-56d2-5845-af70-fbf8ec298af1 | button | Meets specified finish | YES, NO, N/A
fdaac296-a82f-51be-ba9f-b63337230c52 | button | She bolts at correct spacing | YES, NO, N/A
db392050-4d4f-5a2f-9349-48e45f771f35 | button | Ties to correct cover | YES, NO, N/A
14153abc-6340-5726-9804-2c5d04860343 | button | Pour ports | YES, NO, N/A
bc15fba6-cfd5-547d-8042-17c6618eacdf | button | Wash outs | YES, NO, N/A
3be1cd33-b391-56ac-a42f-8c9d2f59c85d | button | Finish levels checked | YES, NO, N/A
55dfdf45-3f91-581c-a77e-b1607e6a84d2 | button | Finish levels marked | YES, NO, N/A
b2bef04c-59eb-5261-9eb7-f72f741a19ad | button | No grout leak points | YES, NO, N/A
497c510a-4889-48ed-b135-b9d5b2b986ae | checkpoint | Penetrations / Sleeves
40d4fe75-4237-5006-a450-a3130476f4f5 | button | Construction / Expansion Joints | YES, NO, N/A
6139c1e2-6eeb-5a18-abe5-6b5d6497b8d2 | button | Location | YES, NO, N/A
ccab40a0-95e6-54a8-bbc5-600ce7924c26 | button | Stability | YES, NO, N/A
cb8094be-383e-5f02-a187-86ebac96ea36 | button | Keyways | YES, NO, N/A
f95bd921-d0dd-573f-b084-db62169ebba6 | button | Water bar | YES, NO, N/A
33dc60e0-ff9a-56ff-a6db-a5dfeebf7971 | button | Release agent | YES, NO, N/A
25cefbf6-302a-4c08-a94d-34533e07f861 | checkpoint | Anchor Bolts
8c6e3060-0911-595a-b840-b6ea8b0cb262 | button | Position | YES, NO, N/A
12e9c128-cf29-5489-888b-b3b4fcd93ef0 | button | Number | YES, NO, N/A
21b3d253-0138-52d2-a53e-75d746cc070b | button | Fixing | YES, NO, N/A
b2111886-c092-536f-ad17-b7a62bdf31fb | button | Projection thread | YES, NO, N/A
08d707c9-12af-5e54-83e6-6554fa4be3a8 | button | Protection | YES, NO, N/A
6d68b7f8-a9d9-4d51-a205-b0b1590a28eb | checkpoint | Embedded Items
c01954b2-fa24-5999-b7a3-25e47955b235 | button | Position | YES, NO, N/A
127e48f7-2297-593f-bfe3-dc9e53bcf3be | button | Fixing | YES, NO, N/A
9c6139bf-7d89-5a56-a1ec-9c9d2026c424 | button | Blockouts | YES, NO, N/A
01e46f1f-23a9-5664-af35-29bdbb7f021c | button | Ducts | YES, NO, N/A
b7fc88c9-bf17-4992-a2e4-2005c3a331de | checkpoint | Reo
5bf02cc0-ca96-5002-adde-8bdddcedad4e | button | Size | YES, NO, N/A
e869f533-544b-5fa0-b1bb-8ad792694c8c | button | Spacing | YES, NO, N/A
55d22449-ed87-5ab2-853e-bc14d102a175 | button | Cover | YES, NO, N/A
d847bba2-bf74-4c6a-8ee7-13808735b911 | checkpoint | Concrete
002f99ea-72b6-5478-ace1-60a0f0bc52b6 | button | Correct MPA | YES, NO, N/A
28ad8c80-f609-5db1-b7a9-9662004aa81d | button | Vibrated | YES, NO, N/A
aa498627-ba09-4ebb-b1ce-3ab3debb294a | checkpoint | Formwork Removal
824dcd93-7d91-5017-9690-0502a8c2d3d8 | button | Reo covered | YES, NO, N/A
17100b69-af45-5e48-95eb-2f03712f171f | button | Finish acceptable | YES, NO, N/A
a0844bd7-a474-4f64-bd29-718e05846e03 | checkpoint | Test Results
d39d5a17-66e7-487e-8a9a-fadffc62c8e5 | checkpoint | Received QA from Subcontractor
599a6c18-0833-40bd-b311-d93f6b1f72c5 | checkpoint | Consultant sign off and date or requested to inspect
62b36599-3d2a-4bc3-8b77-4a6e13cb1085 | checklist | Road Checklist |  | Road Checklist | e5d735dd-07e1-49f5-b6ac-fec6ae728593
da818302-c7ce-46d4-983b-28735dff1150 | checkpoint | Location accurate
dd364c64-5654-44a8-85e4-cd21d1ec84c9 | checkpoint | Materials certificate received
1fd54352-ed8b-46a2-9035-1812ea5dcd46 | checkpoint | Proof rolling photo attach
5fda2f5b-04c9-4eda-91e4-d0088dfe89fe | checkpoint | Scala Penetrometer photo attach and results
8bdb4f63-43a8-4ce6-870a-52cab807f289 | checkpoint | Shear vane testing - received results
3f3c7b78-cb2c-4a72-81e8-c8d5a5423022 | checkpoint | Excavation and trim to the subgrade level
c1e7c8fa-5c1d-4f94-b43e-966140be4a6d | checkpoint | Subgrade surface levels checked -35/+10mm
e11d59d9-c1db-43f0-89b8-c105798c3a51 | checkpoint | Subgrade Density Test results received
67d3313f-3efd-46a2-8bab-b40b3d39f92c | checkpoint | Sub base surface levels checked -/+10mm
7c3b7100-d660-41b3-a86b-3260965054a0 | checkpoint | Base course Density Test results received
9909b5e3-3cc5-479b-99c2-b9722e418a2b | checkpoint | Basecourse surface levels checked -/+10mm
113ee752-eb7d-4452-b3d9-16bb1590ff7f | checkpoint | Basecourse surface levels checked -/+10mm - hard edge or -129/+25mm if shoulder
2ae90def-d8c6-4b6c-83cf-6cc60ca8bbc7 | checkpoint | Detailed excavation completed, reviewed and approved
53c69d08-5f91-4571-878b-16c06b989bac | checkpoint | Relevant tests, photos & as-built information provided
8c134d5a-551f-4a0e-a5fb-507fdd337e67 | checkpoint | Received QA from Subcontractor
c21da70f-96a6-4329-a40d-9802e3049aa1 | checkpoint | Consultant sign off and date or requested to inspect
f67c0869-5d67-4fef-8ffb-3f1b11a533f2 | checklist | Services Checklist |  | Services Checklist | 04f4fdc2-3fd5-4eb0-8b9e-a40895216f8f
aca05be9-ff68-4233-9b00-6a7a2fc03b6e | section | Water mains
479b75bc-91f6-48f4-ae10-58cdee14038d | checkpoint | All fittings scrapped correctly
38cd5cf5-ff8d-4c4f-b5fd-51d7c49ec1d1 | checkpoint | Iso used on fittings
dee272c1-cac6-44f6-a068-d2760314cd22 | checkpoint | Valves fitted correctly
4c0a8c73-7bed-45c4-884d-419f7c23d2bb | checkpoint | Fittings welded & weld indicator has popped out
44ad08bd-be90-4d23-9655-c29544c631f3 | checkpoint | Trace wire and ID tape installed
9e251844-35cb-462a-a224-994e50ad296c | section | Gas main
0d924c5c-9d08-4810-a18e-c4f4d47efb6e | checkpoint | All fittings scrapped correctly
76c12993-9c70-49f8-b186-18dadc7c5658 | checkpoint | Iso used on fittings
eabf28bb-2b8e-4e4f-ad6a-fbc25cacb273 | checkpoint | Valves fitted correctly
8a68cbac-1dd8-4fc2-8e13-0df9c728aed9 | checkpoint | Fittings welded & weld indicator has popped out
29e1b6b9-08e9-4b46-b426-0de08fc62840 | checkpoint | Trace wire and ID tape installed
70f8d967-cc2a-44c4-b790-36648155b1ea | section | General
6c6506e5-803b-4130-bfd2-6509b7eb41ae | checkpoint | All open ends capped
afe317c4-acd5-4fb7-ae15-3fb70c0a5182 | checkpoint | Pipework bedded correctly
fde7721b-53b3-4581-b46c-89a8c4dbcba0 | checkpoint | Tidy work areas
b57ba346-ad17-4b82-bb2e-c9fc208e0ca3 | checkpoint | Pressure test pipework
d2ca47e2-a183-47c1-993c-98d95ae4e620 | checkpoint | Visual check (for leeks from valves, tees, saddles, etc)
789b339d-ecd5-4505-85e3-f202b35ec16a | checkpoint | Backfill around pipework with fines
413728e0-798d-42b8-aab3-fdbd02639ac8 | checkpoint | as-built completed and photo
99490b2f-3f3f-44b5-afe3-e08a1aa39fa7 | checkpoint | Installers name & date works completed
741b3487-7621-517d-8e94-1702c221a34a | textbox | Installers name
8e075b66-f8e1-5a98-889b-1c0d2f2588ee | textbox | Date:
bd6df194-83e5-4631-afcc-22846bca2c20 | checkpoint | Tested by & date
44fecb97-0579-5bd2-9e28-431ae2e8e871 | textbox | Tested by:
e23d1ba7-f38e-53df-a677-c175087b2ede | textbox | Date tested:
9a4f63c2-772a-4989-a4ba-084bff76700b | checkpoint | Council inspector sign off and date
f84bc062-085d-4921-b786-224c860049b7 | checkpoint | Consultant sign off and date or requested to inspect
a4268f80-5346-45fa-8734-6b863df48a4e | checklist | Stormwater (Main Line) - Pipeline Installation Checklist |  | Stormwater (Main Line) - Pipeline Installation Checklist | 355acd02-ebed-413f-bfeb-f7cd062ae841
0d296f86-8d3a-42bb-b162-4da354cb2f45 | checkpoint | Drawings referenced and followed
66736d8d-9e37-5047-8ce8-92c39b5abb2e | textbox | Drawing & Revision Number
61620c41-68eb-4368-af37-21b1cec0eccf | checkpoint | Setout & Excavation completed checked and accurate
0bdc71de-74c5-4cec-b980-ad6f6cacb6b3 | checkpoint | Ground conditions checked & acceptable
fa3cb52c-1d88-4776-9fa2-ad7271cb35af | checkpoint | Bedding depth and material correct (photo required)
56882a43-ad75-4611-87f4-f46ab5e69574 | checkpoint | Correct pipe (size, material & class) laid to specified level, grade and jointed as specified
14772717-8d16-5d94-8e60-2387ae3f684c | textbox | Invert Level (upstream manhole)
913402e4-90e7-5497-8f4b-526dd33840ee | textbox | Invert Level (downstream manhole)
413a3b41-8b68-5e89-9af7-c547e6645214 | textbox | Length of pipe installed (m)
ea69e33a-2362-5545-9fe3-54eba143f243 | textbox | Grade of Pipe-Line %
e8f42042-39d9-4d35-81ab-5ede3c88ca8d | checkpoint | Connections to manholes complete and approved (photo required)
4cbfc8b7-2312-467f-9ae6-9b738499e6a7 | checkpoint | Backfill completed & compacted as specified (Photos during backfill required)
8f8c8a29-74ae-48b5-8ff7-f6f9117f83c0 | checkpoint | Relevant tests, photos & as-built information provided
80f29924-3cab-433e-b035-1ea0b6c7d5ed | checkpoint | Consultant sign off and date or requested to inspect
42dc505a-6a2c-4dbe-84d5-8b51fb04bf6a | checklist | Waste Water (Main Line) - Pipeline Installation Checklist |  | Waste Water (Main Line) - Pipeline Installation Checklist | 2763a264-a943-498f-9920-af41f18215a7
d19cdd17-131c-4898-82fa-36381e19f9f1 | checkpoint | Drawings referenced and followed
7c8e4792-1732-586b-84d1-97782689bbcf | textbox | Drawing & Revision Number
525f0416-7c2b-4037-a09a-25287055845b | checkpoint | Setout & Excavation completed checked and accurate
0f39106c-5bb4-476d-9c77-d7aadfda83a2 | checkpoint | Ground Conditions Checked & Acceptable
c77fa321-6534-431e-8eff-024044f4ee4b | checkpoint | Bedding depth and material correct (photo required)
1cfb2442-72a8-4b97-b0a0-a309571a9078 | checkpoint | Correct pipe (size, material & class) laid to specified level, grade and jointed as specified
c7997df3-b48a-5af9-b755-10a6e7f047e0 | textbox | Invert Level (upstream manhole)
061532f0-e759-50b5-98d2-7f53e36ec6ee | textbox | Invert Level (downstream manhole)
5e60f662-4aa3-589f-96e3-abbea3a0ad5f | textbox | Length of pipe installed (m)
de704be7-92e4-59c9-8d0f-74b4b0d9f117 | textbox | Grade of Pipe-Line %
23e895e0-e880-496b-ae16-6aa700c56e0b | checkpoint | Connections to manholes complete and approved (photo required)
687588f2-5d20-4506-a7cd-6bac65ddb705 | checkpoint | Air/water test completed - Low Pressure Air Test
d40650c5-4553-4092-9960-22a48dccf528 | checkpoint | Backfill completed & compacted as specified
1d523005-e48e-497a-b465-a861b9c25557 | checkpoint | Relevant tests, photos & as-built information attached
cdf329a8-3d09-4018-b947-622b247b3df3 | checkpoint | CCTV
e7be6d34-b5bd-4c47-a969-a1e6c8f2246c | checkpoint | Consultant sign off and date or requested to inspect
45cd6597-9467-4138-922f-922a6209c15f | checklist | Watermain - Pipeline Installation Checklist |  | Watermain - Pipeline Installation Checklist | dcfc9006-d3ef-4bbf-a592-7999908cb33d
688ae8f4-0eca-4899-bb6a-477b7751b232 | checkpoint | Drawings referenced and followed
85a209c0-00ff-5e7d-ab64-55016e43cf16 | textbox | Drawing & Revision Number
6e33ed52-8339-4b56-bc6e-3c5e5736d0e0 | checkpoint | Setout & Excavation completed checked and accurate
1b5c04b1-97b5-4db2-9c22-5d7f2efa8533 | checkpoint | Ground Conditions Checked & Acceptable
c2d4c474-1193-4214-bb7b-f0417251a13d | checkpoint | Bedding depth and material correct (photo required)
8a64bed8-500e-4b8d-87cc-244dadf77124 | checkpoint | Correct pipe (size, material & class) laid to specified level, grade and jointed as specified
63168325-5a24-5163-87f0-a9136b57d984 | textbox | Length of pipe installed (m)
09c2adcf-e193-4607-96cc-7479a8f9ea85 | checkpoint | Connections complete and approved (photo required)
c6deb982-2d7e-4540-a75f-a0a3470a6379 | checkpoint | Hydrostatic Pressure Testing
41dbde01-4492-4da1-a02a-531b1678161a | checkpoint | Pipe Marking
621226b4-feee-4812-9b8e-9a326e1ea56f | checkpoint | Flushing & Disinfection
b9cd8372-3218-4f25-9ac8-75267a544143 | checkpoint | Backfill completed & compacted as specified
3b58d8cb-a452-4a4c-ab55-d2fa436fd114 | checkpoint | Relevant tests, photos & as-built information attached
429f2342-de75-49fd-97ca-e1830f525af9 | checkpoint | Consultant sign off and date or requested to inspect
b69ac2db-2415-48a9-9502-d466d37819a9 | checklist | Waterproofing Checklist |  | Waterproofing Checklist | ec3d3e02-20de-472f-b333-9e71916becb4
06e870aa-b9d2-4821-a695-c8733d67cd4e | checkpoint | Trades QA received, attached, reviewed and approved
a1db6240-2810-4728-8f98-5c76f9de6bd4 | checkpoint | Preparation / Substrate acceptable
ca2073a5-396b-4cb1-b137-510cd46477ca | checkpoint | Correct product delivered and checked - approval given to install
1929c080-db77-4b7a-9025-3b522665b619 | checkpoint | General photos/comments during install
eb6eebfd-6404-4745-af19-f6dd79c9e21e | checkpoint | Any inspections / observations documented, reviewed and closed out
31fe9afb-c4ce-48d2-ba26-e31ddc711b2c | checkpoint | Waterproofing install completed, reviewed and approved to meet required specifications
f85fd7dd-1b93-4cbe-ba42-78ff1d00e7c5 | checkpoint | Received QA from Subcontractor
0d246020-b804-43aa-a649-3e233f1ef45f | checkpoint | Consultant sign off and date or requested to inspect