## Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Checklist Required
Site QA
Tier 2: Retaining Wall; Tier 3: Type 1; Tier 4: Retaining Wall | Retaining Wall Checklist
Tier 3: Type 2; Tier 4: Retaining Wall | Retaining Wall Checklist
Tier 3: VIE; Tier 4: Retaining Wall | Retaining Wall Checklist
Tier 3: Energy Centre; Tier 4: Retaining Wall | Retaining Wall Checklist
Civils
Tier 3: VIE & Energy Centre; Tier 4: Cess Pits | Cess Pits Install Checklist
Tier 4: Channel Drain | Channel Drain Install Checklist
Tier 4: Oil Interceptor | Oil Interceptor Install Checklist
Tier 4: Excavation Checklist | Detailed Excavation Checklist
Tier 4: Services Checklist | Services Checklist
Tier 4: Cess Pit Checklist | Cess Pits Install Checklist
Tier 4: Road Checklist | Road Checklist
Tier 4: Pavement Checklist | Pavement Checklist
Tier 4: Kerbs Checklist | Kerbs Install Checklist
Tier 4: Excavation | Detailed Excavation Checklist
Tier 4: Service Installation | Services Checklist
Tier 4: Waterproofing Checklist | Waterproofing Checklist
Tier 4: Concrete Pour | Concrete Pour
Tier 3: Stage 1; Tier 4: Excavation | Detailed Excavation Checklist
Tier 4: Services | Services Checklist
Tier 4: Manhole | Manhole Install Checklist
Tier 4: Cess pits | Cess Pits Install Checklist
Tier 4: Comms and power pits | Comms Pits Install Checklist
Tier 4: Road | Road Checklist
Tier 4: Pavement | Pavement Checklist
Tier 4: Kerbs | Kerbs Install Checklist
Tier 4: Light poles | Light Pole Foundations
Tier 4: Asphalt | Pavement Checklist
Tier 4: Line marking | Pavement Checklist
Stage 2
Tier 4: Excavation | Detailed Excavation Checklist
Tier 4: Services | Services Checklist
Tier 4: Manhole | Manhole Install Checklist
Tier 4: Cess pits | Cess Pits Install Checklist
Tier 4: Comms and power pits | Comms Pits Install Checklist
Tier 4: Road | Road Checklist
Tier 4: Pavement | Pavement Checklist
Tier 4: Kerbs | Kerbs Install Checklist
Tier 4: Light poles | Light Pole Foundations
Tier 4: Asphalt | Pavement Checklist
Tier 4: Line marking | Pavement Checklist
Stage 3
Tier 4: Excavation | Detailed Excavation Checklist
Tier 4: Services | Services Checklist
Tier 4: Manhole | Manhole Install Checklist
Tier 4: Cess pits | Cess Pits Install Checklist
Tier 4: Comms and power pits | Comms Pits Install Checklist
Tier 4: Road | Road Checklist
Tier 4: Pavement | Pavement Checklist
Tier 4: Kerbs | Kerbs Install Checklist
Tier 4: Light poles | Light Pole Foundations
Tier 4: Asphalt | Pavement Checklist
Tier 4: Line marking | Pavement Checklist
Stage 4
Tier 4: Excavation | Detailed Excavation Checklist
Tier 4: Services | Services Checklist
Tier 4: Manhole | Manhole Install Checklist
Tier 4: Cess pits | Cess Pits Install Checklist
Tier 4: Comms and power pits | Comms Pits Install Checklist
Tier 4: Road | Road Checklist
Tier 4: Pavement | Pavement Checklist
Tier 4: Kerbs | Kerbs Install Checklist
Tier 4: Light poles | Light Pole Foundations
Tier 4: Asphalt | Pavement Checklist
Tier 4: Line marking | Pavement Checklist
Tier 2: Boardwalk; Tier 4: Pond Boardwalk | Pond Boardwalk
Tier 4: Swale Boardwalk | Swale Boardwalk

## Checklists
checklist-flat | Add Document
checkpoint | Upload all relevant documents and press PASS.
checklist-flat | Detailed Excavation Checklist
checkpoint | Location accurate
checkpoint | Depth correct (allow for site concrete if required)
checkpoint | Width correct (allow for boxing if required)
checkpoint | Any relevant excavation for services is completed and accurate
checkpoint | Excess Material Cleaned up and removed as required
checkpoint | Roadprep completed, reviewed and approved
checkpoint | Consultant sign off and date or requested to inspect
checklist-flat | Road Checklist
checkpoint | Location accurate
checkpoint | Materials certificate received
checkpoint | Proof rolling photo attach
checkpoint | Scala Penetrometer photo attach and results
checkpoint | Shear vane testing - received results
checkpoint | Excavation and trim to the subgrade level
checkpoint | Subgrade surface levels checked -35/+10mm
checkpoint | Subgrade Density Test results received
checkpoint | Sub base surface levels checked -/+10mm
checkpoint | Base course Density Test results received
checkpoint | Basecourse surface levels checked -/+10mm
checkpoint | Basecourse surface levels checked -/+10mm - hard edge or -129/+25mm if shoulder
checkpoint | Detailed excavation completed, reviewed and approved
checkpoint | Relevant tests, photos & as-built information provided
checkpoint | Received QA from Subcontractor
checkpoint | Consultant sign off and date or requested to inspect
checklist-flat | Stormwater (Main Line) - Pipeline Installation Checklist
checkpoint | Drawings referenced and followed
text | Drawing & Revision Number
checkpoint | Setout & Excavation completed checked and accurate
checkpoint | Ground conditions checked & acceptable
checkpoint | Bedding depth and material correct (photo required)
checkpoint | Correct pipe (size, material & class) laid to specified level, grade and jointed as specified
text | Invert Level (upstream manhole)
text | Invert Level (downstream manhole)
text | Length of pipe installed (m)
text | Grade of Pipe-Line %
checkpoint | Connections to manholes complete and approved (photo required)
checkpoint | Backfill completed & compacted as specified (Photos during backfill required)
checkpoint | Relevant tests, photos & as-built information provided
checkpoint | Consultant sign off and date or requested to inspect
checklist-flat | Waste Water (Main Line) - Pipeline Installation Checklist
checkpoint | Drawings referenced and followed
text | Drawing & Revision Number
checkpoint | Setout & Excavation completed checked and accurate
checkpoint | Ground Conditions Checked & Acceptable
checkpoint | Bedding depth and material correct (photo required)
checkpoint | Correct pipe (size, material & class) laid to specified level, grade and jointed as specified
text | Invert Level (upstream manhole)
text | Invert Level (downstream manhole)
text | Length of pipe installed (m)
text | Grade of Pipe-Line %
checkpoint | Connections to manholes complete and approved (photo required)
checkpoint | Air/water test completed - Low Pressure Air Test
checkpoint | Backfill completed & compacted as specified
checkpoint | Relevant tests, photos & as-built information attached
checkpoint | CCTV
checkpoint | Consultant sign off and date or requested to inspect
checklist-flat | Watermain - Pipeline Installation Checklist
checkpoint | Drawings referenced and followed
text | Drawing & Revision Number
checkpoint | Setout & Excavation completed checked and accurate
checkpoint | Ground Conditions Checked & Acceptable
checkpoint | Bedding depth and material correct (photo required)
checkpoint | Correct pipe (size, material & class) laid to specified level, grade and jointed as specified
text | Length of pipe installed (m)
checkpoint | Connections complete and approved (photo required)
checkpoint | Hydrostatic Pressure Testing
checkpoint | Pipe Marking
checkpoint | Flushing & Disinfection
checkpoint | Backfill completed & compacted as specified
checkpoint | Relevant tests, photos & as-built information attached
checkpoint | Consultant sign off and date or requested to inspect
checklist | Services Checklist
section | Water mains
checkpoint | All fittings scrapped correctly
checkpoint | Iso used on fittings
checkpoint | Valves fitted correctly
checkpoint | Fittings welded & weld indicator has popped out
checkpoint | Trace wire and ID tape installed
section | Gas main
checkpoint | All fittings scrapped correctly
checkpoint | Iso used on fittings
checkpoint | Valves fitted correctly
checkpoint | Fittings welded & weld indicator has popped out
checkpoint | Trace wire and ID tape installed
section | General
checkpoint | All open ends capped
checkpoint | Pipework bedded correctly
checkpoint | Tidy work areas
checkpoint | Pressure test pipework
checkpoint | Visual check (for leeks from valves, tees, saddles, etc)
checkpoint | Backfill around pipework with fines
checkpoint | as-built completed and photo
checkpoint | Installers name & date works completed
text | Installers name
text | Date:
checkpoint | Tested by & date
text | Tested by:
text | Date tested:
checkpoint | Council inspector sign off and date
checkpoint | Consultant sign off and date or requested to inspect
checklist-flat | Manhole Install Checklist
text | Manhole Number
checkpoint | Drawings referenced and followed
text | Drawing & Revision Number
checkpoint | Setout & Excavation completed checked and accurate
checkpoint | Correct manhole size installed to specified Invert Level
checkpoint | Manhole risers & steps installed and joints sealed as specified (photo required)
checkpoint | Manhole benching completed and acceptable (photo required)
checkpoint | Concrete manhole cover installed and sitting correctly with hole covered if required (photo required)
checkpoint | Cast Iron Lid installed and fixed at correct height (photo required)
checkpoint | Manhole Installation reviewed and approved (photo required)
checkpoint | Backfill completed & compacted as specified (Photos during backfill required)
checkpoint | Received QA from Subcontractor
checkpoint | Consultant sign off and date or requested to inspect
checklist-flat | Channel Drain Install Checklist
checkpoint | Drawings referenced and followed
text | Drawing & Revision Number
checkpoint | Location correction
checkpoint | Setout & Depth, fall and width
checkpoint | Pararrell, straight
checkpoint | Installed as per manufacturing guidelines
checkpoint | Cleaned out
checkpoint | QA received
checkpoint | Consultant sign off and date or requested to inspect
checklist-flat | Backfill
checkpoint | Backfill methodology and material confirmed
checkpoint | Any formwork/ debris removed from area
checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closed out
checkpoint | General photos and observations during backfill
checkpoint | Backfill completed correctly and heights checked/ correct
checkpoint | Consultant sign off and date or requested to inspect
checklist-flat | Kerbs Install Checklist
checkpoint | Drawings referenced and followed
text | Drawing & Revision Number
checkpoint | Setout & level completed checked and accurate
checkpoint | Bedding depth and material correct (photo required)
checkpoint | Haunching - concrete delivery note and photos
checkpoint | Kerbs and drop kerbs laid
checkpoint | Kerbs accepted - no chips, level, in correct location
checkpoint | Received QA from Subcontractor
checkpoint | Consultant sign off and date or requested to inspect
checklist-flat | Light Pole Foundations
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Size and type correct to specification
checkpoint | Reinforcing spacing and location correct
checkpoint | Specified covers checked/correct
checkpoint | Splice laps checked/correct
checkpoint | Any starter bars are installed correctly (location, size and spacing )
checkpoint | conduit installed for cable and draw wire
checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint | Received QA from Subcontractor
checkpoint | Consultant sign off and date or requested to inspect
checklist-flat | Pavement Checklist
checkpoint | Drawings referenced and followed
text | Drawing & Revision Number
checkpoint | Design Mix Agreed
checkpoint | Weed spraying completed and substance agreed with engineer
checkpoint | Membrane seal or tack coat agreed prior
checkpoint | No ponding level +/- 5mm
checkpoint | Received QA from Subcontractor
checkpoint | Consultant sign off and date or requested to inspect
checklist-flat | Comms Pits Install Checklist
checkpoint | Drawings referenced and followed
text | Drawing & Revision Number
checkpoint | Setout & Excavation completed checked and accurate
checkpoint | Bedding depth and material correct (photo required)
checkpoint | Correct pit size installed to specified Invert Level
checkpoint | Ladders required? Y/N
checkpoint | Ducts installed / Core drilled
checkpoint | Cover installed and fixed at correct height
checkpoint | Pit Installation reviewed and approved (photo required)
checkpoint | Backfill completed & compacted as specified (Photos during backfill required)
checkpoint | Received QA from Subcontractor
checkpoint | Consultant sign off and date or requested to inspect
checklist-flat | Cess Pits Install Checklist
checkpoint | Drawings referenced and followed
text | Drawing & Revision Number
checkpoint | Setout & Excavation completed checked and accurate
checkpoint | Bedding depth and material correct (photo required)
checkpoint | Correct pit size installed to specified Invert Level
checkpoint | Grille cover installed and fixed at correct height
checkpoint | Pit Installation reviewed and approved (photo required)
checkpoint | Backfill completed & compacted as specified (Photos during backfill required)
checkpoint | Received QA from Subcontractor
checkpoint | Consultant sign off and date or requested to inspect
checklist-flat | Oil Interceptor Install Checklist
checkpoint | Drawings referenced and followed
text | Drawing & Revision Number
checkpoint | Technical Submission completed
checkpoint | Setout & Excavation completed checked and accurate
checkpoint | Bedding depth and material correct (photo required)
checkpoint | Correct pit size installed to specified Invert Level
checkpoint | PVC connector installed
checkpoint | Eartenware pipe outlet connectected
checkpoint | Lid cover installed and fixed at correct height
checkpoint | Pit Installation reviewed and approved (photo required)
checkpoint | Backfill completed & compacted as specified (Photos during backfill required)
checkpoint | Received QA from Subcontractor
checkpoint | Consultant sign off and date or requested to inspect
checklist-flat | Waterproofing Checklist
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Preparation / Substrate acceptable
checkpoint | Correct product delivered and checked - approval given to install
checkpoint | General photos/comments during install
checkpoint | Any inspections / observations documented, reviewed and closed out
checkpoint | Waterproofing install completed, reviewed and approved to meet required specifications
checkpoint | Received QA from Subcontractor
checkpoint | Consultant sign off and date or requested to inspect
checklist | Concrete Pour
section | Formwork and Embedded Items
checkpoint | Latest drawings available, checked and referenced
text | Grid Line
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Grids and RLs clearly marked for reference
checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint | Formwork sufficiently fixed and braced (incl any propping)
checkpoint | Shear studs installed as-per shop drawings & check ring test
checkpoint | Any rebates/ nibs / cast in items are correctly positioned, sized and appropriately fixed in place
checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint | All surfaces correctly prepared (e.g joints to exisiting concrete, release agent to formwork etc)
checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint | Any additional formwork photos and observations
checkpoint | All formwork elements completed and ready for concrete pour ( excess debris removed )
section | Reinforcing
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Size and type correct to specification
checkpoint | Reinforcing spacing and location correct
checkpoint | Specified covers checked/correct
checkpoint | Splice laps checked/correct
checkpoint | Any starter bars are installed correctly (location, size and spacing )
checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
section | Pre-Pour Completion (Approval to pour)
checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint | Council inspection completed and attached
checkpoint | All relevant inspections completed and attached
checkpoint | Main contractor inspection completed - Approval given to pour concrete
checkpoint | Heights and falls checked/confirmed before placement | YES, NO, N/A
button | Is the cover correct to specification
checkpoint | General photos and observations of concrete placement attached
section | Pour / Post-Pour Checks/Sign Off
checkpoint | Concrete checked on arrival & correct (slump, MPa etc)
checkpoint | Heights and falls checked/ confirmed after placement
checkpoint | Any curing compound applied correctly
checkpoint | Concrete surface to specifications
checkpoint | Area left clean and tidy
checkpoint | Any remedial work completed
checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checkpoint | Consultant sign off and date or requested to inspect
checklist-flat | Retaining Wall Checklist
Ground test results
checkpoint | Base Support
checkpoint | Formwork design by engineer
checkpoint | Formwork construction checked
checkpoint | Blinding Concrete, DPC Membrane
checkpoint | Formwork | YES, NO, N/A
button | Design checked | YES, NO, N/A
button | Position correct | YES, NO, N/A
button | Dimensions | YES, NO, N/A
button | Alignment | YES, NO, N/A
button | Plumb | YES, NO, N/A
button | Cambers built in | YES, NO, N/A
button | Oiled | YES, NO, N/A
button | Chamfers | YES, NO, N/A
button | Bracing | YES, NO, N/A
button | Meets specified finish | YES, NO, N/A
button | She bolts at correct spacing | YES, NO, N/A
button | Ties to correct cover | YES, NO, N/A
button | Pour ports | YES, NO, N/A
button | Wash outs | YES, NO, N/A
button | Finish levels checked | YES, NO, N/A
button | Finish levels marked | YES, NO, N/A
button | No grout leak points
checkpoint | Penetrations / Sleeves | YES, NO, N/A
button | Construction / Expansion Joints | YES, NO, N/A
button | Location | YES, NO, N/A
button | Stability | YES, NO, N/A
button | Keyways | YES, NO, N/A
button | Water bar | YES, NO, N/A
button | Release agent
checkpoint | Anchor Bolts | YES, NO, N/A
button | Position | YES, NO, N/A
button | Number | YES, NO, N/A
button | Fixing | YES, NO, N/A
button | Projection thread | YES, NO, N/A
button | Protection
checkpoint | Embedded Items | YES, NO, N/A
button | Position | YES, NO, N/A
button | Fixing | YES, NO, N/A
button | Blockouts | YES, NO, N/A
button | Ducts
checkpoint | Reo | YES, NO, N/A
button | Size | YES, NO, N/A
button | Spacing | YES, NO, N/A
button | Cover
checkpoint | Concrete | YES, NO, N/A
button | Correct MPA | YES, NO, N/A
button | Vibrated
checkpoint | Formwork Removal | YES, NO, N/A
button | Reo covered | YES, NO, N/A
button | Finish acceptable
checkpoint | Test Results
checkpoint | Received QA from Subcontractor
checkpoint | Consultant sign off and date or requested to inspect
section | Boardwalk
text | Drawing
checkpoint | 30mpa concrete pile 450dia 900 deep
checkpoint | Posts to be 1m clear from services
checkpoint | H5 190 x 190 posts
checkpoint | Quanity and locations correct of piles
checkpoint | 150mm gap above ground
checkpoint | Greater than 2m dist in posts, to hve 4/290x 45 bearers
checkpoint | Less than 2m dist in posts, to hve 2/290x 45 bearers
checkpoint | H3.2 140 x 45 brace over 0.9m, 150 clearing required
checkpoint | H3.2 290 x 45 joists & 600c
checkpoint | H3.2 140x 45 nogs
checkpoint | Straps/ fixings/ bolts/ nails plates all secured
checkpoint | Level of boardwalk correct
checkpoint | H3.2 1/290x45 batten joist & 600c
checkpoint | 550 overhang
checkpoint | 100mm gap from RW to board
checkpoint | 15mm gap from board to kerb
checkpoint | Width of walk correct
checkpoint | H3.2 140 x 22 decking 3mm gap
checkpoint | Decking corner/angle corner detail followed
checkpoint | Ballustrade post- 125x125 timber@1200c and 1200 height
checkpoint | 150x70 capping with light fitting
checkpoint | 50x 50 battons
checkpoint | Handrail s/s 900mm
checkpoint | Received QA from Subcontractor
checkpoint | Consultant sign off and date or requested to inspect