## Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix
c9e115fa-95c0-4ecb-9ad8-e46401ca6f22 | checklist | Byford U-Beam Stage-1 Casting |  | Byford U-Beam Stage-1 Casting Checklist
f038a26a-f77f-40d0-b518-308a515dd430 | section | Pre-Pour Checklist
f9089a6e-cd60-4497-b3ef-37e0d5179012 | checkpoint-no-value | Details
c41d88d8-82d5-551c-b889-24baba0a9ade | textbox | Cast Number
26edf6e1-68ee-583d-884c-06d7f5db3037 | textbox | Beam Number and Orientation
f8c46844-50fb-55d7-b08c-cd00d985c466 | textbox | Strand Arrangement Type
5f97a2e3-54be-5f63-a68c-9ab54a3d732a | textbox | End Diaphragm
5e495764-b4b3-4438-a346-de6fac802ced | checkpoint | Shop Drawings approved for Works
f51424db-fbe2-41ff-b900-983d1557a41e | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
cf3379a0-6a56-5dab-b523-164e9e744969 | note | Length
5c5b1b99-b86a-50b9-bd98-142233d1853e | note | Width
db955fcc-edc8-50b4-9507-261dd5a5bbbe | note | Height
84c0df5c-a94f-51c4-abac-219a35d7def7 | note | Straightness
aebaf78e-e379-5e11-817f-42922332399d | note | Cross-section
297d2350-2c1f-4f35-badd-b3f78d756bf5 | checkpoint | Mould Surface Checked
a901a94e-ef9c-53cd-beb8-de3ad026110f | note | Cleaned
3fe45033-c99f-5a3b-ace3-da928468e932 | note | Sealed
b9bb5648-46f5-543c-a7aa-177b5ad9c01b | note | Rubbers in Place
e26424e1-b546-5eda-a14a-4715cc5936b5 | note | Oiled
f7ddc3bb-c54e-5e50-8532-26b3ae781893 | note | Chamfers in Place
fd675411-86fe-498d-af70-91657dcecce5 | checkpoint | Reinforcement in Accordance with Drawings
faaa4546-688c-57f3-9c5a-500bc924a4fa | note | Reinforcement size
b77bb4f7-5fe6-5a92-a985-3b90172d6ff6 | note | Lap Length
30db3941-b5c1-5c33-a4e1-c0b78b0822ff | note | Splicing
703d80cb-f5e8-5058-a3c3-210795bcd93a | note | Bar Chairs
cd672bd7-f101-56ad-9502-0070f8afcac6 | textbox | Reinforcement bars with couplers
5e41ad3d-383a-584c-951c-fabb9a05d709 | textbox | Reinforcement around lifting loops
acd09d60-c7b7-4b44-9e1f-b0be040ef501 | checkpoint | Detailed inspection of Mould and cage
f93ac21e-bd75-4a7c-9005-c737cb390d68 | checkpoint | Cover maintained and within tolerance
d0d591ec-190a-4d07-99b5-afe140c960ea | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
ebdc4887-3c67-58de-b00c-88fd9a6c9a97 | textbox | Ferrules KSN16M (Web)
b04a6b8f-bcff-56aa-8069-a11d54d3071d | textbox | Ferrules M20x96 (Bottom Flange)
c9de196f-a2dd-5b3b-8e9a-764f05507472 | textbox | Ferrules M16x45 (Ladder) |  |  | Size not confirmed
1db8b07f-034b-524f-a323-7d4150f54691 | textbox | Ferrules M16x70 (Web, Laingorourke Formwork)
4a46170e-03c6-5b61-8a07-29b7e53eaa42 | textbox | Ferrules (Other type, specify)
89abc4f6-8029-4387-aec0-8f466d0ef8eb | checkpoint | All Stainless Items are installed in accordance with Drawings
ce875086-8399-52a8-a6f2-f6534757a1fb | textbox | Other type, specify
f1c085ee-83ec-4683-9d64-ca3cf88cf3a6 | checkpoint | All Blockout Conduits are installed in accordance with Drawings
b51c81ac-c014-57ed-9d65-e399b7952085 | textbox | 20NB PVC Pipe
1e8144b2-aaba-4694-9ec8-db6ad7f7699d | checkpoint | All Lifting Inserts are installed in accordance with Drawings
987eeb36-e463-532d-a1c6-cb3aa12fac7d | textbox | Lifting Hoops
09937c30-a20b-469f-83f1-e9f2787c7a8d | checkpoint | All Bartek Couplers are installed in accordance with Drawings
1aecce61-d7ab-5c89-90bd-f9457fee9f05 | textbox | BPB28
57283504-287a-5f2e-96c7-b71ebfa17f5f | textbox | BPB36
1734b4a4-ce66-5e40-92cd-1f6d7643da41 | textbox | BPB20
ce265c84-92b2-470f-8b5e-bd0af3354f02 | checkpoint | All LENTON Couplers are installed in accordance with Drawings and staggered with KSN16M in web
2c08a51f-8af3-599b-b795-ce25aa664746 | textbox | LENTON EL20A12
cb462ad0-48fd-45be-bd79-56d4ae912b5b | checkpoint | All Bearing plates in Diaphragms are installed as per drawings
a6511f91-fdff-5db2-9ad1-83094f2ed8f4 | textbox | Specify Bearing plate Size/Type
a4a3607d-27fa-490d-b248-d28103aacdf4 | checkpoint | Earthing and Bonding is installed in accordance with Drawings
f88c0a13-d51f-5fc1-9c52-0f410c20ffd7 | textbox | Earthing Terminals (FDB-16)
00a93e71-de19-50c4-b9ab-193dd21b9019 | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
51a2bf98-3c5a-5f72-a99b-b387b2b1c147 | textbox | <20 mOhm across cage Length
222de404-9ade-5083-b52c-4f535a6bec20 | textbox | Checklist Completed (attach results)
a70d2584-5d63-4569-aad0-726e005ffb81 | checkpoint | Prestressing Strands
d58d3d4b-877c-56a8-b4cf-f7d1c39c6171 | textbox | Coil Number Used for this Cast
69fb34df-e782-50ef-8e89-a752c9c4cf74 | textbox | Dia and No. of strands
e9fd66d9-dd4e-542b-834a-e0fbf4223e3a | textbox | Strands arrangements verified
f1137e2b-6e9f-55c0-be66-f3dac59e316b | note | Sag Load all Strands
a2f7a1ce-4bb7-5d82-812b-60d6e5f877b9 | note | Multi-Stress as per Pre-stressing Procedures
25a59fc6-6248-531d-a5d9-3376b57b5476 | note | Verify debonding strands if any
8441591c-5cdf-4fcb-9c0c-34b16b8542b5 | checkpoint | Stressing Records subject to Client Review
0df89bc9-3a10-4c92-a496-8159d0879e4c | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
94c14ae5-2550-4fc7-94d8-5f0c08d08ce4 | checkpoint | All Temperature Loggers are installed as per Approved WMS
4689a9fc-47de-5817-9eb5-fd13c08d4368 | textbox | Ensure All temperature Loggers are Working (Check Maturix)
00a8deaf-299e-49e4-b25a-8b259191fba1 | checkpoint | All Cooling tubes installed as per drawings
9f92dbd8-e5e6-4ea4-8018-03268f8fe898 | checkpoint | Installation of tubs
295e3131-fc21-5091-935a-ed4a4d7dd5aa | note | Tubs are tightened and positioned correctly
0d7c7de7-3210-5c3c-9d07-ffecc3438531 | note | All Sliding arms are locked in position
ccc8ee39-059b-5903-a2b5-636d5e1b9ddb | note | All accrow props are locked in position
92532aae-018d-51d5-99cf-08e689383931 | note | Dimensions of Tub and Webb are correct
6ceb25cf-8a5b-5cbf-9446-2cdcc571f765 | note | All feet for tubs resting on mould & bolted down
b7498bb7-2052-54d0-bae6-6de96780b449 | note | Tubs have release agent
03b7b707-44c4-47e7-83f5-9bb2fdf08ea3 | checkpoint | QA Engineer Check Completed by
ad9dfbe0-02f4-46fa-90ba-03decfb50eee | checkpoint | Client Inspector (if present)
a9f76285-3c3f-4837-99ae-a51efb1a4966 | section | Supervisor Release
61f57523-5f07-47b7-b854-8bd4769241ce | checkpoint | Supervisor Release to Engineering Team
a26d2325-033f-4ceb-9af1-c507fa125446 | section | Casting Checklist
baadb843-05db-4d3b-be8a-96314abf7926 | checkpoint | Casting Information
8fe38f8c-d924-5b50-b98c-4eac4c1cf31d | textbox | Cast Date
c25427f8-6aad-4a06-b9ff-28fc52eb7b2e | checkpoint | Concrete Delivery Dockets
5eca1db2-8fed-5fb3-b96f-df8e1bb0c513 | textbox | Concrete Delivery Dockets (list all)
d64b7aab-3db5-47d3-a400-5c91cfaa6ee7 | checkpoint | Total Concrete Volume
c7039a52-0293-57a1-ae5a-2525edb4e402 | textbox | Volume (m3)
4efd73bb-bce8-462f-84ed-7ed31978caed | checkpoint | Mix Design Verified
dace34b6-c925-5bbc-9a0c-09dde1e86848 | textbox | Specify mix used
a46eebd2-5a64-44fa-b8e5-ab6527988738 | checkpoint | Ambient Temperature within Limits
fb6f43a3-b229-5345-a1cb-a22aa6e725c4 | note | max 38°C
09207f88-be16-48d1-bd71-568e32188c83 | checkpoint | Concrete Temperature
c436a131-9233-5af9-87b1-d6ad621ebb0c | note | max 32°C
26e0fb63-cc1a-403a-b5c6-e25e65d88f96 | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
5b580ca8-c84d-5479-9b42-d600274739dd | textbox | Slump (list all)
4026a645-f3c7-45f1-8bd4-8e5022933870 | checkpoint | Trucks Tested for strength
472ea074-4cc3-5a1e-b59c-2da508e2992e | textbox | Test Report Reference Number (list all)
3302489a-4145-4f4a-9bad-9b8269168553 | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
18194d97-cfc3-49b4-8031-79f1bb08c011 | checkpoint | Concrete Placed within allowable time from Batching Plant
da9b47c9-43fc-47bc-919f-a4c0ebe37ed8 | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
26b41951-ed2d-4357-9dc4-135d88af3358 | checkpoint | Required Finish Applied as per Drawings
0e87e80e-0e6c-422f-9c39-7ce93237880e | checkpoint | Retarders applied on Green Cut areas as shown in drawings
15d511db-c97f-40fb-99a6-a081fb6a9d46 | checkpoint | Concrete Covered Overnight
a6263332-6b68-4d00-8a1f-faac86e6ae5d | checkpoint | Cylinders Stored next to Bed
e039e957-ce0d-454b-95c2-adfc73170889 | section | Stripping Checklist
8083cf91-67de-4b0c-a101-baaeede43324 | checkpoint | Date Stripped
9b5c1a41-8343-53af-9f21-9f770bc063f6 | textbox | Enter Date
32cc10ee-dd77-4cee-9aaf-5d1a23e163ae | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
304d0e23-3343-5b5c-9189-82f4e7a56eed | note | Conversion KN to MPa = Reading / 7.851
54b5418c-8177-53df-9c3d-eb7c4ebcfd4b | textbox | Stripping Strength (Stage-1 Casting)
e8703e58-c503-4c0c-b231-c1b9bab1e5b7 | checkpoint | Verify Destressing/Transfer of stress required strength
bdb03c1d-3057-57d4-8237-0f3983db30d7 | textbox | Specify Strength at time of destressing
cb712fc0-2b91-439b-ac16-679cda642ffb | checkpoint | Lifting Strength Achieved
809b1191-8be0-55d9-aa58-aefdd4ce5ae2 | textbox | Specify strength at time of lifting
59ddb910-3688-4468-9409-96889433b0cf | checkpoint | Curing strength (Stage-1 Casting)
9181e5e4-2f9c-5737-84fb-3ac83e665038 | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
6335b845-eb1b-5a65-a0fa-8414f46f35c6 | note | Mould and Steam Cured until the curing strength achieved
6b8382de-141a-4cb5-be27-fb8f42900dfa | checkpoint | Lifted and Handled as per Drawings
7de22fb1-438d-40ab-99bb-fd56989c1771 | checkpoint | Product Clearly Labelled
1df724cc-2dce-4557-9242-33d4095df9b6 | checkpoint | Storage as per Approved Temporary Works Drawings
caafd690-e3c8-41aa-96fc-d64266f1a5f5 | checkpoint | Secondary Curing as per Approved Methodology if required
58d7dfbb-6449-51db-86cb-b6d5a0982f1d | note | Temperature 5 degrees less than its peak value
5fc720bb-d3e1-5a9f-b6d1-2642c29caf62 | note | Max temperature does not exceed 70°C
88251f20-4b38-58ee-9411-1d0be8ccc489 | note | Differential between Core and Ambient within 30°C
f0d6b281-4db2-5f14-82dd-041eaf622814 | note | Differential between Core and Cover within 25°C
1af5f7dd-f3bf-4689-97d8-91b92fa74429 | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
2a240618-b3ba-5a1f-88cd-aae6a8477bfb | note | Length
aa40f4b9-a380-53bb-b185-52e5b8ca3a88 | note | Width
a0b93503-6eae-54f8-b2f3-6ac071d6a29b | note | Height
e5d22a13-8463-592e-a53a-7eacb487b31d | note | Straightness
7366556d-0202-5698-8258-5de8cd503e4b | note | Cross-section
5c3509a8-803b-4672-abb8-ed2c91a2f601 | checkpoint | Specified Finish Achieved
2b5c127e-2008-42c1-aa9f-82baef12c0e3 | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
478dcf6c-4348-5c43-b1ac-9ac6f30899dc | textbox | Ferrules
09dfd0ce-17a3-57e7-940a-0e669c0161d6 | textbox | Couplers
7e499b2d-ced2-517d-acae-83cf3621f7ba | textbox | Stainless Items
cf26f51d-1db5-51f6-8c55-37e9b36058a7 | textbox | Lifters
5186d4a8-13db-507a-8fbd-4b3264a9cd02 | textbox | Blockouts
e732c755-5f52-47ad-86d8-221e5d8fd88b | checkpoint | Post-Pour Works Completed (As Required)
e01dafba-581c-5f57-af89-689aee8da497 | textbox | Strands are Cut Flush and Epoxied except debonding strands
b279f51a-6eb5-5ec5-956c-74fde643121a | textbox | Couplers are Cleaned and Capped
7c60cad3-fa3d-580e-90ee-9c8d23adaefb | textbox | Roughened Surfaces are Greencut
3078019c-2a9e-5db2-805a-8d451a783517 | textbox | Water Removed out of Cooling Pipes
82adfef5-b56c-5fd8-a991-15466428e967 | textbox | All Miscellaneous Items are Completed
8a5a3844-7623-5182-b3bd-36067f57e593 | textbox | Bottom surface clear from tie wire (Attach Pictures)
7674bfdd-ea6e-4c0f-bf89-6b1ff2382b39 | checkpoint | Survey Hog of Beams (Dumpy)
a0451e16-237f-5f66-b21a-f99e5844848c | textbox | First Reading (Within 2 days of Stripping)
8b04dab8-80b7-5a6d-ba08-86ac6544d908 | textbox | Second Reading (After casting stage 2 top slab and at least 7days after stage 1 casting)
ca58c95b-c03b-5c9b-aef6-cc4af7e41291 | textbox | Third Reading (At 28 days after stage 1 casting)
9632d1a3-671c-583d-96cf-355ec62aa165 | textbox | Final Reading (7 days prior to scheduled delivery)
74ce2bc5-7ece-4731-a313-a3096f528b13 | checkpoint | Temperature Logging Completed and Conforming. Attach Results
ec95c0f0-3340-4360-bc82-10d892556c28 | section | Any Defect Identified
4ac7df22-2e8f-4929-b69e-d88bed680947 | checkpoint | Punchlist Completed
426814e6-42f9-43ad-8100-79567fa25917 | checkpoint | Repairs Required (if applicable)
46a565a1-f6a5-4304-952f-0d94805b1e8b | checkpoint | Repairs Completed as per approved WMS (if applicable)
d0cc4b45-0793-4c60-8337-d508af92c05b | checkpoint | Crack Map Completed
374b130f-8361-482c-9878-ef7a8a699300 | checkpoint | Any NCR Required (if applicable)
30342767-dbdc-4e5e-8627-495f88e42d35 | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
f3f572bd-4663-4aee-8b80-6c41ff64d475 | section | As-Built Drawings
46a64171-c3da-4a61-a5e9-209cc394736d | checkpoint | As-Built Drawings Completed, Stamped and Attached
aa00805a-aad4-41a8-ae66-da3af7234cd6 | section | Concrete Strength Test Report
45e626b3-2800-442c-bfc0-2fae89313794 | checkpoint | Concrete Strength Test Report Received
3312d95e-0d69-5a8a-8fda-ae0b2430f550 | textbox | Concrete Test Report
31417dcc-d866-5e56-adc7-91bf65ea8d6f | textbox | 7 Day Strength (List all)
2762749c-cd52-5395-8fa3-cd8ebc3e3832 | textbox | 28 Day Strength (List all)
48db2af7-07b0-408f-b51c-77d38a9eac66 | section | Transportation Requirements
a3d16895-35a0-40be-a5a2-503409b1d405 | checkpoint | Certificate of Conformance
6c222207-212e-4e3c-895d-df73f600b18d | checkpoint | Inspection Release Certificate
b1f938b2-b664-4d81-ab3e-da95a6907638 | checkpoint | Delivery Notes
5753c899-7228-48b7-a0d2-945cad337167 | checkpoint | Delivery Docket
ea8fede8-7de3-473b-89b2-37288ed059fe | section | Final Acceptance
18b2ac23-087d-4f50-9aee-e710e4d119c7 | checkpoint | Completed by
fe00186b-659d-41a7-b4a6-6d74d9c46742 | checkpoint | Reviewed by
93a4c3d0-989d-48ae-b391-0492fd0c1d12 | checkpoint | Client Representative (if applicable)