## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
61ff5bfa-fb68-5099-b9ce-ba9520b062d6 | checklist-flat | Cold Water BG |  | Cold Water BG
083eb9c4-fa14-554f-aec0-197652d9497a | checkpoint | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
| holdpoint | Notify and gain permit from principal contractor / client for inspection
c14305f2-9ed6-5c66-ba84-f6e1dbe68b58 | checkpoint | Setout & alignment as per drawing (include revision below)
ce333f36-f37e-5e65-b1f5-f7f3229b11bb | textbox | Drawing & revision number(s)
4fc0f552-afec-541b-b654-572f8de432eb | checkpoint | Correct material as per sample register
2ed31540-094b-5126-866c-4e3adfae1a16 | checkpoint | Bedding material installed correctly
2a76a8df-eec9-5f77-a2d0-6c08c6872dc5 | checkpoint | Fittings & joints correctly installed to manufacturer's requirements
797f3654-d0d8-5d28-97d8-43f3007f39cb | checkpoint | Satisfactory welding/pressing of copper pipe
6bdd26cb-9431-532b-86a8-eb6217f929f5 | checkpoint | Witness marks visible
8413c3fa-1c4b-57c3-80a7-3c9d2811675f | checkpoint | Pipework layed correctly and to AS 3500
b9d15f15-f88d-58fe-97f7-a98d9c6fe5a1 | checkpoint | Inspection and Testing Prior to Concealment to AS 3500
ae7f647a-2d28-5dfc-b8c3-04ca6f8e6945 | checkpoint | Seal open ends with caps & high light to avoid damage
5419071a-4563-56ca-be84-852b1e1ec9f0 | checkpoint | Identification of services via I.D tape
d08a8101-0125-591f-9180-7d0df9eb5033 | checkpoint | Backfill & compaction to specification in 300mm layers
a51941bf-58da-55a5-9a43-3db39640fbb2 | checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
443b740b-a999-55c1-a5ed-a4cde8615a57 | note | Passing above includes Builder sign-off
eeda2b32-33f4-5119-a576-6570c6bc1e56 | tickbox | Area clean