## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
c7e17c82-1b52-5fd5-b6ce-d89591eab107 | checklist | Corridor Template |  | Corridor Template
3d3ce6a2-4654-5120-8b31-ac5390c8e9ea | section | High Level Services
083eb9c4-fa14-554f-aec0-197652d9497a | checkpoint | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
| holdpoint | Notify and gain permit from principal contractor / client for inspection
c14305f2-9ed6-5c66-ba84-f6e1dbe68b58 | checkpoint | Setout & alignment as per drawing (include revision below)
cb99b1be-acc6-5dfd-81a1-2d67ec8c7ddc | textbox | Drawing & revision number(s)
8345cfb7-e23e-5a0e-b0d8-7f7b59210905 | checkpoint | Material type as per approved sample submission with AGA or watermarks
f1631ae0-e631-5a33-9c42-ca2a9d2dddaf | checkpoint | Welding , press fittings, witness marks visually checked
410bf4a7-cdb4-5244-8684-ed3de2b0fb1a | checkpoint | Fixings & seismic support to standards
af9ace07-fd1e-51c0-9bdc-ba3ef4ffcc0a | checkpoint | Pipework installations to code requirements
62a129db-b0ea-5746-95a7-efb3c58f1352 | checkpoint | Water meters installed to authority standards
3fbb74a2-7019-5250-b4d3-1252e945ec62 | checkpoint | Gas 25mm separation achieved from other services as per AS 5601.1
1cd6df51-7bfe-551e-b102-bccaaed7eb18 | checkpoint | Penetrations, fire protection, wall sealant installed to the BCA requirements
b1ae14c2-f2fb-534a-8db0-219e412cfc69 | checkpoint | Identifications of services, valves & meters to standards
e540386a-8b73-5857-9fae-b8ff3f7b8db4 | checkpoint | Pressure test to code requirements
a51941bf-58da-55a5-9a43-3db39640fbb2 | checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
9199fe7b-71b2-5f07-8e25-387163764a22 | note | Passing above includes Builder sign-off
76bbce7c-5bf3-51d3-925f-78724a646f60 | tickbox | Area clean
570b8746-d828-55ec-99ba-45ccd417c4bc | section | Drainage
47e42bb2-540b-5eaf-944e-5a95dbb84320 | checkpoint | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual) and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
| holdpoint | Notify and gain permit from principal contractor / client for inspection
0e825ec1-7bae-5068-a735-86d47796832a | checkpoint | Stormwater riser
a7c69516-82ed-5c9e-8b8e-148b67c2cd59 | checkpoint | Syfon drainage
9ea02d57-bc2b-47de-8a91-e0e21a8f0861 | checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
4c3c4be5-d7ec-5d65-a679-489be32d2fb3 | tickbox | Area clean
f8bfbdc9-8053-58bd-a022-baeeb34ce428 | section | Sewer AG
d709259d-12cd-4907-94fd-dee2f46362b3 | checkpoint | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
| holdpoint | Notify and gain permit from principal contractor / client for inspection
ff5c6deb-e870-4def-b8d6-6840d7961c8d | checkpoint | Setout & alignment as per drawing (include revision below)
30735e82-8533-5bac-a2ec-f7cfd2ae63d5 | textbox | Drawing & revision number(s)
ce322e6d-7f63-5bf6-a477-b5f1a151ddbc | checkpoint | Grades, fittings & joints installed to standards
120e5349-cb56-4ac2-ae0f-c4e42292346e | checkpoint | Fixings & seismic support to standards
65c25f8f-22a4-5daa-a14b-2023299a2c1d | checkpoint | Expansion joints per floor installed correctly & clipped
af8e630c-839c-5cad-bff7-e6f0b9c48092 | checkpoint | Pipe risers sealed per floor & capped off to prevent damage
e0f8ec9c-302d-5bb0-8eb3-f4e80b61eade | checkpoint | Correct invert level (As per Standards)
6a147b79-3c3a-5107-9ae1-c708993977f5 | checkpoint | Vents and AAV installed (As per Standards)
58c39949-84e1-5bec-9481-afb3069adeb5 | checkpoint | Acoustic lagging installed to acoustic specification
0eb38021-b577-5e0e-8e61-1868053ab9b4 | checkpoint | Pipework water tested to 15Kpa
7a255cfd-1417-58ed-a027-9a1a06843d91 | checkpoint | Identifications of services
37e88f72-521a-4725-b862-2e485ffbcbdc | checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
a915df0a-ea40-5466-b505-8901c92623c0 | note | Passing above includes Builder sign-off
53b71f03-d600-58bf-bb1b-ce89cc38c824 | tickbox | Area clean