## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
afd2c93f-f6ea-52f7-8654-bf31c23d24bc | checklist | Fix 2 checklist |  | Fix 2 checklist
d2b587ba-e04c-5d8e-9a78-7f27ea1c00a2 | section | Fixtures
083eb9c4-fa14-554f-aec0-197652d9497a | checkpoint | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
| holdpoint | Notify and gain permit from principal contractor / client for inspection
a130cb5d-d1a3-5d59-a952-50ce8d790369 | checkpoint | Correct product (samples provided)
52b86a03-86c0-5db0-a485-04976a168d89 | checkpoint | Check products for imperfections
ff4f4148-bc29-5882-b393-8570d89ccbee | checkpoint | Location & fixings (as per drawings & manufacturer guidelines)
b37858b9-4510-54f9-b379-46fecabc7e37 | checkpoint | Silicone seals are acceptable standard (as applicable)
df7af16b-9bd4-5328-b7c8-cae4076c35d4 | checkpoint | Operation of all fixtures, taps & points of demand
884f19fe-03ab-54b9-a94b-fecf55157759 | checkpoint | Final fit off inspection on all items
46d9f226-f5af-5ddd-8010-253a4c69a164 | textbox | Inspection date
80069c7e-b2ec-550c-88e2-241bcf902e2e | checkpoint | Items protected until commissioning (Attach photos below)
a51941bf-58da-55a5-9a43-3db39640fbb2 | checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
69810024-33d2-5272-aae3-f313c17231cb | note | Passing above includes Builder sign-off
df7ff3fe-0757-5f6d-be88-bab6d62f7c2a | tickbox | Area clean
bdd5cda7-43e6-5934-bc03-37a69b742c8c | section | Commissioning
598f3b6f-8a3e-40fe-ab16-a8b93f94b1a8 | checkpoint | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
| holdpoint | Notify and gain permit from principal contractor / client for inspection
1a6f162a-4359-4c82-b4b1-f92203ff586d | checkpoint | Check products for imperfections
75105f13-45dd-56d6-8fe7-5d137cb4e94a | checkpoint | Fixtures location & fixings all correct (as per drawings & samples)
75293eb1-0271-5738-84c2-43edbe7c86eb | checkpoint | Clean out all strainers / aerators
4a80fbba-8f4d-526c-bed3-65803c5eaf52 | checkpoint | Check for no cross connections / leaks / access to isolation valves
23533c22-fdf6-53df-9b9e-7cec6655b7d3 | checkpoint | Floor wastes (clear of debris & draining correctly)
4dfaaf89-5ce8-59ce-b2a1-e3a7b6811c3a | checkpoint | Quality of silicone seals to fixtures acceptable
bf805153-8bc5-5225-a08a-9099e8638797 | checkpoint | Hot water tempering valve set to 50c (+/- 5c) & DDA thermostatic mixing valve set to 42 degrees.
a4d51ff0-032d-5d47-9069-74c84a4883fe | checkpoint | Water pressure acceptable 350Kpa to 500 Kpa
432aa93e-aa13-4a79-87d8-887465a27d64 | checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
6044ab76-416f-5ca3-8755-f45c75921fe0 | note | Passing above includes Builder sign-off
c09a24d8-f6a7-5b98-b7eb-b202c261c4a4 | tickbox | Area clean