## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
d8d3ab26-8a33-5160-ad5f-33eb9c3f1041 | checklist-flat | Greasy AG |  | Greasy AG
083eb9c4-fa14-554f-aec0-197652d9497a | checkpoint | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
| holdpoint | Notify and gain permit from principal contractor / client for inspection
c14305f2-9ed6-5c66-ba84-f6e1dbe68b58 | checkpoint | Setout & alignment as per drawing (include revision below)
8217a15e-af2a-55c7-8455-07e2c78caae4 | textbox | Drawing & revision number(s)
4fc0f552-afec-541b-b654-572f8de432eb | checkpoint | Correct material as per sample register
b5d6f2ff-34c1-5866-8c0a-07d92be38f96 | checkpoint | Grades, fittings & joints installed to standards including witness marks
ade472d0-53da-5314-be2d-047537d9211b | checkpoint | Fixings & seismic support to code requirements
65c25f8f-22a4-5daa-a14b-2023299a2c1d | checkpoint | Expansion joints per floor installed correctly & clipped
af8e630c-839c-5cad-bff7-e6f0b9c48092 | checkpoint | Pipe risers sealed per floor & capped off to prevent damage
17c9106d-fecc-58ad-9767-59f1a6881c7f | checkpoint | Correct ventilation installed including AAV
58c39949-84e1-5bec-9481-afb3069adeb5 | checkpoint | Acoustic lagging installed to acoustic specification
1339cc75-c05a-520b-b056-2b5d71ce2b08 | checkpoint | Testing to 15KPA with air or full water test
7a255cfd-1417-58ed-a027-9a1a06843d91 | checkpoint | Identifications of services
a51941bf-58da-55a5-9a43-3db39640fbb2 | checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
322ffad7-0247-5d67-a8fd-1d9302e87c2c | note | Passing above includes Builder sign-off
2dcbc319-62e0-5f73-bac8-0f7be9274de8 | tickbox | Area clean