## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
af7d3387-903b-53c7-b902-8a390dd61f95 | checklist-flat | Rainwater |  | Rainwater
083eb9c4-fa14-554f-aec0-197652d9497a | checkpoint | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
| holdpoint | Notify and gain permit from principal contractor / client for inspection
c14305f2-9ed6-5c66-ba84-f6e1dbe68b58 | checkpoint | Setout & alignment as per drawing (include revision below)
556e3567-020d-57e0-83c0-8c9b89b907f0 | textbox | Drawing & revision number(s)
09117d16-dfa2-50b1-bd6e-48ad77253238 | checkpoint | Material type as per approved sample submission
b3af4620-6bbf-5799-a411-13600fc22da4 | checkpoint | Pipework fittings, bends, joints etc (as per AS 3500.1 section 2.6)
1d31dec7-a3e3-542e-972a-be20964718a6 | checkpoint | Welding / pressfit / push fit (as per AS 3500.1)
0cfbef0b-fc60-5c64-928d-cf19e6487023 | checkpoint | Support & fixings (acoustic / seismic / water hammer)
4731048f-36da-51bd-ad5f-526936078ce5 | checkpoint | Pipework Installation (as per AS 3500.1)
5f445bf0-7c65-5ebf-86df-b16d210f8575 | checkpoint | Check no cross connection
d20132f4-2356-54f0-be61-143c1852c66f | checkpoint | Pressure test (1500kpa pressure test)
7a255cfd-1417-58ed-a027-9a1a06843d91 | checkpoint | Identifications of services
a51941bf-58da-55a5-9a43-3db39640fbb2 | checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
d598042d-9beb-5581-bea6-d241ce09f4c9 | note | Passing above includes Builder sign-off
99cf2a97-f2d5-5de0-a106-f9b0e532ef2b | tickbox | Area clean