## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
96cad16c-35bb-5552-9a5a-62f325dc20ad | checklist-flat | Sewer BG |  | Sewer BG
083eb9c4-fa14-554f-aec0-197652d9497a | checkpoint | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
| holdpoint | Notify and gain permit from principal contractor / client for inspection
ca296f48-5010-50b6-a3a2-23677a2db500 | checkpoint | Latest specifications and standards nominated in ITP
7aeeba92-0cf6-54f9-a401-eb28f9fdb45a | checkpoint | Setout & alignment as per latest available drawing (include revision below)
b70c799f-2066-56d8-b665-37b35cd695e4 | textbox | Drawing & revision number(s)
f0f55c81-bcaf-59f1-9682-e6c957a7d1eb | checkpoint | Correct approved materials as per sample register
4455766f-3eac-55cc-8857-4db1f20983f2 | checkpoint | Excavation undertaken & no issues (Any issues comment below)
806f3505-6753-52e1-a009-631eea96230e | checkpoint | Pipe bedding material comply (as per AS 3500)
ce322e6d-7f63-5bf6-a477-b5f1a151ddbc | checkpoint | Grades, fittings & joints installed to standards
1744ed1f-3d17-58c0-b87e-b5de1228f3d4 | checkpoint | Pipe clean out via water flush
308f5ac3-5842-5913-a985-b75f41b1d2ae | checkpoint | Inspection & Testing Prior to Concealment to AS 3500.2 section 13
0ccc95fa-921b-541d-b612-6d25903a866c | checkpoint | Builder sign off prior concealment
ae7f647a-2d28-5dfc-b8c3-04ca6f8e6945 | checkpoint | Seal open ends with caps & high light to avoid damage
e38f2575-5287-591a-80c5-9b90bda8b0c4 | checkpoint | Backfill & Compaction of Material (As per Specification / Geotechnical report)
f206e596-1f32-5446-8a04-d8b5044bb7b3 | checkpoint | CCTV on completion & record results
a51941bf-58da-55a5-9a43-3db39640fbb2 | checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
97dd0b2e-a83d-519f-8182-117ea05afb34 | note | Passing above includes Builder sign-off
8bf65035-b551-5f28-900a-e71621ef0e25 | tickbox | Area clean