## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
68cfc9f4-64f3-5355-837b-6973249088dc | checklist-flat | Stormwater AG |  | Stormwater AG
083eb9c4-fa14-554f-aec0-197652d9497a | checkpoint | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
| holdpoint | Notify and gain permit from principal contractor / client for inspection
c14305f2-9ed6-5c66-ba84-f6e1dbe68b58 | checkpoint | Setout & alignment as per drawing (include revision below)
23e2b1dc-2644-555b-bfa2-5bf65a72adcf | textbox | Drawing & revision number(s)
1427a3fd-c38d-5ebf-928c-558a4f7ed9e4 | checkpoint | Grades (as per AS:3500)
0425c0ef-7719-51c7-a7b1-b1b2088c7aef | checkpoint | Location (as per hydraulic drawing)
4c56132b-0f66-55b1-9162-f1b783bdeeec | textbox | Location
ff9a4ff9-5c7f-5393-9b60-ac364ef2382f | checkpoint | Fixings - Securely fixed (As per Standards)
e4b22e0b-ecbc-5c4f-88db-9e20d3816be8 | checkpoint | Fittings Joints ETC (as per AS 3500)
74b93783-f04a-59f9-9fd8-f08523d1dab8 | checkpoint | Inspection prior to closure
1ef7c64e-399c-5102-b940-881f03e5c003 | checkpoint | Operation of pumps (Commissioning report) if Applicable
9cf7d1b0-458e-528d-9e9d-c7fa76bd2c7a | checkpoint | Test water and discharge requirements are met
a135d123-824b-556f-bb88-5a1febc2ba07 | checkpoint | Correct invert level AS per AS 3500
a51941bf-58da-55a5-9a43-3db39640fbb2 | checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
6cac5e8d-0697-5691-b230-9932953a7a99 | note | Passing above includes Builder sign-off
6223520b-dffa-5cf0-b3f8-2c5e11ece80a | tickbox | Area clean