## Project Structure
Folder Structure |  |  |  | Checklists
COLES TARNEIT
PROJECT DOCUMENTATION & NOTES
DRAWINGS
TECH DATA
POINTS LISTS
NOTES
EXISTING CONDITIONS REPORT
|  |  | MSSB-1 | MSSB CONDITION
EQUIPMENT
|  |  | PLANTROOM EXF | MSSB EQUIPMENT
|  |  | PLANTROOM SAF | MSSB EQUIPMENT
|  |  | AHU-1 | MSSB EQUIPMENT
|  |  | AHU-2 | MSSB EQUIPMENT
ROUGH-IN
|  | ACU-5/CU-5 - CLICK & COLLECT CEILING CASSETTE |  | STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in Checklist
|  | ACU-1 - TEAM RM/LOCKER PAC UNIT |  | STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in Checklist
|  | ACU-3 - BAKERY PAC UNIT |  | STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in Checklist
|  | HP-1 - HEAT PUMP 1 |  | STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in Checklist
|  | HP-2 - HEAT PUMP 2 |  | STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in Checklist
|  | C-HWP-1 |  | STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in Checklist
|  | C-HWP-2 |  | STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in Checklist
|  | TEF-1 STAFF TOILETS |  | STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in Checklist
|  | EF-3 BOH VENTILATION |  | STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in Checklist
|  | EF-4 BOH VENTILATION |  | STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in Checklist
|  | EF-6 CHICKEN OVEN EXHAUST |  | STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in Checklist
|  | EF-10 FISH PREP |  | STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in Checklist
|  | SAF-2 CHICKEN OVEN MAKEUP |  | STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in Checklist
|  | SAF-4 PRODUCE PREP SUPPLY |  | STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in Checklist
FITOFF
|  | ACU-5/CU-5 - CLICK & COLLECT CEILING CASSETTE |  | STANDARD EQUIPMENT Fit off Checklist
|  | ACU-1 - TEAM RM/LOCKER PAC UNIT |  | STANDARD EQUIPMENT Fit off Checklist
|  | ACU-3 - BAKERY PAC UNIT |  | STANDARD EQUIPMENT Fit off Checklist
|  | HP-1 - HEAT PUMP 1 |  | STANDARD EQUIPMENT Fit off Checklist
|  | HP-2 - HEAT PUMP 2 |  | STANDARD EQUIPMENT Fit off Checklist
|  | C-HWP-1 |  | STANDARD EQUIPMENT Fit off Checklist
|  | C-HWP-2 |  | STANDARD EQUIPMENT Fit off Checklist
|  | TEF-1 STAFF TOILETS |  | STANDARD EQUIPMENT Fit off Checklist
|  | EF-3 BOH VENTILATION |  | STANDARD EQUIPMENT Fit off Checklist
|  | EF-4 BOH VENTILATION |  | STANDARD EQUIPMENT Fit off Checklist
|  | EF-6 CHICKEN OVEN EXHAUST |  | STANDARD EQUIPMENT Fit off Checklist
|  | EF-10 FISH PREP |  | STANDARD EQUIPMENT Fit off Checklist
|  | SAF-2 CHICKEN OVEN MAKEUP |  | STANDARD EQUIPMENT Fit off Checklist
|  | SAF-4 PRODUCE PREP SUPPLY |  | STANDARD EQUIPMENT Fit off Checklist
PRE-ENERGISATION TESTS
AS3000 VERIFICATION TESTING DOCUMENT
|  | ACU-5/CU-5 - CLICK & COLLECT CEILING CASSETTE |  | AS3000 MANDATORY TESTS
|  | ACU-1 - TEAM RM/LOCKER PAC UNIT |  | AS3000 MANDATORY TESTS
|  | ACU-3 - BAKERY PAC UNIT |  | AS3000 MANDATORY TESTS
|  | HP-1 - HEAT PUMP 1 |  | AS3000 MANDATORY TESTS
|  | HP-2 - HEAT PUMP 2 |  | AS3000 MANDATORY TESTS
|  | C-HWP-1 |  | AS3000 MANDATORY TESTS
|  | C-HWP-2 |  | AS3000 MANDATORY TESTS
|  | TEF-1 STAFF TOILETS |  | AS3000 MANDATORY TESTS
|  | EF-3 BOH VENTILATION |  | AS3000 MANDATORY TESTS
|  | EF-4 BOH VENTILATION |  | AS3000 MANDATORY TESTS
|  | EF-6 CHICKEN OVEN EXHAUST |  | AS3000 MANDATORY TESTS
|  | EF-10 FISH PREP |  | AS3000 MANDATORY TESTS
|  | SAF-2 CHICKEN OVEN MAKEUP |  | AS3000 MANDATORY TESTS
|  | SAF-4 PRODUCE PREP SUPPLY |  | AS3000 MANDATORY TESTS
ENERGISATION/TESTING
|  | AHU-1 |  | Energisation and Testing from switchboard
|  | AHU-2 |  | Energisation and Testing from switchboard
|  | ACU-5/CU-5 - CLICK & COLLECT CEILING CASSETTE |  | Energisation and Testing from switchboard
|  | ACU-1 - TEAM RM/LOCKER PAC UNIT |  | Energisation and Testing from switchboard
|  | ACU-3 - BAKERY PAC UNIT |  | Energisation and Testing from switchboard
|  | HP-1 - HEAT PUMP 1 |  | Energisation and Testing from switchboard
|  | HP-2 - HEAT PUMP 2 |  | Energisation and Testing from switchboard
|  | C-HWP-1 |  | Energisation and Testing from switchboard
|  | C-HWP-2 |  | Energisation and Testing from switchboard
|  | TEF-1 STAFF TOILETS |  | Energisation and Testing from switchboard
|  | EF-3 BOH VENTILATION |  | Energisation and Testing from switchboard
|  | EF-4 BOH VENTILATION |  | Energisation and Testing from switchboard
|  | EF-6 CHICKEN OVEN EXHAUST |  | Energisation and Testing from switchboard
|  | EF-10 FISH PREP |  | Energisation and Testing from switchboard
|  | SAF-2 CHICKEN OVEN MAKEUP |  | Energisation and Testing from switchboard
|  | SAF-4 PRODUCE PREP SUPPLY |  | Energisation and Testing from switchboard
HANDOVER
HANDOVER CHECKLIST
|  |  | MSSB-1 | Switchboard Handover
|  |  | AS-INSTALLED MANUAL | AS-INSTALLED MANUAL

## Equipment COmmissioning
type | name | values
checklist | Main Controller BMS |  | v | name | values
checkpoint | Controller and cards online |  | Checklist | Supermarket Plantroom Fan Commissioning
checkpoint | Cat5 connected to network |  | checkpoint | Plantroom Temp reading
|  |  | checkpoint | Plantrrom PB tested
type | name | values | checkpoint | Refrigeration interlock tested with Ref. contractor
checklist | Central Controller Commissioning checklist |  | checkpoint | Plantroom fan operation tested
checkpoint | Power supply tested |  | checkpoint | All labels installed
checkpoint | Central controller online
v | name | values
Checklist | VSD/EC FAN Commissioning Checklist
checkpoint | VSD programmed to equipment specs
checkpoint | AOM operation
checkpoint | I/O's tested
checkpoint | Speed tested
type | name | values
Checklist | DOL FAN Commissioning Checklist
checkpoint | AOM operation
checkpoint | I/O's tested
checkpoint | Notes
type | name | values
Checklist | PAC Unit Commissioning Checklist
checkpoint | AOM operation
checkpoint | Field sensors checked (zone, supply etc)
checkpoint | Cool/Heat stages tested
checkpoint | Economy cycle tested
checkpoint | Minimum OA tested
checkpoint | Notes
type | name | values
VRF Condensing unit Commissioning Checklist
checkpoint | Check all terminations
checkpoint | Power supply Tested Voltage
checkpoint | AMP Draw Tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | VRF FCU Commissioning Checklist
checkpoint | Check all terminations
checkpoint | Power supply Tested Voltage
checkpoint | AMP Draw Tested
checkpoint | Controller Online
checkpoint | Heat tested
checkpoint | Cool Tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | EC FAN Commissioning Checklist
checkpoint | Power supply tested Voltage
checkpoint | AOM, local switch tested
checkpoint | Run light tested
checkpoint | Fault light tested
checkpoint | Speed tested
checkpoint | Fan rotation tested
checkpoint | AMP Draw tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | WC FCU Commissioning checklist
checkpoint | Check all terminations
checkpoint | Power supply Tested
checkpoint | Space temp Tested
checkpoint | Supply air temp Tested
checkpoint | Cooling Valve Tested
checkpoint | Heating Valve Tested
checkpoint | Air DP Tested
checkpoint | SAF Enable Tested
checkpoint | AMP Draw tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | AHPB Commissioning
checkpoint | AHPB operating
checkpoint | Neon working
checkpoint | Label installed
type | name | values
Checklist | SPLIT AC Commissioning Checklist
checkpoint | Check all terminations
checkpoint | Power supply to condensing unit Voltage
checkpoint | Power on indoor unit
checkpoint | Local controller operational
checkpoint | Cool Tested
checkpoint | Heat Tested
checkpoint | AMP draw tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | FAN Commissioning Checklist
checkpoint | Power supply tested Voltage
checkpoint | Fan rotation tested
checkpoint | Local switch tested
checkpoint | Fan rotation tested
checkpoint | AMP Draw tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | FAN PBO Commissioning Checklist
checkpoint | Power supply tested Voltage
checkpoint | Fan rotation tested
checkpoint | Local switch tested
checkpoint | Fan rotation tested
checkpoint | AMP Draw tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | SEF VSD FAN Commissioning Checklist
checkpoint | Power supply tested Voltage
checkpoint | Start relay tested
checkpoint | Firemans Start tested
checkpoint | Firemans Stop tested
checkpoint | Run Proof tested
checkpoint | Fault Tested
checkpoint | Speed tested
checkpoint | Fan rotation tested
checkpoint | AMP Draw tested
checkpoint | Fire label and padlock installed

## DELAP ITP
type | name | values
checklist | MSSB CONDITION
checkpoint | General condition (with photos)
checkpoint | Lockouts
checkpoint | Lamp test
checkpoint | GFA present and operational
checkpoint | Data outlet present for BMS
checkpoint | Drawings avaliable
checkpoint | Clearance to AS3000
checkpoint | Location of MSSB
type | name | values
checklist | EXISTING EQUIPMENT
checkpoint | Equipment ID
checkpoint | Circuit breaker/fuse and rating
checkpoint | Cable size/type
checkpoint | Starter- Type (DOL/VSD/EC)
checkpoint | AOM operation
checkpoint | Run/Fault light operation
checkpoint | AMP Rating
checkpoint | AMP Draw
checkpoint | Rotation
checkpoint | Location
checkpoint | Dampers installed & operational
checkpoint | Photo
checkpoint | Operational Y/N, comments

## Switchboard ITP
type | name | values | type | name | values
Checklist | Switchboard Installation |  | Checklist | Switchboard Fit-off
checkpoint | Wall Avaliable for Mounting Switchboard |  | checkpoint | All field cabling terminated
checkpoint | Switchboard Installed on Wall |  | checkpoint | Fire Signal supplied by others and terminated
checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | checkpoint | Sub-mains supplied by others and terminated
|  |  | checkpoint | BMS cables installed and terminated
|  |  | checkpoint | All Field Tests completed
|  |  | checkpoint | Ready for Energisation
type | name | values
Checklist | Switchboard Energisation |  | type | name | values
checkpoint | All field cabling terminated |  | Checklist | Switchboard Commissioning
checkpoint | All field tests completed |  | checkpoint | All circuits operational
checkpoint | Power provided at Main Switch and tested |  | checkpoint | Power meter tested
|  |  | checkpoint | Fire Trip Tested
type | name | values
Checklist | BMS Cubicle Installation |  | type | name | values
checkpoint | Wall Avaliable for Mounting Switchboard |  | Checklist | BMS Cubicle Fit-off
checkpoint | Cubicle Installed on Wall |  | checkpoint | All BMS cabling terminated
checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | checkpoint | Network cabling terminated
|  |  | checkpoint | Ready for power
|  |  | type | name | values
|  |  | Checklist | Switchboard Handover
type | name | values | checkpoint | Fire Trip tested for correct operation of all equipment
Checklist | BMS Cubicle Commissioning |  | checkpoint | All labels installed
checkpoint | BMS Cubicle powered up |  | checkpoint | As-installed Drawings and legend in MSSB
checkpoint | All Cards Online |  | checkpoint | All penetrations sealed
checkpoint | All labels, drawings etc installed |  | checkpoint | MSSB cleaned (photos)
checkpoint | BMS Cubicle cleaned out and ready for Handover |  | Checkpoint | Notes
type | name | values
Checklist | Fire Control Panel Installation
checkpoint | Wall Avaliable for Mounting Switchboard |  | type | name | values
checkpoint | Cubicle Installed on Wall |  | Checklist | Fire Control Panel Fit-off
checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | checkpoint | All interconnecting cabling to MSSB installed and terminated
|  |  | checkpoint | Fire cabling by others installed and terminated
type | name | values
Checklist | Fire Control Panel Commissioning
checkpoint | All fire relays and points test with fire contractor
checkpoint | All labels, drawings etc installed
checkpoint | Fire Control Panel cleaned out and ready for Handover

## Rough-in ITP
type | name | values
checklist | Central Controller Rough In checklist
checkpoint | All transmission cabling installed
checkpoint | Central controller cable roughed in to correct wall position
type | name | values
checklist | Cable Tray Install Checklist
checkpoint | Hangars Installed
checkpoint | Cable Tray Installed
checkpoint | Bolted down, ready for rough-in
type | name | values
Checklist | STANDARD EQUIPMENT PBO Rough-in Checklist
checkpoint | Equipment installed in final position
checkpoint | Isolator installed by others
checkpoint | Control cabling roughed in
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in Checklist
checkpoint | Equipment installed in final position
checkpoint | Power cabling roughed in
checkpoint | Control cabling roughed in
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
Checklist | Essential FAN Rough-in Checklist
checkpoint | Roof penetration marked out
checkpoint | Fire Rated Supply rouged-in
checkpoint | Fire Rated Control cable roughed-in
checkpoint | Stainless Steel cable ties installed
checkpoint | Cables through roof
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
VRF Condensing unit Rough In Checklist
checkpoint | Condensing unit installed in final position
checkpoint | Power supply roughed in
checkpoint | Transmission/Interconnecting cabling Roughed In
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | VRF FCU/BB Rough-in Checklist
checkpoint | FCU/BB Installed
checkpoint | Transmission cabling Roughed In
checkpoint | Hard-wired controller Roughed In
checkpoint | Floor marked for plasterer
type | name | values
Checklist | SPLIT AC Rough-In Checklist
checkpoint | Area ready & accessible
checkpoint | Outdoor unit installed in final position
checkpoint | Power supply to Outdoor unit roughed in
checkpoint | Interconnecting cabling installed
checkpoint | Hard-wired controller roughed in
checkpoint | Floor marked for plasterer
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | Remote sensor Rough In checklist
checkpoint | Wall installed
checkpoint | Remote sensor cable roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | BMS Zone Sensor/AHPB Rough-in Checklist
checkpoint | Wall installed
checkpoint | 3 pair cable roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | Remote Sensor/AHPB Rough-in Checklist
checkpoint | Wall installed
checkpoint | Remote sensor and 2 pair cable roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | BMS Zone Sensor Rough In checklist
checkpoint | Wall installed
checkpoint | 1 pair cable roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | AHPB Rough in Checklist
checkpoint | Wall installed
checkpoint | 2 pair cable roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | DOL FAN Rough-in Checklist
checkpoint | Fan Installed
checkpoint | Local switch roughed in
checkpoint | Cables through roof
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | DOL FAN PBO Rough-in Checklist
checkpoint | Fan Installed
checkpoint | Isolator installed by others
checkpoint | Local switch roughed in
checkpoint | Cables through roof
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values

## Fitoff ITP
type | name | values
checklist | Central Controller Fit off checklist |  | Central Controller Fit off checklist
checkpoint | All transmission cabling and interfcae cards installed and fitoff
checkpoint | Central controller controller Fit off to correct wall position |  | VSD FAN PBO Fit off Checklist
VRF Condensing unit PBO Fit off Checklist
type | name | values | VSD FAN Fit off Checklist
Checklist | STANDARD EQUIPMENT Fit off Checklist |  | EC FAN Rough-in Checklist
checkpoint | Power supply terminated |  | Remote sensor Fit off checklist
checkpoint | Control cable fit off |  | BMS Zone Sensor Fit off checklist
checkpoint | Ready for AS3000 pre-energisation tests |  | Remote Sensor/AHPB Fit off Checklist
checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | SPLIT AC Fit off Checklist
AHPB Fit off Checklist
VRF FCU PBO Fit off Checklist
type | name | values | VSD FAN Fit off Checklist
Checklist | VSD FAN/PUMP Fit off Checklist |  | EC FAN Rough-in Checklist
checkpoint | VSD installed |  | WC FCU Fit off checklist
checkpoint | Power supply terminated/Isolator installed |  | Remote sensor Fit off checklist
checkpoint | EMC cable fit off |  | BMS Zone Sensor/AHPB Fit off Checklist
checkpoint | Control cable fit off |  | BMS Zone Sensor Fit off checklist
checkpoint | Ready for energisation |  | Remote Sensor/AHPB Fit off Checklist
checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | SPLIT AC Fit off Checklist
AHPB Fit off Checklist
type | name | values
Checklist | EC FAN Fit off Checklist
checkpoint | Power supply terminated
checkpoint | Control cable fit off
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | SEF VSD FAN Fitoff Checklist
checkpoint | VSD installed
checkpoint | Power supply terminated
checkpoint | EMC cable fit off
checkpoint | Control cable fit off
checkpoint | Ready for energisation
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
VRF Condensing unit Fitoff Checklist
checkpoint | Condensing unit installed
checkpoint | Isolator and power supply installed
checkpoint | Power supply fit off
checkpoint | Transmission cabling Fit off
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | VRF FCU Fit off Checklist
checkpoint | VRF Indoor unit installed
checkpoint | Isolator and power supply installed
checkpoint | Power supply fit off
checkpoint | Wall plastered/painted
checkpoint | Hard-wired controller fit off both ends
checkpoint | Transmission cabling Fit off
checkpoint | Interface card installed
checkpoint | OA Damper installed and wired
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | SPLIT AC Fit off Checklist
checkpoint | Outdoor unit installed in final position and piped
checkpoint | Power supply to condensing unit Fit off
checkpoint | Interconnecting cabling Fit off
checkpoint | Local thermostat Fit off
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | WC FCU Fit off checklist
checkpoint | FCU installed in final location
checkpoint | Power supply fit off
checkpoint | Wall sensors fit-off
checkpoint | All control points fit-off (Valves, sensors etc.)
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | Remote sensor Fit off checklist
checkpoint | Wall plastered/painted
checkpoint | Remote sensor cable Fit off on wall
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | BMS Control Point Wall Mounted off Checklist
checkpoint | Wall plastered/painted
checkpoint | Fit off on wall
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | BMS Control Point Field off Checklist
checkpoint | Control Point fitoff
checkpoint | Any penetrations sealed
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
Checklist | DOL FAN PBO Fit-off Checklist
checkpoint | Fan Fitoff
checkpoint | Local switch fitoff
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean

## AS3000 TESTS
type | name | values
checklist | AS3000 MANDATORY TESTS |  | Circuit Energisation from switchboard checklist
checkpoint | Continuity
checkpoint | Insulation resistance
checkpoint | Polarity
checkpoint | Correct circuit connects
checkpoint | Fault loop
checkpoint | Operation of RCD's
checkpoint | All cabling re-terminated, ready for energisation

## Energisation ITP
type | name | values
checklist | Energisation and Testing from switchboard |  | Circuit Energisation from switchboard checklist
checkpoint | Power cable terminated at switchboard
checkpoint | Power cable terminated at Equipment
checkpoint | All AS3000 Tests complete and passed
checkpoint | Circuit energised
checkpoint | Voltage Tested at equipment
checkpoint | Amp Draw
checkpoint | Overload setting
checkpoint | Operation/Rotation tested with local controls
checkpoint | All labels installed at equipment
checkpoint | Ensure all rubbish and materials have been picked up and area is clean (photo)
type | name | values
checklist | Circuit Energisation from Isolator checklist
checkpoint | Isolator installed in correct position
checkpoint | Power cable terminated by others
checkpoint | Power cable terminated at Equipment
checkpoint | All AS3000 Tests complete and passed
checkpoint | Circuit energised by others
checkpoint | Voltage Tested at equipment

## HANDOVER ITP
type | name | values
Checklist | Switchboard Handover
checkpoint | Fire Trip tested for correct operation of all equipment
checkpoint | All labels installed
checkpoint | As-installed Drawings and legend in MSSB
checkpoint | All penetrations sealed
checkpoint | MSSB cleaned (photos)
Checkpoint | Notes
type | name | values
Checklist | AS-INSTALLED MANUAL
checkpoint | Electrical Certificate
checkpoint | As-installed Drawings
checkpoint | Legend
checkpoint | Thermal scan
checkpoint | BMS Commissioning Sheet