## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Main Controller BMS | [5 empty] | Equipment Commissioning - Main Controller BMS Checklist
checkpoint | Controller and cards online
checkpoint | Cat5 connected to network
checklist-flat | Central Controller Commissioning | [5 empty] | Equipment Commissioning - Central Controller Commissioning Checklist
checkpoint | Power supply tested
checkpoint | Central controller online
checklist-flat | DOL FAN Commissioning | [5 empty] | Equipment Commissioning - DOL FAN Commissioning Checklist
checkpoint | AOM operation
checkpoint | I/O's tested
checkpoint | Notes
checklist-flat | PAC Unit Commissioning | [5 empty] | Equipment Commissioning - PAC Unit Commissioning Checklist
checkpoint | AOM operation
checkpoint | Field sensors checked (zone, supply etc)
checkpoint | Cool/Heat stages tested
checkpoint | Economy cycle tested
checkpoint | Minimum OA tested
checkpoint | Notes
checklist-flat | VRF Condensing unit Commissioning | [5 empty] | Equipment Commissioning - VRF Condensing unit Commissioning Checklist
checkpoint | Check all terminations
checkpoint | Power supply Tested Voltage
checkpoint | AMP Draw Tested
checkpoint | Labels installed on all equipment
checklist-flat | VRF FCU Commissioning | [5 empty] | Equipment Commissioning - VRF FCU Commissioning Checklist
checkpoint | Check all terminations
checkpoint | Power supply Tested Voltage
checkpoint | AMP Draw Tested
checkpoint | Controller Online
checkpoint | Heat tested
checkpoint | Cool Tested
checkpoint | Labels installed on all equipment
checklist-flat | EC FAN Commissioning | [5 empty] | Equipment Commissioning - EC FAN Commissioning Checklist
checkpoint | Power supply tested Voltage
checkpoint | AOM, local switch tested
checkpoint | Run light tested
checkpoint | Fault light tested
checkpoint | Speed tested
checkpoint | Fan rotation tested
checkpoint | AMP Draw tested
checkpoint | Labels installed on all equipment
checklist-flat | WC FCU Commissioning | [5 empty] | Equipment Commissioning - WC FCU Commissioning Checklist
checkpoint | Check all terminations
checkpoint | Power supply Tested
checkpoint | Space temp Tested
checkpoint | Supply air temp Tested
checkpoint | Cooling Valve Tested
checkpoint | Heating Valve Tested
checkpoint | Air DP Tested
checkpoint | SAF Enable Tested
checkpoint | AMP Draw tested
checkpoint | Labels installed on all equipment
checklist-flat | AHPB Commissioning | [5 empty] | Equipment Commissioning - AHPB Commissioning Checklist
checkpoint | AHPB operating
checkpoint | Neon working
checkpoint | Label installed
checklist-flat | SPLIT AC Commissioning | [5 empty] | Equipment Commissioning - SPLIT AC Commissioning Checklist
checkpoint | Check all terminations
checkpoint | Power supply to condensing unit Voltage
checkpoint | Power on indoor unit
checkpoint | Local controller operational
checkpoint | Cool Tested
checkpoint | Heat Tested
checkpoint | AMP draw tested
checkpoint | Labels installed on all equipment
checklist-flat | FAN Commissioning | [5 empty] | Equipment Commissioning - FAN Commissioning Checklist
checkpoint | Power supply tested Voltage
checkpoint | Fan rotation tested
checkpoint | Local switch tested
checkpoint | Fan rotation tested
checkpoint | AMP Draw tested
checkpoint | Labels installed on all equipment
checklist-flat | FAN PBO Commissioning | [5 empty] | Equipment Commissioning - FAN PBO Commissioning Checklist
checkpoint | Power supply tested Voltage
checkpoint | Fan rotation tested
checkpoint | Local switch tested
checkpoint | Fan rotation tested
checkpoint | AMP Draw tested
checkpoint | Labels installed on all equipment
checklist-flat | SEF VSD FAN Commissioning | [5 empty] | Equipment Commissioning - SEF VSD FAN Commissioning Checklist
checkpoint | Power supply tested Voltage
checkpoint | Start relay tested
checkpoint | Firemans Start tested
checkpoint | Firemans Stop tested
checkpoint | Run Proof tested
checkpoint | Fault Tested
checkpoint | Speed tested
checkpoint | Fan rotation tested
checkpoint | AMP Draw tested
checkpoint | Fire label and padlock installed
checklist-flat | Supermarket Plantroom Fan Commissioning | [5 empty] | Equipment Commissioning - Supermarket Plantroom Fan Commissioning Checklist
checkpoint | Plantroom Temp reading
checkpoint | Plantrrom PB tested
checkpoint | Refrigeration interlock tested with Ref. contractor
checkpoint | Plantroom fan operation tested
checkpoint | All labels installed
checklist-flat | MSSB CONDITION | [5 empty] | DELAP ITP - MSSB CONDITION Checklist
checkpoint | General condition (with photos)
checkpoint | Lockouts
checkpoint | Lamp test
checkpoint | GFA present and operational
checkpoint | Data outlet present for BMS
checkpoint | Drawings avaliable
checkpoint | Clearance to AS3000
checkpoint | Location of MSSB
checklist-flat | EXISTING EQUIPMENT | [5 empty] | DELAP ITP - EXISTING EQUIPMENT Checklist
checkpoint | Equipment ID
checkpoint | Circuit breaker/fuse and rating
checkpoint | Cable size/type
checkpoint | Starter- Type (DOL/VSD/EC)
checkpoint | AOM operation
checkpoint | Run/Fault light operation
checkpoint | AMP Rating
checkpoint | AMP Draw
checkpoint | Rotation
checkpoint | Location
checkpoint | Dampers installed & operational
checkpoint | Photo
checkpoint | Operational Y/N, comments
checklist-flat | Switchboard Installation | [5 empty] | Switchboard ITP - Switchboard Installation Checklist
checkpoint | Wall Avaliable for Mounting Switchboard
checkpoint | Switchboard Installed on Wall
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | Switchboard Energisation | [5 empty] | Switchboard ITP - Switchboard Energisation Checklist
checkpoint | All field cabling terminated
checkpoint | All field tests completed
checkpoint | Power provided at Main Switch and tested
checklist-flat | BMS Cubicle Installation | [5 empty] | Switchboard ITP - BMS Cubicle Installation Checklist
checkpoint | Wall Avaliable for Mounting Switchboard
checkpoint | Cubicle Installed on Wall
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | BMS Cubicle Commissioning | [5 empty] | Switchboard ITP - BMS Cubicle Commissioning Checklist
checkpoint | BMS Cubicle powered up
checkpoint | All Cards Online
checkpoint | All labels, drawings etc installed
checkpoint | BMS Cubicle cleaned out and ready for Handover
checklist-flat | Fire Control Panel Installation | [5 empty] | Switchboard ITP - Fire Control Panel Installation Checklist
checkpoint | Wall Avaliable for Mounting Switchboard
checkpoint | Cubicle Installed on Wall
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | Fire Control Panel Commissioning | [5 empty] | Switchboard ITP - Fire Control Panel Commissioning Checklist
checkpoint | All fire relays and points test with fire contractor
checkpoint | All labels, drawings etc installed
checkpoint | Fire Control Panel cleaned out and ready for Handover
checklist-flat | Switchboard Fit-off | [5 empty] | Switchboard ITP - Switchboard Fit-off Checklist
checkpoint | All field cabling terminated
checkpoint | Fire Signal supplied by others and terminated
checkpoint | Sub-mains supplied by others and terminated
checkpoint | BMS cables installed and terminated
checkpoint | All Field Tests completed
checkpoint | Ready for Energisation
checklist-flat | Switchboard Commissioning | [5 empty] | Switchboard ITP - Switchboard Commissioning Checklist
checkpoint | All circuits operational
checkpoint | Power meter tested
checkpoint | Fire Trip Tested
checklist-flat | BMS Cubicle Fit-off | [5 empty] | Switchboard ITP - BMS Cubicle Fit-off Checklist
checkpoint | All BMS cabling terminated
checkpoint | Network cabling terminated
checkpoint | Ready for power
checklist-flat | Switchboard Handover | [5 empty] | Switchboard ITP - Switchboard Handover Checklist
checkpoint | Fire Trip tested for correct operation of all equipment
checkpoint | All labels installed
checkpoint | As-installed Drawings and legend in MSSB
checkpoint | All penetrations sealed
checkpoint | MSSB cleaned (photos)
checkpoint | Notes
checklist-flat | Fire Control Panel Fit-off | [5 empty] | Switchboard ITP - Fire Control Panel Fit-off Checklist
checkpoint | All interconnecting cabling to MSSB installed and terminated
checkpoint | Fire cabling by others installed and terminated
checklist-flat | Central Controller Rough In | [5 empty] | Rough-in ITP - Central Controller Rough In checklist
checkpoint | All transmission cabling installed
checkpoint | Central controller cable roughed in to correct wall position
checklist-flat | Cable Tray Install | [5 empty] | Rough-in ITP - Cable Tray Install Checklist
checkpoint | Hangars Installed
checkpoint | Cable Tray Installed
checkpoint | Bolted down, ready for rough-in
checklist-flat | STANDARD EQUIPMENT PBO Rough-in | [5 empty] | Rough-in ITP - STANDARD EQUIPMENT PBO Rough-in Checklist
checkpoint | Equipment installed in final position
checkpoint | Isolator installed by others
checkpoint | Control cabling roughed in
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in | [5 empty] | Rough-in ITP - STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in Checklist
checkpoint | Equipment installed in final position
checkpoint | Power cabling roughed in
checkpoint | Control cabling roughed in
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | Essential FAN Rough-in | [5 empty] | Rough-in ITP - Essential FAN Rough-in Checklist
checkpoint | Roof penetration marked out
checkpoint | Fire Rated Supply rouged-in
checkpoint | Fire Rated Control cable roughed-in
checkpoint | Stainless Steel cable ties installed
checkpoint | Cables through roof
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | VRF Condensing unit Rough In | [5 empty] | Rough-in ITP - VRF Condensing unit Rough In Checklist
checkpoint | Condensing unit installed in final position
checkpoint | Power supply roughed in
checkpoint | Transmission/Interconnecting cabling Roughed In
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | VRF FCU/BB Rough-in | [5 empty] | Rough-in ITP - VRF FCU/BB Rough-in Checklist
checkpoint | FCU/BB Installed
checkpoint | Transmission cabling Roughed In
checkpoint | Hard-wired controller Roughed In
checkpoint | Floor marked for plasterer
checklist-flat | SPLIT AC Rough-In | [5 empty] | Rough-in ITP - SPLIT AC Rough-In Checklist
checkpoint | Area ready & accessible
checkpoint | Outdoor unit installed in final position
checkpoint | Power supply to Outdoor unit roughed in
checkpoint | Interconnecting cabling installed
checkpoint | Hard-wired controller roughed in
checkpoint | Floor marked for plasterer
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | Remote sensor Rough In | [5 empty] | Rough-in ITP - Remote sensor Rough In Checklist
checkpoint | Wall installed
checkpoint | Remote sensor cable roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | BMS Zone Sensor/AHPB Rough-in | [5 empty] | Rough-in ITP - BMS Zone Sensor/AHPB Rough-in Checklist
checkpoint | Wall installed
checkpoint | 3 pair cable roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | Remote Sensor/AHPB Rough-in | [5 empty] | Rough-in ITP - Remote Sensor/AHPB Rough-in Checklist
checkpoint | Wall installed
checkpoint | Remote sensor and 2 pair cable roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | BMS Zone Sensor Rough In | [5 empty] | Rough-in ITP - BMS Zone Sensor Rough In Checklist
checkpoint | Wall installed
checkpoint | 1 pair cable roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | AHPB Rough in | [5 empty] | Rough-in ITP - AHPB Rough in Checklist
checkpoint | Wall installed
checkpoint | 2 pair cable roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | DOL FAN Rough-in | [5 empty] | Rough-in ITP - DOL FAN Rough-in Checklist
checkpoint | Fan Installed
checkpoint | Local switch roughed in
checkpoint | Cables through roof
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | DOL FAN PBO Rough-in | [5 empty] | Rough-in ITP - DOL FAN PBO Rough-in Checklist
checkpoint | Fan Installed
checkpoint | Isolator installed by others
checkpoint | Local switch roughed in
checkpoint | Cables through roof
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | VSD FAN/PUMP Fit off | [5 empty] | Fitoff ITP - VSD FAN/PUMP Fit off Checklist
checkpoint | VSD installed
checkpoint | Power supply terminated/Isolator installed
checkpoint | EMC cable fit off
checkpoint | Control cable fit off
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | EC FAN Fit off | [5 empty] | Fitoff ITP - EC FAN Fit off Checklist
checkpoint | Power supply terminated
checkpoint | Control cable fit off
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | SEF VSD FAN Fitoff | [5 empty] | Fitoff ITP - SEF VSD FAN Fitoff Checklist
checkpoint | VSD installed
checkpoint | Power supply terminated
checkpoint | EMC cable fit off
checkpoint | Control cable fit off
checkpoint | Ready for energisation
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | VRF Condensing unit Fitoff | [5 empty] | Fitoff ITP - VRF Condensing unit Fitoff Checklist
checkpoint | Condensing unit installed
checkpoint | Isolator and power supply installed
checkpoint | Power supply fit off
checkpoint | Transmission cabling Fit off
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | VRF FCU Fit off | [5 empty] | Fitoff ITP - VRF FCU Fit off Checklist
checkpoint | VRF Indoor unit installed
checkpoint | Isolator and power supply installed
checkpoint | Power supply fit off
checkpoint | Wall plastered/painted
checkpoint | Hard-wired controller fit off both ends
checkpoint | Transmission cabling Fit off
checkpoint | Interface card installed
checkpoint | OA Damper installed and wired
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | SPLIT AC Fit off | [5 empty] | Fitoff ITP - SPLIT AC Fit off Checklist
checkpoint | Outdoor unit installed in final position and piped
checkpoint | Power supply to condensing unit Fit off
checkpoint | Interconnecting cabling Fit off
checkpoint | Local thermostat Fit off
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | WC FCU Fit off | [5 empty] | Fitoff ITP - WC FCU Fit off Checklist
checkpoint | FCU installed in final location
checkpoint | Power supply fit off
checkpoint | Wall sensors fit-off
checkpoint | All control points fit-off (Valves, sensors etc.)
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | Remote sensor Fit off | [5 empty] | Fitoff ITP - Remote sensor Fit off Checklist
checkpoint | Wall plastered/painted
checkpoint | Remote sensor cable Fit off on wall
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | BMS Control Point Wall Mounted off | [5 empty] | Fitoff ITP - BMS Control Point Wall Mounted off Checklist
checkpoint | Wall plastered/painted
checkpoint | Fit off on wall
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | BMS Control Point Field off | [5 empty] | Fitoff ITP - BMS Control Point Field off Checklist
checkpoint | Control Point fitoff
checkpoint | Any penetrations sealed
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | DOL FAN PBO Fit-off | [5 empty] | Fitoff ITP - DOL FAN PBO Fit-off Checklist
checkpoint | Fan Fitoff
checkpoint | Local switch fitoff
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | AS3000 MANDATORY TESTS | [5 empty] | AS3000 MANDATORY TESTS
checkpoint | Continuity
checkpoint | Insulation resistance
checkpoint | Polarity
checkpoint | Correct circuit connects
checkpoint | Fault loop
checkpoint | Operation of RCD's
checkpoint | All cabling re-terminated, ready for energisation
checklist-flat | Energisation and Testing from switchboard | [5 empty] | Energisation ITP - Energisation and Testing from switchboard Checklist
checkpoint | Power cable terminated at switchboard
checkpoint | Power cable terminated at Equipment
checkpoint | All AS3000 Tests complete and passed
checkpoint | Circuit energised
checkpoint | Voltage Tested at equipment
checkpoint | Amp Draw
checkpoint | Overload setting
checkpoint | Operation/Rotation tested with local controls
checkpoint | All labels installed at equipment
checkpoint | Ensure all rubbish and materials have been picked up and area is clean (photo)
checklist-flat | Circuit Energisation from Isolator | [5 empty] | Energisation ITP - Circuit Energisation from Isolator Checklist
checkpoint | Isolator installed in correct position
checkpoint | Power cable terminated by others
checkpoint | Power cable terminated at Equipment
checkpoint | All AS3000 Tests complete and passed
checkpoint | Circuit energised by others
checkpoint | Voltage Tested at equipment
checklist-flat | Switchboard Handover | [5 empty] | HANDOVER ITP - Switchboard Handover Checklist
checkpoint | Fire Trip tested for correct operation of all equipment
checkpoint | All labels installed
checkpoint | As-installed Drawings and legend in MSSB
checkpoint | All penetrations sealed
checkpoint | MSSB cleaned (photos)
checkpoint | Notes
checklist-flat | AS-INSTALLED MANUAL | [5 empty] | HANDOVER ITP - AS-INSTALLED MANUAL Checklist
checkpoint | Electrical Certificate
checkpoint | As-installed Drawings
checkpoint | Legend
checkpoint | Thermal scan
checkpoint | BMS Commissioning Sheet