## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 0ab4163e-c8c8-4724-ae7a-3f607e5c8538 |  | checklist | Pre-Pour Checklist |  |  |  |  | Yes | Pre-Pour Checklist | 1c560aaf-d3c0-436e-b792-09534335ccb1
checkpoint-group | 71237582-3a25-4efc-8a32-b3e4e4d36436 |  | section | Product Detail
checkpoint-status | 4333faa5-c2a2-419e-b910-9350aa6a1d47 |  | checkpoint | Details
text | 8a2d6b97-6ca0-5d19-bbff-fc6eff68f50f |  | textbox | Product ID
text | 331e08a7-1ebb-5b3a-bbf4-d1c1f87e9b1b |  | textbox | Weight
text | 8e306097-3237-52a3-949c-0782ec8d2a0c |  | textbox | Manufacture Date
checkpoint-group | fc130f05-5623-438c-aae7-b05e04e23ce1 |  | section | Formwork
checkpoint-status | ad723b66-2003-4581-b4a4-95f9cd3457d5 |  | checkpoint | Check Length
text | d3cc0c48-0c7c-57db-a6d0-e69b140da55f |  | textbox | length
checkpoint-status | 588a3452-2c6e-437e-9a88-49dbad4e098b |  | checkpoint | Check Width
text | 3089d711-3eb3-56ff-9554-b1287e8801b9 |  | textbox | width
checkpoint-status | efb4ca93-c165-4251-bd74-c36d6000e9c3 |  | checkpoint | Check Thickness
text | 5d56b875-298a-5d6e-818b-6c6aa8661d71 |  | textbox | thickness
checkpoint-status | 1a8e3915-dbf1-48fb-82e5-c8d0d49852e8 |  | checkpoint | Check Diagnonal
checkpoint-status | 95d6ab43-6cb8-44f9-af04-887e532327ab |  | checkpoint | Sideform Trueness
checkpoint-status | 22eac8c4-07bb-4ab2-8c85-2e94cb3f4e6b |  | checkpoint | Magnets / Forms Secure
checkpoint-status | d8fd7fe8-67ea-4e84-871c-160a57149e99 |  | checkpoint | Splayed forms checked
checkpoint-status | 28411e45-3a65-420c-94bf-02bbbb34c3ec |  | checkpoint | Penotration dimensions checked
checkpoint-status | 671ffb8e-ef41-462a-b5f7-4ec8108b4aed |  | checkpoint | Curves / Radius Checked
checkpoint-status | 06f25685-01b5-4ffa-b481-723f52956de0 |  | checkpoint | Rebates size and location checked
checkpoint-status | 0022bb24-8aeb-4928-ae2a-c759970cc4b6 |  | checkpoint | Weather steps dimensions checked
checkpoint-status | bef1971e-b5d5-4e14-af31-c61d2b3621ce |  | checkpoint | Weather steps orientation checked
checkpoint-status | 6a523abb-30a6-4b5d-a8b0-01b49db68536 |  | checkpoint | Form release applied correctly
checkpoint-group | 1248e0e6-d9b5-4479-82bb-6a7ef3c0926b |  | section | Reinforcement
checkpoint-status | 95bb7804-b0dc-48cb-8af1-fefc91cd0415 |  | checkpoint | Reinforcement mat as per shop drawings
checkpoint-status | 476cb84e-4390-4a16-a028-973838ed199d |  | checkpoint | Reo Mat Orientation
checkpoint-status | 3439715a-5404-428c-a8ea-ea65a8870375 |  | checkpoint | Perimeter Bars Size Correct
checkpoint-status | 8c81e8bb-35f9-4e9d-bd81-7613742ac6e6 |  | checkpoint | Perimeter Bars No. Off Correct
checkpoint-status | f5d8745a-fa84-46ac-b9cf-edcddf6f53ea |  | checkpoint | Additional Bars Correct
checkpoint-status | 769de4c1-5735-402e-8732-66192e1cd3f7 |  | checkpoint | Reo Changes Noted
checkpoint-status | b6105f34-ad96-48b7-a1b8-af82b0909f36 |  | checkpoint | Reo Changes Passed By PM
checkpoint-status | 856d15f2-7d26-4294-a7c8-fa8cc9a54939 |  | checkpoint | COGS / Laps As Per SD
checkpoint-status | 8b733acb-29f4-4731-966f-acdb5e6e4023 |  | checkpoint | Any Splice 40 x Dia Min
checkpoint-status | 91b6b6c1-b10a-4806-8223-0aeb78f685af |  | checkpoint | Rebar Photos
checkpoint-group | 7e5b60d9-f482-43e4-8ece-eb4530d5b764 |  | section | Fixings / Cast Ins
checkpoint-status | 236e9e03-ac02-4ac8-a0cf-01401dd7bdcb |  | checkpoint | Details
text | 96a13377-bedf-5fe6-90dc-8d2c8aea8e6e |  | textbox | Strand Size
text | dede8aac-cf41-5415-8862-a78d961745f6 |  | textbox | Coil Id
text | 8cea9afa-90c6-55cb-b1bf-44122074d8d8 |  | textbox | Strand Photo
checkpoint-status | b0c05e99-c315-4145-8bbf-4f1a59fa46e4 |  | checkpoint | Ferrule Location Checked
checkpoint-status | 4f73175e-9175-4fcb-aa81-01925dbf77d2 |  | checkpoint | Ferrule Cross Bars Inserted
checkpoint-status | 3cc4c539-99e2-45e6-839d-0e5a49f1ce27 |  | checkpoint | Lifting Inserts as Per Lift Design
checkpoint-status | ae5ab204-d3f1-4f4d-8c3d-f7dfbc7f03c9 |  | checkpoint | Lifter Type correct
select | c0c92514-9c1c-5012-9e12-8c505e78fae3 |  | dropdown | Lifter Type | Leviat Edj Pro Mini 8.5T, Leviat Edj Pro Max 15T, Foot Anchor 1.3T, Foot Anchor 2.5T, Foot Anchor 5T, Foot Anchor 10T, Foot Anchor 20T
checkpoint-status | 3de314b4-0da6-4c49-8609-95a7a829499e |  | checkpoint | Lifting V Bars Inserted
checkpoint-status | 9303ec02-47c9-435f-b00e-1af94800eee0 |  | checkpoint | Cast Plates Per Design
checkpoint-status | 0a60a0d3-f465-466e-aeb8-d1249ffea401 |  | checkpoint | Cast Plate Location Checked
checkpoint-status | bcb76f99-5850-404b-9eec-8a64bca26a32 |  | checkpoint | Additional Cast Plate Bars Inserted
checkpoint-status | 2a3280f1-b8b9-4b44-8230-996227a5c996 |  | checkpoint | Starter Bars Correct Per SD
checkpoint-status | d56a1698-6525-41d5-8160-9ed714d760d9 |  | checkpoint | Pertruding Bars Orientation
checkpoint-status | b1d5daa5-a6b7-4ff9-91a6-6171c6b7757b |  | checkpoint | Grout Tube Size Checked
checkpoint-status | 60365f19-772f-407c-95af-65cd615cac47 |  | checkpoint | Grout Tube Exit Orientation Checked
checkpoint-status | 8cef0c00-0e0d-4914-b8bf-6e4c024aa74b |  | checkpoint | Grout Tube Photo
checkpoint-status | e45e9c7f-f306-4853-bffb-1879f39e1fba |  | checkpoint | Lifting Insert Photo
checkpoint-status | c4f4bad6-c511-4387-9322-15a4064151c1 |  | checkpoint | Cast In Plate Photo
checkpoint-status | bcaf0b6f-a0d1-4450-ba81-ae2853b2bf0c |  | checkpoint | Penetration Photo
checkpoint-group | 6775c555-3249-4f9a-95b3-cd2c5364f5d0 |  | section | Final Checks
checkpoint-status | b27dacd7-98ee-4e0e-a24e-95ba0b9634be |  | checkpoint | All SD Dimensions Shown
checkpoint-status | c0abe395-9906-4d98-931a-4590237e87b7 |  | checkpoint | Photo of For "Construction" Shop Drawing
checkpoint-status | f4d394f4-28b7-4848-a504-c73e867b339a |  | checkpoint | Panel ID Tag Placed
checkpoint-status | 32bde135-0fa8-43cd-80b3-9053211d8da7 |  | checkpoint | Product Cleared For Pouring
checkpoint-status | fc888160-e042-45b9-a600-c9d4b80190c3 |  | checkpoint | Inspector sign off attached below
checklist-flat | 6c034146-61bd-49aa-be43-a449c45ac8d1 |  | checklist | Transport Checklist |  |  |  |  | Yes | Transport Checklist | 60fe5619-da44-4f19-a07e-7dcc4ffb5461
checkpoint-no-status | 0faa0a2d-7ed7-47d8-b93f-eaa7551c2f20 |  | checkpoint | Details
text | 73c3f390-c154-553e-ac39-a8a1229394e4 |  | textbox | Shipment Number
text | 54bbc1f1-1cd6-5cda-b427-1f247c723efe |  | textbox | Shipment Date
text | 38f18811-2c33-5205-8533-9a024af52c37 |  | textbox | Install Date
text | 23bc02dc-f9ca-5a94-a61f-e3b7ba6162b7 |  | textbox | Time Requested Onsite
text | f7e917bc-62f5-59a9-a9a4-dd59c2015394 |  | textbox | Carrier
text | 579ed872-b384-5769-bca8-513ce31dfb6a |  | textbox | Delivery Driver Name
text | 0192f996-df66-58f0-b2a4-d8b6f501753c |  | textbox | Delivery Drivers Phone Number
text | 7b3efae9-9d46-5d54-a028-dd8ab32ab823 |  | textbox | Trailer Rego
checkpoint-status | 2436cde7-5040-431c-9f5e-6cbaa5f8e95e |  | checkpoint | Correct Products on Transport
checkpoint-status | cb4dbc40-ec2f-4435-b62d-ff4c073b7f99 |  | checkpoint | Safety Restraints
checkpoint-status | bc3048ab-1fbc-4584-9c5b-c5f66119d1df |  | checkpoint | Rego Photo
checkpoint-status | fba8dec4-29cb-4647-a38a-b21705c7c829 |  | checkpoint | Drivers Side Photo
checkpoint-status | b587c7a4-3cb9-491f-8e8f-4ef13d599074 |  | checkpoint | Passenger Side Photo
checkpoint-status | 0864fd77-74f3-470f-bce8-958d60068759 |  | checkpoint | Transport Safe To Leave Yard
checkpoint-status | efae3246-1196-4373-b3b6-584edb113c12 |  | checkpoint | Inspector sign off attached below
text | d1d025ed-08c7-57c0-9e12-64e8e96f73aa |  | textbox | Item Status
checklist-flat | 1c30f522-a026-486d-a84f-b10a03ef2f02 |  | checklist | Defects Checklist |  |  |  |  | Yes | Defects Checklist | 79c137ef-d0a5-4dee-8c31-1587cf240530
checkpoint-status | 527b4f3f-f3ec-449a-aac6-5b28bd73b1e8 |  | checkpoint | Details and photos below
checklist-flat | 593559b4-d0cf-454f-916d-b2ca07efd47e |  | checklist | Concrete Delivery Checklist |  |  |  |  | Yes | Concrete Delivery Checklist | 7b09e192-b963-45a7-870b-37a3266bd102
checkpoint-no-status | 592cb40a-40a3-495c-8cb3-7968eae2adbd |  | checkpoint | Details
text | 00d4fff8-8702-525a-bb16-2af29796b77c |  | textbox | Concrete Docket Number
text | 72d49f09-ca01-5ae9-8bf0-eef57f2d7a62 |  | textbox | Pour Date
text | 7906b908-03c3-5dc0-a0b2-b6cdc6cb0e5e |  | textbox | Time Batched
text | 50d87fea-5db7-5e9b-a18d-91e930eb101d |  | textbox | Load M3
checkpoint-status | f969e7af-20ef-4487-963d-c470a2d67dfb |  | checkpoint | Picture of Concrete Docket
checkpoint-status | 3799c218-8671-41b2-ac33-8b7c3a0fd8fd |  | checkpoint | Load size match order sheet
checkpoint-status | 28400e61-b2ab-48eb-8ac4-1f8a446c2c3a |  | checkpoint | Mix type match the order sheet
checkpoint-status | 47a6ad5d-dae3-4128-b7b8-7965ecbb7ad0 |  | checkpoint | Mix color match the order sheet
checkpoint-status | b9259093-0262-4fae-ba49-be674e4ba849 |  | checkpoint | MPa match the order sheet
text | ef16278c-b461-5ff1-abb1-0718380cc9fc |  | textbox | Concrete Strength |  |  | MPa
checkpoint-status | 06c16106-c31c-42a1-9d01-49f1d28796d7 |  | checkpoint | Spread / slump within range
text | c178acd7-a162-5912-aa03-600f2714cf75 |  | textbox | Spread / Slump in mm |  |  | mm
checkpoint-status | 2c14a410-ef01-4ef6-8ca3-963c09661c04 |  | checkpoint | Water Added (N/A if no)
text | 174650dd-de95-51b4-8ab7-e5b179cf6138 |  | textbox | Quantity of water added
checkpoint-status | 033ab66e-528f-48f9-b427-2be90e1cd10f |  | checkpoint | Concrete test taken (N/A if no)
checkpoint-status | 76cb840b-5fea-44e1-93a7-8f38b56287b3 |  | checkpoint | Picture of spread check before dispatch
checkpoint-status | 644e4a08-4619-4900-8321-8dcea55cdb2f |  | checkpoint | Inspector sign off attached below
checklist-flat | 54a90f31-efa0-45ac-b1e7-5729454f76f5 |  | checklist | Onsite Install Checklist |  |  |  |  | Yes | Onsite Install Checklist | 938348bc-7e11-4051-9ad5-7a2b8ce2f0cc
checkpoint-status | 9ec3c215-a904-453d-8499-bbefc9c1d2ce |  | checkpoint | All Electrical Equipment is tested and tagged.
boolean | 4ac7017e-3510-5a79-ad06-658e533a74a9 |  | tickbox | Small Hammer Drill
boolean | 34ea1e43-951d-5074-83aa-40a52df2b8df |  | tickbox | 20mm Bit
boolean | c8948549-b895-533d-87a7-273a759bc793 |  | tickbox | Mash Hammer
boolean | 527bd99f-a372-547d-9a4c-60ec2881199d |  | tickbox | Rattle Gun
boolean | 8c37fac3-66de-5882-8a6c-cd77f24f67be |  | tickbox | 30mm bit
boolean | 02450704-feaf-5d1c-b9a6-803662cfca37 |  | tickbox | 32mm bit
boolean | b996b4ed-b172-55ed-beb7-7ca0ad18fc81 |  | tickbox | Batteries & Charger
boolean | fff9dfb8-e3b8-5adf-b428-e220e11bda23 |  | tickbox | Extension Leads
boolean | 89075447-0f12-5136-a686-7ee570c1945d |  | tickbox | RCD Box
boolean | 6e7f0c75-39b4-5e26-8042-f764947d3968 |  | tickbox | Generator
boolean | f36cfee5-9de5-5ed7-972c-a1b3ce9cdf52 |  | tickbox | Level 2000mm
boolean | 5454b43b-3eb4-50c1-8fe2-d76f31d047f3 |  | tickbox | Berker Bar
boolean | 866444d6-40c1-5113-a749-d0b2dad880a5 |  | tickbox | 20mm Prop Bolts
boolean | cd4e927a-60e1-536f-a49a-d11c1fe28a3f |  | tickbox | PBI Bolts
boolean | b2d679a1-1a55-5235-8151-73b336e0656b |  | tickbox | Packers (20mm, 10mm, 5mm, 3mm, 2mm)
boolean | 305f8d79-2243-53bc-ab22-976123d5b37f |  | tickbox | Dowels
boolean | bf4d16cb-3346-591c-b3f9-1037490f7070 |  | tickbox | Stitch Plates
boolean | f337cc8c-141b-5280-b30c-eb2e99a8bcf6 |  | tickbox | Ladder/s
boolean | a88fe6ff-7bd3-503d-b96c-e94ef218cde1 |  | tickbox | Brace Locks & Brace Pins
boolean | 943b3a87-76da-517c-a5b3-fb1edd0b3747 |  | tickbox | Lifting Clutches
boolean | f4d020a7-c4d9-5839-b48e-36542ea89db6 |  | tickbox | Guide Rope
boolean | 7c1c0a86-9fe8-5a80-aeb8-8ddb08dd3a66 |  | tickbox | Release Rope
boolean | 279bd3a7-0f23-51c3-9c54-d0be1e3e9b04 |  | tickbox | Shovel
boolean | d32ecb34-f7c9-594e-83b8-3bf00bc0d556 |  | tickbox | Broom
boolean | e5a00ee3-2760-5b2a-ab04-f117925fd1e1 |  | tickbox | Fuel
checkpoint-status | 8a250c7e-5704-4bae-b39b-36e49f34f4d8 |  | checkpoint | Are any hazards impacting safe panel installation?
checkpoint-status | 7a6716a7-b097-447e-adf1-4efbf42ce7c4 |  | checkpoint | The Shipment of Precast panels match the Install Sequence
checkpoint-status | 6811f69e-be84-46a2-a215-b241e62ac4d2 |  | checkpoint | Panel numbers and location match as per the marking plan?
checkpoint-status | 8c396d5b-2f97-4a74-87e1-48a4741ff701 |  | checkpoint | Dowel pin set out and packer locations are as per drawings?
checkpoint-status | 5f6b719f-e3f9-4800-b0c4-1899d7c3f12a |  | checkpoint | Dowel Bars are correctly aligned, and the size and length are correct?
checkpoint-status | 27db8a0b-e505-4b62-ba86-e5e289e51066 |  | checkpoint | Is correct-size foam doughnuts used?
checkpoint-status | 63a80ed4-fdaf-460b-9597-a76048256610 |  | checkpoint | Are Panel R/L heights are correct?
checkpoint-status | f1fa6e9a-608b-4263-9f74-322aeb1f35c8 |  | checkpoint | The panels are Straight and free from any bows.
checkpoint-status | b54649e7-d62f-4e7a-abbd-98f8b1ad8956 |  | checkpoint | Ferrules, cast plates, rebates, and checkout are correct and as per drawings.
checkpoint-status | 710f31d6-704c-48f3-8d1b-1f3852bffa32 |  | checkpoint | Panel Props are secure and brace locking pins are all locked?
label | e9b392a7-bac0-593e-aba7-b6d712ea1ac4 |  | note | Take a photo of Props installed with pins and lock.
checkpoint-status | 8a98f717-6d49-4643-b92a-90b8bfa5c52d |  | checkpoint | Are Props erected between 45 - 60 degrees angle?
label | 28e25069-beca-56a8-a4f6-4e99f0f7c371 |  | note | Bracing in any alternative locations?
checkpoint-status | 95036c6b-3800-47a9-9778-c3b14ea53319 |  | checkpoint | Site Welding of Stichplates, Corner plates, and any other.
checklist-flat | 54bedb5b-298f-4b25-8593-da54ab1495ed |  | checklist | Grouting/Patching Checklist |  |  |  |  | Yes | Grouting/Patching Checklist | 99b8e5b9-951e-4118-bb7c-29284101b37d
checkpoint-status | d07b817e-0d00-4f96-8057-b87bab3e1107 |  | checkpoint | Have the required gear for works
boolean | ccda7f4a-e865-5d06-9b87-c98bbd998614 |  | tickbox | General Grout
boolean | f08c97cd-dee4-5d16-81bf-c70fc6313acd |  | tickbox | Light Weight
boolean | 744bbd6b-1887-596e-a8c8-dddf8af10f6a |  | tickbox | Fairing Coat
boolean | f010a600-b73e-5a55-819b-c194d1098596 |  | tickbox | Bucket
boolean | 75041bfc-15e2-522e-b0b4-ea67779f7db9 |  | tickbox | Mixer
boolean | c47af38c-8413-5831-818b-ef4e77a6f4b2 |  | tickbox | Water
boolean | 6616cad8-6072-527b-a015-148d9729a446 |  | tickbox | Scraper
boolean | 1da08cb4-09e6-5976-b87f-f14e037fade0 |  | tickbox | Trowel
boolean | 8aa8326d-136b-533e-91b4-531ea05e2aa2 |  | tickbox | Extension Leads
boolean | 59ec39ef-64ed-5944-9bc0-5782e099136e |  | tickbox | Ladder/s
boolean | 6b5f32ca-05a0-5b62-9995-241e15fe3a23 |  | tickbox | Sander
boolean | 8779c597-76e7-5907-84ae-de48f4211fe1 |  | tickbox | Sanding Discs
boolean | 672a0da9-0e69-5118-9986-98064bd951ae |  | tickbox | Batteries & Charger
boolean | 4fa521c8-93e3-54ce-b725-db0c0a38920a |  | tickbox | Generator
boolean | 36ff2621-5369-5a65-b8fe-417e394c493d |  | tickbox | Grinder
boolean | e3df2163-7a5a-5d7e-82d1-7b99ee5228f9 |  | tickbox | Caulk
boolean | 7a3c0cef-ff3f-5ee4-8bc7-0dfa8f494c88 |  | tickbox | Caulking Guns
boolean | db271ed1-90f4-5a06-b749-8cd6bc50c1eb |  | tickbox | Diamond Cutting Disc
boolean | 1cab87fa-5703-565a-b688-76f201957a31 |  | tickbox | Diamond Cup Disc
boolean | adbf014b-4b6b-536d-8985-12c3f82c7782 |  | tickbox | Broom
boolean | f959c506-4e50-5137-b8e5-c81f8e4b1dc2 |  | tickbox | Fuel
checkpoint-status | c77fa268-f44d-428b-9575-f17fb9fe56ba |  | checkpoint | Does the grout match the client's architectural drawings?
checkpoint-status | a4b5c614-c527-4ae6-9047-3c0589e52a44 |  | checkpoint | 20mm Panel base for each panel is filled?
label | 15fef299-21aa-5a06-bd3f-681ac99c0cd2 |  | note | Filled Panel base photo
checkpoint-status | a105e8f5-e1a9-426d-8ad5-4c397205c790 |  | checkpoint | Grout Tubes location checked and cleaned.
checkpoint-status | 484a2566-abe8-4eda-99d5-938a448bc481 |  | checkpoint | Grout Tubes for each panel are filled?
label | 0f845626-6ac9-5d89-a121-00ed868231c4 |  | note | Filled Panel Grout tube photo
checkpoint-status | c9bd6a2b-5db2-4eec-856b-a8675775fb5b |  | checkpoint | Cast Plates for each panel are filled?
label | 8715808c-db81-5700-b6ea-a6c5bc97be2e |  | note | Filled Panel Castplate photo
checkpoint-status | 30be046f-511b-46a3-9a8a-705d77c29bd1 |  | checkpoint | Lifters and ferrules for each panel filled?
label | 1e01d5c0-e046-51c0-97b6-e05da78804a6 |  | note | Filled Panel lifters and ferrules photo
checklist-sectioned | fd451922-3d32-4bdd-8ccf-2885925a0436 |  | checklist | Pre-Pour Checklist Strand |  |  |  |  | Yes | Pre-Pour Checklist Strand | a1e6f345-a9cf-4806-94ac-0e6effdc3476
checkpoint-group | 3b4c79d6-a607-4331-b4be-fd7bc444b2e7 |  | section | Product Detail
checkpoint-status | 57c29981-cbcc-473a-8dfa-f73880f835a1 |  | checkpoint | Details
text | 7233ee70-ab58-5cbb-b2c6-c0fbe21720d5 |  | textbox | Product ID
text | 00431790-c665-59a3-8cb9-315b438d38bf |  | textbox | Weight
text | 1b04ade1-e485-551e-8f0f-da7cb090dcdc |  | textbox | Manufacture Date
checkpoint-group | d864ac16-f363-4f78-98aa-9acdd772aef8 |  | section | Formwork
checkpoint-status | 6da9b84d-61dc-4b4b-92c1-d3734743f0ee |  | checkpoint | Check Length
text | dd84890b-3959-51ee-ae5d-dc0a1b676a39 |  | textbox | length
checkpoint-status | 9abc2ea3-b8cd-4533-b99e-d4640b033bfd |  | checkpoint | Check Width
text | 50e0b2c0-6701-53ba-9122-7bda59d59e52 |  | textbox | width
checkpoint-status | 786405f2-55d4-47e3-ac70-1350f0ab87c6 |  | checkpoint | Check Thickness
text | 97ece5af-4211-505f-8bb8-e3a010263e54 |  | textbox | thickness
checkpoint-status | c091e3b8-c064-4db3-a4d2-e2c81f5e4f07 |  | checkpoint | Check Diagnonal
checkpoint-status | d8886378-6d11-49cb-91af-64e46f085a76 |  | checkpoint | Sideform Trueness
checkpoint-status | 55f91b35-757a-4a2f-b9c1-17005a27daee |  | checkpoint | Magnets / Forms Secure
checkpoint-status | 6470a893-ee96-4ddc-8787-b79162978e75 |  | checkpoint | Splayed forms checked
checkpoint-status | b195679c-a956-4b7f-ba2d-68b5d8d41040 |  | checkpoint | Penotration dimensions checked
checkpoint-status | 866f1f0a-2076-42c2-ac02-13f22f43959b |  | checkpoint | Curves / Radius Checked
checkpoint-status | f435282e-8a0b-4fd4-8713-f63ff861ffa9 |  | checkpoint | Rebates size and location checked
checkpoint-status | f47dcb5c-ae35-4ab2-9055-0543e8a6a388 |  | checkpoint | Weather steps dimensions checked
checkpoint-status | b43f05de-eea8-43de-93f0-1f742753e195 |  | checkpoint | Weather steps orientation checked
checkpoint-status | 2215c343-4161-488a-b478-8c58c78634db |  | checkpoint | Form release applied correctly
checkpoint-group | 0fad1d38-b744-4b4e-b072-da2574f70a4c |  | section | Reinforcement
checkpoint-status | e73ec773-a5ac-4e13-848c-192be0f61d5e |  | checkpoint | Reinforcement mat as per shop drawings
checkpoint-status | 12f3ea7c-6a09-4742-b0fb-a0e4825d93a6 |  | checkpoint | Reo Mat Orientation
checkpoint-status | de70b218-06a0-45aa-ac81-3533c3c74d4b |  | checkpoint | Perimeter Bars Size Correct
checkpoint-status | f2505313-f76e-48e1-9570-819cebb9ef0d |  | checkpoint | Perimeter Bars No. Off Correct
checkpoint-status | 5673881c-138d-431f-888f-5e4f062a1689 |  | checkpoint | Additional Bars Correct
checkpoint-status | 02ab1c29-3a7b-46b0-9814-64600a745521 |  | checkpoint | Reo Changes Noted
checkpoint-status | 75b69920-f37d-49d6-acae-07add1224d27 |  | checkpoint | Reo Changes Passed By PM
checkpoint-status | 4fc04166-f8d5-4f2a-bb47-045cbf113947 |  | checkpoint | COGS / Laps As Per SD
checkpoint-status | c0667ad6-3e05-42a8-9374-281afc317d6f |  | checkpoint | Any Splice 40 x Dia Min
checkpoint-status | 74202838-93cd-414c-890c-85c220e409b5 |  | checkpoint | Rebar Photos
checkpoint-group | 5f54e234-6665-4602-bb93-151a81d6281e |  | section | Fixings / Cast Ins
checkpoint-status | b0ab1932-b633-4810-88e3-dff9fbd19940 |  | checkpoint | Details
text | ce8a454b-0af1-5572-89cd-fed6424b70b4 |  | textbox | Strand Size
text | 83c74cdb-7d87-599b-935c-8240f788f3e9 |  | textbox | Coil Id
text | 99487dd4-5f97-5570-b057-c611c7f24d10 |  | textbox | Strand Photo
checkpoint-status | 6988efb1-4bc3-4ecc-8b89-8461b8c502ab |  | checkpoint | Ferrule Location Checked
checkpoint-status | adf465d7-29a8-4292-9279-ab32b5461589 |  | checkpoint | Ferrule Cross Bars Inserted
checkpoint-status | f7f1eada-a7ed-4e5f-afbb-fa6b6e72ff4c |  | checkpoint | Lifting Inserts as Per Lift Design
checkpoint-status | 0d5c03ed-5b69-48cd-b258-514523e59679 |  | checkpoint | Lifter Type correct
select | aad0581e-3cbd-54d2-871f-24f963ceac49 |  | dropdown | Lifter Type | Leviat Edj Pro Mini 8.5T, Leviat Edj Pro Max 15T, Foot Anchor 1.3T, Foot Anchor 2.5T, Foot Anchor 5T, Foot Anchor 10T, Foot Anchor 20T
checkpoint-status | d6b5d77e-36d2-4250-8f7e-05f7699b36bd |  | checkpoint | Lifting V Bars Inserted
checkpoint-status | 719f68db-d6e1-499e-ac67-9ecadda5d10c |  | checkpoint | Cast Plates Per Design
checkpoint-status | b8df0af0-57c5-4532-adbd-0ab64db073c8 |  | checkpoint | Cast Plate Location Checked
checkpoint-status | 3869a242-451c-4229-bee2-b163fac05989 |  | checkpoint | Additional Cast Plate Bars Inserted
checkpoint-status | 6fcd6a4a-3ec1-4347-a039-517db51a5f70 |  | checkpoint | Starter Bars Correct Per SD
checkpoint-status | 17f0f6c1-c3c3-4772-bae3-bffa348cf5c2 |  | checkpoint | Pertruding Bars Orientation
checkpoint-status | f9ac8fc8-698c-455c-8053-679835c62e1b |  | checkpoint | Grout Tube Size Checked
checkpoint-status | 8c38edf5-a648-4c43-9667-de11406e3e18 |  | checkpoint | Grout Tube Exit Orientation Checked
checkpoint-status | 3f0a76b2-c13c-4f7c-aaf4-174d1d09b759 |  | checkpoint | Grout Tube Photo
checkpoint-status | 3a2d9fe1-1e9f-4802-91ad-72b00054d3e8 |  | checkpoint | Lifting Insert Photo
checkpoint-status | e1b50328-5f4c-4a03-9dc5-8768e9a2041c |  | checkpoint | Cast In Plate Photo
checkpoint-status | f15e079d-23cf-42f4-b657-29257ecdee38 |  | checkpoint | Penetration Photo
checkpoint-group | 49682576-074a-4bff-acdd-774fec400acc |  | section | Final Checks
checkpoint-status | 430639d0-17cb-4254-a56a-53752225f1d1 |  | checkpoint | All SD Dimensions Shown
checkpoint-status | 3ad6f01c-832d-4060-b1f3-7c13e1cee1c2 |  | checkpoint | Photo of For "Construction" Shop Drawing
checkpoint-status | feeb23db-3e1a-4c67-9a3a-03e7d5b7e0c6 |  | checkpoint | Panel ID Tag Placed
checkpoint-status | 7e09dfc1-e350-4b96-beaa-ae5a40fcac08 |  | checkpoint | Product Cleared For Pouring
checkpoint-status | ebdcbe3b-aaab-4f0e-8d91-e7e46868c5dc |  | checkpoint | Inspector sign off attached below
checklist-flat | 69d9751a-978c-48d8-b90d-8ab305ecdf20 |  | checklist | Pre-Install Checklist (Set-out) |  |  |  |  | Yes | Pre-Install Checklist (Set-out) | b07f1494-db27-4f6d-addf-c3bbabf75ad9
checkpoint-status | 08a987fe-705a-4127-bacc-48163d8832d0 |  | checkpoint | All Electrical Equipment is tested and tagged.
checkpoint-status | 58ca14d4-d1bc-4b34-96ae-20f803fab821 |  | checkpoint | Have the required gear for installation
boolean | 474305e9-509b-5c61-a586-bada8ae2c69a |  | tickbox | Laser level
boolean | 37518730-3052-5f2b-85df-fdb30e40f5f6 |  | tickbox | Tripod
boolean | b9cb4d83-86c9-514f-9c12-e6e3e6b5c95c |  | tickbox | Staff
boolean | 4e021244-e2ce-5070-b047-66f462f33f70 |  | tickbox | 30 mtr Tape
boolean | b883938d-fea5-598f-b139-251a3bfde569 |  | tickbox | 10 mtr Tape
boolean | 52effd98-5024-57a8-9d31-8fb9a3d0abd5 |  | tickbox | 300 mm Combination Square
boolean | 53bbd56c-5f46-5719-b25a-4483f8455fb1 |  | tickbox | 600mm Set Square
boolean | ed23a68b-0b9d-5512-8a53-f91cb10876d8 |  | tickbox | Level 2000mm
boolean | da9d4fe9-f697-5877-b5f0-7c06e93cc1f7 |  | tickbox | Level 500mm
boolean | 4542e1d8-2629-565e-b932-eb2bc8625d37 |  | tickbox | Pencils
boolean | 1921dcbb-0b00-5976-b185-f31be3a38020 |  | tickbox | Grinder
boolean | be82982c-235f-5ebd-a06e-614d6fd563c8 |  | tickbox | Batteries & Charger
boolean | 27dc19c7-d761-55c1-beb1-943b9c8accee |  | tickbox | Concrete Cutting Disk
boolean | 59b61e90-ffe3-517a-b3cd-0bcbfb245284 |  | tickbox | Large Hammer Drill
boolean | fe3b945b-4683-589f-bd2a-8ac47556c3a7 |  | tickbox | 32mm bit
boolean | 4cc2fc27-6e98-577d-a8bf-532ac264f758 |  | tickbox | Core Drill
boolean | 9d1a3ab7-3b5e-5bfb-8219-031502c4978d |  | tickbox | 50mm Core bit
boolean | f0304790-e358-5321-996e-9d7c49910fb4 |  | tickbox | 28mm Core nit
boolean | d1d0c32a-b088-5fab-aab1-22586e819d5f |  | tickbox | Extension Leads
boolean | 51e4b019-8501-5a24-bed8-cd3dcff54b77 |  | tickbox | RCD Box
boolean | 955b6fcb-a2df-5c70-9e3b-800e2ef9f746 |  | tickbox | Generator
boolean | e8983efa-3bc2-5ac5-bb80-c05e1611c32b |  | tickbox | Hose and Fittings
boolean | 667aed42-8035-565f-917f-108ea61d63f1 |  | tickbox | Shovel
boolean | fdfca348-4f5c-5267-aec1-e3b252cbba16 |  | tickbox | Marking Paint
boolean | 2d41a192-62cd-50f2-9d41-47dd73e658fd |  | tickbox | Broom
boolean | 0debcef9-1959-5bf6-a547-54a54a29a69a |  | tickbox | Fuel
checklist-sectioned | e90f1869-561d-401c-b451-543bfb3da2be |  | checklist | Pre-Pour Checklist 1 |  |  |  |  | Yes | Pre-Pour Checklist 1 | f33f0bd8-7da8-4686-9f38-8a9e06d8553e
checkpoint-group | 1f5ad4e3-2440-49d1-8cc6-8da58cf41420 |  | section | Product Detail
checkpoint-status | d90bfa34-8b4c-4a15-bb28-723c46deeef4 |  | checkpoint | Details
text | ce8b5be3-ea75-58b1-a3e7-2967a0383f77 |  | textbox | Product ID
text | 57ba2d73-fb61-53ed-8da5-4f1f3c774daa |  | textbox | Weight
text | b5306076-958a-5cc4-8f8e-67426ad1dc5f |  | textbox | Manufacture Date
checkpoint-group | 42c9fa11-750c-4886-a6b6-88596bff77de |  | section | Formwork
checkpoint-status | 3f0cdcab-4b3f-476d-b56b-b16ee107e388 |  | checkpoint | Check Length
text | aa821181-55ff-5434-9c60-590f582ffa1a |  | textbox | length
checkpoint-status | 52ec7df5-ba4b-4cfb-a76e-660dcfff8f63 |  | checkpoint | Check Width
text | 24e33343-a8e9-549c-b3fa-c26f874bb8c4 |  | textbox | width
checkpoint-status | 478266b9-d083-4b39-8262-306e351e2909 |  | checkpoint | Check Thickness
text | 0570df06-5d73-5fa2-a207-7cd5401af655 |  | textbox | thickness
checkpoint-status | dcc56b68-3340-44ea-92f1-17fa5704ae43 |  | checkpoint | Check Diagnonal
checkpoint-status | 5320e261-0158-45f1-80f6-3ac8bfd372dd |  | checkpoint | Sideform Trueness
checkpoint-status | 826c421c-3819-4e01-a290-04d4799f9553 |  | checkpoint | Magnets / Forms Secure
checkpoint-status | fbfd6b1e-be95-4fed-ace9-bd78d0e8e3f9 |  | checkpoint | Splayed forms checked
checkpoint-status | 809900d9-8079-4836-8656-f6783a846e5c |  | checkpoint | Penotration dimensions checked
checkpoint-status | 344dceb0-c2d3-4e2c-afd4-2f75ec739272 |  | checkpoint | Curves / Radius Checked
checkpoint-status | 26a843b1-0618-4e73-9fb7-82c2d06c617c |  | checkpoint | Rebates size and location checked
checkpoint-status | f2115ccc-c889-4060-9566-a6369573178a |  | checkpoint | Weather steps dimensions checked
checkpoint-status | b8c4f4f1-454e-4936-a39c-ed94b5d75f1e |  | checkpoint | Weather steps orientation checked
checkpoint-status | 26681f59-631d-4176-aa8e-8dcb2fcc9401 |  | checkpoint | Form release applied correctly
checkpoint-group | 67e25267-f2b1-4a07-855d-ecbd0989ca8f |  | section | Reinforcement
checkpoint-status | 2f21ec73-92fc-4e82-836f-b3989297918d |  | checkpoint | Reinforcement mat as per shop drawings
checkpoint-status | 1e0aeba2-4fe3-4650-8304-d891167a56a9 |  | checkpoint | Reo Mat Orientation
checkpoint-status | 0c210185-a25b-4466-84b2-1a5e37dcaa5d |  | checkpoint | Perimeter Bars Size Correct
checkpoint-status | 9a489e36-4f9d-4f76-b76d-f289d5e9e5b8 |  | checkpoint | Perimeter Bars No. Off Correct
checkpoint-status | 947f18c1-05a0-4f0e-9d2e-8b6895718245 |  | checkpoint | Additional Bars Correct
checkpoint-status | 0921695a-8f0a-471f-b834-4beb5804a7a0 |  | checkpoint | Reo Changes Noted
checkpoint-status | 1adcf415-b514-4ed5-ab0b-4a5706df10d7 |  | checkpoint | Reo Changes Passed By PM
checkpoint-status | 2b194a7c-1046-4ad3-af5a-5e70144d6d87 |  | checkpoint | COGS / Laps As Per SD
checkpoint-status | 5dcaf330-b436-4a1a-a794-710950fb0b0a |  | checkpoint | Any Splice 40 x Dia Min
checkpoint-status | 78b57408-913e-4838-8887-f9f714bfe8d9 |  | checkpoint | Rebar Photos
checkpoint-group | 6abd83fe-cb5a-4016-b8af-151bbb00796c |  | section | Fixings / Cast Ins
checkpoint-status | 2a353ad3-4ca2-4a79-a2ff-22f917e27dc8 |  | checkpoint | Ferrule Location Checked
checkpoint-status | 976aa919-133c-4371-af4a-65684fe4851d |  | checkpoint | Ferrule Cross Bars Inserted
checkpoint-status | 014bcf87-a1fd-4abd-ab69-4cf240288554 |  | checkpoint | Lifting Inserts as Per Lift Design
checkpoint-status | 04949cef-6019-4944-9abf-bc21c636b45d |  | checkpoint | Lifter Type correct
select | 98ba53ce-8947-5e57-b8b0-b08b91d643fc |  | dropdown | Lifter Type | Leviat Edj Pro Mini 8.5T, Leviat Edj Pro Max 15T, Foot Anchor 1.3T, Foot Anchor 2.5T, Foot Anchor 5T, Foot Anchor 10T, Foot Anchor 20T
checkpoint-status | 0e605e4f-634a-42b2-97b8-af21d479bcf2 |  | checkpoint | Lifting V Bars Inserted
checkpoint-status | c4ec3f31-2fc9-42de-882d-31d8f5f7c1a6 |  | checkpoint | Cast Plates Per Design
checkpoint-status | 140de006-93d1-4cc6-8d8a-175509f130b2 |  | checkpoint | Cast Plate Location Checked
checkpoint-status | e4b203fb-fcb1-4e06-93dc-1fbccdd4ec34 |  | checkpoint | Additional Cast Plate Bars Inserted
checkpoint-status | 1ef55d89-2b7e-4009-81c3-5e8f3153538a |  | checkpoint | Starter Bars Correct Per SD
checkpoint-status | e446f9b8-7a10-4207-93df-b1e230f0ec45 |  | checkpoint | Pertruding Bars Orientation
checkpoint-status | a417c0c9-137f-42cb-a33e-36be0df4875b |  | checkpoint | Grout Tube Size Checked
checkpoint-status | 77f6b57d-9e42-4987-acff-cc1cfadef084 |  | checkpoint | Grout Tube Exit Orientation Checked
checkpoint-status | 84a235aa-1b45-4714-9676-71e05dbd6e80 |  | checkpoint | Grout Tube Photo
checkpoint-status | 3814317c-2f36-41f8-90ff-3e82d38d9f19 |  | checkpoint | Lifting Insert Photo
checkpoint-status | c1b2e65e-761e-4cbd-8e49-2327b604394e |  | checkpoint | Cast In Plate Photo
checkpoint-status | 7f6e72fd-61e0-4019-aef5-f1811355e1b7 |  | checkpoint | Penetration Photo
checkpoint-group | 21422afa-f6af-4343-83e4-64da9761b74d |  | section | Final Checks
checkpoint-status | 6c8bbf16-a6ff-4bd9-8ed4-933a91d76417 |  | checkpoint | All SD Dimensions Shown
checkpoint-status | 9bfb6b82-4553-425d-8c5d-f7b11ccef887 |  | checkpoint | Photo of For "Construction" Shop Drawing
checkpoint-status | f6a6f3c3-e8de-4f22-bb4b-82a888ed9b8d |  | checkpoint | Panel ID Tag Placed
checkpoint-status | 788889ae-a4ca-46d9-a1b6-b83c0a5d78c8 |  | checkpoint | Product Cleared For Pouring
checkpoint-status | c23f8dac-cfd1-4d5b-b829-38f3c8573c22 |  | checkpoint | Inspector sign off attached below
checklist-flat | 22be868c-7a4e-48f3-b51b-0fbcb7efdf87 |  | checklist | Site Details |  |  |  |  | Yes | Site Details | f8ab51b8-b513-4778-900e-a9d5f479fb90
checkpoint-no-status | 4cf5d2d2-43cf-48e6-a703-f391ccaa7fb4 |  | checkpoint | Site Details
text | 80f12b4c-891d-5984-9ae8-345ebfb15f32 |  | textbox | Number
text | 1f1a1b7a-4b89-5458-b91e-8ab88c4cf9df |  | textbox | Name
text | ef4bce91-9955-5b8d-bd0b-b4bdfc381620 |  | textbox | Customer
boolean | bf247050-efe6-59e3-826a-23258e483e48 |  | tickbox | Mark Job as Completed
text | 0079152c-4e8f-5664-bc2e-59938031f242 |  | textbox | Address
text | baf185f7-0bb2-5862-95ab-96b81b28c498 |  | textbox | Contact Name
text | 17c870e1-b393-57aa-acd8-00ebf277a5a9 |  | textbox | Contact Phone Number
text | 5acf748e-296d-54fe-b7f2-f959f536613f |  | textbox | Install Co-ordinator
text | 20ddcc7e-a008-5c4c-a23f-60b721f855ce |  | textbox | Install Co-ordinator Contact Number