## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | New Plywood Substrate Readiness Checklist - Membrane |  |  |  |  | Yes | New Plywood Substrate Readiness Checklist - Membrane | 08083842-44e9-4729-95a2-18baf322fe24
checkpoint-status |  |  | checkpoint | Area ready?
checkpoint-status |  |  | checkpoint | Structure complies to the New Zealand Building Code and plywood complies with AS/NZ 2269
checkpoint-status |  |  | checkpoint | CCA H3.2 treated plywood sheets used
label | 39c0e4d3-ef59-5b1c-a356-2b450c96fba0 |  | note | 17mm thick for roofs, 20mm thick for decks
checkpoint-status |  |  | checkpoint | Plywood sheets supported at 600mm centred rafters and nogs for roofs and decks, unless otherwise specified
checkpoint-status |  |  | checkpoint | Sheets stagger lay (fully offset) with falls as per plan
checkpoint-status |  |  | checkpoint | 5mm clearances from all abutments, 5mm radius to all exposed edges
checkpoint-status |  |  | checkpoint | All sheet edges supported, fixed 150mm on edges and 200mm through girth, edges butt-jointed with no gaps except at abutments
checkpoint-status |  |  | checkpoint | Sheets fixed by gluing and Stainless Steel countersunk screw fixing
checkpoint-status |  |  | checkpoint | Fillets installed to all internal junctions and neatly fitted
checkpoint-status |  |  | checkpoint | Mitres neatly formed
checkpoint-status |  |  | checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface
checkpoint-status |  |  | checkpoint | Sharp edges and lips removed and cavities filleted. All joints flush
checkpoint-status |  |  | checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures
checkpoint-status |  |  | checkpoint | Substrate dry, clean, firm and suitable condition for laying
checkpoint-status |  |  | checkpoint | When substrate is ready complete send this as report to membrane applicator
holdpoint |  |  | signoff | Signed by head contractor
checklist-flat |  |  | checklist | SEALCO TPO - Plywood Substrate Readiness Checklist |  |  |  |  | Yes | SEALCO TPO - Plywood Substrate Readiness Checklist | 24622396-727e-47e8-870c-e0a6657f2b1d
checkpoint-status |  |  | checkpoint | Architect and builder are responsible for correct design, including falls, constructions and detailing of substrate.
checkpoint-status |  |  | checkpoint | CD Structural Grade H3.2 CCA treated Kiln Dried and min. 17mm thick.
checkpoint-status |  |  | checkpoint | Use only square edged construction plywood with all edges fully supported with timber battens. (T&G plywood not acceptable)
checkpoint-status |  |  | checkpoint | Sheets stagger laid (fully offset brick bond pattern), tight butted, with sanded C-face upwards and face grain at right angles to supports or crossmembers.
checkpoint-status |  |  | checkpoint | Plywood glued and screwed, fixed 150mm on edges and 200mm through girth.
checkpoint-status |  |  | checkpoint | Grade 316 stainless steel counter sunk screw fixing, min. 10-gauge x 50mm or a length 3 times that of the plywood thickness.
checkpoint-status |  |  | checkpoint | Plywood installed with correct falls and no ponding.
checkpoint-status |  |  | checkpoint | No fillets required; all internal angles formed at 90 degrees.
checkpoint-status |  |  | checkpoint | 3 - 5mm clearances from all abutments.
checkpoint-status |  |  | checkpoint | Pre-inspection of all penetrations and details.
checkpoint-status |  |  | checkpoint | 5mm radius to all external corners.
checkpoint-status |  |  | checkpoint | Using a moisture measure ensure moisture content at the time of installation is below 20%.
checkpoint-status |  |  | checkpoint | Rainwater outlets and overflow recesses formed in substrate to fit propriety outlets.
checkpoint-status |  |  | checkpoint | Sharp edges and lips removed, and cavities filled. All joints flush.
checkpoint-status |  |  | checkpoint | Substrate is clean, firm, and suitable condition for laying.
checkpoint-status |  |  | checkpoint | Plinths formed for any exterior ventilation, fixtures or similar.
checkpoint-status |  |  | checkpoint | Builder has installed flashings and tapes that are compatible with system
checklist-flat |  |  | checklist | New Concrete Substrate Readiness Checklist - Nuraply 3PM Membrane |  |  |  |  | Yes | New Concrete Substrate Readiness Checklist - Nuraply 3PM Membrane | 2486166e-86b7-4e87-9481-6c5580b7631b
checkpoint-status |  |  | checkpoint | Area ready?
checkpoint-status |  |  | checkpoint | Structure complies to the New Zealand Building Code and concrete complies with NZS 3101 (2006)
checkpoint-status |  |  | checkpoint | Concrete cured with curing membranes removed. Concrete substrate contains less than 5% moisture content
checkpoint-status |  |  | checkpoint | Surface smooth and clean with falls as per plan
checkpoint-status |  |  | checkpoint | Cavities and cracks filled with repair mortar, flushed off and cured
checkpoint-status |  |  | checkpoint | Concrete surface firm with any soft concrete or laitance removed
checkpoint-status |  |  | checkpoint | Ponding areas removed
checkpoint-status |  |  | checkpoint | Roof drains and overflow recesses formed to fit rebated outlets
checkpoint-status |  |  | checkpoint | Mortar or Profili Bitumen fillets to all upstands and smooth 5mm radius to all external edges
checkpoint-status |  |  | checkpoint | If terminating into a chase, pre-form the chase and ensure it is straight and 20mm deep
checkpoint-status |  |  | checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures
checkpoint-status |  |  | checkpoint | Construction joints incorporated in slab as per designers specification
checkpoint-status |  |  | checkpoint | Substrate clean, firm and suitable condition for laying the Nuralite systems
checkpoint-status |  |  | checkpoint | When substrate is ready complete send this as report to Nuralite applicator
holdpoint |  |  | signoff | Signed by head contractor
checklist-sectioned |  |  | checklist | SEALCO TPO - Quality Control Checklist |  |  |  |  | Yes | SEALCO TPO - Quality Control Checklist | 27c7e67b-6f84-4539-a282-6bf753b9c8ad
checkpoint-group |  |  | section | QA Checks
checkpoint-status |  |  | checkpoint | Plywood substrate stagger-bond laid with each sheet offset at least 300mm and edges supported.
checkpoint-status |  |  | checkpoint | Plywood substrate s/s screw fixed to E2/AS1 specification, no loose/drummy sheets or delamination. (
checkpoint-status |  |  | checkpoint | Plywood sheets to be tight butted and 3mm gap to all abutments. (No T&G sheet joints)
checkpoint-status |  |  | checkpoint | Substrate clean, dry and free from foreign matter and sharp edges - Plywood moisture tested with moisture meter and is below 20%. Any holes or indentations filled with builders’ bog and flushed off smooth.
checkpoint-status |  |  | checkpoint | All soft areas in concrete filled and cracks repaired with non-shrink mortar. Any curing compounds removed. Maximum moisture of relative humidity 75% - verified using an approved method.
checkpoint-status |  |  | checkpoint | All external corners chamfered 5mm radius.
checkpoint-status |  |  | checkpoint | 36mm PVC tapes to plywood sheet joints. For concrete, install grid tapes if concrete surface is to be vented.
checkpoint-status |  |  | checkpoint | Movement joints identified and installed to approved specification / detail (attach detail drawings)
checkpoint-status |  |  | checkpoint | Pipe penetrations and rainwater outlets detailed as per Sealco specification.
checkpoint-status |  |  | checkpoint | Gutters correctly and neatly installed, particularly the internal corners - ensure laps above roof line.
checkpoint-status |  |  | checkpoint | DrainRITE® roof drains installed to Sealco specification.
checkpoint-status |  |  | checkpoint | VentRITE® overflows installed to Sealco specification.
checkpoint-status |  |  | checkpoint | EcoTUFF® adhesive within shelf life and correctly mixed.
checkpoint-status |  |  | checkpoint | EcoTUFF® installed to Sealco specification, ensuring adhesive applied to substrate and membrane at correct rate.
checkpoint-status |  |  | checkpoint | All laps minimum 40mm. Lap tested and watertight
checkpoint-status |  |  | checkpoint | No air entrapment or foreign matter contamination under the EcoTUFF® membrane.
checkpoint-status |  |  | checkpoint | EcoTUFF® sheets laid across the roof slope, so water runs over the laps rather than down lap edge
checkpoint-status |  |  | checkpoint | Membrane termination completed to Sealco approved detail.
checkpoint-status |  |  | checkpoint | EcoTUFF® roof vents installed to specification (min. two vents / roof area, with one every 90m²)
checkpoint-status |  |  | checkpoint | All penetration details completed to Sealco specification including EcoTUFF® over flashing.
checkpoint-status |  |  | checkpoint | All non-standard details installed as per pre-approved specifications (attached approved drawings).
checkpoint-status |  |  | checkpoint | Any mechanical damage to EcoTUFF® repaired to Sealco specification
checkpoint-status |  |  | checkpoint | Overall installation free of wrinkles, creases and splits, with no air or foreign matter entrapped.
checkpoint-status |  |  | checkpoint | Job sheets completed recording area installed, date of installation, membrane batch numbers etc.
checkpoint-status |  |  | checkpoint | Remedial action required? If yes, attach photos of damaged areas repaired.
checkpoint-group |  |  | section | Priming coverage calculation
checkpoint-no-status |  |  | checkpoint | Calculation
text | 7547bb00-c13f-5dd9-a74a-5dbe7620494f |  | textbox | Installation Area (M²)
text | d462f519-24da-5d39-98d1-41b9dae7786f |  | textbox | Coverage (ltr/M²)
text | c20e5af1-762c-51ac-bad0-f305526f0726 |  | textbox | Litres required
text | 4319a965-7258-545a-af24-72628117478e |  | textbox | Pails required
text | 65dfbbc6-3eac-55e7-bf9e-2e6a771cf9b9 |  | textbox | Pails used
checklist-flat |  |  | checklist | Roof Readiness Checklist - Nuraply 3PM Membrane |  |  |  |  | Yes | Roof Readiness Checklist - Nuraply 3PM Membrane | 34b731fc-de64-408f-9268-03308c84f7a9
checkpoint-status |  |  | checkpoint | Area ready?
checkpoint-status |  |  | checkpoint | CCA H3.2 treated plywood sheets used
label | fcd82b58-495e-59a1-acd9-248eab619264 |  | note | 17mm thick for roofs, 20mm thick for decks
checkpoint-status |  |  | checkpoint | Plywood sheets supported by joists and nogs at maximum 400mm centers in both directions, unless specified otherwise
checkpoint-status |  |  | checkpoint | Sheets stagger lay (fully offset) with the face grain at right angles to the primary supports
checkpoint-status |  |  | checkpoint | All sheet edges supported by nogs, fixed 100mm on edges and 200mm through girth, edges butt-jointed with no gaps except at abutments
checkpoint-status |  |  | checkpoint | Sheets glued in place and then fixed using 316 grade Stainless Steel 10 gauge countersunk screw fixings
checkpoint-status |  |  | checkpoint | All decks and gutters have correct falls once installed
checkpoint-status |  |  | checkpoint | Fillets installed to all internal junctions and neatly fitted with mitres neatly formed
checkpoint-status |  |  | checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface
checkpoint-status |  |  | checkpoint | 5mm clearances from all abutments, 5mm radius to all exposed edges
checkpoint-status |  |  | checkpoint | Sharp edges and lips removed and cavities filleted. All joints flush
checkpoint-status |  |  | checkpoint | Substrate dry, clean, firm and suitable condition for laying
holdpoint |  |  | signoff | signed by Titus
checklist-flat |  |  | checklist | New ENERTHERM Substrate Readiness Checklist - Nuraply 3PM Membrane |  |  |  |  | Yes | New ENERTHERM Substrate Readiness Checklist - Nuraply 3PM Membrane | 7a998cec-dd0d-4f2e-b2b2-8ac6106c31c8
checkpoint-status |  |  | checkpoint | Area ready?
checkpoint-status |  |  | checkpoint | Structure complies to the New Zealand Building Code
checkpoint-status |  |  | checkpoint | Sheets stagger lay (fully offset)
checkpoint-status |  |  | checkpoint | Confirm the substrate slope complies with plans
checkpoint-status |  |  | checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface
checkpoint-status |  |  | checkpoint | Ensure only approved accessories to be used for drainage and venting
checkpoint-status |  |  | checkpoint | Review penetrations to minimize number and complexity
checkpoint-status |  |  | checkpoint | Any gaps in the insulation filled to prevent thermal bridging
checkpoint-status |  |  | checkpoint | Material fastened with the correct quantity of IKOfix Telescopic Fixing Plates and Fixing Screws
label | 43e7b5bf-be63-57ba-8ac6-7352c8190325 |  | note | 5 per sheet normally, 10 per sheet in extra high wind zones
checkpoint-status |  |  | checkpoint | Edges of insulation supported by metal sheet ridges
checkpoint-status |  |  | checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures
checkpoint-status |  |  | checkpoint | Substrate clean, firm and suitable condition for laying the Nuralite systems
checkpoint-status |  |  | checkpoint | When substrate is ready complete send this as report to Nuralite applicator
holdpoint |  |  | signoff | Signed by head contractor
checklist-flat |  |  | checklist | New Plywood Substrate Readiness Checklist - Nuraply 3PM Membrane |  |  |  |  | Yes | New Plywood Substrate Readiness Checklist - Nuraply 3PM Membrane | 944a7228-bfcf-4a7c-a740-164137c209ad
checkpoint-status |  |  | checkpoint | Area ready?
checkpoint-status |  |  | checkpoint | Structure complies to the New Zealand Building Code and plywood complies with AS/NZ 2269
checkpoint-status |  |  | checkpoint | CCA H3.2 treated plywood sheets used
label | 4952fdd0-59c4-528c-9b60-a3bf2de2b9a1 |  | note | 17mm thick for roofs, 20mm thick for decks
checkpoint-status |  |  | checkpoint | Plywood sheets supported at 600mm centred rafters and nogs for roofs and decks, unless otherwise specified
checkpoint-status |  |  | checkpoint | Sheets stagger lay (fully offset) with falls as per plan
checkpoint-status |  |  | checkpoint | 5mm clearances from all abutments, 5mm radius to all exposed edges
checkpoint-status |  |  | checkpoint | All sheet edges supported, fixed 150mm on edges and 200mm through girth, edges butt-jointed with no gaps except at abutments
checkpoint-status |  |  | checkpoint | Sheets fixed by gluing and Stainless Steel countersunk screw fixing
checkpoint-status |  |  | checkpoint | Fillets installed to all internal junctions and neatly fitted
checkpoint-status |  |  | checkpoint | Mitres neatly formed
checkpoint-status |  |  | checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface
checkpoint-status |  |  | checkpoint | Sharp edges and lips removed and cavities filleted. All joints flush
checkpoint-status |  |  | checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures
checkpoint-status |  |  | checkpoint | Substrate dry, clean, firm and suitable condition for laying
checkpoint-status |  |  | checkpoint | When substrate is ready complete send this as report to Nuralite applicator
holdpoint |  |  | signoff | Signed by head contractor
checklist-flat |  |  | checklist | Existing Roof Substrate Readiness Checklist - Nuraply 3PM Membrane |  |  |  |  | Yes | Existing Roof Substrate Readiness Checklist - Nuraply 3PM Membrane | a2402b38-9df1-4e1f-bfa0-964a957b937d
checkpoint-status |  |  | checkpoint | Area ready?
checkpoint-status |  |  | checkpoint | Confirm the substrate is suitable with no signs of deterioration in the form of rust or rot
checkpoint-status |  |  | checkpoint | Cladding, doors and windows removed to allow upstands to be formed
checkpoint-status |  |  | checkpoint | Confirm the substrate slope exceeds minimum requirements unless approved by Nuralite for this specific project
checkpoint-status |  |  | checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface
checkpoint-status |  |  | checkpoint | Ensure only approved accessories to be used for drainage and venting
checkpoint-status |  |  | checkpoint | Review penetrations to minimize number and complexity
checkpoint-status |  |  | checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures
checkpoint-status |  |  | checkpoint | Substrate clean, firm and suitable condition for laying the Nuralite systems
checkpoint-status |  |  | checkpoint | When substrate is ready complete send this as report to Nuralite applicator
holdpoint |  |  | signoff | Signed by head contractor
checklist-flat |  |  | checklist | Project Sign Off Checklist - Membrane |  |  |  |  | Yes | Project Sign Off Checklist - Membrane | c52e7283-7444-4e77-81d4-b01143f5a991
checkpoint-no-status |  |  | checkpoint | Products used
text | ae30d521-f094-5a3a-b9d2-fc56b0577a27 |  | textbox | Products used
checkpoint-status |  |  | checkpoint | Substrate readiness checklist completed
checkpoint-status |  |  | checkpoint | Under Flashings installed to all corners and upstands
checkpoint-status |  |  | checkpoint | Gutters correctly and neatly installed, particularly the internal corners
checkpoint-status |  |  | checkpoint | Roof drains & overflows installed to specification and watertight
checkpoint-status |  |  | checkpoint | Membrane fully adhered to substrate with no evidence of bubbles or lifting. Correct quantities of primer/adhesive used as per specification
checkpoint-status |  |  | checkpoint | Cap sheet and basesheet fully bonded together, no areas of delamination
checkpoint-status |  |  | checkpoint | Cap sheet side laps 80mm and end laps 100mm fully welded and tidily seamed off
checkpoint-status |  |  | checkpoint | No sign of overheating/excessive bitumen bleed from laps (over 2-3mm)
checkpoint-status |  |  | checkpoint | Cap sheet and base sheet laps offset satisfactorily. No three layer lap build-ups
checkpoint-status |  |  | checkpoint | Overall installation free of wrinkles, creases and splits
checkpoint-status |  |  | checkpoint | Vents installed to specification (one every 20m²)
checkpoint-status |  |  | checkpoint | All penetration details completed to specification including under/over flashing
checkpoint-status |  |  | checkpoint | Standard details used throughout including at upstands, parapets, construction joints
checkpoint-status |  |  | checkpoint | All non standard details installed as per pre-approved specifications (attach approved drawing)
checkpoint-status |  |  | checkpoint | Gutters and outlets have been flood tested
checkpoint-status |  |  | checkpoint | Any damage to cap sheet repaired to specification
checkpoint-status |  |  | checkpoint | Sand finished cap sheets have gel applied (if applicable). Surfaces thoroughly cleaned before coating
checkpoint-status |  |  | checkpoint | Remedial action required?
holdpoint |  |  | signoff | Signed by Builder & Applicator
checklist-flat |  |  | checklist | Roof Readiness Checklist - Membrane |  |  |  |  | Yes | Roof Readiness Checklist - Membrane | d3811646-106a-4b76-a978-0dbbdbccca44
checkpoint-status |  |  | checkpoint | Area ready?
checkpoint-status |  |  | checkpoint | CCA H3.2 treated plywood sheets used
label | 117d6c8d-b9be-5e08-9b0f-7f033838778e |  | note | 17mm thick for roofs, 20mm thick for decks
checkpoint-status |  |  | checkpoint | Plywood sheets supported by joists and nogs at maximum 400mm centers in both directions, unless specified otherwise
checkpoint-status |  |  | checkpoint | Sheets stagger lay (fully offset) with the face grain at right angles to the primary supports
checkpoint-status |  |  | checkpoint | All sheet edges supported by nogs, fixed 100mm on edges and 200mm through girth, edges butt-jointed with no gaps except at abutments
checkpoint-status |  |  | checkpoint | Sheets glued in place and then fixed using 316 grade Stainless Steel 10 gauge countersunk screw fixings
checkpoint-status |  |  | checkpoint | All decks and gutters have correct falls once installed
checkpoint-status |  |  | checkpoint | Fillets installed to all internal junctions and neatly fitted with mitres neatly formed
checkpoint-status |  |  | checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface
checkpoint-status |  |  | checkpoint | 5mm clearances from all abutments, 5mm radius to all exposed edges
checkpoint-status |  |  | checkpoint | Sharp edges and lips removed and cavities filleted. All joints flush
checkpoint-status |  |  | checkpoint | Substrate dry, clean, firm and suitable condition for laying
holdpoint |  |  | signoff | signed by Titus
checklist-flat |  |  | checklist | Project Sign Off Checklist - Nuraply 3PM Membrane |  |  |  |  | Yes | Project Sign Off Checklist - Nuraply 3PM Membrane | f3a71175-e7bb-4b29-a361-d435719bc193
checkpoint-no-status |  |  | checkpoint | Products used
text | b8cd9909-8d9e-575f-88e7-20b197e9716b |  | textbox | Products used
checkpoint-status |  |  | checkpoint | Substrate readiness checklist completed
checkpoint-status |  |  | checkpoint | Under Flashings installed to all corners and upstands
checkpoint-status |  |  | checkpoint | Gutters correctly and neatly installed, particularly the internal corners
checkpoint-status |  |  | checkpoint | Roof drains & overflows installed to specification and watertight
checkpoint-status |  |  | checkpoint | Membrane fully adhered to substrate with no evidence of bubbles or lifting. Correct quantities of primer/adhesive used as per specification
checkpoint-status |  |  | checkpoint | Cap sheet and basesheet fully bonded together, no areas of delamination
checkpoint-status |  |  | checkpoint | Cap sheet side laps 80mm and end laps 100mm fully welded and tidily seamed off
checkpoint-status |  |  | checkpoint | No sign of overheating/excessive bitumen bleed from laps (over 2-3mm)
checkpoint-status |  |  | checkpoint | Cap sheet and base sheet laps offset satisfactorily. No three layer lap build-ups
checkpoint-status |  |  | checkpoint | Overall installation free of wrinkles, creases and splits
checkpoint-status |  |  | checkpoint | Nuravents installed to specification (one every 20m²)
checkpoint-status |  |  | checkpoint | All penetration details completed to specification including under/over flashing
checkpoint-status |  |  | checkpoint | Standard details used throughout including at upstands, parapets, construction joints
checkpoint-status |  |  | checkpoint | All non standard details installed as per pre-approved specifications (attach approved drawing)
checkpoint-status |  |  | checkpoint | Gutters and outlets have been flood tested
checkpoint-status |  |  | checkpoint | Any damage to cap sheet repaired to specification
checkpoint-status |  |  | checkpoint | Sand finished cap sheets have Nura Colour applied to specification. Surfaces thoroughly cleaned before coating
checkpoint-status |  |  | checkpoint | Remedial action required?
holdpoint |  |  | signoff | Signed by Builder & Applicator