## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | SEALCO TPO - Quality Control Checklist |  |  |  |  | Yes | SEALCO TPO - Quality Control Checklist | 12b4d97b-3d7e-4bef-9806-eb75ae170794
checkpoint-group |  |  | section | QA Checks
checkpoint-status |  |  | checkpoint | Plywood substrate stagger-bond laid with each sheet offset at least 300mm and edges supported.
checkpoint-status |  |  | checkpoint | Plywood substrate s/s screw fixed to E2/AS1 specification, no loose/drummy sheets or delamination. (
checkpoint-status |  |  | checkpoint | Plywood sheets to be tight butted and 3mm gap to all abutments. (No T&G sheet joints)
checkpoint-status |  |  | checkpoint | Substrate clean, dry and free from foreign matter and sharp edges - Plywood moisture tested with moisture meter and is below 20%. Any holes or indentations filled with builders’ bog and flushed off smooth.
checkpoint-status |  |  | checkpoint | All soft areas in concrete filled and cracks repaired with non-shrink mortar. Any curing compounds removed. Maximum moisture of relative humidity 75% - verified using an approved method.
checkpoint-status |  |  | checkpoint | All external corners chamfered 5mm radius.
checkpoint-status |  |  | checkpoint | 36mm PVC tapes to plywood sheet joints. For concrete, install grid tapes if concrete surface is to be vented.
checkpoint-status |  |  | checkpoint | Movement joints identified and installed to approved specification / detail (attach detail drawings)
checkpoint-status |  |  | checkpoint | Pipe penetrations and rainwater outlets detailed as per Sealco specification.
checkpoint-status |  |  | checkpoint | Gutters correctly and neatly installed, particularly the internal corners - ensure laps above roof line.
checkpoint-status |  |  | checkpoint | DrainRITE® roof drains installed to Sealco specification.
checkpoint-status |  |  | checkpoint | VentRITE® overflows installed to Sealco specification.
checkpoint-status |  |  | checkpoint | EcoTUFF® adhesive within shelf life and correctly mixed.
checkpoint-status |  |  | checkpoint | EcoTUFF® installed to Sealco specification, ensuring adhesive applied to substrate and membrane at correct rate.
checkpoint-status |  |  | checkpoint | All laps minimum 40mm. Lap tested and watertight
checkpoint-status |  |  | checkpoint | No air entrapment or foreign matter contamination under the EcoTUFF® membrane.
checkpoint-status |  |  | checkpoint | EcoTUFF® sheets laid across the roof slope, so water runs over the laps rather than down lap edge
checkpoint-status |  |  | checkpoint | Membrane termination completed to Sealco approved detail.
checkpoint-status |  |  | checkpoint | EcoTUFF® roof vents installed to specification (min. two vents / roof area, with one every 90m²)
checkpoint-status |  |  | checkpoint | All penetration details completed to Sealco specification including EcoTUFF® over flashing.
checkpoint-status |  |  | checkpoint | All non-standard details installed as per pre-approved specifications (attached approved drawings).
checkpoint-status |  |  | checkpoint | Any mechanical damage to EcoTUFF® repaired to Sealco specification
checkpoint-status |  |  | checkpoint | Overall installation free of wrinkles, creases and splits, with no air or foreign matter entrapped.
checkpoint-status |  |  | checkpoint | Job sheets completed recording area installed, date of installation, membrane batch numbers etc.
checkpoint-status |  |  | checkpoint | Remedial action required? If yes, attach photos of damaged areas repaired.
checkpoint-group |  |  | section | Priming coverage calculation
checkpoint-no-status |  |  | checkpoint | Calculation
text | 3cd00e34-45de-54ce-9a93-112720332869 |  | textbox | Installation Area (M²)
text | 63d190fc-b118-5ab1-8411-18cee3c99a04 |  | textbox | Coverage (ltr/M²)
text | 3f705d4d-fcd4-56a1-a503-a6c4a1377d71 |  | textbox | Litres required
text | 912d3306-1217-5afd-89eb-3d9fddbdb247 |  | textbox | Pails required
text | 35bb1441-4720-53c1-93bd-5358cb2c4c81 |  | textbox | Pails used
checklist-flat |  |  | checklist | Project Sign Off Checklist - Membrane |  |  |  |  | Yes | Project Sign Off Checklist - Membrane | 1d401bcd-88dc-4b48-b251-e49228c546f9
checkpoint-no-status |  |  | checkpoint | Products used
text | b46e66be-ccd5-556f-875d-8ecb0f2598e7 |  | textbox | Products used
checkpoint-status |  |  | checkpoint | Substrate readiness checklist completed
checkpoint-status |  |  | checkpoint | Under Flashings installed to all corners and upstands
checkpoint-status |  |  | checkpoint | Gutters correctly and neatly installed, particularly the internal corners
checkpoint-status |  |  | checkpoint | Roof drains & overflows installed to specification and watertight
checkpoint-status |  |  | checkpoint | Membrane fully adhered to substrate with no evidence of bubbles or lifting. Correct quantities of primer/adhesive used as per specification
checkpoint-status |  |  | checkpoint | Cap sheet and basesheet fully bonded together, no areas of delamination
checkpoint-status |  |  | checkpoint | Cap sheet side laps 80mm and end laps 100mm fully welded and tidily seamed off
checkpoint-status |  |  | checkpoint | No sign of overheating/excessive bitumen bleed from laps (over 2-3mm)
checkpoint-status |  |  | checkpoint | Cap sheet and base sheet laps offset satisfactorily. No three layer lap build-ups
checkpoint-status |  |  | checkpoint | Overall installation free of wrinkles, creases and splits
checkpoint-status |  |  | checkpoint | Vents installed to specification (one every 20m²)
checkpoint-status |  |  | checkpoint | All penetration details completed to specification including under/over flashing
checkpoint-status |  |  | checkpoint | Standard details used throughout including at upstands, parapets, construction joints
checkpoint-status |  |  | checkpoint | All non standard details installed as per pre-approved specifications (attach approved drawing)
checkpoint-status |  |  | checkpoint | Gutters and outlets have been flood tested
checkpoint-status |  |  | checkpoint | Any damage to cap sheet repaired to specification
checkpoint-status |  |  | checkpoint | Sand finished cap sheets have gel applied (if applicable). Surfaces thoroughly cleaned before coating
checkpoint-status |  |  | checkpoint | Remedial action required?
holdpoint |  |  | signoff | Signed by Builder & Applicator
checklist-flat |  |  | checklist | New ENERTHERM Substrate Readiness Checklist - Nuraply 3PM Membrane |  |  |  |  | Yes | New ENERTHERM Substrate Readiness Checklist - Nuraply 3PM Membrane | 2fafc819-4fe8-4913-8b82-b57d90530410
checkpoint-status |  |  | checkpoint | Area ready?
checkpoint-status |  |  | checkpoint | Structure complies to the New Zealand Building Code
checkpoint-status |  |  | checkpoint | Sheets stagger lay (fully offset)
checkpoint-status |  |  | checkpoint | Confirm the substrate slope complies with plans
checkpoint-status |  |  | checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface
checkpoint-status |  |  | checkpoint | Ensure only approved accessories to be used for drainage and venting
checkpoint-status |  |  | checkpoint | Review penetrations to minimize number and complexity
checkpoint-status |  |  | checkpoint | Any gaps in the insulation filled to prevent thermal bridging
checkpoint-status |  |  | checkpoint | Material fastened with the correct quantity of IKOfix Telescopic Fixing Plates and Fixing Screws
label | e341a252-d0aa-52c4-827a-fe5331f794e8 |  | note | 5 per sheet normally, 10 per sheet in extra high wind zones
checkpoint-status |  |  | checkpoint | Edges of insulation supported by metal sheet ridges
checkpoint-status |  |  | checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures
checkpoint-status |  |  | checkpoint | Substrate clean, firm and suitable condition for laying the Nuralite systems
checkpoint-status |  |  | checkpoint | When substrate is ready complete send this as report to Nuralite applicator
holdpoint |  |  | signoff | Signed by head contractor
checklist-flat |  |  | checklist | Roof Readiness Checklist - Membrane |  |  |  |  | Yes | Roof Readiness Checklist - Membrane | 3522bc97-5f4a-4c22-a977-be61b77f614e
checkpoint-status |  |  | checkpoint | Area ready?
checkpoint-status |  |  | checkpoint | CCA H3.2 treated plywood sheets used
label | cda79ad4-a8eb-5f5a-ba56-1fe4b6d31e18 |  | note | 17mm thick for roofs, 20mm thick for decks
checkpoint-status |  |  | checkpoint | Plywood sheets supported by joists and nogs at maximum 400mm centers in both directions, unless specified otherwise
checkpoint-status |  |  | checkpoint | Sheets stagger lay (fully offset) with the face grain at right angles to the primary supports
checkpoint-status |  |  | checkpoint | All sheet edges supported by nogs, fixed 100mm on edges and 200mm through girth, edges butt-jointed with no gaps except at abutments
checkpoint-status |  |  | checkpoint | Sheets glued in place and then fixed using 316 grade Stainless Steel 10 gauge countersunk screw fixings
checkpoint-status |  |  | checkpoint | All decks and gutters have correct falls once installed
checkpoint-status |  |  | checkpoint | Fillets installed to all internal junctions and neatly fitted with mitres neatly formed
checkpoint-status |  |  | checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface
checkpoint-status |  |  | checkpoint | 5mm clearances from all abutments, 5mm radius to all exposed edges
checkpoint-status |  |  | checkpoint | Sharp edges and lips removed and cavities filleted. All joints flush
checkpoint-status |  |  | checkpoint | Substrate dry, clean, firm and suitable condition for laying
holdpoint |  |  | signoff | signed by Titus
checklist-flat |  |  | checklist | Project Sign Off Checklist - Nuraply 3PM Membrane |  |  |  |  | Yes | Project Sign Off Checklist - Nuraply 3PM Membrane | 87f09671-c405-436c-bd21-f3dfb269657d
checkpoint-no-status |  |  | checkpoint | Products used
text | bf8af072-71be-5950-9d63-b689978e3347 |  | textbox | Products used
checkpoint-status |  |  | checkpoint | Substrate readiness checklist completed
checkpoint-status |  |  | checkpoint | Under Flashings installed to all corners and upstands
checkpoint-status |  |  | checkpoint | Gutters correctly and neatly installed, particularly the internal corners
checkpoint-status |  |  | checkpoint | Roof drains & overflows installed to specification and watertight
checkpoint-status |  |  | checkpoint | Membrane fully adhered to substrate with no evidence of bubbles or lifting. Correct quantities of primer/adhesive used as per specification
checkpoint-status |  |  | checkpoint | Cap sheet and basesheet fully bonded together, no areas of delamination
checkpoint-status |  |  | checkpoint | Cap sheet side laps 80mm and end laps 100mm fully welded and tidily seamed off
checkpoint-status |  |  | checkpoint | No sign of overheating/excessive bitumen bleed from laps (over 2-3mm)
checkpoint-status |  |  | checkpoint | Cap sheet and base sheet laps offset satisfactorily. No three layer lap build-ups
checkpoint-status |  |  | checkpoint | Overall installation free of wrinkles, creases and splits
checkpoint-status |  |  | checkpoint | Nuravents installed to specification (one every 20m²)
checkpoint-status |  |  | checkpoint | All penetration details completed to specification including under/over flashing
checkpoint-status |  |  | checkpoint | Standard details used throughout including at upstands, parapets, construction joints
checkpoint-status |  |  | checkpoint | All non standard details installed as per pre-approved specifications (attach approved drawing)
checkpoint-status |  |  | checkpoint | Gutters and outlets have been flood tested
checkpoint-status |  |  | checkpoint | Any damage to cap sheet repaired to specification
checkpoint-status |  |  | checkpoint | Sand finished cap sheets have Nura Colour applied to specification. Surfaces thoroughly cleaned before coating
checkpoint-status |  |  | checkpoint | Remedial action required?
holdpoint |  |  | signoff | Signed by Builder & Applicator
checklist-flat |  |  | checklist | Existing Roof Substrate Readiness Checklist - Nuraply 3PM Membrane |  |  |  |  | Yes | Existing Roof Substrate Readiness Checklist - Nuraply 3PM Membrane | a32adfaf-1fff-46c0-a353-27651de652ca
checkpoint-status |  |  | checkpoint | Area ready?
checkpoint-status |  |  | checkpoint | Confirm the substrate is suitable with no signs of deterioration in the form of rust or rot
checkpoint-status |  |  | checkpoint | Cladding, doors and windows removed to allow upstands to be formed
checkpoint-status |  |  | checkpoint | Confirm the substrate slope exceeds minimum requirements unless approved by Nuralite for this specific project
checkpoint-status |  |  | checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface
checkpoint-status |  |  | checkpoint | Ensure only approved accessories to be used for drainage and venting
checkpoint-status |  |  | checkpoint | Review penetrations to minimize number and complexity
checkpoint-status |  |  | checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures
checkpoint-status |  |  | checkpoint | Substrate clean, firm and suitable condition for laying the Nuralite systems
checkpoint-status |  |  | checkpoint | When substrate is ready complete send this as report to Nuralite applicator
holdpoint |  |  | signoff | Signed by head contractor
checklist-flat |  |  | checklist | New Concrete Substrate Readiness Checklist - Nuraply 3PM Membrane |  |  |  |  | Yes | New Concrete Substrate Readiness Checklist - Nuraply 3PM Membrane | b77d2f7b-7db0-47e5-bf37-6185c443865e
checkpoint-status |  |  | checkpoint | Area ready?
checkpoint-status |  |  | checkpoint | Structure complies to the New Zealand Building Code and concrete complies with NZS 3101 (2006)
checkpoint-status |  |  | checkpoint | Concrete cured with curing membranes removed. Concrete substrate contains less than 5% moisture content
checkpoint-status |  |  | checkpoint | Surface smooth and clean with falls as per plan
checkpoint-status |  |  | checkpoint | Cavities and cracks filled with repair mortar, flushed off and cured
checkpoint-status |  |  | checkpoint | Concrete surface firm with any soft concrete or laitance removed
checkpoint-status |  |  | checkpoint | Ponding areas removed
checkpoint-status |  |  | checkpoint | Roof drains and overflow recesses formed to fit rebated outlets
checkpoint-status |  |  | checkpoint | Mortar or Profili Bitumen fillets to all upstands and smooth 5mm radius to all external edges
checkpoint-status |  |  | checkpoint | If terminating into a chase, pre-form the chase and ensure it is straight and 20mm deep
checkpoint-status |  |  | checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures
checkpoint-status |  |  | checkpoint | Construction joints incorporated in slab as per designers specification
checkpoint-status |  |  | checkpoint | Substrate clean, firm and suitable condition for laying the Nuralite systems
checkpoint-status |  |  | checkpoint | When substrate is ready complete send this as report to Nuralite applicator
holdpoint |  |  | signoff | Signed by head contractor
checklist-flat |  |  | checklist | SEALCO TPO - Plywood Substrate Readiness Checklist |  |  |  |  | Yes | SEALCO TPO - Plywood Substrate Readiness Checklist | d3fcdcc7-3f74-46d9-abe8-ce208fbe0842
checkpoint-status |  |  | checkpoint | Architect and builder are responsible for correct design, including falls, constructions and detailing of substrate.
checkpoint-status |  |  | checkpoint | CD Structural Grade H3.2 CCA treated Kiln Dried and min. 17mm thick.
checkpoint-status |  |  | checkpoint | Use only square edged construction plywood with all edges fully supported with timber battens. (T&G plywood not acceptable)
checkpoint-status |  |  | checkpoint | Sheets stagger laid (fully offset brick bond pattern), tight butted, with sanded C-face upwards and face grain at right angles to supports or crossmembers.
checkpoint-status |  |  | checkpoint | Plywood glued and screwed, fixed 150mm on edges and 200mm through girth.
checkpoint-status |  |  | checkpoint | Grade 316 stainless steel counter sunk screw fixing, min. 10-gauge x 50mm or a length 3 times that of the plywood thickness.
checkpoint-status |  |  | checkpoint | Plywood installed with correct falls and no ponding.
checkpoint-status |  |  | checkpoint | No fillets required; all internal angles formed at 90 degrees.
checkpoint-status |  |  | checkpoint | 3 - 5mm clearances from all abutments.
checkpoint-status |  |  | checkpoint | Pre-inspection of all penetrations and details.
checkpoint-status |  |  | checkpoint | 5mm radius to all external corners.
checkpoint-status |  |  | checkpoint | Using a moisture measure ensure moisture content at the time of installation is below 20%.
checkpoint-status |  |  | checkpoint | Rainwater outlets and overflow recesses formed in substrate to fit propriety outlets.
checkpoint-status |  |  | checkpoint | Sharp edges and lips removed, and cavities filled. All joints flush.
checkpoint-status |  |  | checkpoint | Substrate is clean, firm, and suitable condition for laying.
checkpoint-status |  |  | checkpoint | Plinths formed for any exterior ventilation, fixtures or similar.
checkpoint-status |  |  | checkpoint | Builder has installed flashings and tapes that are compatible with system
checklist-flat |  |  | checklist | Roof Readiness Checklist - Nuraply 3PM Membrane |  |  |  |  | Yes | Roof Readiness Checklist - Nuraply 3PM Membrane | da6e80cc-e940-4daa-89ea-dab9b875fb12
checkpoint-status |  |  | checkpoint | Area ready?
checkpoint-status |  |  | checkpoint | CCA H3.2 treated plywood sheets used
label | 5c5c4ef3-2ebe-5ec3-bb39-1dce4d34a4d0 |  | note | 17mm thick for roofs, 20mm thick for decks
checkpoint-status |  |  | checkpoint | Plywood sheets supported by joists and nogs at maximum 400mm centers in both directions, unless specified otherwise
checkpoint-status |  |  | checkpoint | Sheets stagger lay (fully offset) with the face grain at right angles to the primary supports
checkpoint-status |  |  | checkpoint | All sheet edges supported by nogs, fixed 100mm on edges and 200mm through girth, edges butt-jointed with no gaps except at abutments
checkpoint-status |  |  | checkpoint | Sheets glued in place and then fixed using 316 grade Stainless Steel 10 gauge countersunk screw fixings
checkpoint-status |  |  | checkpoint | All decks and gutters have correct falls once installed
checkpoint-status |  |  | checkpoint | Fillets installed to all internal junctions and neatly fitted with mitres neatly formed
checkpoint-status |  |  | checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface
checkpoint-status |  |  | checkpoint | 5mm clearances from all abutments, 5mm radius to all exposed edges
checkpoint-status |  |  | checkpoint | Sharp edges and lips removed and cavities filleted. All joints flush
checkpoint-status |  |  | checkpoint | Substrate dry, clean, firm and suitable condition for laying
holdpoint |  |  | signoff | signed by Titus
checklist-flat |  |  | checklist | New Plywood Substrate Readiness Checklist - Membrane |  |  |  |  | Yes | New Plywood Substrate Readiness Checklist - Membrane | fd22415a-9f00-4867-aba1-58fae0e46988
checkpoint-status |  |  | checkpoint | Area ready?
checkpoint-status |  |  | checkpoint | Structure complies to the New Zealand Building Code and plywood complies with AS/NZ 2269
checkpoint-status |  |  | checkpoint | CCA H3.2 treated plywood sheets used
label | 449e16b7-950d-5404-b229-ec1eb58e40d9 |  | note | 17mm thick for roofs, 20mm thick for decks
checkpoint-status |  |  | checkpoint | Plywood sheets supported at 600mm centred rafters and nogs for roofs and decks, unless otherwise specified
checkpoint-status |  |  | checkpoint | Sheets stagger lay (fully offset) with falls as per plan
checkpoint-status |  |  | checkpoint | 5mm clearances from all abutments, 5mm radius to all exposed edges
checkpoint-status |  |  | checkpoint | All sheet edges supported, fixed 150mm on edges and 200mm through girth, edges butt-jointed with no gaps except at abutments
checkpoint-status |  |  | checkpoint | Sheets fixed by gluing and Stainless Steel countersunk screw fixing
checkpoint-status |  |  | checkpoint | Fillets installed to all internal junctions and neatly fitted
checkpoint-status |  |  | checkpoint | Mitres neatly formed
checkpoint-status |  |  | checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface
checkpoint-status |  |  | checkpoint | Sharp edges and lips removed and cavities filleted. All joints flush
checkpoint-status |  |  | checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures
checkpoint-status |  |  | checkpoint | Substrate dry, clean, firm and suitable condition for laying
checkpoint-status |  |  | checkpoint | When substrate is ready complete send this as report to membrane applicator
holdpoint |  |  | signoff | Signed by head contractor
checklist-flat |  |  | checklist | New Plywood Substrate Readiness Checklist - Nuraply 3PM Membrane |  |  |  |  | Yes | New Plywood Substrate Readiness Checklist - Nuraply 3PM Membrane | ffe5f5f5-9d00-4c7b-8e96-fa3f160b0fd9
checkpoint-status |  |  | checkpoint | Area ready?
checkpoint-status |  |  | checkpoint | Structure complies to the New Zealand Building Code and plywood complies with AS/NZ 2269
checkpoint-status |  |  | checkpoint | CCA H3.2 treated plywood sheets used
label | 38776eed-88bf-5056-8e03-77365053fc80 |  | note | 17mm thick for roofs, 20mm thick for decks
checkpoint-status |  |  | checkpoint | Plywood sheets supported at 600mm centred rafters and nogs for roofs and decks, unless otherwise specified
checkpoint-status |  |  | checkpoint | Sheets stagger lay (fully offset) with falls as per plan
checkpoint-status |  |  | checkpoint | 5mm clearances from all abutments, 5mm radius to all exposed edges
checkpoint-status |  |  | checkpoint | All sheet edges supported, fixed 150mm on edges and 200mm through girth, edges butt-jointed with no gaps except at abutments
checkpoint-status |  |  | checkpoint | Sheets fixed by gluing and Stainless Steel countersunk screw fixing
checkpoint-status |  |  | checkpoint | Fillets installed to all internal junctions and neatly fitted
checkpoint-status |  |  | checkpoint | Mitres neatly formed
checkpoint-status |  |  | checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface
checkpoint-status |  |  | checkpoint | Sharp edges and lips removed and cavities filleted. All joints flush
checkpoint-status |  |  | checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures
checkpoint-status |  |  | checkpoint | Substrate dry, clean, firm and suitable condition for laying
checkpoint-status |  |  | checkpoint | When substrate is ready complete send this as report to Nuralite applicator
holdpoint |  |  | signoff | Signed by head contractor