## blank
INSPECTION & TEST PLAN WIRE ROPE
U16/53-57 Link Drive Yatala 4207 PH: 07 3803 7912 ABN: 76 122 395 135
Project: |  |  |  | Job No: |  | Date:
Client: |  |  |  | Run No: | Start Ch: |  |  | End Ch:
Client Contact: |  |  |  |  | Site Address:
Job Description |  |  |  |  | As Per Standard Drawing
As Per Suppliers Instruction
Type of Wire Rope Safety Fence Installed:
Quantity Installed |  |  |  | Inspection and Test |  |  | HOLD PT | Initial
Components | Quantity |  |  | Activity | Type of Test |  |  | To Spec | Not to Spec
|  |  |  | Set Out of system | Visual Inspection
Posts at 2 m Centres |  |  |  | Post Holes to Correct Depth | Checked with Tape
Posts at 3 m Centres |  |  |  | Post Heights and Levels Correct | Checked with Tape and Level
Posts as m Centres |  |  |  | Material Compliance Certified | Check Compliance Certificate |  | NA
Wire Rope Installed |  |  |  | Post Reflectors Installed | Visual Check |  | NA
End Terminals |  |  |  | Wire Rope Installed | Visual Check |  | NA
Tension Bays |  |  |  | Terminal Block Excavated to Size | Checked with Measuring Tape
Maintenance / Repairs to Terminals |  |  |  | Concrete Foundation Reinforcement Installed | Installed With Concrete
Maintenance / Repairs to Posts |  |  |  | Concrete Test | See Test Docket |  | NA
Maintenance / Repairs to Wire Rope |  |  |  | Post Caps Installed | Visual Check |  | NA
Anchor Concrete Doc No |  |  |  | Installed to manufacturers Specification
Date Anchor Installed |  |  |  | Area Cleaned Up | Visual Inspection
Post ID |  |  |  | Coil ID No | 1024890101
Tensioning of Wire Rope | [5 empty] | Gauge Reading
Date/ Time/Temp of Tensioning |  | Date Time (°C) |  |  |  | Top Rope |  | (kN)
Maximum Allowable Tension at Temperature |  |  | (kN) |  |  | 2nd Rope |  | (kN)
Minimum Allowable Tension at Temperature |  |  | (kN) |  |  | 3rd Rope |  | (kN)
[6 empty] | 4th Rope |  | (kN)
Additional Comments
I confirm that the above works have been installed in accordance with the Specification Requirements. Any minor alterations to the standards are stated on the attached NCR Report.
Signed by A1 Highways Rep: |  |  |  | Print Name |  | Date:
Signed by Client: |  |  |  | Print Name |  | Date: