## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | FT-01: Aluminium Joinery: |  | FT-01: Aluminium Joinery: | bd16d832-913a-41ef-9857-89a874e17ed8
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Substrate acceptable
a2d0b617-ee4b-5903-90a9-4490a7ff6fa8 | tickbox | Waterproofing complete
| checkpoint | Window frames installed
27b4fe8e-4808-52f5-b44e-89ed4751a6b6 | tickbox | Fixings correct
| checkpoint | Windows sealed
| checkpoint | Glazing installed
| checkpoint | Rainshield angle installed
| checkpoint | Any additional photos, comments and observations
| checklist | FT-02: Brick Veneer: |  | FT-02: Brick Veneer: | 7e2f645c-a090-4bab-8d99-210599d9856e
| section | Substrate
| checkpoint | Nib waterproofing complete
| checkpoint | Fire rating to steel complete
| checkpoint | Framing complete
e0f02510-161b-5530-a150-8c10fecd5233 | tickbox | Correct grade timber used
c4210b6c-86ef-5926-97bf-16899d6eb51a | tickbox | Set-out correct
71b4f07f-9c9f-5c9b-91e7-164517ae6f67 | tickbox | Fixings correct
| checkpoint | RAB installed
| checkpoint | Self adhesive membrane installed
4cb64277-bb10-5d27-816c-0fb55b749729 | tickbox | Penetrations sealed
| checkpoint | Flashing tape installed
| checkpoint | Steel angle installed
| checkpoint | Fire battens installed
| checkpoint | Any additional photos, comments and observations
| section | Brick
| checkpoint | Brick installed
14f33776-f2a6-5c7b-95e7-4be052d26a96 | tickbox | Clean outs provided
cc218ec2-5228-5754-940d-d080c0612d78 | tickbox | Weep holes installed
c1307f24-0676-5ede-8c97-9642c64c2d25 | tickbox | Wall ties correct
fa54c384-883a-5bfc-a7f0-4918a165d8fc | tickbox | Cavity within tolerance and clean
| checkpoint | Masonry records kept
| checkpoint | Stolit Bag Wash complete
| checkpoint | Any additional photos, comments and observations
| checklist | FT-03: Nu-wall: |  | FT-03: Nu-wall: | e32399c0-359f-48bc-ab88-079d4ed6eb56
| section | Substrate
| checkpoint | Nib waterproofing complete
| checkpoint | Fire rating to steel complete
| checkpoint | Framing complete
6e392a28-835a-549f-a9ce-24667abd2850 | tickbox | Correct grade timber used
7c518531-0d70-5dad-b53c-665d7188ff8d | tickbox | Set-out correct
944d6e2a-a300-5974-af82-c2eef74e08ed | tickbox | Fixings correct
| checkpoint | RAB installed
| checkpoint | Self adhesive membrane installed
b4086dfb-c31a-5ce4-887c-e4bcd51b00b3 | tickbox | Penetrations sealed
| checkpoint | Flashing tape installed
| checkpoint | Fire battens installed
| checkpoint | Any additional photos, comments and observations
| section | Nu-wall
| checkpoint | Extrusions and underflashings installed
| checkpoint | Panels installed
bdd18078-ee22-55d4-86fa-090a2f30399f | tickbox | Fixings correct
| checkpoint | Panels sealed
| checkpoint | Additional flashings installed
| checkpoint | Any additional photos, comments and observations
| checklist | FT-05: |  | FT-05: | 884a09d9-8bae-468b-a2f3-f9e2709aa843
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Substrate acceptable
| checkpoint | Mounting brackets installed
| checkpoint | Vertical louvres installed
| checkpoint | Any additional photos, comments and observations
| checkpoint | Trades QA received & attached as applicable
| checklist | FT-06: Balcony Timber Pergolas: |  | FT-06: Balcony Timber Pergolas: | 6e6919e8-69a1-4e61-8937-b9c372fed246
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Soffit framing installed
| checkpoint | Hermpac cedar installed
| checkpoint | Any additional photos, comments and observations
| checkpoint | Trades QA received & attached as applicable
| checklist | FT-07: Balcony Timber Screens: |  | FT-07: Balcony Timber Screens: | d1140b30-144f-43e1-9f8d-0d50f194c060
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Structural steel installed
| checkpoint | Timber framing complete
| checkpoint | Self adhesive membrane installed
| checkpoint | Aluminium panels installed
| checkpoint | Louvres installed
| checkpoint | Any additional photos, comments and observations
| checkpoint | Trades QA received & attached as applicable
fe1a87f5-bce5-4d9a-8319-1c496468ca65 | checklist | MMP Reporting |  | MMP Reporting | f230dfa6-5e22-46b9-9309-f6567244bfe6
92e2e170-8430-47ce-aea1-3beb7ebfccdf | section | MMP Reporting Details
1c29747a-28e1-4503-97e0-8ad0463dfa79 | checkpoint-no-value | Details
90dea922-5933-5b42-a055-5bcece175268 | date | Date
6b54b1d9-befa-523f-8913-134ceed8917f | dropdown | Instrument used | Trotec T510, Other - please specify in text box
9a64aadd-73cc-5174-b00d-cdaee29c1996 | textbox | -
3354a9a4-aed7-5c59-a08a-37a7f3612d40 | dropdown | Probing depth: | 20mm, 45mm, 20 & 45mm, Other - please specify in text box
ca1894b3-859e-5c4b-a745-875992018c98 | textbox | -
b163d359-fc94-564b-9579-f1cc0b7b75f9 | dropdown | Instrument calibration | TBC
c61d211b-fba1-5515-9988-203d41ead094 | date | Date Calibrated
73cc9e74-1d1e-5297-8dc7-0bfcf1924adc | dropdown | Weather at time of reading | Sunny, Overcast, Windy, Rainy, Other - please specify in textbox
16593c08-81a4-5f7f-9e14-263794f62d75 | textbox | -
b053fad5-c0bb-5891-8f08-80ecee7721d7 | textbox | Time since last rain
3529e297-f61d-5544-a74b-891eba887f67 | textbox | Air temperature humidity
cfede116-f9c4-4144-803a-8068df5ecd58 | checkpoint | Test location
6e1d6538-0dca-461c-bb11-e54b284e8c27 | section-nested-checklists | Test Results
| checklist | MT-01: Balcony Membrane: |  | MT-01: Balcony Membrane: | 286b1235-1d77-4f90-a8d8-e1b64bda75e4
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Substrate acceptable
| checkpoint | Membrane installed
| checkpoint | Saddle flashings installed
| checkpoint | Deck tiles installed
| checkpoint | Outlets installed
| checkpoint | Any additional photos, comments and observations
| checklist | QA - Concrete Pour |  | Concrete Pour for Area: | 54cd3388-be00-4f11-a1f8-2dae3b1f08b1
| section | Concrete Pre-pour
| checkpoint | Set-out correct
| checkpoint | Any/All cast in items checked / correct (location and size)
| checkpoint | Penetrations correctly formed / located, checked and accurate
| checkpoint | Reinforcing checked and correct
0b8b12f4-7aec-564f-adb6-923ede08c7fb | button | Size and type correct to specification | Yes, N/A
5a1a1978-5513-52bb-a763-305e1fb16372 | tickbox | Reinforcing spacing and location correct
8ef410a8-1bf3-5b47-a654-628373862bf0 | tickbox | Specified covers checked / correct
36b77f08-c984-5546-88a3-4a1667147e5c | tickbox | Splice laps checked/correct
ec071fad-d9c3-53c6-a0af-eebcb51685f6 | tickbox | Any starter bars are installed correctly (location, size and spacing )
654ba5e5-0dc2-52c6-b7e1-019d6011808d | tickbox | Any additional items installed / completed (trimmer bars etc) and excess reinforcing removed
| checkpoint | Waterproofing (checked and correct)
| checkpoint | Bottom of concrete pour is clean and free of debris / roughened
| checkpoint | Any additional photos, comments and observations
| checkpoint | Engineer informed of pour checks completed (see consultant folder and ensure observations are closed out)
| section | Concrete Pour /Post Pour
| checkpoint | General photos/comments/observations
5a059e79-6052-56c2-b453-7ded34f80758 | tickbox | All concrete dockets photographed/attached here
e289c314-c718-56fa-a76b-5e0a821b2216 | tickbox | Trades QA received & attached as applicable
| checklist | RT-01: Dimond Roof: |  | RT-01: Dimond Roof: | b617aaac-a630-4c2d-8626-26e05e859c39
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Framing complete
| checkpoint | Underlay installed
| checkpoint | Roofing installed
| checkpoint | Service penetrations installed
| checkpoint | Roof hatch installed
| checkpoint | Anchor points installed
| checkpoint | Flashings installed
| checkpoint | Gutters installed
| checkpoint | Soffit installed
| checkpoint | Roof/gutter testing witnessed by Inhabit
| checkpoint | Any additional photos, comments and observations
c623fe2c-4e3c-4797-ace5-2b99d73c76d5 | checklist | Test Results |  | Test Results | 45cf5f4c-119a-4fbb-a60d-ac77117bb329
3f8a5a86-f278-4c74-8ef8-e8eb30dca914 | checkpoint-no-value | Test Results
dd041405-9927-510b-af9c-58a9e6d72197 | button | Material being tested | CLT Timber
f42e7c2b-a7ef-522e-b5ab-8a2ae3af4c50 | dropdown | Elements being tested | Wall, Floor, Roof
95c986c5-18b2-5446-b145-46d0f5f3fba1 | dropdown | Packaging condition | Wrapped, Unwrapped
25ff7d66-cff7-54ec-8222-66b786b085cc | dropdown | Moisture at time of test | Wet, Dry, Damp
7d4ad9cf-5cf0-5b5a-bd8d-0177d7d1ecbc | textbox | Moisture Reading 1
9574fcc3-08c7-5297-ae44-3fb956e8b186 | textbox | Moisture Reading 2
7e083d53-da96-516f-b9b4-5c792bb506b1 | textbox | Moisture Reading 3
9b2d3ac0-c71d-5784-8fad-23ea6e4f7799 | textbox | Moisture Reading Average
cafa883d-413d-444d-9ba6-a9affc069a5e | checkpoint | Photos