## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Shoulder Widening | itp |  |  |  |  | ITP - Shoulder Widening Rev 0
section | 1.0. AGGREGATE ACCEPTANCE TESTING
checkpoint | 1.00 - AP40 Basecourse Aggregates used for overlay
label | Detail of Activity / Test - Crushing Resistance
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 10,000 m3
label | Inspection / Test method - NZS4407:3.10
label | Acceptance Criteria - < 10% passing 2.36mm sieve at 130kN
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.01 - AP40 Basecourse Aggregates used for overlay
label | Detail of Activity / Test - Particle Size Distribution
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m3
label | Inspection / Test method - NZS4407:3.8.1
label | Acceptance Criteria - NZTA M04:2024-Class 2
label | ○ Class 2 in Table 12 for PSD
label | ○ Table 13 for shape control
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
section | 2.0. Construction
checkpoint | 2.01 - Mark out earthwork extents
label | Detail of Activity / Test - Set out and approve extent of earthworks
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to earthworks
label | Inspection / Test method - Visual
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.02 - Earthworks
label | Detail of Activity / Test - Cut 150mm rebate at Edge of seal (EOS) and strip organic material from shoulder
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - As per design drawings
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.03 - M04 AP40 Placement
label | Detail of Activity / Test - M04 AP40 Placed in Accordance with Design Drawing and Survey
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - As per design drawings
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - In Accordance with Design Drawing
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.04 - M04 AP40 Compaction
label | Detail of Activity / Test - Compact in Layers no greater than 150mm.
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1MDD Test per 50m
label | Inspection / Test method - Nuclear Densometer MDD Test
label | Acceptance Criteria - Average of 95% MDD with individual result >/= 92%
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature