## WRSB Install
|  |  |  | Construction Process: | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | 0 | 1 | 2 | 3
[5 empty] | Finish RP |  | Prepared by Project Engineer: |  | PE name | dd/mm/yy
|  |  |  | Project Name: Tirau to Waiouru Rehabilitation Acceleration Programe (TWRAP) Works |  |  | Reviewed by Construction Manager: |  | PM name | dd/mm/yy
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Surfacing or Pavement Manager | dd/mm/yy
Client's Rep. : Engineers Rep Name |  | Contractor's Rep. : Contractor's Rep Name |  | Specifications: NZTA M23, NZTA B/2, Wire Rope Safety Barrier |  |  | Approved Quality Manager.: |  | Nominated by Group Quality Manager | dd/mm/yy
[7 empty] | Approved Pavements SME.: |  | Responsible Group SME | dd/mm/yy
[7 empty] | Issued by: Project Engineer: |  | PE name | dd/mm/yy
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by R = Responsible, I, Informed, A = Approve |  |  |  | Comment
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) | Inspection / Test method |  |  |  |  | Sire Engineer | Eng. Rep / NZTA | Contractor | Date
1.0. GUARDRAIL HARDWARE ACCEPTANCE
1.01 | Guardrail Hardware | MASH Tested | H | 1 Test per material per source | Visual / Photo | AS/NZS3845 | Data Sheet / Delivery docket | Contractor |  | A | I | R | dd/mm/yy | Data sheet / Delviery docket
1.02 | Labelling | All components labelled with AS/NZS3845 | H | 1 Test per material per source | Visual / Photo | AS/NZS3845 | Product/ supplier certification | Contractor |  | A | I | R | dd/mm/yy | Data sheet / Delviery docket
2.0. CONSTRUCTION
2.01 | Leading and trailing treatments | Start and End locations marked out | W | All barrier lengths | Visual | Positions in agreed marked out location | Check sheet | Contractor | Note: Terminal excavation measured for acceptance against supplier diagram, Anchor bracket installed as per supplier specification and Concrete poured and screened flush or slightly proud of seal. | A | I | R | dd/mm/yy
2.02 | Leading and trailing treatments | Correct type | W | All barrier lengths | Visual | Types as specified on drawings | Check sheet | Contractor |  | A | I | R | dd/mm/yy
2.03 | Excavate WRSB Post Holes | Excavate post holes to a depth as specified in the design drawing | M | Where every post will be installed | Measure | Site Engineers Approval | Photo / Measurement Sheet | Contractor | Sides of excavation shall be parallel and not collapsing | A | I | R | dd/mm/yy
2.04 | Cast concrete into WRSB pile | Check condition of finished pile | M | All piles | Visual / Photo | Top of pile is level and Flush with ground at front face of pile | As per manufacturer's checklist | Contractor |  | A | I | R | dd/mm/yy
2.05 | Install WRSB | Install MashFlex post at a depth specified in the design drawing and above finished road level | H | Where every post will be installed | Visual / Photo | Site Engineers Approval | As per manufacturer's checklist | Contractor |  | I | A | R | dd/mm/yy
2.06 | Install WRSB | Cables at correct position as per manufacturer's installation manual | M | All post | Visual / Photo | Cables are in or on the seating position | As per manufacturer's checklist | Contractor |  | A | I | R | dd/mm/yy
2.07 | Install WRSB | Ensure posts have plastic cap inserted into the post and insert MashFlex Plug into hole on side of cap. | M | All post | Visual / Photo | 100% | As per manufacturer's checklist | Contractor |  | A | I | R | dd/mm/yy
2.08 | Install WRSB | All cables are tensioned correctly | M | All barrier lengths | Visual / Photo | As per manufacturer's installation manual | Photo | Contractor |  | A | I | R | dd/mm/yy
As per manufacturer's checklist
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.