## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - WRSB Installation | itp |  |  |  |  | ITP - WRSB Installation Rev 0
section | 1.0. GUARDRAIL HARDWARE ACCEPTANCE
checkpoint | 1.01 - Guardrail Hardware
label | Detail of Activity / Test - MASH Tested
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - AS/NZS3845
label | Record documents (QCP - Quality Control Portal) - Data Sheet / Delivery docket
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - Labelling
label | Detail of Activity / Test - All components labelled with AS/NZS3845
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - AS/NZS3845
label | Record documents (QCP - Quality Control Portal) - Product/ supplier certification
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
section | 2.0. CONSTRUCTION
checkpoint | 2.01 - Leading and trailing treatments
label | Detail of Activity / Test - Start and End locations marked out
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - All barrier lengths
label | Inspection / Test method - Visual
label | Acceptance Criteria - Positions in agreed marked out location
label | Record documents (QCP - Quality Control Portal) - Check sheet
label | Responsibility - Contractor
label | Project Specific Notes / Instructions - Note: Terminal excavation measured for acceptance against supplier diagram, Anchor bracket installed as per supplier specification and Concrete poured and screened flush or slightly proud of seal.
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.02 - Leading and trailing treatments
label | Detail of Activity / Test - Correct type
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - All barrier lengths
label | Inspection / Test method - Visual
label | Acceptance Criteria - Types as specified on drawings
label | Record documents (QCP - Quality Control Portal) - Check sheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.03 - Excavate WRSB Post Holes
label | Detail of Activity / Test - Excavate post holes to a depth as specified in the design drawing
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Where every post will be installed
label | Inspection / Test method - Measure
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Photo / Measurement Sheet
label | Responsibility - Contractor
label | Project Specific Notes / Instructions - Sides of excavation shall be parallel and not collapsing
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.04 - Cast concrete into WRSB pile
label | Detail of Activity / Test - Check condition of finished pile
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - All piles
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Top of pile is level and Flush with ground at front face of pile
label | Record documents (QCP - Quality Control Portal) - As per manufacturer's checklist
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.05 - Install WRSB
label | Detail of Activity / Test - Install MashFlex post at a depth specified in the design drawing and above finished road level
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Where every post will be installed
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - As per manufacturer's checklist
label | Responsibility - Contractor
label | Site Engineer - I
label | Eng. Rep / NZTA - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.06 - Install WRSB
label | Detail of Activity / Test - Cables at correct position as per manufacturer's installation manual
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - All post
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Cables are in or on the seating position
label | Record documents (QCP - Quality Control Portal) - As per manufacturer's checklist
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.07 - Install WRSB
label | Detail of Activity / Test - Ensure posts have plastic cap inserted into the post and insert MashFlex Plug into hole on side of cap.
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - All post
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - 100%
label | Record documents (QCP - Quality Control Portal) - As per manufacturer's checklist
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.08 - Install WRSB
label | Detail of Activity / Test - All cables are tensioned correctly
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - All barrier lengths
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - As per manufacturer's installation manual
label | Record documents (QCP - Quality Control Portal) - Photo
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature