## Table 1
Inspection Test Plan Title: |  |  |  | Internal Waterproofing | [6 empty] | ITP No: | [5 empty] | Date:
Contract No: |  |  |  | 1270 | [6 empty] | ITP Location: (e.g. Level 1)
Project Name: |  |  |  | Cambridge Street, Epping | [6 empty] | Principal Contractor |  | Richard Crookes Constructions
Project Address: |  |  |  | 6 Cambridge Street, Epping NSW 2121
Item No. | Work items and/or activities to be verified |  |  | Timing / Frequency | Method |  | Inspection / Test Done By | [5 empty] | Verification Type |  | Acceptance Criteria |  |  | References (Dwg No, Spec, Aust. Standard) |  |  | Record Type
[7 empty] | Position |  | Company |  |  |  | S/C | RCC
1 | Acceptance of substrate by Waterproofing Subcontractor & 3rd Party WC. --Smooth flat finish to falls (no negative falls) Free of deep depressions and/or protrusions Sheeting finished 2-5mm from concrete substrate Check wall finishes are flush Door frames 5mm above threshold |  |  | All items to be checked for each area before any works commence | Visual |  | SC /WC/E |  | 3rd Party WC |  |  |  | H | H | As per manufacturer’s recommendations & 3rd Party Consultant |  |  | Manufacturer Tech data sheets |  |  | 3rd Party WC Report
2 | Mechanically fix angles/waterstops in accordance with documentation |  |  | Before works commence | Visual |  | SC |  | MDS Stone |  |  |  | S | W | As per drawings, specification, 3rd Party Consultant recommendations
3 | Prime Area using approved non-porous primer and allow to cure |  |  | Each area | Review Docs |  | SC |  | MDS Stone |  |  |  | S | W | As per manufacturer recommendations and spec |  |  | AS-3740 |  |  | Photo Records Curing Time…….
4 | Caulking of all joints, penetrations and changes of direction with approved polyurethane joint sealant. |  |  | Each area | Visual |  | SC/WC |  | MDS Stone |  |  |  | S | W | As per manufacturer recommendations and standard |  |  | AS-3740 |  |  | Photo records
5 | Apply first coat of liquid applied waterproof membrane and measure wet film thickness |  |  | Each area | Physical measure with comb gauge |  | SC/E |  | MDS Stone |  |  |  | V | W | As per manufacturer recommendations and spec | [5 empty] | Minimum 3 test / area / coat. logged in register
6 | Apply second coat of liquid applied waterproof membrane and measure wet film thickness |  |  | Each area | Physical measure with comb gauge |  | SC/E |  | MDS Stone |  |  |  | V | W | As per manufacturer recommendations and spec | [5 empty] | Minimum 3 test / area / coat. Logged in register
7 | Allow Curing Times (Liquid Membranes) in accordance with manufacturers spec |  |  | Each area | Inspection |  | SC/E |  | MDS Stone |  |  |  | S | W | As per manufacturer recommendations and spec | [5 empty] | Curing Time………
8 | Water flood testing to be carried out to ALL WET AREAS. Flood test to a depth of 5mm below highest water- stop. Flood test duration 2 days |  |  | All wet areas | Visual Include photos |  | SC/E |  | MDS Stone |  |  |  | H | H | Verification photos to ALL WET AREAS |  |  | AS-3740 |  |  | Photos of ALL flood testing
9 | Acceptance of waterproof membrane areas by a tiler |  |  | Each area | Visual |  | SC (Tiler) |  | MDS Stone |  |  |  | H | H | As per manufacturer & 3rd Party Consultant recommendations
10 | Tilers install screed. Confirm the specified fall on screed has been achieved Showers (1:80mm min.) Bathrooms (1:100mm min.) |  |  | Each Area | Visual (Level Check) |  | SC/F |  | MDS Stone |  |  |  | H | H | Acceptance of screed by waterproofing subcontractor
11 | Prime screed & upturns & allow to cure as per manufacturers recommendation |  |  | Before tiling works commence | Visual |  | SC |  | MDS Stone |  |  |  | S | W | Manufacturers Curing time…….
12 | Joint seal perimeter |  |  | Before tiling works commence | Visual |  | SC |  | MDS Stone |  |  |  | S | W | As per drawings, specification & manufacturers recommendations |  |  | AS-3740
13 | Apply approved wet film screed to shower walls & splashbacks to manufacturers approved thickness and allow to cure |  |  | Before tiling works commence | Visual |  | SC |  | MDS Stone |  |  |  | S | W | As per drawings, specification& manufacturers recommendations |  |  | AS-3740
Non-Conformances / Issues:
Item No. | NC No. | Description | [7 empty] | Corrective Action Required |  |  |  | Responsibility |  | By When (Date) |  |  | Verified as Actioned By |  |  | Date Closed
Additional Comments:
Prepared by Subcontractor: | [7 empty] | Reviewed by:
Company Name: |  |  | MDS Stone Pty Ltd |  |  |  |  | Company Name: |  |  |  | Richard Crookes Constructions
Full Name (Print): | [7 empty] | Full Name (Print):
Position: | [7 empty] | Position: |  |  |  | ☐Project Manager ☐Site Manager ☐ Foreman
Signature: | [7 empty] | Signature:
Date: | [7 empty] | Date:
Legend |  |  | W – Witness |  |  |  The Engineer or Consultant or RCC may review, witness, inspect method or process of work. The activities however may proceed. | [13 empty] | PM |  Project Manager
|  |  | H – Hold Point |  |  |  The “hold” in “hold point” refers to putting a hold on construction activities until an inspection is passed by an Engineer, Consultant or RCC | [13 empty] | SM |  Site Manager
|  |  | V – Verify |  |  |  A document, drawing, photo or similar must be submitted and attached (such as site plans, DA, spec, report) | [13 empty] | FM |  Foreman
|  |  | S – Surveillance |  |  |  Periodic monitoring of any stage of the work in progress (whether by Subcontractor, RCC or the Client). | [13 empty] | CA |  Contract Administrator
|  |  | IR – Inspection Record / Review Docs |  |  |  The responsible party must review the record/document to ensure that the check, inspection or test has been done and it has passed. | [13 empty] | C |  Consultant
|  |  | NC – Non-conformance |  |  |  If a work item or activity does not comply, and if a Non-Conformance is raised, input Non-Conformance Report number in the ‘NC No’. section. | [13 empty] | E |  Engineer
|  |  | RCC Sign Off |  |  |  To be signed off by only the Site Manager, Foreman or Project Manager | [13 empty] | SC |  Subcontractor