## Table 1
Item No. | Work items and/or activities to be verified |  |  | Timing / Frequency | Method | Verification Type |  | Acceptance Criteria |  | Record Type |  | References (Dwg No,
[6 empty] | SC | RCC |  |  |  |  | Spec, Aust. Standard
1 | Submit samples and material data sheets for approval by Architect/Client |  |  | Prior to commencing | Visual | V | H | Submit Sample and Technical Data Submission and Approval Form in accordance with specification or its equivalent with Technical Data Sheet and Slip Test Report. |  | Approved Sample and Technical Data Submission and Approval Form
Safety
2 | 2.1 Mandatory WHS certificates are sighted & copied. |  |  | Prior to commencing | Visual | S | W | Safe Work Method Statement (SWMS) to be approved prior to commencement |  | Approved Safe Work Method Statement (SWMS)
| 2.2 SWMS complete & all workers have been inducted into the SWMS |  |  | Prior to commencing | Visual | V | W | Safe Work Method Statement (SWMS) to be approved prior to commencement |  | Approved Safe Work Method Statement (SWMS)
| 2.3 Check and ensure access to work area. |  |  | Prior to commencing | Visual | S | W | Safe Work Method Statement (SWMS) to be approved prior to commencement |  | Approved Safe Work Method Statement (SWMS)
| 2.4 Additional safety risks |  |  | Prior to commencing | Visual | S | W | Safe Work Method Statement (SWMS) to be approved prior to commencement |  | Approved Safe Work Method Statement (SWMS)
Setout
3 | 3.1 Check and confirm waterproofing has been completed before commencing work in wet areas. |  |  | Prior to Commencing tiling areas | Visual | S | W | As per spec, Manufacturer recommendations & 3rd Party Consultant Confirmation |  | ITP
| 3.2 Check angles and levels are correct using a digital level. |  |  | Prior to Commencing tiling areas | Visual and testing
| 3.3 Check and measure correct falls in wet areas. |  |  | Prior to Commencing tiling areas | Visual | S | W
| 3.4 Inspect work area |  |  | Prior to Commencing tiling areas | Visual | S | W
| 3.5 Check set-out points |  |  | Prior to Commencing tiling areas | Visual | S | H
| 3.6 Set out of angles above wall/skirting tiles |  |  | Prior to Commencing tiling areas | Visual | S | H
4 | Check and ensure all materials delivered to site as per approved submitted samples |  |  | Prior to commencing | Visual | S | S |  |  | Delivery Dockets
Installation of Sand & Cement screed
5 | 5.1 Check and ensure sand clean and without any sharps |  |  | Prior to commencing | Visual | S | W | As per drawings and spec
| 5.2 Check and ensure FFL before installation of bedding |  |  | Prior to commencing | Visual | S | W | As per drawings and spec
| 5.3 Ensure sand & cement ratio is correct which is 4:1 |  |  | Prior to commencing | Visual | S | W | As per drawings and spec
| 5.4 Screed curing time is 3-4 days before glue is applied |  |  | Prior to commencing | Visual | S | W | As per drawings and spec
| 5.5 Check that an admixture is being used in the bedding mix in accordance with the manufacturer’s specification and method statement |  |  | Prior to commencing | Visual | S | W | As per drawings and spec
| 5.6 Carry out impact tests to establish the soundness of all screeded substrates. Testing shall include both light tap and heavy weight impact using 4kg, in compliance with a screed tester. Alternative substrate testing methods may be put forward for consideration and acceptance by the Superintendent. |  |  | Prior to commencing | Visual | S | W | As per drawings and spec
Installation of Tiles/Pavers
6 | 6.1 Check and ensure specification that correct tile/paver has been supplied. |  |  | Prior to commencing | Visual | S | W | As per drawings and as per approved sample |  | Approved Sample and Technical Data Submission and Approval Form
| 6.2 Check and ensure walls & floors for square & straightness |  |  | Prior to commencing | Visual | S | W | As per drawings and as per approved sample |  | Approved Sample and Technical Data Submission and Approval Form
| 6.3 Check and ensure grout joint widths |  |  | Prior to commencing | Visual | S | W | As per drawings and as per approved sample |  | Approved Sample and Technical Data Submission and Approval Form
| 6.4 Check layout of expansion joints and sizes |  |  | Prior to commencing | Visual | S | W | As per drawings and as per approved sample |  | Approved Sample and Technical Data Submission and Approval Form
| 6.5 Install vertical and horizontal trims, half moons |  |  | Prior to commencing | Visual | S | W | As per drawings and as per approved sample |  | Approved Sample and Technical Data Submission and Approval Form
| 6.6 Installation of floor waste in wet areas |  |  | Prior to commencing | Visual | S | W | As per drawings and as per approved sample |  | Approved Sample and Technical Data Submission and Approval Form
| 6.7 Protection to floor waste during screeding |  |  | Prior to commencing | Visual | S | W | As per drawings and as per approved sample |  | Approved Sample and Technical Data Submission and Approval Form
| 6.8 Wall tiles to be fixed before floor tiles. |  |  | Prior to commencing | Visual | S | W | As per drawings and as per approved sample |  | Approved Sample and Technical Data Submission and Approval Form
| 6.9 Mortar bed complete with correct ramps / fall to wastes – 1:60 minimum to shower areas and 1:100 outside the showers |  |  | Prior to commencing | Visual | S | W | As per drawings and as per approved sample |  | Approved Sample and Technical Data Submission and Approval Form
| 6.10 Ponding Testing-Floor tiles laid to correct RL’s with correct ramps and fall to wastes without ponding |  |  | Prior to commencing | Visual | S | W | As per drawings and as per approved sample |  | Approved Sample and Technical Data Submission and Approval Form
| 6.11 Ensure that excessive water is not added to the mix |  |  | Prior to commencing | Visual | S | W | As per drawings and as per approved sample |  | Approved Sample and Technical Data Submission and Approval Form
| 6.12 Ensure proper curing of concrete |  |  | Prior to commencing | Visual | S | W | As per drawings and as per approved sample |  | Approved Sample and Technical Data Submission and Approval Form
| 6.13 Verify that there is adhesion over the whole tile area |  |  | Prior to commencing | Visual | S | W | As per drawings and as per approved sample |  | Approved Sample and Technical Data Submission and Approval Form
Grouting
7 | 7.1 Check and ensure correct grout is used including colour and type of grout and thickness |  |  | Before commencing grouting works | Visual/Photos | V | H | As per specification grouting sample to be approved prior to grout commencement |  | Approved Sample and Technical Data Submission and Approval Form
| 7.2 Check and confirm caulking |  |  | Before commencing grouting works | Visual/Photos | V | H | As per specification grouting sample to be approved prior to grout commencement |  | Approved Sample and Technical Data Submission and Approval Form
Cleaning
8 | 8.1 Checks falls using digital laser pre and post tiling |  |  | All areas | Visual | S | H | In accordance with Design
8 | 8.2 Ensure workplace is left clean & free of defects. |  |  | All areas | Visual | S | H | In accordance with Design
8 | 8.3 Ensure floor wastes are protected from any materials and debris deposited |  |  | All areas | Visual | S | H | In accordance with Design
8 | 8.4 Floor wastes are protected (tapes or other means of protection) |  |  | All areas | Visual | S | H | In accordance with Design
8 | 8.5 Protection of floor and wall tiles at wet areas. |  |  | All areas | Visual | S | H | In accordance with Design
8 | 8.6 Clean tiles & remove all boxes & leftover tiles |  |  | All areas | Visual | S | H | In accordance with Design
Additional Comments:
Prepared by:
Company Name: |  | MDS Stone Pty Ltd
Full Name (Print):
Position: |  | ☐Project Manager ☐Site Manager
Signature:
Date:
Legend |  | W – Witness |  The Engineer or Consultant or RCC may review, witness, inspect method or process of work. The activities however may proceed. | [5 empty] | PM |  |  Project Manager
|  | H – Hold Point |  The “hold” in “hold point” refers to putting a hold on construction activities until an inspection is passed by an Engineer, Consultant or RCC | [5 empty] | SM |  |  Site Manager
|  | V – Verify |  A document, drawing, photo or similar must be submitted and attached (such as site plans, DA, spec, report) | [5 empty] | FM |  |  Foreman
|  | S – Surveillance |  Periodic monitoring of any stage of the work in progress (whether by Subcontractor, RCC or the Client). | [5 empty] | SC |  |  Subcontractor
|  | IR – Inspection Record / Review Docs |  The responsible party must review the record/document to ensure that the check, inspection or test has been done and it has passed. | [7 empty] | 
|  |  |  | [7 empty] | 