## Sheet1
[7 empty] | - | Timing / Frequency - | Method - | Inspection / Test Done By: Position - | Inspection / Test Done By: Company - | Verification Type: S/C - | Verification Type: RCC - | Acceptance Criteria - | References (Dwg No, Spec, Aust. Standard) - | Record Type - | -
Timing / Frequency -
Method -
Inspection / Test Done By: Position -
Inspection / Test Done By: Company -
Verification Type: S/C -
Verification Type: RCC -
Acceptance Criteria -
References (Dwg No, Spec, Aust. Standard) -
Record Type -
2.1 Mandatory WHS certificates are sighted CHAR(AMP) copied. | Prior to commencing | Visual | S | W | Safe Work Method Statement (SWMS) to be approved prior to commencement | Approved Safe Work Method Statement (SWMS) | 2.1 Mandatory WHS certificates are sighted CHAR(AMP) copied. | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - Safe Work Method Statement (SWMS) to be approved prior to commencement | Record Type - Approved Safe Work Method Statement (SWMS) |  |  |  | 2.1 Mandatory WHS certificates are sighted CHAR(AMP) copied.
2.2 SWMS complete CHAR(AMP) all workers have been inducted into the SWMS | Prior to commencing | Visual | V | W | Safe Work Method Statement (SWMS) to be approved prior to commencement | Approved Safe Work Method Statement (SWMS) | 2.2 SWMS complete CHAR(AMP) all workers have been inducted into the SWMS | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - V | Verification Type: RCC - W | Acceptance Criteria - Safe Work Method Statement (SWMS) to be approved prior to commencement | Record Type - Approved Safe Work Method Statement (SWMS) |  |  |  | Timing / Frequency - Prior to commencing
2.3 Check and ensure access to work area. | Prior to commencing | Visual | S | W | Safe Work Method Statement (SWMS) to be approved prior to commencement | Approved Safe Work Method Statement (SWMS) | 2.3 Check and ensure access to work area. | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - Safe Work Method Statement (SWMS) to be approved prior to commencement | Record Type - Approved Safe Work Method Statement (SWMS) |  |  |  | Method - Visual
2.4 Additional safety risks | Prior to commencing | Visual | S | W | Safe Work Method Statement (SWMS) to be approved prior to commencement | Approved Safe Work Method Statement (SWMS) | 2.4 Additional safety risks | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - Safe Work Method Statement (SWMS) to be approved prior to commencement | Record Type - Approved Safe Work Method Statement (SWMS) |  |  |  | Verification Type: SC - S
3.1 Check and confirm waterproofing has been completed before commencing work in wet areas. | Prior to Commencing tiling areas | Visual | S | W | As per spec, Manufacturer recommendations CHAR(AMP) 3rd Party Consultant Confirmation | ITP | 3.1 Check and confirm waterproofing has been completed before commencing work in wet areas. | Timing / Frequency - Prior to Commencing tiling areas | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - As per spec, Manufacturer recommendations CHAR(AMP) 3rd Party Consultant Confirmation | Record Type - ITP |  |  |  | Verification Type: RCC - W
3.2 Check angles and levels are correct using a digital level. | Prior to Commencing tiling areas | Visual and testing |  |  |  |  | 3.2 Check angles and levels are correct using a digital level. | Timing / Frequency - Prior to Commencing tiling areas | Method - Visual and testing | Verification Type: SC - | Verification Type: RCC - | Acceptance Criteria - | Record Type - |  |  |  | Acceptance Criteria - Safe Work Method Statement (SWMS) to be approved prior to commencement
3.3 Check and measure correct falls in wet areas. | Prior to Commencing tiling areas | Visual | S | W |  |  | 3.3 Check and measure correct falls in wet areas. | Timing / Frequency - Prior to Commencing tiling areas | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - | Record Type - |  |  |  | Record Type - Approved Safe Work Method Statement (SWMS)
3.4 Inspect work area | Prior to Commencing tiling areas | Visual | S | W |  |  | 3.4 Inspect work area | Timing / Frequency - Prior to Commencing tiling areas | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - | Record Type - |  |  |  | 2.2 SWMS complete CHAR(AMP) all workers have been inducted into the SWMS
3.5 Check set-out points | Prior to Commencing tiling areas | Visual | S | H |  |  | 3.5 Check set-out points | Timing / Frequency - Prior to Commencing tiling areas | Method - Visual | Verification Type: SC - S | Verification Type: RCC - H | Acceptance Criteria - | Record Type - |  |  |  | Timing / Frequency - Prior to commencing
3.6 Set out of angles above wall/skirting tiles | Prior to Commencing tiling areas | Visual | S | H |  |  | 3.6 Set out of angles above wall/skirting tiles | Timing / Frequency - Prior to Commencing tiling areas | Method - Visual | Verification Type: SC - S | Verification Type: RCC - H | Acceptance Criteria - | Record Type - |  |  |  | Method - Visual
Check and ensure all materials delivered to site as per approved submitted samples | Prior to commencing | Visual | S | S |  | Delivery Dockets | Check and ensure all materials delivered to site as per approved submitted samples | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - S | Acceptance Criteria - | Record Type - Delivery Dockets |  |  |  | Verification Type: SC - V
5.1 Check and ensure sand clean and without any sharps | Prior to commencing | Visual | S | W | As per drawings and spec |  | 5.1 Check and ensure sand clean and without any sharps | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - As per drawings and spec | Record Type - |  |  |  | Verification Type: RCC - W
5.2 Check and ensure FFL before installation of bedding | Prior to commencing | Visual | S | W | As per drawings and spec |  | 5.2 Check and ensure FFL before installation of bedding | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - As per drawings and spec | Record Type - |  |  |  | Acceptance Criteria - Safe Work Method Statement (SWMS) to be approved prior to commencement
5.3 Ensure sand CHAR(AMP) cement ratio is correct which is 4:1 | Prior to commencing | Visual | S | W | As per drawings and spec |  | 5.3 Ensure sand CHAR(AMP) cement ratio is correct which is 4:1 | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - As per drawings and spec | Record Type - |  |  |  | Record Type - Approved Safe Work Method Statement (SWMS)
5.4 Screed curing time is 3-4 days before glue is applied | Prior to commencing | Visual | S | W | As per drawings and spec |  | 5.4 Screed curing time is 3-4 days before glue is applied | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - As per drawings and spec | Record Type - |  |  |  | 2.3 Check and ensure access to work area.
5.5 Check that an admixture is being used in the bedding mix in accordance with the manufacturer’s specification and method statement | Prior to commencing | Visual | S | W | As per drawings and spec |  | 5.5 Check that an admixture is being used in the bedding mix in accordance with the manufacturer’s specification and method statement | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - As per drawings and spec | Record Type - |  |  |  | Timing / Frequency - Prior to commencing
5.6 Carry out impact tests to establish the soundness of all screeded substrates. Testing shall include both light tap and heavy weight impact using 4kg, in compliance with a screed tester. Alternative substrate testing methods may be put forward for consideration and acceptance by the Superintendent. | Prior to commencing | Visual | S | W | As per drawings and spec |  | 5.6 Carry out impact tests to establish the soundness of all screeded substrates. Testing shall include both light tap and heavy weight impact using 4kg, in compliance with a screed tester. Alternative substrate testing methods may be put forward for consideration and acceptance by the Superintendent. | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - As per drawings and spec | Record Type - |  |  |  | Method - Visual
6.1 Check and ensure specification that correct tile/paver has been supplied. | Prior to commencing | Visual | S | W | As per drawings and as per approved sample | Approved Sample and Technical Data Submission and Approval Form | 6.1 Check and ensure specification that correct tile/paver has been supplied. | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - As per drawings and as per approved sample | Record Type - Approved Sample and Technical Data Submission and Approval Form |  |  |  | Verification Type: SC - S
6.2 Check and ensure walls CHAR(AMP) floors for square CHAR(AMP) straightness | Prior to commencing | Visual | S | W | As per drawings and as per approved sample | Approved Sample and Technical Data Submission and Approval Form | 6.2 Check and ensure walls CHAR(AMP) floors for square CHAR(AMP) straightness | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - As per drawings and as per approved sample | Record Type - Approved Sample and Technical Data Submission and Approval Form |  |  |  | Verification Type: RCC - W
6.3 Check and ensure grout joint widths | Prior to commencing | Visual | S | W | As per drawings and as per approved sample | Approved Sample and Technical Data Submission and Approval Form | 6.3 Check and ensure grout joint widths | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - As per drawings and as per approved sample | Record Type - Approved Sample and Technical Data Submission and Approval Form |  |  |  | Acceptance Criteria - Safe Work Method Statement (SWMS) to be approved prior to commencement
6.4 Check layout of expansion joints and sizes | Prior to commencing | Visual | S | W | As per drawings and as per approved sample | Approved Sample and Technical Data Submission and Approval Form | 6.4 Check layout of expansion joints and sizes | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - As per drawings and as per approved sample | Record Type - Approved Sample and Technical Data Submission and Approval Form |  |  |  | Record Type - Approved Safe Work Method Statement (SWMS)
6.5 Install vertical and horizontal trims, half moons | Prior to commencing | Visual | S | W | As per drawings and as per approved sample | Approved Sample and Technical Data Submission and Approval Form | 6.5 Install vertical and horizontal trims, half moons | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - As per drawings and as per approved sample | Record Type - Approved Sample and Technical Data Submission and Approval Form |  |  |  | 2.4 Additional safety risks
6.6 Installation of floor waste in wet areas | Prior to commencing | Visual | S | W | As per drawings and as per approved sample | Approved Sample and Technical Data Submission and Approval Form | 6.6 Installation of floor waste in wet areas | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - As per drawings and as per approved sample | Record Type - Approved Sample and Technical Data Submission and Approval Form |  |  |  | Timing / Frequency - Prior to commencing
6.7 Protection to floor waste during screeding | Prior to commencing | Visual | S | W | As per drawings and as per approved sample | Approved Sample and Technical Data Submission and Approval Form | 6.7 Protection to floor waste during screeding | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - As per drawings and as per approved sample | Record Type - Approved Sample and Technical Data Submission and Approval Form |  |  |  | Method - Visual
6.8 Wall tiles to be fixed before floor tiles. | Prior to commencing | Visual | S | W | As per drawings and as per approved sample | Approved Sample and Technical Data Submission and Approval Form | 6.8 Wall tiles to be fixed before floor tiles. | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - As per drawings and as per approved sample | Record Type - Approved Sample and Technical Data Submission and Approval Form |  |  |  | Verification Type: SC - S
6.9 Mortar bed complete with correct ramps / fall to wastes – 1:60 minimum to shower areas and 1:100 outside the showers | Prior to commencing | Visual | S | W | As per drawings and as per approved sample | Approved Sample and Technical Data Submission and Approval Form | 6.9 Mortar bed complete with correct ramps / fall to wastes – 1:60 minimum to shower areas and 1:100 outside the showers | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - As per drawings and as per approved sample | Record Type - Approved Sample and Technical Data Submission and Approval Form |  |  |  | Verification Type: RCC - W
6.10 Ponding Testing-Floor tiles laid to correct RL’s with correct ramps and fall to wastes without ponding | Prior to commencing | Visual | S | W | As per drawings and as per approved sample | Approved Sample and Technical Data Submission and Approval Form | 6.10 Ponding Testing-Floor tiles laid to correct RL’s with correct ramps and fall to wastes without ponding | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - As per drawings and as per approved sample | Record Type - Approved Sample and Technical Data Submission and Approval Form |  |  |  | Acceptance Criteria - Safe Work Method Statement (SWMS) to be approved prior to commencement
6.11 Ensure that excessive water is not added to the mix | Prior to commencing | Visual | S | W | As per drawings and as per approved sample | Approved Sample and Technical Data Submission and Approval Form | 6.11 Ensure that excessive water is not added to the mix | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - As per drawings and as per approved sample | Record Type - Approved Sample and Technical Data Submission and Approval Form |  |  |  | Record Type - Approved Safe Work Method Statement (SWMS)
6.12 Ensure proper curing of concrete | Prior to commencing | Visual | S | W | As per drawings and as per approved sample | Approved Sample and Technical Data Submission and Approval Form | 6.12 Ensure proper curing of concrete | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - As per drawings and as per approved sample | Record Type - Approved Sample and Technical Data Submission and Approval Form |  |  |  | 3.1 Check and confirm waterproofing has been completed before commencing work in wet areas.
6.13 Verify that there is adhesion over the whole tile area | Prior to commencing | Visual | S | W | As per drawings and as per approved sample | Approved Sample and Technical Data Submission and Approval Form | 6.13 Verify that there is adhesion over the whole tile area | Timing / Frequency - Prior to commencing | Method - Visual | Verification Type: SC - S | Verification Type: RCC - W | Acceptance Criteria - As per drawings and as per approved sample | Record Type - Approved Sample and Technical Data Submission and Approval Form |  |  |  | Timing / Frequency - Prior to Commencing tiling areas
7.1 Check and ensure correct grout is used including colour and type of grout and thickness | Before commencing grouting works | Visual/Photos | V | H | As per specification grouting sample to be approved prior to grout commencement | Approved Sample and Technical Data Submission and Approval Form | 7.1 Check and ensure correct grout is used including colour and type of grout and thickness | Timing / Frequency - Before commencing grouting works | Method - Visual/Photos | Verification Type: SC - V | Verification Type: RCC - H | Acceptance Criteria - As per specification grouting sample to be approved prior to grout commencement | Record Type - Approved Sample and Technical Data Submission and Approval Form |  |  |  | Method - Visual
7.2 Check and confirm caulking | Before commencing grouting works | Visual/Photos | V | H | As per specification grouting sample to be approved prior to grout commencement | Approved Sample and Technical Data Submission and Approval Form | 7.2 Check and confirm caulking | Timing / Frequency - Before commencing grouting works | Method - Visual/Photos | Verification Type: SC - V | Verification Type: RCC - H | Acceptance Criteria - As per specification grouting sample to be approved prior to grout commencement | Record Type - Approved Sample and Technical Data Submission and Approval Form |  |  |  | Verification Type: SC - S
8.1 Checks falls using digital laser pre and post tiling | All areas | Visual | S | H | In accordance with Design |  | 8.1 Checks falls using digital laser pre and post tiling | Timing / Frequency - All areas | Method - Visual | Verification Type: SC - S | Verification Type: RCC - H | Acceptance Criteria - In accordance with Design | Record Type - |  |  |  | Verification Type: RCC - W
8.2 Ensure workplace is left clean CHAR(AMP) free of defects. | All areas | Visual | S | H | In accordance with Design |  | 8.2 Ensure workplace is left clean CHAR(AMP) free of defects. | Timing / Frequency - All areas | Method - Visual | Verification Type: SC - S | Verification Type: RCC - H | Acceptance Criteria - In accordance with Design | Record Type - |  |  |  | Acceptance Criteria - As per spec, Manufacturer recommendations CHAR(AMP) 3rd Party Consultant Confirmation
8.3 Ensure floor wastes are protected from any materials and debris deposited | All areas | Visual | S | H | In accordance with Design |  | 8.3 Ensure floor wastes are protected from any materials and debris deposited | Timing / Frequency - All areas | Method - Visual | Verification Type: SC - S | Verification Type: RCC - H | Acceptance Criteria - In accordance with Design | Record Type - |  |  |  | Record Type - ITP
8.4 Floor wastes are protected (tapes or other means of protection) | All areas | Visual | S | H | In accordance with Design |  | 8.4 Floor wastes are protected (tapes or other means of protection) | Timing / Frequency - All areas | Method - Visual | Verification Type: SC - S | Verification Type: RCC - H | Acceptance Criteria - In accordance with Design | Record Type - |  |  |  | 3.2 Check angles and levels are correct using a digital level.
8.5 Protection of floor and wall tiles at wet areas. | All areas | Visual | S | H | In accordance with Design |  | 8.5 Protection of floor and wall tiles at wet areas. | Timing / Frequency - All areas | Method - Visual | Verification Type: SC - S | Verification Type: RCC - H | Acceptance Criteria - In accordance with Design | Record Type - |  |  |  | Timing / Frequency - Prior to Commencing tiling areas
8.6 Clean tiles CHAR(AMP) remove all boxes CHAR(AMP) leftover tiles | All areas | Visual | S | H | In accordance with Design |  | 8.6 Clean tiles CHAR(AMP) remove all boxes CHAR(AMP) leftover tiles | Timing / Frequency - All areas | Method - Visual | Verification Type: SC - S | Verification Type: RCC - H | Acceptance Criteria - In accordance with Design | Record Type - |  |  |  | Method - Visual and testing
Verification Type: SC -
Verification Type: RCC -
Acceptance Criteria -
Record Type -
3.3 Check and measure correct falls in wet areas.
Timing / Frequency - Prior to Commencing tiling areas
Method - Visual
Verification Type: SC - S
Verification Type: RCC - W
Acceptance Criteria -
Record Type -
3.4 Inspect work area
Timing / Frequency - Prior to Commencing tiling areas
Method - Visual
Verification Type: SC - S
Verification Type: RCC - W
Acceptance Criteria -
Record Type -
3.5 Check set-out points
Timing / Frequency - Prior to Commencing tiling areas
Method - Visual
Verification Type: SC - S
Verification Type: RCC - H
Acceptance Criteria -
Record Type -
3.6 Set out of angles above wall/skirting tiles
Timing / Frequency - Prior to Commencing tiling areas
Method - Visual
Verification Type: SC - S
Verification Type: RCC - H
Acceptance Criteria -
Record Type -
Check and ensure all materials delivered to site as per approved submitted samples
Timing / Frequency - Prior to commencing
Method - Visual
Verification Type: SC - S
Verification Type: RCC - S
Acceptance Criteria -
Record Type - Delivery Dockets
5.1 Check and ensure sand clean and without any sharps
Timing / Frequency - Prior to commencing
Method - Visual
Verification Type: SC - S
Verification Type: RCC - W
Acceptance Criteria - As per drawings and spec
Record Type -
5.2 Check and ensure FFL before installation of bedding
Timing / Frequency - Prior to commencing
Method - Visual
Verification Type: SC - S
Verification Type: RCC - W
Acceptance Criteria - As per drawings and spec
Record Type -
5.3 Ensure sand CHAR(AMP) cement ratio is correct which is 4:1
Timing / Frequency - Prior to commencing
Method - Visual
Verification Type: SC - S
Verification Type: RCC - W
Acceptance Criteria - As per drawings and spec
Record Type -
5.4 Screed curing time is 3-4 days before glue is applied
Timing / Frequency - Prior to commencing
Method - Visual
Verification Type: SC - S
Verification Type: RCC - W
Acceptance Criteria - As per drawings and spec
Record Type -
5.5 Check that an admixture is being used in the bedding mix in accordance with the manufacturer’s specification and method statement
Timing / Frequency - Prior to commencing
Method - Visual
Verification Type: SC - S
Verification Type: RCC - W
Acceptance Criteria - As per drawings and spec
Record Type -
5.6 Carry out impact tests to establish the soundness of all screeded substrates. Testing shall include both light tap and heavy weight impact using 4kg, in compliance with a screed tester. Alternative substrate testing methods may be put forward for consideration and acceptance by the Superintendent.
Timing / Frequency - Prior to commencing
Method - Visual
Verification Type: SC - S
Verification Type: RCC - W
Acceptance Criteria - As per drawings and spec
Record Type -
6.1 Check and ensure specification that correct tile/paver has been supplied.
Timing / Frequency - Prior to commencing
Method - Visual
Verification Type: SC - S
Verification Type: RCC - W
Acceptance Criteria - As per drawings and as per approved sample
Record Type - Approved Sample and Technical Data Submission and Approval Form
6.2 Check and ensure walls CHAR(AMP) floors for square CHAR(AMP) straightness
Timing / Frequency - Prior to commencing
Method - Visual
Verification Type: SC - S
Verification Type: RCC - W
Acceptance Criteria - As per drawings and as per approved sample
Record Type - Approved Sample and Technical Data Submission and Approval Form
6.3 Check and ensure grout joint widths
Timing / Frequency - Prior to commencing
Method - Visual
Verification Type: SC - S
Verification Type: RCC - W
Acceptance Criteria - As per drawings and as per approved sample
Record Type - Approved Sample and Technical Data Submission and Approval Form
6.4 Check layout of expansion joints and sizes
Timing / Frequency - Prior to commencing
Method - Visual
Verification Type: SC - S
Verification Type: RCC - W
Acceptance Criteria - As per drawings and as per approved sample
Record Type - Approved Sample and Technical Data Submission and Approval Form
6.5 Install vertical and horizontal trims, half moons
Timing / Frequency - Prior to commencing
Method - Visual
Verification Type: SC - S
Verification Type: RCC - W
Acceptance Criteria - As per drawings and as per approved sample
Record Type - Approved Sample and Technical Data Submission and Approval Form
6.6 Installation of floor waste in wet areas
Timing / Frequency - Prior to commencing
Method - Visual
Verification Type: SC - S
Verification Type: RCC - W
Acceptance Criteria - As per drawings and as per approved sample
Record Type - Approved Sample and Technical Data Submission and Approval Form
6.7 Protection to floor waste during screeding
Timing / Frequency - Prior to commencing
Method - Visual
Verification Type: SC - S
Verification Type: RCC - W
Acceptance Criteria - As per drawings and as per approved sample
Record Type - Approved Sample and Technical Data Submission and Approval Form
6.8 Wall tiles to be fixed before floor tiles.
Timing / Frequency - Prior to commencing
Method - Visual
Verification Type: SC - S
Verification Type: RCC - W
Acceptance Criteria - As per drawings and as per approved sample
Record Type - Approved Sample and Technical Data Submission and Approval Form
6.9 Mortar bed complete with correct ramps / fall to wastes – 1:60 minimum to shower areas and 1:100 outside the showers
Timing / Frequency - Prior to commencing
Method - Visual
Verification Type: SC - S
Verification Type: RCC - W
Acceptance Criteria - As per drawings and as per approved sample
Record Type - Approved Sample and Technical Data Submission and Approval Form
6.10 Ponding Testing-Floor tiles laid to correct RL’s with correct ramps and fall to wastes without ponding
Timing / Frequency - Prior to commencing
Method - Visual
Verification Type: SC - S
Verification Type: RCC - W
Acceptance Criteria - As per drawings and as per approved sample
Record Type - Approved Sample and Technical Data Submission and Approval Form
6.11 Ensure that excessive water is not added to the mix
Timing / Frequency - Prior to commencing
Method - Visual
Verification Type: SC - S
Verification Type: RCC - W
Acceptance Criteria - As per drawings and as per approved sample
Record Type - Approved Sample and Technical Data Submission and Approval Form
6.12 Ensure proper curing of concrete
Timing / Frequency - Prior to commencing
Method - Visual
Verification Type: SC - S
Verification Type: RCC - W
Acceptance Criteria - As per drawings and as per approved sample
Record Type - Approved Sample and Technical Data Submission and Approval Form
6.13 Verify that there is adhesion over the whole tile area
Timing / Frequency - Prior to commencing
Method - Visual
Verification Type: SC - S
Verification Type: RCC - W
Acceptance Criteria - As per drawings and as per approved sample
Record Type - Approved Sample and Technical Data Submission and Approval Form
7.1 Check and ensure correct grout is used including colour and type of grout and thickness
Timing / Frequency - Before commencing grouting works
Method - Visual/Photos
Verification Type: SC - V
Verification Type: RCC - H
Acceptance Criteria - As per specification grouting sample to be approved prior to grout commencement
Record Type - Approved Sample and Technical Data Submission and Approval Form
7.2 Check and confirm caulking
Timing / Frequency - Before commencing grouting works
Method - Visual/Photos
Verification Type: SC - V
Verification Type: RCC - H
Acceptance Criteria - As per specification grouting sample to be approved prior to grout commencement
Record Type - Approved Sample and Technical Data Submission and Approval Form
8.1 Checks falls using digital laser pre and post tiling
Timing / Frequency - All areas
Method - Visual
Verification Type: SC - S
Verification Type: RCC - H
Acceptance Criteria - In accordance with Design
Record Type -
8.2 Ensure workplace is left clean CHAR(AMP) free of defects.
Timing / Frequency - All areas
Method - Visual
Verification Type: SC - S
Verification Type: RCC - H
Acceptance Criteria - In accordance with Design
Record Type -
8.3 Ensure floor wastes are protected from any materials and debris deposited
Timing / Frequency - All areas
Method - Visual
Verification Type: SC - S
Verification Type: RCC - H
Acceptance Criteria - In accordance with Design
Record Type -
8.4 Floor wastes are protected (tapes or other means of protection)
Timing / Frequency - All areas
Method - Visual
Verification Type: SC - S
Verification Type: RCC - H
Acceptance Criteria - In accordance with Design
Record Type -
8.5 Protection of floor and wall tiles at wet areas.
Timing / Frequency - All areas
Method - Visual
Verification Type: SC - S
Verification Type: RCC - H
Acceptance Criteria - In accordance with Design
Record Type -
8.6 Clean tiles CHAR(AMP) remove all boxes CHAR(AMP) leftover tiles
Timing / Frequency - All areas
Method - Visual
Verification Type: SC - S
Verification Type: RCC - H
Acceptance Criteria - In accordance with Design
Record Type -