## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Internal Waterproofing | itp |  |  |  |  | ITP - Internal Waterproofing
section | Work items and/or activities to be verified
checkpoint | 1 - Acceptance of substrate by Waterproofing Subcontractor & 3rd Party WC. Smooth flat finish to falls (no negative falls). Free of deep depressions and/or protrusions. Sheeting finished 2-5mm from concrete substrate. Check wall finishes are flush Door frames 5mm above threshold.
label | Timing / Frequency - All items to be checked for each area before any works commence
label | Method - Visual
label | Inspection / Test Done By: Position - SC /WC/E
label | Inspection / Test Done By: Company - 3rd Party WC
label | Verification Type: S/C - H
label | Verification Type: RCC - H
label | Acceptance Criteria - As per manufacturer’s recommendations & 3rd Party Consultant
label | References (Dwg No, Spec, Aust. Standard) - Manufacturer Tech data sheets
label | Record Type - 3rd Party WC Report
holdpoint | HOLD POINT
checkpoint | 2 - Mechanically fix angles/waterstops in accordance with documentation
label | Timing / Frequency - Before works commence
label | Method - Visual
label | Inspection / Test Done By: Position - SC
label | Inspection / Test Done By: Company - MDS Stone
label | Verification Type: S/C - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings, specification, 3rd Party Consultant recommendations
checkpoint | 3 - Prime Area using approved non-porous primer and allow to cure
label | Timing / Frequency - Each area
label | Method - Review Docs
label | Inspection / Test Done By: Position - SC
label | Inspection / Test Done By: Company - MDS Stone
label | Verification Type: S/C - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per manufacturer recommendations and spec
label | References (Dwg No, Spec, Aust. Standard) - AS-3740
textbox | Record Type - Photo Records Curing Time
checkpoint | 4 - Caulking of all joints, penetrations and changes of direction with approved polyurethane joint sealant.
label | Timing / Frequency - Each area
label | Method - Visual
label | Inspection / Test Done By: Position - SC/WC
label | Inspection / Test Done By: Company - MDS Stone
label | Verification Type: S/C - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per manufacturer recommendations and standard
label | References (Dwg No, Spec, Aust. Standard) - AS-3740
label | Record Type - Photo records
checkpoint | 5 - Apply first coat of liquid applied waterproof membrane and measure wet film thickness
label | Timing / Frequency - Each area
label | Method - Physical measure with comb gauge
label | Inspection / Test Done By: Position - SC/E
label | Inspection / Test Done By: Company - MDS Stone
label | Verification Type: S/C - V
label | Verification Type: RCC - W
label | Acceptance Criteria - As per manufacturer recommendations and spec
label | Record Type - Minimum 3 test / area / coat. logged in register
checkpoint | 6 - Apply second coat of liquid applied waterproof membrane and measure wet film thickness
label | Timing / Frequency - Each area
label | Method - Physical measure with comb gauge
label | Inspection / Test Done By: Position - SC/E
label | Inspection / Test Done By: Company - MDS Stone
label | Verification Type: S/C - V
label | Verification Type: RCC - W
label | Acceptance Criteria - As per manufacturer recommendations and spec
label | Record Type - Minimum 3 test / area / coat. Logged in register
checkpoint | 7 - Allow Curing Times (Liquid Membranes) in accordance with manufacturers spec
label | Timing / Frequency - Each area
label | Method - Inspection
label | Inspection / Test Done By: Position - SC/E
label | Inspection / Test Done By: Company - MDS Stone
label | Verification Type: S/C - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per manufacturer recommendations and spec
textbox | Record Type - Curing Time
checkpoint | 8 - Water flood testing to be carried out to ALL WET AREAS. Flood test to a depth of 5mm below highest waterstop. Flood test duration 2 days.
label | Timing / Frequency - All wet areas
label | Method - Visual Include photos
label | Inspection / Test Done By: Position - SC/E
label | Inspection / Test Done By: Company - MDS Stone
label | Verification Type: S/C - H
label | Verification Type: RCC - H
label | Acceptance Criteria - Verification photos to ALL WET AREAS
label | References (Dwg No, Spec, Aust. Standard) - AS-3740
label | Record Type - Photos of ALL flood testing
holdpoint | HOLD POINT
checkpoint | 9 - Acceptance of waterproof membrane areas by a tiler
label | Timing / Frequency - Each area
label | Method - Visual
label | Inspection / Test Done By: Position - SC (Tiler)
label | Inspection / Test Done By: Company - MDS Stone
label | Verification Type: S/C - H
label | Verification Type: RCC - H
label | Acceptance Criteria - As per manufacturer & 3rd Party Consultant recommendations
holdpoint | HOLD POINT
checkpoint | 10 - Tilers install screed. Confirm the specified fall on screed has been achieved Showers (1:80mm min.) Bathrooms (1:100mm min.)
label | Timing / Frequency - Each Area
label | Method - Visual (Level Check)
label | Inspection / Test Done By: Position - SC/F
label | Inspection / Test Done By: Company - MDS Stone
label | Verification Type: S/C - H
label | Verification Type: RCC - H
label | Acceptance Criteria - Acceptance of screed by waterproofing subcontractor
holdpoint | HOLD POINT
checkpoint | 11 - Prime screed & upturns & allow to cure as per manufacturers recommendation
label | Timing / Frequency - Before tiling works commence
label | Method - Visual
label | Inspection / Test Done By: Position - SC
label | Inspection / Test Done By: Company - MDS Stone
label | Verification Type: S/C - S
label | Verification Type: RCC - W
textbox | Acceptance Criteria - Manufacturers Curing time
checkpoint | 12 - Joint seal perimeter
label | Timing / Frequency - Before tiling works commence
label | Method - Visual
label | Inspection / Test Done By: Position - SC
label | Inspection / Test Done By: Company - MDS Stone
label | Verification Type: S/C - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings, specification & manufacturers recommendations
label | References (Dwg No, Spec, Aust. Standard) - AS-3740
checkpoint | 13 - Apply approved wet film screed to shower walls & splashbacks to manufacturers approved thickness and allow to cure
label | Timing / Frequency - Before tiling works commence
label | Method - Visual
label | Inspection / Test Done By: Position - SC
label | Inspection / Test Done By: Company - MDS Stone
label | Verification Type: S/C - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings, specification& manufacturers recommendations
label | References (Dwg No, Spec, Aust. Standard) - AS-3740
checklist | ITP - Tiling | itp |  |  |  |  | ITP - Tiling
section | 1 - Submit samples and material data sheets for approval by Architect/Client
checkpoint | Submit samples and material data sheets for approval by Architect/Client
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - V
label | Verification Type: RCC - H
label | Acceptance Criteria - Submit Sample and Technical Data Submission and Approval Form in accordance with specification or its equivalent with Technical Data Sheet and Slip Test Report.
label | Record Type - Approved Sample and Technical Data Submission and Approval Form
holdpoint | HOLD POINT
section | 2 - Safety
checkpoint | 2.1 - Mandatory WHS certificates are sighted & copied.
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - Safe Work Method Statement (SWMS) to be approved prior to commencement
label | Record Type - Approved Safe Work Method Statement (SWMS)
checkpoint | 2.2 - SWMS complete & all workers have been inducted into the SWMS
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - V
label | Verification Type: RCC - W
label | Acceptance Criteria - Safe Work Method Statement (SWMS) to be approved prior to commencement
label | Record Type - Approved Safe Work Method Statement (SWMS)
checkpoint | 2.3 - Check and ensure access to work area.
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - Safe Work Method Statement (SWMS) to be approved prior to commencement
label | Record Type - Approved Safe Work Method Statement (SWMS)
checkpoint | 2.4 - Additional safety risks
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - Safe Work Method Statement (SWMS) to be approved prior to commencement
label | Record Type - Approved Safe Work Method Statement (SWMS)
section | 3 - Setout
checkpoint | 3.1 - Check and confirm waterproofing has been completed before commencing work in wet areas.
label | Timing / Frequency - Prior to Commencing tiling areas
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per spec, Manufacturer recommendations & 3rd Party Consultant Confirmation
label | Record Type - ITP
checkpoint | 3.2 - Check angles and levels are correct using a digital level.
label | Timing / Frequency - Prior to Commencing tiling areas
label | Method - Visual and testing
checkpoint | 3.3 - Check and measure correct falls in wet areas.
label | Timing / Frequency - Prior to Commencing tiling areas
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
checkpoint | 3.4 - Inspect work area
label | Timing / Frequency - Prior to Commencing tiling areas
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
checkpoint | 3.5 - Check set-out points
label | Timing / Frequency - Prior to Commencing tiling areas
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - H
holdpoint | HOLD POINT
checkpoint | 3.6 - Set out of angles above wall/skirting tiles
label | Timing / Frequency - Prior to Commencing tiling areas
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - H
holdpoint | HOLD POINT
section | 4 - Check and ensure all materials delivered to site as per approved submitted samples
checkpoint | Check and ensure all materials delivered to site as per approved submitted samples
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - S
label | Record Type - Delivery Dockets
section | 5 - Installation of Sand & Cement screed
checkpoint | 5.1 - Check and ensure sand clean and without any sharps
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings and spec
checkpoint | 5.2 - Check and ensure FFL before installation of bedding
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings and spec
checkpoint | 5.3 - Ensure sand & cement ratio is correct which is 4:1
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings and spec
checkpoint | 5.4 - Screed curing time is 3-4 days before glue is applied
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings and spec
checkpoint | 5.5 - Check that an admixture is being used in the bedding mix in accordance with the manufacturer’s specification and method statement
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings and spec
checkpoint | 5.6 - Carry out impact tests to establish the soundness of all screeded substrates. Testing shall include both light tap and heavy weight impact using 4kg, in compliance with a screed tester. Alternative substrate testing methods may be put forward for consideration and acceptance by the Superintendent.
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings and spec
section | 6 - Installation of Tiles/Pavers
checkpoint | 6.1 - Check and ensure specification that correct tile/paver has been supplied.
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings and as per approved sample
label | Record Type - Approved Sample and Technical Data Submission and Approval Form
checkpoint | 6.2 - Check and ensure walls & floors for square & straightness
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings and as per approved sample
label | Record Type - Approved Sample and Technical Data Submission and Approval Form
checkpoint | 6.3 - Check and ensure grout joint widths
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings and as per approved sample
label | Record Type - Approved Sample and Technical Data Submission and Approval Form
checkpoint | 6.4 - Check layout of expansion joints and sizes
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings and as per approved sample
label | Record Type - Approved Sample and Technical Data Submission and Approval Form
checkpoint | 6.5 - Install vertical and horizontal trims, half moons
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings and as per approved sample
label | Record Type - Approved Sample and Technical Data Submission and Approval Form
checkpoint | 6.6 - Installation of floor waste in wet areas
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings and as per approved sample
label | Record Type - Approved Sample and Technical Data Submission and Approval Form
checkpoint | 6.7 - Protection to floor waste during screeding
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings and as per approved sample
label | Record Type - Approved Sample and Technical Data Submission and Approval Form
checkpoint | 6.8 - Wall tiles to be fixed before floor tiles.
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings and as per approved sample
label | Record Type - Approved Sample and Technical Data Submission and Approval Form
checkpoint | 6.9 - Mortar bed complete with correct ramps / fall to wastes – 1:60 minimum to shower areas and 1:100 outside the showers
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings and as per approved sample
label | Record Type - Approved Sample and Technical Data Submission and Approval Form
checkpoint | 6.10 Ponding Testing-Floor tiles laid to correct RL’s with correct ramps and fall to wastes without ponding
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings and as per approved sample
label | Record Type - Approved Sample and Technical Data Submission and Approval Form
checkpoint | 6.11 Ensure that excessive water is not added to the mix
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings and as per approved sample
label | Record Type - Approved Sample and Technical Data Submission and Approval Form
checkpoint | 6.12 Ensure proper curing of concrete
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings and as per approved sample
label | Record Type - Approved Sample and Technical Data Submission and Approval Form
checkpoint | 6.13 Verify that there is adhesion over the whole tile area
label | Timing / Frequency - Prior to commencing
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - W
label | Acceptance Criteria - As per drawings and as per approved sample
label | Record Type - Approved Sample and Technical Data Submission and Approval Form
section | 7 - Grouting
checkpoint | 7.1 - Check and ensure correct grout is used including colour and type of grout and thickness
label | Timing / Frequency - Before commencing grouting works
label | Method - Visual/Photos
label | Verification Type: SC - V
label | Verification Type: RCC - H
label | Acceptance Criteria - As per specification grouting sample to be approved prior to grout commencement
label | Record Type - Approved Sample and Technical Data Submission and Approval Form
holdpoint | HOLD POINT
checkpoint | 7.2 - Check and confirm caulking
label | Timing / Frequency - Before commencing grouting works
label | Method - Visual/Photos
label | Verification Type: SC - V
label | Verification Type: RCC - H
label | Acceptance Criteria - As per specification grouting sample to be approved prior to grout commencement
label | Record Type - Approved Sample and Technical Data Submission and Approval Form
holdpoint | HOLD POINT
section | 8 - Cleaning
checkpoint | 8.1 - Checks falls using digital laser pre and post tiling
label | Timing / Frequency - All areas
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - H
label | Acceptance Criteria - In accordance with Design
holdpoint | HOLD POINT
checkpoint | 8.2 - Ensure workplace is left clean & free of defects.
label | Timing / Frequency - All areas
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - H
label | Acceptance Criteria - In accordance with Design
holdpoint | HOLD POINT
checkpoint | 8.3 - Ensure floor wastes are protected from any materials and debris deposited
label | Timing / Frequency - All areas
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - H
label | Acceptance Criteria - In accordance with Design
holdpoint | HOLD POINT
checkpoint | 8.4 - Floor wastes are protected (tapes or other means of protection)
label | Timing / Frequency - All areas
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - H
label | Acceptance Criteria - In accordance with Design
holdpoint | HOLD POINT
checkpoint | 8.5 - Protection of floor and wall tiles at wet areas.
label | Timing / Frequency - All areas
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - H
label | Acceptance Criteria - In accordance with Design
holdpoint | HOLD POINT
checkpoint | 8.6 - Clean tiles & remove all boxes & leftover tiles
label | Timing / Frequency - All areas
label | Method - Visual
label | Verification Type: SC - S
label | Verification Type: RCC - H
label | Acceptance Criteria - In accordance with Design
holdpoint | HOLD POINT