## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP-204-CIV-CPD-Landscaping-Planting Rev 1 | itp | ITP-204-CIV-CPD-Landscaping-Planting |  | 9e4d7a18-6467-48a7-83ab-f99726ac1a93
| section | 1. Referenced Documentation
| checkpoint-no-value | Referenced Documentation
dbddaa85-d2e8-5ae5-8fe0-240b20aff472 | note | Document Title: ITP-204-CIV-CPD-Landscaping-Planting
c11f4e7e-1110-59aa-bf7f-9ecc04bb9b44 | note | ITP Description: Landscaping - Planting
4c73aae3-955b-578a-a309-79ca03c3822a | note | Discipline (e.g. CIV/STR/RAIL): CIV
91f18bf7-f8ef-51d2-b6b9-7a95f41a30af | note | Revision Number: 0
be17aae1-07a1-5520-8573-1699cb7042ee | note | Revision Date: 2/10/2024
bcda5be2-1fde-5df9-bad0-eae5060329c8 | note | ITP created by: Jason Quan/Derek Collins
3abf5e76-5ad2-50e2-97d1-e7527a07dd99 | note | ITP approved for use by: Pradeep Talasila
ac61ed49-5671-51c5-aad3-98b78c5b8676 | note | References: IFC Drawings
bf92d7c0-9e1f-505a-b91c-b9f4665c0caf | note | ○ AS 4454
ee7c3100-2b0e-5e63-ac39-110b3e0193af | note | ○ AS 4419
ca72b278-4587-57e6-aed7-d97692aacba9 | note | ○ IFC Drawings
3c23d8e2-7941-5c60-b6ac-4934d67ad4bb | note | ○ Sub Contractor ITP
| section | 2. Preliminaries
| checkpoint | 2.1 - Check for correct documentation
b74794ec-6b23-522c-ba25-0a2606e16928 | note | Reference - Drawings and Drawing Register
acdc21d9-8f90-5cc8-bcb7-6d347c2a62eb | note | Acceptance Criteria - Ensure that all employees and subcontractors are using:
cee55482-bd22-5ef9-bbcd-abbbf10096cb | note | – The correct and complete set of drawings
b57ffa16-069a-51d5-95ff-4cdfc074198e | note | – All drawings are the latest revision
b743700a-0f19-5e46-9918-09d3eb0302e0 | note | Method - Document Review
b44efda6-c282-5d6d-910a-1b9d8adfbbf4 | note | Frequency - Prior to Commencing works
297acf46-6fb0-57bd-afcd-83b04f75d50c | note | Category - N/A
21ee88ef-5dbe-5b67-8d1a-b66792c46da4 | note | Responsibility - SE
2e7963dc-1956-542b-a7d2-d13eabe2414c | note | Verifying Documents - This ITP
b43beb51-b89b-5952-ab48-240deca70dcf | date | Date Completed:
| checkpoint | 2.2 - Submission and records
9896fe70-cc3b-5a76-899a-247caf295d5b | note | Reference - VicRoads Spec.
01c6fa2b-b17e-5742-be88-b6c8fac5a0fd | note | – Cl.720.03
89ed34e6-0cf9-56c5-b077-716634a707a9 | note | Acceptance Criteria - Inspections, Samples, records and certificates shall be provided to the Superintendent at least 10 working days prior to bulk delivery.
837decae-c640-5177-902c-1d84b40b0a6d | note | ○ Following information shall be provided to the superintendent:
f67701eb-0808-53d4-a869-c44485c2850e | note | – Inspections of plant stock for all plant species
5a6026be-3604-5c18-9965-8ae57297ba20 | note | ○ Records:
d2964491-8841-5156-b2ab-133297fa43d1 | note | – Evidence of origin of indigenous provenance plant material
52cea890-865d-56c9-bb18-9c52e05d5acc | note | – Analysis certificates for grass seed
003722ef-5915-530c-8d3a-f6f89c61419e | note | – Details of suppliers
eec71052-26ca-5060-917b-615ee1478c25 | note | – Copies/Photos of fertiliser labels
f05f769c-ed01-5f2c-9665-50981ce55f04 | note | Method - Document Review
96c17454-8e86-5cdf-a36b-f6aa92b96212 | note | Frequency - Prior to Commencing works
a49f7df9-7483-55f5-8f85-e0e38a5ca441 | note | Category - HP
4abe28fa-5d89-56ce-b88c-cf7ab24894e8 | note | Responsibility - SE,Superintendent
dae396c5-2c2a-58fd-8a1c-105126c2c0d4 | note | Verifying Documents - This ITP, Attach Records to TeamBinder Approval Form
d69363f2-b4c2-5a48-8e8f-63d13cdf3f93 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Supply of Plant Stock
f5c087ae-c1c9-5370-a986-ed6a72ce5110 | note | Reference - VicRoads Spec.
adf541b8-e902-5a22-83e5-503071de63a6 | note | – Cl.720.04
9dd1fe1c-06d3-597a-ac9a-68e429f56b28 | note | – Table 720.041
190d6a03-5b91-5228-80ea-a668b9f74a5c | note | Acceptance Criteria - All plants shall be of the type, height, container size and trunk caliper specified in the Plant Schedules, Specification and Planting Plans.
c578b0e6-b554-54ad-ab01-42c4235f5d79 | note | ○ Plants are to conform to the supply properties specified in Table 720.041
0c381aa4-cd37-51bc-82ad-c3afa2f2bd70 | note | Method - Verify
e1be89ff-6df9-5558-bd5a-2807d4d51352 | note | Frequency - Prior to Commencing works
2bd927ef-9de6-5677-983b-280efdfd7918 | note | Category - N/A
ce2569d9-a5b3-5f0d-9c2f-bf128222c876 | note | Responsibility - SE
33360eb4-376d-5ed8-8aa5-7b96205e4cee | note | Verifying Documents - This ITP
3bea56f9-a520-53c7-914e-834b64b48c54 | date | Date Completed:
| checkpoint | 2.4 - Supply of indigenous plant stock
c04a7ae6-7534-5e78-ad16-c0ba329b425d | note | Reference - VicRoads Spec.
c7e5804c-ca76-5ad9-b96a-e2c050823a57 | note | – Cl.720.04
2316064c-27f5-506e-9622-03adb956b2ec | note | Acceptance Criteria - A species listed on the planting schedule shall be classed as an indigenous plant if the plant is likely to have occurred within 10 km of the project site (pre 1750).
93277025-c75f-5418-ad36-63eef20cd3e3 | note | ○ The Contractor shall submit documentation of origin of indigenous provenance plant material which shall include the following details for each seed lot:
03306561-68c1-5bab-8d24-6cc688975971 | note | ○ species name
02bcb2f7-72d9-55a5-8abd-a218912ab2e1 | note | ○ storage code
787afc63-fdbb-5e38-85c4-e994b36e9ec8 | note | ○ collection locality - Latitude/longitude or AMG
5e5c0ff6-1405-5a2c-a34a-c2fe5d27252b | note | ○ approximate number of parent plants sampled
3cf841dc-1b19-5ed2-a032-0b552854a744 | note | ○ approximate number of plants in that local population
bd3fa373-64c4-5dcc-82d6-42d038b06ce6 | note | Method - Verify
5107092c-66d1-5312-8422-7b2fbdb18e6e | note | Frequency - Prior to Commencing works
0b97176e-85bb-5c3e-9c7f-eff597cc3f80 | note | Category - N/A
12d328f2-f92d-5c42-ac5f-6a0394b6230f | note | Responsibility - SE
b4808f9b-f434-50b0-8cbd-96306b351d59 | note | Verifying Documents - This ITP
293feb1e-0e12-5028-bedc-dbead08283ba | date | Date Completed:
| checkpoint | 2.5 - Supply of grass seed
108209bc-d432-5e42-9a8d-dabcc38eb107 | note | Reference - VicRoads Spec.
ddbf3995-8b72-5055-9a25-758783128bd7 | note | – Cl.720.04
794a1872-3e03-577d-aef7-57dd801d1eee | note | – Table 720.045
9af68b66-c383-56ad-b886-4b16f5b82405 | note | Acceptance Criteria - Grass seed shall comply with Table 720.045
8f7785bb-f97d-5e05-816d-18e99db65735 | note | Method - Verify
322d93d5-3c09-54aa-ba56-41520e61fe65 | note | Frequency - Prior to Commencing works
ab5cabf5-3f39-5b84-9f34-5ba6fcaf95a8 | note | Category - N/A
ce7e80c1-4d2c-5a22-9200-624c67c8b150 | note | Responsibility - SE
fe7e6ef8-e66b-55e9-a90a-542eec7d0d22 | note | Verifying Documents - This ITP
f7e70521-2730-51e8-985e-445afdf54b43 | date | Date Completed:
| checkpoint | 2.6 - Check with Landscape Architect
| note | Reference - Recommended Verification Activities LXRP
| note | Acceptance Criteria - All Plants to be inspected and approved by the Project Landscape Achitect/Arborist/Certified Horticulturalist prior to planting to ensure the stock quality
| note | Method - Verify
| note | Frequency - Prior to Commencing works
| note | Category - WP
| note | Responsibility - SE
| note | Verifying Documents - This ITP
| date | Date Completed:
| section | 3. Subcontractor ITP
| checkpoint | 3.1 - Subcontractor ITP
5bb6dfac-062d-5806-86bb-b0921b212704 | note | Reference - Subcontractor ITP
4fde9257-df82-5a49-8206-c737c1641d7c | note | Acceptance Criteria - Subcontractor ITP to be reviewed and approved by MRPA.
57aaa5ef-fbed-53f9-81d6-5943043bfd3b | note | Method - Document Review
651f6d98-4956-5ec8-bf23-17befb90cb6f | note | Frequency - Each Lot
fdacd02f-801b-590a-ae3a-64274f410df6 | note | Category - WP
126defa7-b89a-5f4d-a882-244a3efa3d23 | note | Responsibility - SE/PE
7e887009-b7c1-5841-bf42-befff91cc2e1 | note | Verifying Documents - Sign ITP
aafb884e-16a8-524a-9e91-63c218102d2e | date | Date Completed:
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Planting Section Approval
823cf8c7-af8e-50ae-ac4d-d824c9911a7c | note | Reference - VicRoads Spec.
8a34518c-f7da-5704-b098-06e1273abb2d | note | – Cl.720.06
2e8e456c-4e1c-58e3-bd39-531110f4939e | note | – Landscape Plus Planting ITP
46ebd1d5-10f0-5446-b6c9-e8c61c84e1d1 | note | Acceptance Criteria - Trial planting sections have been approved by the Superintendent. These approved sections shall be used as a reference for the remaining planting works
9fd00689-6208-5318-a8ad-10594af3dd2f | note | Method - Verify
e15e7a25-df05-5f7a-a839-72688620b5e2 | note | Frequency - Once
be6a0bc4-7d10-5a6a-926e-af4500f112f2 | note | Category - HP
4edcff2e-1bae-599c-b87c-21217912dbb9 | note | Responsibility - SE
0c42aab2-ff84-5359-a86b-2b3003897053 | note | Verifying Documents - This ITP
ebdbd169-9f38-59b7-807a-f5b3f01bfa9e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Pest and Weed Control
95c9b183-98e4-51f9-8fc2-8ccea77ce263 | note | Reference - Cl.720.05
bfa9274e-faa7-5da5-982d-918f94a3a398 | note | Acceptance Criteria - The Contractor shall develop and implement site specific pest and weed management procedures to control pest and weed populations.
c9d8698a-eae3-59a9-93f2-bbb6f06d6a4f | note | ○ Pre-planting weed control shall be undertaken to ensure that planting areas and new grassed areas are free of visible weeds prior to the commencement of planting and grassing.
90375bf2-3dd1-5be2-9411-0cbaa550bfb2 | note | Method - Verify
4252ab9e-d78f-5df1-8e65-e2422119e197 | note | Frequency - Once
2616b15b-c952-57dc-b0fe-a2d6cfdfbd01 | note | Category - HP*
196fe410-1b77-5040-9271-2d3a62d99c1d | note | Responsibility - SE
5aac82d1-4873-5983-86cd-86dac63d846d | note | Verifying Documents - This ITP
1494389c-77d2-50fc-b79d-2b35e736537f | date | Date Completed:
| checkpoint | 4.3 - Setting out planting areas
68390771-a2d8-535f-8ef1-13b701564aac | note | Reference - VicRoads Spec.
57d3a990-ea06-5ac3-8503-4157aa324003 | note | – Cl.720.06
aef95e56-8f0d-5940-b6be-b3728f44f844 | note | Acceptance Criteria - Planting areas are to be set out to the location and shape specified in the landscape drawings.
084935b9-9fdf-5ee6-b582-bace09684124 | note | ○ Plant density requiremens and planting offsets established in the plant schedule are to be adhered to.
af3a2a28-167f-5c45-953e-e24125c196ab | note | ○ Individual plants shall be located in accordance with the drawings such that the mature form of the plant will be in accordance with VicRoads Road Design Guidelines, including clear zone and sight distance requirements.
88837507-024a-5243-9b2d-feaf468ec028 | note | Method - Verify
395d049a-3bf0-50e2-be43-93511909a60e | note | Frequency - Each Applicable Lot
ec9f5358-cea1-5fce-9ace-7f8458461a0e | note | Category - N/A
09fc96df-b232-56af-8c74-f2b7d1a14aaf | note | Responsibility - SE
3bf67216-b824-5f26-a404-80714676cf6f | note | Verifying Documents - This ITP
34fe7f79-010b-5c0a-8876-b1c101c0faa1 | date | Date Completed:
| section | 5. Construction
| checkpoint | 5.1 - Planting
a6a46c9c-30b6-5d48-a89a-b74401e24f1e | note | Reference - VicRoads Spec.
8ead4ab7-2821-5368-b54c-105742ee7099 | note | – Cl.720.09
f571b18d-50d2-5fd5-82be-c2daa19fe9fd | note | – Landscape Plus Planting ITP
12c86a04-0624-5e80-af21-9a4c54d962fa | note | Acceptance Criteria - All planting will be undertaken in accordance to Landscpe Plus Planting ITP
b37cab87-598b-5cfd-8d6c-8a009112de46 | note | Method - Verify
f121a3d6-a136-5a13-aec5-f8a7da5e61b6 | note | Frequency - Each Applicable Lot
fb2662ef-9742-5f40-93d2-604ebfb86941 | note | Category - NA
95200c3d-611b-5ade-aa81-27f9cf52102f | note | Responsibility - SE,Foreman
80656432-740b-5171-81d0-4a6206217218 | note | Verifying Documents - This ITP
97f11251-7b9e-535c-96b0-0ec4c21081ab | date | Date Completed:
| section | 6. Completion
| checkpoint | 6.1 - Site Final Inspection
908b0e21-e415-51fe-9caf-9634e9cb7582 | note | Reference - Landscape Plus Planting ITP
768797f2-435b-5aa2-9a3d-ad99ee20f5ad | note | Acceptance Criteria - Landscape Plus ITP signed and completed
bea0698d-d355-53b4-ab8e-7405ebf72217 | note | Method - Document review & Site Inspection
2396b4e0-5e42-590f-b33e-8cf5af416815 | note | Frequency - Following completion of planting works
b93bfcfb-17c5-5606-9033-13130c3888ef | note | Category - N/A
9526a218-0db5-523a-ba30-faf74331e816 | note | Responsibility - SE
f1402e43-81b8-5d47-8763-218486d1cf06 | note | Verifying Documents - Sub-Contractor ITP completed, signed and to be attached
63d4a55a-0f73-52a8-9a14-5639a1745b51 | date | Date Completed:
| checkpoint | Final Inspection
ac4e86a6-3efe-5b46-ace1-348cae0fc468 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
c6231273-ddc6-51c0-9f24-60a1230598b5 | textbox | Name:
c77bcf46-2a77-5857-bfc9-0dbd72075171 | textbox | Position:
5f192e10-614a-5c56-918e-316b012f8d78 | textbox | Date Completed:
| signoff | Sign ITP