## Master List Templates
Id | Type | Name | Values | Prompting Name | Prefix | Postfix
8c253716-b068-4463-864a-a3ae084d0e6b | checklist | Add Site Visit Checklist |  | Site Visit Date:
4729aca8-cc4e-4c3b-9d0d-a415b9052b42 | checkpoint | Details entered
c3a4ba6a-1e39-5d18-880b-bcdc67943f1e | textbox | Site visit performed by
4c7c7e47-fb8f-57a7-b263-468dc7b66dfc | textbox | Site visit completed with / attendees
ab920d2f-11ad-511e-b608-b814391e07d9 | textbox | Description of area
2ebdfd27-7e28-4565-8eee-4f24e4f57fca | checkpoint | Photos taken
83fe08c2-8d6e-434f-bf70-eb85b3f4bb73 | checkpoint | General observations and comments
4394ccfc-826d-4325-b3ea-75b1f92f751f | checklist | Add Variation |  | Variation Details -
5812f9c1-031f-4ef4-8377-40218f3be5b5 | checkpoint | Variation Details Approved
a1dcf207-c630-5a69-87a0-3ffad882385e | textbox | Reference/Drawing/Instruction Number
e72912a4-382e-5a1d-b596-ca10ca275739 | textbox | Variation Area
b09de357-4c7d-5c81-b481-e02733600b27 | textbox | Materials & labour breakdown
42639ab8-ba44-4321-b193-ffa3b389b783 | signoff | Request Variation Acknowledgement
5720f4c5-8810-49b3-8227-164f7f441f37 | checkpoint | Variation Completed
743190f8-163d-40f9-995b-87adf468e9f5 | signoff | Request Variation Signoff
2aa2a7ed-2364-4deb-ba20-22d94b115844 | checklist | Document Attach |  | Document:
12c8ad85-0133-4af1-948a-ad327307b0f9 | checkpoint | Document Attached
38b67e46-1e69-489a-8d15-9b4d83ec728a | checklist | QA - (10 Madden St) - Waterstop RX Checklist |  | Waterstop RX Checklist -Zone / Grids:
5693b8d0-a03d-406c-abeb-d8ae99a16f14 | section | Surface Preparation
fbf8654e-27b0-40c7-b02c-f086ce2ae379 | checkpoint | Surface clean
5500ce89-6d16-40af-83f1-d5c5c59f7759 | checkpoint | Rust removed
a93b2638-d18f-4dc6-9c1d-e706194558db | checkpoint | Suitable surface profile
cdc38440-f373-4a35-8fc4-0fdfe0f8b5eb | checkpoint | Standing water ice or snow
18836565-1813-4539-a041-f41d3970a512 | checkpoint | WB Adhesive turn black
d30c228f-cc52-4f64-bc95-cba53efc0e3c | checkpoint | WB Adhesive 6+ hours old
a3e27a4f-6a7c-417d-acf2-d9805454d8a9 | checkpoint | WB Adhesive wide enough
8a0f64e6-db8f-4268-aade-49e535acbee9 | checkpoint | WB Adhesive continuous
ece9d851-25ff-491d-807b-110e4141da52 | checkpoint | WB Adhesive frozen
58447d74-7b11-5a96-a5b1-17f061214727 | textbox | Other adhesive name
9475d47f-e06c-4fd9-a9fb-493e265e8fb9 | section | Installation
54e1d209-f3a8-422f-be7f-b184d5f3dea2 | checkpoint | Removable forms used
784c002d-cfb2-489c-8e77-f5c86995e689 | checkpoint | Entire length engaged
4943ae9c-423a-412a-9605-5b940249a339 | checkpoint | Mechanical fasteners
91451a5d-350f-45a7-9e47-06c91664296b | checkpoint | Ends tightly butted
4e17add2-fdd3-4d6c-afc9-e9813bd18ca3 | checkpoint | Ends overlapped
1f1f4e34-ff08-4210-9469-1b91ca799e60 | checkpoint | Correct Waterstop being used
0b99fcf0-9824-58c8-aab7-5d088c046902 | dropdown | Waterstop RX being used: | 50m Concrete Cover (Akwaswell 3.8" bead), 75mm Concrete Cover (Akwastop),50mm Concrete Cover (RX 102),75mm Concrete Cover (RX 101)
11a9dbc0-2e69-4e78-9d11-25d215d9a4c9 | checkpoint | Voids between concrete and waterstop
1dc86a91-b42d-4e8c-b681-39fbe9a22b38 | checkpoint | Prematurely hydrated
96ac1b72-77ea-443a-bd8f-46124cfd4c36 | checkpoint | Placed in keyway
f632faa8-cc42-4099-9028-61464b8577b6 | checkpoint | Proper type for conditions
c209b8ed-b48e-4d45-90ba-124da639d079 | checkpoint | RX grid pattern or protection slab
19a8c61d-6589-4752-8f76-2efcd4a7b8cd | section | Penetrations
0cccf26d-1bf7-43bb-b9f9-5bd52528d2a4 | checkpoint | RX around PVC pipes
fc1fd657-8846-5856-85cd-02ad3a8700a6 | textbox | TYPE
f0ff01ea-f533-4b32-b3cf-86f790d640ae | checkpoint | RX 102 at 100mm between pipes
dfe95385-5b4e-4a66-9430-31ec51ba41fd | checkpoint | Waterstop RX continuous
e238570a-5753-40ce-a66a-4f8c0dc282cb | checkpoint | Ends tightly butted
7b6e2d40-0ea3-4d9a-a06f-078191b13b1b | checkpoint | Adhesive used:
c39dd231-b1cf-5f0d-b091-b826846d525f | textbox | Name
c1cc0de8-9247-4491-b8de-98d28857f547 | checkpoint | Tiewire used
9e3a7b0a-1b34-4ce5-b4db-17cb5f2570c9 | checkpoint | Proper concrete cover
7f3fed94-2787-422c-be7b-7687fc493bec | checkpoint | On both sleeve & penetration
4844c7f7-b2ce-493f-a81a-c436cb4c60f6 | section | Pile Caps and Grade Beams
cb4a26ae-a121-4aa8-9890-0f5bfd79fdbb | checkpoint | Above waterproofing
017db697-dfbb-43ff-9381-909f0e44b89c | checkpoint | Rebar encircled
dae0b198-1ef2-496a-83d2-1539dbb79f99 | checkpoint | Waterstop continuous
89b0baaf-1646-46a7-ba88-706722d8ec0c | checkpoint | Ends tightly butted
a13cd06f-7121-443b-96d9-3dba223a72e9 | checkpoint | Proper concrete cover
09778b35-7573-4569-a1a0-7c0315010e3d | section | Completion / Handover
59e167fc-f451-406e-ae1d-39acffb1bc3a | checkpoint | Product installed correctly, checked & reviewed - as per specification
90a86817-3a32-4a13-8f3a-f43f524da090 | signoff | Raise Remedial / Request Review
72195132-8a77-4d1b-9801-7c35c3859301 | checkpoint | Area left clean & tidy
389650a9-414e-4e89-aa01-4795e5c93c9d | signoff | Raise Remedial / Request Review
e0ba3fc8-f9b4-403b-95ef-d111839280b3 | checklist | QA - (CRL) Underfloor Checklist |  | CRL Underfloor QA Check List
c1bc04ff-5f86-45bf-9dbd-11ff139c280e | checkpoint | Gridlines
807be599-f4e0-5935-beb5-85e66f54a5fd | textbox | Gridlines |  |  | ( | ) to
67d36bdf-0d6e-592d-aefe-503b0bd832b7 | textbox | Gridlines |  |  | ( | )
c607b32f-b7d2-4134-a2f0-b09ef9dc502f | checkpoint | Site concrete poured and accepted
8ae2a759-d5c2-4a26-a672-2965970822f0 | checkpoint | Geotextile placed
6bf53b12-9138-474f-8863-af76506588e2 | checkpoint | Sikaproof A placed
c0fab7d5-13b3-4161-84b3-440b4bcad4ac | checkpoint | All laps taped with sikaproof tape 150
665aba32-3942-4594-a5c2-4e37ade9ca0d | checkpoint | All piles detailed as per the specification
47b80a41-f714-4141-8f39-5e00dc884758 | checkpoint | All waterstops and injection hoses have been placed
66947f4a-3dd0-4cb1-9aa2-111836a70cec | checkpoint | Waterbars have been installed where required
15b6fd1d-a37f-4a9d-a41c-1f8ca85d4d57 | checkpoint | Final inspection and hand over
3f82f95c-e0d2-4844-9e1d-3d9600308d02 | checklist | QA - (Fisher&Paykel) - Joint Sealant Checklist |  | F&P - Joint Sealant Checklist
8c340bb7-3c1a-495e-bcc3-a2220f7353a6 | checkpoint | Panel Joint 10 - 40mm
6d8021a6-874c-457f-bd0b-113eaf59b67e | checkpoint | Substrate Acceptable
20c889aa-cde8-484f-a2d6-0b4001b4fec4 | checkpoint | Adhesion Testing completed
48ed4a33-24ec-4e14-b87b-f77b08d645d7 | signoff | Raise Remedial / Request Sign-Off
f34f0c21-ad0f-449d-9668-bcacad2946b4 | checkpoint | Joint sealing - PEF rod installed
3db5a990-8b52-43ca-984f-8623c4c92d80 | checkpoint | Joint sealing - Bond breaker tape installed
ece223d4-1d7d-480d-8699-095e99a0fdc2 | checkpoint | Joint sealing - masked either side of joint
8b19ca47-f790-4c2d-bfed-ccb245ef44c6 | checkpoint | Primer applied
2c4c0f04-9cce-5ac5-92da-7970a7dbc7e0 | dropdown | Primer Type: | OTHER, Sika Activator-205, Sika Primer-215, TREMprime Silicone Metal Primer, TREMprime Silicone Porous Primer,Sika Primer-3 N
59b3c343-183b-47ad-9bcc-2d987f4c7ba9 | checkpoint | Batch number photographed or input
ee66649c-1817-57f7-b141-ec26d9e99459 | textbox | Batch Number:
d3a20886-36ae-4f6d-a8b6-6fa387298ef9 | checkpoint | Sealant applied
de74cdec-4498-5f85-9159-a5305e0a50ef | dropdown | Sealant Type: | Dymonic FC, OTHER, Sika Blackseal-1, Sika Firerate, SikaHyflex-250 Façade, Sikaflex AT-Façade, Sikaflex MS, Sikaflex Tank N, Sikaflex-400 Fire,Sikaflex-11 FC
4ff0ed72-9479-4ad8-a504-c7d1d8a1282f | checkpoint | Batch number photographed or input
2d3b2ca4-58ff-5ce2-9389-3aeef0cdc0ee | textbox | Batch Number:
f0af3c32-20b6-4c86-93a2-01a4f269f738 | checkpoint | Joint Sealant installed correctly, checked and reviewed as per specification
85fb5397-12cf-4f31-8590-78cee2020f0f | checkpoint | Site Area - Clean & Tidy
67753cd0-d4f7-4614-bd8b-eca602f896df | checklist | QA - C1 Tunnel Stub Sign Off |  | C1 Tunnel Stub Sign Off
604050b0-e693-4f90-92e8-35658ceb9cdc | checkpoint | Substrate and all voids prepped
730c4e97-3e01-4270-b42a-d18c4b1bf97f | checkpoint | Sikaproof A is tied into the water bars where required
ebc21560-6129-4dfa-9957-7a03927bb594 | checkpoint | Sikaproof P areas are primed
1ee80b94-4742-4208-96de-305e8e6bd78a | checkpoint | Sikaproof P is installed and tied into the water bars where required
7c95b751-077f-4f31-a6a0-ce94f135cbd4 | checkpoint | All external tapes are in place where required and geotextile protection in place
cf6a11d2-a974-4306-94ba-65c5104aac03 | checkpoint | Roof geotextile in place to receive the sikaplan 1100-20H
2fffbe69-f476-4028-a0fc-d77dc86e25d2 | checkpoint | Sikaplan 1100-20H placed and welded to the water bars where required
1fe44e23-3125-4f40-a6fb-4a1fbb3d8eed | checkpoint | EFVM test completed and any required repairs done
1cb94142-3e97-4f4f-a0f6-700b3b16f79b | checkpoint | Geotextile protection placed to receive the backfill material
1be3c28a-6b2e-4c76-9057-a68e56e805e1 | checklist | QA - Concrete Repair Checklist |  | Concrete Repair Checklist
fee00e50-3958-4b79-a663-6fa647967173 | section | SB1 Dicore Supports
97b95b7d-1301-492b-9dbb-9539fb79b59d | checkpoint | Marking holes
687ceda9-19b8-4ed5-b5ae-bcdafd3f1900 | checkpoint | Drilling 150mm deep
d15301e1-36b6-4371-a0ff-661a8625bfa4 | checkpoint | Cleaning holes
2af0efd8-c8d5-4fd2-b82e-da594ad5888e | checkpoint | Fitting bolts
d98e0549-43dd-486f-9fb8-aaffd6cdd1c4 | checkpoint | Fitting plate
257ee064-d598-4fa4-9122-ef61bdf03378 | checkpoint | Bolt tension
05827e6d-950b-493d-ae77-5789762f2247 | section | M12 Hangers
f8b49ba9-31db-4204-a9a1-496b7a12c83d | checkpoint | Hole location
5a6494f3-ce0c-4b70-89d0-a10b513b15bb | checkpoint | Hole depth 380mm
8421cc68-8681-4000-a4ab-57f7e3c4aea4 | checkpoint | Cutting 380mm
e5b2c94e-bf59-4266-bfbd-b09311dcb0a1 | checkpoint | Chip out 20mm deep
e7e66b97-60d4-4004-847b-440164c25e31 | checkpoint | Fit bolt, washer, nut, pour epoxy under plate, tighten nut
4f2f1ddc-f054-40e1-a66d-3da6033f479f | checklist | QA - Coreflex Pre-Installation Checklist |  | Coreflex Pre-Installation Checklist
c193ff7d-42c5-4bef-a64c-a7640413e7a9 | section | Pre-Installation Meeting
e7766ef3-c71f-40b8-8fc9-e02917cc85de | checkpoint | Installer information input
16f5fbfb-9d2d-57d3-97f9-d9243d2d145e | textbox | Name
536c046b-04a4-5231-bce3-d41bfc3b45a3 | textbox | Email
e99ed156-5c0d-4dab-8c88-74064fb2596f | checkpoint | Installer has signed on screen
9f9ce9c3-4f75-4e15-9c38-16dd50aa71a8 | section | General Substrate Requirements
b13d5b4b-5087-45e4-8037-05cabb9e25ad | checkpoint | Concrete substrate must be uniform smooth finish with 19mm max sized aggregate to be used
667747c9-30e2-4dab-b15d-9f00339ebb58 | checkpoint | No sharp edge aggregate to protrude through the smooth substrate layer.
c92e179e-9bef-413e-95c5-ace07c6d3d09 | checkpoint | Acceptable weather for application.
127a45c7-550f-41ca-a94a-5d0c8377d169 | checkpoint | Substrate must be free of debris (windy conditions need to be accounted for)
7e40f2f2-f649-4876-a159-43282f4d7586 | checkpoint | No standing water to be present where application is to take place
b66fb1e7-04a7-47d7-aade-fddcc15c3d73 | checkpoint | No ice to be present
38538826-5a55-4ea0-b160-342610b1ecef | checkpoint | Weather forecase must be monitored to ensure substrate doesn't become compromised
56815062-6c8f-4d5e-9a33-db7d7a35a0a0 | checklist | QA - Crack Injection Checklist |  | Crack Injection
3fced928-64f0-40be-9485-37e549bc2aab | section | Checks
27199827-c936-4738-a3da-c6855452b566 | checkpoint | Identity the type of crack and the method of injection required (Polyurethane, Epoxy, Acrylic gel)
61f56787-3734-4e3b-95f8-6d444d1fd018 | checkpoint | Identify if the crack needs to be injected via surface ports or drilled in borepackers
f3a919be-0c93-40b1-b77e-779996bf1def | checkpoint | Mark out ports and borepacker holes
b52f480c-bf5f-43ba-a0e7-925bd060e055 | checkpoint | Drill holes and place borepackers
67b03e5d-17f5-45d8-9ff8-73f0f9b91dc2 | checkpoint | Form surface ports and place surface seal over the crack
55e8169d-5483-4d2a-be68-5fc42f91f3b0 | checkpoint | Mix and inject material to manufacturer's specification
7b7a89ec-1822-4a61-aaba-6dfaee2ba31e | checkpoint | Manual injection with caulking gun
ee5235d2-a6ba-4ddf-ba14-7a9a95ffac76 | checkpoint | Single component injection pump
52e79db9-0bb2-4df4-89b1-9e162295c26a | checkpoint | Two component injection pump
8a9e7861-6d6f-43ac-ab13-a099bd989376 | checkpoint | Injection clean up
22f0e5ae-1566-4c80-a9fe-979aa0db3962 | checkpoint | Complete QA documents
35f92607-05a4-40e4-b845-87e40f42c58d | checklist | QA - Fuko Hose/Water Bar Tunnel Wall/Roof Installation Checklist |  | Fuko Hose/Water Bar Tunnel Wall/Roof Installation -
99835080-b8ee-4c01-9484-a9768e824ad0 | checkpoint | Substrate clean and ready to receive the fuko hose
b4a003a4-ef98-48b4-85f7-653f99c66c55 | checkpoint | Fuko hose placed
99778d69-cf87-46b6-87a1-8db1e281baa7 | checkpoint | Water bar taped ready for form work
c66e795e-558c-4b37-b9de-7b8ed7279136 | checkpoint | Water bar adhered to form work ready for the concrete
38446323-0815-447e-956b-42986460ab49 | checkpoint | Concrete poured by others
833e8c3a-7344-48fa-b579-b5473fdd38d4 | checkpoint | Sign Off
9bcd9d76-4f5b-418e-9c48-c55bd1449191 | checklist | QA - Ground Beam Tanking V1 Checklist |  | Ground Beam Tanking -
24fe2ea7-a419-453d-87c4-f571413bd8ad | section | Pre Start
fe3d39de-2e50-48ff-aba1-13008e8b8e45 | checkpoint | Work area clear, tidy and accessible
6cf7ec7f-faeb-465a-a3cd-441090fdbc71 | checkpoint | Previous substrate/opening acceptable
54331a01-e9b2-4c14-9c46-4db6004b3e0c | section | Install QA
cbcf461c-bb2f-49b8-a04c-7ba1bee32f3a | checkpoint | Area (grid lines)
9b8be6fc-c899-4c0d-9ef8-5f5c66aea451 | checkpoint | Pile tops sealed with epoxy
3fe075f3-e13c-4d07-aeb6-7fe24e5a4fc7 | checkpoint | Preprufe placed and laps taped with Preprufe bedded into LM 3000 on top of piles
761924f8-0955-4268-902f-788c99a809fe | checkpoint | Adcor 500 T placed around the top of the pile
9429a955-3c47-44bc-826a-48a841d5a41e | checkpoint | Swell seal WA placed around all pile bars
2f59a5a4-d12f-40a8-922f-d7c4f8e83758 | checkpoint | Preprufe lapped and taped to the DPM
fb9e85a1-4d55-4a77-8ddf-814406700bb5 | section | Handover
01e2331b-6a86-4200-9afc-ae4e443d649f | checkpoint | Area and item left clean and tidy
8fb874e3-559b-44d9-9a74-b8a3936865e8 | checkpoint | Final Sign Off
e04c25ca-7d71-4212-9f17-cc05cd7743e4 | checklist | QA - Head Wall Bituthene 3000 Checklist |  | Head Wall Bituthene 3000
066a87af-30f6-4833-9186-d3c0520a6752 | checkpoint | Substrate and all voids filled
79561e5d-1acd-478c-b668-f145bac3ec39 | checkpoint | Substrate primed ready to receive the Bituthene 3000
967d5174-f263-4fa0-bc2c-240e67fec856 | checkpoint | Bituthene 3000 placed on the prepped area
23368520-53a3-493f-b61d-a26d85ebe3d2 | checkpoint | Laps sealed with Liquid Membrane
1f83d5ee-569a-4a2c-b22b-05bd414aeb4d | checkpoint | Coreflute protection placed
0f71d9a4-27b0-45c8-ae4e-2aa42ce6a279 | checklist | QA - Horizontal Stitch Checklist |  | Horizontal Stitch Checklist
38c566a4-5fb0-4017-8bac-1b5a979a650d | checkpoint | Work area/substrate is clean, dry and ready to start
d2771573-ca4e-487c-a1fe-6e4ddd0c277e | signoff | Raise Remedial / Request Signoff
22b5bc39-f4c2-438b-aefb-87511296c285 | checkpoint | Photograph(s) taken of substrate
ed02631d-b321-4841-91ec-51cf8b7153c5 | checkpoint | Joint width measured
5eb92ebb-6f75-46fd-bd22-f5d94c4bff98 | checkpoint | Photograph(s) taken of installed backing (showing sealant)
deb860b0-8521-4679-a51a-ae13d724ae3e | checkpoint | All joint sealant installed correctly, checked & reviewed - as per specification
eb0198fc-cd49-4523-8051-a187843d3cb3 | signoff | Raise Remedial / Request Review
8aae4d2a-94bf-44ed-a74e-7b4b389f7e0f | checkpoint | Area left clean & tidy
2dc6e05a-1689-46cd-8f58-79769e212154 | checklist | QA - Hydrotech Checklist |  | Hydrotech
49b00c15-54be-437a-adba-1954e4e7676c | section | Project Details
62c20fda-e81b-4ec7-89d3-ea4f82f8bd1c | checkpoint | Details Complete:
75aa5cfe-075e-57df-846c-c3f040457a8f | textbox | Project Name:
80ca1298-5893-5c87-8d5a-525e789d8772 | textbox | Project Address:
5a70efe2-7daf-52ec-9fd0-13a480eff418 | textbox | Certified Installer of Hydrotech:
c690e7d5-85d6-54d8-8438-dead96d0cfb4 | textbox | Main Contractor:
8ed6c882-da6e-5a7b-bad2-dd51aa037041 | textbox | Project Manager:
b328805d-0b8d-5f3f-be17-44c5cbbfbb4d | textbox | Project Manager Contact Details:
ec9f99db-8cc9-5f78-ac61-11aa3ab45ef3 | textbox | Key Contact with Main Contractor:
bfce3769-5985-59f7-899e-bc1e27f387a3 | textbox | Total Estimate Quantity of Hydrotech |  |  |  | m2
a36a9278-ee7f-5770-ae6f-6900eb185e4d | textbox | Estimated Start Date:
713ff723-bf85-57cb-bbab-511a94402816 | textbox | Type of Situation Hydrotech is being used in
99a376e2-c87a-5118-a50f-6b80e4cdf393 | radio | Type of Situation Hydrotech is being used in | Blue Roof,Deck,Green,Inverted
0768d9b6-7bee-561d-9737-082a6a32f3b9 | textbox | Confirm type of Balas to be used:
7e39cc17-6381-59a8-8a00-4110db6e1396 | button | Is this going to be staged work? | No,Yes
5c785696-9d28-57d1-969e-fb412dd0594e | textbox | If yes, please provide brief description:
ecb28790-7d58-5b71-bdaa-58040b26cd7b | radio | How will this be applied? | Both,Pail,Via Kettle
2c4e10a7-9f23-535a-82be-9487c0225b7b | button | Is the site aware of the size of the Kettle? | No,Yes
9058083a-35f9-5796-afff-f21f299733f0 | button | Is the Site aware of the Hot Works? | No,Yes
9f0fb70e-ce47-58d5-8d02-02c79fbaa282 | button | All parties are aware of the relevant PPE? | No,Yes
17ba364b-3980-4c6d-af2d-db00a4f96df8 | section | Substrate Acceptance
8d605b3a-b783-42a7-9940-74bb4920fd64 | checkpoint | Substrate Accepted
e4d139d8-e200-50f6-b0ca-bac7eff7da0c | button | Is the substrate acceptable being dust & dirt free? | No,Yes
cf10e1e9-9959-5b40-ab29-22fc714d298a | button | Is the substrate acceptable being completely dry | No,Yes
bdf454ae-c854-56e9-9085-637c92aacda0 | button | The substrate doesn't exceed the maximum degree in slope to apply | No,Yes
12ee7833-dc7b-581e-bdbd-89ea1503023d | button | Substrate bonding test has been completed | No,Yes
1c52ac05-12cf-571b-903f-1117121d2ea1 | button | Substrate bond test was acceptable | No,Yes
771f53ef-9743-417b-953f-430bb14c5c8b | section | Installation of Hydrotech
9ae33e54-1644-4a42-b1a3-6c0e835695c4 | checkpoint | Installation Complete
57124a56-877f-5630-9ad3-5bba4fced7d4 | button | Weather forecast is acceptable to commence application of Hydrotech | No,Yes
4e3305a1-96bd-5cc8-9667-33dc43764f9f | button | All penetrations have been identified and agreed to | No,Yes
ad221d64-35da-5527-acef-0d75f6c8c3e1 | button | All penetrations involved in Hydrotech are detailed accordingly a per specification | No,Yes
04144c15-160c-5a9e-99ef-93348847182a | button | All upstands control joints and penetrations have been identified and prepped (NOTE: Upstands require min 150mm vertically and 75mm horizontally with flex flash x reinforcing) | No,Yes
12fb5279-aecf-50db-9ae4-17ed25468805 | button | All upstands and details completed | No,Yes
0735b289-d4c7-4452-b5c0-537107502c8b | section | Installation
2664bb12-23ec-41d6-bc63-1d651d28b246 | checkpoint | Installation complete
d6af5082-fa96-5912-85fd-4eafe7e9a8f2 | button | 1st coat of Hydrotech has been successfully applicated under correct weather conditions | No,Yes
15d4500d-4e91-57a4-b0c9-7d3226092cbc | button | Evidence of 1st coat being consistently 3mm thick has been provided | No,Yes
c0f03f70-a973-53bd-a37c-b0357514f77b | button | Reinforcement has been successfully embedded into 1st layer of Hydrotech | No,Yes
799b9d0e-c99d-576d-869b-18660ca9f8a4 | button | Reinforcement layers has had all air pockets removed | No,Yes
fe872fcd-2de6-57c9-944c-938459f8219f | button | 2nd layer of Hydrotech has been successfully applied | No,Yes
8f6142cf-cb54-5509-adaf-5ae63d77f2dc | button | Apply protect sheet as final layer | No,Yes
cf0b0467-0472-5436-8ab8-c254d10ba239 | button | Check overall thickness and provide evidence using a hydrotech depth gauge being 8mm+ | No,Yes
b1b88fc8-e635-5f4b-a768-9e11aaf56888 | button | 1st coat of Hydrotech has been successfully applicated underte correct weather conditions | No,Yes
e535e3d3-ef3f-42bc-9f05-bfad0efd6b66 | checklist | QA - Hydrotech Checklist (Simple) |  | Hydrotech Checklist
487534a7-a52a-4509-a5ba-ff548664b182 | section | Substrate Acceptance
92604fdd-7a55-48b5-b664-9118467177c6 | checkpoint | Is the area accessible/acceptable?
f639fd46-bab9-4851-9c43-263bf25dbb85 | checkpoint | Is the substrate dust & dirt free?
da9d38aa-5f42-4304-88b3-787905a33b69 | checkpoint | Is the substrate completely dry
c9ed6828-c83a-40da-9ac4-dd8d55bf8bd4 | checkpoint | Has the approved primer been applied to substrate
2739025b-fe6f-49bc-8c4c-3156f920e512 | checkpoint | Are substrate falls as per specification
c5299c99-03ad-4f7c-ae9c-f41b99e43245 | checkpoint | Substrate bonding test has been completed
6732327d-7d58-4f8f-a071-ab23a2b08c26 | checkpoint | Substrate bond test was acceptable (if no, seek advice from Allco)
1990da3a-fc22-43a8-b3bd-7294ff616e49 | section | Install QA
32d9555a-0963-4fd7-a93b-9776037c35c3 | checkpoint | All penetrations involved in Hydrotech are detailed accordingly as per specification
73a5afcb-2ec4-4287-bb54-f0dae555be8f | checkpoint | All upstands and details completed
35334a41-012a-4488-9cfe-e37a0d2abdf8 | checkpoint | 1st coat of Hydrotech has been successfully applicated under correct weather conditions
60ca6e38-8ce1-43bd-b085-e09d5ed8abad | checkpoint | Evidence of 1st coat being consistently 3mm thick has been provided
68fc3678-ce23-47e9-90e7-9a3354809687 | checkpoint | Reinforcement (Flex Flash F) has been successfully embedded into 1st layer of Hydrotech
34dea74f-0a32-476d-b17e-48ca21de6118 | checkpoint | 2nd layer of Hydrotech has been successfully applied consistently at 3mm
1d90deb7-9d0f-4ff3-8e6a-5b7759852da0 | checkpoint | Apply protection sheet as final layer
8f59b1e6-054e-4150-9d1d-6fddf331ebaa | checkpoint | Check overall thickness and provide evidence using a hydrotech depth gauge being 8.5mm+
416de179-7ebd-41a0-a048-7a640b527833 | checkpoint | ILD Test Completed
1e94a879-ab06-431f-9a48-9ac0ecae6e8d | checkpoint | Ballast Installation
696b24bb-95e0-4915-a7fd-112b732fb607 | checkpoint | XPS board being installed. Correct thickness used.
607f9911-ad3d-4c76-a184-367c9803c6e6 | checklist | QA - Joint Sealant V1 Checklist |  | Joint Sealant Checklist
03724bda-8c88-443a-905c-93abc16c42ab | checkpoint | Weather conditions recorded
2d23b91b-0be6-5c12-aecd-9a331dde836d | textbox | Morning
c8b7d3be-2732-5999-9c42-b79ef7c49262 | textbox | Afternoon
7c80bea4-edfd-464f-b61f-9c406fcf68a4 | checkpoint | Existing sealant removed
02e8d279-0641-4c86-b3c8-57fe38bbba93 | checkpoint | Joint edges ground clean
f0840434-21c4-4492-aa7f-e688e3698670 | checkpoint | Joint edges clean and free of defects
fb94355b-e7ad-4677-805c-471e9786b2ca | checkpoint | Joint size between 10 and 40mm wide
b451991c-31b9-4927-8b46-a6453114aed3 | checkpoint | PEF rod installed?
58402d35-d22a-453a-8674-6bc0ed8b0afc | checkpoint | Expansion tape installed?
7ecd0420-9b79-4a60-8f0d-415b36a692eb | checkpoint | Bond breaker tape installed?
6a68a36a-5551-4df1-9194-9c164a607f5d | checkpoint | Masked either side of joint?
74286fe5-4d7a-44db-9d9f-5e515ae9dda8 | checkpoint | Primer applied
e009fb79-a8e1-58e1-ae02-f980fc0ddf93 | textbox | Primer type
b2751b1e-c81c-5396-ae23-6787a6b08a40 | textbox | Batch number (s)
68166514-09a3-4b47-852d-e3ba7aa91ce7 | checkpoint | Sealant applied
3fead575-ef21-535d-90c9-f11fb26601ac | textbox | Sealant type
d6028252-e976-5ac3-8c6b-d847127b23b8 | textbox | Batch number (s)
dc808911-3d13-411b-b9e3-2abed7d33f2b | checkpoint | All joint sealant installed correctly, checked & reviewed - as per specification
0cb0a1e2-a99f-4f97-96a1-2241b512f86d | signoff | Raise Remedial / Request Review
d453590e-67f8-476e-9d15-a760ada6dc6e | checkpoint | Area left clean & tidy
9dedc8b4-d1e0-488f-819e-a746fc6fd99c | checklist | QA - Mapei QA Checklist |  | Date:
cfcfa32b-31cd-4587-9c27-eb7246dac6d5 | section | Details
27c6ddfa-31a7-456e-85a1-172cb4f9ef67 | checkpoint | Details Complete
505240d8-8387-5303-8ac2-94c9b40bde8a | textbox | Date of Application:
3dd9f2da-5921-51f3-a5cb-c2bb99a479aa | textbox | Application area:
9e04ec04-ccdf-5cad-84a5-2500f4301caa | textbox | Installer:
5b2b8484-ed15-42e9-8278-2be94a0f9143 | checkpoint | Product used (Name – Quantity – Correct labeling – Batch Date – Expiry Date): (product must have been be stored in a dry place in temperatures between +8 degrees Celsius - + 35 degrees Celsius)
c0dc1ba6-5c37-4a59-86bd-222d49739baa | section | Setup
c077ebfa-ed75-412c-9db7-ff5510eda1a3 | checkpoint | Confirm testing regimes, types, and frequency required by the project engineer
56a06d0e-50f4-451a-8d22-710300c89ee1 | checkpoint | Confirm the design drawings are current
650ae8a1-43e9-4c88-a7cf-1b398cc8ca26 | checkpoint | Ensure that all tooling is available
3e18cbdf-bb0b-414d-a6b3-48a6caeaef86 | checkpoint | Check that all personnel on site are aware of their individual responsibilities and know what they are doing.
67ee7ee3-fbd8-46fb-90a2-d034f74f48f7 | checkpoint | Protect all surrounding areas from damage
5f137ba6-8cea-4d36-9439-7552a9cfd54d | checkpoint | Have all necessary personal protection equipment on site and in use
a8ad8f95-230f-45b1-b24d-7417dfcbc965 | checkpoint | Take photos of each step of the operation
9b8bfe6d-25c2-433a-abe8-79974128b142 | section | Environment
25f3279d-5bfd-4007-a616-bc8f89345a38 | checkpoint | Check and record ambient temperature (Must be between +8 degrees Celsius and + 35 degrees Celsius)
524b3af8-172c-5c75-866f-ce26fdad7ad4 | textbox | Check and record ambient temperature |  |  |  | Degrees Celsius
3bc585ee-8f99-4144-a9d0-f3e0a940eb64 | checkpoint | Check and record substrate temperature (Must be between +8 degrees Celsius and + 35 degrees Celsius)
e044ca3d-7539-5660-855e-6c46d37b52f0 | textbox | Check and record substrate temperature |  |  |  | Degrees Celsius
52f1397c-25f2-4a5c-a808-c09194a509f7 | checkpoint | Check and record air humidity (Be aware of Dew Point, especially in the mornings, evenings and at any other time there may have been a sudden increase or decrease in air temperature)
7215a8e7-4789-4e77-b380-cfd99986c04f | checkpoint | Check RH of substrate it should not be damp, it should not be above 75% RH it should not be subject to rising damp. If dampness is present then consult with Mapei for an appropriate solution
657fd534-0e47-43bd-b602-8ded0a850cf4 | section | Substrate
39da0bc4-954e-44f1-8c86-560782dc826f | checkpoint | Checked to be structurally sound
2db5415a-2611-42ab-8b0d-5fa040abce57 | checkpoint | Checked to be dry and dust free
29308ba8-3cd8-4b1b-b7fc-35850444a830 | checkpoint | Checked to be free of all contamination
a73d1f94-2259-4a61-8b0e-7d850f3f33eb | checkpoint | Checked to ensure concrete has a tensile strength - 1.5MPa
fea434ff-b21a-4498-9594-2a295a5a2926 | checkpoint | Rusted steel work cleaned to bright finish and treated with Mapefer 1k
90d19e33-2519-4d28-bc22-4f3a0ddc79b5 | checkpoint | Carry out any required repair work to the concrete host substrate using Mapegrout T60, Mapegrout Hi-Flow SP, or Adesilex PG 1 depending on the nature of the repair work being undertaken. Allow adequate curing of items prior to installation of the Mapewrap system
1fa989a8-9c3f-43ec-8ffe-e32995b6413b | checkpoint | Ensure there are no sharp edges or sharp protrusions in the substrate that could damage the application – External corners must be rounded to a radius not less than 20mm
955eb6bf-3e8e-4b83-97f4-7a9863229e91 | checkpoint | Cracks wider than 0.3mm repaired with Epojet LV
fe6b7829-7889-545a-9df1-dea80bb56520 | note | Take Photos
2a03abc7-f046-426f-9b75-aa432c7fe8bf | section | Substrate preparation
2cadf4b9-8237-41ee-94d2-55ac03292ad4 | checkpoint | Substrate must be freshly exposed and have a slight surface texture (around 80 grit). It must not have a polished finish
a844cd6f-dea0-4db9-a5ed-83e446f7c517 | checkpoint | Substrate must be free of all resulting loose and unsound materials. Check for any chalkiness to the concrete surface using a scrape test and if the substrate is chalky then this part of the surface must be removed to provide a structurally sound bond face
17236910-10ca-4d10-b178-bdddcf700d85 | checkpoint | Existing soft materials must be removed and if it appears the substrate is of low compressive strength then this must be reported to the installation team foreman for further action and instruction before proceeding, this should include a consultation with the project engineer
9d9cb79d-0123-428e-8b96-6c3447b39a65 | checkpoint | Ensure external corners are rounded to a radius of not less than 20mm
5ee9475e-3a06-4f76-a246-5debcbb60342 | checkpoint | Mechanically remove any sharp protrusions or surfaces. Ensure the substrate is smooth and has no sudden changes of plane (must not exceed 1mm)
7d1aa48d-4bbe-4198-9c49-04f4886b461f | checkpoint | Check for any pin holes or voids in the prepared substrate, these must be repaired and smoothed prior to the installation of the wrap using products from the Mapegrout range or, if immediate repair work is required, use Adesilex PG 1 or Adesilex PG 2
7b49514e-07b8-474f-b4ae-1c6ccb5e173a | checkpoint | Accurately mark out positions for Mapewrap to be applied as per Engineers drawings. Any variations of the orientation of the fabric of more than 5 must be reported to the project engineer
daafc067-4485-50b9-a668-627095fa7cb9 | note | Take Photos
66bed653-49b2-41d0-bc17-7de256ce5c75 | section | Preparation of Materials
6f1bff76-4738-4647-962f-7e4609bd2bb8 | checkpoint | Ensure Mapewrap is cut to exactly the required length. It must be stored in a clean & dry area and be temperature conditioned before use
ea72af8d-5fe7-420a-a8e7-1dc29b653b41 | checkpoint | Check for damage to Mapewrap (damaged materials must not be used)
9a0b9593-bf1c-4e2d-a05f-9e253b629b38 | checkpoint | Mapewrap Primer 1 SP must be temperature conditioned and mixed at correct ratio being 3:1 (A:B) by weight for 1-2 minutes with a slow speed mixer until a homogenous mix is achieved
575872f6-aa86-417c-b470-47fc2ccbb855 | checkpoint | Mapewrap Primer 1 SP used within its recommended pot life (60 minutes @ +23 Degrees Celsius )
50181c88-3c01-4404-9c35-7f3a719b05fd | checkpoint | Mapewrap 31 SP epoxy saturant must be temperature conditioned and mixed at correct ratio being 3:1 (A:B) by weight with a slow speed mixer until a homogenous mix is achieved
1247ab7c-96db-4b56-afa7-dac04dbacac8 | checkpoint | Mapewrap 31 SP is used within its recommended pot life (60 minutes @ +23 Degrees Celsius )
c3b29a42-14c6-5411-96db-15d1806f682b | note | Take Photos
1979bd02-1937-4672-b042-b2f2b29a4efa | section | Installation
fc6c80cb-e575-4b3f-8e84-ecc8760a2e4c | checkpoint | Clearly define, label, and note application area. Accurately site measure each area and calculate the estimated consumption rates for the materials to be used recording these on the consumption chart. Monitor and record the actual consumption rates of the materials used and ensure the estimated and actual consumption rates are in line with each other. Any variations must be investigated, noted, and reported to management
b3a0db95-d8ec-415a-8eb9-81978f810af9 | checkpoint | Provide adequate temporary coverings to surfaces in the surrounding surfaces to protect against dropping and spillage of the resin based products being used.
21b7f6d1-185b-4257-8396-abc00fd06cd6 | checkpoint | Correctly prepare substrate priming it with Mapewrap Primer 1 SP using a brush or a roller. Depending on the absorbency of the substrate a second primer coat may be required
418b00d4-b916-4bcb-8255-244ab9aef581 | checkpoint | Install Adesilex PG 1 to all concrete substrate areas that require smoothing or have pin holes. The follow on application of the Wrap must occur while the Adesilex PG 1 is still freshly applied (within 12 hours of the Adesilex PG 1 being applied). Should application of resin based products be required over Adesilex PG 1 that is beyond its fresh time then the Adesilex PG 1 must have its top surface ground then wiped with Isopropyl Alcohol ensuring all resulting dust has been removed. Any areas where concrete has been exposed during this process will require further priming with MapeWrap Primer 1 SP. Should the Adesilex PG 1 have a oily, waxy, or greasy feel to it then do not proceed with the follow on installation and instead report to management for further instructions
19f6d5ce-8d90-4ba1-828b-ce1cdfd525fc | checkpoint | Apply a roller coat of MapeWrap 31 SP to the substrate to provide an even coat of product to the area being treated (refer to consumption chart)
7b4e78a0-94d9-409c-9277-ca521e8f638c | checkpoint | Saturate Mapewrap with Mapewrap 31 SP (refer consumption chart)
ada48b3b-41aa-44ea-9e6c-15d7d18a1a86 | checkpoint | install Mapewrap as per orientation in Engineers drawing, constant pressure applied over the Mapewrap smoothing by hand and including using a ribbed roller to ensure the fabric is impregnated with the resin and any entrapped air is removed. Always roll in the direction of the fibre never across it as there is a risk that the roller used could damage the fibre. If required apply another roller coat of MapeWrap 31 SP
2d8ccfa4-a3a4-41fd-9682-ae6a91a3d734 | checkpoint | Thoroughly check any entrapped air is removed and complete a visual inspection to ensure there is no evidence of dry fibres. Any potential issues identified must be immediately reported to the project foreman for further action
030731f1-b703-4482-9723-a12beeebb738 | checkpoint | Misalignment of the direction of the fabric of more than 5 degrees to the Engineers drawing must be reported to the Engineer for evaluation and acceptance
ab2f1f14-f7ef-4a12-8a3d-c42a57ad7e85 | checkpoint | Laps must be staggered and not in line with each other (unless otherwise directed by the Engineer) the minimum overlap for laps in the direction of the fabric is 200mm, the side laps for Uni-directional fabric can be butt jointed
9c4b1f9f-e363-4f6f-88a5-9777ce5ad4c4 | checkpoint | When the final layer of Wrap has been applied and if a layer of sand is required to be applied as a mechanical key for the follow on protective and/or aesthetic coatings then the broadcasting of sand is to be carried out as a separate process once the MapeWrap 31 SP used to saturate the last layer of wrap has tacked off but before the fresh time of the top layer has expired
8f4cabce-3200-4d28-8a34-3adc9c91f04e | checkpoint | At all times during the process keep samples of resins mixed and wrap used for further analysis if required. Label and record these samples including the date mixed, the application area and keep them in the same area as the application being undertaken at that time until cured after which these are to be kept safely stored.
3bea9d7e-b923-522e-a903-ab82f1851b4e | note | Take Photos
30b7f204-7901-449b-867b-b7325c8aff09 | section | Testing (All results to be recorded and forwarded to the Engineer)
0458d739-a046-49f0-b198-e5253357a2b2 | checkpoint | Perform both a visual and acoustic tapping test of the installed Mapewrap to check for voids 24 hours after installation.
04cf1048-98ce-47bd-8b0a-d52e8b7dc380 | checkpoint | Carry out any other tests required as has been directed by the project engineer
bb55911b-07b3-4a75-8916-77351ad498ef | checkpoint | Keep and tag samples of materials used at a minimum of a daily basis or as directed by the project engineer for future testing and analysis.
1efba250-1c7b-57bc-aafa-35cb723abfcf | textbox | Signed: |  |  |  | Qualified Supervisor
1bafad63-605c-50ad-bc20-403d11de27bd | textbox | Name:
352e979a-55cb-59ce-b728-688c51f5b115 | textbox | Date:
58bc3bed-2f62-417e-a0b7-5a34fa9565ff | checklist | QA - Matacryl Checklist |  | Matacryl Checklist
c9415b1d-65ed-4205-9b3f-b5ae1f3e3c56 | checkpoint | Surface Preparation
bca1db4e-20df-4926-ba68-7405bd2709a7 | checkpoint | Primer
97bd8f4e-58a6-4eca-8bf7-322ba1312de8 | checkpoint | Coating 1st layer
de28b834-5961-4465-b129-bdb1e22d5910 | checkpoint | Coating 2nd layer
ed674d4a-b85e-4a5b-9d48-c2b5715c9edc | checkpoint | Coating 3rd layer
5d1faaf0-e815-474e-a304-6d5341d43742 | checklist | QA - Membrane Checklist |  | Membrane Checklist
e1aa7a35-42db-4a44-baed-838610ea283f | section | Checks
807d16cb-f05d-4559-8d7f-486790b54d0d | checkpoint | Checks
9750008c-ab76-5113-ac39-f876ebcd0c67 | textbox | Location:
1644b1b1-af9b-52a7-8dfc-2d971184de66 | textbox | Grid Line:
df4c51d9-2553-53b5-b8fc-a9893b0b5fa9 | textbox | Grid Line:
54991145-a9ce-4b52-80a4-9fdb951c9738 | checkpoint | Substrate
e6c4a773-5c40-43cd-b656-dd7145c05bff | checkpoint | Fillets
a4e3b257-4097-4a33-b7b9-c9b05d3a6aee | checkpoint | Flashings
adc01f17-e3e2-4caa-91e2-aad1dee9c0aa | checkpoint | Outlets
1524cf7e-28b3-42a8-98a5-cf8511542faf | section | Membrane
12e0e2be-ec7f-42f2-a9fd-bca6848d64ee | checkpoint | Primer
41b4cc0e-1f50-5e1d-9732-8fefa0da0bf0 | button | Batch completed | No,Yes
88a6101c-81b2-5c02-8f02-90c68000cf9c | button | 80mm side lap | No,Yes
835f94da-b8c4-5f50-b29e-9a5e47691655 | button | 100mm end lap | No,Yes
2bf2b1ff-3b21-4c96-9182-0d1fb02a3bdd | checkpoint | 1st Layer
8ab0bda2-bf91-5f33-85fb-d7ae1c179bcd | button | Batch Completed | No,Yes
2bdfb138-1440-56cf-9424-74b0179758cc | button | 80mm side lap | No,Yes
fc79f22d-f0fe-5c41-b234-11621ce2c4e3 | button | 100mm end lap | No,Yes
f64761ea-ba9f-4569-9b62-daa3c1f0455d | checkpoint | 2nd Layer
1b0c82ad-11d1-5e95-a8d8-76506bcd0c44 | button | Batch completed | No,Yes
b7fa285a-84e4-5f01-8c5d-3c1aece63952 | button | 80mm side lap | No,Yes
8fc16865-b05c-5343-a16e-f25250e4ab87 | button | 100mm end lap | No,Yes
43b4f119-72a2-46e5-b7cf-c12567f374ca | checkpoint | EFVM Test or Flood Test
d6c01044-9715-5e89-a00c-1c0136052840 | button | Batch completed | No,Yes
8208b1bd-7cc2-55d9-b7bb-6b370a261b95 | button | 80mm side lap | No,Yes
a85a45c7-77a2-5032-a023-a5eb971bd256 | button | 100mm end lap | No,Yes
1ef07454-e908-4779-bb2b-fb5ec605b694 | checklist | QA - New Joint Sealant V1 Checklist |  | Joint Sealant QA -
060aedc7-e1a8-4b85-b250-372d7cb12a1b | section | General Details
51504fa3-7551-4680-818d-cc8ab4ce098e | checkpoint-no-value | Details Correct
aef0d9d1-aa7d-5a5f-b97e-70853bb2fdcc | textbox | Job Name:
5aa6bc04-6485-5e8c-b0c0-7fe02c0047a4 | textbox | Job Number:
9ed7b018-9a98-40da-8820-892c240c157d | section | General Information
f4125a9f-2672-4137-aea8-ff50d61d44b1 | checkpoint-no-value | Details Recorded
f6c6428e-715c-5827-8374-815b90ba8938 | textbox | Work Crew:
a396ce2a-0359-54a9-a070-124e00168f5c | note | Weather Conditions:
ed922f9a-0d8e-5997-831b-dc45f35074a3 | dropdown | Morning | Cloudy,Overcast,Rain,Sunny
538f698b-943c-5ee3-afbb-b6d51bee9ded | dropdown | Afternoon | Cloudy,Overcast,Rain,Sunny
7d8e17fd-c679-4edb-89b8-314cf8ed0f64 | section | Joint Preparation
bb8978d2-d900-4220-b748-efafd1cc1471 | checkpoint | Existing sealant removed?
50533e58-c3c8-4bde-86e8-f880d543059c | checkpoint | Joint edges ground clean?
b801b5d3-6662-4a65-a5ba-5a6f7be6806f | checkpoint | Joint edges clean and free of defects?
01da8098-c44d-4e49-96f8-2a4711205350 | section | Joint Sealing
c22fce3f-7a21-43af-9e88-614f806ab75a | checkpoint | PEF rod installed?
b0be208a-878b-4e58-a44a-dd731ea59822 | checkpoint | Bond breaker tape installed?
04f66e5d-ea6a-4a58-a510-f5d8456fd8c9 | checkpoint | Masked either side of joint?
36714540-1ed2-422e-9f56-a4d9611a3f48 | checkpoint | Primer applied?
8753571b-d231-50f2-94b4-f4225e668d05 | textbox | Primer type:
ea227503-f196-5056-9b67-6252fef7951c | textbox | Batch number(s):
c3502815-b28c-40f3-8612-ab47a75c21da | checkpoint | Sealant applied?
699daf2a-7eeb-59df-b5a8-d0a00a0ee33c | textbox | Sealant type:
48a0a087-f651-5913-8e63-9c9bfa62ecd8 | textbox | Batch number(s):
62ded608-da04-55a0-8ff3-04d9e4e15f6d | note | Joint size and length
3afbac44-1e7c-4ddc-aa7e-44d07837580d | checkpoint | Joint size and length measured
d648f550-26bb-5745-89bc-aa134f748bfd | tickbox | 5mm x 5mm
6d0c0901-9bdc-5eae-99b4-94b35e8fa313 | textbox | Length:
3e7ac9ed-fe58-593b-a21d-053750acc9ac | textbox | Location:
574f3edd-a236-5c90-a172-3f81a2d091e2 | tickbox | 10mm x 10mm
53821cd7-fc76-5c68-9932-a2c582c919cc | textbox | Length:
f0244ca9-4f66-5920-af5e-45bdf5e7cfc7 | textbox | Location:
184f514e-d330-52a5-b31b-0fe3d6777f67 | tickbox | 15mm x 12mm
93c77ef1-439c-5b48-ad6d-0e21f2cb3bf5 | textbox | Length:
4c63c7db-892f-5b29-becd-2dac9f76dfc4 | textbox | Location:
9a5e6df4-14d5-517c-9527-6c770876e30b | tickbox | 20mm x 12mm
e7e41d31-278b-547b-9e72-b396a6e57aa5 | textbox | Length:
4d6fe4d9-79e9-5618-9175-05c7161a0fd4 | textbox | Location:
532c1fd9-b034-5f4f-980c-29821fbe37d4 | tickbox | 25mm x 12.5mm
c5c9e493-a772-5902-9c01-48b9e1253c66 | textbox | Length:
b8efe3df-a804-5b5d-a7c2-1321b34dd9d9 | textbox | Location:
c883945e-d13c-55cf-9ffa-ee5cbd3aec25 | tickbox | 30mm x 15mm
eaaadfc5-6d60-513c-8a8b-c73b3eebb726 | textbox | Length:
8d1a44af-9502-5721-8016-72f47c43ee71 | textbox | Location:
86eaf9af-d57c-595c-971e-db4339c98889 | tickbox | 35mm x 17.5mm
16a7c27e-9f66-5d07-9508-149a3ec86b9e | textbox | Length:
522fa87c-0f99-5a62-bed9-e76d986d08f2 | textbox | Location:
cafdcd16-4b82-5cb8-9fc2-bf4717d94724 | tickbox | 40mm x 20mm
02a4f8b8-80bd-5a7b-aab6-87055579a796 | textbox | Length:
eec7f79c-8232-52f8-8f6c-04b757c1df61 | textbox | Location:
aaad3aba-278d-5906-95d9-1841ed7872cb | textbox | Other:
cebaf9fe-f4ee-467d-8b88-b4dfd669d18d | section | Environmental
33769c16-bb2f-457b-84c0-5bc191ee1e5d | checkpoint | All waste removed from site?
93ca4c7c-1543-445f-9ae2-7d074043525b | section | Final Sign Off
d4c19d4d-6dce-43a4-953e-ad430835a313 | checkpoint | Completed to specification?
22e58c0b-04ed-46f4-a5e9-648a22ddacce | checkpoint | Joints free from defects?
e5008d02-666a-4369-bd7c-71688c45743f | checkpoint | Sansom Supervisor Sign Off
66823f0d-241a-5767-89d5-603a973cd4b1 | textbox | Full Name:
a28ece45-d8c0-4a90-a935-a7650c9407d7 | signoff | Request Sign Off
140069f8-32a4-4ece-841f-6f60300ec737 | checkpoint | Client Sign Off (if required)
8da83e28-ee51-50e8-9610-3d8880e6d7a9 | textbox | Full Name:
83ee50aa-95f8-4057-aedd-f4be2e17b70d | signoff | Request Sign Off
b2c81599-4186-4530-9666-56d69303e9ea | checklist | QA - Pile Cap Detailing Checklist |  | Pile -
4db48b45-98fb-43e0-93e6-4b762e3fac3f | section | Steps
d01eeaf1-da0e-4e00-9994-18157a6bc4af | checkpoint | Pile Cap Handover
30d8f76b-68fd-4a04-ab42-4ec2ec4bd440 | checkpoint | Diameter
7b461b78-02ef-5ac8-90f7-6043a5b41858 | textbox | Diameter |  |  | Specified diameter of pile
5aa3a2af-5434-5d0c-b56c-af96eb6b662e | textbox | Diameter |  |  | Actual diameter of pile
b49352b5-0a07-4538-b502-49c0fbe7317d | checkpoint | Surface Preparation (type) (Grind Flush only)
7ec59b3a-fc40-4d41-96bd-7758c35d322f | checkpoint | No Breakdown included
8f1beca2-5ebf-57ee-9123-f88c0bc45d18 | note | (If required, request Site Instruction)
b50889eb-a29d-4871-ba60-f423b45004c2 | checkpoint | CEM 100 Grout
e6819921-d472-476e-b86c-3b3e4a121108 | checkpoint | EP 75 Epoxy
3eda810d-b0a9-43fb-8570-535d938390ce | checkpoint | LM 3000 Bedding
607215ec-3384-4b20-89b8-086540cddfdd | checkpoint | Bituthene 3000 - (Side of Pile)
38d0e4e6-9409-4f11-b575-cdb18dc0937c | checkpoint | Termination Bar
ded37f68-a3cc-4ed0-a20b-5ebf1afed40e | checkpoint | LM 3000 Termination
b7ffe0ee-033e-4041-b739-56d788a9c4fb | checkpoint | Protection Placed
87f3b0e3-7ad4-4a51-8391-259ef9af3b89 | checkpoint | Backfilled with Site Concrete (By Others)
e0f4108c-c78f-44b0-ad61-1ffc9b9f7b25 | checkpoint | Bituthene 3000 cut, patched (Detailing)
57b456db-33d4-4f94-876c-957726f87e8e | checkpoint | Bituthene 3000 & Preprufe Tape (Top of Pile)
a2c423d3-c355-454d-83fa-7304a194ad69 | checkpoint | LM 3000 to reinforcing bars
b2abcb2f-c773-4e18-a310-647f52e42901 | checkpoint | Swellseal - Mastic (10mm Bead) To Bars
6e0819b9-b364-47d2-ac90-a06eadebe66a | checkpoint | Adcor 500T (75mm min cover) with Swellseal Mastic
14969e35-0b22-4836-9433-822f7b469341 | checkpoint | S Felt Protection
21d88a54-2a65-4875-80a9-6a8c70095aa9 | checkpoint | Preprufe 300 lapped
94c12dc9-85c6-4eb5-97c1-e16dd708ed1c | checkpoint | Sealed with LM 3000
849bdb13-be7a-447f-bde3-a95892756d71 | checkpoint | Concrete poured on (By Others)
21901150-8114-4d3e-8f80-59a79f446847 | checkpoint | Pile Cap No:
45b71c00-631b-4615-aeb7-9e1ce876c674 | checkpoint | Reviewed by:
084b9322-4bde-41c6-ad91-30354d5d50aa | checklist | QA - Pile Detailing Checklist |  | Pile Detail Checklist
47f8bfb3-a264-4e07-a960-2724675845cb | section | Checks
e260faba-f14a-44ed-ba59-732cb2a639ac | checkpoint | Pile number and handover / Specified size and actual size
4734d441-5110-472d-b69e-8ff6120b6c18 | checkpoint | Pile preparation Grind / water blast
c0f27205-7674-42b5-a7ac-8539c148957c | checkpoint | Two layers of sikadur-32 along the top of the pile for a total of 2mm thickness minimum
80038fd2-a449-4122-bbf5-d0970c61996c | checkpoint | Install Sarna Tape 200 to the face of the pile extending down 100mm leave the release paper on the top half
d0592dd9-ee82-41fc-a459-f26e8dcdb83a | checkpoint | Secure the bottom edge of the saran tape with termination bar sealed with Sikadur-31
5a540e15-00d9-42c1-a2a1-f2cd9f60ae8a | checkpoint | Sikaswell A waterstop placed between the sikaproof A and the steel reinforcing
c019279f-e88f-43f9-84d2-96cfb4fd6c44 | checkpoint | Sikaswell A wrapped around all perimeter reinforcing bars
45151397-8c64-401c-bc2f-422e61509608 | checklist | QA - Plunge Columns Infill Slab Checklist |  | Plunge columns infill slab -
b2b2dea7-b323-412c-ae17-8289daad9c61 | checkpoint | Gridlines location
d7d6dfdd-3cdb-4aa4-a9b5-d246d0d4883c | checkpoint | Site concrete poured and handover
a43f2a8e-fece-464e-8820-2c4f117fd68f | checkpoint | Geotextile placed
20664bab-7281-452c-aea1-837148372438 | checkpoint | Sikaproof A placed
74b7fdd7-4859-43a5-9ce6-8d2757b7b265 | checkpoint | Place two lines of sika Fix tape 50 and sika swell S2 as per(10.3.21) in the specification
233a8a87-aa58-441e-806f-7ec18321dae3 | checkpoint | Place termination bar and sarnatape 200
71202aee-0d7d-4ec1-8c07-206b27b5c930 | checkpoint | Fix the injection hose in place
58c68d9f-7513-4ea6-90dd-22af594be67a | checkpoint | Infill slab poured
78f50b57-24a0-493d-ba5d-148ec411f6d8 | checkpoint | Sika icosit and Ethafoam installed
18caa610-399d-4f86-9ced-97f7eaa976e3 | checkpoint | Final inspection and handover
2e355d13-f3ac-46d5-8014-c75f877e5a07 | checklist | QA - Preprufe 160 Wall Installation Checklist |  | Preprufe 160 Wall Installation
335a619a-caf6-45f1-b93d-6859f2fd4291 | checkpoint | Underfloor Area
2fbb6a7b-e0c6-5b82-8c98-5c05339d4815 | textbox | Underfloor Area |  |  | Wall Section Grid Line
2e1f5b8e-d550-54e5-b20d-5d4a9c361466 | textbox | Underfloor Area |  |  | To Grid Line
0620810f-88dc-46d1-849f-4e9cc4c0b260 | checkpoint | Wall hand over as per manufacturer's requirements (Flat, Smooth and Plumb)
9d537ba6-a119-4f2e-a2f7-612dc723a5c1 | checkpoint | All Materials Batch
1d9a5373-59fc-5b18-9964-7ba411079454 | textbox | Batch Numbers:
1e5a6914-fb4c-5f5b-8316-d9ff4c8c7151 | textbox | Batch Numbers:
be4dbf5a-44ea-5ace-be84-2c0d218d5862 | textbox | Batch Numbers:
6a11002a-3c21-5e2a-b3b1-beedda027127 | textbox | Batch Numbers:
d9946498-fc97-4960-bab3-69d45e2c7188 | checkpoint | Protection Core Flute
7add3cfc-9de8-593f-8c71-d2e97e1c27ac | textbox | Installed:
34fb0fa6-5cc0-4b70-a3ff-c4e557cc3b5e | checkpoint | Recorded Temperatures
aaaf8ea0-556c-5ba2-8533-0781a7c29653 | textbox | Substrate
21376922-7906-551e-96a6-6f8837e964a6 | textbox | Ambient
baef241e-553e-4bcf-bee8-67cfcf2dac94 | checkpoint | Preprufe Installation and all laps and lap tapes done as per manufacturer's requirements
8aed99f2-9934-4868-85f6-fbe01fc188e3 | checkpoint | All water stops installed
0b08f6e8-9ba0-4d1b-bb13-cd08b7ac87c2 | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements Take Photos and release To other trades
a684e39d-4dfc-4e8a-8c52-28253b26c4e8 | checkpoint | Perform Work and Pour Final inspection once other trades are finished. Do any required repairs Take photos
2e07a8dd-3f1e-480b-8d02-b4e2401ade0f | checklist | QA - Preprufe 300 R Plus Underfloor Checklist |  | Preprufe 300 R Plus Underfloor-Commercial Bay
8a342a8d-7dd9-4930-8f99-99c8fa0b5240 | checkpoint | Underfloor Area
79110ae4-6052-535f-9eb1-c0547d9ce2a6 | textbox | Underfloor Area |  |  | Gridlines
a07b841d-7527-52e8-8faf-d14d90c701a7 | textbox | Underfloor Area |  |  | To Gridlines
5caa1eb0-677c-4028-8dcf-8fefedfd539e | checkpoint | Site Concrete Handover
87a42c21-13ae-497c-8f02-67f7cd1d037e | checkpoint | Surface Preparation
9760c6b5-325b-4477-bd37-e58757f52daa | checkpoint | Lay the sheets out and lap to the specification, provide a 300mm lapping tail at any point of future membrane tie in points
910e3097-ba59-4f13-af52-c80538c128ca | checkpoint | Roll all laps with approved roller
4c1275f5-01c7-499f-8eec-50af190deb43 | checkpoint | Field Cut Laps- All Field cut laps to be done as per the specification (Detail 10.3.31)
5b904d56-d424-4490-90b6-f3dc7179326d | checkpoint | All piles to be detailed as per the specification (Detail 10.3.20)
871ccf6b-7d97-400e-ad3b-310757579ffa | checkpoint | Construction Joints- All construction joints to be nominated and have Preprufe CJ Tape placed at these locations
e11353db-ee93-44a6-bd3b-0b1d74f9abd1 | checkpoint | Final inspection before handover, any damage repaired as per the manufacturer’s specification (Detail 10.3.37
29a50b0d-71d4-48db-83de-d80a908c2033 | checkpoint | Reviewed By
ba235420-a56b-454e-af0a-215ada1107fb | checklist | QA - Preprufe 300R Beams and Underfloor Checklist |  | Preprufe 300R beams and underfloor
88fe1f26-3759-441b-a1a8-95b9edbb4897 | checkpoint | Area Specified Below
2b2a2483-8866-426c-8f8f-7ebb53c670fe | checkpoint | Geotextile to substrate
3deb7a31-d595-47e3-bd70-a925d846d87a | checkpoint | Preprufe placed all laps taped Preprufe bedded into LM 300 on top of piles
b3a67443-5c9f-4dcd-8cee-19d16fb84679 | checkpoint | Adcor 500 T placed around top of pile
800214cf-f4a5-4011-9e8e-bdd288ddec7f | checkpoint | Swell seal WA placed around all pile bars
d316b9d0-5fd9-48ee-86f7-00ae522fdb6a | checklist | QA - Preprufe 300R Walls Checklist |  | Preprufe 300R walls
98d39c9c-37a5-4e04-be8e-2116011c6c9c | checkpoint | Area Specified Below
6f0980b2-c89b-4fe3-86da-549e4be0b685 | checkpoint | Geotextile to walls
0c3782f9-8830-467a-adaf-d5e99782ce00 | checkpoint | Preprufe to walls
3946e244-852a-4761-9b21-50842af6d8b8 | checkpoint | All laps taped
31fcea8d-145e-4462-b3f8-282a5ddd17c0 | checklist | QA - Preprufe Installation Checklist |  | Preprufe Installation
37acc2b2-fcec-4b3e-aa38-e48e86c0f314 | checkpoint | Substrate to manufacturer's specifications (are there any voids that need filling, clean, etc.)
e519d3d4-0a45-4885-93e8-58bb3d51ee9b | checkpoint | Preprufe installation and all laps and lap tapes done as per manufacturers requirements
4a9586c8-100e-4e9e-ba2b-35191204f19a | checkpoint | Provide photos of completed works area
34c89ad6-caf9-4320-aef4-17956c6962b9 | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
43e5788b-7616-46ba-8617-3beb34cef32d | checkpoint | Install Anchor Waterbar where required
934c9407-ec63-41b7-91c1-0b3e205a028d | checkpoint | Preform work and pour final inspection once other trades are finished. Do any required repairs. Take photos.
f3a44ba4-020f-47c4-ab69-8ac39ead8078 | checkpoint | Photo of highlighted drawing showing locations of work
ce501018-7a86-4b35-8e51-c1e1fab89214 | checklist | QA - Preprufe Tanking Underfloor Checklist |  | Preprufe Tanking Underfloor -
42fb288c-2c8b-4e27-88a2-9ebda5fc286d | section | Pre Start
963b26f6-5433-455b-8550-4ff74e469d3a | checkpoint | Work area clear, tidy and accessible
570e1148-bde6-4d3d-856f-460d7af052f0 | checkpoint | Previous substrate/opening acceptable
43142905-8d2a-4160-97a0-c0d7d76efed9 | section | Install QA
ca473746-51d0-4a23-8bfc-012b7130bb13 | checkpoint | Area (grid lines)
9167ce90-44c8-4c72-b66f-422590c1e136 | checkpoint | Pile tops sealed with epoxy
3a614a17-f14b-464f-b564-925e91258776 | checkpoint | Preprufe placed and laps taped with Preprufe bedded into LM 3000 on top of piles
946e6605-2950-4130-8bcd-cdf0b35a953c | checkpoint | Adcor 500 T placed around top of pile
b05a4d6b-cdf8-4737-b194-836fa2aeb2ec | checkpoint | Swell seal WA placed around all pile bars
cce585c6-d07c-4879-8ccd-28d6f081282d | checkpoint | CJ tape placed at construction joint locations
a504488d-a485-4f13-88bc-2223b43579de | checkpoint | Preprufe lapped and taped to the DPM
852d4f5e-e199-4481-8ea1-3585d17ed278 | section | Handover
8df12188-f17e-433f-b1a0-7dd811f3f6d1 | checkpoint | Area and item left clean and tidy
bc25c7c1-c107-445b-b8e7-d1868ac692fd | checkpoint | Final Sign Off
9453b48a-9536-4d4f-b8ad-6765535ce227 | checklist | QA - Preprufe Tanking Walls (Vertical) Checklist |  | Preprufe Tanking Walls (Vertical) -
2d813df3-3b71-45da-8d3c-5b952a3e5415 | section | Pre Start
ffba914e-1b83-4f66-9fcb-5f29e4ae9e53 | checkpoint | Work area clear, tidy and accessible
3d39e041-d74a-4080-813b-3959016856f4 | checkpoint | Previous substrate/opening acceptable
c1a3fd3b-ba56-4957-9e03-88dbe789fbc4 | section | Install QA
5e5e5dc8-4c85-4893-b897-d78ba2910a4b | checkpoint | Area (grid lines)
de758458-b479-403a-a1c1-f9b8abb53f27 | checkpoint | Join wall (vertical) sheets to the underfloor tanking
3ac42438-00c9-4835-8779-df48e142ba2b | checkpoint | Tape all laps
dea0527c-b375-4e1e-ada2-20c83a6be095 | checkpoint | Dress Preprufe into ground beam locations
8a563f7b-02f5-4a0e-825d-bbcb6f5c4cb8 | checkpoint | Place adcor 500 T in all construction joints
e54e3b51-9d16-42a8-9181-25aa8da76f03 | section | Handover
422618e8-f822-4ef1-aa90-b1e1699e03c2 | checkpoint | Area and item left clean and tidy
93c68293-b90b-45a6-ba27-3888c43981d5 | checkpoint | Final Sign Off
6cee02be-2aba-4830-b359-4d1ad6aff74f | checklist | QA - Sikaproof P Wall Application Checklist |  | Sikaproof P wall application
9c11bd18-6c63-43ca-8129-604e685ef630 | checkpoint | Details completed
353c0705-4119-56c6-866e-a62e8ea227aa | textbox | Pour :
f86b7efc-7d70-5fa3-bdef-29070089215c | textbox | Tunnel :
4c4521d2-c904-586c-876c-6ab0357e384d | textbox | Wall :
0766e3a7-2a04-4537-97b9-eb124bda367e | checkpoint | Check Substrate are all voids filled
35f5404a-40d5-469b-8305-ba70f20c97ee | checkpoint | Prime the substrate
db006018-268d-4b18-bf2a-a6b039cb87bf | checkpoint | Apply the sikaproof P
6d5cfe2c-4b2c-411d-99fe-a6a55be2ff37 | checkpoint | Tape laps with sikaproof EX tape 150
f9010268-b513-4471-9a4c-0e8a0f85bb36 | checkpoint | Place termination bar as per the specification where required
26ec0aad-080a-4237-ac31-063f32ff2564 | checkpoint | Protection layer placed
288cae2b-f177-4e53-88dc-2c7e507cc2bc | checkpoint | Final inspection and sign off
235da4fa-86ef-4926-b2a2-0439869b2fdc | checklist | QA - Swelltite Checklist |  | Swellite Checklist
99b7d6e3-f254-4795-a181-8e9f14709b45 | checkpoint | Check the substrate (are there any voids that need filling, if precast panels are all the joints filled).
2e2bd86e-e5dc-460c-bdf6-5c63a2e2d4c3 | checkpoint | Check and clean the voltex flap for the swelltite
52f55515-1100-43fc-99ee-7e16c4ab01fa | checkpoint | Apply glue to the wall ready for the swelltite
e01c0f59-03a7-4dd8-9276-2233a42a67da | checkpoint | Place water stoppage granules along the wall floor junction
02e316ae-5571-4300-88f6-9c02d9e0b52d | checkpoint | Measure and cut the drops of swelltite
2a88176f-af47-4c6d-873e-15e4dc288502 | checkpoint | Hang the drops of swelltite straight
958af548-4a04-4137-a35f-3be0d495d2a0 | checkpoint | Complete penetrations
df607d90-54fd-45e0-a87d-b0ea44b2d508 | checkpoint | Tape the laps
a1bdfaf4-2bb2-47a6-87a3-0b76c774506f | checkpoint | Place the termination bar
4c959f99-b5b3-422f-b6cf-3bd9657f01d8 | checkpoint | Apply cetcoat
9a5dba6f-99df-4f80-ac44-f1a4c5c7e816 | checkpoint | Hang protection layer
d3e85697-53de-4afc-a5e6-29d2f141c6fc | checkpoint | Complete QA forms
2df26e1b-ca37-4f91-af0b-c2f62ad12337 | checklist | QA - Tanking - Beam and Capping Beam Remedial Checklist |  | Tanking - Beam and Capping Beam Remedial
bc1c3746-7f41-4270-84c2-7c039bfe4102 | section | Pre-installation QA
3f68e0ee-d4a4-4335-91f4-8cb64c929d95 | checkpoint | Latest consented drawings available, checked and referenced
e176908a-94f3-560c-8ec8-cd44395e48f9 | textbox | Relevant drawings & revisions for reference:
34f95565-d95a-4507-9753-14ef11633d67 | signoff | Raise Remedial / Request Review
7fe02acf-0e31-41b8-993f-4fb96066ee39 | checkpoint | Work area/substrate acceptable & approval given to start work
9f59afa6-2c86-40dc-aeef-3fe82d017943 | signoff | Raise Remedial / Request Signoff
99ba6c34-e75f-4e63-b292-b28eee7923d9 | section | Installation QA
1babb576-5d9a-4b93-aeb4-145ba2445f5b | checkpoint | Product being used input
c263ac2a-0c03-5ff2-a93d-6030a72dbbf2 | dropdown | Product name | Other, Preprufe 300, Voltex, Voltex DS, Voltex WSR,Preprufe 160
05f49c82-daf5-41c4-aa10-0e5f22438b06 | checkpoint | Location where being applied input.
0b737eb1-1db9-5579-90fb-57f87485f042 | textbox | Area or pile or beam number:
35a0366a-2c29-4c86-b0ca-2c247858ac8f | checkpoint | Protection core flute installed
56aad446-c508-44c1-89d8-352aab737098 | checkpoint | LM to beam/capping beam/pile
3d30c473-a797-46ca-bb22-750254b6313a | checkpoint | Preprufe embedded to LM
e9419456-bc44-4c64-ada0-a172f340e362 | checkpoint | Preprufe installation and all laps and lap tapes done as per manufacturer's requirements
5a4621ad-1206-4e44-9cb4-eb96696f235a | checkpoint | All water stops installed
b45ad762-c68f-401e-bfa3-aeac418182b6 | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
8dafdba3-f083-4f0d-beda-f52ebcaf0634 | checkpoint | Perform work and pour final inspection once other trades are finished. Do any required repairs. Take photos.
2aafd651-c540-4d1d-a669-5a9088193ff7 | section | Completion / Handover
05fa21b7-cfed-443b-a33e-0285cb42b23d | checkpoint | Product installed correctly, checked & reviewed - as per specification
a0c624cb-152f-4644-97b7-d6d270fbcdaa | signoff | Raise Remedial / Request Review
fd76d0fb-d695-456a-b7b9-c4d3b81643f2 | checkpoint | Area left clean & tidy
dd07d81d-bd44-425b-a0de-d615d5e805ca | signoff | Raise Remedial / Request Review
4d7054e1-8309-41dc-8786-fa30ce7dbabd | checklist | QA - Tanking - Pile Remedial Checklist |  | Tanking - Pile Remedial Checklist
b0a3061e-50bb-4cf5-883e-ad3b18bbce37 | section | Pre-installation QA
2b2a7140-02c1-41db-93a4-74d073ddeeb3 | checkpoint | Latest consented drawings available, checked and referenced
c8bc673a-5173-5df7-aa06-d1de5e2cd309 | textbox | Relevant drawings & revisions for reference:
7df5327e-be85-4073-94f8-9f9c9b84015c | signoff | Raise Remedial / Request Review
ffb8a698-92b7-4eb9-a870-7a5dcd8d4410 | checkpoint | Work area/substrate acceptable & approval given to start work
502b7bfc-aba7-4919-813a-297bae37109d | signoff | Raise Remedial / Request Signoff
143dd6f7-df70-44b9-858c-4061a47c066f | section | Installation QA
90b6e79c-641b-4d5b-a973-ac2c8e343baa | checkpoint | Product being used input
bb91fe73-e3f7-5c78-834b-aa1be38b00d0 | dropdown | Product name | Other, Preprufe 300, Voltex, Voltex DS, Voltex WSR,Preprufe 160
585d3725-5f6b-4e19-9d2f-9ba23a064e79 | checkpoint | Location where being applied input.
7a4aff0f-d5ef-5a03-b38b-0adc3ae19708 | textbox | Area or pile number:
50533053-be77-4ac5-8136-b2a099b0c5ae | checkpoint | Protection core flute installed
8448b08b-73fd-437b-a143-af63b1bee9bb | checkpoint | LM to pile
c4af7835-0b3b-4757-b4c8-60a2d3776516 | checkpoint | Preprufe embedded to LM
d399cbb8-793d-4d36-892e-614d7a5de950 | checkpoint | Preprufe installation and all laps and lap tapes done as per manufacturer's requirements
8829979d-d0e8-4e9e-b167-7cadfaef387b | checkpoint | All water stops installed
4123bbc6-531e-4a65-bbcb-22329812c1b9 | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
5bb229a4-7396-4418-afce-c503d4ae6034 | checkpoint | Perform work and pour final inspection once other trades are finished. Do any required repairs. Take photos.
e683fd7c-0eeb-4984-be8c-1814848de5d1 | section | Completion / Handover
78f0523e-c6d4-45e3-a961-ba45373d9b9a | checkpoint | Product installed correctly, checked & reviewed - as per specification
303348b4-45bd-458c-beda-8ad95397123c | signoff | Raise Remedial / Request Review
5688ff98-8fd4-4e79-a3d4-1e5c4b073928 | checkpoint | Area left clean & tidy
bb42569d-605e-4d32-8ea0-a80deb397257 | signoff | Raise Remedial / Request Review
2e8035c0-3639-4583-ba3d-5ac5ca32d78e | checklist | QA - Tanking - Underfloor Checklist |  | Tanking - Underfloor Checklist
4f7fee47-030a-44d1-b706-831449433d58 | section | Pre-installation QA
5a2c425b-5233-408e-a01b-8fe1510207b4 | checkpoint | Latest consented drawings available, checked and referenced
32c85864-a078-5f28-a8d1-a93fd6a7bde2 | textbox | Relevant drawings & revisions for reference:
b9405014-00bc-4694-bb20-47ce39668bba | signoff | Raise Remedial / Request Review
955e2bdf-edfb-46b5-9a9a-c05c51197030 | checkpoint | Work area/substrate acceptable & approval given to start work
822f33b2-4d60-420b-95b5-8058227a6a50 | signoff | Raise Remedial / Request Signoff
51779cb8-c1c9-40b3-ac66-61f21fa7c1ba | section | Installation QA
72086ab3-a457-4eaa-b4f6-554861540aa2 | checkpoint | Product being used input
2a71f153-affd-5323-bc67-865ebeb2bf7a | dropdown | Product name | Other, Preprufe 300, Voltex, Voltex DS, Voltex WSR,Preprufe 160
b6fc2261-bb0a-4a0b-8d8c-38a2a71a6550 | checkpoint | Location where being applied input.
14a774ba-5e77-52b9-8b2b-0617201dc03d | textbox | Area:
57d207ea-1c73-4ac9-97b7-00fef1bbe403 | checkpoint | Geotextile in place if required
727cd36b-75cb-49ce-bc5e-ea1221b2c6b3 | checkpoint | All laps to manufacturer's specifications.
8911459f-e8e0-480a-8ca5-563cc585a0e0 | checkpoint | (Voltex DS only) DPC must be removed 100mm minimum for lapping
2f031cd4-03ac-4687-acbe-bcc7236cd777 | checkpoint | Penetrations are detailed as to manufacturer's specification
862cd297-c1d1-4b7a-bae9-5a843d382e5e | checkpoint | All water stops installed
8833c7bf-0263-4d85-b50b-01b3c0c25e55 | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
96b2ebec-f5bb-441f-ae34-f94b0fa42ff5 | checkpoint | Perform work and pour final inspection once other trades are finished. Do any required repairs. Take photos.
f3abca5e-d147-4753-b706-1d73cccc281f | section | Completion / Handover
1f1c4818-a72f-4cd2-9be3-425ef3aaf17d | checkpoint | Product installed correctly, checked & reviewed - as per specification
54265baf-46a2-449d-8710-e921ee157141 | signoff | Raise Remedial / Request Review
fb4e3f6d-f96b-41d9-b3a8-67a7425e8ac2 | checkpoint | Area left clean & tidy
364aff96-7147-45af-854b-e6982468d3fe | signoff | Raise Remedial / Request Review
16e127ed-f5e7-44bd-945f-153b5baab83f | checklist | QA - Tanking - Wall Post-Construction Checklist |  | Tanking - Wall Post-Construction
f017cbb5-2739-472e-8f3e-84dfc515e003 | section | Pre-installation QA
932c4c9c-1b7d-4c43-9be1-c67c1f972334 | checkpoint | Latest consented drawings available, checked and referenced
020fbf6b-b045-55a7-81c1-a0888df353fb | textbox | Relevant drawings & revisions for reference:
9b402c25-3587-442b-99d4-dad669220eb2 | signoff | Raise Remedial / Request Review
0ea03389-7729-4393-aa89-edb140f6e30e | checkpoint | Work area/substrate acceptable & approval given to start work
8e97c662-b3a8-46a8-9dfa-89bcec74ce7f | signoff | Raise Remedial / Request Signoff
eb3fbd9b-645e-4081-998e-7eac3d056edd | section | Installation QA
8c46bc33-860d-47db-89c7-73c294dc41c4 | checkpoint | Product being used input
b41568d7-c46f-5d8b-969e-e0ba84c31f53 | dropdown | Product name | Bituthene 3000, Other,Swelltite
7f09ec06-bacb-41c2-878c-55c3f9d94082 | checkpoint | Location where being applied input.
d0a91b29-c8c6-548d-b8c1-33c9c1a6401c | textbox | Area:
af094389-5160-4e8e-a41b-aa6c1761cfa6 | checkpoint | Check the substrate (are there any voids that need filling, if precast panels are all the joints filled).
9ffc7e6d-92f8-4939-9131-ed9fad4945f6 | checkpoint | Check and clean flap.
c1c30e0a-11f9-4bd2-a595-542171a42136 | checkpoint | Material installed as per manufacturer's specification.
4741319e-0cbd-41ba-9c92-eda68e33cf6a | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
b87f3684-6a74-414b-9891-574c680f34bd | checkpoint | Complete penetrations
1372f30b-6d16-42ca-8aca-7e512921be7b | checkpoint | Tape the laps
16c00c60-e6ef-44d6-92ce-8b4685619e1c | checkpoint | Place the termination bar
56a9b2d0-8ea1-4bac-bf7e-1e7a7d32e9ef | checkpoint | Cetcoat applied
b56b6901-90c6-4ced-beab-3e48cc18581a | checkpoint | Protection layer installed
9e73a654-20ef-4c63-b9a0-965f7c60aa62 | checkpoint | Drainage installed and 100mm away from wall
2828d70d-b6db-4bc3-9a96-441fe6fcbb5b | section | Completion / Handover
2889d000-fd68-4108-9f08-6d65904bbc0e | checkpoint | Product installed correctly, checked & reviewed - as per specification
82e52c43-6c1e-49de-a9da-a7e5ba4688ed | signoff | Raise Remedial / Request Review
40e94ef4-91c7-44ee-b9a8-7d4741d7a588 | checkpoint | Area left clean & tidy
d4117923-e529-4592-a045-7e76edafa291 | signoff | Raise Remedial / Request Review
24170416-a2cf-46c4-b075-53624f45320e | checklist | QA - Tanking - Wall Pre-Construction Checklist |  | Tanking - Wall Pre-Construction Checklist
b3f6f557-3356-4e3c-8288-56e6947a4716 | section | Pre-installation QA
4c62a7e2-7d4b-4baa-9b54-c6d1e99f9e26 | checkpoint | Latest consented drawings available, checked and referenced
c33576a2-8b59-5815-9c9d-793c7a915b8e | textbox | Relevant drawings & revisions for reference:
dd0146b3-6f7e-4ffe-b9e9-15ccad653ea0 | signoff | Raise Remedial / Request Review
518100e2-eabb-49f9-b3b8-65a383713aaf | checkpoint | Work area/substrate acceptable & approval given to start work
20ad7f81-c216-4eab-a2eb-88cff8ede442 | signoff | Raise Remedial / Request Signoff
ba46541e-c624-4f36-aa6b-10cc02e41f6c | section | Installation QA
b613cda1-3384-406a-a2dd-58e727f2e4d6 | checkpoint | Product being used input
b7cb5c0c-7fc1-5b51-b66b-86f5bb926962 | dropdown | Product name | Other, Preprufe,Voltex
4f3baeb3-3ed0-4264-abb0-3d57b9beda68 | checkpoint | Location where being applied input.
dfefb683-c3b7-569c-b970-d5027e44207c | textbox | Area:
93b531ad-1b37-4cc1-a3a2-7665fef801fa | checkpoint | Geotextile or coreflute or drainage gecell in place if required
dd943a7a-5538-4d66-8e2a-5afe2f293581 | checkpoint | All laps to manufacturer's specifications.
937009af-cfae-4a09-a06b-1e648076ea4d | checkpoint | (Voltex DS only) DPC must be removed 100mm minimum for lapping
210bc1e4-dfb4-4444-b489-9aa2b4704387 | checkpoint | All water stops installed
5125e0c6-0ac1-4cfc-821e-fcd6c2a9177b | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
4861f754-2c9d-4281-a6a3-19dcff58c44e | checkpoint | Perform work and pour final inspection once other trades are finished. Do any required repairs. Take photos.
b42edae8-850b-43f5-ab5d-31b3303328f2 | section | Completion / Handover
3e729858-c180-4d73-a447-872391a55881 | checkpoint | Product installed correctly, checked & reviewed - as per specification
45c43c54-0d36-40ba-9313-3d8fbc04fae5 | signoff | Raise Remedial / Request Review
5dda602a-76e0-45ef-bd8a-7db0268221a9 | checkpoint | Area left clean & tidy
0a5539ae-ddc3-42ea-8262-9bdbaf1b915d | signoff | Raise Remedial / Request Review
4f5dbe8b-f245-422f-a118-a2439bd3a56e | checklist | QA - Tanking Insitu Walls |  | Tanking Insitu Walls - Area:
6a33c569-c42b-4510-b414-687d1c2e6d22 | checkpoint | Substrate to manufacturer's specifications (are there any voids that need filling, clean, etc.)
db1451a2-cca0-4cae-baf2-d5918e66b49a | checkpoint | Check and clean flap.
66ca7dad-ab3a-443c-b8fb-8e3aeb0322df | checkpoint | Material installed as per manufacturer's specification.
14da9a43-7ba1-4580-9087-f4e2f7561dc4 | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
8d74d06c-ab8f-4213-bd97-38d8b41ef25b | checkpoint | Complete penetrations
bf581c1b-f6b5-4a05-9b4e-cf09fcadf020 | checkpoint | Tape the laps
b1caaa3b-21e8-4fbc-99b8-8fa19ce5189a | checkpoint | Place the termination bar
04686fc5-e71d-40f9-9b96-18c584324f80 | checkpoint | Cetcoat applied
0f046a7e-88d8-4f0f-883d-692efb60fe38 | checkpoint | Protection layer installed
e452e725-7572-45ad-bf21-bf1097c3156c | checkpoint | Drainage installed and 100mm away from wall
8738cd04-9661-4c8b-8a98-869f6f4afb28 | checkpoint | Photo of highlighted drawing showing locations of work
a50eb699-7490-4656-b25d-7457300df0ad | checklist | QA - Tanking Underfloor (V2) |  | Tanking Underfloor - Area:
258d0911-5c53-4f47-8ac3-9a2fd8696090 | checkpoint | Substrate to manufacturer's specifications (are there any voids that need filling, clean, etc.)
69085ed4-6796-4689-a2dc-58dbe92aa687 | checkpoint | Membrane installed to manufacturer's specifications
3e0130e5-39f4-4383-bb38-9453e9d7012a | checkpoint | Reo installed (by others) checked for damage to membrane and repaired (if necessary)
e5dc7605-b95d-44bd-8998-f0961bc34278 | checkpoint | Photos of completed work
b9037fd2-763a-4ad3-9871-2c5b74a4da87 | checkpoint | Final inspection before concrete
03053433-8c56-4f2e-8fca-358615da6fe8 | checkpoint | Waterbar installed to all cold joints
8d43df60-1806-43ad-ac68-e9ccdbbc8f76 | checkpoint | Photo of highlighted drawing showing locations of work
9461573b-647b-4f8b-8ac2-6b23b65ac440 | checklist | QA - Tanking Voltex |  | Voltex - Area:
64bd6d35-882a-4747-aefb-8fce065faeee | checkpoint | Substrate to manufacturer's specifications (are there any voids that need filling, clean, etc.)
9b2ad16f-4db6-40b0-bfe1-6fcb5e2e0925 | checkpoint | Form work acceptable
70ac0545-c20e-4ab6-b8ad-e12586f886c4 | checkpoint | Voltex installed to wall as per specification
859be09c-6532-439c-b549-df69f6c4fd7c | checkpoint | Penetration(s) detailed and photo(s) taken of each
64cfd265-c97c-4e9c-8a04-76314b3d1cea | checkpoint | Photo of highlighted drawing showing locations of work
0bc8b793-8cab-40a0-bb4c-120679628f4a | checklist | QA - Torch On Membrane |  | Torch On Membrane
c6d14088-b8e8-48b6-a77c-5a1cff9ac4f8 | section | Details
a104a6dc-b248-42e8-ab3c-6fdb9b407c5b | checkpoint | Substrate, inspect/clean
443ef495-df31-41e7-beff-5cf8f2dfe649 | checkpoint | Membrane primer
a52f7036-6036-4f1c-89ae-7daa779f90dc | checkpoint | IlD mesh/plates
3e27f11f-20cb-43da-a6a4-1bc38441fd86 | checkpoint | Base sheet fully torched/Self adhesive
a4220fff-56b5-4cec-b620-05dfc23bec25 | checkpoint | Cap sheet
e95b6012-4283-4f49-9f8c-ac7f61c7b3e6 | checkpoint | Penetration detailing
0648b885-f654-4aee-8894-46f67162177f | checkpoint | Termination bar/sealant if required
c3a81ebe-0a77-4645-a3b1-0524b8ec9c98 | checkpoint | Completion photos
cd9c345c-3cf8-4e5c-b4ed-9939958760d0 | checkpoint | ILD test completed
dc8bf004-cade-4163-9bc0-30ec322d1ff6 | checklist | QA - Tunnel Roof Sections Checklist |  | Tunnel Roof Section -
a357ed94-000b-4194-9ab5-0404c543bc68 | checkpoint | Substrate is ready to receive the sika S felt, all voids filled
0a263d1f-eaee-474b-b6fd-eedf71b8553c | checkpoint | Place the Sika S felt Geo mat
5a7ce2e9-a578-4289-ad90-99fd156fa2fa | checkpoint | Sika plan WP1100-20 HL placed and laps welded
503be17a-8f0e-4f40-bfe0-74c4ee7e18dd | checkpoint | Sika plan WP1100-20 HL welded to water bars
2f54612d-4214-4762-84a5-02bf669ed319 | checkpoint | EFVM test completed and any required repairs completed
2adc3582-5fc6-4564-a7ad-8442c3d9a368 | checkpoint | Protection layer placed
ac069eab-f931-44e6-9eac-000ba3624b60 | checklist | QA - Vertical Stitch Checklist |  | Vertical Stitch Checklist
2821fc76-f9fe-4781-9dd0-180612017992 | checkpoint | Work area/substrate is clean, dry and ready to start
fd8f016f-1dd1-4fdc-83d9-cc5fbe304efc | signoff | Raise Remedial / Request Signoff
76ba48ff-9011-4cef-bb64-a3ea6ac284b2 | checkpoint | Photograph(s) taken of substrate
d5840523-5c85-4702-9129-0f1158b0231f | checkpoint | Joint width measured
b7558d89-7a31-409e-815a-632eb3fdf3f7 | checkpoint | Photograph(s) taken of installed backing (before protection board is installed)
24a6f687-c459-458e-8d26-64dc2fcfc891 | checkpoint | Protection board installed
9511c157-4793-4947-8347-ea4ef4db0a30 | checkpoint | Photograph(s) of protection board
d7b6355f-7673-4f98-bdab-5915df150e3e | checkpoint | All joint sealant installed correctly, checked & reviewed - as per specification
708a49cc-6649-4f9e-8118-799ee1070bc3 | signoff | Raise Remedial / Request Review
3d1a54f9-b460-4ec8-b34c-7d124e068541 | checkpoint | Area left clean & tidy
0cc25f8c-8f0f-4bd6-a61a-5226c6bf5303 | checklist | QA - Voltex to Ground Beams |  | Voltex to GB. Date/Area:
6ba67195-3f87-4a78-ba86-5f99af7df671 | checkpoint | Substrate acceptable
10f23f72-9a8a-4a73-9cac-84959d1832c6 | checkpoint | Form work acceptable
e02be2b0-9474-44ab-b6a7-4d571aa896f0 | checkpoint | Voltex installed to wall as per specification
1767750a-9414-4f6d-9a8d-1a7526c75f9e | checkpoint | Penetration(s) detailed and photo(s) taken of each
e89437ab-7e1e-4025-98a2-1b9a45882923 | checkpoint | Area left clean, tidy and rubbish removed
a01722f8-8ec5-4a77-9cb7-90b659fa905e | checkpoint | Photo of highlighted drawing showing locations of work
737a6941-2a95-4edb-b95a-b0f5c43e3f1d | checklist | QA - Voltex to Wall Checklist |  | Voltex to Wall Checklist
a3ecf379-5c40-4896-b613-42690d351dfa | checkpoint | Substrate acceptable
68f95399-faff-44cf-b631-df916cdd82e2 | checkpoint | Is lap from capping beam accessible/acceptable
1a62e5e9-5f35-418f-8c9c-313473286d27 | checkpoint | Voltex installed to wall as per specification
230f88cd-58f5-4fde-b498-c062b4d68ef8 | checkpoint | Rx Waterbar 101t/bentoseal installed to piles/capping beam
4e2095d9-7e03-4067-afc9-dbe5cb540927 | checkpoint | Penetration(s) detailed?
b814ab5a-e6c2-5126-b6d4-1acda5719979 | tickbox | Photo taken of each
d4817a2e-2b8d-4290-96ed-6e9a08be1a22 | checkpoint | Area left clean, tidy and rubbish removed
9705d97b-77cb-4268-8743-19859eb8aa10 | checklist | Tanking - Underfloor Checklist |  | Tanking - Underfloor Checklist
02c5cd8d-f3c9-4632-a9b6-f811985e26ba | section | Pre-installation QA
2913ae52-41ed-4f40-aa59-e85d39a72100 | checkpoint | Latest consented drawings available, checked and referenced
44a90409-d407-5027-af35-70bae8536a72 | textbox | Relevant drawings & revisions for reference:
aca9f6c9-3c67-41e8-b50b-2f9e9ede8196 | signoff | Raise Remedial / Request Review
57a61876-3275-471f-839b-a436045e8228 | checkpoint | Work area/substrate acceptable & approval given to start work
34388176-c469-450f-9906-c44b930096cb | signoff | Raise Remedial / Request Signoff
a9f81e2b-f9bc-4644-b8eb-ca343c290f6c | section | Installation QA
10fa128a-0779-46ef-b1ac-c398ec8daf78 | checkpoint | Product being used input
8cb25423-685a-5d39-9c8e-6170cfd3b06e | dropdown | Product name | Other, Preprufe 300, Voltex, Voltex DS, Voltex WSR,Preprufe 160
d42a2656-dbc5-4e69-8974-c9d408066171 | checkpoint | Location where being applied input.
be70f033-71e8-54c7-bf29-588173eb55c4 | textbox | Area:
751bf866-b716-45c0-be67-1ce504bd89f6 | checkpoint | Geotextile in place if required
491488ff-e29e-4c31-af2c-d75b48c19295 | checkpoint | All laps to manufacturer's specifications.
d2dd62cb-5288-43f7-8fa9-0930a70c9e0a | checkpoint | (Voltex DS only) DPC must be removed 100mm minimum for lapping
daca8256-53d8-4175-bd7b-e1faaceee435 | checkpoint | Penetrations are detailed as to manufacturer's specification
9d20bbeb-f5b5-4fbe-964e-ceeac8d0bf5e | checkpoint | All water stops installed
8bdcecdd-7c42-4284-92b5-4df73cfc38dc | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
0a90a46a-8363-4058-97ae-8d33f099ff74 | checkpoint | Perform work and pour final inspection once other trades are finished. Do any required repairs. Take photos.
bbff268b-1d56-441c-95bc-fe8cad51c580 | section | Completion / Handover
d4801dc4-6706-4d84-909e-e4c22adc6481 | checkpoint | Product installed correctly, checked & reviewed - as per specification
e21dbac8-9890-4acc-9916-3789cc7068b7 | signoff | Raise Remedial / Request Review
a9ef2c24-d2db-4ec4-b49f-8346223271b2 | checkpoint | Area left clean & tidy
502d46a9-494d-4cd5-a9f5-d77fd8554169 | signoff | Raise Remedial / Request Review
3e44e0de-6c3b-4802-9414-2bcda241fefd | checklist | Warranty Req - Volclay Waterproofing |  | Volclay Waterproofing Warranty Request
5cdd2af4-5658-448a-832a-cb301e12bdf1 | section | Project Info
0f1dfeff-a0cb-4613-bb1b-2b0e8a9a6c4a | checkpoint | Project Info
985899ca-5d13-53f9-9886-5cd63b9b17b6 | textbox | PROJECT ADDRESS:
2bbbc9ed-2a61-591f-adc8-015b11c3c50b | textbox | PROJECT SIZE (sq m):
a4e1c0e4-2f5c-535c-9734-20c6b59d5259 | textbox | PROJECT START DATE:
dfeada96-48ff-5587-89bc-c91cdd339ea8 | textbox | COMPLETION DATE:
8e5106b5-e755-5158-8f11-d343c70785ad | radio | HYDROSTATIC HEAD (select one “x”): | No,Yes
2bfba684-ed36-5952-b21a-3a6d721ce861 | textbox | If yes, how many metres?
40458e8a-4005-55af-abe4-1fd7a1010435 | radio | WARRANTY TYPE (select one “x”): | Product,System
93bb0ca2-6098-40d8-855e-834ef5b8ac11 | section | OWNER/BUILDER INFORMATION
33ac443a-4f28-49c5-95de-7714ec421b0f | checkpoint | OWNER/BUILDER INFORMATION
287ce15c-0d83-53e4-aa5a-1e27d70e9d5e | radio | OWNER/BUILDER INFORMATION (Please indicate which) | Builder,Owner
b14909ae-46f7-543e-aaca-432508e80887 | textbox | NAME:
d4375383-a979-5ae4-9cb8-149141aa6441 | textbox | CONTACT:
aa5ae38b-0fd8-576e-838e-9c6446b7702c | textbox | ADDRESS:
584f2a19-c1b5-56f7-b74c-d77eb9145536 | textbox | PHONE:
1d0213b9-f439-518d-9dbb-aad7f185cf6a | textbox | FAX:
13a629e4-60b9-5575-8155-f438552be6c0 | textbox | EMAIL:
e64a0c21-f4b1-4511-aa67-cce495b428e5 | section | APPLICATOR INFORMATION
4d9aa94c-f3f8-4b27-a422-822b4ffb5ed5 | checkpoint | APPLICATOR INFORMATION
08db5e9c-4191-5c51-bb46-0efb155efbdd | textbox | APPLICATOR:
a50422d6-2eaa-5b6a-9a6b-def65567731a | textbox | CONTACT:
0c3de058-268d-5fd7-846d-c83a730467ed | textbox | ADDRESS:
d0fab130-35c0-5dc6-9d40-e23bbfb3e533 | textbox | PHONE:
1084e6a6-eeb7-503c-ae9a-293f2d26c938 | textbox | FAX:
a4ec1ddc-0e73-5f4a-9433-e2f17a4decaf | textbox | EMAIL:
52288543-a8e7-4f9d-a5d0-b230f669d7e9 | section | LIST QUANTITY OF FOLLOWING PRODUCTS USED:
720e1124-0bc5-4c78-b185-bc42ae9265c6 | checkpoint | LIST QUANTITY OF FOLLOWING PRODUCTS USED:
82e5accc-a7b7-5b0f-96fb-46180e37a166 | note | (Provide sq m, linear metres, litres used) MUST BE COMPLETED
ec373b23-5fb6-42b9-9f54-e1f8dd953276 | checkpoint | STRATASEAL
b3e077b1-a4de-5724-9649-e4261ac19c6e | tickbox | Hot Rubber
e6ce31b5-abdb-4d2c-bbe4-60f3d070b038 | checkpoint | SWELLTITE
de469fa3-8afe-5c5d-a835-ce520a0a13a9 | tickbox | Swelltite
fdc27cf2-983b-4633-a25e-46842e757315 | checkpoint | VOLTEX
71e0e0f7-f8f3-5651-a8cb-ba37f17accb0 | tickbox | Reg
df39d6e2-ce34-5691-b6dd-9401b4e5be97 | tickbox | DS
1ec45f59-2f77-565b-ba38-93246604d70c | tickbox | DS/SWR
cf5916aa-4fea-4dd5-b78e-3b628a0d7e7b | checkpoint | WATERSTOP-RX
2a575ffa-8801-5eef-8674-e8ca91e585a6 | tickbox | RX-101
a01a2d3a-065c-5050-9df0-d07c47df9565 | tickbox | RX-101T
26d975c5-65d2-5780-bfed-993d1a20422a | tickbox | RX-102
444fe6ee-76cb-525c-bc5d-cdc2a3e8f2da | tickbox | Cetseal
406bbc48-1d5c-5173-aa0b-eb32e3dee949 | tickbox | Revofix (Mesh)
0ea228ca-aea0-475b-836e-4196672ca638 | checkpoint | AQUADRAIN
14f3d8f2-c634-5bc3-9a2f-c62fe8bfe22c | tickbox | 15x
47c95381-187d-577d-8db4-092975fcef17 | tickbox | GS310
160228de-9015-412a-a762-401e92a33093 | checkpoint | ULTRASEAL
b8c4ebda-f2ca-5978-8146-4bc03989d827 | tickbox | BT
9bffeefa-91d8-53a0-a831-1e14d1ec1eab | tickbox | SP
dbea5f13-592d-4a79-bbb7-077264ff3cc6 | checkpoint | ACCESSORIES
8c054e5f-4d42-5649-8dd7-e8eb5cc43262 | tickbox | AKWASEAL
4d50a17e-ff21-53e4-8590-a35946b85455 | tickbox | AKWASTOP
d5f4d2c5-9a1b-5709-b430-ddd10b23c441 | tickbox | BENTOGROUT
b825c27b-6a50-5b5b-bed5-e17327be1683 | tickbox | BENTOSEAL
057c3c64-c320-596e-a2db-f456d1531204 | tickbox | CETCOAT
7ed256dc-0f08-50a9-8e90-325cd4e98001 | tickbox | ENVIROSHEET
9b907af9-2c89-54af-8832-5e6f31f6b920 | tickbox | ENVIROSHEET LT
d5a0448f-6984-5ecc-b036-8aa296c9bd9e | tickbox | HYDROBAR TUBES
55ae270b-a041-5f80-a10d-b77e8f869c65 | tickbox | WATERSTOPPAGE
87005300-caa5-4aa5-a32b-d9b097896d81 | checkpoint | “x” PROJECT TYPE:
63f61117-4f35-5265-a113-82d4f5845878 | tickbox | Residential
39d1cd48-8b6b-5b4a-af35-fbdab45589d3 | tickbox | Apartment
816fce82-a7be-5ca1-a385-58b4939f3cb5 | tickbox | Commercial Bldg
200a3e3b-fbc4-5516-947a-9242b2898e2d | tickbox | Roading
28d46e11-02da-5cbb-b362-f5a08de10506 | tickbox | Educational
d127be2d-773d-5589-a390-ae6768d64ab4 | tickbox | Civil
7994f92d-5960-5776-9761-cee6e5829a1e | tickbox | Sports facility
8dc5d33a-4b03-5813-92d4-ca471cd320a6 | tickbox | Hospital
903bb69f-dd00-522f-9fed-caf0d96449cb | tickbox | Hotel
c4b6f640-333b-4151-aff4-caf684e34c42 | checkpoint | “x” CONSTRUCTION APPLICATION(S): (Tick as many as apply) MUST BE COMPLETED
d069b7ba-a061-5b1d-9cae-bc67548607b8 | tickbox | Backfilled Walls
3fbd9271-ad90-5014-a47d-9a4418722367 | tickbox | Precast Panel
a8f6e5fb-013f-5af8-b199-44fcc3399792 | tickbox | Contiguous Pile Shotcrete
fb649d11-df73-5748-99c0-e81c1118829f | tickbox | Insitu Poured Concrete
97516521-0c13-59f6-9f82-29c8a6038da1 | tickbox | Grout Injection
7ab0c7f1-1c9a-530a-8539-cd9ffdeab265 | tickbox | Injection (urethane)
14e59786-9d3e-5bf1-b1ce-e323128f67c5 | tickbox | Footings
779cc54d-03f4-5437-872a-8ed77a82a1d3 | tickbox | Lift pits
be7a9727-e44a-5b1f-b8c6-1d830197bf2f | tickbox | Masonry Block Wall
7e641474-f261-5ea1-80d4-3a9992c08e3d | tickbox | Foundations
3c1cfaa3-5962-57a1-8bfb-f041b366cc42 | tickbox | Plaza Deck
b855ac96-2d25-51e8-9ba8-c76c809560ef | tickbox | Green Roof
6d004166-8ad5-553c-8a78-a703acdeca13 | tickbox | Secant Pile
6d87238f-fbc3-537d-8cf1-4367e05c97a6 | tickbox | Sheet Piling
2918360d-df5d-53a2-b513-133df7db0462 | tickbox | Underslab
8a248273-4c9b-50c2-a227-20c8cfb18e14 | tickbox | Shotcrete Piled Wall
dbdf6a92-fd4c-581d-a36f-0833dcba3711 | tickbox | Split Slab
47342001-3529-500c-a806-7e38d45b1d5b | tickbox | Tunnel
efb9e575-cf26-576a-978b-d66f2f2b0bac | tickbox | Underslab
443b6ff8-e078-5ce5-a999-8a89bf94fecb | textbox | OTHER (Please state)
843fa1b9-6874-5f81-8ce2-78f344bc3860 | note | *** Please remember to attach all relevant Quality Assurance photographs*** *** Please note areas on the request that must be completed***