## Sheet1
1 | AP40 Basecourse Aggregates used for overlay | Crushing Resistance | H | 1 per 10,000 m3 | NZS4407:3.10 | CHAR(LESS) 10% passing 2.36mm sieve at 130kN | IANZ report | Contractor | A | I | R | 1 - AP40 Basecourse Aggregates used for overlay | Detail of Activity / Test - Crushing Resistance | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 10,000 m3 | Inspection / Test method - NZS4407:3.10 | Acceptance Criteria - CHAR(LESS) 10% passing 2.36mm sieve at 130kN | Record documents (QCP - Quality Control Portal) - IANZ report | Responsibility - Contractor | Project Specific Notes / Instructions - | QA / Site Engineer - A | Eng. Rep / NZTA - I | Contractor - R | 1 - AP40 Basecourse Aggregates used for overlay
1.01 | AP40 Basecourse Aggregates used for overlay | Particle Size Distribution | H | 1 per 1,000 m3 | NZS4407:3.8.1 | NZTA M04:2024-Class 2 Class 2 in Table 12 for PSD Table 13 for shape control | IANZ report | Contractor | A | I | R | 1.01 - AP40 Basecourse Aggregates used for overlay | Detail of Activity / Test - Particle Size Distribution | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m3 | Inspection / Test method - NZS4407:3.8.1 | Acceptance Criteria - NZTA M04:2024-Class 2 Class 2 in Table 12 for PSD Table 13 for shape control | Record documents (QCP - Quality Control Portal) - IANZ report | Responsibility - Contractor | Project Specific Notes / Instructions - | QA / Site Engineer - A | Eng. Rep / NZTA - I | Contractor - R | Detail of Activity / Test - Crushing Resistance
2.01 | Mark out earthwork extents | Set out and approve extent of earthworks | M | Prior to earthworks | Visual | Site Engineers Approval | Checksheet | Contractor | A | I | R | 2.01 - Mark out earthwork extents | Detail of Activity / Test - Set out and approve extent of earthworks | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to earthworks | Inspection / Test method - Visual | Acceptance Criteria - Site Engineers Approval | Record documents (QCP - Quality Control Portal) - Checksheet | Responsibility - Contractor | Project Specific Notes / Instructions - | QA / Site Engineer - A | Eng. Rep / NZTA - I | Contractor - R | Action (Hold, Monitor, Witness) - H
2.02 | Earthworks | Cut 150mm rebate at Edge of seal (EOS) and strip organic material from shoulder | M | As per design drawings | Visual / Photo | Site Engineers Approval | Checksheet | Contractor | A | I | R | 2.02 - Earthworks | Detail of Activity / Test - Cut 150mm rebate at Edge of seal (EOS) and strip organic material from shoulder | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - As per design drawings | Inspection / Test method - Visual / Photo | Acceptance Criteria - Site Engineers Approval | Record documents (QCP - Quality Control Portal) - Checksheet | Responsibility - Contractor | Project Specific Notes / Instructions - | QA / Site Engineer - A | Eng. Rep / NZTA - I | Contractor - R | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 10,000 m3
2.03 | M04 AP40 Placement | M04 AP40 Placed in Accordance with Design Drawing and Survey | M | As per design drawings | Visual / Photo | In Accordance with Design Drawing | Checksheet | Contractor | A | I | R | 2.03 - M04 AP40 Placement | Detail of Activity / Test - M04 AP40 Placed in Accordance with Design Drawing and Survey | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - As per design drawings | Inspection / Test method - Visual / Photo | Acceptance Criteria - In Accordance with Design Drawing | Record documents (QCP - Quality Control Portal) - Checksheet | Responsibility - Contractor | Project Specific Notes / Instructions - | QA / Site Engineer - A | Eng. Rep / NZTA - I | Contractor - R | Inspection / Test method - NZS4407:3.10
2.04 | M04 AP40 Compaction | Compact in Layers no greater than 150mm. | H | 1MDD Test per 50m | Nuclear Densometer MDD Test | Average of 95% MDD with individual result >/= 92% | IANZ report | Contractor | A | I | R | 2.04 - M04 AP40 Compaction | Detail of Activity / Test - Compact in Layers no greater than 150mm. | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1MDD Test per 50m | Inspection / Test method - Nuclear Densometer MDD Test | Acceptance Criteria - Average of 95% MDD with individual result >/= 92% | Record documents (QCP - Quality Control Portal) - IANZ report | Responsibility - Contractor | Project Specific Notes / Instructions - | QA / Site Engineer - A | Eng. Rep / NZTA - I | Contractor - R | Acceptance Criteria - CHAR(LESS) 10% passing 2.36mm sieve at 130kN
Record documents (QCP - Quality Control Portal) - IANZ report
Responsibility - Contractor
Project Specific Notes / Instructions -
QA / Site Engineer - A
Eng. Rep / NZTA - I
Contractor - R
1.01 - AP40 Basecourse Aggregates used for overlay
Detail of Activity / Test - Particle Size Distribution
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m3
Inspection / Test method - NZS4407:3.8.1
Acceptance Criteria - NZTA M04:2024-Class 2 Class 2 in Table 12 for PSD Table 13 for shape control
Record documents (QCP - Quality Control Portal) - IANZ report
Responsibility - Contractor
Project Specific Notes / Instructions -
QA / Site Engineer - A
Eng. Rep / NZTA - I
Contractor - R
2.01 - Mark out earthwork extents
Detail of Activity / Test - Set out and approve extent of earthworks
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to earthworks
Inspection / Test method - Visual
Acceptance Criteria - Site Engineers Approval
Record documents (QCP - Quality Control Portal) - Checksheet
Responsibility - Contractor
Project Specific Notes / Instructions -
QA / Site Engineer - A
Eng. Rep / NZTA - I
Contractor - R
2.02 - Earthworks
Detail of Activity / Test - Cut 150mm rebate at Edge of seal (EOS) and strip organic material from shoulder
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - As per design drawings
Inspection / Test method - Visual / Photo
Acceptance Criteria - Site Engineers Approval
Record documents (QCP - Quality Control Portal) - Checksheet
Responsibility - Contractor
Project Specific Notes / Instructions -
QA / Site Engineer - A
Eng. Rep / NZTA - I
Contractor - R
2.03 - M04 AP40 Placement
Detail of Activity / Test - M04 AP40 Placed in Accordance with Design Drawing and Survey
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - As per design drawings
Inspection / Test method - Visual / Photo
Acceptance Criteria - In Accordance with Design Drawing
Record documents (QCP - Quality Control Portal) - Checksheet
Responsibility - Contractor
Project Specific Notes / Instructions -
QA / Site Engineer - A
Eng. Rep / NZTA - I
Contractor - R
2.04 - M04 AP40 Compaction
Detail of Activity / Test - Compact in Layers no greater than 150mm.
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1MDD Test per 50m
Inspection / Test method - Nuclear Densometer MDD Test
Acceptance Criteria - Average of 95% MDD with individual result >/= 92%
Record documents (QCP - Quality Control Portal) - IANZ report
Responsibility - Contractor
Project Specific Notes / Instructions -
QA / Site Engineer - A
Eng. Rep / NZTA - I
Contractor - R