## ITP-01
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # FHC-ITP-032
[11 empty] | Revision : 01 | Date : 07/07/2022
Client: |  | MRPA |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Tarneit South East Carpark |  | CONCRETE BASE AND LEAN MIX CONCRETE SUBBASE |  | Name: | Samuel Johnson | Name: | Patrick Fagan |  | Name: | Shaun Kent
Contract No: |  | 7426000 |  | Specifications: AS 3600-2018, VicRoads Standard Specification Section 503
|  |  |  | Structure / Component: Cabinet Slab |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Tarneit Train Station |  | Date : | 2023-02-16 | Date : | 2023-02-16 |  | Date : | 2023-02-16
Lot No: | 1 |  | Lot Details: | Structural Slab Pour |  |  |  |  | Lot Size/ Quantity: |  | 1
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Design and Submissions
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Approval of mix design |  | Prior to the first concrete pour | Structural Concrete Design & Submission ITP completed and signed | 503.04 | Verify | This ITP signed | IP | Fulton Hogan Engineer | N/A |  | N/A
1.4 | Reinforcement schedule |  | Prior to concrete pour | Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations | 503.09 | Verify | This ITP signed | IP | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction/Erection of Formwork
2.1 | Excavation |  | Prior to concrete pour | Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation | Contract Drawings | Inspect | This ITP signed | IP | Fulton Hogan Engineer | N/A |  | N/A
2.2 | Construction Methodology |  | Prior to erection | Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry | Contract Drawings | Verify | This ITP signed | IP | Fulton Hogan Engineer | N/A |  | N/A
3 | Pre-Pour Planning and Inspection
3.1 | Excavation/Foundation – Blinding, sealing or foundation concrete |  | Prior to concrete pour | Blinding, sealing or foundation concrete shall not be placed until the bottom of the excavation has been reviewed by the Superintendent. Inspected and approved by the Superintendent. Hold Point released by the Superintendent. | Contract Drawings | Verify | This ITP signed | HP | Fulton Hogan / VicRoads |  |  | N/A
3.2 | Formwork levels and position |  | Prior to concrete pour | A pre-pour survey carried out to confirm erected formwork within the tolerance. Any errors in the level or positioning of formwork is to be corrected prior to placing concrete | Contract Drawings | Verify | This ITP signed | SCP HP* | Fulton Hogan Engineer | N/A |  | N/A
3.3 | Location of splices |  | Schedule Review | In lapped splices, the bars shall be placed in contact and the specified cover shall be maintained. | Contract Drawings | Inspect | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
3.4 | Cleaning formwork |  | Each concrete pour | Concrete shall not be placed until all foreign material has been completely removed from the forms | 503.13 | Verify | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
3.5 | Correct forms, reinforcements, rag bolt assembly and embedments |  | Prior to concrete pour | Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications. Pre-pour checklist completed and signed. | 503.07 | Verify | This ITP signed & Pre-Pour checklist completed | HP | Fulton Hogan / VicRoads |  |  | N/A
3.6 | Reinforcement assembly of piles |  | Prior to concrete pour | Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent. | 503.07 | Verify | This ITP signed | HP | Fulton Hogan | N/A |  | N/A
3.7 | Monitoring weather |  | Prior to concrete pour | Concrete shall not be place when temperature is <5°C or > 35°C All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed | 503.07 | Verify | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
3.8 | Assessment of Base Thickness |  | Prior to lot closure | Within the lots defined for assessment of compressive strength the surface levels of the subbase shall be measured as specified in Section 173. Levels of the base surface shall be taken at the same locations as taken on the subbase. | 503.05 | Verify | This ITP signed | TP | Fulton Hogan | N/A |  | N/A
3.9 | Concrete Sampling and Testing |  | Prior to placement | Concrete sampled and tested for slump test. | 503.05 | Verify | This ITP signed | TP | Fulton Hogan | N/A |  | N/A
3.1 | Sampling and Testing of Cylinder Specimens |  | During concrete pour | The Contractor shall record 3 sample, prepare, cure and compression test of 12 cylinders cast on site in accordance with AS 1012. The concrete shall be sampled at the point of discharge to the roadbed. Each sample shall consist of two cylinder specimens for testing at age 28 days. | 503.05 | Verify | This ITP signed | TP | Fulton Hogan | N/A |  | N/A
4 | Placing and Finishing Concrete
4.1 | Carry out sampling of concrete |  | Each concrete pour | Sampling in accordance with 503.05 | 503.05 | Checklist | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
4.2 | Discharge time |  | Each concrete pour | Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise. | 503.05 | Verify | This ITP signed. Accurate Site Notes & Load Mapping | IP | Fulton Hogan | N/A |  | N/A
4.3 | Concrete Placement |  | Each concrete pour | Concrete shall not be placed until the proposed method of placement, spacing of planned transverse construction joints and the provision of dowels, constructed formwork, reinforcement and embedments conforming to the requirements of this specification and the drawings, has been reviewed by the Superintendent. | 503.05 | Verify | This ITP signed. Accurate Site Notes & Load Mapping | HP | Fulton Hogan Engineer | N/A |  | N/A
4.4 | Methodology of Placement |  | Each concrete pour | Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials Concrete shall not be moved horizontally by vibrators In continuous pours the max. time lag between truckloads on site is 25 minutes | 503.07 | Verify | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
4.5 | Compaction |  | During concrete pour | Base and subbase concrete shall be compacted to meet the requirements of clause 503.05. Concrete placed around dowel bars shall be carefully vibrated without the vibrators touching the dowels. | 503.07 | Verify | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
4.6 | Screeding and Finishing |  | Post concrete pour | The concrete shall be finished to provide a dense and homogeneous concrete surface satisfying the requirements of clause 503.03. The subbase concrete shall be finished to a uniform non-textured surface. The base concrete shall be finished to a textured surface as specified. | 503.07 | Verify | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
4.7 | Joint Sealants |  | Post concrete pour | Permanent seals shall be either a neoprene compression seal or an in situ cast silicone sealant. A full technical description of the proposed sealant and method of installation recommended by its manufacturer shall be submitted for approval by the Superintendent at least four weeks prior to installation. | Contract Drawings | Verify | This ITP signed | IP | Fulton Hogan Engineer | N/A |  | N/A
4.8 | Joint Sealants for Base |  | Post concrete pour | Joints shall be constructed as specified and shown on the drawings. Joints shall be straight and vertical. Transverse joints shall be continuous from edge to edge of the pavement. Tie bars shall be installed such that anchorage strength of at least 85% of the yield strength of the bar is developed upon hardening of the base. | 503.13 | Verify | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
4.9 | Texturing of Surface |  | Post concrete pour | Texturing of the concrete surface shall be carried out to the standard of surface specified in clause 503.21 using a hessian drag or steel tines. The textured surface shall extend across the full width of the base and shall be uniform in appearance. The concrete surface shall be finished to achieve an average texture depth between 0.40 mm and 0.70 mm. The texture depth shall generally be achieved using steel tining equipment which shall comprise of rectangular shaped tines of flat spring steel, approximately 0.6 mm thick. The width of the tines shall be 2 mm. | 503.17 | Verify | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
5 | Post-Pour Details and Inspection
5.1 | Curing and Protection |  | Post concrete pour | Curing of the base and subbase concrete shall be undertaken by the use of a curing compound sprayed onto the freshly laid concrete at the application rates specified in this clause. Curing compound shall not be sprayed when bleed water is present. | 503.18 | Verify | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
5.2 | Curing Compounds |  | Post concrete pour | Prior to the use of curing compounds, the Contractor shall submit to the Superintendent for review not less than four weeks prior to placement of concrete | 503.18 | Verify | This ITP signed | HP | Fulton Hogan Engineer | N/A |  | N/A
5.3 | Formwork removal |  | Post concrete pour | Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation | Contract Drawings | Verify | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
5.4 | Concrete Base Course |  | Post concrete pour | With the exception of concrete saws, personnel the concrete base course shall not be trafficked until the in situ compressive strength has reached at least 20 MPa based on concrete cylinder testing. | 503.19 | Verify | This ITP signed | HP | Fulton Hogan Engineer | N/A |  | N/A
5.5 | Positional tolerance and dimensions of concrete members and piles |  | Each concrete pour | Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40) | AS3600 Cl 17.5 | Verify | This ITP signed Post Pour Checklist completed | IP | Fulton Hogan | N/A |  | N/A
5.6 | Concrete Sampling and Testing |  | Prior to lot closure | Concrete sampled and tested for compressive strength. The required strength of concrete must be in accordance with the drawings | 503.05 | Verify | This ITP signed | TP | Fulton Hogan | N/A |  | N/A
5.7 | Curing and Protection |  | Post concrete pour | Saw cutting and joint sealing shall be allowed on the finished base concrete until the in situ strength of the concrete is at least 60% of the target 28 day compressive strength. | 503.18 | Verify | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
5.8 | As Built Drawings |  | Prior to lot closure | Recorded of as-built drawings | Fulton Hogan Procedure | Verify | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent