## Sheet1
Onslow College
Phase 3 Block M & L
Stage 1
Upper Roof
Delap photos
Clean roof
Remove existing cap flashings
Install screws to substrate
Install Trough Infill PIR
New Vapour Barrier
New 80mm PIR
Taper PIR closest to spouting
New Aluminium Drip Edge
New Fibretite Membrane
Penetration through roof
New Fascias
Install Pressure Bars
New Gutters and Down Pipes
Awning Roof
Remove Existing Clearlite
Install new Fibreglass Roofing
Install closed cell profiled foam strip
Install Apron Flashing
New Gutters and Down Pipes
Stage 2
Upper Roof
Delap photos
Clean roof
Remove existing cap flashings
Install screws to substrate
Install Trough Infill PIR
New Vapour Barrier
New 80mm PIR
Taper PIR closest to spouting
New Aluminium Drip Edge
New Fibretite Membrane
Penetration through roof
New Fascias
Install Pressure Bars
New Gutters and Down Pipes
Awning Roof
Remove Existing Clearlite
Install new Fibreglass Roofing
Install closed cell profiled foam strip
Install Apron Flashing
New Gutters and Down Pipes