## res_ITP-CIV Delineation Fence R
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-STR-Soil Nails | itp |  |  |  | Yes | ITP-STR-Soil Nails Rev 1 | 613f7709-8c75-4936-9f45-67bd76112139
section | Referenced Documentation
checkpoint | Referenced Documentation
note | ITP Description: Soil Nails
note | Discipline (e.g. CIV/STR/RAIL): STR
note | Revision Number: 1
note | Revision Date: 3/08/2021
note | ITP created by: Mike Freeman
note | ITP approved for use by: Mike Freeman
note | 1.1 Non Dependent
label | REFERENCE: VicRoads Section 610 June 2019
note | 1.1 Non Dependent
label | REFERENCE: VicRoads Section 611 November 2018
note | 1.1 Non Dependent
label | REFERENCE: VicRoads Section 683 April 2019
section | 2 - Preliminaries
checkpoint | 2.1 Design
note | REFERENCE: 683.04
note | 683.04 (d) (i - xi)
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: The Contractor shall submit construction drawings for review by the Superintendent prior to soil nail installation.
note | See: MRP-DPK-072-00-CSW-0021 (Robinsons Road)
textbox | ---------------------------------
note | METHOD: Document Review
textbox | ---------------------------------
note | FREQUENCY: Once, 4 weeks prior to installation of soil nails
textbox | ---------------------------------
note | CATEGORY: HP
textbox | ---------------------------------
note | RESPONSIBILITY: Nominated Authority
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: ConQA Hold Point Release (note this hold point is already released)
textbox | Date Completed:
checkpoint | 2.2 Nail Certification - Steel
note | REFERENCE: 683.06 (a)
note | 683.07 (b)
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: Current ACRS certification for Grade 500N materials including couplers (where applicable).
textbox | Enter: Teambinder Material Approval number
textbox | ---------------------------------
note | METHOD: Document Review
textbox | ---------------------------------
note | FREQUENCY: Where applicable, once for each supplier, prior to installation of soil nails
textbox | ---------------------------------
note | CATEGORY: WP
textbox | ---------------------------------
note | RESPONSIBILITY: Nominated Authority
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 2.3 Nail Certification - Carbon or Fibre Reinforced Polymer (FRP)
note | REFERENCE: 683.06 (b)
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: Carbon or FRP nails shall not be installed until the material certificates for all batches of nails have been reviewed and approval granted by the Superintendent.
textbox | Enter: Teambinder Material Approval number
textbox | Enter: Teambinder Approval Number
textbox | ---------------------------------
note | METHOD: Document Review
textbox | ---------------------------------
note | FREQUENCY: Where applicable, once for each supplier, prior to installation of soil nails
textbox | ---------------------------------
note | CATEGORY: HP
textbox | ---------------------------------
note | RESPONSIBILITY: Nominated Authority
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.4 Corrosion Protection (for All Steel Componentry)
note | REFERENCE: 683.07 (b)
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: Coatings for corrosion protection on all steel materials shall be either:
note | i. Galvanised to thickness as per AS/NZS 4680
note | ii. Thermo-diffusion coated to Coating Class 80 or ≥80µm
note | iii. ≥80% zinc-rich product with ≥100µm DFT
note | Attach: Coating Certificate of Compliance
note | Or alternatively, include in the nail certification in the Teambinder Material Approval.
textbox | Enter: Teambinder Material Approval Number
textbox | ---------------------------------
note | METHOD: Document Review
textbox | ---------------------------------
note | FREQUENCY: Once for each batch of materials, prior to installation of soil nails
textbox | ---------------------------------
note | CATEGORY: WP
textbox | ---------------------------------
note | RESPONSIBILITY: Nominated Authority
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 2.5 Grout Mix Design
note | REFERENCE: 683.11 (a) (i - iii)
note | IFC Drawings
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: The proposed low shrinkage grout mix design with supporting test results to be submitted for review to the Nominated Authority.
note | The following test results and information shall be provided:
note | i. Water cement ratio between 0.38 - 0.45
note | ii. The chemical admixture
note | iii. 7 day compressive strength test results ≥32MPa
note | iv. 28 day compressive strength results ≥40MPa (Robinson's Road)
note | v. Flow cone test result between 10-30 seconds
note | vi. Bleed test result ≤2% 3 hours after mixing, ≤4% at any time and separated water absorbed within 24 hours
note | vii. Chloride-ion content ≤0.07%
note | viii. Sulphate content ≤5%
note | The grout shall be made strictly in accordance with the approved grout mix design and in the event of changes, re-submitted for review and approval to the Nominated Authority.
textbox | Enter: Teambinder Approval number
textbox | ---------------------------------
note | METHOD: Document Review
note | FREQUENCY: 2 weeks prior to installation of design verification testing
textbox | ---------------------------------
note | CATEGORY: WP
textbox | ---------------------------------
note | RESPONSIBILITY: Nominated Authority
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
checkpoint | 2.6 Soil Nail Installation, Grouting & Testing Work Procedure
note | REFERENCE: 683.12 (b)
note | 683.11 (b)
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: Soil nail installation WP, fully detailing the proposed drilling, grouting & testing equipment, methodologies and reporting, to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
textbox | ---------------------------------
note | METHOD: Document Review
note | FREQUENCY: 2 weeks prior to installation of design verification testing
textbox | ---------------------------------
note | CATEGORY: HP
textbox | ---------------------------------
note | RESPONSIBILITY: Nominated Authority
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.7 Soil Nail Testing - Type I / Design Verification
note | REFERENCE: IFC Drawings
note | 683.12 (a, c - d)
note | 683.13 (a - b)
note | Table 683.161
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: 3 no. soil nails per soil/rock type encountered on site, are to be installed as per the design, approved methodologies, materials and equipment in locations selected by the Geotechnical Engineer's representative.
note | Load testing is to be in accordance with the loads shown on the IFC Drawings and the load cycles shown on table 683.161.
note | Testing shall be carried out in the presence of the Nominated Authority and reports issued with valid calibration certificates within 24 hours from completion of the test.
textbox | Enter: Teambinder Approval number
textbox | ---------------------------------
note | METHOD: Document Review
textbox | ---------------------------------
note | FREQUENCY: Once, 3 no. tests per soil/rock type
textbox | ---------------------------------
note | CATEGORY: WP
textbox | ---------------------------------
note | RESPONSIBILITY: Nominated Authority
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 2.8 Testing - Type I / Design Verification Test Failure
note | REFERENCE: IFC Drawings
note | 683.13 (b)
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: Where applicable, if any Type I / Designer Verification Test results fail, Type II / Sacrificial Testing & Exhumation Testing shall not proceed.
note | Where this occurs, the Designers must be notified immediately and design assumptions modified and re-issued to the Superintendent's satisfaction.
textbox | Enter: Teambinder Approval number
textbox | ---------------------------------
note | METHOD: Document Review
textbox | ---------------------------------
note | FREQUENCY: Where applicable, per failed test result per soil/rock type
textbox | ---------------------------------
note | CATEGORY: HP
textbox | ---------------------------------
note | RESPONSIBILITY: Nominated Authority
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.9 Testing - Type II / Sacrificial Testing & Exhumation
note | REFERENCE: IFC Drawings
note | 683.12 (a, c - d)
note | 683.14 (a - c)
note | Table 683.161
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: 3 no. soil nails per soil/rock type encountered on site, are to be installed as per the design, approved methodologies, materials and equipment in locations selected by the Geotechnical Engineer's representative.
note | Load testing is to be in accordance with the loads shown on the IFC Drawings and the load cycles shown on table 683.161.
note | Testing shall be carried out in the presence of the Nominated Authority and reports issued with valid calibration certificates within 24 hours from completion of the test.
note | Exhumation of the sacrificial nails shall be conducted in a manner to avoid damaging the grout column and cut into 500mm lengths with ends photographed to prove grout cover of the nail.
note | Note: Dispensation from Type II testing in rock can be requested if:
note | i. All Type I test results pass in that material
note | ii. The material is not weathered more than slightly weathered and/or less hard than a Rock Quality Designator (RQD) of 50
note | iii. Encapsulation sheaths are used for steel nails
textbox | Enter: Teambinder Approval number
textbox | ---------------------------------
note | METHOD: Document Review
textbox | ---------------------------------
note | FREQUENCY: Once, 3 no. tests per soil/rock type
textbox | ---------------------------------
note | CATEGORY: WP
textbox | ---------------------------------
note | RESPONSIBILITY: Nominated Authority
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 2.10 Acceptance of Test Results
note | REFERENCE: 683.10
note | 683.15
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: Installation of production nails shall not commence until the Type I & Type II test results have passed the design requirements (inclusive of any re-design assumptions).
textbox | Enter: Teambinder Approval number
textbox | ---------------------------------
note | METHOD: Document Review
textbox | ---------------------------------
note | FREQUENCY: Once, 7 days prior to commencing production nails
textbox | ---------------------------------
note | CATEGORY: HP
textbox | ---------------------------------
note | RESPONSIBILITY: Nominated Authority
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
signoff | NOMINATED AUTHORITY HOLDPOINT
section | 3 - Pre-construction Activities
checkpoint | 3.1 IFC Drawings
note | REFERENCE: MRPA Quality Management Plan
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
textbox | ---------------------------------
note | METHOD: Document Review
textbox | ---------------------------------
note | FREQUENCY: Prior to starting Works and at regular intervals
textbox | ---------------------------------
note | CATEGORY: HP*
textbox | ---------------------------------
note | RESPONSIBILITY: All
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | 4 - Construction Activities
checkpoint | 4.1 Excavation - Change of Soil/Rock Profile from Design
note | REFERENCE: IFC Drawings
note | 683.05
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: Excavate in layers shown on the drawings.
note | Where applicable, if the Geotechnical Engineer's representative determines from an on-site inspection that the soil/rock profile does not match the design assumptions, no nails shall be installed until the design is verified or amended to the satisfaction of the Superintendent.
textbox | Enter: Teambinder Approval Number
textbox | ---------------------------------
note | METHOD: Visual , Document Review
textbox | ---------------------------------
note | FREQUENCY: Where applicable
textbox | ---------------------------------
note | CATEGORY: HP
textbox | ---------------------------------
note | RESPONSIBILITY: Nominated Authority
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 4.2 Drilling
note | REFERENCE: IFC Drawings
note | Soil Nail Work Procedure
note | 683.08
note | 683.10 (b)
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: Drill holes shall be the depths, diameters and angles shown on the IFC drawings using the equipment stated in the Work Procedure.
note | Where casings are used or sheathing is omitted, the hole diameter shall ensure that the cover to the nail is 40mm min.
note | Drilling records shall be kept including any observations or difficulties encountered.
note | Only air flushing is permitted, no drilling fluid or water shall be used.
note | Placement tolerances to comply with the following:
note | i. Horizontally = ±50mm
note | ii. Vertically = ±50mm
note | iii. Alignment = 1:20
note | iv. Straightness = 20mm in 3m
note | v. Inclination = +0° to -3°
note | Attach: Drilling Records
textbox | ---------------------------------
note | METHOD: Measure , Visual
textbox | ---------------------------------
note | FREQUENCY: Each drill hole
textbox | ---------------------------------
note | CATEGORY: IP
textbox | ---------------------------------
note | RESPONSIBILITY: Foreman , SE/PE/SPE , Surveyor
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.3 Hole Inspection
note | REFERENCE: 683.10 (c)
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: All drill holes shall be inspected following air flushing and prior to insertion of the nails.
note | Drill records shall be made available for review.
textbox | ---------------------------------
note | METHOD: Measure , Visual , Document Review
textbox | ---------------------------------
note | FREQUENCY: Each drill hole
textbox | ---------------------------------
note | CATEGORY: HP
textbox | ---------------------------------
note | RESPONSIBILITY: Nominated Authority
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 4.4 Nail System Installation
note | REFERENCE: IFC Drawings
note | 683.07 (c - f)
note | 683.09
note | 683.10 (c)
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: Each nail shall be made from the correct material, be the diameter and length as shown on the IFC drawings and be free from defects or damage.
note | Centralisers shall be spaced at 1.0m max., ensuring that 40mm min. cover is maintained all around.
note | Steel nails shall be encapsulated by a corrugated sheath unless previously approved during the Type I & II testing.
note | Steel nails shall be isolated 300mm min. where they are to be in contact with the shotcrete facing using tapes or other approved methods.
note | Grout tube shall be positioned at the base of the hole to displace any moisture present in the hole and to prevent entrapping air.
note | The resulting set up shall achieve the minimum bonding length, projection and be able to resist the forces expected during the grouting operations.
textbox | ---------------------------------
note | METHOD: Measure , Visual
textbox | ---------------------------------
note | FREQUENCY: Each drill hole
textbox | ---------------------------------
note | CATEGORY: IP
textbox | ---------------------------------
note | RESPONSIBILITY: Foreman , SE/PE/SPE , Surveyor
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.5 Grout Mixing
note | REFERENCE: Soil Nail Installation Work Procedure
note | 683.11 (b - c)
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: Grouting shall not take place when the air temperature is below 5°C and above 35°C.
note | Mixing shall continue for at least 2 minutes and until a uniform consistency is observed using the same equipment nominated in the Soil Nail Installation Work Procedure.
note | Grout shall be discharged/pumped within 90 minutes from the addition of cement.
note | Record: Required information on the Grout Pour Record
textbox | ---------------------------------
note | METHOD: Visual , Measure
textbox | ---------------------------------
note | FREQUENCY: Each batch
textbox | ---------------------------------
note | CATEGORY: IP
textbox | ---------------------------------
note | RESPONSIBILITY: Foreman , SE/PE/SPE
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.6 Grout Testing
note | REFERENCE: IFC Drawings
note | Soil Nail Installation Work Procedure
note | 683.11 (a) (iii)
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: Each test shall consist of:
note | i. 3 no. compressive strength cubes = 2 no. 7 day strength, 1 no. 28 day strength.
note | ii. 1 no. flow cone test = result between 10-30 seconds
note | vi. 1 no. bleed test = result ≤2% 3 hours after and shall not exceed 4% at any time with all separated water gone after 24 hours
note | Record: Required information on the Grout Pour Record.
textbox | ---------------------------------
note | METHOD: Visual , Measure
textbox | ---------------------------------
note | FREQUENCY: Each 5m³ or part thereof batched per lot
textbox | ---------------------------------
note | CATEGORY: IP
textbox | ---------------------------------
note | RESPONSIBILITY: Foreman , SE/PE/SPE
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.7 Grout Pumping
note | REFERENCE: Soil Nail Installation Work Procedure
note | 683.08
note | 683.11 (b - c)
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: Grout shall be pumped in a continuous operation and monitored with flow and pressure gauges so that the flow rate is between 0.3m to 0.6m per second. Where temporary casings are used, these shall be extracted progressively once 0.5m of the hole has been filled.
note | The volume of the grout used per hole is to be recorded and checked against the theoretical volume.
note | If grout seepage has occurred, the grout shall be topped up to the required level.
note | Where applicable, if the actual volume is 10 times higher than the theoretical volume, pumping operations shall cease at the completion of that hole and be reported to the Superintendent - no further grout shall be pumped until the conditions are reviewed and approval to proceed has been provided.
note | Record: Required information on the Grout Pour Record
textbox | ---------------------------------
note | METHOD: Visual , Measure
textbox | ---------------------------------
note | FREQUENCY: Each batch
textbox | ---------------------------------
note | CATEGORY: IP
textbox | ---------------------------------
note | RESPONSIBILITY: Foreman , SE/PE/SPE
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | 5 - Post-construction Activities
checkpoint | 5.1 Grout Compressive Strength Results
note | REFERENCE: IFC Drawings
note | Soil Nail Installation Work Procedure
note | 683.11 (a) (iii)
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: 7 day compressive strengths to achieve 32MPa min.
note | 28 day compressive strengths to achieve 40MPa min. (Robinsons Road)
note | Attach: Compressive Strength Test Results
textbox | ---------------------------------
note | METHOD: Document Review
textbox | ---------------------------------
note | FREQUENCY: Each cube
textbox | ---------------------------------
note | CATEGORY: IP
textbox | ---------------------------------
note | RESPONSIBILITY: SE/PE/SPE
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.2 As-built Survey
note | REFERENCE: IFC Drawings
note | 683.10 (b)
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate nails comply with the following placement tolerances:
note | i. Horizontally = ±50mm
note | ii. Vertically = ±50mm
note | Attach: Survey As-builts / Survey Report
textbox | ---------------------------------
note | METHOD: Measure , Document Review
textbox | ---------------------------------
note | FREQUENCY: Each nail
textbox | ---------------------------------
note | CATEGORY: IP
textbox | ---------------------------------
note | RESPONSIBILITY: Surveyor , SE/PE/SPE
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.3 Testing - Type III / Production Testing
note | REFERENCE: IFC Drawings
note | 683.12 (a, c - d)
note | 683.15 (a - c)
note | Table 683.162
note | Table 683.163
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: 3 no. soil nails per soil/rock type encountered on site, are to be installed as per the design, approved methodologies, materials and equipment in locations selected by the Geotechnical Engineer's representative.
note | Load testing is to be in accordance with the loads shown on the IFC Drawings and the load cycles shown on table 683.162.
note | Testing shall be carried out in the presence of the Nominated Authority and reports issued with valid calibration certificates within 24 hours from completion of the test.
textbox | Enter: Teambinder Approval number
textbox | ---------------------------------
note | METHOD: Document Review
textbox | ---------------------------------
note | FREQUENCY: The greatest value from, 5% of all nails, 2 no. soil nails, 2 no. soil nails per type of soil, 2 no. nails per installation method
textbox | ---------------------------------
note | CATEGORY: WP
textbox | ---------------------------------
note | RESPONSIBILITY: Nominated Authority
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.4 Testing - Type III / Production Test Failure
note | REFERENCE: IFC Drawings
note | 683.15 (c)
note | 683.16 (b) (i - iii)
note | Table 683.163
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: Where applicable, if any Type III / Production Test results fail, the Designers must be notified immediately and design assumptions modified and re-issued to the Superintendent's satisfaction.
note | An additional 2 no. nails are to be installed using updated installation procedures, either side of the failed nail and shall pass the load test - note that the loads may require updating.
textbox | Enter: Teambinder Approval number
textbox | ---------------------------------
note | METHOD: Document Review
textbox | ---------------------------------
note | FREQUENCY: Where applicable, per failed test result per soil/rock type
textbox | ---------------------------------
note | CATEGORY: HP
textbox | ---------------------------------
note | RESPONSIBILITY: Nominated Authority
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.5 Non-conformance Report (NCR) Closure
note | REFERENCE: MRPA Quality Management Plan
textbox | ---------------------------------
note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
textbox | ---------------------------------
note | METHOD: Document Review
textbox | ---------------------------------
note | FREQUENCY: Once, prior to closure of this lot / element / Work area
textbox | ---------------------------------
note | CATEGORY: HP*
textbox | ---------------------------------
note | RESPONSIBILITY: SE/PE/SPE
textbox | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | Metropolitan Roads Program Alliance Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP